4444 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618 | A | 131242-WSD11-DR-S-5305_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5305_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4445 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618 | A | 131242-WSD11-DR-S-5306_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5306_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4446 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618 | A | 131242-WSD11-DR-S-5307_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5307_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4447 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618 | A | 131242-WSD11-DR-S-5308_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5308_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4448 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618 | A | 131242-WSD11-DR-S-5309_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5309_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4449 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618 | A | 131242-WSD11-DR-S-5310_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5310_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4450 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8001_ST618 | A | 131242-WSD11-DR-S-8001_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-8001_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4451 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618 | A | 131242-WSD11-DR-S-0302_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-0302_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4452 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618 | A | 131242-WSD11-DR-S-1300_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1300_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4453 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618 | A | 131242-WSD11-DR-S-1301_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1301_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4454 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618 | A | 131242-WSD11-DR-S-1302_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1302_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4455 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618 | A | 131242-WSD11-DR-S-1303_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1303_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4456 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618 | A | 131242-WSD11-DR-S-1304_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1304_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4457 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618 | A | 131242-WSD11-DR-S-1305_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1305_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4458 | 000801 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0048 | 0 | 131242-WSW41-LT-PM-0048-0 | 2024-11-06 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024) | Rev (0): Received for information. Please refer to S.O. correspondence no. 333 dated 17 April 2025. | 2024-12-04 | 2025-11-20 | For Information |  | YES | NA |  | 131242-WSW41-LT-0048 | NA | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements (C4B – 006_AUG_2024)" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365) | 2024-11-26 | 379 | INF | 2024-11-06 | 0 | 000801 | 2024-11-06 | 00 | 1 | For Information | INF | 2025-12-10 | Overdue | 0 | INF | INF
4459 | 000802 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 0 | 131242-WSW41-VI-M-0008-0 | 2024-11-06 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-04 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-VI-0008 | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-20 | 29 | AWC | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4460 | 000802 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 1 | 131242-WSW41-VI-M-0008-1 | 2025-01-26 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WSW41-VI-0008 | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 91 | AWC | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4461 | 000802 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0008 | 2 | 131242-WSW41-VI-M-0008-2 | 2025-06-16 | Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion) | Rev 2: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-11-24 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0008 | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-30 | 161 | AWC | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
4462 | 000803 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0049 | 0 | 131242-WSW41-CD-IM-0049-0 | 2024-11-08 | Submission of BIM Coordination VCM Model (Oct 2024) | For Information | 2024-12-06 | 2024-11-24 | For Information |  | YES | NA |  | 131242-WSW41-CD-0049 | NA | "Submission of BIM Coordination VCM Model (Oct 2024)" | 2024-11-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-28 | 16 | INF | 2024-11-08 | 0 | 000803 | 2024-11-08 | 00 | 1 | For Information | INF | 2024-12-12 | Overdue | 0 | INF | INF
4463 | 000804 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0018 | 0 | 131242-WSW41-RT-PM-0018-0 | 2024-11-09 | C4B Monthly Progress Report Number No.18 (10 24) | Rev. 0 - Approved with comments (need to re-submit / see attached comments sheet) | 2024-12-06 | 2024-12-03 | Approved with Comments | 2024-12-23 | NO | Overdue |  | 131242-WSW41-RT-0018 | NA | "C4B Monthly Progress Report Number No.18 (10 24) " | 2024-11-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-29 | 24 | AWC | 2024-11-09 | 0 | 000804 | 2024-11-09 | 00 | 1 | Approved with Comments | AWC | 2024-12-23 | Overdue | 0 | AWC | AWC
4464 | 000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0004 | 0 | 131242-WST02-CL-S-0004-0 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 | Approved with Comments | 2024-12-23 | NO | Overdue |  | 131242-WST02-CL-0004 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-25 | 22 | AWC | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2024-12-23 | Overdue | 0 | AWC | AWC
4465 | 000805 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0005 | 0 | 131242-WST02-CL-S-0005-0 | 2024-11-11 | Anchor bolt Details for pipe supports for post drill and Cast-in type | Rev.0: Approved with comments. Refer to comment sheet. | 2024-12-09 | 2024-12-03 | Approved with Comments | 2024-12-23 | NO | Overdue |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-25 | 22 | AWC | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
4466 | 000806 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 0 | 131242-WSW41-VI-M-0030-0 | 2024-11-11 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-09 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted | In progress. as SO comment s/n.4, provide Vendor product presentation slides to SO on 14 Feb, will resubmit | 131242-WSW41-VI-0030 | NA | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | 2024-11-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-01 | 24 | AWC | 2025-03-20 | 1 | 000806 | 2024-11-11, 2025-03-20 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4467 | 000806 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0030 | 1 | 131242-WSW41-VI-M-0030-1 | 2025-03-20 | Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-11-24 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0030 | NA | "Preliminary Design and Vendor Approval – Manual Lifting Equipment (Portable A-Frame and T-Davit Crane) - (Growa/Woo Sing)" | 2024-11-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-03 | 249 | AWC | 2025-03-20 | 1 | 000806 | 2024-11-11, 2025-03-20 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
4468 | 000807 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 0 | 131242-WSW41-DS-E-1388-0 | 2024-11-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-21 | Approved with Comments | 2024-12-11 | YES | Resubmitted |  | 131242-WSW41-DS-1388 | NA | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | 2024-11-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-02 | 9 | AWC | 2025-03-12 | 1 | 000807 | 2024-11-12, 2025-03-12 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
4469 | 000807 | 01 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1388 | 1 | 131242-WSW41-DS-E-1388-1 | 2025-03-12 | Sample board submission for SS consumables (Bolt, Nut, Washer and Screws) | Rev 1: Approved. | 2025-04-01 | 2025-05-05 | Approved |  | YES | NA |  | 131242-WSW41-DS-1388 | NA | "Sample board submission for SS consumables (Bolt, Nut, Washer and Screws)" | 2024-11-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 54 | APP | 2025-03-12 | 1 | 000807 | 2024-11-12, 2025-03-12 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
4470 | 000808 | 00 | Radha | QAQC | NA | 131242 | WSW41 | DS | E | 1387 | 0 | 131242-WSW41-DS-E-1387-0 | 2024-11-12 | Sample board submission for SS Cable ladder, trays & accessories (United U-Li) | Rev 0: Approved with comments. To revise and resubmit. | 2024-12-10 | 2024-11-25 | Approved with Comments | 2024-12-13 | NO | Overdue |  | 131242-WSW41-DS-1387 | NA | "Sample board submission for SS Cable ladder, trays & accessories (United U-Li)" | 2024-11-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-02 | 13 | AWC | 2024-11-12 | 0 | 000808 | 2024-11-12 | 00 | 1 | Approved with Comments | AWC | 2024-12-13 | Overdue | 0 | AWC | AWC
4471 | 000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1000 | A | 131242-WST02-DR-A-1000-A | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | INF | INF
4472 | 000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001-A | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | INF | INF
4473 | 000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2000 | A | 131242-WST02-DR-A-2000-A | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | INF | INF
4474 | 000809 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 3000 | B | 131242-WST02-DR-A-3000-B | 2024-11-13 | SSN Overall Area Layout And Sections | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | INF | INF
4475 | 000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1003 | A | 131242-WST02-DR-A-1003-A | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | INF | INF
4476 | 000810 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2002 | A | 131242-WST02-DR-A-2002-A | 2024-11-13 | SSN_Shelter 001 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | INF | INF
4477 | 000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1004 | A | 131242-WST02-DR-A-1004-A | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | INF | INF
4478 | 000811 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2003 | A | 131242-WST02-DR-A-2003-A | 2024-11-13 | SSN_Shelter 002 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 25 | INF | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | INF | INF
4479 | 000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 1009 | A | 131242-WST02-DR-A-1009-A | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | For Information |  | YES | NA |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-03 | 25 | INF | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | INF | INF
4480 | 000812 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | A | 2007 | A | 131242-WST02-DR-A-2007-A | 2024-11-13 | SSN_Shelter 003 Layout and Elevation | For Information | 2024-12-11 | 2024-12-08 | For Information | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-2007 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 25 | INF | 2026-02-03 | A.2 | 000812&&001194&&001924 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02 | 6 | Not Approved | NAP |  |  | 0 | INF | INF
4481 | 000813 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 0 | 131242-WSW41-QA-M-0023-0 | 2024-11-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-QA-0023 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-04 | 21 | AWC | 2025-10-23 | 1 | 000813&&001024 | 2024-11-14, 2025-02-07, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4482 | 000813 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0023 | 1 | 131242-WSW41-QA-M-0023-1 | 2025-10-23 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-12 | 2025-12-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0023 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 61 | AWC | 2025-10-23 | 1 | 000813&&001024 | 2024-11-14, 2025-02-07, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC | 2026-01-12 | Overdue | 0 | AWC | AWC
4483 | 000814 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0019 | 0 | 131242-WSW41-QA-C-0019-0 | 2024-11-14 | Monthly Concrete Cube Records for Structural works for August 2024 | For Information | 2024-12-12 | 2024-12-07 | For Information |  | YES | NA |  | 131242-WSW41-QA-0019 | NA | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" && "Monthly Concrete Cube Records for Structural works for August 2024" && "T&C Check List " && "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-28 | 23 | INF | 2025-09-30 | 0 | 000738&&000814&&001343&&001712 | 2024-09-28, 2024-11-14, 2025-06-04, 2025-09-30 | 00 | 4 | Approved with Comments | AWC |  |  | 0 | INF | INF
4484 | 000815 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0004 | 0 | 131242-WSW41-MS-M-0004-0 | 2024-11-15 | MSRA and SWP for Installation of Manway | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-05 | Approved with Comments |  | YES | NA |  | 131242-WSW41-MS-0004 | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-29 | 20 | AWC | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4485 | 000816 | 00 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0005 | 0 | 131242-WSW41-VI-I-0005-0 | 2024-11-16 | Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech) | Rev 0: Rejected. Based on CES request. | 2024-12-13 | 2024-12-05 | Rejected | 2024-12-26 | YES | Resubmitted | Email sent on 25 Nov 24 | 131242-WSW41-VI-0005 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-30 | 19 | REJ | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | Approved | APP |  |  | 0 | REJ | REJ
4486 | 000817 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0024 | 0 | 131242-WSW41-VI-E-0024-0 | 2024-11-16 | Preliminary Design and Vendor Approval – HDMANN Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-13 | 2024-12-06 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSW41-VI-0024 | NA | "Preliminary Design and Vendor Approval – HDMANN Unistrut Support" | 2024-11-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 20 | AWC | 2024-11-16 | 0 | 000817 | 2024-11-16 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4487 | 000818 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0003 | 0 | 131242-WSW41-MS-M-0003-0 | 2024-11-16 | MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-12-13 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-MS-0003 | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-30 | 20 | AWC | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4488 | 000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001 | A | 131242-WSD11-DR-A-1001-A | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-02 | 59 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | INF | INF
4489 | 000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A | 131242-WSD11-DR-A-1002-A | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-02 | 59 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | INF | INF
4490 | 000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A | 131242-WSD11-DR-A-1003-A | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-02 | 59 | INF | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | INF | INF
4491 | 000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A | 131242-WSD11-DR-A-2000-A | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSD11-DR-2000 | NA | "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" | 2024-11-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-08 | 59 | INF | 2026-01-05 | A | 000819&&001893&&001931 | 2024-11-18, 2025-12-14, 2026-01-05 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
4492 | 000819 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A | 131242-WSD11-DR-A-3000-A | 2024-11-18 | THP Layout, Elevations and Section Details | For Information. Please refer to comment sheet. | 2024-12-16 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-02 | 59 | INF | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | INF | INF
4493 | 000820 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5000 | A | 131242-WSD11-DR-A-5000-A | 2024-11-18 | THP Door and Finishes Schedules | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-18 | Not Approved | 2025-01-08 | NO | Overdue |  | 131242-WSD11-DR-5000 | NA | "Dry Riser Installation Details" && "THP Door and Finishes Schedules" | 2024-11-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-08 | 30 | NAP | 2025-12-16 | A | 000820&&001902 | 2024-11-18, 2025-12-16 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
4494 | 000821 | 00 | Anna | CSA | NA | 131242 | WSD11 | DR | A | 5006 | A | 131242-WSD11-DR-A-5006-A | 2024-11-18 | THP Corridor & Stair Compartment Waterproofing Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-16 | 2024-12-21 | Not Approved | 2025-01-10 | NO | Overdue |  | 131242-WSD11-DR-5006 | NA | "THP Corridor & Stair Compartment Waterproofing Details" | 2024-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-08 | 33 | NAP | 2024-11-18 | A | 000821 | 2024-11-18 | 00 | 1 | Not Approved | NAP | 2025-01-09 | Overdue | 0 | NAP | NAP
4495 | 000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5001 | A | 131242-WSD11-DR-A-5001-A | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5001 | NA | "THP Handrail Layout and Cad Ladder Details" && "Typical Fire Alarm Installation Detail (THP)" | 2024-11-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-08 | 19 | AWC | 2025-12-16 | A | 000822&&001901 | 2024-11-18, 2025-12-16 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
4496 | 000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5002 | A | 131242-WSD11-DR-A-5002-A | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5002 | NA | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-08 | 19 | AWC | 2024-11-18 | A | 000822 | 2024-11-18 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4497 | 000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5003 | A | 131242-WSD11-DR-A-5003-A | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5003 | NA | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-08 | 19 | AWC | 2024-11-18 | A | 000822 | 2024-11-18 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4498 | 000822 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 5004 | A | 131242-WSD11-DR-A-5004-A | 2024-11-18 | THP Handrail Layout and Cad Ladder Details | Rev.0: Approved with comments Revise and resubmit. | 2024-12-16 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5004 | NA | "THP Handrail Layout and Cad Ladder Details" | 2024-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-08 | 19 | AWC | 2024-11-18 | A | 000822 | 2024-11-18 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4499 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609 | D | 131242-WST00-DR-S-8004_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST00-DR-8004_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4500 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0300_ST609 | D | 131242-WST02-DR-S-0300_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0300_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4501 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0301_ST609 | D | 131242-WST02-DR-S-0301_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0301_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4502 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0303_ST609 | D | 131242-WST02-DR-S-0303_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0303_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4503 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0304_ST609 | D | 131242-WST02-DR-S-0304_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0304_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4504 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0305_ST609 | D | 131242-WST02-DR-S-0305_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0305_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4505 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0306_ST609 | D | 131242-WST02-DR-S-0306_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0306_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4506 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0307_ST609 | D | 131242-WST02-DR-S-0307_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0307_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4507 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0308_ST609 | D | 131242-WST02-DR-S-0308_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0308_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4508 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0309_ST609 | D | 131242-WST02-DR-S-0309_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0309_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4509 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1100_ST609 | D | 131242-WST02-DR-S-1100_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1100_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4510 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1101_ST609 | D | 131242-WST02-DR-S-1101_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1101_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4511 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1102_ST609 | D | 131242-WST02-DR-S-1102_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1102_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4512 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1103_ST609 | D | 131242-WST02-DR-S-1103_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1103_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4513 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2100_ST609 | D | 131242-WST02-DR-S-2100_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2100_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4514 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2101_ST609 | D | 131242-WST02-DR-S-2101_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2101_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4515 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2102_ST609 | D | 131242-WST02-DR-S-2102_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2102_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4516 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3100_ST609 | D | 131242-WST02-DR-S-3100_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-3100_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4517 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3101_ST609 | D | 131242-WST02-DR-S-3101_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-3101_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4518 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3102_ST609 | D | 131242-WST02-DR-S-3102_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-3102_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4519 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5100_ST609 | D | 131242-WST02-DR-S-5100_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5100_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4520 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5101_ST609 | D | 131242-WST02-DR-S-5101_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5101_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4521 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5102_ST609 | D | 131242-WST02-DR-S-5102_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5102_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4522 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5103_ST609 | D | 131242-WST02-DR-S-5103_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5103_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4523 | 000823 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5104_ST609 | D | 131242-WST02-DR-S-5104_ST609-D | 2024-11-19 | ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) | For Information | 2024-12-17 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5104_ST609 | NA | "ST609_SSN Pipe Racks (SSN-PR-01,02,04,05) " | 2024-11-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-09 | 58 | INF | 2024-11-19 | D | 000823 | 2024-11-19 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
4524 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-S-0300_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-0300_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4525 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | A | 131242-WSD11-DR-S-0301_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-0301_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4526 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | A | 131242-WSD11-DR-S-1000_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4527 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | A | 131242-WSD11-DR-S-1001_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4528 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | A | 131242-WSD11-DR-S-1002_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4529 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | A | 131242-WSD11-DR-S-1003_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-1003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4530 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | A | 131242-WSD11-DR-S-2000_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-2000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4531 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | A | 131242-WSD11-DR-S-2001_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-2001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4532 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | A | 131242-WSD11-DR-S-3000_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-3000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4533 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | A | 131242-WSD11-DR-S-3001_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-3001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4534 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | A | 131242-WSD11-DR-S-3002_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-3002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4535 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | A | 131242-WSD11-DR-S-5000_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4536 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | A | 131242-WSD11-DR-S-5001_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4537 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | A | 131242-WSD11-DR-S-5002_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4538 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | A | 131242-WSD11-DR-S-5003_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4539 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | A | 131242-WSD11-DR-S-5004_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5004_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4540 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | A | 131242-WSD11-DR-S-5005_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5005_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4541 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | A | 131242-WSD11-DR-S-5006_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5006_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4542 | 000824 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | A | 131242-WSD11-DR-S-8000_ST617-A | 2024-11-19 | ST617 -THP PLATFORM 01 & 02 | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-12-17 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-8000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-03 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4543 | 000825 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-C-0021-0 | 2024-11-20 | Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm | For Information | 2024-12-18 | 2024-11-27 | For Information |  | YES | NA |  | 131242-WSW41-QA-0021 | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-04 | 7 | INF | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | INF | INF
4544 | 000826 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 0 | 131242-WSD11-RT-E-0002-0 | 2024-11-20 | THP Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-04 | 24 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4545 | 000826 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0002 | 1 | 131242-WSD11-RT-E-0002-1 | 2025-03-25 | THP Load Flow Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 42 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4546 | 000827 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 0 | 131242-WSD11-RT-E-0003-0 | 2024-11-20 | THP Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-18 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-RT-0003 | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-04 | 24 | AWC | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
4547 | 000827 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0003 | 1 | 131242-WSD11-RT-E-0003-1 | 2025-03-25 | THP Short Circuit Study Report | Rev 1: Approved with Comments. Please refer to attached file for comments. | 2025-04-14 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-RT-0003 | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 42 | AWC | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
4548 | 000828 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 0 | 131242-WSW41-MS-M-0005-0 | 2024-11-21 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-MS-0005 | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 14 | NAP | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
4549 | 000828 | 01 | Charles | HSE | NA | 131242 | WSW41 | MS | M | 0005 | 1 | 131242-WSW41-MS-M-0005-1 | 2024-12-11 | MSRA and SWP for Delivery of 2000kVA Transformer | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2024-12-30 | Approved with Comments | 2025-01-17 | NO | Overdue |  | 131242-WSW41-MS-0005 | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 19 | AWC | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
4550 | 000829 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5006 | A | 131242-WST02-DR-A-5006-A | 2024-11-21 | Fire Seal Detail | Rev.0: Not approved. Please revise and resubmit. | 2024-12-19 | 2024-12-06 | Not Approved | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-5006 | NA | "Fire Seal Detail" && "SSN Cast-in Schedule & Details" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 15 | NAP | 2025-02-26 | C.1 | 000492&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4551 | 000830 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0020 | 0 | 131242-WSW41-QA-C-0020-0 | 2024-11-21 | Monthly Concrete Cube Records for Structural works for September 2024 | For information. | 2024-12-19 | 2024-11-27 | For Information |  | YES | NA |  | 131242-WSW41-QA-0020 | NA | "Monthly Concrete Cube Records for Structural works for September 2024" && "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" && "T&C Check List " | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-05 | 6 | INF | 2025-09-30 | 0 | 000756&&000830&&001712 | 2024-10-11, 2024-11-21, 2025-09-30 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
4552 | 000831 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | A | 131242-WST02-DR-A-5003-A | 2024-11-22 | SSN_CAT Ladder | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-08 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 16 | NAP | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4553 | 000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | - | 131242-WST02-DR-A-5003-- | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | Not Approved | 2025-05-16 | YES | Resubmitted |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-18 | 24 | NAP | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4554 | 000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1007 | A | 131242-WST02-DR-A-1007-A | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | Not Approved | 2025-05-16 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-18 | 24 | NAP | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4555 | 000831 | 01 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1008 | A | 131242-WST02-DR-A-1008-A | 2025-04-04 | SSN_CAT Ladder | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-24 | 2025-04-28 | Not Approved | 2025-05-16 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-18 | 24 | NAP | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4556 | 000831 | 02 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5003 | D | 131242-WST02-DR-A-5003-D | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | Not Approved | 2025-11-04 | NO | Overdue |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 57 | NAP | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4557 | 000831 | 02 | Anna | CSA | NA | PE report | NA | RT | A | 9999 | C | PE report--RT-A--C | 2025-08-19 | SSN_CAT Ladder | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-10-15 | Not Approved | 2025-11-04 | NO | Overdue |  | PE report-NA-RT-9999 | NA | "SSN_CAT Ladder " | 2025-08-19 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 57 | NAP | 2025-08-19 | C | 000831 | 2025-08-19 | 02 | 1 | Not Approved | NAP | 2025-11-04 | Overdue | 0 | NAP | NAP
4558 | 000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1002 | A | 131242-WST02-DR-A-1002-A | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 15 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
4559 | 000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 2001 | A | 131242-WST02-DR-A-2001-A | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 15 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
4560 | 000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5004 | A | 131242-WST02-DR-A-5004-A | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-5004 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 15 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4561 | 000832 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 5005 | A | 131242-WST02-DR-A-5005-A | 2024-11-22 | SSN Electrical Building Archi Drawing | Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-5005 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 15 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4562 | 000833 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 5002 | A | 131242-WST02-DR-A-5002-A | 2024-11-22 | SSN Door Window Schedule | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 15 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4563 | 000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | B | 131242-WST02-DR-A-5002-B | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | Approved with Comments | 2025-03-31 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 21 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4564 | 000833 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5007 | A | 131242-WST02-DR-A-5007-A | 2025-02-18 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-03-10 | 2025-03-11 | Approved with Comments | 2025-03-31 | YES | Resubmitted |  | 131242-WST02-DR-5007 | NA | "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 21 | AWC | 2025-02-26 | C.1 | 000492&&000833 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4565 | 000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-A-5002-A.2 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | Approved with Comments | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 36 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4566 | 000833 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5001 | A.2 | 131242-WST02-DR-A-5001-A.2 | 2025-08-19 | SSN Door Window Schedule | Rev.1: Approved with comments. Revise and resubmit. | 2025-09-08 | 2025-09-24 | Approved with Comments | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 36 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4567 | 000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5002 | A.2 | 131242-WST02-DR-A-5002-A.2 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 | Approved with Comments | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 13 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC | 2025-12-24 | Overdue | 0 | AWC | AWC
4568 | 000833 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5001 | A.2 | 131242-WST02-DR-A-5001-A.2 | 2025-11-21 | SSN Door Window Schedule | Rev.3: Approved with comments. Revise and resubmit. | 2025-12-11 | 2025-12-04 | Approved with Comments | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 13 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC | 2025-12-24 | Overdue | 0 | AWC | AWC
4569 | 000834 | 00 | Anna | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001-A | 2024-11-22 | SSN Railing Layout | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-20 | 2024-12-07 | Approved with Comments |  | YES | NA |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-06 | 15 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
4570 | 000835 | 00 | Franklin | CSA | NA | 131242 | WST02 | DR | C | 1025 | A | 131242-WST02-DR-C-1025-A | 2024-11-22 | SSN Pavement Plan | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-20 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 16 | AWC | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
4571 | 000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5400 | A | 131242-WST02-DR-S-5400-A | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 | Not Approved | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-5400 | NA | "Hookup Drawing -TSS Analyser" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 14 | NAP | 2025-12-18 | F | 000753&&000836&&001730&&001788&&001914 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
4572 | 000836 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1400 | A | 131242-WST02-DR-S-1400-A | 2024-11-22 | SSN Wall Mounted Pipe Support Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-20 | 2024-12-06 | Not Approved | 2024-12-27 | NO | Overdue |  | 131242-WST02-DR-1400 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 14 | NAP | 2025-12-18 | H | 000753&&000836&&001148&&001730&&001914 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
4573 | 000837 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 0 | 131242-WSD11-CL-S-0005-0 | 2024-11-22 | Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check | Approved | 2024-12-20 | 2024-12-06 | Approved |  | YES | NA |  | 131242-WSD11-CL-0005 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-06 | 14 | APP | 2024-11-22 | 0 | 000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | APP | APP
4574 | 000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0034 | 0 | 131242-WSD11-MI-P-0034-0 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 | For Information |  | YES | NA |  | 131242-WSD11-MI-0034 | NA | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | 2024-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-12-12 | 13 | INF | 2024-11-22 | 0 | 000838 | 2024-11-22 | 00 | 1 | For Information | INF | 2024-12-25 | Overdue | 0 | INF | INF
4575 | 000838 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0035 | 0 | 131242-WSD11-MI-P-0035-0 | 2024-11-22 | Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107 | For Information | 2024-12-20 | 2024-12-05 | For Information | 2024-12-26 | NO | Overdue |  | 131242-WSD11-MI-0035 | NA | "Process & MEICA Meeting Minutes 0034 & 0035_20241024 & 1107" | 2024-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-12 | 13 | INF | 2024-11-22 | 0 | 000838 | 2024-11-22 | 00 | 1 | For Information | INF | 2024-12-25 | Overdue | 0 | INF | INF
4576 | 000839 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0020 | 0 | 131242-WSW41-MS-C-0020-0 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold | Approved | 2024-12-20 | 2024-12-18 | Approved |  | YES | NA |  | 131242-WSW41-MS-0020 | NA | "MSRA & SWP for Erection, Modification and Dismantling of Tower Scaffold" | 2024-11-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-13 | 25 | APP | 2024-11-23 | 0 | 000839 | 2024-11-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4577 | 000840 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0021 | 0 | 131242-WSW41-MS-C-0021-0 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold | Approved | 2024-12-20 | 2024-12-07 | Approved |  | YES | NA |  | 131242-WSW41-MS-0021 | NA | "MSRA & SWP for Erection, Modification and Dismantling for Birdcage Scaffold" | 2024-11-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-13 | 14 | APP | 2024-11-23 | 0 | 000840 | 2024-11-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4578 | 000841 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0022 | 0 | 131242-WSW41-MS-C-0022-0 | 2024-11-23 | MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold | Approved | 2024-12-20 | 2024-12-18 | Approved |  | YES | NA |  | 131242-WSW41-MS-0022 | NA | "MSRA & SWP for Erection, Modification and Dismantling for Access Scaffold" | 2024-11-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-13 | 25 | APP | 2024-11-23 | 0 | 000841 | 2024-11-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4579 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST619 | A | 131242-WSD11-DR-S-0304_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0304_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4580 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 0305_ST619 | A | 131242-WSD11-DR-S-0305_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0305_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4581 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619 | A | 131242-WSD11-DR-S-1100_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1100_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4582 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619 | A | 131242-WSD11-DR-S-1101_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1101_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4583 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619 | A | 131242-WSD11-DR-S-2100_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-2100_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4584 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619 | A | 131242-WSD11-DR-S-3100_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-3100_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4585 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619 | A | 131242-WSD11-DR-S-5100_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-5100_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4586 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619 | A | 131242-WSD11-DR-S-5101_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-5101_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4587 | 000842 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619 | A | 131242-WSD11-DR-S-8002_ST619-A | 2024-11-25 | Drawings and PE Calculation of ST619 | Rev 0 - Approved with comments, no resubmission required | 2024-12-23 | 2024-12-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-8002_ST619 | NA | "Drawings and PE Calculation of ST619 " | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-15 | 11 | AWC | 2024-11-25 | A | 000842 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4588 | 000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1500_ST611 | A | 131242-WST02-DR-S-1500_ST611-A | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-1500_ST611 | NA | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 12 | AWC | 2024-11-25 | A | 000843 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4589 | 000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5500_ST611 | A | 131242-WST02-DR-S-5500_ST611-A | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-5500_ST611 | NA | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 12 | AWC | 2024-11-25 | A | 000843 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4590 | 000843 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5501_ST611 | A | 131242-WST02-DR-S-5501_ST611-A | 2024-11-25 | Drawings and PE Calculation of ST611 (Pipe Support more than 2m) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-23 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-DR-5501_ST611 | NA | "Drawings and PE Calculation of ST611 (Pipe Support more than 2m)" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 12 | AWC | 2024-11-25 | A | 000843 | 2024-11-25 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4591 | 000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-S-1501-A | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 12 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4592 | 000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3500 | A | 131242-WSD11-DR-S-3500-A | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-3500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 12 | AWC | 2025-09-24 | G | 000844&&000845&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4593 | 000844 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1500 | A | 131242-WSD11-DR-S-1500-A | 2024-11-25 | THP Courtyard RC Plinth Detail | Rev.0: Approved with comments. Revise and resubmit. | 2024-12-23 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 12 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4594 | 000844 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment reply | A | 131242-WSD11-DR-S-comment reply - | 2025-08-22 | THP Courtyard RC Plinth Detail | Rev.1: For Information | 2025-09-11 | 2025-09-17 | For Information |  | YES | NA |  | 131242-WSD11-DR-comment reply | NA | "THP Courtyard RC Plinth Detail" | 2025-08-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-11 | 26 | INF | 2025-08-22 | A | 000844 | 2025-08-22 | 01 | 1 | For Information | INF | 2025-10-07 | Overdue | 0 | INF | INF
4595 | 000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1501 | A | 131242-WSD11-DR-S-1501-A | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | Rejected | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 0 | REJ | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
4596 | 000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3500 | A | 131242-WSD11-DR-S-3500-A | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | Rejected | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-3500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 0 | REJ | 2025-09-24 | G | 000844&&000845&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
4597 | 000845 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1500 | A | 131242-WSD11-DR-S-1500-A | 2024-12-06 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2025-01-06 | 2024-12-06 | Rejected | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 0 | REJ | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
4598 | 000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1505_Superceded | A | 131242-WSD11-DR-S-1505_Superceded-A | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-13 | 2024-12-18 | Rejected | 2025-01-08 | YES | Resubmitted |  | 131242-WSD11-DR-1505_Superceded | NA | " THP Courtyard Equipment Anchor Bolt Details" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 23 | REJ | 2024-11-25 | A | 000845 | 2024-11-25 | 01 | 1 | Rejected | REJ | 2025-01-07 | Overdue | 0 | REJ | REJ
4599 | 000845 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 3505_Superceded | A | 131242-WSD11-DR-S-3505_Superceded-A | 2024-11-25 | THP Courtyard Equipment Anchor Bolt Details | Rev 0 - As per CES requested to reject this submittal. | 2024-12-23 | 2024-12-18 | Rejected | 2025-01-08 | YES | Resubmitted |  | 131242-WSD11-DR-3505_Superceded | NA | " THP Courtyard Equipment Anchor Bolt Details" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-15 | 23 | REJ | 2024-11-25 | A | 000845 | 2024-11-25 | 01 | 1 | Rejected | REJ | 2025-01-07 | Overdue | 0 | REJ | REJ
4600 | 000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1505 | A | 131242-WSD11-DR-S-1505-A | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-08 | 2025-02-12 | Approved with Comments | 2025-03-04 | NO | Overdue |  | 131242-WSD11-DR-1505 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 56 | AWC | 2025-08-13 | B | 000845&&001382 | 2024-12-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4601 | 000845 | 02 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3505 | A | 131242-WSD11-DR-S-3505-A | 2024-12-18 | THP Courtyard Equipment Anchor Bolt Details | Rev.2: Approved with comments. Please find comment sheet for resubmission. | 2025-01-16 | 2025-02-12 | Approved with Comments | 2025-03-04 | NO | Overdue |  | 131242-WSD11-DR-3505 | NA | " THP Courtyard Equipment Anchor Bolt Details" | 2024-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 56 | AWC | 2024-12-18 | A | 000845 | 2024-12-18 | 02 | 1 | Approved with Comments | AWC | 2025-03-04 | Overdue | 0 | AWC | AWC
4602 | 000846 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 0 | 131242-WST02-DS-M-5481-0 | 2024-11-28 | Data Sheet for Hyperbolic Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted | In progress: 1). await TVU to confirm motor area (safety zone or not, Qili checking w TUV, will discuss with SO this Friday); 2). needTenwit confirm anchor bolt detail in C&S Dwg -> in 2 weeks | 131242-WST02-DS-5481 | NA | "Data Sheet for Hyperbolic Mixer" | 2024-11-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-18 | 16 | AWC | 2025-03-27 | 1 | 000846 | 2024-11-28, 2025-03-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
4603 | 000846 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5481 | 1 | 131242-WST02-DS-M-5481-1 | 2025-03-27 | Data Sheet for Hyperbolic Mixer | Rev 1: Approved | 2025-04-16 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WST02-DS-5481 | NA | "Data Sheet for Hyperbolic Mixer" | 2024-11-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-10 | 31 | APP | 2025-03-27 | 1 | 000846 | 2024-11-28, 2025-03-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
4604 | 000847 | 00 | Yibo/ Qili | Mech | NA | 131242 | WST02 | CL | P | 5481 | 0 | 131242-WST02-CL-P-5481-0 | 2024-11-28 | SSN Hyperbolic Mixer CFD | Rev 0: Not approved - Revise and Resubmit | 2024-12-27 | 2024-12-14 | Not Approved | 2025-01-03 | NO | Overdue | To be handled by Process (QiLi), will be VO for revised CFD version | 131242-WST02-CL-5481 | NA | "SSN Hyperbolic Mixer CFD" | 2024-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-18 | 16 | NAP | 2024-11-28 | 0 | 000847 | 2024-11-28 | 00 | 1 | Not Approved | NAP | 2025-01-02 | Overdue | 0 | NAP | NAP
4605 | 000848 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0014 | 0 | 131242-WST02-VI-E-0014-0 | 2024-11-28 | Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue | To follow-up with HDMANN. | 131242-WST02-VI-0014 | NA | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" && "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-12 | 7 | AWC | 2025-01-08 | 1 | 000501&&000848 | 2024-05-31, 2024-11-28, 2025-01-08 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4606 | 000849 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 0 | 131242-WST02-RT-E-0007-0 | 2024-11-28 | SSN Load Flow Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-RT-0007 | NA | "SSN Load Flow Study Report" | 2024-11-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-18 | 16 | AWC | 2025-05-04 | 1 | 000849 | 2024-11-28, 2025-05-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4607 | 000849 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0007 | 1 | 131242-WST02-RT-E-0007-1 | 2025-05-04 | SSN Load Flow Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-22 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WST02-RT-0007 | NA | "SSN Load Flow Study Report" | 2024-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 26 | AWC | 2025-05-04 | 1 | 000849 | 2024-11-28, 2025-05-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
4608 | 000850 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 0 | 131242-WST02-RT-E-0008-0 | 2024-11-28 | SSN Short Circuit Study Report | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-27 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-RT-0008 | NA | "SSN Short Circuit Study Report" | 2024-11-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-18 | 16 | AWC | 2025-05-30 | 1 | 000850 | 2024-11-28, 2025-05-30 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4609 | 000850 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0008 | 1 | 131242-WST02-RT-E-0008-1 | 2025-05-30 | SSN Short Circuit Study Report | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-06-19 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WST02-RT-0008 | NA | "SSN Short Circuit Study Report" | 2024-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 54 | AWC | 2025-05-30 | 1 | 000850 | 2024-11-28, 2025-05-30 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
4610 | 000851 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0036 | 0 | 131242-WSW41-MI-C-0036-0 | 2024-11-28 | CSA Meeting Minutes 0036_14112024 | For Information | 2024-12-27 | 2024-12-07 | For Information |  | YES | NA |  | 131242-WSW41-MI-0036 | NA | "CSA Meeting Minutes 0036_14112024" && "Process & MEICA Meeting Minutes 0036_21112024" | 2024-11-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-18 | 9 | INF | 2025-01-11 | 0 | 000851&&000965 | 2024-11-28, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4611 | 000852 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0013 | 0 | 131242-WSW41-RT-C-0013-0 | 2024-11-28 | Quarterly Safety Review Follow Up on SSN RC Works | For Information | 2024-12-27 | 2024-12-07 | For Information |  | YES | NA |  | 131242-WSW41-RT-0013 | NA | "C4B Monthly Progress Report Number No.13 (05 24)" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Quarterly Safety Review Follow Up on SSN RC Works" | 2024-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-12 | 9 | INF | 2025-07-01 | 1 | 000520&&000852&&001420 | 2024-06-12, 2024-11-28, 2025-07-01 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
4612 | 000853 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0022 | 0 | 131242-WST02-VI-I-0022-0 | 2024-11-28 | Vendor approval of SSN Package (Autosampler) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-27 | 2025-03-14 | Approved with Comments | 2025-04-03 | NO | Overdue |  | 131242-WST02-VI-0022 | NA | "Vendor approval of SSN Package (Autosampler) " | 2024-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-18 | 106 | AWC | 2024-11-28 | 0 | 000853 | 2024-11-28 | 00 | 1 | Approved with Comments | AWC | 2025-04-03 | Overdue | 0 | AWC | AWC
4613 | 000854 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0003 | 0 | 131242-WST02-VI-A-0003-0 | 2024-11-28 | Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd. | Approved | 2024-12-27 | 2024-12-07 | Approved |  | YES | NA |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-12 | 9 | APP | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
4614 | 000855 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-A-0004-0 | 2024-11-28 | Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd. | Approved | 2024-12-27 | 2024-12-05 | Approved |  | YES | NA |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-12 | 7 | APP | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | APP | APP
4615 | 000856 | 00 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 0 | 131242-WST02-QA-A-0003-0 | 2024-11-29 | 2Hrs Fire rated AAC Blocks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2024-12-06 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-QA-0003 | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-13 | 7 | NAP | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | For Information | INF |  |  | 0 | NAP | NAP
4616 | 000856 | 01 | Muthu | QAQC | NA | 131242 | WST02 | QA | A | 0003 | 1 | 131242-WST02-QA-A-0003-1 | 2024-12-20 | 2Hrs Fire rated AAC Blocks | Rev.1: Approved | 2025-01-10 | 2025-01-02 | Approved |  | YES | NA |  | 131242-WST02-QA-0003 | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-03 | 13 | APP | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | For Information | INF |  |  | 0 | APP | APP
4617 | 000857 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 0 | 131242-WSW41-DS-I-0001-0 | 2024-11-29 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-30 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WSW41-DS-0001 | NA | "Datasheet for Unistrut Supports" && "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-19 | 116 | AWC | 2025-09-15 | 1 | 000857&&000943 | 2024-11-29, 2025-01-03, 2025-09-15 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4618 | 000857 | 01 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | I | 0001 | 1 | 131242-WSW41-DS-I-0001-1 | 2025-09-15 | SSN and THP ICA, ELV and Communication Cable datasheet and specification | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-10-03 | 2025-12-02 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DS-0001 | NA | "Datasheet for Unistrut Supports" && "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-29 | 78 | AWC | 2025-09-15 | 1 | 000857&&000943 | 2024-11-29, 2025-01-03, 2025-09-15 | 00, 01 | 3 | Approved with Comments | AWC | 2025-12-22 | Overdue | 0 | AWC | AWC
4619 | 000858 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0008 | 0 | 131242-WSW41-QA-E-0008-0 | 2024-11-30 | FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-12-30 | 2024-12-14 | Approved with Comments | 2025-01-03 | NO | Overdue |  | 131242-WSW41-QA-0008 | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-14 | 14 | AWC | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | Approved with Comments | AWC | 2025-01-02 | Overdue | 0 | AWC | AWC
4620 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5218 | A | 131242-WST02-SD-S-5218-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5218 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4621 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5219 | A | 131242-WST02-SD-S-5219-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5219 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4622 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5220 | A | 131242-WST02-SD-S-5220-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5220 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4623 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5221 | A | 131242-WST02-SD-S-5221-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5221 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4624 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5223 | A | 131242-WST02-SD-S-5223-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5223 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4625 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5224 | A | 131242-WST02-SD-S-5224-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5224 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4626 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1201 | A | 131242-WST02-SD-S-1201-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-1201 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4627 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1202 | A | 131242-WST02-SD-S-1202-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-1202 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4628 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1203 | A.1 | 131242-WST02-SD-S-1203-A.1 | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-1203 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A.1 | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4629 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 1204 | A | 131242-WST02-SD-S-1204-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-1204 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4630 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5212 | A | 131242-WST02-SD-S-5212-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5212 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4631 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5213 | A | 131242-WST02-SD-S-5213-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5213 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4632 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5214 | A | 131242-WST02-SD-S-5214-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5214 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4633 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5215 | A | 131242-WST02-SD-S-5215-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5215 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4634 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5216 | A | 131242-WST02-SD-S-5216-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5216 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4635 | 000859 | 00 | Franklin | CSA | NA | 131242 | WST02 | SD | S | 5217 | A | 131242-WST02-SD-S-5217-A | 2024-11-30 | SSN Wall Shop Drawing | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-SD-5217 | NA | "SSN Wall Shop Drawing" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 47 | AWC | 2024-11-30 | A | 000859 | 2024-11-30 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
4636 | 000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1027 | A | 131242-WST02-DR-C-1027-A | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | Not Approved | 2025-03-24 | NO | Overdue |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-14 | 94 | NAP | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4637 | 000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1026 | A | 131242-WST02-DR-C-1026-A | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | Not Approved | 2025-03-24 | NO | Overdue |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-14 | 94 | NAP | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | NAP | NAP
4638 | 000860 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5008 | A | 131242-WST02-DR-C-5008-A | 2024-11-30 | SSN-Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-04 | Not Approved | 2025-03-24 | NO | Overdue |  | 131242-WST02-DR-5008 | NA | "SSN Cast-in Schedule & Details" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-14 | 94 | NAP | 2025-02-26 | C.1 | 000492&&000860 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4639 | 000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210-A | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | Not Approved | 2025-04-10 | YES | Resubmitted |  | 131242-WSD11-DR-1210 | NA | "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 111 | NAP | 2025-12-14 | A | 000861&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | NAP | NAP
4640 | 000861 | 00 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200-A | 2024-11-30 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-30 | 2025-03-21 | Not Approved | 2025-04-10 | YES | Resubmitted |  | 131242-WSD11-DR-5200 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 111 | NAP | 2025-12-14 | A | 000861&&001226&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
4641 | 000861 | 01 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | cmmt sheet | A | 131242-WSD11-DR-S-cmmt sheet- | 2025-09-15 | THP- Valve Pit, Sump and Kerb Detail | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSD11-DR-cmmt sheet | NA | "THP- Valve Pit, Sump and Kerb Detail" | 2025-09-15 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-10-05 | 10 | INF | 2025-09-15 | A | 000861 | 2025-09-15 | 01 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
4642 | 000862 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0018 | 0 | 131242-WSW41-PS-PM-0018-0 | 2024-11-30 | Monthly Progress Presentation No. 18 (1124) | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PS-0018 | NA | "Incentive/ Disincentive Audit Scheme for Oct 2024" && "Monthly Progress Presentation No. 18 (1124)" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-20 | 5 | INF | 2024-12-12 | 0 | 000862&&000888 | 2024-11-30, 2024-12-12 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4643 | 000863 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0018 | 0 | 131242-WSW41-MI-PM-0018-0 | 2024-11-30 | Monthly Progress Meeting Minutes 0018_20241113 | Rev. 0 - For Information | 2024-12-30 | 2024-12-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0018 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0018_20241113" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-12-14 | 5 | INF | 2024-11-30 | 0 | 000313&&000320&&000339&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | For Information | INF | 2024-12-25 | Overdue | 0 | INF | INF
4644 | 000864 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0031 | 0 | 131242-WSW41-VI-M-0031-0 | 2024-12-02 | Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2024-06-12 | Approved with Comments | 2024-07-03 | NO | Overdue |  | 131242-WSW41-VI-0031 | NA | "Vendor Approval of Stainless Steel Pipes and Fittings Fabricator and QA QC Document - Cyclect Engineering Pte. Ltd." | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 |  | AWC | 2024-12-02 | 0 | 000864 | 2024-12-02 | 00 | 1 | Approved with Comments | AWC | 2024-07-02 | Overdue | 0 | AWC | AWC
4645 | 000865 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 0 | 131242-WSW41-PC-W-0017-0 | 2024-12-02 | Payment Claim No.17 | As requested by C4BJV to reject this submittal and resubmit. | 2024-12-31 | 2024-12-03 | Rejected | 2024-12-23 | YES | Resubmitted |  | 131242-WSW41-PC-0017 | NA | "Payment Claim No.17" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 1 | REJ | 2024-12-03 | 1 | 000865 | 2024-12-02, 2024-12-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | REJ | REJ
4646 | 000865 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0017 | 1 | 131242-WSW41-PC-W-0017-1 | 2024-12-03 | Payment Claim No.17 | Rev(1): Approved. Please refer to S.O. correspondence no 259 3 Dec 2024. | 2024-12-23 | 2025-01-08 | Approved |  | YES | NA |  | 131242-WSW41-PC-0017 | NA | "Payment Claim No.17" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-17 | 36 | APP | 2024-12-03 | 1 | 000865 | 2024-12-02, 2024-12-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
4647 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | A | 131242-WST02-DR-EP-3008-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-16 | 67 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
4648 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | A | 131242-WST02-DR-EP-3009-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-16 | 67 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
4649 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | A | 131242-WST02-DR-EP-3010-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-16 | 67 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4650 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | A | 131242-WST02-DR-EP-3011-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-16 | 67 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4651 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | A | 131242-WST02-DR-EP-3012-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4652 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | A | 131242-WST02-DR-EP-3013-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4653 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | A | 131242-WST02-DR-EP-3014-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4654 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | A | 131242-WST02-DR-EP-3015-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4655 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | A | 131242-WST02-DR-EP-3016-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4656 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | A | 131242-WST02-DR-EP-3017-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4657 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | A | 131242-WST02-DR-EP-3018-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4658 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | A | 131242-WST02-DR-EP-3019-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4659 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | A | 131242-WST02-DR-EP-3020-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4660 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | A | 131242-WST02-DR-EP-3021-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4661 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | A | 131242-WST02-DR-EP-3022-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4662 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | A | 131242-WST02-DR-EP-3023-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4663 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | A | 131242-WST02-DR-EP-7110-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4664 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | A | 131242-WST02-DR-EP-7111-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4665 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | A | 131242-WST02-DR-EP-7112-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7112 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4666 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | A | 131242-WST02-DR-EP-7113-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7113 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4667 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | A | 131242-WST02-DR-EP-7114-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7114 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4668 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | A | 131242-WST02-DR-EP-7115-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7115 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4669 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | A | 131242-WST02-DR-EP-7116-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7116 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4670 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | A | 131242-WST02-DR-EP-7117-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7117 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4671 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | A | 131242-WST02-DR-EP-7118-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7118 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4672 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | A | 131242-WST02-DR-EP-7119-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7119 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4673 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | A | 131242-WST02-DR-EP-7120-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4674 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | A | 131242-WST02-DR-EP-7121-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4675 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | A | 131242-WST02-DR-EP-7122-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4676 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | A | 131242-WST02-DR-EP-7123-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4677 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | A | 131242-WST02-DR-EP-7124-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4678 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | A | 131242-WST02-DR-EP-7125-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4679 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | A | 131242-WST02-DR-EP-7126-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7126 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4680 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | A | 131242-WST02-DR-EP-7127-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7127 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4681 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | A | 131242-WST02-DR-EI-7040-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7040 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4682 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | A | 131242-WST02-DR-EI-7041-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7041 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4683 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | A | 131242-WST02-DR-EI-7042-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7042 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4684 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | A | 131242-WST02-DR-EI-7043-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7043 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4685 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | A | 131242-WST02-DR-EI-7044-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7044 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4686 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | A | 131242-WST02-DR-EI-7045-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7045 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4687 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | A | 131242-WST02-DR-EI-7046-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7046 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4688 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | A | 131242-WST02-DR-EI-7047-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7047 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4689 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | A | 131242-WST02-DR-EI-7048-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7048 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4690 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | A | 131242-WST02-DR-EI-7049-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7049 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4691 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | A | 131242-WST02-DR-EI-7050-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7050 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4692 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | A | 131242-WST02-DR-EI-7051-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7051 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4693 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | A | 131242-WST02-DR-EI-7052-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7052 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4694 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | A | 131242-WST02-DR-EI-7053-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7053 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4695 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | A | 131242-WST02-DR-EI-7054-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7054 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4696 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | A | 131242-WST02-DR-EI-7055-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7055 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002003 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4697 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | A | 131242-WST02-DR-EI-7060-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7060 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4698 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | A | 131242-WST02-DR-EI-7061-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7061 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4699 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | A | 131242-WST02-DR-EI-7062-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7062 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4700 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | A | 131242-WST02-DR-EI-7063-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7063 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4701 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | A | 131242-WST02-DR-EI-7064-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7064 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4702 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | A | 131242-WST02-DR-EI-7065-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7065 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4703 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | A | 131242-WST02-DR-EI-7066-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7066 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4704 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | A | 131242-WST02-DR-EI-7067-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7067 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4705 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | A | 131242-WST02-DR-EI-7068-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7068 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4706 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | A | 131242-WST02-DR-EI-7069-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7069 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4707 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | A | 131242-WST02-DR-EI-7070-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7070 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4708 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | A | 131242-WST02-DR-EI-7071-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7071 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4709 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | A | 131242-WST02-DR-EI-7072-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7072 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4710 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | A | 131242-WST02-DR-EI-7073-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7073 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4711 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | A | 131242-WST02-DR-EI-7074-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7074 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4712 | 000866 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | A | 131242-WST02-DR-EI-7075-A | 2024-12-02 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7075 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4713 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | B | 131242-WST02-DR-EI-7040-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7040 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4714 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | B | 131242-WST02-DR-EI-7041-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7041 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4715 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | B | 131242-WST02-DR-EI-7042-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7042 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4716 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | B | 131242-WST02-DR-EI-7043-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7043 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4717 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | B | 131242-WST02-DR-EI-7044-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7044 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4718 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | B | 131242-WST02-DR-EI-7045-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7045 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4719 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | B | 131242-WST02-DR-EI-7046-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7046 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4720 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | B | 131242-WST02-DR-EI-7047-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7047 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4721 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | B | 131242-WST02-DR-EI-7048-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7048 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4722 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | B | 131242-WST02-DR-EI-7049-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7049 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4723 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | B | 131242-WST02-DR-EI-7050-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7050 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4724 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | B | 131242-WST02-DR-EI-7051-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7051 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4725 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | B | 131242-WST02-DR-EI-7052-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7052 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4726 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | B | 131242-WST02-DR-EI-7053-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7053 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4727 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | B | 131242-WST02-DR-EI-7054-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7054 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4728 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | B | 131242-WST02-DR-EI-7055-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7055 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002003 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4729 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | B | 131242-WST02-DR-EI-7056-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7056 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 6 | NAP | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4730 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | B | 131242-WST02-DR-EI-7057-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7057 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 6 | NAP | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4731 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | B | 131242-WST02-DR-EI-7058-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7058 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 6 | NAP | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4732 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | B | 131242-WST02-DR-EI-7060-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7060 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4733 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | B | 131242-WST02-DR-EI-7061-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7061 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4734 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | B | 131242-WST02-DR-EI-7062-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7062 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4735 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | B | 131242-WST02-DR-EI-7063-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7063 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4736 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | B | 131242-WST02-DR-EI-7064-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7064 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4737 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | B | 131242-WST02-DR-EI-7065-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7065 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4738 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | B | 131242-WST02-DR-EI-7066-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7066 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4739 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | B | 131242-WST02-DR-EI-7067-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7067 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4740 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | B | 131242-WST02-DR-EI-7068-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7068 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4741 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | B | 131242-WST02-DR-EI-7069-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7069 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4742 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | B | 131242-WST02-DR-EI-7070-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7070 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4743 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | B | 131242-WST02-DR-EI-7071-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7071 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4744 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | B | 131242-WST02-DR-EI-7072-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7072 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4745 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | B | 131242-WST02-DR-EI-7073-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7073 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4746 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | B | 131242-WST02-DR-EI-7074-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7074 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4747 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | B | 131242-WST02-DR-EI-7075-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7075 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4748 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | B | 131242-WST02-DR-EI-7076-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7076 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 6 | NAP | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4749 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | B | 131242-WST02-DR-EI-7077-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7077 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 6 | NAP | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4750 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | B | 131242-WST02-DR-EI-7078-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7078 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 6 | NAP | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4751 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | B | 131242-WST02-DR-EP-3008-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
4752 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | B | 131242-WST02-DR-EP-3009-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
4753 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | B | 131242-WST02-DR-EP-3010-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4754 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | B | 131242-WST02-DR-EP-3011-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4755 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | B | 131242-WST02-DR-EP-3012-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4756 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | B | 131242-WST02-DR-EP-3013-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4757 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | B | 131242-WST02-DR-EP-3014-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4758 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | B | 131242-WST02-DR-EP-3015-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4759 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | B | 131242-WST02-DR-EP-3016-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4760 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | B | 131242-WST02-DR-EP-3017-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
4761 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | B | 131242-WST02-DR-EP-3018-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4762 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | B | 131242-WST02-DR-EP-3019-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4763 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | B | 131242-WST02-DR-EP-3020-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4764 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | B | 131242-WST02-DR-EP-3021-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4765 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | B | 131242-WST02-DR-EP-3022-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4766 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | B | 131242-WST02-DR-EP-3023-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4767 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | B | 131242-WST02-DR-EP-7110-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4768 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | B | 131242-WST02-DR-EP-7111-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4769 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | B | 131242-WST02-DR-EP-7112-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7112 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4770 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | B | 131242-WST02-DR-EP-7113-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7113 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4771 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | B | 131242-WST02-DR-EP-7114-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7114 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4772 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | B | 131242-WST02-DR-EP-7115-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7115 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4773 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | B | 131242-WST02-DR-EP-7116-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7116 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4774 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | B | 131242-WST02-DR-EP-7117-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7117 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4775 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | B | 131242-WST02-DR-EP-7118-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7118 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4776 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | B | 131242-WST02-DR-EP-7119-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7119 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4777 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | B | 131242-WST02-DR-EP-7120-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4778 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | B | 131242-WST02-DR-EP-7121-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4779 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | B | 131242-WST02-DR-EP-7122-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4780 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | B | 131242-WST02-DR-EP-7123-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4781 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | B | 131242-WST02-DR-EP-7124-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4782 | 000866 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | B | 131242-WST02-DR-EP-7125-B | 2025-03-07 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-13 | Not Approved | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 6 | NAP | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4783 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | C | 131242-WST02-DR-EI-7040-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7040 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4784 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | C | 131242-WST02-DR-EI-7041-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7041 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4785 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | C | 131242-WST02-DR-EI-7042-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7042 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4786 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | C | 131242-WST02-DR-EI-7043-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7043 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4787 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | C | 131242-WST02-DR-EI-7044-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7044 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4788 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | C | 131242-WST02-DR-EI-7045-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7045 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4789 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | C | 131242-WST02-DR-EI-7046-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7046 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4790 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | C | 131242-WST02-DR-EI-7047-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7047 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4791 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | C | 131242-WST02-DR-EI-7048-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7048 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4792 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | C | 131242-WST02-DR-EI-7049-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7049 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4793 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | C | 131242-WST02-DR-EI-7050-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7050 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4794 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | C | 131242-WST02-DR-EI-7051-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7051 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4795 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | C | 131242-WST02-DR-EI-7052-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7052 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4796 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | C | 131242-WST02-DR-EI-7053-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7053 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4797 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | C | 131242-WST02-DR-EI-7054-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7054 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4798 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | C | 131242-WST02-DR-EI-7055-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7055 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002003 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4799 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | C | 131242-WST02-DR-EI-7056-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7056 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4800 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | C | 131242-WST02-DR-EI-7057-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7057 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4801 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | C | 131242-WST02-DR-EI-7058-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7058 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4802 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | C | 131242-WST02-DR-EI-7060-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7060 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4803 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | C | 131242-WST02-DR-EI-7061-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7061 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4804 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | C | 131242-WST02-DR-EI-7062-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7062 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4805 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | C | 131242-WST02-DR-EI-7063-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7063 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4806 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | C | 131242-WST02-DR-EI-7064-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7064 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4807 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | C | 131242-WST02-DR-EI-7065-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7065 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4808 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | C | 131242-WST02-DR-EI-7066-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7066 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4809 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | C | 131242-WST02-DR-EI-7067-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7067 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4810 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | C | 131242-WST02-DR-EI-7068-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7068 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4811 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | C | 131242-WST02-DR-EI-7069-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7069 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4812 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | C | 131242-WST02-DR-EI-7070-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7070 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4813 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | C | 131242-WST02-DR-EI-7071-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7071 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4814 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | C | 131242-WST02-DR-EI-7072-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7072 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4815 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | C | 131242-WST02-DR-EI-7073-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7073 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4816 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | C | 131242-WST02-DR-EI-7074-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7074 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4817 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | C | 131242-WST02-DR-EI-7075-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7075 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4818 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | C | 131242-WST02-DR-EI-7076-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7076 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4819 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | C | 131242-WST02-DR-EI-7077-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7077 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4820 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | C | 131242-WST02-DR-EI-7078-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7078 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4821 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | C | 131242-WST02-DR-EP-3008-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
4822 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | C | 131242-WST02-DR-EP-3009-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
4823 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | C | 131242-WST02-DR-EP-3010-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4824 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | C | 131242-WST02-DR-EP-3011-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4825 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | C | 131242-WST02-DR-EP-3012-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4826 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | C | 131242-WST02-DR-EP-3013-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4827 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | C | 131242-WST02-DR-EP-3014-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4828 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | C | 131242-WST02-DR-EP-3015-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4829 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | C | 131242-WST02-DR-EP-3016-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4830 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | C | 131242-WST02-DR-EP-3017-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4831 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | C | 131242-WST02-DR-EP-3018-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4832 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | C | 131242-WST02-DR-EP-3019-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4833 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | C | 131242-WST02-DR-EP-3020-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4834 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | C | 131242-WST02-DR-EP-3021-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4835 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | C | 131242-WST02-DR-EP-3022-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4836 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | C | 131242-WST02-DR-EP-3023-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4837 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | C | 131242-WST02-DR-EP-7110-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4838 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | C | 131242-WST02-DR-EP-7111-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4839 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | C | 131242-WST02-DR-EP-7112-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7112 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4840 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | C | 131242-WST02-DR-EP-7113-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7113 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4841 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | C | 131242-WST02-DR-EP-7114-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7114 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4842 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | C | 131242-WST02-DR-EP-7115-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7115 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4843 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | C | 131242-WST02-DR-EP-7116-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7116 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4844 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | C | 131242-WST02-DR-EP-7117-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7117 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4845 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | C | 131242-WST02-DR-EP-7118-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7118 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4846 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | C | 131242-WST02-DR-EP-7119-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7119 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4847 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | C | 131242-WST02-DR-EP-7120-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4848 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | C | 131242-WST02-DR-EP-7121-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4849 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | C | 131242-WST02-DR-EP-7122-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4850 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | C | 131242-WST02-DR-EP-7123-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4851 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | C | 131242-WST02-DR-EP-7124-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4852 | 000866 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | C | 131242-WST02-DR-EP-7125-C | 2025-03-28 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4853 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7040 | D | 131242-WST02-DR-EI-7040-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7040 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4854 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7041 | D | 131242-WST02-DR-EI-7041-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7041 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4855 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7042 | D | 131242-WST02-DR-EI-7042-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7042 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4856 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7043 | D | 131242-WST02-DR-EI-7043-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7043 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4857 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7044 | D | 131242-WST02-DR-EI-7044-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7044 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4858 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7045 | D | 131242-WST02-DR-EI-7045-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7045 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4859 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7046 | D | 131242-WST02-DR-EI-7046-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7046 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4860 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7047 | D | 131242-WST02-DR-EI-7047-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7047 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4861 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7048 | D | 131242-WST02-DR-EI-7048-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7048 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4862 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7049 | D | 131242-WST02-DR-EI-7049-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7049 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4863 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7050 | D | 131242-WST02-DR-EI-7050-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7050 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4864 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7051 | D | 131242-WST02-DR-EI-7051-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7051 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4865 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7052 | D | 131242-WST02-DR-EI-7052-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7052 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4866 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7053 | D | 131242-WST02-DR-EI-7053-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7053 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4867 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7054 | D | 131242-WST02-DR-EI-7054-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7054 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4868 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7055 | D | 131242-WST02-DR-EI-7055-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7055 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002003 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4869 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7056 | D | 131242-WST02-DR-EI-7056-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7056 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4870 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7057 | D | 131242-WST02-DR-EI-7057-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7057 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4871 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7058 | D | 131242-WST02-DR-EI-7058-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7058 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4872 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7060 | D | 131242-WST02-DR-EI-7060-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7060 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4873 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7061 | D | 131242-WST02-DR-EI-7061-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7061 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4874 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7062 | D | 131242-WST02-DR-EI-7062-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7062 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4875 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7063 | D | 131242-WST02-DR-EI-7063-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7063 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4876 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7064 | D | 131242-WST02-DR-EI-7064-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7064 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4877 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7065 | D | 131242-WST02-DR-EI-7065-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7065 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4878 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7066 | D | 131242-WST02-DR-EI-7066-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7066 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4879 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7067 | D | 131242-WST02-DR-EI-7067-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7067 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4880 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7068 | D | 131242-WST02-DR-EI-7068-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7068 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4881 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7069 | D | 131242-WST02-DR-EI-7069-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7069 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4882 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7070 | D | 131242-WST02-DR-EI-7070-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7070 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4883 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7071 | D | 131242-WST02-DR-EI-7071-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7071 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4884 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7072 | D | 131242-WST02-DR-EI-7072-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7072 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4885 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7073 | D | 131242-WST02-DR-EI-7073-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7073 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4886 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7074 | D | 131242-WST02-DR-EI-7074-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7074 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4887 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7075 | D | 131242-WST02-DR-EI-7075-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7075 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4888 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7076 | D | 131242-WST02-DR-EI-7076-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7076 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4889 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7077 | D | 131242-WST02-DR-EI-7077-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7077 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4890 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7078 | D | 131242-WST02-DR-EI-7078-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7078 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2025-03-07, 2025-03-28, 2025-07-01 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4891 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | D | 131242-WST02-DR-EP-3008-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
4892 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | D | 131242-WST02-DR-EP-3009-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
4893 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | D | 131242-WST02-DR-EP-3010-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4894 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | D | 131242-WST02-DR-EP-3011-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4895 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3012 | D | 131242-WST02-DR-EP-3012-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4896 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3013 | D | 131242-WST02-DR-EP-3013-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4897 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3014 | D | 131242-WST02-DR-EP-3014-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4898 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3015 | D | 131242-WST02-DR-EP-3015-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4899 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3016 | D | 131242-WST02-DR-EP-3016-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4900 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3017 | D | 131242-WST02-DR-EP-3017-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4901 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3018 | D | 131242-WST02-DR-EP-3018-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4902 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3019 | D | 131242-WST02-DR-EP-3019-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4903 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3020 | D | 131242-WST02-DR-EP-3020-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4904 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3021 | D | 131242-WST02-DR-EP-3021-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4905 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3022 | D | 131242-WST02-DR-EP-3022-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4906 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3023 | D | 131242-WST02-DR-EP-3023-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4907 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7110 | D | 131242-WST02-DR-EP-7110-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4908 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7111 | D | 131242-WST02-DR-EP-7111-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4909 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7112 | D | 131242-WST02-DR-EP-7112-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7112 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4910 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7113 | D | 131242-WST02-DR-EP-7113-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7113 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4911 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7114 | D | 131242-WST02-DR-EP-7114-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7114 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4912 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7115 | D | 131242-WST02-DR-EP-7115-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7115 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4913 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7116 | D | 131242-WST02-DR-EP-7116-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7116 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4914 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7117 | D | 131242-WST02-DR-EP-7117-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7117 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4915 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7118 | D | 131242-WST02-DR-EP-7118-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7118 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4916 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7119 | D | 131242-WST02-DR-EP-7119-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7119 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4917 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7120 | D | 131242-WST02-DR-EP-7120-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4918 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7121 | D | 131242-WST02-DR-EP-7121-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4919 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7122 | D | 131242-WST02-DR-EP-7122-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4920 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7123 | D | 131242-WST02-DR-EP-7123-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4921 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7124 | D | 131242-WST02-DR-EP-7124-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4922 | 000866 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7125 | D | 131242-WST02-DR-EP-7125-D | 2025-07-01 | GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 97 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4923 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | A | 131242-WST02-DR-EP-3038-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3038 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-08-21 | C | 000867 | 2024-12-02, 2025-03-28, 2025-08-21 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4924 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | A | 131242-WST02-DR-EP-3039-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3039 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4925 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | A | 131242-WST02-DR-EP-3040-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3040 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2026-02-03 | B | 000867&&001813 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4926 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | A | 131242-WST02-DR-EP-3041-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3041 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4927 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | A | 131242-WST02-DR-EP-3042-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3042 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4928 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | A | 131242-WST02-DR-EP-3043-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3043 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4929 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | A | 131242-WST02-DR-EP-3044-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3044 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4930 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | A | 131242-WST02-DR-EP-3045-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3045 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4931 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | A | 131242-WST02-DR-EP-3046-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3046 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4932 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | A | 131242-WST02-DR-EP-3047-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3047 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4933 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | A | 131242-WST02-DR-EP-3048-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3048 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4934 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | A | 131242-WST02-DR-EP-3049-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3049 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4935 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | A | 131242-WST02-DR-EP-3050-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3050 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4936 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | A | 131242-WST02-DR-EP-3051-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-3051 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2026-02-03 | A | 000867&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4937 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | A | 131242-WST02-DR-EP-7136-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7136 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4938 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | A | 131242-WST02-DR-EP-7137-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7137 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4939 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | A | 131242-WST02-DR-EP-7138-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7138 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4940 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | A | 131242-WST02-DR-EP-7139-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7139 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4941 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | A | 131242-WST02-DR-EP-7140-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7140 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4942 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | A | 131242-WST02-DR-EP-7141-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7141 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4943 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | A | 131242-WST02-DR-EI-7120-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4944 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | A | 131242-WST02-DR-EI-7121-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4945 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | A | 131242-WST02-DR-EI-7122-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4946 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | A | 131242-WST02-DR-EI-7123-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4947 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | A | 131242-WST02-DR-EI-7124-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4948 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | A | 131242-WST02-DR-EI-7125-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4949 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | A | 131242-WST02-DR-EI-7126-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7126 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4950 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | A | 131242-WST02-DR-EI-7127-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7127 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4951 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | A | 131242-WST02-DR-EI-7128-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7128 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-24 | C | 000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4952 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | A | 131242-WST02-DR-EI-7140-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7140 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4953 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | A | 131242-WST02-DR-EI-7141-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7141 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4954 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | A | 131242-WST02-DR-EI-7142-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7142 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4955 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | A | 131242-WST02-DR-EI-7143-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7143 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4956 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | A | 131242-WST02-DR-EI-7144-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7144 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4957 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | A | 131242-WST02-DR-EI-7145-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7145 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4958 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | A | 131242-WST02-DR-EI-7146-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7146 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4959 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | A | 131242-WST02-DR-EI-7147-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7147 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4960 | 000867 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | A | 131242-WST02-DR-EI-7148-A | 2024-12-02 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-31 | 2025-02-07 | Approved with Comments | 2025-02-27 | NO | Overdue |  | 131242-WST02-DR-7148 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 67 | AWC | 2025-07-21 | B | 000867&&001157 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4961 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | B | 131242-WST02-DR-EP-3038-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3038 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-08-21 | C | 000867 | 2024-12-02, 2025-03-28, 2025-08-21 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4962 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | B | 131242-WST02-DR-EP-3039-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3039 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4963 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | B | 131242-WST02-DR-EP-3040-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3040 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | B | 000867&&001813 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4964 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | B | 131242-WST02-DR-EP-3041-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3041 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4965 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | B | 131242-WST02-DR-EP-3042-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3042 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4966 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | B | 131242-WST02-DR-EP-3043-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3043 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4967 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | B | 131242-WST02-DR-EP-3044-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3044 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4968 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | B | 131242-WST02-DR-EP-3045-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3045 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4969 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | B | 131242-WST02-DR-EP-3046-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3046 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4970 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | B | 131242-WST02-DR-EP-3047-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3047 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4971 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | B | 131242-WST02-DR-EP-3048-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3048 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4972 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | B | 131242-WST02-DR-EP-3049-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3049 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4973 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | B | 131242-WST02-DR-EP-3050-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3050 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4974 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | B | 131242-WST02-DR-EP-3051-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3051 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-02-03 | A | 000867&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4975 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | B | 131242-WST02-DR-EP-7136-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7136 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4976 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | B | 131242-WST02-DR-EP-7137-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7137 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4977 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | B | 131242-WST02-DR-EP-7138-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7138 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4978 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | B | 131242-WST02-DR-EP-7139-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7139 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4979 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | B | 131242-WST02-DR-EP-7140-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7140 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4980 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | B | 131242-WST02-DR-EP-7141-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7141 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4981 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | B | 131242-WST02-DR-EI-7120-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4982 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | B | 131242-WST02-DR-EI-7121-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4983 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | B | 131242-WST02-DR-EI-7122-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4984 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | B | 131242-WST02-DR-EI-7123-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4985 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | B | 131242-WST02-DR-EI-7124-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4986 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | B | 131242-WST02-DR-EI-7125-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4987 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | B | 131242-WST02-DR-EI-7126-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7126 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4988 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | B | 131242-WST02-DR-EI-7127-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7127 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4989 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | B | 131242-WST02-DR-EI-7128-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7128 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-24 | C | 000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4990 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | B | 131242-WST02-DR-EI-7140-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7140 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4991 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | B | 131242-WST02-DR-EI-7141-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7141 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
4992 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | B | 131242-WST02-DR-EI-7142-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7142 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4993 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | B | 131242-WST02-DR-EI-7143-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7143 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4994 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | B | 131242-WST02-DR-EI-7144-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7144 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4995 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | B | 131242-WST02-DR-EI-7145-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7145 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4996 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | B | 131242-WST02-DR-EI-7146-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7146 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4997 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | B | 131242-WST02-DR-EI-7147-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7147 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4998 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | B | 131242-WST02-DR-EI-7148-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7148 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001157 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4999 | 000867 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7149 | B | 131242-WST02-DR-EI-7149-B | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7149 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-07-21 | B | 000867&&001157 | 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5000 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3038 | C | 131242-WST02-DR-EP-3038-C | 2025-08-21 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3038 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 41 | AWC | 2025-08-21 | C | 000867 | 2024-12-02, 2025-03-28, 2025-08-21 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5001 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3039 | C | 131242-WST02-DR-EP-3039-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3039 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5002 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3040 | C | 131242-WST02-DR-EP-3040-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3040 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2026-02-03 | B | 000867&&001813 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5003 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3041 | C | 131242-WST02-DR-EP-3041-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3041 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5004 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3042 | C | 131242-WST02-DR-EP-3042-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3042 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5005 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3043 | C | 131242-WST02-DR-EP-3043-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3043 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5006 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3044 | C | 131242-WST02-DR-EP-3044-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3044 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5007 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3045 | C | 131242-WST02-DR-EP-3045-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3045 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5008 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3046 | C | 131242-WST02-DR-EP-3046-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3046 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5009 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3047 | C | 131242-WST02-DR-EP-3047-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3047 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5010 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3048 | C | 131242-WST02-DR-EP-3048-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3048 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5011 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3049 | C | 131242-WST02-DR-EP-3049-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3049 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | B | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5012 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3050 | C | 131242-WST02-DR-EP-3050-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3050 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5013 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3051 | C | 131242-WST02-DR-EP-3051-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-3051 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2026-02-03 | A | 000867&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5014 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7136 | C | 131242-WST02-DR-EP-7136-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7136 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5015 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7137 | C | 131242-WST02-DR-EP-7137-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7137 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5016 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7138 | C | 131242-WST02-DR-EP-7138-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7138 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5017 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7139 | C | 131242-WST02-DR-EP-7139-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7139 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5018 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7140 | C | 131242-WST02-DR-EP-7140-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7140 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5019 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7141 | C | 131242-WST02-DR-EP-7141-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7141 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5020 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7120 | C | 131242-WST02-DR-EI-7120-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7120 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5021 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7121 | C | 131242-WST02-DR-EI-7121-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7121 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5022 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7122 | C | 131242-WST02-DR-EI-7122-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7122 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5023 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7123 | C | 131242-WST02-DR-EI-7123-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7123 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5024 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7124 | C | 131242-WST02-DR-EI-7124-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7124 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5025 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7125 | C | 131242-WST02-DR-EI-7125-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7125 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-01 | D | 000866&&000867 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5026 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7126 | C | 131242-WST02-DR-EI-7126-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7126 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5027 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7127 | C | 131242-WST02-DR-EI-7127-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7127 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5028 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7128 | C | 131242-WST02-DR-EI-7128-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7128 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-24 | C | 000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5029 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7140 | C | 131242-WST02-DR-EI-7140-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7140 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5030 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7141 | C | 131242-WST02-DR-EI-7141-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7141 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-03-28 | C | 000867 | 2024-12-02, 2025-03-28 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
5031 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7142 | C | 131242-WST02-DR-EI-7142-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7142 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5032 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7143 | C | 131242-WST02-DR-EI-7143-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7143 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5033 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7144 | C | 131242-WST02-DR-EI-7144-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7144 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5034 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7145 | C | 131242-WST02-DR-EI-7145-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7145 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5035 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7146 | C | 131242-WST02-DR-EI-7146-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7146 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5036 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7147 | C | 131242-WST02-DR-EI-7147-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7147 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5037 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7148 | C | 131242-WST02-DR-EI-7148-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7148 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2024-12-02 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001157 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5038 | 000867 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7149 | C | 131242-WST02-DR-EI-7149-C | 2025-03-28 | GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7149 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 187 | AWC | 2025-07-21 | B | 000867&&001157 | 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5039 | 000868 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 0 | 131242-WSW41-SP-C-0022-0 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2024-12-31 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WSW41-SP-0022 | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 37 | NAP | 2025-02-20 | 2 | 000868 | 2024-12-02, 2025-02-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
5040 | 000868 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 1 | 131242-WSW41-SP-C-0022-1 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-17 | Approved with Comments | 2025-03-07 | YES | Resubmitted |  | 131242-WSW41-SP-0022 | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 77 | AWC | 2025-02-20 | 2 | 000868 | 2024-12-02, 2025-02-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
5041 | 000868 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0022 | 2 | 131242-WSW41-SP-C-0022-2 | 2025-02-20 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited) | R2: Approved | 2025-03-12 | 2025-03-04 | Approved |  | YES | NA |  | 131242-WSW41-SP-0022 | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (PanUnited)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-06 | 12 | APP | 2025-02-20 | 2 | 000868 | 2024-12-02, 2025-02-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
5042 | 000869 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 0 | 131242-WSW41-SP-C-0023-0 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R0: Not Approved. Please refer to comment sheet for resubmission | 2024-12-31 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WSW41-SP-0023 | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 37 | NAP | 2024-12-02 | 1 | 000869 | 2024-12-02 | 00, 01 | 2 | Not Approved | NAP | 2025-01-28 | Overdue | 0 | NAP | NAP
5043 | 000869 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0023 | 1 | 131242-WSW41-SP-C-0023-1 | 2024-12-02 | SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance) | R1:Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-20 | 2025-02-03 | Approved with Comments | 2025-02-21 | NO | Overdue |  | 131242-WSW41-SP-0023 | NA | "SSN Water Tank Wall Openings Box Out - Non Shrink Concrete Design Mix C35/45 (Alliance)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-22 | 63 | AWC | 2024-12-02 | 1 | 000869 | 2024-12-02 | 00, 01 | 2 | Not Approved | NAP | 2025-02-21 | Overdue | 0 | AWC | AWC
5044 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | A | 131242-WST02-DR-EP-3024-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5045 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | A | 131242-WST02-DR-EP-3025-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3025 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2026-02-03 | B | 000870&&001809&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5046 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | A | 131242-WST02-DR-EP-3026-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5047 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | A | 131242-WST02-DR-EP-3027-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3027 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5048 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | A | 131242-WST02-DR-EP-3028-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3028 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5049 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | A | 131242-WST02-DR-EP-3029-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3029 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5050 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | A | 131242-WST02-DR-EP-3030-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5051 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | A | 131242-WST02-DR-EP-3031-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5052 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | A | 131242-WST02-DR-EP-3032-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3032 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5053 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | A | 131242-WST02-DR-EP-3033-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3033 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-09-29 | A | 000163&&000870&&001702 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5054 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | A | 131242-WST02-DR-EP-3034-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3034 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5055 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | A | 131242-WST02-DR-EP-3035-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3035 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-10-31 | A | 000162&&000870&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5056 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | A | 131242-WST02-DR-EI-7080-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7080 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5057 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | A | 131242-WST02-DR-EI-7081-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7081 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5058 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | A | 131242-WST02-DR-EI-7082-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7082 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5059 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | A | 131242-WST02-DR-EI-7083-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7083 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5060 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | A | 131242-WST02-DR-EI-7084-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7084 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5061 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | A | 131242-WST02-DR-EI-7085-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7085 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5062 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | A | 131242-WST02-DR-EI-7086-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7086 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5063 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | A | 131242-WST02-DR-EI-7087-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7087 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5064 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | A | 131242-WST02-DR-EI-7088-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7088 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5065 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | A | 131242-WST02-DR-EI-7089-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7089 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5066 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | A | 131242-WST02-DR-EI-7090-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7090 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5067 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | A | 131242-WST02-DR-EI-7091-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7091 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 66 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5068 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | A | 131242-WST02-DR-EI-7100-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5069 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | A | 131242-WST02-DR-EI-7101-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5070 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | A | 131242-WST02-DR-EI-7102-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5071 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | A | 131242-WST02-DR-EI-7103-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5072 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | A | 131242-WST02-DR-EI-7104-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5073 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | A | 131242-WST02-DR-EI-7105-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5074 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | A | 131242-WST02-DR-EI-7106-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5075 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | A | 131242-WST02-DR-EI-7107-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5076 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | A | 131242-WST02-DR-EI-7108-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5077 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | A | 131242-WST02-DR-EI-7109-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5078 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | A | 131242-WST02-DR-EI-7110-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5079 | 000870 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | A | 131242-WST02-DR-EI-7111-A | 2024-12-03 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-01 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 66 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5080 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | B | 131242-WST02-DR-EP-3024-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5081 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | B | 131242-WST02-DR-EP-3025-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3025 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2026-02-03 | B | 000870&&001809&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5082 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | B | 131242-WST02-DR-EP-3026-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5083 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | B | 131242-WST02-DR-EP-3027-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3027 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5084 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | B | 131242-WST02-DR-EP-3028-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3028 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5085 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | B | 131242-WST02-DR-EP-3029-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3029 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5086 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | B | 131242-WST02-DR-EP-3030-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5087 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | B | 131242-WST02-DR-EP-3031-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5088 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | B | 131242-WST02-DR-EP-3032-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3032 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5089 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | B | 131242-WST02-DR-EP-3033-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3033 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-09-29 | A | 000163&&000870&&001702 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5090 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | B | 131242-WST02-DR-EP-3034-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3034 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5091 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | B | 131242-WST02-DR-EP-3035-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-3035 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-10-31 | A | 000162&&000870&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5092 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | B | 131242-WST02-DR-EP-7126-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7126 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5093 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | B | 131242-WST02-DR-EP-7127-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7127 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5094 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7128 | B | 131242-WST02-DR-EP-7128-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7128 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5095 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7129 | B | 131242-WST02-DR-EP-7129-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7129 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5096 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7130 | B | 131242-WST02-DR-EP-7130-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7130 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5097 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7131 | B | 131242-WST02-DR-EP-7131-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7131 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5098 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7132 | B | 131242-WST02-DR-EP-7132-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7132 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5099 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7133 | B | 131242-WST02-DR-EP-7133-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7133 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5100 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7134 | B | 131242-WST02-DR-EP-7134-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7134 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5101 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7135 | B | 131242-WST02-DR-EP-7135-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7135 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5102 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | B | 131242-WST02-DR-EI-7080-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7080 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5103 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | B | 131242-WST02-DR-EI-7081-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7081 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5104 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | B | 131242-WST02-DR-EI-7082-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7082 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5105 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | B | 131242-WST02-DR-EI-7083-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7083 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5106 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | B | 131242-WST02-DR-EI-7084-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7084 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5107 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | B | 131242-WST02-DR-EI-7085-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7085 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5108 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | B | 131242-WST02-DR-EI-7086-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7086 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5109 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | B | 131242-WST02-DR-EI-7087-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7087 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5110 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | B | 131242-WST02-DR-EI-7088-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7088 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5111 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | B | 131242-WST02-DR-EI-7089-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7089 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5112 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | B | 131242-WST02-DR-EI-7090-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7090 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5113 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | B | 131242-WST02-DR-EI-7091-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7091 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5114 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7092 | B | 131242-WST02-DR-EI-7092-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7092 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 28 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5115 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | B | 131242-WST02-DR-EI-7100-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5116 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | B | 131242-WST02-DR-EI-7101-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5117 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | B | 131242-WST02-DR-EI-7102-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5118 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | B | 131242-WST02-DR-EI-7103-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5119 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | B | 131242-WST02-DR-EI-7104-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5120 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | B | 131242-WST02-DR-EI-7105-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5121 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | B | 131242-WST02-DR-EI-7106-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5122 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | B | 131242-WST02-DR-EI-7107-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5123 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | B | 131242-WST02-DR-EI-7108-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5124 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | B | 131242-WST02-DR-EI-7109-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5125 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | B | 131242-WST02-DR-EI-7110-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5126 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | B | 131242-WST02-DR-EI-7111-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5127 | 000870 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7112 | B | 131242-WST02-DR-EI-7112-B | 2025-04-08 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-7112 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 28 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5128 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3024 | C | 131242-WST02-DR-EP-3024-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5129 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3025 | C | 131242-WST02-DR-EP-3025-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3025 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2026-02-03 | B | 000870&&001809&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5130 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3026 | C | 131242-WST02-DR-EP-3026-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5131 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3027 | C | 131242-WST02-DR-EP-3027-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3027 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5132 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3028 | C | 131242-WST02-DR-EP-3028-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3028 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5133 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3029 | C | 131242-WST02-DR-EP-3029-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3029 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5134 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3030 | C | 131242-WST02-DR-EP-3030-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5135 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3031 | C | 131242-WST02-DR-EP-3031-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5136 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3032 | C | 131242-WST02-DR-EP-3032-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3032 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5137 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3033 | C | 131242-WST02-DR-EP-3033-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3033 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-09-29 | A | 000163&&000870&&001702 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5138 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3034 | C | 131242-WST02-DR-EP-3034-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3034 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5139 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3035 | C | 131242-WST02-DR-EP-3035-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-3035 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-10-31 | A | 000162&&000870&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5140 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7126 | C | 131242-WST02-DR-EP-7126-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7126 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5141 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7127 | C | 131242-WST02-DR-EP-7127-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7127 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000866&&000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5142 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7128 | C | 131242-WST02-DR-EP-7128-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7128 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000867&&000870 | 2024-12-02, 2025-03-28, 2025-04-08, 2025-07-24 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5143 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7129 | C | 131242-WST02-DR-EP-7129-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7129 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5144 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7130 | C | 131242-WST02-DR-EP-7130-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7130 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5145 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7131 | C | 131242-WST02-DR-EP-7131-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7131 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5146 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7132 | C | 131242-WST02-DR-EP-7132-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7132 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5147 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7133 | C | 131242-WST02-DR-EP-7133-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7133 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5148 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7134 | C | 131242-WST02-DR-EP-7134-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7134 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5149 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7135 | C | 131242-WST02-DR-EP-7135-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7135 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5150 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7080 | C | 131242-WST02-DR-EI-7080-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7080 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5151 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7081 | C | 131242-WST02-DR-EI-7081-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7081 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5152 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7082 | C | 131242-WST02-DR-EI-7082-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7082 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5153 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7083 | C | 131242-WST02-DR-EI-7083-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7083 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5154 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7084 | C | 131242-WST02-DR-EI-7084-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7084 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5155 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7085 | C | 131242-WST02-DR-EI-7085-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7085 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5156 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7086 | C | 131242-WST02-DR-EI-7086-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7086 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5157 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7087 | C | 131242-WST02-DR-EI-7087-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7087 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5158 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7088 | C | 131242-WST02-DR-EI-7088-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7088 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5159 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7089 | C | 131242-WST02-DR-EI-7089-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7089 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5160 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7090 | C | 131242-WST02-DR-EI-7090-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7090 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5161 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7091 | C | 131242-WST02-DR-EI-7091-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7091 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2024-12-03, 2025-04-08, 2025-07-24 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5162 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7092 | C | 131242-WST02-DR-EI-7092-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7092 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000870 | 2025-04-08, 2025-07-24 | 01, 02 | 2 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5163 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7100 | C | 131242-WST02-DR-EI-7100-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5164 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7101 | C | 131242-WST02-DR-EI-7101-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5165 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7102 | C | 131242-WST02-DR-EI-7102-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5166 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7103 | C | 131242-WST02-DR-EI-7103-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5167 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7104 | C | 131242-WST02-DR-EI-7104-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5168 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7105 | C | 131242-WST02-DR-EI-7105-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5169 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7106 | C | 131242-WST02-DR-EI-7106-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5170 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7107 | C | 131242-WST02-DR-EI-7107-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5171 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7108 | C | 131242-WST02-DR-EI-7108-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5172 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7109 | C | 131242-WST02-DR-EI-7109-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5173 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7110 | C | 131242-WST02-DR-EI-7110-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7110 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5174 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7111 | C | 131242-WST02-DR-EI-7111-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7111 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2024-12-03, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5175 | 000870 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7112 | C | 131242-WST02-DR-EI-7112-C | 2025-07-24 | GA, Schematic Diagram and SLD for WST02-MCC-0102A/B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-13 | 2026-01-02 | Approved with Comments | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-7112 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 162 | AWC | 2025-07-24 | C | 000866&&000870 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-04-08, 2025-07-01, 2025-07-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-01-22 | Overdue | 0 | AWC | AWC
5176 | 000871 | 00 | Thet Myo | QAQC | NA | 131242 | WSD11 | MM | S | 0001 | 0 | 131242-WSD11-MM-S-0001-0 | 2024-12-03 | THP Courtyard SCDF Consultation Letter | For Information | 2025-01-01 | 2024-11-14 | For Information |  | YES | NA |  | 131242-WSD11-MM-0001 | NA | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" && "THP Courtyard SCDF Consultation Letter" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-23 |  | INF | 2025-11-20 | 0 | 000871&&001859 | 2024-12-03, 2025-11-20 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5177 | 000872 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0026 | 0 | 131242-WSW41-QA-M-0026-0 | 2024-12-04 | Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-02 | 2024-12-14 | Approved with Comments | 2025-01-03 | NO | Overdue |  | 131242-WSW41-QA-0026 | NA | "Factory Acceptance Test Report for pH Analyser" && "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" | 2024-12-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 10 | AWC | 2025-07-08 | 0 | 000872&&001241&&001447 | 2024-12-04, 2025-04-21, 2025-07-08 | 00 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
5178 | 000873 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0009 | 0 | 131242-WST02-QA-E-0009-0 | 2024-12-04 | FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-02 | 2024-12-23 | Approved with Comments | 2025-01-13 | NO | Overdue |  | 131242-WST02-QA-0009 | NA | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " && "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | 2024-12-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 19 | AWC | 2025-09-15 | 0 | 000873&&000901&&001679 | 2024-12-04, 2024-12-13, 2025-09-15 | 00 | 3 | For Information | INF |  |  | 0 | AWC | AWC
5179 | 000874 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 0 | 131242-WST02-CL-P-5431-0 | 2024-12-04 | SSN Catchpot Sizing Calculation | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-02 | 2025-01-08 | Approved with Comments | 2025-01-28 | YES | Resubmitted | comments received on 14 Feb | 131242-WST02-CL-5431 | NA | "SSN Catchpot Sizing Calculation " | 2024-12-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 35 | AWC | 2025-07-14 | 2 | 000874 | 2024-12-04, 2025-03-14, 2025-07-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5180 | 000874 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 1 | 131242-WST02-CL-P-5431-1 | 2025-03-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-28 | Approved with Comments | 2025-05-16 | YES | Resubmitted |  | 131242-WST02-CL-5431 | NA | "SSN Catchpot Sizing Calculation " | 2024-12-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 45 | AWC | 2025-07-14 | 2 | 000874 | 2024-12-04, 2025-03-14, 2025-07-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5181 | 000874 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 5431 | 2 | 131242-WST02-CL-P-5431-2 | 2025-07-14 | SSN Catchpot Sizing Calculation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-01 | 2025-09-17 | Approved with Comments | 2025-10-07 | NO | Overdue |  | 131242-WST02-CL-5431 | NA | "SSN Catchpot Sizing Calculation " | 2024-12-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 65 | AWC | 2025-07-14 | 2 | 000874 | 2024-12-04, 2025-03-14, 2025-07-14 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-07 | Overdue | 0 | AWC | AWC
5182 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | E | 131242-WST00-DR-S-8005_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST00-DR-8005_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5183 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | E | 131242-WST02-DR-S-0302_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0302_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5184 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0310_ST608_BCA | E | 131242-WST02-DR-S-0310_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0310_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-25 | 42 | INF | 2024-12-05 | E | 000875 | 2024-12-05 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5185 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0311_ST608_BCA | E | 131242-WST02-DR-S-0311_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0311_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-25 | 42 | INF | 2024-12-05 | E | 000875 | 2024-12-05 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5186 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0312_ST608_BCA | E | 131242-WST02-DR-S-0312_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-0312_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" | 2024-12-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-25 | 42 | INF | 2024-12-05 | E | 000875 | 2024-12-05 | 00 | 1 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5187 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | E | 131242-WST02-DR-S-1200_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5188 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | E | 131242-WST02-DR-S-1201_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5189 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | E | 131242-WST02-DR-S-1202_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5190 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | E | 131242-WST02-DR-S-1203_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1203_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5191 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | E | 131242-WST02-DR-S-1204_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1204_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5192 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | E | 131242-WST02-DR-S-1205_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-1205_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5193 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | E | 131242-WST02-DR-S-2200_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5194 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | E | 131242-WST02-DR-S-2201_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5195 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | E | 131242-WST02-DR-S-2202_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5196 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | E | 131242-WST02-DR-S-2203_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-2203_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5197 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | E | 131242-WST02-DR-S-3200_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-3200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5198 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | E | 131242-WST02-DR-S-3201_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-3201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5199 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | E | 131242-WST02-DR-S-3202_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-3202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5200 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | E | 131242-WST02-DR-S-5200_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5201 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | E | 131242-WST02-DR-S-5201_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5202 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | E | 131242-WST02-DR-S-5202_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5203 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | E | 131242-WST02-DR-S-5203_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5203_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5204 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | E | 131242-WST02-DR-S-5204_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5204_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5205 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | E | 131242-WST02-DR-S-5205_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5205_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5206 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | E | 131242-WST02-DR-S-5206_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5206_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5207 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | E | 131242-WST02-DR-S-5207_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5207_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5208 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | E | 131242-WST02-DR-S-5208_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5208_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5209 | 000875 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | E | 131242-WST02-DR-S-5209_ST608_BCA-E | 2024-12-05 | BCA approval of ST608 - SSN Shelter | For Information | 2025-01-03 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WST02-DR-5209_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-19 | 42 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5210 | 000876 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 0 | 131242-WST02-QA-A-0001-0 | 2024-12-05 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-03 | 2024-12-23 | Approved with Comments | 2025-01-13 | YES | Resubmitted |  | 131242-WST02-QA-0001 | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 18 | AWC | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | AWC | AWC
5211 | 000876 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0001 | 1 | 131242-WST02-QA-A-0001-1 | 2025-04-11 | Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions | Approved with Comments | 2025-05-01 | 2025-06-09 | Approved with Comments | 2025-06-27 | NO | Overdue |  | 131242-WST02-QA-0001 | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-25 | 59 | AWC | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | AWC | AWC
5212 | 000877 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0051 | 0 | 131242-WSW41-LT-PM-0051-0 | 2024-12-07 | CV of Team Member (CSEM) | Rev 0: Accepted for Information. | 2025-01-06 | 2025-03-25 | For Information |  | YES | NA |  | 131242-WSW41-LT-0051 | NA | "CV of Team Member (CSEM)" | 2024-12-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-12-27 | 108 | INF | 2024-12-07 | 0 | 000877 | 2024-12-07 | 00 | 1 | For Information | INF | 2025-04-14 | Overdue | 0 | INF | INF
5213 | 000878 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0052 | 0 | 131242-WSW41-LT-PM-0052-0 | 2024-12-07 | Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3) | Rev (0): Rejected. Please refer to S.O. correspondence no. 397 dated 10 Sep 25. | 2025-01-06 | 2025-09-23 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0052 | NA | "Request for Extension of Time and Additional Cost for Notice of Delay of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (Letter No 3)" | 2024-12-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-12-27 | 290 | REJ | 2024-12-07 | 0 | 000878 | 2024-12-07 | 00 | 1 | Rejected | REJ | 2025-10-13 | Overdue | 0 | REJ | REJ
5214 | 000879 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 9999 | 0 | 131242-WSW41-CD-IM--0 | 2024-12-09 | VCM Model Submission | For Information. | 2025-01-07 | 2024-12-23 | For Information |  | YES | NA |  | 131242-WSW41-CD-9999 | NA | " VCM Submission for 2025-11" && "VCM Model Submission" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2024-12-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-29 | 14 | INF | 2026-02-09 | A | 000879&&001888&&001941&&002009 | 2024-12-09, 2025-12-08, 2026-01-08, 2026-02-09 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
5215 | 000880 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5391 | 0 | 131242-WST02-CL-P-5391-0 | 2024-12-10 | Sampling Pump Calculation | Rev 0: Approved | 2025-01-08 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WST02-CL-5391 | NA | "Sampling Pump Calculation" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-30 | 138 | APP | 2024-12-10 | 0 | 000880 | 2024-12-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5216 | 000881 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 0 | 131242-WSW41-QA-M-0025-0 | 2024-12-10 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-08 | 2025-01-20 | Approved with Comments | 2025-02-07 | YES | Resubmitted |  | 131242-WSW41-QA-0025 | NA | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" && "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" && "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-30 | 41 | AWC | 2025-07-08 | 0 | 000881&&001221&&001446 | 2024-12-10, 2025-03-13, 2025-04-11, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5217 | 000881 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0025 | 1 | 131242-WSW41-QA-M-0025-1 | 2025-03-13 | Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication | Approved | 2025-04-02 | 2025-05-19 | Approved |  | YES | NA |  | 131242-WSW41-QA-0025 | NA | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" && "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" && "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-27 | 67 | APP | 2025-07-08 | 0 | 000881&&001221&&001446 | 2024-12-10, 2025-03-13, 2025-04-11, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
5218 | 000882 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0005 | 0 | 131242-WST02-VI-E-0005-0 | 2024-12-10 | Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex) | Rev 0: Approved with comments. To revise and resubmit. | 2025-01-08 | 2024-12-23 | Approved with Comments | 2025-01-13 | NO | Overdue | To follow-up with Jebsen and Jessen. | 131242-WST02-VI-0005 | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 13 | AWC | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5219 | 000883 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0008 | 0 | 131242-WST02-QA-A-0008-0 | 2024-12-10 | Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-08 | 2024-12-23 | Approved |  | YES | NA |  | 131242-WST02-QA-0008 | NA | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" && "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " && "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-30 | 13 | APP | 2025-09-04 | 0 | 000883&&001268&&001654 | 2024-12-10, 2025-05-04, 2025-07-05, 2025-09-04 | 00, 01 | 4 | For Information | INF |  |  | 0 | APP | APP
5220 | 000884 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0007 | 0 | 131242-WST02-QA-A-0007-0 | 2024-12-11 | Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) | Rev.0: Approved | 2025-01-09 | 2024-12-23 | Approved |  | YES | NA |  | 131242-WST02-QA-0007 | NA | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " && "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " && "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2024-12-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-31 | 12 | APP | 2025-08-27 | 0 | 000884&&001263&&001629 | 2024-12-11, 2025-05-02, 2025-07-07, 2025-08-27 | 00, 01 | 4 | For Information | INF |  |  | 0 | APP | APP
5221 | 000885 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 0 | 131242-WSW41-QA-S-0010-0 | 2024-12-11 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.0: As requested by CES to reject this submission. | 2025-01-09 | 2024-12-14 | Rejected | 2025-01-03 | YES | Resubmitted |  | 131242-WSW41-QA-0010 | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 3 | REJ | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
5222 | 000885 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | S | 0010 | 1 | 131242-WSW41-QA-S-0010-1 | 2024-12-18 | Materials submission and Vendor Approval of Top Manway Cover – Maccanvas | Rev.1: Approved with comments. Please refer comment sheet for resubmission. | 2025-01-08 | 2024-12-23 | Approved with Comments | 2025-01-13 | NO | Overdue |  | 131242-WSW41-QA-0010 | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-01 | 5 | AWC | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | Approved with Comments | AWC | 2025-01-10 | Overdue | 0 | AWC | AWC
5223 | 000886 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | I | 0006 | 0 | 131242-WSW41-VI-I-0006-0 | 2024-12-11 | Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-09 | 2025-01-08 | Approved with Comments | 2025-01-28 | NO | Overdue |  | 131242-WSW41-VI-0006 | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 28 | AWC | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | Approved with Comments | AWC | 2025-01-28 | Overdue | 0 | AWC | AWC
5224 | 000887 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0017 | 0 | 131242-WSW41-PS-HS-0017-0 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Sept 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2025-01-10 | 2024-12-30 | For Information |  | YES | NA |  | 131242-WSW41-PS-0017 | NA | "Incentive/ Disincentive Audit Scheme for Sept 2024" | 2024-12-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-01 | 18 | INF | 2024-12-12 | 0 | 000887 | 2024-12-12 | 00 | 1 | For Information | INF | 2025-01-17 | Overdue | 0 | INF | INF
5225 | 000888 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0018 | 0 | 131242-WSW41-PS-HS-0018-0 | 2024-12-12 | Incentive/ Disincentive Audit Scheme for Oct 2024 | Rev 0: Scoring confirmed to be at 60/100 | 2025-01-10 | 2024-12-30 | For Information |  | YES | NA |  | 131242-WSW41-PS-0018 | NA | "Incentive/ Disincentive Audit Scheme for Oct 2024" && "Monthly Progress Presentation No. 18 (1124)" | 2024-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-12-26 | 18 | INF | 2024-12-12 | 0 | 000862&&000888 | 2024-11-30, 2024-12-12 | 00 | 2 | For Information | INF | 2025-01-17 | Overdue | 0 | INF | INF
5226 | 000889 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-M-0027-0 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-01-20 | Approved with Comments | 2025-02-07 | YES | Resubmitted |  | 131242-WSW41-QA-0027 | NA | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" && "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" && "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-01 | 39 | AWC | 2025-08-26 | 0 | 000889&&001240&&001626 | 2024-12-12, 2025-04-21, 2025-08-26 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
5227 | 000889 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0027 | 0 | 131242-WSW41-QA-M-0027-0 | 2024-12-12 | Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton) | Rev 1: Approved. | 2025-01-02 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0027 | NA | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" && "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" && "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365) | 2025-01-01 | 376 | APP | 2025-08-26 | 0 | 000889&&001240&&001626 | 2024-12-12, 2025-04-21, 2025-08-26 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
5228 | 000890 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0019 | 0 | 131242-WSW41-RT-PM-19-0 | 2024-12-13 | C4B Monthly Progress Report Number No.19 (11 24) | Rev. 0 - Approved with comments (see attached comment sheet / need to re-submit) | 2025-01-13 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WSW41-RT-0019 | NA | "C4B Monthly Progress Report Number No.19 (11 24) " | 2024-12-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 34 | AWC | 2024-12-13 | 0 | 000890 | 2024-12-13 | 00 | 1 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
5229 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | A | 131242-WSW41-DR-M-5201-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | YES | Resubmitted | Pending vendor resubmission - Jash | 131242-WSW41-DR-5201 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-03-13 | B | 000891 | 2024-12-13, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5230 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5202 | A | 131242-WSW41-DR-M-5202-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5202 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5231 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5203 | A | 131242-WSW41-DR-M-5203-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5203 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5232 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5204 | A | 131242-WSW41-DR-M-5204-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5204 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5233 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5205 | A | 131242-WSW41-DR-M-5205-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5205 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5234 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5206 | A | 131242-WSW41-DR-M-5206-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5206 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5235 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5207 | A | 131242-WSW41-DR-M-5207-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5207 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5236 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5208 | A | 131242-WSW41-DR-M-5208-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5208 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5237 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5209 | A | 131242-WSW41-DR-M-5209-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5209 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5238 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5210 | A | 131242-WSW41-DR-M-5210-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5210 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5239 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5211 | A | 131242-WSW41-DR-M-5211-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5211 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5240 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5212 | A | 131242-WSW41-DR-M-5212-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5212 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5241 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5213 | A | 131242-WSW41-DR-M-5213-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5213 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5242 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5214 | A | 131242-WSW41-DR-M-5214-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5214 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5243 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5215 | A | 131242-WSW41-DR-M-5215-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5215 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5244 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5216 | A | 131242-WSW41-DR-M-5216-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5216 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5245 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5217 | A | 131242-WSW41-DR-M-5217-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5217 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5246 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5218 | A | 131242-WSW41-DR-M-5218-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5218 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5247 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5219 | A | 131242-WSW41-DR-M-5219-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5219 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5248 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5220 | A | 131242-WSW41-DR-M-5220-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5220 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5249 | 000891 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5221 | A | 131242-WSW41-DR-M-5221-A | 2024-12-13 | GA drawing for Metallic Knife Gate Valves | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-12 | Approved with Comments | 2025-01-30 | NO | Overdue |  | 131242-WSW41-DR-5221 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 30 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5250 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5201 | B | 131242-WSW41-DR-M-5201-B | 2025-03-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue | Pending vendor resubmission - Jash | 131242-WSW41-DR-5201 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 26 | AWC | 2025-03-13 | B | 000891 | 2024-12-13, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5251 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5202 | B | 131242-WSW41-DR-M-5202-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5202 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5252 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5203 | B | 131242-WSW41-DR-M-5203-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5203 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5253 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5204 | B | 131242-WSW41-DR-M-5204-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5204 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5254 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5205 | B | 131242-WSW41-DR-M-5205-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5205 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5255 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5206 | B | 131242-WSW41-DR-M-5206-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5206 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5256 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5207 | B | 131242-WSW41-DR-M-5207-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5207 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5257 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5208 | B | 131242-WSW41-DR-M-5208-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5208 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5258 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5209 | B | 131242-WSW41-DR-M-5209-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5209 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5259 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5210 | B | 131242-WSW41-DR-M-5210-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5210 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5260 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5211 | B | 131242-WSW41-DR-M-5211-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5211 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5261 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5212 | B | 131242-WSW41-DR-M-5212-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5212 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5262 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5213 | B | 131242-WSW41-DR-M-5213-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5213 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5263 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5214 | B | 131242-WSW41-DR-M-5214-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5214 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5264 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5215 | B | 131242-WSW41-DR-M-5215-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5215 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5265 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5216 | B | 131242-WSW41-DR-M-5216-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5216 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5266 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5217 | B | 131242-WSW41-DR-M-5217-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5217 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5267 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5218 | B | 131242-WSW41-DR-M-5218-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5218 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5268 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5219 | B | 131242-WSW41-DR-M-5219-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5219 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5269 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5220 | B | 131242-WSW41-DR-M-5220-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5220 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5270 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5221 | B | 131242-WSW41-DR-M-5221-B | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5221 | NA | "GA drawing for Metallic Knife Gate Valves " | 2024-12-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 85 | AWC | 2025-01-13 | B | 000891 | 2024-12-13, 2025-01-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5271 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5222 | A | 131242-WSW41-DR-M-5222-A | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5222 | NA | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-02 | 85 | AWC | 2025-01-13 | A | 000891 | 2025-01-13 | 01 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5272 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5223 | A | 131242-WSW41-DR-M-5223-A | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5223 | NA | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-02 | 85 | AWC | 2025-01-13 | A | 000891 | 2025-01-13 | 01 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5273 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5224 | A | 131242-WSW41-DR-M-5224-A | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5224 | NA | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-02 | 85 | AWC | 2025-01-13 | A | 000891 | 2025-01-13 | 01 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5274 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5225 | A | 131242-WSW41-DR-M-5225-A | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5225 | NA | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-02 | 85 | AWC | 2025-01-13 | A | 000891 | 2025-01-13 | 01 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5275 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5226 | A | 131242-WSW41-DR-M-5226-A | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5226 | NA | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-02 | 85 | AWC | 2025-01-13 | A | 000891 | 2025-01-13 | 01 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5276 | 000891 | 01 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5227 | A | 131242-WSW41-DR-M-5227-A | 2025-01-13 | GA drawing for Metallic Knife Gate Valves | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-DR-5227 | NA | "GA drawing for Metallic Knife Gate Valves " | 2025-01-13 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-02 | 85 | AWC | 2025-01-13 | A | 000891 | 2025-01-13 | 01 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5277 | 000892 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0037 | 0 | 131242-WSW41-MI-C-0037-0 | 2024-12-13 | CSA Meeting Minutes 0037_28112024 | For Information | 2025-01-13 | 2024-12-30 | For Information |  | YES | NA |  | 131242-WSW41-MI-0037 | NA | "CSA Meeting Minutes 0037_28112024" && "Process & MEICA Meeting Minutes 0037_05122024" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-02 | 17 | INF | 2025-01-11 | 0 | 000892&&000966 | 2024-12-13, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5278 | 000893 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0023 | 0 | 131242-WST02-VI-I-0023-0 | 2024-12-13 | Vendor Approval of SSN Package (Rotameter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-14 | Approved with Comments | 2025-04-03 | NO | Overdue |  | 131242-WST02-VI-0023 | NA | "Vendor Approval of SSN Package (Rotameter)" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 91 | AWC | 2024-12-13 | 0 | 000893 | 2024-12-13 | 00 | 1 | Approved with Comments | AWC | 2025-04-03 | Overdue | 0 | AWC | AWC
5279 | 000894 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0050 | 0 | 131242-WSW41-LT-PM-0050-0 | 2024-12-13 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025. | 2025-01-13 | 2025-08-25 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0050 | NA | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-02 | 255 | REJ | 2024-12-13 | 0 | 000894 | 2024-12-13 | 00 | 1 | Rejected | REJ | 2025-09-12 | Overdue | 0 | REJ | REJ
5280 | 000895 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 0 | 131242-WSW41-DS-E-1390-0 | 2024-12-13 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2024-12-23 | Approved with Comments | 2025-01-13 | YES | Resubmitted |  | 131242-WSW41-DS-1390 | NA | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 10 | AWC | 2025-02-14 | 1 | 000895 | 2024-12-13, 2025-02-14 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5281 | 000895 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1390 | 1 | 131242-WSW41-DS-E-1390-1 | 2025-02-14 | Sample Board Submission for SS Unistrut Support Accessories (HDMANN) | Rev 1: Approved. | 2025-03-06 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSW41-DS-1390 | NA | "Sample Board Submission for SS Unistrut Support Accessories (HDMANN)" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-28 | 72 | APP | 2025-02-14 | 1 | 000895 | 2024-12-13, 2025-02-14 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5282 | 000896 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 0 | 131242-WSW41-DS-E-1389-0 | 2024-12-13 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSW41-DS-1389 | NA | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 34 | AWC | 2025-03-06 | 1 | 000896 | 2024-12-13, 2025-03-06 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5283 | 000896 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1389 | 1 | 131242-WSW41-DS-E-1389-1 | 2025-03-06 | Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-26 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WSW41-DS-1389 | NA | "Sample Board Submission for SS Cable Ladder Tray Accessories (HDMANN)" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 52 | AWC | 2025-03-06 | 1 | 000896 | 2024-12-13, 2025-03-06 | 00, 01 | 2 | Approved with Comments | AWC | 2025-05-15 | Overdue | 0 | AWC | AWC
5284 | 000897 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-E-1391-0 | 2024-12-13 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-13 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSW41-DS-1391 | NA | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 34 | AWC | 2025-03-11 | 0 | 000897 | 2024-12-13, 2025-03-11 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5285 | 000897 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1391 | 0 | 131242-WSW41-DS-E-1391-0 | 2025-03-11 | Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable) | Rev 1: Approved. | 2025-03-31 | 2025-05-05 | Approved |  | YES | NA |  | 131242-WSW41-DS-1391 | NA | "Sample Board Submission for LV,ELV Power cable, Earth cable (Keyston Cable)" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-25 | 55 | APP | 2025-03-11 | 0 | 000897 | 2024-12-13, 2025-03-11 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5286 | 000898 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-C-0023-0 | 2024-12-13 | MSRA and SWP for Installation of AAC Block Wall | Approved | 2025-01-13 | 2025-01-08 | Approved |  | YES | NA |  | 131242-WSW41-MS-0023 | NA | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-02 | 26 | APP | 2025-02-16 | 0 | 000898&&001044 | 2024-12-13, 2025-02-16 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
5287 | 000899 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0030 | 0 | 131242-WST02-DS-M-0030-0 | 2024-12-13 | Data Sheet for Blower Discharge Sliencer | Rev 0: Approved | 2025-01-13 | 2025-03-04 | Approved |  | YES | NA |  | 131242-WST02-DS-0030 | NA | "Data Sheet for Blower Discharge Sliencer" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-02 | 81 | APP | 2024-12-13 | 0 | 000899 | 2024-12-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5288 | 000900 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 0 | 131242-WST02-DS-I -0002-0 | 2024-12-13 | Datasheet for Electromagnetic Flowmeter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DS-0002 | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-27 | 102 | NAP | 2025-06-26 | 1 | 000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5289 | 000900 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0002 | 1 | 131242-WST02-DS-I -0002-1 | 2025-06-26 | Datasheet for Electromagnetic Flowmeter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-16 | 2025-07-28 | Approved with Comments | 2025-08-15 | NO | Overdue |  | 131242-WST02-DS-0002 | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-10 | 32 | AWC | 2025-06-26 | 1 | 000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | Approved with Comments | AWC | 2025-08-15 | Overdue | 0 | AWC | AWC
5290 | 000901 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0009 | 0 | 131242-WST02-QA-A-0009-0 | 2024-12-13 | Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh | For Information | 2025-01-13 | 2024-12-23 | For Information |  | YES | NA |  | 131242-WST02-QA-0009 | NA | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " && "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | 2024-12-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-27 | 10 | INF | 2025-09-15 | 0 | 000873&&000901&&001679 | 2024-12-04, 2024-12-13, 2025-09-15 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
5291 | 000902 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004_Withdraw | 0 | 131242-WSD11-QA-N-0004_Withdraw-0 | 2024-12-13 | Instrument Differential Pressure Switch SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | Rejected |  | YES | NA |  | 131242-WSD11-QA-0004_Withdraw | NA | "Instrument Differential Pressure Switch SAT" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-02 | 56 | REJ | 2024-12-13 | 0 | 000902 | 2024-12-13 | 00 | 1 | Rejected | REJ | 2025-02-27 | Overdue | 0 | REJ | REJ
5292 | 000903 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005_Withdraw | 0 | 131242-WSD11-QA-N-0005_Withdraw-0 | 2024-12-13 | Instrument Pressure Transmitter SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | Rejected |  | YES | NA |  | 131242-WSD11-QA-0005_Withdraw | NA | "Instrument Pressure Transmitter SAT" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-02 | 56 | REJ | 2024-12-13 | 0 | 000903 | 2024-12-13 | 00 | 1 | Rejected | REJ | 2025-02-27 | Overdue | 0 | REJ | REJ
5293 | 000904 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006_Withdraw | 0 | 131242-WSD11-QA-N-0006_Withdraw-0 | 2024-12-13 | Penumatic on/ off Valve SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | Rejected |  | YES | NA |  | 131242-WSD11-QA-0006_Withdraw | NA | "Penumatic on/ off Valve SAT" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-02 | 56 | REJ | 2024-12-13 | 0 | 000904 | 2024-12-13 | 00 | 1 | Rejected | REJ | 2025-02-27 | Overdue | 0 | REJ | REJ
5294 | 000905 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002_Withdraw | 0 | 131242-WSD11-QA-N-0002_Withdraw-0 | 2024-12-13 | Air Compresspor SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | Rejected |  | YES | NA |  | 131242-WSD11-QA-0002_Withdraw | NA | "Air Compresspor SAT" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-02 | 56 | REJ | 2024-12-13 | 0 | 000905 | 2024-12-13 | 00 | 1 | Rejected | REJ | 2025-02-27 | Overdue | 0 | REJ | REJ
5295 | 000906 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003_Withdraw | 0 | 131242-WSD11-QA-N-0003_Withdraw-0 | 2024-12-13 | Air Dryer SAT | Rejected, as requested by Contractor. | 2025-01-13 | 2025-02-07 | Rejected |  | YES | NA |  | 131242-WSD11-QA-0003_Withdraw | NA | "Air Dryer SAT" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-02 | 56 | REJ | 2024-12-13 | 0 | 000906 | 2024-12-13 | 00 | 1 | Rejected | REJ | 2025-02-27 | Overdue | 0 | REJ | REJ
5296 | 000907 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 0 | 131242-WST02-RT-E-0009-0 | 2024-12-16 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | Approved with Comments | 2025-03-10 | YES | Resubmitted |  | 131242-WST02-RT-0009 | NA | "SSN Harmonics Study Report" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-05 | 64 | AWC | 2026-01-20 | 1 | 000907 | 2024-12-16, 2026-01-20 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5297 | 000907 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0009 | 1 | 131242-WST02-RT-E-0009-1 | 2026-01-20 | SSN Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-RT-0009 | NA | "SSN Harmonics Study Report" | 2024-12-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | 1 | 000907 | 2024-12-16, 2026-01-20 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-09 |  | 0 | PEN | PEN
5298 | 000908 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0004 | 0 | 131242-WSD11-RT-E-0004-0 | 2024-12-16 | THP Harmonics Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-RT-0004 | NA | "H2S Dispersion Simulation And Risk Assessement Report" && "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" && "THP Harmonics Study Report" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-05 | 64 | AWC | 2025-09-03 | 1 | 000908&&001311&&001419 | 2024-12-16, 2025-05-19, 2025-07-01, 2025-07-28, 2025-09-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
5299 | 000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A | 131242-WSW41-DR-M-5128-A | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | 131242-WSW41-DR-5128 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-05 | 31 | AWC | 2025-03-13 | A.1 | 000909 | 2024-12-16, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5300 | 000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A | 131242-WSW41-DR-M-5129-A | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSW41-DR-5129 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-05 | 31 | AWC | 2025-06-25 | A.2 | 000909 | 2024-12-16, 2025-03-13, 2025-06-25 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5301 | 000909 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5130 | A | 131242-WSW41-DR-M-5130-A | 2024-12-16 | Pipe Support Standard- SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-14 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSW41-DR-5130 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-05 | 31 | AWC | 2025-03-13 | A.1 | 000909 | 2024-12-16, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5302 | 000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5128 | A.1 | 131242-WSW41-DR-M-5128-A.1 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted | 2nd priority (Shall update and submit under as built drawing) - comments to be cleared | 131242-WSW41-DR-5128 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000909 | 2024-12-16, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
5303 | 000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.1 | 131242-WSW41-DR-M-5129-A.1 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5129 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-06-25 | A.2 | 000909 | 2024-12-16, 2025-03-13, 2025-06-25 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5304 | 000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5130 | A.1 | 131242-WSW41-DR-M-5130-A.1 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5130 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000909 | 2024-12-16, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
5305 | 000909 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-M-5100-A.1 | 2025-03-13 | Pipe Support Standard- SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - General Notes" && "Pipe Support Standard- SWPR" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2026-01-19 | E | 000297&&000909&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
5306 | 000909 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5129 | A.2 | 131242-WSW41-DR-M-5129-A.2 | 2025-06-25 | Pipe Support Standard- SWPR | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DR-5129 | NA | "Pipe Support Standard- SWPR" | 2024-12-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-09 | 103 | AWC | 2025-06-25 | A.2 | 000909 | 2024-12-16, 2025-03-13, 2025-06-25 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
5307 | 000910 | 00 | David | Mech | NA | 131242 | WSW41 | DS | M | 5341 | 0 | 131242-WSW41-DS-M-5341-0 | 2024-12-17 | Data Sheet of Auto Lubrication Unit for centrifugal pump | Rev 0: Not approved - Revise and Resubmit | 2025-01-15 | 2025-01-20 | Not Approved | 2025-02-07 | NO | Overdue | In Progress | 131242-WSW41-DS-5341 | NA | "Data Sheet of Auto Lubrication Unit for centrifugal pump" | 2024-12-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 34 | NAP | 2024-12-17 | 0 | 000910 | 2024-12-17 | 00 | 1 | Not Approved | NAP | 2025-02-07 | Overdue | 0 | NAP | NAP
5308 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A | 131242-WST02-DR-M-5401-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted | In Progress | 131242-WST02-DR-5401 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing -TSS Analyser" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-10-23 | A | 000911&&001788 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5309 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5402 | A | 131242-WST02-DR-M-5402-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5402 | NA | "GA Drawing for FRP Tank" && "Standardize Support Design for Shelter 1" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-12-05 | A | 000911&&001881 | 2024-12-17, 2025-04-01, 2025-12-05 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5310 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5403 | A | 131242-WST02-DR-M-5403-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5403 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5311 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5404 | A | 131242-WST02-DR-M-5404-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5404 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5312 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5405 | A | 131242-WST02-DR-M-5405-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5405 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5313 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5416 | A | 131242-WST02-DR-M-5416-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5416 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5314 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5417 | A | 131242-WST02-DR-M-5417-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5417 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5315 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5419 | A | 131242-WST02-DR-M-5419-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5419 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5316 | 000911 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5420 | A | 131242-WST02-DR-M-5420-A | 2024-12-17 | GA Drawing for FRP Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5420 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing - DO Analyser" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 30 | AWC | 2025-10-23 | A | 000911&&001786 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5317 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5401 | A.1 | 131242-WST02-DR-M-5401-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5401 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing -TSS Analyser" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-10-23 | A | 000911&&001788 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
5318 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5402 | A.1 | 131242-WST02-DR-M-5402-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5402 | NA | "GA Drawing for FRP Tank" && "Standardize Support Design for Shelter 1" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-12-05 | A | 000911&&001881 | 2024-12-17, 2025-04-01, 2025-12-05 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
5319 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5403 | A.1 | 131242-WST02-DR-M-5403-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5403 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5320 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5404 | A.1 | 131242-WST02-DR-M-5404-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5404 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5321 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5405 | A.1 | 131242-WST02-DR-M-5405-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5405 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5322 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5406 | A.1 | 131242-WST02-DR-M-5406-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5406 | NA | "GA Drawing for FRP Tank" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 188 | APP | 2025-12-18 | E | 000911&&001914 | 2025-04-01, 2025-12-18 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | APP | APP
5323 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5407 | A.1 | 131242-WST02-DR-M-5407-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5407 | NA | "GA Drawing for FRP Tank" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2025-04-01 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
5324 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5408 | A.1 | 131242-WST02-DR-M-5408-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5408 | NA | "GA Drawing for FRP Tank" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2025-04-01 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
5325 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5416 | A.1 | 131242-WST02-DR-M-5416-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5416 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5326 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5417 | A.1 | 131242-WST02-DR-M-5417-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5417 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5327 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5418 | A.1 | 131242-WST02-DR-M-5418-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5418 | NA | "GA Drawing for FRP Tank" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2025-04-01 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
5328 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5419 | A.1 | 131242-WST02-DR-M-5419-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5419 | NA | "GA Drawing for FRP Tank" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2024-12-17, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5329 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5420 | A.1 | 131242-WST02-DR-M-5420-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5420 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing - DO Analyser" | 2024-12-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-10-23 | A | 000911&&001786 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
5330 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5421 | A.1 | 131242-WST02-DR-M-5421-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5421 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing - DO Analyser" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 188 | APP | 2025-10-23 | A | 000911&&001786 | 2025-04-01, 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
5331 | 000911 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5422 | A.1 | 131242-WST02-DR-M-5422-A.1 | 2025-04-01 | GA Drawing for FRP Tank | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5422 | NA | "GA Drawing for FRP Tank" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 188 | APP | 2025-04-01 | A.1 | 000911 | 2025-04-01 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
5332 | 000912 | 00 | Max | Project | NA | 131242 | WST02 | RT | S | 0001 | 0 | 131242-WST02-RT-S-0001-0 | 2024-12-18 | Safety Review Report for SSN Structures | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-16 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-01 | 29 | AWC | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
5333 | 000913 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0010 | 0 | 131242-WST02-QA-E-0010-0 | 2024-12-18 | FAT report for Earth cable, LV Power cable (Unwitnessed) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WST02-QA-0010 | NA | "FAT report for Earth cable, LV Power cable (Unwitnessed)" && "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 62 | AWC | 2025-09-26 | 0 | 000913&&000935&&001424&&001699 | 2024-12-18, 2024-12-31, 2025-07-02, 2025-09-26 | 00 | 4 | For Information | INF |  |  | 0 | AWC | AWC
5334 | 000914 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0028 | 0 | 131242-WSD11-QA-M-0028-0 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | Approved with Comments | 2025-04-07 | NO | Overdue |  | 131242-WSD11-QA-0028 | NA | "Vendor Manufacturing Inspection and test plan and FATprocedure for Desuperheater (CAMBI)" | 2024-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 90 | AWC | 2024-12-18 | 0 | 000914 | 2024-12-18 | 00 | 1 | Approved with Comments | AWC | 2025-04-07 | Overdue | 0 | AWC | AWC
5335 | 000915 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0024 | 0 | 131242-WSD11-QA-M-0024-0 | 2024-12-18 | Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-18 | Approved with Comments | 2025-04-07 | NO | Overdue |  | 131242-WSD11-QA-0024 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 90 | AWC | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | Rejected | REJ |  |  | 0 | AWC | AWC
5336 | 000916 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0013 | 0 | 131242-WSD11-CL-P-0013-0 | 2024-12-18 | THP G2D Plant Hydraulic Network Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WSD11-CL-0013 | NA | "THP G2D Plant Hydraulic Network Calculation" | 2024-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 130 | AWC | 2024-12-18 | 0 | 000916 | 2024-12-18 | 00 | 1 | Approved with Comments | AWC | 2025-05-15 | Overdue | 0 | AWC | AWC
5337 | 000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | A | 131242-WST02-DR-M-5501-A | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5501 | NA | "GA Drawing for Dosing Pump" && "Hookup Drawing for Magnetic Level Gauge" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-01 | 76 | AWC | 2026-01-20 | 0 | 000573&&000917&&001969 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5338 | 000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5511 | A | 131242-WST02-DR-M-5511-A | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5511 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 76 | AWC | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5339 | 000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5521 | A | 131242-WST02-DR-M-5521-A | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5521 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 76 | AWC | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5340 | 000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5531 | A | 131242-WST02-DR-M-5531-A | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5531 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 76 | AWC | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5341 | 000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5541 | A | 131242-WST02-DR-M-5541-A | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5541 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 76 | AWC | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5342 | 000917 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5551 | A | 131242-WST02-DR-M-5551-A | 2024-12-18 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5551 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 76 | AWC | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5343 | 000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5501 | B | 131242-WST02-DR-M-5501-B | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5501 | NA | "GA Drawing for Dosing Pump" && "Hookup Drawing for Magnetic Level Gauge" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 295 | PEN | 2026-01-20 | 0 | 000573&&000917&&001969 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
5344 | 000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5511 | B | 131242-WST02-DR-M-5511-B | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5511 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 295 | PEN | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-31 |  | 0 | PEN | PEN
5345 | 000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5521 | B | 131242-WST02-DR-M-5521-B | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5521 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 295 | PEN | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-31 |  | 0 | PEN | PEN
5346 | 000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5531 | B | 131242-WST02-DR-M-5531-B | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5531 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 295 | PEN | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-31 |  | 0 | PEN | PEN
5347 | 000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5541 | B | 131242-WST02-DR-M-5541-B | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5541 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 295 | PEN | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-31 |  | 0 | PEN | PEN
5348 | 000917 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5551 | B | 131242-WST02-DR-M-5551-B | 2025-06-15 | GA Drawing for Dosing Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5551 | NA | "GA Drawing for Dosing Pump" | 2024-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 295 | PEN | 2025-06-15 | B | 000917 | 2024-12-18, 2025-06-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-31 |  | 0 | PEN | PEN
5349 | 000918 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 0 | 131242-WST02-CL-BF-8000-0 | 2024-12-18 | Hydraulic Calculation (HOSEREEL) | Rev 0: Not approved - Revise and Resubmit | 2025-01-16 | 2025-01-24 | Not Approved | 2025-02-13 | YES | Resubmitted |  | 131242-WST02-CL-8000 | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-01 | 37 | NAP | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5350 | 000918 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8000 | 1 | 131242-WST02-CL-BF-8000-1 | 2025-02-19 | Hydraulic Calculation (HOSEREEL) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-11 | 2025-03-18 | Approved with Comments |  | YES | NA |  | 131242-WST02-CL-8000 | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-05 | 27 | AWC | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5351 | 000919 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 0 | 131242-WSW41-LT-PM-0053-0 | 2024-12-19 | CV of Team Member (T&C Manager) | Rejected as requested by Contractor | 2025-01-17 | 2024-12-27 | Rejected | 2025-01-16 | YES | Resubmitted |  | 131242-WSW41-LT-0053 | NA | "CV of Team Member (T&C Manager)" | 2024-12-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-08 | 8 | REJ | 2024-12-27 | 1 | 000919 | 2024-12-19, 2024-12-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
5352 | 000919 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0053 | 1 | 131242-WSW41-LT-PM-0053-1 | 2024-12-27 | CV of Team Member (T&C Manager) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-16 | 2025-03-21 | Approved with Comments | 2025-04-10 | NO | Overdue |  | 131242-WSW41-LT-0053 | NA | "CV of Team Member (T&C Manager)" | 2024-12-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-10 | 84 | AWC | 2024-12-27 | 1 | 000919 | 2024-12-19, 2024-12-27 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-10 | Overdue | 0 | AWC | AWC
5353 | 000920 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0006 | 0 | 131242-WSW41-MS-E-0006-0 | 2024-12-18 | Installation of Cable Container Support System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the attached file for comments. | 2025-01-16 | 2025-12-17 | Approved with Comments | 2026-01-06 | NO | Overdue |  | 131242-WSW41-MS-0006 | NA | "Installation of Cable Container Support System" && "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " && "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-01 | 364 | AWC | 2025-01-14 | 0 | 000122&&000920&&000975 | 2023-10-10, 2024-12-18, 2025-01-14 | 00 | 3 | Approved | APP |  |  | 0 | AWC | AWC
5354 | 000921 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 0 | 131242-WSW41-VI-M-2004-0 | 2024-12-19 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-17 | 2025-03-10 | Approved with Comments | 2025-03-28 | YES | Resubmitted |  | 131242-WSW41-VI-2004 | NA | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | 2024-12-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-08 | 81 | AWC | 2025-04-01 | 1 | 000921 | 2024-12-19, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5355 | 000921 | 01 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2004 | 1 | 131242-WSW41-VI-M-2004-1 | 2025-04-01 | Preliminary Design and Vendor Approval Document – Pressure Reducing Valve | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSW41-VI-2004 | NA | "Preliminary Design and Vendor Approval Document – Pressure Reducing Valve" | 2024-12-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | 1 | 000921 | 2024-12-19, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5356 | 000922 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1393 | 0 | 131242-WST02-DS-E-1393-0 | 2024-12-19 | Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-1393 | NA | "Sample Board Submission for SS Anchor Rod, Nut,Washers (Hilti) " | 2024-12-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-08 | 61 | AWC | 2024-12-19 | 0 | 000922 | 2024-12-19 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5357 | 000923 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1392 | 0 | 131242-WST02-DS-E-1392-0 | 2024-12-19 | Sample Board Submission for SS Cable Ladder, Accessories (United U-LI) | Rev 0: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2025-01-17 | 2025-02-18 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-1392 | NA | "Sample Board Submission for SS Cable Ladder, Accessories (United U-LI)" | 2024-12-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-08 | 61 | AWC | 2024-12-19 | 0 | 000923 | 2024-12-19 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5358 | 000924 | 00 | Yuen Fatt | Project | NA | 131242 | WSD11 | VI | M | 0032 | 0 | 131242-WSD11-VI-M-0032-0 | 2024-12-20 | Vendor Approval of Ducting - CES_Salcon Sdn Bhd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-20 | 2025-01-09 | Approved with Comments | 2025-01-29 | NO | Overdue |  | 131242-WSD11-VI-0032 | NA | "Vendor Approval of Ducting - CES_Salcon Sdn Bhd" | 2024-12-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-09 | 20 | AWC | 2024-12-20 | 0 | 000924 | 2024-12-20 | 00 | 1 | Approved with Comments | AWC | 2025-01-29 | Overdue | 0 | AWC | AWC
5359 | 000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5351 | A | 131242-WST02-DR-M-5351-A | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DR-5351 | NA | "Hookup Drawing - Capacitive Level Switch" && "PC Pump GA Drawing " | 2024-12-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-12 | 125 | AWC | 2025-10-23 | A | 000925&&001784 | 2024-12-23, 2025-10-23 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
5360 | 000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5361 | A | 131242-WST02-DR-M-5361-A | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-5361 | NA | "PC Pump GA Drawing " | 2024-12-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-12 | 125 | PEN | 2024-12-23 | A | 000925 | 2024-12-23 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-05-15 | Overdue | 0 | PEN | PEN
5361 | 000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5371 | A | 131242-WST02-DR-M-5371-A | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-5371 | NA | "PC Pump GA Drawing " && "SSN Instrument Hookup Drawing for Temperature Transmitter" | 2024-12-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-12 | 125 | PEN | 2025-09-10 | A | 000925&&001674 | 2024-12-23, 2025-09-10 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
5362 | 000925 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5381 | A | 131242-WST02-DR-M-5381-A | 2024-12-23 | PC Pump GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-21 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-5381 | NA | "Hookup Drawing - Autosampler" && "PC Pump GA Drawing " | 2024-12-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-12 | 125 | PEN | 2025-11-05 | 0 | 000925&&001822 | 2024-12-23, 2025-11-05 | 00 | 2 | Awaiting S.O.'s response | PEN |  |  | 0 | PEN | PEN
5363 | 000926 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0012 | 0 | 131242-WST02-VI-E-0012-0 | 2024-12-23 | Vendor Approval - Passive Harmonic Filter | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-01-21 | 2025-01-19 | Rejected |  | YES | NA |  | 131242-WST02-VI-0012 | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-06 | 27 | REJ | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | REJ | REJ
5364 | 000927 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-E-0011-0 | 2024-12-23 | FAT Report for Cable Ladder 1st Batch (United ULI) | Rev 0: Approved. | 2025-01-21 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WST02-QA-0011 | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-12 | 57 | APP | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
5365 | 000928 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0018 | 0 | 131242-WSW41-PC-W-0018-0 | 2024-12-24 | Payment Claim No.18 | Rev(0): Approved. Please refer to S.O. correspondence no. 273 dated 26 Dec 2024. | 2025-01-22 | 2025-01-08 | Approved |  | YES | NA |  | 131242-WSW41-PC-0018 | NA | "Payment Claim No.18" | 2024-12-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-13 | 15 | APP | 2024-12-24 | 0 | 000928 | 2024-12-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5366 | 000929 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0030 | 0 | 131242-WSW41-QA-M-0030-0 | 2024-12-24 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-22 | 2025-03-11 | Approved with Comments | 2025-03-31 | NO | Overdue |  | 131242-WSW41-QA-0030 | NA | "FAT Report for Control Cable and Power Cables" && "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" && "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" | 2024-12-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-13 | 77 | AWC | 2025-04-25 | 0 | 000929&&001237&&001253 | 2024-12-24, 2025-04-21, 2025-04-25 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5367 | 000930 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0031 | 0 | 131242-WSD11-QA-M-0031-0 | 2024-12-26 | Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) | Rev 0: Approved | 2025-01-23 | 2025-03-11 | Approved |  | YES | NA |  | 131242-WSD11-QA-0031 | NA | "Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) " && "SAT Report for WSD11-MCC-0101A&B" | 2024-12-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-15 | 75 | APP | 2025-05-23 | 0 | 000930&&001317 | 2024-12-26, 2025-05-23 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
5368 | 000931 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | A | 131242-WST02-DR-M-5601-A | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-24 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DR-5601 | NA | "Data Sheet for Parabolic Screen" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Screen General Arrangement Drawing" | 2024-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-16 | 67 | AWC | 2025-07-24 | A | 000931&&001051&&001528 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
5369 | 000931 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | B | 131242-WST02-DR-M-5601-B | 2025-05-26 | Screen General Arrangement Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5601 | NA | "Data Sheet for Parabolic Screen" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Screen General Arrangement Drawing" | 2024-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-09 | 315 | PEN | 2025-07-24 | A | 000931&&001051&&001528 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | PEN | PEN
5370 | 000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0011 | 0 | 131242-WSD11-OM-M-0011-0 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-OM-0011 | NA | "O&M manual for Air Dryer and Air Compressor" | 2024-12-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-16 | 73 | INF | 2024-12-27 | 0 | 000932 | 2024-12-27 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5371 | 000932 | 00 | YiBo | Mech | NA | 131242 | WSD11 | OM | M | 0010 | 0 | 131242-WSD11-OM-M-0010-0 | 2024-12-27 | O&M manual for Air Dryer and Air Compressor | Rev 0: For Information | 2025-01-24 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-OM-0010 | NA | "O&M manual for Air Dryer and Air Compressor" | 2024-12-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-16 | 73 | INF | 2024-12-27 | 0 | 000932 | 2024-12-27 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5372 | 000933 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601_WITHDRAW | A | 131242-WST02-DR-M-5601_WITHDRAW-A | 2024-12-27 | Screen General Arrangement Drawing | Rev 0: Rejected Submittal 931 include the same content and is already reviewed. | 2025-01-24 | 2025-03-04 | Rejected |  | YES | NA |  | 131242-WST02-DR-5601_WITHDRAW | NA | "Screen General Arrangement Drawing" | 2024-12-27 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-16 | 67 | REJ | 2024-12-27 | A | 000933 | 2024-12-27 | 00 | 1 | Rejected | REJ | 2025-03-24 | Overdue | 0 | REJ | REJ
5373 | 000934 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5136 | 0 | 131242-WST02-DR-M-5136-0 | 2024-12-31 | Blower Name Plate Drawing | Rev 0: Approved | 2025-01-28 | 2025-04-08 | Approved |  | YES | NA |  | 131242-WST02-DR-5136 | NA | "Blower Name Plate Drawing " | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-20 | 98 | APP | 2024-12-31 | 0 | 000934 | 2024-12-31 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5374 | 000935 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0010 | 0 | 131242-WST02-QA-A-0010-0 | 2024-12-31 | Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-01-28 | 2025-02-24 | Approved with Comments | 2025-03-14 | NO | Overdue |  | 131242-WST02-QA-0010 | NA | "FAT report for Earth cable, LV Power cable (Unwitnessed)" && "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-14 | 55 | AWC | 2025-09-26 | 0 | 000913&&000935&&001424&&001699 | 2024-12-18, 2024-12-31, 2025-07-02, 2025-09-26 | 00 | 4 | For Information | INF |  |  | 0 | AWC | AWC
5375 | 000936 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0012 | 0 | 131242-WSW41-QA-E-0012-0 | 2024-12-31 | FAT Report for Power Cable, Control Cable, MV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-28 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WSW41-QA-0012 | NA | "FAT Report for Power Cable, Control Cable, MV Cable" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-20 | 20 | AWC | 2026-01-28 | 0 | 000936&&001304&&001636&&001712 | 2024-12-31, 2025-05-18, 2025-09-30, 2026-01-28 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5376 | 000937 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0034 | 0 | 131242-WSW41-QA-M-0034-0 | 2024-12-31 | Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0034 | NA | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" && "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" && "Site Acceptance Test Procedure for 22KV HV Cable" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-20 | 98 | APP | 2025-07-08 | 0 | 000937&&001280&&001449 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
5377 | 000938 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0035 | 0 | 131242-WSW41-QA-M-0035-0 | 2024-12-31 | Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site) | Rev 0: Approved | 2025-01-28 | 2025-04-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0035 | NA | "Inspection and Test Plan for Cable Laying, Installation, Testing and Termination " && "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " && "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-20 | 98 | APP | 2025-07-08 | 0 | 000938&&001292&&001450 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
5378 | 000939 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0032 | 0 | 131242-WSW41-QA-M-0032-0 | 2025-01-02 | QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details) | Rev 0: Approved | 2025-01-30 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSW41-QA-0032 | NA | "Issue for Information-Monthly reinforcement steel delivery records for Mar 2024" && "QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details)" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-22 | 115 | APP | 2025-05-13 | 0 | 000939&&001278 | 2025-01-02, 2025-05-13 | 00 | 2 | For Information | INF |  |  | 0 | APP | APP
5379 | 000940 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0029 | 0 | 131242-WSW41-QA-M-0029-0 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating | Rev 0: Approved | 2025-01-30 | 2025-04-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0029 | NA | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" && "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" && "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" && "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-22 | 96 | APP | 2025-10-13 | 0 | 000940&&001217&&001238&&001745 | 2025-01-02, 2025-04-10, 2025-04-21, 2025-10-13 | 00 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
5380 | 000941 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 0 | 131242-WSW41-QA-M-0033-0 | 2025-01-02 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Rev 0: Not approved - Revise and Resubmit | 2025-01-30 | 2025-03-18 | Not Approved | 2025-04-07 | YES | Resubmitted |  | 131242-WSW41-QA-0033 | NA | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" && "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-22 | 75 | NAP | 2025-07-08 | 0 | 000941&&001279&&001448 | 2025-01-02, 2025-04-21, 2025-05-13, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5381 | 000941 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0033 | 1 | 131242-WSW41-QA-M-0033-1 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd) | Approved | 2025-05-09 | 2025-05-19 | Approved |  | YES | NA |  | 131242-WSW41-QA-0033 | NA | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" && "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 28 | APP | 2025-07-08 | 0 | 000941&&001279&&001448 | 2025-01-02, 2025-04-21, 2025-05-13, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
5382 | 000942 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 0 | 131242-WSW41-SH-M-1004-0 | 2025-01-02 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | Approved with Comments | 2025-03-04 | YES | Resubmitted | SO comment: Please furnish GA drawings in TWRP format. (vendor not able to provide) | 131242-WSW41-SH-1004 | NA | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-22 | 41 | AWC | 2025-06-16 | 1 | 000942 | 2025-01-02, 2025-06-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5383 | 000942 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1004 | 1 | 131242-WSW41-SH-M-1004-1 | 2025-06-16 | Piping Valve GA & Datasheet - Metallic Ball Valve (OVS) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WSW41-SH-1004 | NA | "Piping Valve GA & Datasheet - Metallic Ball Valve (OVS)" | 2025-01-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 80 | AWC | 2025-06-16 | 1 | 000942 | 2025-01-02, 2025-06-16 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
5384 | 000943 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DS | E | 0001 | 0 | 131242-WSW41-DS-E-0001-0 | 2025-01-03 | Datasheet for Unistrut Supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DS-0001 | NA | "Datasheet for Unistrut Supports" && "SSN and THP ICA, ELV and Communication Cable datasheet and specification" | 2024-11-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 69 | AWC | 2025-09-15 | 1 | 000857&&000943 | 2024-11-29, 2025-01-03, 2025-09-15 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5385 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1300 | A | 131242-WSW41-DR-E-1300-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1300 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5386 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1301 | A | 131242-WSW41-DR-E-1301-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1301 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5387 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1302 | A | 131242-WSW41-DR-E-1302-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1302 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5388 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1303 | A | 131242-WSW41-DR-E-1303-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1303 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5389 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1304 | A | 131242-WSW41-DR-E-1304-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1304 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5390 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1305 | A | 131242-WSW41-DR-E-1305-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1305 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5391 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1306 | A | 131242-WSW41-DR-E-1306-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1306 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5392 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1307 | A | 131242-WSW41-DR-E-1307-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1307 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5393 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1308 | A | 131242-WSW41-DR-E-1308-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1308 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5394 | 000944 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | DR | E | 1309 | A | 131242-WSW41-DR-E-1309-A | 2025-01-03 | Drawing Submission for Unistrut EICA Cable tray supports | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-01-31 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-DR-1309 | NA | "Drawing Submission for Unistrut EICA Cable tray supports " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-23 | 69 | AWC | 2025-01-03 | A | 000944 | 2025-01-03 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5395 | 000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-S-1600_ST611_BCA-D | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | For Information |  | YES | NA |  | 131242-WST02-DR-1600_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 5 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5396 | 000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | D | 131242-WST02-DR-S-1601_ST611_BCA-D | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | For Information |  | YES | NA |  | 131242-WST02-DR-1601_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 5 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5397 | 000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | D | 131242-WST02-DR-S-5600_ST611_BCA-D | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | For Information |  | YES | NA |  | 131242-WST02-DR-5600_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 5 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5398 | 000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-S-5601_ST611_BCA-D | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | For Information |  | YES | NA |  | 131242-WST02-DR-5601_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 5 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5399 | 000945 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | D | 131242-WST02-DR-S-5602_ST611_BCA-D | 2025-01-03 | BCA submission of ST611 (Pipe Support More Than 2m) | For information. | 2025-01-31 | 2025-01-08 | For Information |  | YES | NA |  | 131242-WST02-DR-5602_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 5 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5400 | 000946 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8004_ST609_BCA | E | 131242-WST00-DR-S-8004_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST00-DR-8004_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5401 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1100__ST609_BCA | E | 131242-WST02-DR-S-1100__ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-1100__ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5402 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0300__ST609_BCA | E | 131242-WST02-DR-S-0300__ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0300__ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5403 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0301_ST609_BCA | E | 131242-WST02-DR-S-0301_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0301_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5404 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0303_ST609_BCA | E | 131242-WST02-DR-S-0303_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0303_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5405 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0304_ST609_BCA | E | 131242-WST02-DR-S-0304_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0304_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5406 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0305_ST609_BCA | E | 131242-WST02-DR-S-0305_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0305_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5407 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0306_ST609_BCA | E | 131242-WST02-DR-S-0306_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0306_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5408 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0307_ST609_BCA | E | 131242-WST02-DR-S-0307_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0307_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5409 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0308_ST609_BCA | E | 131242-WST02-DR-S-0308_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0308_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5410 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0309_ST609_BCA | E | 131242-WST02-DR-S-0309_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-0309_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5411 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1101_ST609_BCA | E | 131242-WST02-DR-S-1101_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-1101_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5412 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1102_ST609_BCA | E | 131242-WST02-DR-S-1102_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-1102_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5413 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1103_ST609_BCA | E | 131242-WST02-DR-S-1103_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-1103_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5414 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2100_ST609_BCA | E | 131242-WST02-DR-S-2100_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-2100_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5415 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2101_ST609_BCA | E | 131242-WST02-DR-S-2101_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-2101_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5416 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2102_ST609_BCA | E | 131242-WST02-DR-S-2102_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-2102_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5417 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3100_ST609_BCA | E | 131242-WST02-DR-S-3100_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-3100_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5418 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3101_ST609_BCA | E | 131242-WST02-DR-S-3101_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-3101_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5419 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3102_ST609_BCA | E | 131242-WST02-DR-S-3102_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-3102_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5420 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5100_ST609_BCA | E | 131242-WST02-DR-S-5100_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-5100_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5421 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5101_ST609_BCA | E | 131242-WST02-DR-S-5101_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-5101_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5422 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5102_ST609_BCA | E | 131242-WST02-DR-S-5102_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-5102_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5423 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5103_ST609_BCA | E | 131242-WST02-DR-S-5103_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-5103_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5424 | 000946 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5104_ST609_BCA | E | 131242-WST02-DR-S-5104_ST609_BCA-E | 2025-01-03 | BCA Approval of ST609: SSN-PR-001/002/004 & 005 | For information. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WST02-DR-5104_ST609_BCA | NA | "BCA Approval of ST609: SSN-PR-001/002/004 & 005" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 9 | INF | 2025-01-03 | E | 000946 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5425 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | D | 131242-WSW41-DR-S-8002_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-8002_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5426 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | D | 131242-WSW41-DR-S-1100_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5427 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | D | 131242-WSW41-DR-S-0310_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-0310_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5428 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | D | 131242-WSW41-DR-S-0311_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-0311_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5429 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | C | 131242-WSW41-DR-S-0312_ST614_BCA-C | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-0312_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5430 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | C | 131242-WSW41-DR-S-0313_ST614_BCA-C | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-0313_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5431 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | C | 131242-WSW41-DR-S-0314_ST614_BCA-C | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-0314_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5432 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | C | 131242-WSW41-DR-S-0315_ST614_BCA-C | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-0315_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5433 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | D | 131242-WSW41-DR-S-1101_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1101_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5434 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | D | 131242-WSW41-DR-S-1102_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1102_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5435 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | D | 131242-WSW41-DR-S-1103_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1103_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5436 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | D | 131242-WSW41-DR-S-1104_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1104_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5437 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1105_ST614_BCA | D | 131242-WSW41-DR-S-1105_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1105_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 40 | INF | 2025-01-03 | D | 000947 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5438 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1106_ST614_BCA | D | 131242-WSW41-DR-S-1106_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-1106_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-23 | 40 | INF | 2025-01-03 | D | 000947 | 2025-01-03 | 00 | 1 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5439 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | D | 131242-WSW41-DR-S-2100_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-2100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5440 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | D | 131242-WSW41-DR-S-2101_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-2101_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5441 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | D | 131242-WSW41-DR-S-3100_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-3100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5442 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | D | 131242-WSW41-DR-S-5100_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-5100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5443 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | D | 131242-WSW41-DR-S-5101_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-5101_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5444 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | D | 131242-WSW41-DR-S-5102_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-5102_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5445 | 000947 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | D | 131242-WSW41-DR-S-5103_ST614_BCA-D | 2025-01-03 | BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) | For information. | 2025-01-31 | 2025-02-12 | For Information |  | YES | NA |  | 131242-WSW41-DR-5103_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-17 | 40 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF | 2025-03-04 | Overdue | 0 | INF | INF
5446 | 000948 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | RT | C | 0014 | 0 | 131242-WSW41-RT-C-0014-0 | 2025-01-03 | Bored Piling Pile Eccentricity Reports (ECC 19 & 20) | For Information. Please refer comment sheet. | 2025-01-31 | 2025-01-12 | For Information |  | YES | NA |  | 131242-WSW41-RT-0014 | NA | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" && "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-17 | 9 | INF | 2025-01-03 | 0 | 000552&&000948 | 2024-07-09, 2024-07-13, 2025-01-03 | 00, 01 | 3 | For Information | INF | 2025-01-30 | Overdue | 0 | INF | INF
5447 | 000949 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 0 | 131242-WSW41-MS-E-0007-0 | 2025-01-03 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-01-31 | 2025-01-24 | Not Approved | 2025-02-13 | YES | Resubmitted |  | 131242-WSW41-MS-0007 | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 21 | NAP | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | NAP | NAP
5448 | 000949 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0007 | 1 | 131242-WSW41-MS-E-0007-1 | 2025-02-27 | Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WSW41-MS-0007 | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-13 | 59 | AWC | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
5449 | 000950 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0005 | 0 | 131242-WST02-VI-A-0005-0 | 2025-01-03 | Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd. | Approved | 2025-01-31 | 2025-01-16 | Approved |  | YES | NA |  | 131242-WST02-VI-0005 | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-17 | 13 | APP | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
5450 | 000951 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0011 | 0 | 131242-WST02-QA-A-0011-0 | 2025-01-04 | Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-01-31 | 2025-02-03 | Approved with Comments | 2025-02-21 | NO | Overdue |  | 131242-WST02-QA-0011 | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-18 | 30 | AWC | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
5451 | 000952 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0021 | 0 | 131242-WSW41-QA-C-0021-0 | 2025-01-04 | Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024 | For information. | 2025-01-31 | 2025-01-24 | For Information |  | YES | NA |  | 131242-WSW41-QA-0021 | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-18 | 20 | INF | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | INF | INF
5452 | 000953 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1003 | 0 | 131242-WSW41-SH-M-1003-0 | 2025-01-07 | C4B Knife Gate Valve List & Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-04 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSW41-SH-1003 | NA | "C4B Knife Gate Valve List & Datasheet" | 2025-01-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 91 | AWC | 2025-01-07 | 0 | 000953 | 2025-01-07 | 00 | 1 | Approved with Comments | AWC | 2025-04-28 | Overdue | 0 | AWC | AWC
5453 | 000954 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 0 | 131242-WSW41-VI-M-1013-0 | 2025-01-07 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 0: Not approved - Revise and Resubmit | 2025-02-04 | 2025-02-12 | Rejected | 2025-03-04 | YES | Resubmitted |  | 131242-WSW41-VI-1013 | NA | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 36 | REJ | 2025-06-17 | 2 | 000954 | 2025-01-07, 2025-03-27, 2025-06-17 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | REJ | REJ
5454 | 000954 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 1 | 131242-WSW41-VI-M-1013-1 | 2025-03-27 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-04-11 | Approved with Comments | 2025-05-01 | YES | Resubmitted | Pending vendor clarification - Breen | 131242-WSW41-VI-1013 | NA | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 15 | AWC | 2025-06-17 | 2 | 000954 | 2025-01-07, 2025-03-27, 2025-06-17 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
5455 | 000954 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1013 | 2 | 131242-WSW41-VI-M-1013-2 | 2025-06-17 | Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN) | Rev 2: Approved | 2025-07-07 | 2025-07-28 | Approved |  | YES | NA |  | 131242-WSW41-VI-1013 | NA | "Preliminary Design and Vendor Approval Metallic Non-Return Check Valves (BREEN)" | 2025-01-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-01 | 41 | APP | 2025-06-17 | 2 | 000954 | 2025-01-07, 2025-03-27, 2025-06-17 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
5456 | 000955 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0036 | 0 | 131242-WSW41-QA-M-0036-0 | 2025-01-07 | FAT/MDR Report for Side Manway (9 no;) | Rev 0: Approved | 2025-02-04 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WSW41-QA-0036 | NA | "FAT/MDR Report for Side Manway (9 no;)" && "Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024" | 2025-01-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-27 | 77 | APP | 2025-05-13 | 0 | 000955&&001293 | 2025-01-07, 2025-05-13 | 00 | 2 | For Information | INF |  |  | 0 | APP | APP
5457 | 000956 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0051 | 0 | 131242-WSW41-CD-IM-0051-0 | 2025-01-08 | Submission of BIM Coordination VCM Model (Dec 2024) | For Information. Score= 71/100 | 2025-02-05 | 2025-01-24 | For Information |  | YES | NA |  | 131242-WSW41-CD-0051 | NA | "Submission of BIM Coordination VCM Model (Dec 2024)" | 2025-01-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-28 | 16 | INF | 2025-01-08 | 0 | 000956 | 2025-01-08 | 00 | 1 | For Information | INF | 2025-02-13 | Overdue | 0 | INF | INF
5458 | 000957 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0038 | 0 | 131242-WSW41-MI-C-0038-0 | 2025-01-09 | CSA Meeting Minutes 0038_12122024 | For information. | 2025-02-06 | 2025-01-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0038 | NA | "CSA Meeting Minutes 0038_12122024" | 2025-01-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-29 | 15 | INF | 2025-01-09 | 0 | 000957 | 2025-01-09 | 00 | 1 | For Information | INF | 2025-02-13 | Overdue | 0 | INF | INF
5459 | 000958 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0038 | 0 | 131242-WST02-QA-M-0038-0 | 2025-01-09 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch) | Rev 0: Approved | 2025-02-06 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WST02-QA-0038 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" && "Factory Acceptance Test Report for TSS Analyser - Optical" && "Inspection Test Plan for Low Voltage Switchgear" | 2025-01-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-29 | 75 | APP | 2025-07-22 | 0 | 000958&&001490&&001521 | 2025-01-09, 2025-07-21, 2025-07-22 | 00 | 3 | Approved | APP |  |  | 0 | APP | APP
5460 | 000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0006 | A | 131242-WSD11-CL-S-0006-A | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-CL-0006 | NA | "Air Compressor Pressure Loss Calculation" && "Support design for compressed Air system <2m" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-24 | 39 | AWC | 2025-01-10 | A | 000597&&000959 | 2024-07-30, 2024-09-30, 2025-01-10 | 00, 01 | 3 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5461 | 000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1602 | A | 131242-WSD11-DR-S-1602-A | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-DR-1602 | NA | "Support design for compressed Air system <2m" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-01-10 | A | 000959 | 2025-01-10 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5462 | 000959 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5602 | A | 131242-WSD11-DR-S-5602-A | 2025-01-10 | Support design for compressed Air system <2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-DR-5602 | NA | "Support design for compressed Air system <2m" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-01-10 | A | 000959 | 2025-01-10 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5463 | 000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007 | A | 131242-WSD11-CL-S-0007-A | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-CL-0007 | NA | "G2D Pipe Support_Report from QPD" && "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-24 | 39 | AWC | 2026-01-12 | 1 | 000664&&000960&&001945 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5464 | 000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600 | A | 131242-WSD11-DR-S-5600-A | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-DR-5600 | NA | "Support design for compressed Air system >2m" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-01-10 | A | 000960 | 2025-01-10 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5465 | 000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601 | A | 131242-WSD11-DR-S-5601-A | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-DR-5601 | NA | "Support design for compressed Air system >2m" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-01-10 | A | 000960 | 2025-01-10 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5466 | 000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600 | A | 131242-WSD11-DR-S-1600-A | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-DR-1600 | NA | "Support design for compressed Air system >2m" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-01-10 | A | 000960 | 2025-01-10 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5467 | 000960 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601 | A | 131242-WSD11-DR-S-1601-A | 2025-01-10 | Support design for compressed Air system >2m | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSD11-DR-1601 | NA | "Support design for compressed Air system >2m" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-01-10 | A | 000960 | 2025-01-10 | 00 | 1 | Approved with Comments | AWC | 2025-03-10 | Overdue | 0 | AWC | AWC
5468 | 000961 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 0 | 131242-WSD11-DS-I-0004-0 | 2025-01-10 | Datasheet for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | Approved with Comments | 2025-03-05 | YES | Resubmitted |  | 131242-WSD11-DS-0004 | NA | "Datasheet for Pressure Transmitter" | 2025-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 34 | AWC | 2025-03-17 | 1 | 000961 | 2025-01-10, 2025-03-17 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5469 | 000961 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0004 | 1 | 131242-WSD11-DS-I-0004-1 | 2025-03-17 | Datasheet for Pressure Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | Approved with Comments | 2025-05-27 | NO | Overdue |  | 131242-WSD11-DS-0004 | NA | "Datasheet for Pressure Transmitter" | 2025-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 51 | AWC | 2025-03-17 | 1 | 000961 | 2025-01-10, 2025-03-17 | 00, 01 | 2 | Approved with Comments | AWC | 2025-05-27 | Overdue | 0 | AWC | AWC
5470 | 000962 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 0 | 131242-WSD11-QA-M-0039-0 | 2025-01-10 | FAT report for THP Train 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-07 | 2025-02-20 | Approved with Comments | 2025-03-12 | YES | Resubmitted |  | 131242-WSD11-QA-0039 | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 41 | AWC | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | Rejected | REJ |  |  | 0 | AWC | AWC
5471 | 000962 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 1 | 131242-WSD11-QA-M-0039-1 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rejected, as requested by contractor via email dated 8 Dec 2025. They will resubmit ZIP files with clear descriptive folder names instead of individual file | 2025-12-26 | 2025-12-08 | Rejected | 2025-12-26 | YES | Resubmitted |  | 131242-WSD11-QA-0039 | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-22 | 0 | REJ | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | Rejected | REJ |  |  | 0 | REJ | REJ
5472 | 000962 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 2 | 131242-WSD11-QA-M-0039-2 | 2025-12-08 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2025-12-23 | Approved with Comments | 2026-01-12 | YES | Resubmitted |  | 131242-WSD11-QA-0039 | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-22 | 15 | AWC | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | Rejected | REJ |  |  | 0 | AWC | AWC
5473 | 000962 | 03 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0039 | 3 | 131242-WSD11-QA-M-0039-3 | 2026-01-06 | FAT report for THP Train 1 (Part-1) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0039 | NA | "FAT report for THP Train 1 (Part-1)" | 2025-01-10 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | 3 | 000962 | 2025-01-10, 2025-12-08, 2026-01-06 | 00, 01, 02, 03 | 4 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
5474 | 000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611_BCA | D | 131242-WST02-DR-S-5601_ST611_BCA-D | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | For Information |  | YES | NA |  | 131242-WST02-DR-5601_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-25 | 27 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-27 | Overdue | 0 | INF | INF
5475 | 000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST611_BCA | D | 131242-WST02-DR-S-5602_ST611_BCA-D | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | For Information |  | YES | NA |  | 131242-WST02-DR-5602_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-25 | 27 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-27 | Overdue | 0 | INF | INF
5476 | 000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611_BCA | D | 131242-WST02-DR-S-1600_ST611_BCA-D | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | For Information |  | YES | NA |  | 131242-WST02-DR-1600_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-25 | 27 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-27 | Overdue | 0 | INF | INF
5477 | 000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611_BCA | D | 131242-WST02-DR-S-1601_ST611_BCA-D | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | For Information |  | YES | NA |  | 131242-WST02-DR-1601_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-25 | 27 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-27 | Overdue | 0 | INF | INF
5478 | 000963 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611_BCA | D | 131242-WST02-DR-S-5600_ST611_BCA-D | 2025-01-11 | BCA Approval of ST611 (Pipe Support more than 2m) | For information. | 2025-02-07 | 2025-02-07 | For Information |  | YES | NA |  | 131242-WST02-DR-5600_ST611_BCA | NA | "BCA Approval of ST611 (Pipe Support more than 2m)" && "BCA submission of ST611 (Pipe Support More Than 2m)" | 2025-01-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-01-25 | 27 | INF | 2025-01-11 | D | 000945&&000963 | 2025-01-03, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-27 | Overdue | 0 | INF | INF
5479 | 000964 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 0 | 131242-WSD11-SP-I-0004-0 | 2025-01-11 | Functional Design Specification (Air Compressor System) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WSD11-SP-0004 | NA | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-31 | 52 | AWC | 2025-08-12 | 2 | 000964 | 2025-01-11, 2025-06-04, 2025-08-12 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5480 | 000964 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 1 | 131242-WSD11-SP-I-0004-1 | 2025-06-04 | Functional Design Specification (Air Compressor System) | R1: Approved with comments. No resubmittal is required at this moment. The resubmittal is required only if any changes during the detailing. | 2025-06-24 | 2025-07-02 | Approved with Comments |  | YES | NA |  | 131242-WSD11-SP-0004 | NA | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-18 | 28 | AWC | 2025-08-12 | 2 | 000964 | 2025-01-11, 2025-06-04, 2025-08-12 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5481 | 000964 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0004 | 2 | 131242-WSD11-SP-I-0004-2 | 2025-08-12 | Functional Design Specification (Air Compressor System) | R2: Approved with comments. However, no resubmission at this stage unless there is a change to the document. | 2025-09-01 | 2025-10-08 | Approved with Comments |  | YES | NA |  | 131242-WSD11-SP-0004 | NA | "Functional Design Specification (Air Compressor System)" | 2025-01-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-26 | 57 | AWC | 2025-08-12 | 2 | 000964 | 2025-01-11, 2025-06-04, 2025-08-12 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
5482 | 000965 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0036 | 0 | 131242-WSW41-MI-P-0036-0 | 2025-01-11 | Process & MEICA Meeting Minutes 0036_21112024 | For Information | 2025-02-07 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSW41-MI-0036 | NA | "CSA Meeting Minutes 0036_14112024" && "Process & MEICA Meeting Minutes 0036_21112024" | 2024-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-25 | 5 | INF | 2025-01-11 | 0 | 000851&&000965 | 2024-11-28, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5483 | 000966 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0037 | 0 | 131242-WSW41-MI-P-0037-0 | 2025-01-11 | Process & MEICA Meeting Minutes 0037_05122024 | For Information | 2025-02-07 | 2025-01-16 | For Information |  | YES | NA |  | 131242-WSW41-MI-0037 | NA | "CSA Meeting Minutes 0037_28112024" && "Process & MEICA Meeting Minutes 0037_05122024" | 2024-12-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-25 | 5 | INF | 2025-01-11 | 0 | 000892&&000966 | 2024-12-13, 2025-01-11 | 00 | 2 | For Information | INF | 2025-02-05 | Overdue | 0 | INF | INF
5484 | 000967 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 0 | 131242-WST02-DS-I-0005-0 | 2025-01-11 | Datasheet for pH Transmitter & Sensor | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-07 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DS-0005 | NA | "Datasheet for pH Transmitter & Sensor " | 2025-01-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-31 | 33 | NAP | 2025-08-15 | 1 | 000967 | 2025-01-11, 2025-08-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5485 | 000967 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0005 | 1 | 131242-WST02-DS-I-0005-1 | 2025-08-15 | Datasheet for pH Transmitter & Sensor | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DS-0005 | NA | "Datasheet for pH Transmitter & Sensor " | 2025-01-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-29 | 103 | AWC | 2025-08-15 | 1 | 000967 | 2025-01-11, 2025-08-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-16 | Overdue | 0 | AWC | AWC
5486 | 000968 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 0 | 131242-WST02-QA-A-0012-0 | 2025-01-11 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-02-24 | Not Approved | 2025-03-14 | YES | Resubmitted |  | 131242-WST02-QA-0012 | NA | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-31 | 44 | NAP | 2025-04-23 | 1 | 000968 | 2025-01-11, 2025-03-10, 2025-04-23 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5487 | 000968 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-A-0012-1 | 2025-03-10 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-14 | Not Approved | 2025-05-02 | YES | Resubmitted |  | 131242-WST02-QA-0012 | NA | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 35 | NAP | 2025-04-23 | 1 | 000968 | 2025-01-11, 2025-03-10, 2025-04-23 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5488 | 000968 | 02 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0012 | 1 | 131242-WST02-QA-A-0012-1 | 2025-04-23 | Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd | Rev.2: Not Approved. Please refer to comment sheet for resubmission | 2025-05-13 | 2025-04-28 | Not Approved | 2025-05-16 | NO | Overdue |  | 131242-WST02-QA-0012 | NA | "Material Submission HIMEX RAISED FLOOR SYSTEM (HFS1000) under HEMSCO (S) Pte Ltd" | 2025-01-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-07 | 5 | NAP | 2025-04-23 | 1 | 000968 | 2025-01-11, 2025-03-10, 2025-04-23 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-05-16 | Overdue | 0 | NAP | NAP
5489 | 000969 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | I | 0005 | 0 | 131242-WSW41-QA-I-0005-0 | 2025-01-13 | FAT report for Power cable, Control Cable, Instrument Cable (Witness) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-02-10 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WSW41-QA-0005 | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 7 | AWC | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
5490 | 000970 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0013 | 0 | 131242-WSW41-QA-E-0013-0 | 2025-01-13 | FAT report for SS Unistrut Support, Accessories (HDMANN) | Rev 0: Approved with comments. Resubmission not required. Please refer to attached file for comments as noted. | 2025-02-10 | 2025-03-02 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-27 | 48 | AWC | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5491 | 000971 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0014 | 0 | 131242-WSW41-QA-E-0014-0 | 2025-01-13 | FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-27 | 36 | APP | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
5492 | 000972 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0015 | 0 | 131242-WST02-QA-E-0015-0 | 2025-01-13 | FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN) | Rev 0: Approved. | 2025-02-10 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WST02-QA-0015 | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-02 | 36 | APP | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
5493 | 000973 | 00 | Franklin | CSA | NA | 131242 | WSW41 | CN | S | 0002 | 0 | 131242-WSW41-CN-S-0002-0 | 2025-01-13 | Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-10 | 2025-02-24 | Approved with Comments | 2025-03-14 | NO | Overdue |  | 131242-WSW41-CN-0002 | NA | "Proposed change of Manufacturer for SSN Aeration blowers" && "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" | 2023-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-27 | 42 | AWC | 2025-01-13 | 0 | 000116&&000973 | 2023-10-06, 2025-01-13 | 00 | 2 | Approved with Comments | AWC | 2025-03-14 | Overdue | 0 | AWC | AWC
5494 | 000974 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0040 | 0 | 131242-WSW41-QA-M-0040-0 | 2025-01-14 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) | Rev 0: Approved | 2025-02-11 | 2025-03-18 | Approved |  | YES | NA |  | 131242-WSW41-QA-0040 | NA | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " && "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | 2025-01-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-03 | 63 | APP | 2025-08-18 | 1 | 000974&&001454&&001491 | 2025-01-14, 2025-07-09, 2025-07-21, 2025-08-18 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
5495 | 000975 | 00 | K. Balaji | Mech | NA | 131242 | WSW41 | MS | M | 0006 | 0 | 131242-WSW41-MS-M-0006-0 | 2025-01-14 | Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 | Rev 0: Approved | 2025-02-11 | 2025-04-11 | Approved |  | YES | NA |  | 131242-WSW41-MS-0006 | NA | "Installation of Cable Container Support System" && "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " && "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-28 | 87 | APP | 2025-01-14 | 0 | 000122&&000920&&000975 | 2023-10-10, 2024-12-18, 2025-01-14 | 00 | 3 | Approved | APP |  |  | 0 | APP | APP
5496 | 000976 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 0 | 131242-WSD11-QA-M-0041-0 | 2025-01-15 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-12 | 2025-02-20 | Approved with Comments | 2025-03-12 | YES | Resubmitted |  | 131242-WSD11-QA-0041 | NA | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 36 | AWC | 2026-01-06 | 2 | 000976 | 2025-01-15, 2025-12-09, 2026-01-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5497 | 000976 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 1 | 131242-WSD11-QA-M-0041-1 | 2025-12-09 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-29 | 2025-12-23 | Approved with Comments | 2026-01-12 | YES | Resubmitted |  | 131242-WSD11-QA-0041 | NA | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-23 | 14 | AWC | 2026-01-06 | 2 | 000976 | 2025-01-15, 2025-12-09, 2026-01-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5498 | 000976 | 02 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0041 | 2 | 131242-WSD11-QA-M-0041-2 | 2026-01-06 | FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0041 | NA | "FAT report for THP Train 2 (Part-1) (Flash tank module, Flash tank pump skid module, Process gas skid module, Reactor feed pump skid module, Reactor 1 to 4 module, Lower cage module)" | 2025-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | 2 | 000976 | 2025-01-15, 2025-12-09, 2026-01-06 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-23 |  | 0 | PEN | PEN
5499 | 000977 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0024 | 0 | 131242-WSW41-SP-C-0024-0 | 2025-01-15 | Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-12 | 2025-03-04 | Approved with Comments | 2025-03-24 | NO | Overdue |  | 131242-WSW41-SP-0024 | NA | "Steel Structure – Welding Procedure Specifications (Sanhe - Fujian Tung Kang Steel Co., Ltd)" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 48 | AWC | 2025-01-15 | 0 | 000977 | 2025-01-15 | 00 | 1 | Approved with Comments | AWC | 2025-03-24 | Overdue | 0 | AWC | AWC
5500 | 000978 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0043 | 0 | 131242-WST02-QA-M-0043-0 | 2025-01-16 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch) | Rev 0: Approved | 2025-02-13 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WST02-QA-0043 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch)" && "Factory Acceptance Test Report for PH Analyser" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-05 | 68 | APP | 2025-07-30 | 0 | 000978&&001540 | 2025-01-16, 2025-07-30 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
5501 | 000979 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0019 | 0 | 131242-WSW41-PS-PM-0019-0 | 2025-01-16 | Monthly Progress Presentation No. 19 (1224) | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 | For Information | 2025-02-06 | YES | Resubmitted |  | 131242-WSW41-PS-0019 | NA | "Incentive/ Disincentive Audit Scheme for Nov 2024" && "Monthly Progress Presentation No. 19 (1224)" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 3 | INF | 2025-03-17 | 0 | 000979&&001128 | 2025-01-16, 2025-03-17 | 00 | 2 | Approved | APP |  |  | 0 | INF | INF
5502 | 000980 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0019 | 0 | 131242-WSW41-MI-PM-0019-0 | 2025-01-16 | Monthly Progress Meeting Minutes 0019_20241217 | Rev. 0 - For Information | 2025-02-13 | 2025-01-19 | For Information | 2025-02-06 | YES | Resubmitted |  | 131242-WSW41-MI-0019 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 3 | INF | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | For Information | INF | 2025-02-06 | Overdue | 0 | INF | INF
5503 | 000981 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0002 | 0 | 131242-WSW41-RT-HS-0002-0 | 2025-01-16 | Final Investigation Report (Incident on Leg Injury) | For Information | 2025-02-13 | 2025-12-23 | For Information |  | YES | NA |  | 131242-WSW41-RT-0002 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-30 | 341 | INF | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | For Information | INF | 2026-01-12 | Overdue | 0 | INF | INF
5504 | 000982 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0022 | 0 | 131242-WSW41-QA-C-0022-0 | 2025-01-16 | Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2025-02-13 | 2025-02-24 | Approved with Comments | 2025-03-14 | NO | Overdue |  | 131242-WSW41-QA-0022 | NA | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" && "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" && "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2024-11-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 39 | AWC | 2025-02-18 | 0 | 000795&&000982&&001055 | 2024-11-01, 2025-01-16, 2025-02-18 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5505 | 000983 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 0 | 131242-WSD11-QA-M-0042-0 | 2025-01-16 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-02-20 | Approved with Comments | 2025-03-12 | YES | Resubmitted |  | 131242-WSD11-QA-0042 | NA | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 35 | AWC | 2025-12-02 | 1 | 000983 | 2025-01-16, 2025-12-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5506 | 000983 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0042 | 1 | 131242-WSD11-QA-M-0042-1 | 2025-12-02 | FAT report for THP Sludge cooler A Stage 1 (Part-1) | Rev 1: Approved | 2025-12-22 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSD11-QA-0042 | NA | "FAT report for THP Sludge cooler A Stage 1 (Part-1)" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 21 | APP | 2025-12-02 | 1 | 000983 | 2025-01-16, 2025-12-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5507 | 000984 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 0 | 131242-WSW41-VI-M-1014-0 | 2025-01-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-13 | 2025-01-20 | Approved with Comments | 2025-02-07 | YES | Resubmitted |  | 131242-WSW41-VI-1014 | NA | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 4 | AWC | 2025-06-16 | 1 | 000984 | 2025-01-16, 2025-06-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5508 | 000984 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1014 | 1 | 131242-WSW41-VI-M-1014-1 | 2025-06-16 | Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-04 | 2025-06-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1014 | NA | "Preliminary Design and Vendor Approval of Metallic Butterfly Valves (OVS)" | 2025-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-30 | 7 | AWC | 2025-06-16 | 1 | 000984 | 2025-01-16, 2025-06-16 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
5509 | 000985 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0044 | 0 | 131242-WSW41-QA-M-0044-0 | 2025-01-17 | Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-14 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WSW41-QA-0044 | NA | " Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025" && "Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd " | 2025-01-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-06 | 100 | AWC | 2025-09-30 | 0 | 000985&&001708 | 2025-01-17, 2025-09-30 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5510 | 000986 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0020 | 0 | 131242-WSW41-RT-PM-0020-0 | 2025-01-19 | C4B Monthly Progress Report Number No.20 (12 24) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-02-14 | 2025-02-03 | Approved with Comments | 2025-02-21 | NO | Overdue |  | 131242-WSW41-RT-0020 | NA | "C4B Monthly Progress Report Number No.20 (12 24) " | 2025-01-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-08 | 15 | AWC | 2025-01-19 | 0 | 000986 | 2025-01-19 | 00 | 1 | Approved with Comments | AWC | 2025-02-21 | Overdue | 0 | AWC | AWC
5511 | 000987 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0024 | 0 | 131242-WSW41-MS-C-0024-0 | 2025-01-20 | MSRA and SWP for Waterproofing Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-17 | 2025-02-17 | Approved with Comments | 2025-03-07 | NO | Overdue |  | 131242-WSW41-MS-0024 | NA | "MSRA and SWP for Waterproofing Work" | 2025-01-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 28 | AWC | 2025-01-20 | 0 | 000987 | 2025-01-20 | 00 | 1 | Approved with Comments | AWC | 2025-03-07 | Overdue | 0 | AWC | AWC
5512 | 000988 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 0 | 131242-WSW41-VI-M-2005-0 | 2025-01-20 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 | Approved with Comments | 2025-03-04 | YES | Resubmitted |  | 131242-WSW41-VI-2005 | NA | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 23 | AWC | 2025-06-18 | 1 | 000988 | 2025-01-20, 2025-06-18 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5513 | 000988 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2005 | 1 | 131242-WSW41-VI-M-2005-1 | 2025-06-18 | Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-08 | 2026-01-07 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-2005 | NA | "Preliminary Design and Vendor Approval of Air Flow Control Valve (Emile Egger & Cie SA)" | 2025-01-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-02 | 203 | AWC | 2025-06-18 | 1 | 000988 | 2025-01-20, 2025-06-18 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-27 | Overdue | 0 | AWC | AWC
5514 | 000989 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 0 | 131242-WSW41-VI-M-2002-0 | 2025-01-20 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-01-24 | Approved with Comments | 2025-02-13 | YES | Resubmitted |  | 131242-WSW41-VI-2002 | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 4 | AWC | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5515 | 000989 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002-1 | 2025-02-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-VI-2002 | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 36 | AWC | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5516 | 000989 | 02 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002-1 | 2025-04-17 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-05-07 | 2025-05-21 | Approved with Comments | 2025-06-10 | YES | Resubmitted |  | 131242-WSW41-VI-2002 | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 34 | AWC | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5517 | 000989 | 03 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2002 | 1 | 131242-WSW41-VI-M-2002-1 | 2025-08-25 | Preliminary Design and Vendor Approval of Flow Control Valve (KSB) | Approved with Comments | 2025-09-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-VI-2002 | NA | "Preliminary Design and Vendor Approval of Flow Control Valve (KSB)" | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-09-08 | 224 | PEN | 2025-08-25 | 1 | 000989 | 2025-01-20, 2025-02-25, 2025-04-17, 2025-08-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-10 |  | 0 | PEN | PEN
5518 | 000990 | 00 | Prachi | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-P-0014-0 | 2025-01-20 | THP Steam Pressure Loss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-CL-0014 | NA | "Process Gas Hydraulic Calculation" && "THP Steam Pressure Loss Calculation" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-09 | 259 | APP | 2025-01-26 | 0 | 000990&&001007 | 2025-01-20, 2025-01-26 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
5519 | 000991 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0011 | 0 | 131242-WST02-CL-P-0011-0 | 2025-01-20 | SSN Compressed Air Headloss Calculation | Rev 0: Approved. Please include PE Endorsement. | 2025-02-17 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-CL-0011 | NA | "SSN Compressed Air Headloss Calculation" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-09 | 259 | APP | 2025-01-20 | 0 | 000991 | 2025-01-20 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5520 | 000992 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-M-0025-0 | 2025-01-20 | Air Compressor On Off Valve Data sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-17 | 2025-02-12 | Approved with Comments | 2025-03-04 | YES | Resubmitted |  | 131242-WSD11-DS-0025 | NA | "Air Compressor On Off Valve Data sheet" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 23 | AWC | 2025-03-07 | 0 | 000992 | 2025-01-20, 2025-03-07 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5521 | 000992 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0025 | 0 | 131242-WSD11-DS-M-0025-0 | 2025-03-07 | Air Compressor On Off Valve Data sheet | Rev 1: Approved | 2025-03-27 | 2025-07-08 | Approved |  | YES | NA |  | 131242-WSD11-DS-0025 | NA | "Air Compressor On Off Valve Data sheet" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-21 | 123 | APP | 2025-03-07 | 0 | 000992 | 2025-01-20, 2025-03-07 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5522 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0002 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5523 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0003 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5524 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0004 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-03 | 14 | AWC | 2026-01-28 | 0 | 000764&&000993 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5525 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 0 | 131242-WSD11-QA-N-0005-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0005 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2026-01-28 | 1 | 000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5526 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 0 | 131242-WSD11-QA-N-0006-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0006 | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2026-01-28 | 1 | 000993&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5527 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 0 | 131242-WSD11-QA-N-0009-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0009 | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2026-01-28 | 1 | 000993&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5528 | 000993 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010-0 | 2025-01-20 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev.0: Approved with Comments. Resubmission is required. Please send the attached file "TWRP_ANI (Instruments_Analog and Alarm Detection) - Rev3" to Contractor together with the SRC. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0010 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5529 | 000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005-1 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | Approved with Comments | 2025-04-07 | YES | Resubmitted |  | 131242-WSD11-QA-0005 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 12 | AWC | 2026-01-28 | 1 | 000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5530 | 000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006-1 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | Approved with Comments | 2025-04-07 | YES | Resubmitted |  | 131242-WSD11-QA-0006 | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 12 | AWC | 2026-01-28 | 1 | 000993&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5531 | 000993 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009-1 | 2025-03-06 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 1: Approved with comments. Resubmittal required. Other assets check sheets are missing | 2025-03-26 | 2025-03-18 | Approved with Comments | 2025-04-07 | YES | Resubmitted |  | 131242-WSD11-QA-0009 | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 12 | AWC | 2026-01-28 | 1 | 000993&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5532 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002-0 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0002 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5533 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003-0 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0003 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5534 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004-0 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0004 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 0 | 000764&&000993 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5535 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005-1 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0005 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 1 | 000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5536 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006-1 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0006 | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 1 | 000993&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5537 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009-1 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0009 | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 1 | 000993&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5538 | 000993 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010-0 | 2025-04-08 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2025-04-28 | 2025-04-22 | Approved with Comments | 2025-05-12 | NO | Overdue |  | 131242-WSD11-QA-0010 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 14 | AWC | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5539 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0002 | 0 | 131242-WSD11-QA-N-0002-0 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0002 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5540 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0003 | 0 | 131242-WSD11-QA-N-0003-0 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0003 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5541 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0004 | 0 | 131242-WSD11-QA-N-0004-0 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0004 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000764&&000993 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5542 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0005 | 1 | 131242-WSD11-QA-N-0005-1 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0005 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 1 | 000993 | 2025-01-20, 2025-03-06, 2025-04-08, 2026-01-28 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5543 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0006 | 1 | 131242-WSD11-QA-N-0006-1 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0006 | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 1 | 000993&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5544 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0009 | 1 | 131242-WSD11-QA-N-0009-1 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0009 | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 1 | 000993&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5545 | 000993 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0010 | 0 | 131242-WSD11-QA-N-0010-0 | 2026-01-28 | T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check | Rev 2: Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0010 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000993 | 2025-01-20, 2025-04-08, 2026-01-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
5546 | 000994 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 0 | 131242-WSD11-QA-N-0001-0 | 2025-01-20 | Commissioning Plan for THP Air Compressor System | Rev.0: Approved with Comments. Revise and resubmit. | 2025-02-17 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WSD11-QA-0001 | NA | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 14 | AWC | 2025-05-10 | 2 | 000994 | 2025-01-20, 2025-03-06, 2025-05-10 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5547 | 000994 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 1 | 131242-WSD11-QA-N-0001-1 | 2025-03-06 | Commissioning Plan for THP Air Compressor System | Rev.1: Approved with Comments. Resubmittal is required | 2025-03-26 | 2025-03-18 | Approved with Comments | 2025-04-07 | YES | Resubmitted |  | 131242-WSD11-QA-0001 | NA | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 12 | AWC | 2025-05-10 | 2 | 000994 | 2025-01-20, 2025-03-06, 2025-05-10 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5548 | 000994 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0001 | 2 | 131242-WSD11-QA-N-0001-2 | 2025-05-10 | Commissioning Plan for THP Air Compressor System | Rev.2: Approved with Comments. Resubmittal is required | 2025-05-29 | 2025-06-04 | Approved with Comments | 2025-06-24 | NO | Overdue |  | 131242-WSD11-QA-0001 | NA | "Commissioning Plan for THP Air Compressor System" | 2025-01-20 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-24 | 25 | AWC | 2025-05-10 | 2 | 000994 | 2025-01-20, 2025-03-06, 2025-05-10 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-24 | Overdue | 0 | AWC | AWC
5549 | 000995 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 0 | 131242-WSD11-DR-I-7209-0 | 2025-01-21 | THP Biosolids PMS Network Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-18 | 2025-03-31 | Not Approved | 2025-04-18 | YES | Resubmitted |  | 131242-WSD11-DR-7209 | NA | "THP Biosolids PMS Network Architecture Drawing" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 69 | NAP | 2025-04-09 | 1 | 000995 | 2025-01-21, 2025-04-09 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5550 | 000995 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | I | 7209 | 1 | 131242-WSD11-DR-I-7209-1 | 2025-04-09 | THP Biosolids PMS Network Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-29 | 2025-05-07 | Approved with Comments | 2025-05-27 | NO | Overdue |  | 131242-WSD11-DR-7209 | NA | "THP Biosolids PMS Network Architecture Drawing" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 28 | AWC | 2025-04-09 | 1 | 000995 | 2025-01-21, 2025-04-09 | 00, 01 | 2 | Approved with Comments | AWC | 2025-05-27 | Overdue | 0 | AWC | AWC
5551 | 000996 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 0001 | A | 131242-WSD11-DR-E-0001-A | 2025-01-21 | THP Drawing Index for Cable Raceway and Room Layout | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2025-02-18 | 2025-03-13 | Not Approved | 2025-04-02 | NO | Overdue |  | 131242-WSD11-DR-0001 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 51 | NAP | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | For Information | INF |  |  | 0 | NAP | NAP
5552 | 000997 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0020 | 0 | 131242-WSD11-QA-E-0020-0 | 2025-01-22 | Electrical Documents for THP Train 1 & Train 2 (CAMBI) | Rev 0: Rejected. Please refer to attached file for comments. | 2025-02-19 | 2025-03-13 | Not Approved | 2025-04-02 | NO | Overdue |  | 131242-WSD11-QA-0020 | NA | "Electrical Documents for THP Train 1 & Train 2 (CAMBI)" | 2025-01-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-11 | 50 | NAP | 2025-01-22 | 0 | 000997 | 2025-01-22 | 00 | 1 | Not Approved | NAP | 2025-04-02 | Overdue | 0 | NAP | NAP
5553 | 000998 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 0 | 131242-WSW41-QA-A-0014-0 | 2025-01-22 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-19 | 2025-02-24 | Not Approved | 2025-03-14 | YES | Resubmitted |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 33 | NAP | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5554 | 000998 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0014 | 1 | 131242-WSW41-QA-A-0014-1 | 2025-03-10 | Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-11 | Not Approved | 2025-05-01 | NO | Overdue |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 32 | NAP | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5555 | 000999 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0013 | 0 | 131242-WSW41-QA-A-0013-0 | 2025-01-24 | Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd) | Approved | 2025-02-21 | 2025-02-24 | Approved |  | YES | NA |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-07 | 31 | APP | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
5556 | 001000 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 0 | 131242-WSW41-SP-C-0025-0 | 2025-01-24 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WSW41-SP-0025 | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-13 | 20 | NAP | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
5557 | 001000 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 1 | 131242-WSW41-SP-C-0025-1 | 2025-03-14 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-03 | 2025-04-06 | Not Approved | 2025-04-24 | YES | Resubmitted |  | 131242-WSW41-SP-0025 | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 23 | NAP | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
5558 | 001000 | 02 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 2 | 131242-WSW41-SP-C-0025-2 | 2025-04-08 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Approved with Comments | 2025-04-28 | 2025-05-16 | Approved with Comments | 2025-06-05 | YES | Resubmitted |  | 131242-WSW41-SP-0025 | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 38 | AWC | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
5559 | 001000 | 03 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0025 | 3 | 131242-WSW41-SP-C-0025-3 | 2025-06-06 | Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe) | Rev.3: Approved | 2025-06-26 | 2025-07-04 | Approved |  | YES | NA |  | 131242-WSW41-SP-0025 | NA | "Steel Structure Normal Painting system & Fireproofing Painting system Specification (Sanhe)" | 2025-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-20 | 28 | APP | 2025-06-06 | 3 | 001000 | 2025-01-24, 2025-03-14, 2025-04-08, 2025-06-06 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
5560 | 001001 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0026 | 0 | 131242-WSW41-SP-C-0026-0 | 2025-01-24 | Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information. | 2025-02-21 | 2025-02-20 | For Information |  | YES | NA |  | 131242-WSW41-SP-0026 | NA | "Reinforcement Bar Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32)" | 2025-01-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-02-13 | 27 | INF | 2025-01-24 | 0 | 001001 | 2025-01-24 | 00 | 1 | For Information | INF | 2025-03-12 | Overdue | 0 | INF | INF
5561 | 001002 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 0001 | A | 131242-WSD11-DR-B-0001-A | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSD11-DR-0001 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-09 | 91 | INF | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | For Information | INF |  |  | 0 | INF | INF
5562 | 001002 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | B | 0001 | A | 131242-WST02-DR-B-0001-A | 2025-01-26 | Drawing Index (Building and Services Mech.) | Rev 0: For Information | 2025-02-21 | 2025-04-27 | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-0001 | NA | "Drawing Index (Building and Services Mech.)" && "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-09 | 91 | PEN | 2025-02-21 | A | 000779&&001002&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00 | 4 | Rejected | REJ |  |  | 0 | PEN | PEN
5563 | 001003 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0054 | 0 | 131242-WSW41-LT-PM-0054-0 | 2025-01-26 | CV of Team member (Senior Planning Engineer) | Rev. 0 - Approved | 2025-02-21 | 2025-02-07 | Approved |  | YES | NA |  | 131242-WSW41-LT-0054 | NA | "CV of Team member (Senior Planning Engineer)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-15 | 12 | APP | 2025-01-26 | 0 | 001003 | 2025-01-26 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5564 | 001004 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0021 | 0 | 131242-WST02-QA-E-0021-0 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WST02-QA-0021 | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 4th batch (United ULI)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-15 | 23 | APP | 2025-01-26 | 0 | 001004 | 2025-01-26 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5565 | 001005 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1394 | 0 | 131242-WST02-DS-E-1394-0 | 2025-01-26 | Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-03-02 | Approved with Comments | 2025-03-20 | NO | Overdue |  | 131242-WST02-DS-1394 | NA | "Sample Board Submission for Nylon Cable Tie, Nylon gland ip68,Vinyl End Cap, Ucat Series 44.5 Hole Spacing, U-lug Cable lug ucct Series (Cyclect Electrical engineering Pte Ltd)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 35 | AWC | 2025-01-26 | 0 | 001005 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-20 | Overdue | 0 | AWC | AWC
5566 | 001006 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 0 | 131242-WSD11-MS-N-0001-0 | 2025-01-26 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.0: Approved with comments. Please refer to comment sheet. | 2025-02-21 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WSD11-MS-0001 | NA | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 12 | AWC | 2025-05-19 | 1 | 001006 | 2025-01-26, 2025-05-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5567 | 001006 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | MS | N | 0001 | 1 | 131242-WSD11-MS-N-0001-1 | 2025-05-19 | MSRA & SWP for Plant Testing & Commissioning (Site Wide) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-06 | 2025-07-02 | Approved with Comments | 2025-07-22 | NO | Overdue |  | 131242-WSD11-MS-0001 | NA | "MSRA & SWP for Plant Testing & Commissioning (Site Wide)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 44 | AWC | 2025-05-19 | 1 | 001006 | 2025-01-26, 2025-05-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
5568 | 001007 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0014 | 0 | 131242-WSD11-CL-P-0014-0 | 2025-01-26 | Process Gas Hydraulic Calculation | Rev 0: Approved. Please furnish PE Endorsement. | 2025-02-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-CL-0014 | NA | "Process Gas Hydraulic Calculation" && "THP Steam Pressure Loss Calculation" | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-09 | 253 | APP | 2025-01-26 | 0 | 000990&&001007 | 2025-01-20, 2025-01-26 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
5569 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | A | 131242-WST02-SD-A-1010-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-1010 | NA | "Lintel and Stiffener Shop Drawings" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-22 | A.1 | 001008&&001042&&001616 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02 | 5 | (VOID NOT IN USE) | VOID |  |  | 0 | NAP | NAP
5570 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | A | 131242-WST02-SD-A-1011-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-1011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5571 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | A | 131242-WST02-SD-A-1012-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-1012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5572 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | A | 131242-WST02-SD-A-1013-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-1013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5573 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | A | 131242-WST02-SD-A-3006-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3006 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5574 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | A | 131242-WST02-SD-A-3007-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3007 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5575 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | A | 131242-WST02-SD-A-3008-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3008 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5576 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | A | 131242-WST02-SD-A-3009-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3009 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5577 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | A | 131242-WST02-SD-A-3010-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3010 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5578 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | A | 131242-WST02-SD-A-3011-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5579 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | A | 131242-WST02-SD-A-3012-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5580 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | A | 131242-WST02-SD-A-3013-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST02-SD-3013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 22 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5581 | 001008 | 00 | Yuen Fatt | Project | NA | 131242 | WST00 | DR | S | 0001 | A | 131242-WST00-DR-S-0001-A | 2025-01-26 | Shop Drawings for Lintel and Stiffener | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-17 | Not Approved | 2025-03-07 | YES | Resubmitted |  | 131242-WST00-DR-0001 | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "Shop Drawings for Lintel and Stiffener " && "THP Process Flow Diagram" | 2023-05-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 22 | NAP | 2025-01-26 | A | 000018&&000143&&001008 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03 | 6 | Not Approved | NAP | 2025-03-07 | Overdue | 0 | NAP | NAP
5582 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-A-1010-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-10 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-1010 | NA | "Lintel and Stiffener Shop Drawings" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-22 | A.1 | 001008&&001042&&001616 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02 | 5 | (VOID NOT IN USE) | VOID |  |  | 0 | NAP | NAP
5583 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | B | 131242-WST02-SD-A-1011-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-1011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5584 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | B | 131242-WST02-SD-A-1012-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-1012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5585 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | B | 131242-WST02-SD-A-1013-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-1013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5586 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-A-3006-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3006 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5587 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | B | 131242-WST02-SD-A-3007-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3007 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5588 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | B | 131242-WST02-SD-A-3008-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3008 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5589 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | B | 131242-WST02-SD-A-3009-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3009 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5590 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | B | 131242-WST02-SD-A-3010-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3010 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5591 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | B | 131242-WST02-SD-A-3011-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5592 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | B | 131242-WST02-SD-A-3012-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5593 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | B | 131242-WST02-SD-A-3013-B | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-SD-3013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 7 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5594 | 001008 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | QA | A | 0001_supporting docs | 1 | 131242-WSW41-QA-A-0001_supporting docs-1 | 2025-03-21 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-18 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WSW41-QA-0001_supporting docs | NA | "Shop Drawings for Block Wall" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 7 | NAP | 2025-03-21 | 1 | 001008 | 2025-03-21 | 01 | 1 | Not Approved | NAP | 2025-04-17 | Overdue | 0 | NAP | NAP
5595 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | C | 131242-WST02-SD-A-1010-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-1010 | NA | "Lintel and Stiffener Shop Drawings" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-22 | A.1 | 001008&&001042&&001616 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02 | 5 | (VOID NOT IN USE) | VOID |  |  | 0 | NAP | NAP
5596 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | C | 131242-WST02-SD-A-1011-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-1011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5597 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | C | 131242-WST02-SD-A-1012-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-1012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5598 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | C | 131242-WST02-SD-A-1013-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-1013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5599 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | C | 131242-WST02-SD-A-3006-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3006 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5600 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3007 | C | 131242-WST02-SD-A-3007-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3007 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5601 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3008 | C | 131242-WST02-SD-A-3008-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3008 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5602 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3009 | C | 131242-WST02-SD-A-3009-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3009 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5603 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3010 | C | 131242-WST02-SD-A-3010-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3010 | NA | "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008 | 2025-01-26, 2025-03-21, 2025-08-13 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5604 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | C | 131242-WST02-SD-A-3011-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5605 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | C | 131242-WST02-SD-A-3012-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5606 | 001008 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | C | 131242-WST02-SD-A-3013-C | 2025-08-13 | Shop Drawings for Block Wall | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-15 | Not Approved | 2025-10-03 | NO | Overdue |  | 131242-WST02-SD-3013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 33 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | NAP | NAP
5607 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617_BCA | B | 131242-WSD11-DR-S-0300_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0300_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5608 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617_BCA | B | 131242-WSD11-DR-S-0301_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0301_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5609 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST617_BCA | B | 131242-WSD11-DR-S-0302_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0302_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5610 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0303_ST617_BCA | B | 131242-WSD11-DR-S-0303_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0303_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5611 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0304_ST617_BCA | B | 131242-WSD11-DR-S-0304_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0304_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5612 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0305_ST617_BCA | B | 131242-WSD11-DR-S-0305_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0305_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5613 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617_BCA | B | 131242-WSD11-DR-S-1000_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-1000_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5614 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617_BCA | B | 131242-WSD11-DR-S-1001_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-1001_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5615 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617_BCA | B | 131242-WSD11-DR-S-1002_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-1002_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5616 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617_BCA | B | 131242-WSD11-DR-S-1003_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-1003_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5617 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617_BCA | B | 131242-WSD11-DR-S-2000_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-2000_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5618 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617_BCA | B | 131242-WSD11-DR-S-2001_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-2001_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5619 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617_BCA | B | 131242-WSD11-DR-S-3000_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-3000_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5620 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617_BCA | B | 131242-WSD11-DR-S-3001_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-3001_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5621 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617_BCA | B | 131242-WSD11-DR-S-3002_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-3002_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5622 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617_BCA | B | 131242-WSD11-DR-S-5000_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5000_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5623 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617_BCA | B | 131242-WSD11-DR-S-5001_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5001_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5624 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617_BCA | B | 131242-WSD11-DR-S-5002_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5002_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5625 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617_BCA | B | 131242-WSD11-DR-S-5003_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5003_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5626 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617_BCA | B | 131242-WSD11-DR-S-5004_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5004_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5627 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617_BCA | B | 131242-WSD11-DR-S-5005_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5005_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5628 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617_BCA | B | 131242-WSD11-DR-S-5006_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5006_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5629 | 001009 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617_BCA | B | 131242-WSD11-DR-S-8000_ST617_BCA-B | 2025-01-26 | BCA Submission of ST617 (THP Platforms) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-8000_ST617_BCA | NA | "BCA Submission of ST617 (THP Platforms) " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-01-26 | B | 001009 | 2025-01-26 | 00 | 1 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5630 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-S-0306_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0306_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5631 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | B | 131242-WSD11-DR-S-0307_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0307_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5632 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | B | 131242-WSD11-DR-S-0308_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-0308_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5633 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | B | 131242-WSD11-DR-S-1100_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-1100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5634 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | B | 131242-WSD11-DR-S-1101_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-1101_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5635 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | B | 131242-WSD11-DR-S-2100_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-2100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5636 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | B | 131242-WSD11-DR-S-3100_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-3100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5637 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | B | 131242-WSD11-DR-S-5100_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5638 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | B | 131242-WSD11-DR-S-5101_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-5101_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5639 | 001010 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | B | 131242-WSD11-DR-S-8002_ST619_BCA-B | 2025-01-26 | BCA Submission of ST619 (THP Pipe Rack) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-21 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSD11-DR-8002_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 25 | AWC | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
5640 | 001011 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0006 | 0 | 131242-WSD11-QA-I-0006-0 | 2025-01-26 | Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-21 | 2025-04-11 | Not Approved | 2025-05-01 | NO | Overdue |  | 131242-WSD11-QA-0006 | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 75 | NAP | 2026-01-28 | 1 | 000993&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5641 | 001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7001 | A | 131242-WSD11-DR-BE-7001-A | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | Rejected | 2025-04-22 | NO | Overdue |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 66 | REJ | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | REJ | REJ
5642 | 001012 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1005 | A | 131242-WSD11-DR-EL-1005-A | 2025-01-26 | THP Compartmentalization Lighting and Ventilation Fan | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-02-21 | 2025-04-02 | Rejected | 2025-04-22 | NO | Overdue |  | 131242-WSD11-DR-1005 | NA | "THP Compartmentalization Lighting and Ventilation Fan" && "THP ICA GA & Wiring drawings" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-15 | 66 | REJ | 2025-10-28 | B | 001012&&001328 | 2025-01-26, 2025-05-28, 2025-10-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
5643 | 001013 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0019 | 0 | 131242-WST02-QA-E-0019-0 | 2025-01-26 | FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) | Rev 0: Approved. | 2025-02-21 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WST02-QA-0019 | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-15 | 23 | APP | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
5644 | 001014 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 0 | 131242-WSW41-QA-E-0016-0 | 2025-01-26 | ITP for Lightning Protection System Installation | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file and incorporate minor comments. | 2025-02-21 | 2025-03-13 | Approved with Comments | 2025-04-02 | YES | Resubmitted |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-09 | 46 | AWC | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5645 | 001014 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0016 | 1 | 131242-WSW41-QA-E-0016-1 | 2025-03-14 | ITP for Lightning Protection System Installation | Rev 1: Approved. | 2025-04-03 | 2025-05-07 | Approved |  | YES | NA |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-28 | 54 | APP | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
5646 | 001015 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0010 | 0 | 131242-WSW41-VI-S-0010-0 | 2025-02-03 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-03 | 2025-02-20 | Approved with Comments | 2025-03-12 | NO | Overdue |  | 131242-WSW41-VI-0010 | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-17 | 17 | AWC | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | Approved with Comments | AWC | 2025-03-12 | Overdue | 0 | AWC | AWC
5647 | 001016 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0019 | 0 | 131242-WSW41-PC-W-0019-0 | 2025-02-03 | Payment Claim No.19 | Rev (0): Approved. Please refer to S.O. Correspondence no. 291 dated 5 Feb 2025. | 2025-03-03 | 2025-02-17 | Approved |  | YES | NA |  | 131242-WSW41-PC-0019 | NA | "Payment Claim No.19" | 2025-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-23 | 14 | APP | 2025-02-03 | 0 | 001016 | 2025-02-03 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5648 | 001017 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BH | 7000 | A | 131242-WSD11-DR-BH-7000-A | 2025-02-03 | THP Protected Corridor Fan Control Circuit Diagram | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2025-03-03 | 2025-04-27 | Rejected | 2025-05-15 | NO | Overdue |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-17 | 83 | REJ | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | REJ | REJ
5649 | 001018 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 0 | 131242-WSD11-QA-M-0047-0 | 2025-02-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-03 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-QA-0047 | NA | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | 2025-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-23 | 50 | AWC | 2025-07-03 | 1 | 001018 | 2025-02-03, 2025-07-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5650 | 001018 | 01 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0047 | 1 | 131242-WSD11-QA-M-0047-1 | 2025-07-03 | FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch) | Rev 1: Approved | 2025-07-23 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSD11-QA-0047 | NA | "FAT Report for Air Compressor Package SS Pipe Spools in Biosolid Building (Cyclect-1st Batch)" | 2025-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-17 | 173 | APP | 2025-07-03 | 1 | 001018 | 2025-02-03, 2025-07-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5651 | 001019 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0045 | 0 | 131242-WSW41-QA-M-0045-0 | 2025-02-03 | WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd | Rev 0: For Information | 2025-03-03 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSW41-QA-0045 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" && "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | 2025-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-23 | 83 | INF | 2026-01-15 | 1 | 001019&&001545&&001830 | 2025-02-03, 2025-07-31, 2025-11-07, 2026-01-15 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
5652 | 001020 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 0 | 131242-WST02-DS-E-1395-0 | 2025-02-04 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-04 | 2025-03-02 | Approved with Comments | 2025-03-20 | YES | Resubmitted |  | 131242-WST02-DS-1395 | NA | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | 2025-02-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-24 | 26 | AWC | 2025-03-14 | 1 | 001020 | 2025-02-04, 2025-03-14 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5653 | 001020 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | DS | E | 1395 | 1 | 131242-WST02-DS-E-1395-1 | 2025-03-14 | Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DS-1395 | NA | "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" && "Sample Board Submission for SS Cable Gland CABTEK -A2 20S, CMP-E1X-25L, CMP E1W-20S (Cyclect Electrical engineering Pte Ltd)" | 2025-02-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 52 | AWC | 2025-03-14 | 1 | 001020 | 2025-02-04, 2025-03-14 | 00, 01 | 2 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
5654 | 001021 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0048 | 0 | 131242-WST02-QA-M-0048-0 | 2025-02-05 | FAT Report for Air Blowers (Aerzen) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-QA-0048 | NA | "FAT Report for Air Blowers (Aerzen)" && "Factory Acceptance Test Report for Thermal Flow Switch" | 2025-02-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-25 | 48 | AWC | 2025-08-17 | 0 | 001021&&001598 | 2025-02-05, 2025-08-17 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5655 | 001022 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0016 | 0 | 131242-WSW41-QA-A-0016-0 | 2025-02-06 | Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-06 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-20 | 12 | AWC | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5656 | 001023 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-C-0025-0 | 2025-02-07 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-03-02 | Not Approved | 2025-03-20 | YES | Resubmitted |  | 131242-WSW41-MS-0025 | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 23 | NAP | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5657 | 001023 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-C-0025-1 | 2025-03-10 | SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd | Approved with Comments | 2025-03-28 | 2025-06-11 | Approved with Comments | 2025-07-01 | NO | Overdue |  | 131242-WSW41-MS-0025 | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 93 | AWC | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
5658 | 001024 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0023 | 0 | 131242-WSW41-QA-C-0023-0 | 2025-02-07 | Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024 | For information. | 2025-03-07 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSW41-QA-0023 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for November 2024" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Chemical Dosing Pumps (Prominent)" | 2024-11-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-21 | 11 | INF | 2025-10-23 | 1 | 000813&&001024 | 2024-11-14, 2025-02-07, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
5659 | 001025 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0015 | 0 | 131242-WST02-QA-A-0015-0 | 2025-02-07 | Sample Board Submission for Roof Waterproofing (G-Concept) | For information. Please provide technical data sheet for the proposed system and submit shop drawings for approval. | 2025-03-07 | 2025-02-24 | For Information |  | YES | NA |  | 131242-WST02-QA-0015 | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-21 | 17 | INF | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | INF | INF
5660 | 001026 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1014 | 0 | 131242-WST02-SD-A-1014-0 | 2025-02-07 | Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-07 | 2025-02-24 | Not Approved | 2025-03-14 | NO | Overdue |  | 131242-WST02-SD-1014 | NA | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 17 | NAP | 2025-08-27 | C | 001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5661 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | A | 131242-WSD11-DR-EI-7040-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7040 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5662 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | A | 131242-WSD11-DR-EI-7041-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7041 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5663 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | A | 131242-WSD11-DR-EI-7042-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7042 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5664 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | A | 131242-WSD11-DR-EI-7043-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7043 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5665 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | A | 131242-WSD11-DR-EI-7044-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7044 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5666 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | A | 131242-WSD11-DR-EI-7045-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7045 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5667 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | A | 131242-WSD11-DR-EI-7046-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7046 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5668 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | A | 131242-WSD11-DR-EI-7047-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7047 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5669 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | A | 131242-WSD11-DR-EI-7048-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7048 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5670 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | A | 131242-WSD11-DR-EI-7049-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7049 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5671 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | A | 131242-WSD11-DR-EI-7050-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7050 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5672 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | A | 131242-WSD11-DR-EI-7060-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7060 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5673 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | A | 131242-WSD11-DR-EI-7061-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7061 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5674 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | A | 131242-WSD11-DR-EI-7062-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7062 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5675 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | A | 131242-WSD11-DR-EI-7063-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7063 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5676 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | A | 131242-WSD11-DR-EI-7064-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7064 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5677 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | A | 131242-WSD11-DR-EI-7065-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7065 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5678 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | A | 131242-WSD11-DR-EI-7066-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7066 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5679 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | A | 131242-WSD11-DR-EI-7067-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7067 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5680 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | A | 131242-WSD11-DR-EI-7068-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7068 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5681 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | A | 131242-WSD11-DR-EI-7069-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7069 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5682 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | A | 131242-WSD11-DR-EI-7070-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7070 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5683 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | A | 131242-WSD11-DR-EP-3014-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5684 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | A | 131242-WSD11-DR-EP-3015-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5685 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | A | 131242-WSD11-DR-EP-3016-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5686 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | A | 131242-WSD11-DR-EP-3017-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5687 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | A | 131242-WSD11-DR-EP-3018-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5688 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | A | 131242-WSD11-DR-EP-3019-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5689 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | A | 131242-WSD11-DR-EP-3020-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5690 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | A | 131242-WSD11-DR-EP-3021-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5691 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | A | 131242-WSD11-DR-EP-3022-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5692 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | A | 131242-WSD11-DR-EP-3023-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5693 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | A | 131242-WSD11-DR-EP-3024-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5694 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | A | 131242-WSD11-DR-EP-3025-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5695 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | A | 131242-WSD11-DR-EP-3026-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3026 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5696 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | A | 131242-WSD11-DR-EP-3027-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-3027 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5697 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | A | 131242-WSD11-DR-EP-7110-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7110 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5698 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | A | 131242-WSD11-DR-EP-7111-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7111 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5699 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | A | 131242-WSD11-DR-EP-7112-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7112 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5700 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | A | 131242-WSD11-DR-EP-7113-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7113 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5701 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | A | 131242-WSD11-DR-EP-7114-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7114 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5702 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | A | 131242-WSD11-DR-EP-7115-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7115 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5703 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | A | 131242-WSD11-DR-EP-7116-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7116 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5704 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | A | 131242-WSD11-DR-EP-7117-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7117 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5705 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | A | 131242-WSD11-DR-EP-7118-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7118 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5706 | 001027 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | A | 131242-WSD11-DR-EP-7119-A | 2025-02-07 | THP-MCC-0001AB MCC Drawings | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-08 | Not Approved | 2025-04-28 | YES | Resubmitted |  | 131242-WSD11-DR-7119 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 60 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5707 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | B | 131242-WSD11-DR-EI-7040-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7040 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5708 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | B | 131242-WSD11-DR-EI-7041-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7041 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5709 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | B | 131242-WSD11-DR-EI-7042-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7042 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5710 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | B | 131242-WSD11-DR-EI-7043-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7043 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5711 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | B | 131242-WSD11-DR-EI-7044-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7044 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5712 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | B | 131242-WSD11-DR-EI-7045-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7045 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5713 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | B | 131242-WSD11-DR-EI-7046-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7046 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5714 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | B | 131242-WSD11-DR-EI-7047-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7047 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5715 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | B | 131242-WSD11-DR-EI-7048-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7048 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5716 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | B | 131242-WSD11-DR-EI-7049-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7049 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5717 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | B | 131242-WSD11-DR-EI-7050-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7050 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5718 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | B | 131242-WSD11-DR-EI-7060-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7060 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5719 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | B | 131242-WSD11-DR-EI-7061-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7061 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5720 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | B | 131242-WSD11-DR-EI-7062-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7062 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5721 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | B | 131242-WSD11-DR-EI-7063-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7063 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5722 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | B | 131242-WSD11-DR-EI-7064-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7064 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5723 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | B | 131242-WSD11-DR-EI-7065-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7065 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5724 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | B | 131242-WSD11-DR-EI-7066-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7066 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5725 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | B | 131242-WSD11-DR-EI-7067-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7067 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5726 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | B | 131242-WSD11-DR-EI-7068-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7068 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5727 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | B | 131242-WSD11-DR-EI-7069-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7069 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5728 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | B | 131242-WSD11-DR-EI-7070-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7070 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5729 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | B | 131242-WSD11-DR-EP-3014-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5730 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | B | 131242-WSD11-DR-EP-3015-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5731 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | B | 131242-WSD11-DR-EP-3016-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5732 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | B | 131242-WSD11-DR-EP-3017-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5733 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | B | 131242-WSD11-DR-EP-3018-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5734 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | B | 131242-WSD11-DR-EP-3019-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5735 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | B | 131242-WSD11-DR-EP-3020-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5736 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | B | 131242-WSD11-DR-EP-3021-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5737 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | B | 131242-WSD11-DR-EP-3022-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5738 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | B | 131242-WSD11-DR-EP-3023-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5739 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | B | 131242-WSD11-DR-EP-3024-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5740 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | B | 131242-WSD11-DR-EP-3025-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5741 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | B | 131242-WSD11-DR-EP-3026-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3026 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5742 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | B | 131242-WSD11-DR-EP-3027-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-3027 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5743 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | B | 131242-WSD11-DR-EP-7110-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7110 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5744 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | B | 131242-WSD11-DR-EP-7111-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7111 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5745 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | B | 131242-WSD11-DR-EP-7112-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7112 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5746 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | B | 131242-WSD11-DR-EP-7113-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7113 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5747 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | B | 131242-WSD11-DR-EP-7114-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7114 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5748 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | B | 131242-WSD11-DR-EP-7115-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7115 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5749 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | B | 131242-WSD11-DR-EP-7116-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7116 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5750 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | B | 131242-WSD11-DR-EP-7117-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7117 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5751 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | B | 131242-WSD11-DR-EP-7118-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7118 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5752 | 001027 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | B | 131242-WSD11-DR-EP-7119-B | 2025-05-30 | THP-MCC-0001AB MCC Drawings | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-06-19 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WSD11-DR-7119 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 31 | NAP | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5753 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7040 | C | 131242-WSD11-DR-EI-7040-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7040 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5754 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7041 | C | 131242-WSD11-DR-EI-7041-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7041 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5755 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7042 | C | 131242-WSD11-DR-EI-7042-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7042 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5756 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7043 | C | 131242-WSD11-DR-EI-7043-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7043 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5757 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7044 | C | 131242-WSD11-DR-EI-7044-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7044 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5758 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7045 | C | 131242-WSD11-DR-EI-7045-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7045 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5759 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7046 | C | 131242-WSD11-DR-EI-7046-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7046 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5760 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7047 | C | 131242-WSD11-DR-EI-7047-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7047 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5761 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7048 | C | 131242-WSD11-DR-EI-7048-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7048 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5762 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7049 | C | 131242-WSD11-DR-EI-7049-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7049 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5763 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7050 | C | 131242-WSD11-DR-EI-7050-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7050 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5764 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7060 | C | 131242-WSD11-DR-EI-7060-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7060 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5765 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7061 | C | 131242-WSD11-DR-EI-7061-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7061 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5766 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7062 | C | 131242-WSD11-DR-EI-7062-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7062 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5767 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7063 | C | 131242-WSD11-DR-EI-7063-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7063 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5768 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7064 | C | 131242-WSD11-DR-EI-7064-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7064 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5769 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7065 | C | 131242-WSD11-DR-EI-7065-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7065 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5770 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7066 | C | 131242-WSD11-DR-EI-7066-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7066 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5771 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7067 | C | 131242-WSD11-DR-EI-7067-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7067 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5772 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7068 | C | 131242-WSD11-DR-EI-7068-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7068 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5773 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7069 | C | 131242-WSD11-DR-EI-7069-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7069 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5774 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7070 | C | 131242-WSD11-DR-EI-7070-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7070 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5775 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3014 | C | 131242-WSD11-DR-EP-3014-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5776 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3015 | C | 131242-WSD11-DR-EP-3015-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5777 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3016 | C | 131242-WSD11-DR-EP-3016-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5778 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3017 | C | 131242-WSD11-DR-EP-3017-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5779 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3018 | C | 131242-WSD11-DR-EP-3018-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5780 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3019 | C | 131242-WSD11-DR-EP-3019-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5781 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3020 | C | 131242-WSD11-DR-EP-3020-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5782 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3021 | C | 131242-WSD11-DR-EP-3021-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5783 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3022 | C | 131242-WSD11-DR-EP-3022-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5784 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3023 | C | 131242-WSD11-DR-EP-3023-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5785 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3024 | C | 131242-WSD11-DR-EP-3024-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5786 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3025 | C | 131242-WSD11-DR-EP-3025-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5787 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3026 | C | 131242-WSD11-DR-EP-3026-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3026 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5788 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3027 | C | 131242-WSD11-DR-EP-3027-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-3027 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5789 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7110 | C | 131242-WSD11-DR-EP-7110-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7110 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5790 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7111 | C | 131242-WSD11-DR-EP-7111-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7111 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5791 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7112 | C | 131242-WSD11-DR-EP-7112-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7112 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5792 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7113 | C | 131242-WSD11-DR-EP-7113-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7113 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5793 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7114 | C | 131242-WSD11-DR-EP-7114-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7114 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5794 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7115 | C | 131242-WSD11-DR-EP-7115-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7115 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5795 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7116 | C | 131242-WSD11-DR-EP-7116-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7116 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5796 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7117 | C | 131242-WSD11-DR-EP-7117-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7117 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5797 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7118 | C | 131242-WSD11-DR-EP-7118-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7118 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5798 | 001027 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7119 | C | 131242-WSD11-DR-EP-7119-C | 2025-08-05 | THP-MCC-0001AB MCC Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WSD11-DR-7119 | NA | "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | C | 001027 | 2025-02-07, 2025-05-30, 2025-08-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
5799 | 001028 | 00 | Zora | CSA | NA | 131242 | NA | NA | NA | FOR INFORMATION | 0 |  | 2025-02-07 | BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters | For information. | 2025-03-07 | 2025-02-18 | For Information |  | YES | NA |  | 131242-NA-NA-FOR INFORMATION | NA | "BCA submission record of As-Built Piling for ST604/615 & ST605/616 with BCA’s In order Letters " | 2025-02-07 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-02-27 | 11 | INF | 2025-02-07 | 0 | 001028 | 2025-02-07 | 00 | 1 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5800 | 001029 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 0 | 131242-WSW41-QA-M-0037-0 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Rev 0: Not approved - Revise and Resubmit | 2025-03-07 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSW41-QA-0037 | NA | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 46 | NAP | 2025-05-14 | 0 | 001029&&001294 | 2025-02-07, 2025-04-21, 2025-05-14 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
5801 | 001029 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0037 | 1 | 131242-WSW41-QA-M-0037-1 | 2025-04-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) | Approved | 2025-05-09 | 2025-05-12 | Approved |  | YES | NA |  | 131242-WSW41-QA-0037 | NA | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 21 | APP | 2025-05-14 | 0 | 001029&&001294 | 2025-02-07, 2025-04-21, 2025-05-14 | 00, 01 | 3 | For Information | INF |  |  | 0 | APP | APP
5802 | 001030 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 0 | 131242-WSW41-QA-M-0046-0 | 2025-02-07 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-07 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WSW41-QA-0046 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 79 | AWC | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | For Information | INF |  |  | 0 | AWC | AWC
5803 | 001030 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0046 | 1 | 131242-WSW41-QA-M-0046-1 | 2025-06-18 | Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-08 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0046 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-02 | 82 | APP | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | For Information | INF |  |  | 0 | APP | APP
5804 | 001031 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0009 | 0 | 131242-WST02-CL-P-0009-0 | 2025-02-07 | SSN Energy Consumption Computation | Rev 0: For Information | 2025-03-07 | 2025-10-06 | For Information |  | YES | NA |  | 131242-WST02-CL-0009 | NA | " SSN Energy Consumption Computation" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-02-27 | 241 | INF | 2025-02-07 | 0 | 001031 | 2025-02-07 | 00 | 1 | For Information | INF | 2025-10-24 | Overdue | 0 | INF | INF
5805 | 001032 | 00 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 0 | 131242-WST02-SP-P-0002-0 | 2025-02-07 | SSN Aeration Blower Control Philosophy | Rev0: approved with comments, resubmission is required. | 2025-03-07 | 2025-03-13 | Approved with Comments | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-SP-0002 | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-21 | 34 | AWC | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5806 | 001032 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0002 | 1 | 131242-WST02-SP-P-0002-1 | 2025-06-04 | SSN Aeration Blower Control Philosophy | Rev1: approved with comments, resubmission is required. | 2025-06-24 | 2025-07-02 | Approved with Comments | 2025-07-22 | NO | Overdue |  | 131242-WST02-SP-0002 | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 28 | AWC | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
5807 | 001033 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 0 | 131242-WSD11-VI-I-0004-0 | 2025-02-10 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-10 | 2025-02-13 | Approved with Comments | 2025-03-05 | YES | Resubmitted |  | 131242-WSD11-VI-0004 | NA | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" && "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-02-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-02 | 3 | AWC | 2025-05-10 | 0 | 001033&&001274 | 2025-02-10, 2025-03-17, 2025-05-10 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5808 | 001033 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0004 | 1 | 131242-WSD11-VI-I-0004-1 | 2025-03-17 | Vendor Approval for THP Air Compressor System (Pressure Transmitter) | Rev 1: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-04-04 | 2025-05-07 | Approved with Comments |  | YES | NA |  | 131242-WSD11-VI-0004 | NA | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" && "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-02-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-31 | 51 | AWC | 2025-05-10 | 0 | 001033&&001274 | 2025-02-10, 2025-03-17, 2025-05-10 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5809 | 001034 | 00 | Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-IM-0052-0 | 2025-02-10 | Submission of BIM Coordination VCM Model (Jan 2025) | For Information. Score= 70/100 | 2025-03-10 | 2025-02-20 | For Information |  | YES | NA |  | 131242-WST02-CD-0052 | NA | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | 2025-02-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-02 | 10 | INF | 2025-12-16 | 0 | 000163&&001034 | 2025-02-10, 2025-12-16 | 00, 03 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
5810 | 001035 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0049 | 0 | 131242-WSD11-QA-M-0049-0 | 2025-02-10 | FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch) | Rev 0: Approved | 2025-03-10 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WSD11-QA-0049 | NA | "FAT Report for Air Compressor Package SS Penetration Pipe Sleeve in Biosolid Building (Cycelct 2nd Batch)" | 2025-02-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-02 | 43 | APP | 2025-02-10 | 0 | 001035 | 2025-02-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5811 | 001036 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | A | 0017 | 0 | 131242-WST02-QA-A-0017-0 | 2025-02-11 | Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd) | For information. | 2025-03-11 | 2025-02-24 | For Information |  | YES | NA |  | 131242-WST02-QA-0017 | NA | "QA/QC Report for Mechanical Ventilation Fan" && "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | 2025-02-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-03 | 13 | INF | 2025-10-13 | 1 | 001036&&001601 | 2025-02-11, 2025-08-19, 2025-10-13 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
5812 | 001037 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0055 | 0 | 131242-WSW41-LT-PM-0055-0 | 2025-02-11 | EOT Notice Letter for ST617 & ST619 | Rev (0): For Information. Please refer to S.O. correspondence no. 327 dated 14 April 2025. | 2025-03-11 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSW41-LT-0055 | NA | "EOT Notice Letter for ST617 & ST619" | 2025-02-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-03 | 75 | INF | 2025-02-11 | 0 | 001037 | 2025-02-11 | 00 | 1 | For Information | INF | 2025-05-15 | Overdue | 0 | INF | INF
5813 | 001038 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0004 | 0 | 131242-WSW41-PO-E-0004-0 | 2025-02-11 | Unppriced PO for YHW | Rev 0: For Information. | 2025-03-11 | 2025-03-13 | For Information | 2025-04-02 | NO | Overdue |  | 131242-WSW41-PO-0004 | NA | "Unppriced PO for YHW" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for Metallic Butterfly Valve (OVS Engineering)" | 2025-02-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-03 | 30 | INF | 2025-08-01 | 0 | 001038&&001503&&001515 | 2025-02-11, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
5814 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A | 131242-WSD11-DR-B-1003-A | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
5815 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 3000 | A1 | 131242-WSD11-DR-BH-3000-A1 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | NAP | NAP
5816 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1000 | A1 | 131242-WSD11-DR-BH-1000-A1 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
5817 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1001 | A1 | 131242-WSD11-DR-BH-1001-A1 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
5818 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1002 | A1 | 131242-WSD11-DR-BH-1002-A1 | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
5819 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1002 | A | 131242-WSD11-DR-BF-1002-A | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
5820 | 001039 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3001 | A | 131242-WSD11-DR-BF-3001-A | 2025-02-12 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 0: Not approved - Revise and Resubmit | 2025-03-12 | 2025-03-25 | Not Approved | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-26 | 41 | NAP | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5821 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | CL | BH | 8000 | 0 | 131242-WSD11-CL-BH-8000-0 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-CL-8000 | NA | "THP Protected Corridor Area-Building Service (Mechanical)" | 2025-06-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-24 | 43 | AWC | 2025-06-04 | 0 | 001039 | 2025-06-04 | 01 | 1 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
5822 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | B | 1003 | A.2 | 131242-WSD11-DR-B-1003-A.2 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
5823 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 3000 | A.3 | 131242-WSD11-DR-BH-3000-A.3 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
5824 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1000 | A.3 | 131242-WSD11-DR-BH-1000-A.3 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
5825 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1001 | A.3 | 131242-WSD11-DR-BH-1001-A.3 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
5826 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BH | 1002 | A.3 | 131242-WSD11-DR-BH-1002-A.3 | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
5827 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1002 | A | 131242-WSD11-DR-BF-1002-A | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
5828 | 001039 | 01 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3001 | A | 131242-WSD11-DR-BF-3001-A | 2025-06-04 | THP Protected Corridor Area-Building Service (Mechanical) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-24 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 43 | AWC | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5829 | 001040 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 0 | 131242-WSD11-QA-E-0023-0 | 2025-02-12 | FAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. | 2025-03-12 | 2025-03-13 | Approved with Comments | 2025-04-02 | YES | Resubmitted |  | 131242-WSD11-QA-0023 | NA | "FAT Report for WSD11-MCC-0101A&B" | 2025-02-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 29 | AWC | 2025-03-27 | 1 | 001040 | 2025-02-12, 2025-03-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5830 | 001040 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0023 | 1 | 131242-WSD11-QA-E-0023-1 | 2025-03-27 | FAT Report for WSD11-MCC-0101A&B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-16 | 2025-05-07 | Approved with Comments | 2025-05-27 | NO | Overdue |  | 131242-WSD11-QA-0023 | NA | "FAT Report for WSD11-MCC-0101A&B" | 2025-02-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 41 | AWC | 2025-03-27 | 1 | 001040 | 2025-02-12, 2025-03-27 | 00, 01 | 2 | Approved with Comments | AWC | 2025-05-27 | Overdue | 0 | AWC | AWC
5831 | 001041 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 0 | 131242-WSW41-QA-M-0051-0 | 2025-02-13 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Rev 0: Not approved - Revise and Resubmit | 2025-03-13 | 2025-02-18 | Not Approved | 2025-03-10 | YES | Resubmitted |  | 131242-WSW41-QA-0051 | NA | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | 2025-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-05 | 5 | NAP | 2025-03-24 | 1 | 001041 | 2025-02-13, 2025-03-24 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
5832 | 001041 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0051 | 1 | 131242-WSW41-QA-M-0051-1 | 2025-03-24 | FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1) | Approved | 2025-04-11 | 2025-05-19 | Approved |  | YES | NA |  | 131242-WSW41-QA-0051 | NA | "FAT Report for CSEL Cast-in Pipe Sleeve (Batch 1)" | 2025-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-07 | 56 | APP | 2025-03-24 | 1 | 001041 | 2025-02-13, 2025-03-24 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5833 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3006 | B | 131242-WST02-SD-A-3006-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-3006 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5834 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3011 | B | 131242-WST02-SD-A-3011-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-3011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5835 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3012 | B | 131242-WST02-SD-A-3012-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-3012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5836 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 3013 | B | 131242-WST02-SD-A-3013-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-3013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-08-13 | C | 001008&&001042 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5837 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1010 | B | 131242-WST02-SD-A-1010-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-1010 | NA | "Lintel and Stiffener Shop Drawings" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-08-22 | A.1 | 001008&&001042&&001616 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02 | 5 | (VOID NOT IN USE) | VOID |  |  | 0 | NAP | NAP
5838 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1011 | B | 131242-WST02-SD-A-1011-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-1011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5839 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1012 | B | 131242-WST02-SD-A-1012-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-1012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5840 | 001042 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | SD | A | 1013 | B | 131242-WST02-SD-A-1013-B | 2025-02-14 | Lintel and Stiffener Shop Drawings | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-14 | 2025-03-21 | Not Approved | 2025-04-10 | NO | Overdue |  | 131242-WST02-SD-1013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 35 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5841 | 001043 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 0 | 131242-WSW41-VI-M-1007-0 | 2025-02-14 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-04-05 | Approved with Comments | 2025-04-24 | YES | Resubmitted |  | 131242-WSW41-VI-1007 | NA | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | 2025-02-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 50 | AWC | 2025-06-09 | 1 | 001043 | 2025-02-14, 2025-06-09 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5842 | 001043 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1007 | 1 | 131242-WSW41-VI-M-1007-1 | 2025-06-09 | Preliminary design and Vendor Approval – Plastic Valves (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-20 | Approved with Comments | 2025-07-10 | NO | Overdue |  | 131242-WSW41-VI-1007 | NA | "Preliminary design and Vendor Approval – Plastic Valves (GF)" | 2025-02-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-23 | 11 | AWC | 2025-06-09 | 1 | 001043 | 2025-02-14, 2025-06-09 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-10 | Overdue | 0 | AWC | AWC
5843 | 001044 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0023 | 0 | 131242-WSW41-MS-C-0023-0 | 2025-02-16 | MSRA, SWP for Site Wide Pipe Rack Installation | Approved | 2025-03-14 | 2025-12-17 | Approved |  | YES | NA |  | 131242-WSW41-MS-0023 | NA | "MSRA and SWP for Installation of AAC Block Wall" && "MSRA, SWP for Site Wide Pipe Rack Installation" | 2024-12-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-02 | 304 | APP | 2025-02-16 | 0 | 000898&&001044 | 2024-12-13, 2025-02-16 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
5844 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0306_ST619_BCA | B | 131242-WSD11-DR-S-0306_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-0306_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5845 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0307_ST619_BCA | B | 131242-WSD11-DR-S-0307_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-0307_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5846 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 0308_ST619_BCA | B | 131242-WSD11-DR-S-0308_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-0308_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5847 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1100_ST619_BCA | B | 131242-WSD11-DR-S-1100_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-1100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5848 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1101_ST619_BCA | B | 131242-WSD11-DR-S-1101_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-1101_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5849 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 2100_ST619_BCA | B | 131242-WSD11-DR-S-2100_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-2100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5850 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 3100_ST619_BCA | B | 131242-WSD11-DR-S-3100_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-3100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5851 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5100_ST619_BCA | B | 131242-WSD11-DR-S-5100_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-5100_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5852 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5101_ST619_BCA | B | 131242-WSD11-DR-S-5101_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-5101_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5853 | 001045 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 8002_ST619_BCA | B | 131242-WSD11-DR-S-8002_ST619_BCA-B | 2025-02-17 | BCA Approval of ST619 (THP Pipe Rack) | For information. | 2025-03-17 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSD11-DR-8002_ST619_BCA | NA | "BCA Approval of ST619 (THP Pipe Rack)" && "BCA Submission of ST619 (THP Pipe Rack)" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-03 | 1 | INF | 2025-02-17 | B | 001010&&001045 | 2025-01-26, 2025-02-17 | 00 | 2 | For Information | INF | 2025-03-10 | Overdue | 0 | INF | INF
5854 | 001046 | 00 | Jun | HSE | NA | 131242 | WSW41 | MS | E | 0008 | 0 | 131242-WSW41-MS-E-0008-0 | 2025-02-17 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-03-17 | Approved with Comments | 2025-04-04 | NO | Overdue |  | 131242-WSW41-MS-0008 | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" && "MSRA, SWP for Time Lapse Camera Steel Pole Erection" && "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2024-03-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-03 | 28 | AWC | 2025-12-05 | 1 | 000347&&001046&&001337 | 2024-03-08, 2025-02-17, 2025-05-30, 2025-12-05 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5855 | 001047 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0021 | 0 | 131242-WSW41-RT-PM-0021-0 | 2025-02-17 | C4B Monthly Progress Report Number No.21 (01 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-03-17 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WSW41-RT-0021 | NA | "C4B Monthly Progress Report Number No.21 (01 25) " | 2025-02-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-09 | 24 | AWC | 2025-02-17 | 0 | 001047 | 2025-02-17 | 00 | 1 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
5856 | 001048 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0020 | 0 | 131242-WSW41-PS-PM-0020-0 | 2025-02-18 | Monthly Progress Presentation No. 20 (0125) | Rev. 0 - For Information | 2025-03-18 | 2025-02-18 | For Information |  | YES | NA |  | 131242-WSW41-PS-0020 | NA | "Monthly Progress Presentation No. 20 (0125)" && "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-10 | 0 | INF | 2025-03-18 | 0 | 001048&&001130 | 2025-02-18, 2025-03-18 | 00 | 2 | Approved | APP |  |  | 0 | INF | INF
5857 | 001049 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0020 | 0 | 131242-WSW41-MI-PM-0020-0 | 2025-02-18 | Monthly Progress Meeting Minutes 0020_20250122 | Rev. 0 - For Information | 2025-03-18 | 2025-02-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0020 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0020_20250122" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 6 | INF | 2025-02-18 | 0 | 000353&&000388&&000684&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | For Information | INF | 2025-03-14 | Overdue | 0 | INF | INF
5858 | 001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | A | 131242-WST02-SD-A-1014-A | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 | Not Approved | 2025-04-02 | NO | Overdue |  | 131242-WST02-SD-1014 | NA | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 23 | NAP | 2025-08-27 | C | 001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5859 | 001050 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | A | 131242-WST02-SD-A-3014-A | 2025-02-18 | Shop Drawings for SSN Electrical Building Roof Waterproofing | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-18 | 2025-03-13 | Not Approved | 2025-04-02 | NO | Overdue |  | 131242-WST02-SD-3014 | NA | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 23 | NAP | 2025-08-27 | D | 001050&&001356 | 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5860 | 001051 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 0 | 131242-WST02-DS-M-5601-0 | 2025-02-18 | Data Sheet for Parabolic Screen | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-DS-5601 | NA | "Data Sheet for Parabolic Screen" | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 14 | AWC | 2025-04-01 | 1 | 001051 | 2025-02-18, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
5861 | 001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5601 | 1 | 131242-WST02-DS-M-5601-1 | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DS-5601 | NA | "Data Sheet for Parabolic Screen" | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | 1 | 001051 | 2025-02-18, 2025-04-01 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
5862 | 001051 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5601 | F | 131242-WST02-DR-M-5601-F | 2025-04-01 | Data Sheet for Parabolic Screen | Rev 1: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5601 | NA | "Data Sheet for Parabolic Screen" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Screen General Arrangement Drawing" | 2024-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-07-24 | A | 000931&&001051&&001528 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
5863 | 001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3203 | A | 131242-WST02-DR-E-3203-A | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | Not Approved | 2025-04-28 | NO | Overdue |  | 131242-WST02-DR-3203 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 49 | NAP | 2025-03-06 | A | 000553&&001052 | 2025-02-18, 2025-03-06 | 00, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5864 | 001052 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3204 | A | 131242-WST02-DR-E-3204-A | 2025-02-18 | PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-08 | Not Approved | 2025-04-28 | NO | Overdue |  | 131242-WST02-DR-3204 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 49 | NAP | 2025-03-06 | A | 000553&&001052 | 2025-02-18, 2025-03-06 | 00, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5865 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_BCA | B | 131242-WSD11-DR-S-0300_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-0300_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5866 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_BCA | B | 131242-WSD11-DR-S-0301_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-0301_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5867 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0302_BCA | B | 131242-WSD11-DR-S-0302_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-0302_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5868 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0303_BCA | B | 131242-WSD11-DR-S-0303_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-0303_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5869 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0304_BCA | B | 131242-WSD11-DR-S-0304_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-0304_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5870 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0305_BCA | B | 131242-WSD11-DR-S-0305_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-0305_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5871 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_BCA | B | 131242-WSD11-DR-S-1000_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-1000_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5872 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_BCA | B | 131242-WSD11-DR-S-1001_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-1001_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5873 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_BCA | B | 131242-WSD11-DR-S-1002_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-1002_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5874 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_BCA | B | 131242-WSD11-DR-S-1003_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-1003_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5875 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_BCA | B | 131242-WSD11-DR-S-2000_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-2000_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5876 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_BCA | B | 131242-WSD11-DR-S-2001_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-2001_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5877 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_BCA | B | 131242-WSD11-DR-S-3000_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-3000_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5878 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_BCA | B | 131242-WSD11-DR-S-3001_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-3001_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5879 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_BCA | B | 131242-WSD11-DR-S-3002_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-3002_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5880 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_BCA | B | 131242-WSD11-DR-S-5000_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5000_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5881 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_BCA | B | 131242-WSD11-DR-S-5001_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5001_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5882 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_BCA | B | 131242-WSD11-DR-S-5002_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5002_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5883 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_BCA | B | 131242-WSD11-DR-S-5003_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5003_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5884 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_BCA | B | 131242-WSD11-DR-S-5004_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5004_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5885 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_BCA | B | 131242-WSD11-DR-S-5005_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5005_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5886 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_BCA | B | 131242-WSD11-DR-S-5006_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-5006_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5887 | 001053 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_BCA | B | 131242-WSD11-DR-S-8000_BCA-B | 2025-02-18 | BCA Approval of ST617 (THP Platform 01 & 02) | For information. | 2025-03-18 | 2025-03-10 | For Information |  | YES | NA |  | 131242-WSD11-DR-8000_BCA | NA | "BCA Approval of ST617 (THP Platform 01 & 02)" | 2025-02-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-10 | 20 | INF | 2025-02-18 | B | 001053 | 2025-02-18 | 00 | 1 | For Information | INF | 2025-03-28 | Overdue | 0 | INF | INF
5888 | 001054 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0018 | 0 | 131242-WSW41-QA-A-0018-0 | 2025-02-18 | Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works | Rev.0:Approved. Please submit MSRA. | 2025-03-18 | 2025-02-24 | Approved |  | YES | NA |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 6 | APP | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
5889 | 001055 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0022 | 0 | 131242-WSW41-QA-E-0022-0 | 2025-02-18 | Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSW41-QA-0022 | NA | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" && "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" && "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2024-11-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | AWC | 2025-02-18 | 0 | 000795&&000982&&001055 | 2024-11-01, 2025-01-16, 2025-02-18 | 00 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
5890 | 001056 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0017 | 0 | 131242-WSW41-QA-E-0017-0 | 2025-02-18 | Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | AWC | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5891 | 001057 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0018 | 0 | 131242-WSW41-QA-E-0018-0 | 2025-02-18 | Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-18 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | AWC | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5892 | 001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-S-1600_ST620_BCA-D | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-1600_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-11 | 22 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5893 | 001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | D | 131242-WSD11-DR-S-1601_ST620_BCA-D | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-1601_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-11 | 22 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5894 | 001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | D | 131242-WSD11-DR-S-5600_ST620_BCA-D | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-5600_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-11 | 22 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5895 | 001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | D | 131242-WSD11-DR-S-5601_ST620_BCA-D | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-5601_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-11 | 22 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
5896 | 001058 | 00 | Franklin | CSA | NA | 131242 | WSD11 | CL | S | 0007_ST620_BCA | 1 | 131242-WSD11-CL-S-0007_ST620_BCA-1 | 2025-02-19 | BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m) | R0- Not using BIM Authorized Tools. For information | 2025-03-19 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-CL-0007_ST620_BCA | NA | "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-11 | 22 | INF | 2025-02-19 | 1 | 001058 | 2025-02-19 | 00 | 1 | For Information | INF | 2025-04-02 | Overdue | 0 | INF | INF
5897 | 001059 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0050 | 0 | 131242-WST02-QA-M-0050-0 | 2025-02-19 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch) | Rev 0: Approved | 2025-03-19 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WST02-QA-0050 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch)" && "Factory Acceptance Test Report for Conductive Probe Level Switches" | 2025-02-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-11 | 67 | APP | 2025-08-29 | 0 | 001059&&001639 | 2025-02-19, 2025-08-29 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
5898 | 001060 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0052 | 0 | 131242-WSD11-QA-M-0052-0 | 2025-02-19 | Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-04-02 | Approved with Comments | 2025-04-22 | NO | Overdue |  | 131242-WSD11-QA-0052 | NA | "Vendor Manufacturing Inspection Test Plan – Ducting work for THP compressed air system" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 42 | AWC | 2025-02-19 | 0 | 001060 | 2025-02-19 | 00 | 1 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
5899 | 001061 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 0 | 131242-WSD11-QA-E-0024-0 | 2025-02-20 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-03-20 | 2025-02-25 | Not Approved | 2025-03-17 | YES | Resubmitted |  | 131242-WSD11-QA-0024 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 5 | NAP | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | Rejected | REJ |  |  | 0 | NAP | NAP
5900 | 001061 | 01 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 1 | 131242-WSD11-QA-E-0024-1 | 2025-03-10 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSD11-QA-0024 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 23 | AWC | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | Rejected | REJ |  |  | 0 | AWC | AWC
5901 | 001061 | 02 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 2 | 131242-WSD11-QA-E-0024-2 | 2025-04-11 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2025-05-01 | 2025-05-12 | Approved with Comments | 2025-05-30 | YES | Resubmitted |  | 131242-WSD11-QA-0024 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-25 | 31 | AWC | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | Rejected | REJ |  |  | 0 | AWC | AWC
5902 | 001061 | 03 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 3 | 131242-WSD11-QA-E-0024-3 | 2025-05-02 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-05-12 | Approved with Comments | 2025-05-30 | YES | Resubmitted |  | 131242-WSD11-QA-0024 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-16 | 10 | AWC | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | Rejected | REJ |  |  | 0 | AWC | AWC
5903 | 001061 | 04 | Danapal | QAQC | NA | 131242 | WSD11 | QA | E | 0024 | 4 | 131242-WSD11-QA-E-0024-4 | 2025-06-28 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight) | Rev 4: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-07-17 | 2025-07-23 | Rejected | 2025-08-12 | NO | Overdue |  | 131242-WSD11-QA-0024 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B (Sunlight)" && "Vendor Manufacturing Inspection and test plan and FATprocedure for Progressive Cavity Pumps (CAMBI) " | 2024-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-12 | 25 | REJ | 2025-06-28 | 4 | 000915&&001061 | 2024-12-18, 2025-02-20, 2025-03-10, 2025-04-11, 2025-05-02, 2025-06-28 | 00, 01, 02, 03, 04 | 6 | Rejected | REJ | 2025-08-12 | Overdue | 0 | REJ | REJ
5904 | 001062 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0007 | 0 | 131242-WSD11-QA-I-0007-0 | 2025-02-20 | Inspection and Test plan for THP air Compressor System Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-03-20 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WSD11-QA-0007 | NA | "Inspection and Test plan for THP air Compressor System Pressure Transmitter " | 2025-02-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 99 | AWC | 2025-02-20 | 0 | 001062 | 2025-02-20 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
5905 | 001063 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | E | 0001 | A | 131242-WST02-DR-E-0001-A | 2025-02-21 | SSN Drawing Index (Cable Tray Layout) | Rev 0: Rejected. Refer to attached file for comments to note. | 2025-03-21 | 2025-05-06 | Rejected |  | YES | NA |  | 131242-WST02-DR-0001 | NA | "Drawing Index (Building and Services Mech.)" && "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-07 | 74 | REJ | 2025-02-21 | A | 000779&&001002&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00 | 4 | Rejected | REJ | 2025-05-26 | Overdue | 0 | REJ | REJ
5906 | 001064 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 0001 | A | 131242-WST02-DR-I-0001-A | 2025-02-21 | SSN Drawing Index (Instrument Layout) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-21 | 2025-05-07 | Not Approved | 2025-05-27 | NO | Overdue |  | 131242-WST02-DR-0001 | NA | "Drawing Index (Building and Services Mech.)" && "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-07 | 75 | NAP | 2025-02-21 | A | 000779&&001002&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00 | 4 | Rejected | REJ | 2025-05-27 | Overdue | 0 | NAP | NAP
5907 | 001065 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0053 | 0 | 131242-WSD11-QA-M-0053-0 | 2025-02-21 | Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton) | Rev 0: Approved | 2025-03-21 | 2025-04-02 | Approved |  | YES | NA |  | 131242-WSD11-QA-0053 | NA | "Vendor Manufacturing Inspection test plan and test procedure for Auto ball valves (Compressed air system) (Heaton)" | 2025-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-13 | 40 | APP | 2025-02-21 | 0 | 001065 | 2025-02-21 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5908 | 001066 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0026 | 0 | 131242-WSW41-VI-M-0026-0 | 2025-02-21 | Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-21 | 2025-04-02 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0026 | NA | "Preliminary Design and Vendor Approval for Rectangular Bellow (Willbrandt KG, Eriks)" | 2025-02-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-13 | 40 | AWC | 2025-02-21 | 0 | 001066 | 2025-02-21 | 00 | 1 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
5909 | 001067 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0026 | 0 | 131242-WSD11-DS-M-0026-0 | 2025-02-21 | Data Sheet for Steam Sparger G2D Inlet Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-21 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WSD11-DS-0026 | NA | "Data Sheet for Steam Sparger G2D Inlet Control Valve" | 2025-02-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-13 | 66 | AWC | 2025-02-21 | 0 | 001067 | 2025-02-21 | 00 | 1 | Approved with Comments | AWC | 2025-05-16 | Overdue | 0 | AWC | AWC
5910 | 001068 | 00 | Charles | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 0 | 131242-WSW41-MS-C-0025-0 | 2025-02-24 | MSRA, SWP for Box Out Concreting | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-24 | 2025-03-18 | Not Approved | 2025-04-07 | NO | Overdue |  | 131242-WSW41-MS-0025 | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 22 | NAP | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5911 | 001068 | 01 | Kumar | HSE | NA | 131242 | WSW41 | MS | C | 0025 | 1 | 131242-WSW41-MS-C-0025-1 | 2025-03-28 | MSRA, SWP for Box Out Concreting | R1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-04-15 | Not Approved | 2025-05-05 | NO | Overdue |  | 131242-WSW41-MS-0025 | NA | "MSRA, SWP for Box Out Concreting" && "SSN Watertank wall rectification procedure - Cementaid (S.E.A) Pte Ltd" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 18 | NAP | 2025-03-28 | 1 | 001023&&001068 | 2025-02-07, 2025-02-24, 2025-03-10, 2025-03-28 | 00, 01 | 4 | Not Approved | NAP | 2025-05-05 | Overdue | 0 | NAP | NAP
5912 | 001069 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0013 | 0 | 131242-WSW41-PO-M-0013-0 | 2025-02-24 | Unpriced PO for CSEL Pipes (MUSG) | Rev 0: For Information. | 2025-03-24 | 2025-03-27 | For Information |  | YES | NA |  | 131242-WSW41-PO-0013 | NA | "Unpriced PO for CSEL Pipes (MUSG)" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) " | 2025-02-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-16 | 31 | INF | 2025-08-22 | 0 | 001069&&001503&&001611 | 2025-02-24, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
5913 | 001070 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0005 | 0 | 131242-WSW41-PO-E-0005-0 | 2025-02-24 | Unpriced PO for Cable Raceway (United-U Li) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSW41-PO-0005 | NA | "Unpriced PO for Cable Raceway (United-U Li) " && "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" && "Unpriced PO for Sludge Pump (Netzsch) " | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-10 | 17 | INF | 2025-08-01 | 0 | 000548&&001070&&001504&&001516 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
5914 | 001071 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0006 | 0 | 131242-WSW41-PO-E-0006-0 | 2025-02-24 | Unpriced PO for Cable Raceway (Jebsen & Jessen) | Rev 0: For Information. | 2025-03-24 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSW41-PO-0006 | NA | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" && "Unpriced PO for cPVC Pipes (George Fischer)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-10 | 17 | INF | 2025-08-01 | 0 | 000549&&001071&&001505&&001517 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
5915 | 001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0039 | 0 | 131242-WSW41-MI-C-0039-0 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | For Information |  | YES | NA |  | 131242-WSW41-MI-0039 | NA | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 14 | INF | 2025-02-25 | 0 | 001072 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-03-31 | Overdue | 0 | INF | INF
5916 | 001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0040 | 0 | 131242-WSW41-MI-C-0040-0 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | For Information |  | YES | NA |  | 131242-WSW41-MI-0040 | NA | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 14 | INF | 2025-02-25 | 0 | 001072 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-03-31 | Overdue | 0 | INF | INF
5917 | 001072 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0041 | 0 | 131242-WSW41-MI-C-0041-0 | 2025-02-25 | CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025 | For information. | 2025-03-25 | 2025-03-11 | For Information |  | YES | NA |  | 131242-WSW41-MI-0041 | NA | "CSA Meeting Minutes 0039,40,41_0901, 2301 and 0502 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 14 | INF | 2025-02-25 | 0 | 001072 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-03-31 | Overdue | 0 | INF | INF
5918 | 001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 7000 | A | 131242-WSD11-DR-BF-7000-A | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 28 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
5919 | 001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000-A | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 28 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
5920 | 001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001-A | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 28 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
5921 | 001073 | 00 | Kyaw Myo | BS | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000-A | 2025-02-25 | THP-Dry Riser System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-25 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 28 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
5922 | 001074 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | E | 0025 | 0 | 131242-WSD11-QA-E-0025-0 | 2025-02-26 | FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch | Rev 0: Approved. | 2025-03-26 | 2025-05-06 | Approved |  | YES | NA |  | 131242-WSD11-QA-0025 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) 3rd batch" | 2025-02-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 69 | APP | 2025-02-26 | 0 | 001074 | 2025-02-26 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5923 | 001075 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0020 | 0 | 131242-WST02-QA-A-0020-0 | 2025-02-27 | Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd) | For Information | 2025-03-27 | 2025-04-11 | Approved |  | YES | NA |  | 131242-WST02-QA-0020 | NA | "SAT Procedure for Public Address System" && "Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd)" | 2025-02-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-19 | 43 | APP | 2025-12-18 | 0 | 001075&&001909 | 2025-02-27, 2025-12-18 | 00 | 2 | Not Approved | NAP |  |  | 0 | APP | APP
5924 | 001076 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8000 | 0 | 131242-WST02-CL-BH-8000-0 | 2025-02-27 | Fan Static Load Calculation (SSN Electrical Building) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-CL-8000 | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-13 | 26 | AWC | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2025-04-14 | Overdue | 0 | AWC | AWC
5925 | 001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620_BCA | D | 131242-WSD11-DR-S-1600_ST620_BCA-D | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-1600_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-14 | 13 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF | 2025-04-02 | Overdue | 0 | INF | INF
5926 | 001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620_BCA | D | 131242-WSD11-DR-S-1601_ST620_BCA-D | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-1601_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-14 | 13 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF | 2025-04-02 | Overdue | 0 | INF | INF
5927 | 001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620_BCA | D | 131242-WSD11-DR-S-5600_ST620_BCA-D | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-5600_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-14 | 13 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF | 2025-04-02 | Overdue | 0 | INF | INF
5928 | 001077 | 00 | Franklin | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620_BCA | D | 131242-WSD11-DR-S-5601_ST620_BCA-D | 2025-02-28 | BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m) | For information. | 2025-03-28 | 2025-03-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-5601_ST620_BCA | NA | "BCA Approval of ST620 (Air Compressor's Ducting Support, and THP pipe support >2m)" && "BCA Submission of ST620 (BCA submission for Air Compressor's Ducting Support, and THP pipe support >2m)" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-03-14 | 13 | INF | 2025-02-28 | D | 001058&&001077 | 2025-02-19, 2025-02-28 | 00 | 2 | For Information | INF | 2025-04-02 | Overdue | 0 | INF | INF
5929 | 001078 | 00 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 0 | 131242-WST02-QA-A-0019-0 | 2025-02-28 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-28 | 2025-04-06 | Not Approved | 2025-04-24 | YES | Resubmitted |  | 131242-WST02-QA-0019 | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-14 | 37 | NAP | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5930 | 001078 | 01 | N.Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0019 | 1 | 131242-WST02-QA-A-0019-1 | 2025-04-09 | Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-29 | 2025-05-27 | Not Approved | 2025-06-16 | NO | Overdue |  | 131242-WST02-QA-0019 | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 48 | NAP | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
5931 | 001079 | 00 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5751 | 0 | 131242-WST02-CL-P-5751-0 | 2025-02-28 | C4B SSN Pressure Reducing Valve Calculations | Rev 0: Approved | 2025-03-28 | 2025-04-28 | Approved |  | YES | NA |  | 131242-WST02-CL-5751 | NA | "C4B SSN Pressure Reducing Valve Calculations" | 2025-02-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-20 | 59 | APP | 2025-02-28 | 0 | 001079 | 2025-02-28 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5932 | 001080 | 00 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 0 | 131242-WST02-DS-M-5751-0 | 2025-02-28 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-28 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DS-5751 | NA | "C4B SSN Pressure Reducing Valve Datasheet" | 2025-02-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 59 | AWC | 2025-07-07 | 1 | 001080 | 2025-02-28, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5933 | 001080 | 01 | Prachi | Process | NA | 131242 | WST02 | DS | M | 5751 | 1 | 131242-WST02-DS-M-5751-1 | 2025-07-07 | C4B SSN Pressure Reducing Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5751 | NA | "C4B SSN Pressure Reducing Valve Datasheet" | 2025-02-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001080 | 2025-02-28, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
5934 | 001081 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 0 | 131242-WSD11-VI-M-0003-0 | 2025-03-03 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-31 | 2025-03-04 | Approved with Comments | 2025-03-24 | YES | Resubmitted |  | 131242-WSD11-VI-0003 | NA | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | 2025-03-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-23 | 1 | AWC | 2025-03-14 | 1 | 001081 | 2025-03-03, 2025-03-14 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5935 | 001081 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0003 | 1 | 131242-WSD11-VI-M-0003-1 | 2025-03-14 | Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-02 | Approved with Comments | 2025-04-22 | NO | Overdue |  | 131242-WSD11-VI-0003 | NA | "Preliminary Design and Vendor Approval document of G1 and G2D Booster Pumps (Cambi Supply) (KSB)" | 2025-03-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 19 | AWC | 2025-03-14 | 1 | 001081 | 2025-03-03, 2025-03-14 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
5936 | 001082 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | S | 0010 | 0 | 131242-WST02-VI-S-0010-0 | 2025-03-03 | Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-03-31 | 2025-04-02 | Not Approved | 2025-04-22 | NO | Overdue |  | 131242-WST02-VI-0010 | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-17 | 30 | NAP | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
5937 | 001083 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0024 | 0 | 131242-WSD11-DS-M-0024-0 | 2025-03-04 | Ring Circulation Pump Data Sheet | Rev 0: Approved | 2025-04-01 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0024 | NA | "Ring Circulation Pump Data Sheet" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-24 | 216 | APP | 2025-03-04 | 0 | 001083 | 2025-03-04 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5938 | 001084 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0028 | 0 | 131242-WSD11-CL-P-0028-0 | 2025-03-04 | Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-07-08 | Approved with Comments | 2025-07-28 | NO | Overdue |  | 131242-WSD11-CL-0028 | NA | "Digester Feed Pump & Ring Circulation Pump Pressure Loss Calculation" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 126 | AWC | 2025-03-04 | 0 | 001084 | 2025-03-04 | 00 | 1 | Approved with Comments | AWC | 2025-07-28 | Overdue | 0 | AWC | AWC
5939 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 0301 | A1 | 131242-WSW41-SD-S-0301-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-0301 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5940 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1101 | A1 | 131242-WSW41-SD-S-1101-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1101 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5941 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1102 | A1 | 131242-WSW41-SD-S-1102-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1102 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5942 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1103 | A1 | 131242-WSW41-SD-S-1103-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1103 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5943 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1104 | A1 | 131242-WSW41-SD-S-1104-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1104 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5944 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1105 | A1 | 131242-WSW41-SD-S-1105-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1105 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5945 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1106 | A1 | 131242-WSW41-SD-S-1106-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1106 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5946 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1107 | A1 | 131242-WSW41-SD-S-1107-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1107 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5947 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 1108 | A1 | 131242-WSW41-SD-S-1108-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-1108 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5948 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2100 | A1 | 131242-WSW41-SD-S-2100-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-2100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5949 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2101 | A1 | 131242-WSW41-SD-S-2101-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-2101 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5950 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 2102 | A1 | 131242-WSW41-SD-S-2102-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-2102 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5951 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 3100 | A1 | 131242-WSW41-SD-S-3100-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-3100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" | 2024-07-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-18 | 97 | NAP | 2025-12-17 | X | 000581&&001085&&001906 | 2024-07-23, 2025-03-04, 2025-12-17 | 00 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
5952 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 3101 | A1 | 131242-WSW41-SD-S-3101-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-3101 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5953 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5100 | A1 | 131242-WSW41-SD-S-5100-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5954 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5101 | A1 | 131242-WSW41-SD-S-5101-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5101 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5955 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5102 | A1 | 131242-WSW41-SD-S-5102-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5102 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5956 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5103 | A1 | 131242-WSW41-SD-S-5103-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5103 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5957 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5104 | A1 | 131242-WSW41-SD-S-5104-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5104 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5958 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5105 | A1 | 131242-WSW41-SD-S-5105-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5105 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5959 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 5106 | A1 | 131242-WSW41-SD-S-5106-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-5106 | NA | "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-03-04 | A1 | 001085 | 2025-03-04 | 00 | 1 | Not Approved | NAP | 2025-06-27 | Overdue | 0 | NAP | NAP
5960 | 001085 | 00 | Franklin | CSA | NA | 131242 | WSW41 | SD | S | 8002 | A1 | 131242-WSW41-SD-S-8002-A1 | 2025-03-04 | Shop Drawing of ST614_Side Wide Pipe Rack 03 | Not Approved - Revise and resubmit | 2025-04-01 | 2025-06-09 | Not Approved | 2025-06-27 | NO | Overdue |  | 131242-WSW41-SD-8002 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 97 | NAP | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5961 | 001086 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0055 | 0 | 131242-WST02-QA-M-0055-0 | 2025-03-04 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch) | Rev 0: Approved | 2025-04-01 | 2025-04-30 | Approved |  | YES | NA |  | 131242-WST02-QA-0055 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch)" && "Factory Acceptance Test Report for Rotameter" | 2025-03-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-24 | 57 | APP | 2025-09-09 | 0 | 001086&&001662 | 2025-03-04, 2025-09-09 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
5962 | 001087 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0011 | 0 | 131242-WST02-QA-E-0011-0 | 2025-03-05 | FAT report for Cable Ladder 1st batch (United ULI) | For information | 2025-04-02 | 2025-05-05 | Approved |  | YES | NA |  | 131242-WST02-QA-0011 | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-19 | 61 | APP | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
5963 | 001088 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0033 | 0 | 131242-WSD11-VI-M-0033-0 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | Rejected |  | YES | NA |  | 131242-WSD11-VI-0033 | NA | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings - ANN AIK LIMITED" | 2025-03-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-25 | 13 | REJ | 2025-03-05 | 0 | 001088 | 2025-03-05 | 00 | 1 | Rejected | REJ | 2025-04-07 | Overdue | 0 | REJ | REJ
5964 | 001089 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0034 | 0 | 131242-WSD11-VI-M-0034-0 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | Rejected |  | YES | NA |  | 131242-WSD11-VI-0034 | NA | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – SALIRAN INDUSTRIAL SUPPLIES SDN. BHD " | 2025-03-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-25 | 13 | REJ | 2025-03-05 | 0 | 001089 | 2025-03-05 | 00 | 1 | Rejected | REJ | 2025-04-07 | Overdue | 0 | REJ | REJ
5965 | 001090 | 00 | K. Balaji | Const; | NA | 131242 | WSD11 | VI | M | 0035 | 0 | 131242-WSD11-VI-M-0035-0 | 2025-03-05 | Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES | Rev 0: Rejected | 2025-04-02 | 2025-03-18 | Rejected |  | YES | NA |  | 131242-WSD11-VI-0035 | NA | "Vendor Approval of Stainless Steel & Carbon Steel Pipes & Fittings – LCS ENGINEERING INDUSTRIAL SUPPLIES" | 2025-03-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-25 | 13 | REJ | 2025-03-05 | 0 | 001090 | 2025-03-05 | 00 | 1 | Rejected | REJ | 2025-04-07 | Overdue | 0 | REJ | REJ
5966 | 001091 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0054 | 0 | 131242-WSW41-QA-M-0054-0 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-03-25 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0054 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Spray Nozzles (PNR Italia SrL)" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 19 | AWC | 2025-03-06 | 0 | 001091 | 2025-03-06 | 00 | 1 | Approved with Comments | AWC | 2025-04-14 | Overdue | 0 | AWC | AWC
5967 | 001092 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0028 | 0 | 131242-WSD11-DS-M-0028-0 | 2025-03-06 | Manual Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0028 | NA | "Manual Gate Valve Data Sheet (Cambi Supply)" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 214 | APP | 2025-03-06 | 0 | 001092 | 2025-03-06 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5968 | 001093 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0029 | 0 | 131242-WSD11-DS-M-0029-0 | 2025-03-06 | Manual Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-03 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0029 | NA | "Manual Ball Valve Data Sheet (Cambi Supply)" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 214 | APP | 2025-03-06 | 0 | 001093 | 2025-03-06 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5969 | 001094 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0030 | 0 | 131242-WSD11-DS-M-0030-0 | 2025-03-06 | Manual Globe Valve Data Sheet (Cambi Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | Approved with Comments | 2025-07-28 | NO | Overdue |  | 131242-WSD11-DS-0030 | NA | "Manual Globe Valve Data Sheet (Cambi Supply)" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 124 | AWC | 2025-03-06 | 0 | 001094 | 2025-03-06 | 00 | 1 | Approved with Comments | AWC | 2025-07-28 | Overdue | 0 | AWC | AWC
5970 | 001095 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | E | 1395 | 0 | 131242-WSW41-DS-E-1395-0 | 2025-03-06 | Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) | Rev 0: Approved with comments. Please refer to attached file for comments to note. | 2025-04-03 | 2025-05-05 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DS-1395 | NA | "Sample Board Submission for Thermoplastic Cable Ladder,Tary and Accessories (Jebsen & Jessen-Unex) " | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 60 | AWC | 2025-03-06 | 0 | 001095 | 2025-03-06 | 00 | 1 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
5971 | 001096 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0056 | 0 | 131242-WST02-QA-M-0056-0 | 2025-03-06 | FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved | 2025-04-03 | 2025-03-21 | Approved |  | YES | NA |  | 131242-WST02-QA-0056 | NA | " Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN)" && "FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 15 | APP | 2025-09-30 | 0 | 001096&&001705 | 2025-03-06, 2025-09-30 | 00 | 2 | Not Approved | NAP |  |  | 0 | APP | APP
5972 | 001097 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSD11 | QA | I | 0026 | 0 | 131242-WSD11-QA-I-0026-0 | 2025-03-06 | FAT report for Pressure transmitter (Air compressor) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WSD11-QA-0026 | NA | "FAT report for Pressure transmitter (Air compressor)" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 85 | AWC | 2025-03-06 | 0 | 001097 | 2025-03-06 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
5973 | 001098 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0014 | 0 | 131242-WSW41-PO-M-0014-0 | 2025-03-06 | Unpriced PO for HDPE Pipes (AGRU) | Rev 0 for information | 2025-04-03 | 2025-03-27 | For Information |  | YES | NA |  | 131242-WSW41-PO-0014 | NA | "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for HDPE Pipes (AGRU) " && "Unpriced PO for Thermal Flow Switch (Endress & Hauser) " | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-26 | 21 | INF | 2025-08-22 | 0 | 001098&&001504&&001612 | 2025-03-06, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
5974 | 001099 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 0 | 131242-WST02-CD-I-0009-0 | 2025-03-06 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | Approved with Comments | 2025-05-12 | YES | Resubmitted |  | 131242-WST02-CD-0009 | NA | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 47 | AWC | 2025-08-19 | 2 | 001099 | 2025-03-06, 2025-06-16, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5975 | 001099 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 1 | 131242-WST02-CD-I-0009-1 | 2025-06-16 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | Approved with Comments | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-CD-0009 | NA | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 24 | AWC | 2025-08-19 | 2 | 001099 | 2025-03-06, 2025-06-16, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5976 | 001099 | 02 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0009 | 2 | 131242-WST02-CD-I-0009-2 | 2025-08-19 | SSN -RIO PANEL 0001A/0001B- I/O List | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-CD-0009 | NA | "SSN -RIO PANEL 0001A/0001B- I/O List " | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 35 | AWC | 2025-08-19 | 2 | 001099 | 2025-03-06, 2025-06-16, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
5977 | 001100 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 0 | 131242-WST02-CD-I-0008-0 | 2025-03-06 | SSN Aeration Blowers I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-03 | 2025-04-22 | Not Approved | 2025-05-12 | YES | Resubmitted |  | 131242-WST02-CD-0008 | NA | "SSN Aeration Blowers I/O List" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 47 | NAP | 2025-07-11 | 1 | 001100 | 2025-03-06, 2025-07-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5978 | 001100 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0008 | 1 | 131242-WST02-CD-I-0008-1 | 2025-07-11 | SSN Aeration Blowers I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-CD-0008 | NA | "SSN Aeration Blowers I/O List" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-07-11 | 1 | 001100 | 2025-03-06, 2025-07-11 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
5979 | 001101 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0011 | 0 | 131242-WST02-RT-E-0011-0 | 2025-03-07 | SSN Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | Approved with Comments | 2025-05-27 | NO | Overdue |  | 131242-WST02-RT-0011 | NA | "SSN Motor Starting Study Report " | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 61 | AWC | 2025-03-07 | 0 | 001101 | 2025-03-07 | 00 | 1 | Approved with Comments | AWC | 2025-05-27 | Overdue | 0 | AWC | AWC
5980 | 001102 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0006 | 0 | 131242-WSD11-RT-E-0006-0 | 2025-03-07 | THP Motor Starting Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-04 | 2025-05-07 | Approved with Comments | 2025-05-27 | NO | Overdue |  | 131242-WSD11-RT-0006 | NA | "THP Motor Starting Study Report " | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 61 | AWC | 2025-03-07 | 0 | 001102 | 2025-03-07 | 00 | 1 | Approved with Comments | AWC | 2025-05-27 | Overdue | 0 | AWC | AWC
5981 | 001103 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0032 | 0 | 131242-WSD11-DS-M-0032-0 | 2025-03-07 | ON OFF Gate Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0032 | NA | "ON OFF Gate Valve Data Sheet (Cambi Supply)" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-27 | 213 | APP | 2025-03-07 | 0 | 001103 | 2025-03-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5982 | 001104 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0033 | 0 | 131242-WSD11-DS-M-0033-0 | 2025-03-07 | ON OFF Ball Valve Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0033 | NA | "ON OFF Ball Valve Data Sheet (Cambi Supply)" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-27 | 213 | APP | 2025-03-07 | 0 | 001104 | 2025-03-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5983 | 001105 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0034 | 0 | 131242-WSD11-DS-M-0034-0 | 2025-03-07 | ON OFF Ball Valve PN25 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0034 | NA | "ON OFF Ball Valve PN25 Data Sheet (Cambi Supply)" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-27 | 213 | APP | 2025-03-07 | 0 | 001105 | 2025-03-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5984 | 001106 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0035 | 0 | 131242-WSD11-DS-M-0035-0 | 2025-03-07 | ON OFF Ball Valve PN40 Data Sheet (Cambi Supply) | Rev 0: Approved | 2025-04-04 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0035 | NA | "ON OFF Ball Valve PN40 Data Sheet (Cambi Supply)" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-27 | 213 | APP | 2025-03-07 | 0 | 001106 | 2025-03-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
5985 | 001107 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0022 | 0 | 131242-WSW41-RT-PM-0022-0 | 2025-03-10 | C4B Monthly Progress Report Number No.22 (02 25) | Rev. 0 - Approved with comments (need to re-submit / see attached comment sheet) | 2025-04-07 | 2025-03-27 | Approved with Comments | 2025-04-16 | NO | Overdue |  | 131242-WSW41-RT-0022 | NA | "C4B Monthly Progress Report Number No.22 (02 25) " | 2025-03-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-30 | 17 | AWC | 2025-03-10 | 0 | 001107 | 2025-03-10 | 00 | 1 | Approved with Comments | AWC | 2025-04-16 | Overdue | 0 | AWC | AWC
5986 | 001108 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 0 | 131242-WST02-VI-B-0003-0 | 2025-03-10 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 15 | AWC | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
5987 | 001108 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0003 | 1 | 131242-WST02-VI-B-0003-1 | 2025-08-22 | Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 227 | PEN | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC | 2025-10-09 |  | 0 | PEN | PEN
5988 | 001109 | 00 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 0 | 131242-WST02-VI-B-0002-0 | 2025-03-10 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-07 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 15 | AWC | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
5989 | 001109 | 01 | Karthikeyan | BS | NA | 131242 | WST02 | VI | B | 0002 | 1 | 131242-WST02-VI-B-0002-1 | 2025-04-18 | Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-08 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-02 | 18 | AWC | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
5990 | 001110 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0053 | 0 | 131242-WSW41-CD-IM-0053-0 | 2025-03-10 | Submission of BIM Coordination VCM Model (Feb 2025) | For information. | 2025-04-07 | 2025-03-25 | For Information |  | YES | NA |  | 131242-WSW41-CD-0053 | NA | " Submission of BIM Coordination VCM Model (Feb 2025) " | 2025-03-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-30 | 15 | INF | 2025-03-10 | 0 | 001110 | 2025-03-10 | 00 | 1 | For Information | INF | 2025-04-14 | Overdue | 0 | INF | INF
5991 | 001111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0020 | 0 | 131242-WSW41-PC-W-0020-0 | 2025-03-10 | Payment Claim No.20 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-04-07 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSW41-PC-0020 | NA | "Payment Claim No.20" | 2025-03-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-30 | 48 | INF | 2025-03-10 | 0 | 001111 | 2025-03-10 | 00 | 1 | For Information | INF | 2025-05-15 | Overdue | 0 | INF | INF
5992 | 001112 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 0 | 131242-WST02-DR-I-7209-0 | 2025-03-10 | SSN PMS Network Architecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-07 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-7209 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN PMS Network Architecture Drawings" | 2025-03-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-30 | 58 | NAP | 2025-08-07 | 1 | 001112&&001157 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
5993 | 001112 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7209 | 1 | 131242-WST02-DR-I-7209-1 | 2025-08-07 | SSN PMS Network Architecture Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-23 | Approved with Comments | 2025-11-12 | NO | Overdue |  | 131242-WST02-DR-7209 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN PMS Network Architecture Drawings" | 2025-03-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 77 | AWC | 2025-08-07 | 1 | 001112&&001157 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01 | 4 | Approved with Comments | AWC | 2025-11-12 | Overdue | 0 | AWC | AWC
5994 | 001113 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 0 | 131242-WST02-VI-BP-0001-0 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-04-07 | 2025-03-28 | Not Approved | 2025-04-17 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 18 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
5995 | 001113 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 1 | 131242-WST02-VI-BP-0001-1 | 2025-03-10 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2025-03-28 | 2025-05-29 | Not Approved | 2025-06-18 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 80 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
5996 | 001113 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BP | 0001 | 2 | 131242-WST02-VI-BP-0001-2 | 2026-02-05 | Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY | Rev 0: Not approved - Revise and Resubmit | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-19 | 60 | PEN | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | PEN | PEN
5997 | 001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3015 | A | 131242-WST02-SD-A-3015-A | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 | Not Approved | 2025-04-22 | NO | Overdue |  | 131242-WST02-SD-3015 | NA | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " | 2025-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 22 | NAP | 2025-06-12 | A | 001114&&001356 | 2025-03-11, 2025-06-12 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
5998 | 001114 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1015 | A | 131242-WST02-SD-A-1015-A | 2025-03-11 | Shop Drawings for Siphonic System (Fast Flow) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-08 | 2025-04-02 | Not Approved | 2025-04-22 | NO | Overdue |  | 131242-WST02-SD-1015 | NA | "Shop Drawings for Siphonic System (Fast Flow)" | 2025-03-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 22 | NAP | 2025-03-11 | A | 001114 | 2025-03-11 | 00 | 1 | Not Approved | NAP | 2025-04-22 | Overdue | 0 | NAP | NAP
5999 | 001115 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0007 | 0 | 131242-WSW41-PO-E-0007-0 | 2025-03-11 | Unpriced PO for Cable Support System (Jiangsu HDMann) | Rev 0: For Information. | 2025-04-08 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSW41-PO-0007 | NA | "Unpriced PO for Cable Support System (Jiangsu HDMann) " && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | 2024-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-25 | 47 | INF | 2025-08-01 | 0 | 000595&&001115&&001506 | 2024-07-30, 2025-03-11, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
6000 | 001116 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0057 | 0 | 131242-WSD11-QA-M-0057-0 | 2025-03-12 | FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-09 | 2025-03-21 | Approved with Comments | 2025-04-10 | NO | Overdue |  | 131242-WSD11-QA-0057 | NA | "FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) " && "Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP)" | 2025-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 9 | AWC | 2025-10-06 | 0 | 001116&&001726 | 2025-03-12, 2025-10-06 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6001 | 001117 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 0 | 131242-WST02-CD-I-0010-0 | 2025-03-12 | SSN -RIO PANEL 0202- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-09 | 2025-04-22 | Not Approved | 2025-05-12 | YES | Resubmitted |  | 131242-WST02-CD-0010 | NA | "SSN -RIO PANEL 0202- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 41 | NAP | 2025-06-18 | 1 | 000183&&001117 | 2023-11-10, 2025-03-12, 2025-06-18 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6002 | 001117 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0010 | 1 | 131242-WST02-CD-I-0010-1 | 2025-06-18 | SSN -RIO PANEL 0202- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WST02-CD-0010 | NA | "SSN -RIO PANEL 0202- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 76 | AWC | 2025-06-18 | 1 | 000183&&001117 | 2023-11-10, 2025-03-12, 2025-06-18 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
6003 | 001118 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2007 | 0 | 131242-WSW41-VI-M-2007-0 | 2025-03-12 | Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-09 | 2025-07-08 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-2007 | NA | "Preliminary Design and Vendor Approval Document – SSN Automatic Condensate Drain" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-01 | 118 | AWC | 2025-03-12 | 0 | 001118 | 2025-03-12 | 00 | 1 | Approved with Comments | AWC | 2025-07-28 | Overdue | 0 | AWC | AWC
6004 | 001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_LTA_NPKS | A | 131242-WSD11-DR-A-1002_LTA_NPKS-A | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1002_LTA_NPKS | NA | "THP LTA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001119 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6005 | 001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_LTA_NPKS | A | 131242-WSD11-DR-A-1003_LTA_NPKS-A | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1003_LTA_NPKS | NA | "THP LTA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001119 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6006 | 001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_LTA_NPKS | A | 131242-WSD11-DR-A-1004_LTA_NPKS-A | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1004_LTA_NPKS | NA | "THP LTA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001119 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6007 | 001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_LTA_NPKS | A | 131242-WSD11-DR-A-2000_LTA_NPKS-A | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-2000_LTA_NPKS | NA | "THP LTA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001119 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6008 | 001119 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_LTA_NPKS | A | 131242-WSD11-DR-A-3000_LTA_NPKS-A | 2025-03-12 | THP LTA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-3000_LTA_NPKS | NA | "THP LTA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001119 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6009 | 001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_PUB | A | 131242-WSD11-DR-A-1002_PUB-A | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1002_PUB | NA | "THP PUB Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001120 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6010 | 001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_PUB | A | 131242-WSD11-DR-A-1003_PUB-A | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1003_PUB | NA | "THP PUB Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001120 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6011 | 001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_PUB | A | 131242-WSD11-DR-A-1004_PUB-A | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1004_PUB | NA | "THP PUB Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001120 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6012 | 001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_PUB | A | 131242-WSD11-DR-A-2000_PUB-A | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-2000_PUB | NA | "THP PUB Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001120 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6013 | 001120 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_PUB | A | 131242-WSD11-DR-A-3000_PUB-A | 2025-03-12 | THP PUB Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-3000_PUB | NA | "THP PUB Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001120 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6014 | 001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_NEA | A | 131242-WSD11-DR-A-1002_NEA-A | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1002_NEA | NA | "THP NEA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001121 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6015 | 001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_NEA | A | 131242-WSD11-DR-A-1003_NEA-A | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1003_NEA | NA | "THP NEA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001121 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6016 | 001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_NEA | A | 131242-WSD11-DR-A-1004_NEA-A | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1004_NEA | NA | "THP NEA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001121 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6017 | 001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_NEA | A | 131242-WSD11-DR-A-2000_NEA-A | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-2000_NEA | NA | "THP NEA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001121 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6018 | 001121 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_NEA | A | 131242-WSD11-DR-A-3000_NEA-A | 2025-03-12 | THP NEA Submission | Not Approved - Revise and resubmit | 2025-04-09 | 2025-06-11 | Not Approved | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-3000_NEA | NA | "THP NEA Submission" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 91 | NAP | 2025-03-12 | A | 001121 | 2025-03-12 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
6019 | 001122 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0056 | 0 | 131242-WSW41-LT-PM-0056-0 | 2025-03-13 | NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings | For Information. Please refer to S.O. correspondence no. 353 dated 28 May 2025. | 2025-04-10 | 2025-08-25 | For Information |  | YES | NA |  | 131242-WSW41-LT-0056 | NA | "NOTICE Extension of Time and Cost for C3A/3B1 E Duct Work Delays to the Electrical and Transformer Buildings" | 2025-03-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-02 | 165 | INF | 2025-03-13 | 0 | 001122 | 2025-03-13 | 00 | 1 | For Information | INF | 2025-09-12 | Overdue | 0 | INF | INF
6020 | 001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | A | 131242-WST02-DR-M-5484-A | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-5484 | NA | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-02 | 45 | AWC | 2025-07-07 | B | 001123 | 2025-03-13, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6021 | 001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5481 | A | 131242-WST02-DR-M-5481-A | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-5481 | NA | "Hookup Drawing - Hydrostatic Level Switch" && "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-02 | 45 | AWC | 2025-09-24 | A | 001123&&001691 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
6022 | 001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5482 | A | 131242-WST02-DR-M-5482-A | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-5482 | NA | "Hookup Drawing - Hydrostatic Level Switch" && "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-02 | 45 | AWC | 2025-09-24 | A | 001123&&001691 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
6023 | 001123 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5483 | A | 131242-WST02-DR-M-5483-A | 2025-03-13 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-10 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-5483 | NA | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-02 | 45 | AWC | 2025-07-07 | B | 001123 | 2025-03-13, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6024 | 001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5484 | B | 131242-WST02-DR-M-5484-B | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WST02-DR-5484 | NA | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 207 | AWC | 2025-07-07 | B | 001123 | 2025-03-13, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
6025 | 001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5481 | B | 131242-WST02-DR-M-5481-B | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WST02-DR-5481 | NA | "Hookup Drawing - Hydrostatic Level Switch" && "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 207 | AWC | 2025-09-24 | A | 001123&&001691 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
6026 | 001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5482 | B | 131242-WST02-DR-M-5482-B | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WST02-DR-5482 | NA | "Hookup Drawing - Hydrostatic Level Switch" && "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 207 | AWC | 2025-09-24 | A | 001123&&001691 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
6027 | 001123 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5483 | B | 131242-WST02-DR-M-5483-B | 2025-07-07 | Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WST02-DR-5483 | NA | "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 207 | AWC | 2025-07-07 | B | 001123 | 2025-03-13, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
6028 | 001124 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 5483 | 0 | 131242-WSD11-QA-M-5483-0 | 2025-03-14 | Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON) | Rev 0: Approved | 2025-04-11 | 2025-07-08 | Approved |  | YES | NA |  | 131242-WSD11-QA-5483 | NA | "Function test report for pneumatic actuated valve (on-off valve) & Material Test certificate EN 10204-3.1 for Manual ball valves for Compressed Air System (OVS/HEATON)" | 2025-03-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-03 | 116 | APP | 2025-03-14 | 0 | 001124 | 2025-03-14 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
6029 | 001125 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2003 | 0 | 131242-WSW41-VI-M-2003-0 | 2025-03-14 | Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-11 | 2025-04-27 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-2003 | NA | "Preliminary Design and Vendor Approval document - Safety Relief Valve (ARI-Armturen)" | 2025-03-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-03 | 44 | AWC | 2025-03-14 | 0 | 001125 | 2025-03-14 | 00 | 1 | Approved with Comments | AWC | 2025-05-15 | Overdue | 0 | AWC | AWC
6030 | 001126 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0026 | 0 | 131242-WSW41-MS-C-0026-0 | 2025-03-14 | SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd. | R0: As communicated, CES would like to withdraw the submittal as CES has no intention to use the proposed materials for grouting. Hence, this submittal is rejected and no resubmission is required. | 2025-04-11 | 2025-06-04 | Rejected |  | YES | NA |  | 131242-WSW41-MS-0026 | NA | "SSN Watertank wall Box out Pressure Grout procedure with materials submission - Cementaid (S.E.A) Pte Ltd." | 2025-03-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-03 | 82 | REJ | 2025-03-14 | 0 | 001126 | 2025-03-14 | 00 | 1 | Rejected | REJ | 2025-06-24 | Overdue | 0 | REJ | REJ
6031 | 001127 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0005 | 0 | 131242-WSD11-DS-I-0005-0 | 2025-03-17 | Datasheet for Differential Pressure Switch (Compressed Air System) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-14 | 2025-07-10 | Approved with Comments | 2025-07-30 | NO | Overdue |  | 131242-WSD11-DS-0005 | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 115 | AWC | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC | 2025-07-30 | Overdue | 0 | AWC | AWC
6032 | 001128 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0019 | 0 | 131242-WSW41-PS-HS-0019-0 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Nov 2024 | Rev 0: Scoring confirmed to be at 70/100 | 2025-04-14 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WSW41-PS-0019 | NA | "Incentive/ Disincentive Audit Scheme for Nov 2024" && "Monthly Progress Presentation No. 19 (1224)" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-31 | 8 | APP | 2025-03-17 | 0 | 000979&&001128 | 2025-01-16, 2025-03-17 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
6033 | 001129 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | B | 0005 | 0 | 131242-WST02-VI-B-0005-0 | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-VI-0005 | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 7 | AWC | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | Approved with Comments | AWC | 2025-04-14 | Overdue | 0 | AWC | AWC
6034 | 001129 | 01 | Yuen Fatt | Project | NA | 131242 | NA | NA | NA | Cmt reply sheet | 0 | 131242----Cmt reply sheet- | 2025-03-18 | Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) | Rev 1: Approved | 2025-04-07 | 2025-05-06 | Approved |  | YES | NA |  | 131242-NA-NA-Cmt reply sheet | NA | "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " | 2025-03-18 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-04-07 | 49 | APP | 2025-03-18 | 0 | 001129 | 2025-03-18 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
6035 | 001130 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0020 | 0 | 131242-WSW41-PS-HS-0020-0 | 2025-03-18 | Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025 | Rev 0: Noted for information | 2025-04-15 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WSW41-PS-0020 | NA | "Monthly Progress Presentation No. 20 (0125)" && "Quarterly Risk Management Workshop 6th Quarterly RM Workshop – 22 Jan 2025" | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-01 | 7 | APP | 2025-03-18 | 0 | 001048&&001130 | 2025-02-18, 2025-03-18 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
6036 | 001131 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 0 | 131242-WST02-RT-S-0002-0 | 2025-03-18 | Safety Review Report for Sitewide Pipe Rack | Approved with Comments | 2025-04-15 | 2025-05-13 | Approved with Comments | 2025-06-02 | YES | Resubmitted |  | 131242-WST02-RT-0002 | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 56 | AWC | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
6037 | 001131 | 01 | Max | HSE | NA | 131242 | WST02 | RT | S | 0002 | 1 | 131242-WST02-RT-S-0002-1 | 2025-06-18 | Safety Review Report for Sitewide Pipe Rack | R1: Approved | 2025-07-08 | 2025-07-07 | Approved |  | YES | NA |  | 131242-WST02-RT-0002 | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-02 | 19 | APP | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
6038 | 001132 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 0 | 131242-WST02-QA-EI-0026-0 | 2025-03-18 | FAT Procedure for LVSG Panels (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-15 | 2025-05-07 | Approved with Comments | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-QA-0026 | NA | " Factory Acceptance Test Report for Conductivity Analyser" && "FAT Procedure for LVSG Panels (Sunlight)" && "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 50 | AWC | 2025-08-06 | 0 | 001132&&001466&&001568 | 2025-03-18, 2025-05-23, 2025-07-11, 2025-08-06 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6039 | 001132 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0026 | 1 | 131242-WST02-QA-EI-0026-1 | 2025-05-23 | FAT Procedure for LVSG Panels (Sunlight) | Rev 1: Approved. | 2025-06-12 | 2025-07-14 | Approved |  | YES | NA |  | 131242-WST02-QA-0026 | NA | " Factory Acceptance Test Report for Conductivity Analyser" && "FAT Procedure for LVSG Panels (Sunlight)" && "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-06 | 52 | APP | 2025-08-06 | 0 | 001132&&001466&&001568 | 2025-03-18, 2025-05-23, 2025-07-11, 2025-08-06 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
6040 | 001133 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | EI | 0027 | 0 | 131242-WST02-QA-EI-0027-0 | 2025-03-18 | FAT Procedure for MDB Panels (Sunlight) | Approved with Comments | 2025-04-15 | 2025-05-21 | Approved with Comments | 2025-06-10 | NO | Overdue |  | 131242-WST02-QA-0027 | NA | " FAT Procedure for MDB Panels (Sunlight)" && "Factory Acceptance Test Report for Pressure Gauges" && "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" | 2025-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 64 | AWC | 2025-07-14 | 0 | 001133&&001463&&001476 | 2025-03-18, 2025-07-11, 2025-07-14 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6041 | 001134 | 00 | Max | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 0 | 131242-WSD11-RT-S-0001-0 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-12 | Not Approved | 2025-05-30 | YES | Resubmitted |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 55 | NAP | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6042 | 001134 | 01 | Htet Nu | PMT | NA | 131242 | WSD11 | RT | S | 0001 | 1 | 131242-WSD11-RT-S-0001-1 | 2025-03-18 | Report of DFS (GUIDE 3) for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-07 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-01 | 121 | AWC | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6043 | 001135 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5801 | A | 131242-WST02-DS-M-5801-A | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-DS-5801 | NA | "SSN Spray Nozzle datasheet and drawing" | 2025-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 116 | AWC | 2025-03-20 | A | 001135 | 2025-03-20 | 00 | 1 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
6044 | 001135 | 00 | Qili | Process | NA | 131242 | WST02 | DR | M | 5801 | 0 | 131242-WST02-DR-M-5801-0 | 2025-03-20 | SSN Spray Nozzle datasheet and drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-DR-5801 | NA | "SSN Spray Nozzle datasheet and drawing" | 2025-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 116 | AWC | 2025-03-20 | 0 | 001135 | 2025-03-20 | 00 | 1 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
6045 | 001136 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | A | 5000 | A | 131242-WSW41-DR-A-5000-A | 2025-03-20 | Sitewide Piperack Handrail and Cad Ladder Layout and Details | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | Not Approved | 2025-05-27 | NO | Overdue |  | 131242-WSW41-DR-5000 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Earthing System" && "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | 2024-01-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-03 | 48 | NAP | 2026-01-19 | F | 000281&&001136&&001963 | 2024-01-23, 2025-03-20, 2026-01-19 | 00 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6046 | 001137 | 00 | Radha | QAQC | NA | 131101 | WSW41 | MM | C | 0002 | 0 | 131101-WSW41-MM-C-0002-0 | 2025-03-20 | Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-17 | 2025-05-07 | Approved with Comments | 2025-05-27 | NO | Overdue |  | 131101-WSW41-MM-0002 | NA | "Site memo (131101-WSW41-MM-C-0002) closure document (Concrete cube strength not meeting specified requirements at SSN Annamox tank wall)" | 2025-03-20 | NO | YES | Project_Code not in project_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 48 | AWC | 2025-03-20 | 0 | 001137 | 2025-03-20 | 00 | 1 | Approved with Comments | AWC | 2025-05-27 | Overdue | 0 | AWC | AWC
6047 | 001138 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | QA | E | 0028 | 0 | 131242-WSW41-QA-E-0028-0 | 2025-03-20 | FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI) | Approved | 2025-04-17 | 2025-05-06 | Approved |  | YES | NA |  | 131242-WSW41-QA-0028 | NA | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" && "SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team)" && "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" | 2025-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-09 | 47 | APP | 2025-10-06 | 0 | 001138&&001239&&001723 | 2025-03-20, 2025-04-21, 2025-10-06 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
6048 | 001139 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 0 | 131242-WSW41-VI-M-2006-0 | 2025-03-20 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-17 | 2025-04-05 | Approved with Comments | 2025-04-24 | YES | Resubmitted |  | 131242-WSW41-VI-2006 | NA | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | 2025-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 16 | AWC | 2025-05-05 | 1 | 001139 | 2025-03-20, 2025-05-05 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6049 | 001139 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2006 | 1 | 131242-WSW41-VI-M-2006-1 | 2025-05-05 | Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-VI-2006 | NA | "Preliminary Design and Vendor Approval Document for Pressure Reducing Valve (Instrument Air) (Goetze-MV resourses)" | 2025-03-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-19 | 336 | PEN | 2025-05-05 | 1 | 001139 | 2025-03-20, 2025-05-05 | 00, 01 | 2 | Approved with Comments | AWC | 2025-06-20 |  | 0 | PEN | PEN
6050 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | A | 131242-WST02-DR-EI-7160-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7160 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6051 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7161 | A | 131242-WST02-DR-EI-7161-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7161 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6052 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7162 | A | 131242-WST02-DR-EI-7162-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7162 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6053 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7163 | A | 131242-WST02-DR-EI-7163-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7163 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6054 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7164 | A | 131242-WST02-DR-EI-7164-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7164 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6055 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7165 | A | 131242-WST02-DR-EI-7165-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7165 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6056 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7166 | A | 131242-WST02-DR-EI-7166-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7166 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6057 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7167 | A | 131242-WST02-DR-EI-7167-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7167 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6058 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7180 | A | 131242-WST02-DR-EI-7180-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7180 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6059 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7181 | A | 131242-WST02-DR-EI-7181-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7181 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6060 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7182 | A | 131242-WST02-DR-EI-7182-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7182 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6061 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7183 | A | 131242-WST02-DR-EI-7183-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7183 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6062 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7184 | A | 131242-WST02-DR-EI-7184-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7184 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6063 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7185 | A | 131242-WST02-DR-EI-7185-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7185 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6064 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7186 | A | 131242-WST02-DR-EI-7186-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7186 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6065 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7187 | A | 131242-WST02-DR-EI-7187-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7187 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6066 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3052 | A | 131242-WST02-DR-EP-3052-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3052 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6067 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3053 | A | 131242-WST02-DR-EP-3053-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3053 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6068 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3054 | A | 131242-WST02-DR-EP-3054-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3054 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6069 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3055 | A | 131242-WST02-DR-EP-3055-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3055 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2026-02-03 | A | 001140&&002005 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6070 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3056 | A | 131242-WST02-DR-EP-3056-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3056 | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2026-02-03 | A | 001140&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6071 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3057 | A | 131242-WST02-DR-EP-3057-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3057 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6072 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3058 | A | 131242-WST02-DR-EP-3058-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3058 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6073 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3059 | A | 131242-WST02-DR-EP-3059-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3059 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6074 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3060 | A | 131242-WST02-DR-EP-3060-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3060 | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2026-02-03 | A | 001140&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6075 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3061 | A | 131242-WST02-DR-EP-3061-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3061 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6076 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3062 | A | 131242-WST02-DR-EP-3062-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3062 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6077 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3063 | A | 131242-WST02-DR-EP-3063-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3063 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6078 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3064 | A | 131242-WST02-DR-EP-3064-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3064 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6079 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3065 | A | 131242-WST02-DR-EP-3065-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3065 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 60 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6080 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7142 | A | 131242-WST02-DR-EP-7142-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7142 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 60 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6081 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7143 | A | 131242-WST02-DR-EP-7143-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7143 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 60 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6082 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7144 | A | 131242-WST02-DR-EP-7144-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7144 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 60 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6083 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7145 | A | 131242-WST02-DR-EP-7145-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7145 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 60 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6084 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7146 | A | 131242-WST02-DR-EP-7146-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7146 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 60 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6085 | 001140 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7147 | A | 131242-WST02-DR-EP-7147-A | 2025-03-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 0: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-04-18 | 2025-05-20 | Approved with Comments | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7147 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 60 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6086 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7160 | B | 131242-WST02-DR-EI-7160-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7160 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6087 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7161 | B | 131242-WST02-DR-EI-7161-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7161 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6088 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7162 | B | 131242-WST02-DR-EI-7162-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7162 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6089 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7163 | B | 131242-WST02-DR-EI-7163-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7163 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6090 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7164 | B | 131242-WST02-DR-EI-7164-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7164 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6091 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7165 | B | 131242-WST02-DR-EI-7165-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7165 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6092 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7166 | B | 131242-WST02-DR-EI-7166-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7166 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6093 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7167 | B | 131242-WST02-DR-EI-7167-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7167 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6094 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7180 | B | 131242-WST02-DR-EI-7180-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7180 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6095 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7181 | B | 131242-WST02-DR-EI-7181-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7181 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6096 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7182 | B | 131242-WST02-DR-EI-7182-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7182 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6097 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7183 | B | 131242-WST02-DR-EI-7183-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7183 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6098 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7184 | B | 131242-WST02-DR-EI-7184-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7184 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6099 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7185 | B | 131242-WST02-DR-EI-7185-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7185 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6100 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7186 | B | 131242-WST02-DR-EI-7186-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7186 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6101 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7187 | B | 131242-WST02-DR-EI-7187-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7187 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6102 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3052 | B | 131242-WST02-DR-EP-3052-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3052 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6103 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3053 | B | 131242-WST02-DR-EP-3053-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3053 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6104 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3054 | B | 131242-WST02-DR-EP-3054-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3054 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6105 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3055 | B | 131242-WST02-DR-EP-3055-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3055 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2026-02-03 | A | 001140&&002005 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6106 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3056 | B | 131242-WST02-DR-EP-3056-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3056 | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2026-02-03 | A | 001140&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6107 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3057 | B | 131242-WST02-DR-EP-3057-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3057 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6108 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3058 | B | 131242-WST02-DR-EP-3058-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3058 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6109 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3059 | B | 131242-WST02-DR-EP-3059-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3059 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6110 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3060 | B | 131242-WST02-DR-EP-3060-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3060 | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2026-02-03 | A | 001140&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6111 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3061 | B | 131242-WST02-DR-EP-3061-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3061 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6112 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3062 | B | 131242-WST02-DR-EP-3062-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3062 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6113 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3063 | B | 131242-WST02-DR-EP-3063-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3063 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6114 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3064 | B | 131242-WST02-DR-EP-3064-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3064 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6115 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3065 | B | 131242-WST02-DR-EP-3065-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-3065 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 001140 | 2025-03-21, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6116 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7142 | B | 131242-WST02-DR-EP-7142-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7142 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6117 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7143 | B | 131242-WST02-DR-EP-7143-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7143 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6118 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7144 | B | 131242-WST02-DR-EP-7144-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7144 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6119 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7145 | B | 131242-WST02-DR-EP-7145-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7145 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6120 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7146 | B | 131242-WST02-DR-EP-7146-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7146 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6121 | 001140 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7147 | B | 131242-WST02-DR-EP-7147-B | 2025-07-21 | SSN MDB-1001A.B SLD, Schem and GA Drawings | Rev 1: Approved with comment. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-7147 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 64 | AWC | 2025-07-21 | B | 000867&&001140 | 2024-12-02, 2025-03-21, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
6122 | 001141 | 00 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 0 | 131242-WST02-VI-I-0024-0 | 2025-03-21 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-VI-0024 | NA | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 28 | NAP | 2025-04-30 | 1 | 001141 | 2025-03-21, 2025-04-30 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6123 | 001141 | 01 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0024 | 1 | 131242-WST02-VI-I-0024-1 | 2025-04-30 | Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-04 | Approved with Comments | 2025-06-24 | NO | Overdue |  | 131242-WST02-VI-0024 | NA | "Preliminary Design and Vendor Approval Document – SSN PLC/RIO Panels (Fox)" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-14 | 35 | AWC | 2025-04-30 | 1 | 001141 | 2025-03-21, 2025-04-30 | 00, 01 | 2 | Approved with Comments | AWC | 2025-06-24 | Overdue | 0 | AWC | AWC
6124 | 001142 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 0 | 131242-WST02-CD-I-0011-0 | 2025-03-21 | SSN -RIO PANEL 0401- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-22 | Not Approved | 2025-05-12 | YES | Resubmitted |  | 131242-WST02-CD-0011 | NA | "SSN -RIO PANEL 0401- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 32 | NAP | 2025-06-25 | 1 | 000183&&001142 | 2023-11-10, 2025-03-21, 2025-06-25 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6125 | 001142 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0011 | 1 | 131242-WST02-CD-I-0011-1 | 2025-06-25 | SSN -RIO PANEL 0401- I/O List | Rev 1: Approved with Comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-15 | Approved with Comments | 2025-10-03 | NO | Overdue |  | 131242-WST02-CD-0011 | NA | "SSN -RIO PANEL 0401- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-09 | 82 | AWC | 2025-06-25 | 1 | 000183&&001142 | 2023-11-10, 2025-03-21, 2025-06-25 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-03 | Overdue | 0 | AWC | AWC
6126 | 001143 | 00 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 0 | 131242-WSD11-MS-M-0007-0 | 2025-03-21 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Rev 0: Not approved - Revise and Resubmit. Refer to comments provided during MSRA briefing meeting dated 28th March 2025 and 4 April 2025. | 2025-04-18 | 2025-04-05 | Not Approved | 2025-04-24 | YES | Resubmitted |  | 131242-WSD11-MS-0007 | NA | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " && "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 15 | NAP | 2025-05-30 | 0 | 001143&&001334 | 2025-03-21, 2025-04-10, 2025-05-30 | 00, 01 | 3 | Approved | APP |  |  | 0 | NAP | NAP
6127 | 001143 | 01 | K. Balaji | EICA | NA | 131242 | WSD11 | MS | M | 0007 | 1 | 131242-WSD11-MS-M-0007-1 | 2025-04-10 | Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard | Approved | 2025-04-30 | 2025-05-21 | Approved |  | YES | NA |  | 131242-WSD11-MS-0007 | NA | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " && "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-24 | 41 | APP | 2025-05-30 | 0 | 001143&&001334 | 2025-03-21, 2025-04-10, 2025-05-30 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
6128 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-IP-1001-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
6129 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1002 | B | 131242-WST02-DR-IP-1002-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
6130 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1003 | B | 131242-WST02-DR-IP-1003-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
6131 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1004 | B | 131242-WST02-DR-IP-1004-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
6132 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1005 | B | 131242-WST02-DR-IP-1005-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
6133 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1006 | B | 131242-WST02-DR-IP-1006-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | NAP | NAP
6134 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1007 | B | 131242-WST02-DR-IP-1007-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6135 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1008 | B | 131242-WST02-DR-IP-1008-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6136 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1009 | B | 131242-WST02-DR-IP-1009-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | NAP | NAP
6137 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1010 | B | 131242-WST02-DR-IP-1010-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6138 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1011 | B | 131242-WST02-DR-IP-1011-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6139 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1012 | B | 131242-WST02-DR-IP-1012-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6140 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1013 | B | 131242-WST02-DR-IP-1013-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 56 | NAP | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6141 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1014 | B | 131242-WST02-DR-IP-1014-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6142 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1015 | B | 131242-WST02-DR-IP-1015-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6143 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1016 | B | 131242-WST02-DR-IP-1016-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6144 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1017 | B | 131242-WST02-DR-IP-1017-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6145 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1018 | B | 131242-WST02-DR-IP-1018-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6146 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1019 | B | 131242-WST02-DR-IP-1019-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6147 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1020 | B | 131242-WST02-DR-IP-1020-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6148 | 001144 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1021 | B | 131242-WST02-DR-IP-1021-B | 2025-03-21 | SSN ECCP-1000- GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-04-18 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6149 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1001 | B | 131242-WST02-DR-IP-1001-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
6150 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1002 | B | 131242-WST02-DR-IP-1002-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
6151 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1003 | B | 131242-WST02-DR-IP-1003-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
6152 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1004 | B | 131242-WST02-DR-IP-1004-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
6153 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1005 | B | 131242-WST02-DR-IP-1005-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
6154 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1006 | B | 131242-WST02-DR-IP-1006-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
6155 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1007 | B | 131242-WST02-DR-IP-1007-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6156 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1008 | B | 131242-WST02-DR-IP-1008-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6157 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1009 | B | 131242-WST02-DR-IP-1009-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | AWC | AWC
6158 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1010 | B | 131242-WST02-DR-IP-1010-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6159 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1011 | B | 131242-WST02-DR-IP-1011-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6160 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1012 | B | 131242-WST02-DR-IP-1012-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6161 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1013 | B | 131242-WST02-DR-IP-1013-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6162 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1014 | B | 131242-WST02-DR-IP-1014-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6163 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1015 | B | 131242-WST02-DR-IP-1015-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6164 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1016 | B | 131242-WST02-DR-IP-1016-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6165 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1017 | B | 131242-WST02-DR-IP-1017-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6166 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1018 | B | 131242-WST02-DR-IP-1018-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6167 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1019 | B | 131242-WST02-DR-IP-1019-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6168 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1020 | B | 131242-WST02-DR-IP-1020-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6169 | 001144 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1021 | B | 131242-WST02-DR-IP-1021-B | 2025-08-19 | SSN ECCP-1000- GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6170 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | B | 131242-WST02-DR-IP-1051-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1051 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6171 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1052 | B | 131242-WST02-DR-IP-1052-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1052 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6172 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1053 | B | 131242-WST02-DR-IP-1053-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1053 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6173 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1054 | B | 131242-WST02-DR-IP-1054-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1054 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6174 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1055 | B | 131242-WST02-DR-IP-1055-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1055 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6175 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1056 | B | 131242-WST02-DR-IP-1056-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1056 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6176 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1057 | B | 131242-WST02-DR-IP-1057-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1057 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6177 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1058 | B | 131242-WST02-DR-IP-1058-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1058 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6178 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1059 | B | 131242-WST02-DR-IP-1059-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1059 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6179 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1060 | B | 131242-WST02-DR-IP-1060-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1060 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6180 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1061 | B | 131242-WST02-DR-IP-1061-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1061 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6181 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1062 | B | 131242-WST02-DR-IP-1062-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1062 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6182 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1063 | B | 131242-WST02-DR-IP-1063-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1063 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6183 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1064 | B | 131242-WST02-DR-IP-1064-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1064 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6184 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1065 | B | 131242-WST02-DR-IP-1065-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1065 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6185 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1066 | B | 131242-WST02-DR-IP-1066-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1066 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6186 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1067 | B | 131242-WST02-DR-IP-1067-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1067 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6187 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1068 | B | 131242-WST02-DR-IP-1068-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1068 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6188 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1069 | B | 131242-WST02-DR-IP-1069-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1069 | NA | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | C | 001145 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6189 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1070 | B | 131242-WST02-DR-IP-1070-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1070 | NA | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | C | 001145 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6190 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1071 | B | 131242-WST02-DR-IP-1071-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1071 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6191 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1072 | B | 131242-WST02-DR-IP-1072-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1072 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6192 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1073 | B | 131242-WST02-DR-IP-1073-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1073 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6193 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1074 | B | 131242-WST02-DR-IP-1074-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1074 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6194 | 001145 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1075 | B | 131242-WST02-DR-IP-1075-B | 2025-03-21 | SSN RIO 0001A GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1075 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6195 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1051 | C | 131242-WST02-DR-IP-1051-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1051 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6196 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1052 | C | 131242-WST02-DR-IP-1052-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1052 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6197 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1053 | C | 131242-WST02-DR-IP-1053-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1053 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6198 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1054 | C | 131242-WST02-DR-IP-1054-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1054 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6199 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1055 | C | 131242-WST02-DR-IP-1055-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1055 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6200 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1056 | C | 131242-WST02-DR-IP-1056-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1056 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6201 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1057 | C | 131242-WST02-DR-IP-1057-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1057 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6202 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1058 | C | 131242-WST02-DR-IP-1058-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1058 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6203 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1059 | C | 131242-WST02-DR-IP-1059-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1059 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6204 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1060 | C | 131242-WST02-DR-IP-1060-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1060 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6205 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1061 | C | 131242-WST02-DR-IP-1061-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1061 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6206 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1062 | C | 131242-WST02-DR-IP-1062-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1062 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6207 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1063 | C | 131242-WST02-DR-IP-1063-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1063 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6208 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1064 | C | 131242-WST02-DR-IP-1064-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1064 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6209 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1065 | C | 131242-WST02-DR-IP-1065-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1065 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6210 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1066 | C | 131242-WST02-DR-IP-1066-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1066 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6211 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1067 | C | 131242-WST02-DR-IP-1067-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1067 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6212 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1068 | C | 131242-WST02-DR-IP-1068-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1068 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6213 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1069 | C | 131242-WST02-DR-IP-1069-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1069 | NA | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2025-08-19 | C | 001145 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
6214 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1070 | C | 131242-WST02-DR-IP-1070-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1070 | NA | "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2025-08-19 | C | 001145 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
6215 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1071 | C | 131242-WST02-DR-IP-1071-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1071 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6216 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1072 | C | 131242-WST02-DR-IP-1072-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1072 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6217 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1073 | C | 131242-WST02-DR-IP-1073-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1073 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6218 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1074 | C | 131242-WST02-DR-IP-1074-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1074 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6219 | 001145 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1075 | C | 131242-WST02-DR-IP-1075-C | 2025-08-19 | SSN RIO 0001A GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1075 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 43 | AWC | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6220 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-IP-1101-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1101 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 40 | NAP | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6221 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1102 | B | 131242-WST02-DR-IP-1102-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1102 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 40 | NAP | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6222 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1103 | B | 131242-WST02-DR-IP-1103-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1103 | NA | "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 40 | NAP | 2025-08-19 | B | 000245&&001146 | 2023-12-18, 2025-03-21, 2025-08-19 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6223 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1104 | B | 131242-WST02-DR-IP-1104-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1104 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6224 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1105 | B | 131242-WST02-DR-IP-1105-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1105 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6225 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1106 | B | 131242-WST02-DR-IP-1106-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1106 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6226 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1107 | B | 131242-WST02-DR-IP-1107-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1107 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6227 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1108 | B | 131242-WST02-DR-IP-1108-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1108 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6228 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1109 | B | 131242-WST02-DR-IP-1109-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1109 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6229 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1110 | B | 131242-WST02-DR-IP-1110-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1110 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6230 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1111 | B | 131242-WST02-DR-IP-1111-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1111 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6231 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1112 | B | 131242-WST02-DR-IP-1112-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1112 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6232 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1113 | B | 131242-WST02-DR-IP-1113-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1113 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6233 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1114 | B | 131242-WST02-DR-IP-1114-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1114 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6234 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1115 | B | 131242-WST02-DR-IP-1115-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1115 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6235 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1116 | B | 131242-WST02-DR-IP-1116-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1116 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6236 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1117 | B | 131242-WST02-DR-IP-1117-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1117 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6237 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1118 | B | 131242-WST02-DR-IP-1118-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1118 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6238 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1119 | B | 131242-WST02-DR-IP-1119-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1119 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6239 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1120 | B | 131242-WST02-DR-IP-1120-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1120 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6240 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1121 | B | 131242-WST02-DR-IP-1121-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1121 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6241 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1122 | B | 131242-WST02-DR-IP-1122-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1122 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6242 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1123 | B | 131242-WST02-DR-IP-1123-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1123 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6243 | 001146 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1124 | B | 131242-WST02-DR-IP-1124-B | 2025-03-21 | SSN RIO 0001B GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-04-30 | Not Approved | 2025-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1124 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 40 | NAP | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6244 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1101 | B | 131242-WST02-DR-IP-1101-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1101 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6245 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1102 | B | 131242-WST02-DR-IP-1102-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1102 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6246 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1103 | B | 131242-WST02-DR-IP-1103-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1103 | NA | "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 000245&&001146 | 2023-12-18, 2025-03-21, 2025-08-19 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6247 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1104 | B | 131242-WST02-DR-IP-1104-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1104 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6248 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1105 | B | 131242-WST02-DR-IP-1105-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1105 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6249 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1106 | B | 131242-WST02-DR-IP-1106-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1106 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6250 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1107 | B | 131242-WST02-DR-IP-1107-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1107 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6251 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1108 | B | 131242-WST02-DR-IP-1108-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1108 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6252 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1109 | B | 131242-WST02-DR-IP-1109-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1109 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6253 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1110 | B | 131242-WST02-DR-IP-1110-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1110 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6254 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1111 | B | 131242-WST02-DR-IP-1111-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1111 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6255 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1112 | B | 131242-WST02-DR-IP-1112-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1112 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6256 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1113 | B | 131242-WST02-DR-IP-1113-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1113 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6257 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1114 | B | 131242-WST02-DR-IP-1114-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1114 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6258 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1115 | B | 131242-WST02-DR-IP-1115-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1115 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
6259 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1116 | B | 131242-WST02-DR-IP-1116-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1116 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
6260 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1117 | B | 131242-WST02-DR-IP-1117-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1117 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
6261 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1118 | B | 131242-WST02-DR-IP-1118-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1118 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6262 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1119 | B | 131242-WST02-DR-IP-1119-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1119 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6263 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1120 | B | 131242-WST02-DR-IP-1120-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1120 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6264 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1121 | B | 131242-WST02-DR-IP-1121-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1121 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6265 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1122 | B | 131242-WST02-DR-IP-1122-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1122 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6266 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1123 | B | 131242-WST02-DR-IP-1123-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1123 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6267 | 001146 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1124 | B | 131242-WST02-DR-IP-1124-B | 2025-08-19 | SSN RIO 0001B GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-10-08 | Approved with Comments | 2025-10-28 | NO | Overdue |  | 131242-WST02-DR-1124 | NA | "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 50 | AWC | 2025-08-19 | B | 001146 | 2025-03-21, 2025-08-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
6268 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | B | 131242-WST02-DR-IP-1151-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1151 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6269 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1152 | B | 131242-WST02-DR-IP-1152-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1152 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6270 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1153 | B | 131242-WST02-DR-IP-1153-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1153 | NA | "SSN Electrical building L2, Column C2A PE Endorsement" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147&&001525 | 2025-03-21, 2025-07-24, 2025-07-29 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6271 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1154 | B | 131242-WST02-DR-IP-1154-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1154 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6272 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1155 | B | 131242-WST02-DR-IP-1155-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1155 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6273 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1156 | B | 131242-WST02-DR-IP-1156-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1156 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6274 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1157 | B | 131242-WST02-DR-IP-1157-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1157 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6275 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1158 | B | 131242-WST02-DR-IP-1158-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1158 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6276 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1159 | B | 131242-WST02-DR-IP-1159-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1159 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6277 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1160 | B | 131242-WST02-DR-IP-1160-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1160 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6278 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1161 | B | 131242-WST02-DR-IP-1161-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1161 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6279 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1162 | B | 131242-WST02-DR-IP-1162-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1162 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6280 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1163 | B | 131242-WST02-DR-IP-1163-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1163 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6281 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1164 | B | 131242-WST02-DR-IP-1164-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1164 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6282 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1165 | B | 131242-WST02-DR-IP-1165-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1165 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6283 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1166 | B | 131242-WST02-DR-IP-1166-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1166 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6284 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1167 | B | 131242-WST02-DR-IP-1167-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1167 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6285 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1168 | B | 131242-WST02-DR-IP-1168-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1168 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6286 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1169 | B | 131242-WST02-DR-IP-1169-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1169 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6287 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1170 | B | 131242-WST02-DR-IP-1170-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1170 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6288 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1171 | B | 131242-WST02-DR-IP-1171-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1171 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6289 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1172 | B | 131242-WST02-DR-IP-1172-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1172 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6290 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1173 | B | 131242-WST02-DR-IP-1173-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1173 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6291 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1174 | B | 131242-WST02-DR-IP-1174-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1174 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6292 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1175 | B | 131242-WST02-DR-IP-1175-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1175 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6293 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1176 | B | 131242-WST02-DR-IP-1176-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1176 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6294 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1177 | B | 131242-WST02-DR-IP-1177-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1177 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6295 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1178 | B | 131242-WST02-DR-IP-1178-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1178 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6296 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1179 | B | 131242-WST02-DR-IP-1179-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1179 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6297 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1180 | B | 131242-WST02-DR-IP-1180-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1180 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6298 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1181 | B | 131242-WST02-DR-IP-1181-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1181 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6299 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1182 | B | 131242-WST02-DR-IP-1182-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1182 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6300 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1183 | B | 131242-WST02-DR-IP-1183-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1183 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6301 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1184 | B | 131242-WST02-DR-IP-1184-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1184 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6302 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1185 | B | 131242-WST02-DR-IP-1185-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1185 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6303 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1186 | B | 131242-WST02-DR-IP-1186-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1186 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6304 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1187 | B | 131242-WST02-DR-IP-1187-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1187 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6305 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1188 | B | 131242-WST02-DR-IP-1188-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1188 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6306 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1189 | B | 131242-WST02-DR-IP-1189-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1189 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6307 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1190 | B | 131242-WST02-DR-IP-1190-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1190 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6308 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1191 | B | 131242-WST02-DR-IP-1191-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1191 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6309 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1192 | B | 131242-WST02-DR-IP-1192-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1192 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6310 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1193 | B | 131242-WST02-DR-IP-1193-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1193 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6311 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1194 | B | 131242-WST02-DR-IP-1194-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1194 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6312 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1195 | B | 131242-WST02-DR-IP-1195-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1195 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6313 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1196 | B | 131242-WST02-DR-IP-1196-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1196 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6314 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1197 | B | 131242-WST02-DR-IP-1197-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1197 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6315 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1198 | B | 131242-WST02-DR-IP-1198-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1198 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6316 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1199 | B | 131242-WST02-DR-IP-1199-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1199 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6317 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1200 | B | 131242-WST02-DR-IP-1200-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1200 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6318 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1201 | B | 131242-WST02-DR-IP-1201-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1201 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6319 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1202 | B | 131242-WST02-DR-IP-1202-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1202 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6320 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1203 | B | 131242-WST02-DR-IP-1203-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1203 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6321 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1204 | B | 131242-WST02-DR-IP-1204-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1204 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6322 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1205 | B | 131242-WST02-DR-IP-1205-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1205 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6323 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1206 | B | 131242-WST02-DR-IP-1206-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1206 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6324 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1207 | B | 131242-WST02-DR-IP-1207-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1207 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6325 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1208 | B | 131242-WST02-DR-IP-1208-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1208 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6326 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1209 | B | 131242-WST02-DR-IP-1209-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1209 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6327 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1210 | B | 131242-WST02-DR-IP-1210-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1210 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6328 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1211 | B | 131242-WST02-DR-IP-1211-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1211 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6329 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1212 | B | 131242-WST02-DR-IP-1212-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1212 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6330 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1213 | B | 131242-WST02-DR-IP-1213-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1213 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6331 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1214 | B | 131242-WST02-DR-IP-1214-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1214 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6332 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1215 | B | 131242-WST02-DR-IP-1215-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1215 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6333 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1216 | B | 131242-WST02-DR-IP-1216-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1216 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6334 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1217 | B | 131242-WST02-DR-IP-1217-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1217 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6335 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1218 | B | 131242-WST02-DR-IP-1218-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1218 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6336 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1219 | B | 131242-WST02-DR-IP-1219-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1219 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6337 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1220 | B | 131242-WST02-DR-IP-1220-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1220 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6338 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1221 | B | 131242-WST02-DR-IP-1221-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1221 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6339 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1222 | B | 131242-WST02-DR-IP-1222-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1222 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6340 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1223 | B | 131242-WST02-DR-IP-1223-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1223 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6341 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1224 | B | 131242-WST02-DR-IP-1224-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1224 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6342 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1225 | B | 131242-WST02-DR-IP-1225-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1225 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6343 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1226 | B | 131242-WST02-DR-IP-1226-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1226 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6344 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1227 | B | 131242-WST02-DR-IP-1227-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1227 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6345 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1228 | B | 131242-WST02-DR-IP-1228-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1228 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6346 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1229 | B | 131242-WST02-DR-IP-1229-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1229 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6347 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1230 | B | 131242-WST02-DR-IP-1230-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1230 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6348 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1231 | B | 131242-WST02-DR-IP-1231-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1231 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6349 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1232 | B | 131242-WST02-DR-IP-1232-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1232 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6350 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1233 | B | 131242-WST02-DR-IP-1233-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1233 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6351 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1234 | B | 131242-WST02-DR-IP-1234-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1234 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6352 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1235 | B | 131242-WST02-DR-IP-1235-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1235 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6353 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1236 | B | 131242-WST02-DR-IP-1236-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1236 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6354 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1237 | B | 131242-WST02-DR-IP-1237-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1237 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6355 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1238 | B | 131242-WST02-DR-IP-1238-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1238 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6356 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1239 | B | 131242-WST02-DR-IP-1239-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1239 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6357 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1240 | B | 131242-WST02-DR-IP-1240-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1240 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6358 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1241 | B | 131242-WST02-DR-IP-1241-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1241 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6359 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1242 | B | 131242-WST02-DR-IP-1242-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1242 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6360 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1243 | B | 131242-WST02-DR-IP-1243-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1243 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6361 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1244 | B | 131242-WST02-DR-IP-1244-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1244 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6362 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1245 | B | 131242-WST02-DR-IP-1245-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1245 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6363 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1246 | B | 131242-WST02-DR-IP-1246-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1246 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6364 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1247 | B | 131242-WST02-DR-IP-1247-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1247 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6365 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1248 | B | 131242-WST02-DR-IP-1248-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1248 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6366 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1249 | B | 131242-WST02-DR-IP-1249-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1249 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6367 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1250 | B | 131242-WST02-DR-IP-1250-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1250 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6368 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1251 | B | 131242-WST02-DR-IP-1251-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1251 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6369 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1252 | B | 131242-WST02-DR-IP-1252-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1252 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6370 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1253 | B | 131242-WST02-DR-IP-1253-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1253 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6371 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1254 | B | 131242-WST02-DR-IP-1254-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1254 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6372 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1255 | B | 131242-WST02-DR-IP-1255-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1255 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6373 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1256 | B | 131242-WST02-DR-IP-1256-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1256 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6374 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1257 | B | 131242-WST02-DR-IP-1257-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1257 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6375 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1258 | B | 131242-WST02-DR-IP-1258-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1258 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6376 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1259 | B | 131242-WST02-DR-IP-1259-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1259 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6377 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1260 | B | 131242-WST02-DR-IP-1260-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1260 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6378 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1261 | B | 131242-WST02-DR-IP-1261-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1261 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6379 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1262 | B | 131242-WST02-DR-IP-1262-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1262 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6380 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1263 | B | 131242-WST02-DR-IP-1263-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1263 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6381 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1264 | B | 131242-WST02-DR-IP-1264-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1264 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6382 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1265 | B | 131242-WST02-DR-IP-1265-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1265 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6383 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1266 | B | 131242-WST02-DR-IP-1266-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1266 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6384 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1267 | B | 131242-WST02-DR-IP-1267-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1267 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6385 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1268 | B | 131242-WST02-DR-IP-1268-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1268 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6386 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1269 | B | 131242-WST02-DR-IP-1269-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1269 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6387 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1270 | B | 131242-WST02-DR-IP-1270-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1270 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6388 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1271 | B | 131242-WST02-DR-IP-1271-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1271 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6389 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1272 | B | 131242-WST02-DR-IP-1272-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1272 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6390 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1273 | B | 131242-WST02-DR-IP-1273-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1273 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6391 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1274 | B | 131242-WST02-DR-IP-1274-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1274 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6392 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1275 | B | 131242-WST02-DR-IP-1275-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1275 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6393 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1276 | B | 131242-WST02-DR-IP-1276-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1276 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6394 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1277 | B | 131242-WST02-DR-IP-1277-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1277 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6395 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1278 | B | 131242-WST02-DR-IP-1278-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1278 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6396 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1279 | B | 131242-WST02-DR-IP-1279-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1279 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6397 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1280 | B | 131242-WST02-DR-IP-1280-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1280 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6398 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1281 | B | 131242-WST02-DR-IP-1281-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1281 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6399 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1282 | B | 131242-WST02-DR-IP-1282-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1282 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6400 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1283 | B | 131242-WST02-DR-IP-1283-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1283 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6401 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1284 | B | 131242-WST02-DR-IP-1284-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1284 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6402 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1285 | B | 131242-WST02-DR-IP-1285-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1285 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6403 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1286 | B | 131242-WST02-DR-IP-1286-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1286 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6404 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1287 | B | 131242-WST02-DR-IP-1287-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1287 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6405 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1288 | B | 131242-WST02-DR-IP-1288-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1288 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6406 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1289 | B | 131242-WST02-DR-IP-1289-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1289 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6407 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1290 | B | 131242-WST02-DR-IP-1290-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1290 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6408 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1291 | B | 131242-WST02-DR-IP-1291-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1291 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6409 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1292 | B | 131242-WST02-DR-IP-1292-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1292 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6410 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1293 | B | 131242-WST02-DR-IP-1293-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1293 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6411 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1294 | B | 131242-WST02-DR-IP-1294-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1294 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6412 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1295 | B | 131242-WST02-DR-IP-1295-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1295 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6413 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1296 | B | 131242-WST02-DR-IP-1296-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1296 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6414 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1297 | B | 131242-WST02-DR-IP-1297-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1297 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6415 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1298 | B | 131242-WST02-DR-IP-1298-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1298 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6416 | 001147 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1299 | B | 131242-WST02-DR-IP-1299-B | 2025-03-21 | SSN RIO 0201 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1299 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6417 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1151 | C | 131242-WST02-DR-IP-1151-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1151 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6418 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1152 | C | 131242-WST02-DR-IP-1152-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1152 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6419 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1153 | C | 131242-WST02-DR-IP-1153-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1153 | NA | "SSN Electrical building L2, Column C2A PE Endorsement" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147&&001525 | 2025-03-21, 2025-07-24, 2025-07-29 | 00, 01 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6420 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1154 | C | 131242-WST02-DR-IP-1154-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1154 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6421 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1155 | C | 131242-WST02-DR-IP-1155-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1155 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6422 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1156 | C | 131242-WST02-DR-IP-1156-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1156 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6423 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1157 | C | 131242-WST02-DR-IP-1157-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1157 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6424 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1158 | C | 131242-WST02-DR-IP-1158-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1158 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6425 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1159 | C | 131242-WST02-DR-IP-1159-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1159 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6426 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1160 | C | 131242-WST02-DR-IP-1160-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1160 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6427 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1161 | C | 131242-WST02-DR-IP-1161-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1161 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6428 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1162 | C | 131242-WST02-DR-IP-1162-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1162 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6429 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1163 | C | 131242-WST02-DR-IP-1163-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1163 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6430 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1164 | C | 131242-WST02-DR-IP-1164-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1164 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6431 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1165 | C | 131242-WST02-DR-IP-1165-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1165 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6432 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1166 | C | 131242-WST02-DR-IP-1166-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1166 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6433 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1167 | C | 131242-WST02-DR-IP-1167-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1167 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6434 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1168 | C | 131242-WST02-DR-IP-1168-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1168 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6435 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1169 | C | 131242-WST02-DR-IP-1169-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1169 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6436 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1170 | C | 131242-WST02-DR-IP-1170-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1170 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6437 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1171 | C | 131242-WST02-DR-IP-1171-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1171 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6438 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1172 | C | 131242-WST02-DR-IP-1172-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1172 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6439 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1173 | C | 131242-WST02-DR-IP-1173-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1173 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6440 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1174 | C | 131242-WST02-DR-IP-1174-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1174 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6441 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1175 | C | 131242-WST02-DR-IP-1175-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1175 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6442 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1176 | C | 131242-WST02-DR-IP-1176-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1176 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6443 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1177 | C | 131242-WST02-DR-IP-1177-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1177 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6444 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1178 | C | 131242-WST02-DR-IP-1178-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1178 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6445 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1179 | C | 131242-WST02-DR-IP-1179-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1179 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6446 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1180 | C | 131242-WST02-DR-IP-1180-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1180 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6447 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1181 | C | 131242-WST02-DR-IP-1181-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1181 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6448 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1182 | C | 131242-WST02-DR-IP-1182-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1182 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6449 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1183 | C | 131242-WST02-DR-IP-1183-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1183 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6450 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1184 | C | 131242-WST02-DR-IP-1184-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1184 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6451 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1185 | C | 131242-WST02-DR-IP-1185-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1185 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6452 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1186 | C | 131242-WST02-DR-IP-1186-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1186 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6453 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1187 | C | 131242-WST02-DR-IP-1187-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1187 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6454 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1188 | C | 131242-WST02-DR-IP-1188-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1188 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6455 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1189 | C | 131242-WST02-DR-IP-1189-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1189 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6456 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1190 | C | 131242-WST02-DR-IP-1190-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1190 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6457 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1191 | C | 131242-WST02-DR-IP-1191-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1191 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6458 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1192 | C | 131242-WST02-DR-IP-1192-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1192 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6459 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1193 | C | 131242-WST02-DR-IP-1193-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1193 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6460 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1194 | C | 131242-WST02-DR-IP-1194-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1194 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6461 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1195 | C | 131242-WST02-DR-IP-1195-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1195 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6462 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1196 | C | 131242-WST02-DR-IP-1196-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1196 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6463 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1197 | C | 131242-WST02-DR-IP-1197-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1197 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6464 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1198 | C | 131242-WST02-DR-IP-1198-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1198 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6465 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1199 | C | 131242-WST02-DR-IP-1199-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1199 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6466 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1200 | C | 131242-WST02-DR-IP-1200-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1200 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6467 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1201 | C | 131242-WST02-DR-IP-1201-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1201 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6468 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1202 | C | 131242-WST02-DR-IP-1202-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1202 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6469 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1203 | C | 131242-WST02-DR-IP-1203-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1203 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6470 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1204 | C | 131242-WST02-DR-IP-1204-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1204 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6471 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1205 | C | 131242-WST02-DR-IP-1205-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1205 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6472 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1206 | C | 131242-WST02-DR-IP-1206-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1206 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6473 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1207 | C | 131242-WST02-DR-IP-1207-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1207 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6474 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1208 | C | 131242-WST02-DR-IP-1208-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1208 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6475 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1209 | C | 131242-WST02-DR-IP-1209-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1209 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6476 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1210 | C | 131242-WST02-DR-IP-1210-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1210 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6477 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1211 | C | 131242-WST02-DR-IP-1211-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1211 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6478 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1212 | C | 131242-WST02-DR-IP-1212-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1212 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6479 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1213 | C | 131242-WST02-DR-IP-1213-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1213 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6480 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1214 | C | 131242-WST02-DR-IP-1214-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1214 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6481 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1215 | C | 131242-WST02-DR-IP-1215-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1215 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6482 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1216 | C | 131242-WST02-DR-IP-1216-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1216 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6483 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1217 | C | 131242-WST02-DR-IP-1217-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1217 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6484 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1218 | C | 131242-WST02-DR-IP-1218-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1218 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6485 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1219 | C | 131242-WST02-DR-IP-1219-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1219 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6486 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1220 | C | 131242-WST02-DR-IP-1220-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1220 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6487 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1221 | C | 131242-WST02-DR-IP-1221-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1221 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6488 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1222 | C | 131242-WST02-DR-IP-1222-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1222 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6489 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1223 | C | 131242-WST02-DR-IP-1223-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1223 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6490 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1224 | C | 131242-WST02-DR-IP-1224-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1224 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6491 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1225 | C | 131242-WST02-DR-IP-1225-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1225 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6492 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1226 | C | 131242-WST02-DR-IP-1226-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1226 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6493 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1227 | C | 131242-WST02-DR-IP-1227-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1227 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6494 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1228 | C | 131242-WST02-DR-IP-1228-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1228 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6495 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1229 | C | 131242-WST02-DR-IP-1229-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1229 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6496 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1230 | C | 131242-WST02-DR-IP-1230-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1230 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6497 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1231 | C | 131242-WST02-DR-IP-1231-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1231 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6498 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1232 | C | 131242-WST02-DR-IP-1232-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1232 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6499 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1233 | C | 131242-WST02-DR-IP-1233-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1233 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6500 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1234 | C | 131242-WST02-DR-IP-1234-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1234 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6501 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1235 | C | 131242-WST02-DR-IP-1235-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1235 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6502 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1236 | C | 131242-WST02-DR-IP-1236-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1236 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6503 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1237 | C | 131242-WST02-DR-IP-1237-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1237 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6504 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1238 | C | 131242-WST02-DR-IP-1238-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1238 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6505 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1239 | C | 131242-WST02-DR-IP-1239-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1239 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6506 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1240 | C | 131242-WST02-DR-IP-1240-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1240 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6507 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1241 | C | 131242-WST02-DR-IP-1241-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1241 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6508 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1242 | C | 131242-WST02-DR-IP-1242-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1242 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6509 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1243 | C | 131242-WST02-DR-IP-1243-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1243 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6510 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1244 | C | 131242-WST02-DR-IP-1244-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1244 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6511 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1245 | C | 131242-WST02-DR-IP-1245-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1245 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6512 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1246 | C | 131242-WST02-DR-IP-1246-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1246 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6513 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1247 | C | 131242-WST02-DR-IP-1247-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1247 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6514 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1248 | C | 131242-WST02-DR-IP-1248-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1248 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6515 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1249 | C | 131242-WST02-DR-IP-1249-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1249 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6516 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1250 | C | 131242-WST02-DR-IP-1250-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1250 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6517 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1251 | C | 131242-WST02-DR-IP-1251-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1251 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6518 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1252 | C | 131242-WST02-DR-IP-1252-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1252 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6519 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1253 | C | 131242-WST02-DR-IP-1253-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1253 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6520 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1254 | C | 131242-WST02-DR-IP-1254-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1254 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6521 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1255 | C | 131242-WST02-DR-IP-1255-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1255 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6522 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1256 | C | 131242-WST02-DR-IP-1256-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1256 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6523 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1257 | C | 131242-WST02-DR-IP-1257-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1257 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6524 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1258 | C | 131242-WST02-DR-IP-1258-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1258 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6525 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1259 | C | 131242-WST02-DR-IP-1259-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1259 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6526 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1260 | C | 131242-WST02-DR-IP-1260-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1260 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6527 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1261 | C | 131242-WST02-DR-IP-1261-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1261 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6528 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1262 | C | 131242-WST02-DR-IP-1262-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1262 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6529 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1263 | C | 131242-WST02-DR-IP-1263-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1263 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6530 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1264 | C | 131242-WST02-DR-IP-1264-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1264 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6531 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1265 | C | 131242-WST02-DR-IP-1265-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1265 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6532 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1266 | C | 131242-WST02-DR-IP-1266-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1266 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6533 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1267 | C | 131242-WST02-DR-IP-1267-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1267 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6534 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1268 | C | 131242-WST02-DR-IP-1268-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1268 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6535 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1269 | C | 131242-WST02-DR-IP-1269-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1269 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6536 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1270 | C | 131242-WST02-DR-IP-1270-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1270 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6537 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1271 | C | 131242-WST02-DR-IP-1271-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1271 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6538 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1272 | C | 131242-WST02-DR-IP-1272-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1272 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6539 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1273 | C | 131242-WST02-DR-IP-1273-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1273 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6540 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1274 | C | 131242-WST02-DR-IP-1274-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1274 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6541 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1275 | C | 131242-WST02-DR-IP-1275-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1275 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6542 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1276 | C | 131242-WST02-DR-IP-1276-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1276 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6543 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1277 | C | 131242-WST02-DR-IP-1277-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1277 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6544 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1278 | C | 131242-WST02-DR-IP-1278-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1278 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6545 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1279 | C | 131242-WST02-DR-IP-1279-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1279 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6546 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1280 | C | 131242-WST02-DR-IP-1280-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1280 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6547 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1281 | C | 131242-WST02-DR-IP-1281-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1281 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6548 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1282 | C | 131242-WST02-DR-IP-1282-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1282 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6549 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1283 | C | 131242-WST02-DR-IP-1283-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1283 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6550 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1284 | C | 131242-WST02-DR-IP-1284-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1284 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6551 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1285 | C | 131242-WST02-DR-IP-1285-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1285 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6552 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1286 | C | 131242-WST02-DR-IP-1286-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1286 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6553 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1287 | C | 131242-WST02-DR-IP-1287-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1287 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6554 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1288 | C | 131242-WST02-DR-IP-1288-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1288 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6555 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1289 | C | 131242-WST02-DR-IP-1289-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1289 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6556 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1290 | C | 131242-WST02-DR-IP-1290-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1290 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6557 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1291 | C | 131242-WST02-DR-IP-1291-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1291 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6558 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1292 | C | 131242-WST02-DR-IP-1292-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1292 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6559 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1293 | C | 131242-WST02-DR-IP-1293-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1293 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6560 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1294 | C | 131242-WST02-DR-IP-1294-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1294 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6561 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1295 | C | 131242-WST02-DR-IP-1295-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1295 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6562 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1296 | C | 131242-WST02-DR-IP-1296-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1296 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6563 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1297 | C | 131242-WST02-DR-IP-1297-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1297 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6564 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1298 | C | 131242-WST02-DR-IP-1298-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1298 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6565 | 001147 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1299 | C | 131242-WST02-DR-IP-1299-C | 2025-07-29 | SSN RIO 0201 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1299 | NA | "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | C | 001147 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6566 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-IP-1351-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1351 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6567 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1352 | B | 131242-WST02-DR-IP-1352-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1352 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6568 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1353 | B | 131242-WST02-DR-IP-1353-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1353 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6569 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1354 | B | 131242-WST02-DR-IP-1354-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1354 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6570 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1355 | B | 131242-WST02-DR-IP-1355-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1355 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6571 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1356 | B | 131242-WST02-DR-IP-1356-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1356 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6572 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1357 | B | 131242-WST02-DR-IP-1357-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1357 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6573 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1358 | B | 131242-WST02-DR-IP-1358-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1358 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6574 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1359 | B | 131242-WST02-DR-IP-1359-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1359 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6575 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1360 | B | 131242-WST02-DR-IP-1360-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1360 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6576 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1361 | B | 131242-WST02-DR-IP-1361-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1361 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6577 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1362 | B | 131242-WST02-DR-IP-1362-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1362 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6578 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1363 | B | 131242-WST02-DR-IP-1363-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1363 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6579 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1364 | B | 131242-WST02-DR-IP-1364-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1364 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6580 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1365 | B | 131242-WST02-DR-IP-1365-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1365 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6581 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1366 | B | 131242-WST02-DR-IP-1366-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1366 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6582 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1367 | B | 131242-WST02-DR-IP-1367-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1367 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6583 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1368 | B | 131242-WST02-DR-IP-1368-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1368 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6584 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1369 | B | 131242-WST02-DR-IP-1369-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1369 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6585 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1370 | B | 131242-WST02-DR-IP-1370-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1370 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6586 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1371 | B | 131242-WST02-DR-IP-1371-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1371 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6587 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1372 | B | 131242-WST02-DR-IP-1372-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1372 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6588 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1373 | B | 131242-WST02-DR-IP-1373-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1373 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6589 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1374 | B | 131242-WST02-DR-IP-1374-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1374 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6590 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1375 | B | 131242-WST02-DR-IP-1375-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1375 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6591 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1376 | B | 131242-WST02-DR-IP-1376-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1376 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6592 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1377 | B | 131242-WST02-DR-IP-1377-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1377 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6593 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1378 | B | 131242-WST02-DR-IP-1378-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1378 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6594 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1379 | B | 131242-WST02-DR-IP-1379-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1379 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6595 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1380 | B | 131242-WST02-DR-IP-1380-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1380 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6596 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1381 | B | 131242-WST02-DR-IP-1381-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1381 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6597 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1382 | B | 131242-WST02-DR-IP-1382-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1382 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6598 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1383 | B | 131242-WST02-DR-IP-1383-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1383 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6599 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1384 | B | 131242-WST02-DR-IP-1384-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1384 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6600 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1385 | B | 131242-WST02-DR-IP-1385-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1385 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6601 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1386 | B | 131242-WST02-DR-IP-1386-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1386 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6602 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1387 | B | 131242-WST02-DR-IP-1387-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1387 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6603 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1388 | B | 131242-WST02-DR-IP-1388-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1388 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6604 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1389 | B | 131242-WST02-DR-IP-1389-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1389 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6605 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1390 | B | 131242-WST02-DR-IP-1390-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1390 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6606 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1391 | B | 131242-WST02-DR-IP-1391-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1391 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6607 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1392 | B | 131242-WST02-DR-IP-1392-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1392 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6608 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1393 | B | 131242-WST02-DR-IP-1393-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1393 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6609 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1394 | B | 131242-WST02-DR-IP-1394-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1394 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6610 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1395 | B | 131242-WST02-DR-IP-1395-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1395 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6611 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1396 | B | 131242-WST02-DR-IP-1396-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1396 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6612 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1397 | B | 131242-WST02-DR-IP-1397-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1397 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6613 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1398 | B | 131242-WST02-DR-IP-1398-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1398 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6614 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1399 | B | 131242-WST02-DR-IP-1399-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1399 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6615 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1400 | B | 131242-WST02-DR-IP-1400-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1400 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 111 | NAP | 2025-12-18 | H | 000753&&000836&&001148&&001730&&001914 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
6616 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1401 | B | 131242-WST02-DR-IP-1401-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1401 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-12-18 | H | 001148&&001730&&001914 | 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6617 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1402 | B | 131242-WST02-DR-IP-1402-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1402 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-12-18 | C | 001148&&001914 | 2025-03-21, 2025-07-29, 2025-12-18 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6618 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1403 | B | 131242-WST02-DR-IP-1403-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1403 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-12-18 | C | 001148&&001914 | 2025-03-21, 2025-07-29, 2025-12-18 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6619 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1404 | B | 131242-WST02-DR-IP-1404-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1404 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6620 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1405 | B | 131242-WST02-DR-IP-1405-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1405 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6621 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1406 | B | 131242-WST02-DR-IP-1406-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1406 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6622 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1407 | B | 131242-WST02-DR-IP-1407-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1407 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6623 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1408 | B | 131242-WST02-DR-IP-1408-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1408 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6624 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1409 | B | 131242-WST02-DR-IP-1409-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1409 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6625 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1410 | B | 131242-WST02-DR-IP-1410-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1410 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6626 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1411 | B | 131242-WST02-DR-IP-1411-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1411 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6627 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1412 | B | 131242-WST02-DR-IP-1412-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1412 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6628 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1413 | B | 131242-WST02-DR-IP-1413-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1413 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6629 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1414 | B | 131242-WST02-DR-IP-1414-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1414 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6630 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1415 | B | 131242-WST02-DR-IP-1415-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1415 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6631 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1416 | B | 131242-WST02-DR-IP-1416-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1416 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6632 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1417 | B | 131242-WST02-DR-IP-1417-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1417 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6633 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1418 | B | 131242-WST02-DR-IP-1418-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1418 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6634 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1419 | B | 131242-WST02-DR-IP-1419-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1419 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6635 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1420 | B | 131242-WST02-DR-IP-1420-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1420 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6636 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1421 | B | 131242-WST02-DR-IP-1421-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1421 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6637 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1422 | B | 131242-WST02-DR-IP-1422-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1422 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6638 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1423 | B | 131242-WST02-DR-IP-1423-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1423 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6639 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1424 | B | 131242-WST02-DR-IP-1424-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1424 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6640 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1425 | B | 131242-WST02-DR-IP-1425-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1425 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6641 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1426 | B | 131242-WST02-DR-IP-1426-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1426 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6642 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1427 | B | 131242-WST02-DR-IP-1427-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1427 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6643 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1428 | B | 131242-WST02-DR-IP-1428-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1428 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6644 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1429 | B | 131242-WST02-DR-IP-1429-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1429 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6645 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1430 | B | 131242-WST02-DR-IP-1430-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1430 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6646 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1431 | B | 131242-WST02-DR-IP-1431-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1431 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6647 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1432 | B | 131242-WST02-DR-IP-1432-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1432 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6648 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1433 | B | 131242-WST02-DR-IP-1433-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1433 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6649 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1434 | B | 131242-WST02-DR-IP-1434-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1434 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6650 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1435 | B | 131242-WST02-DR-IP-1435-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1435 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6651 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1436 | B | 131242-WST02-DR-IP-1436-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1436 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6652 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1437 | B | 131242-WST02-DR-IP-1437-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1437 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6653 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1438 | B | 131242-WST02-DR-IP-1438-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1438 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6654 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1439 | B | 131242-WST02-DR-IP-1439-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1439 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6655 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1440 | B | 131242-WST02-DR-IP-1440-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1440 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6656 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1441 | B | 131242-WST02-DR-IP-1441-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1441 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6657 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1442 | B | 131242-WST02-DR-IP-1442-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1442 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6658 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1443 | B | 131242-WST02-DR-IP-1443-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1443 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6659 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1444 | B | 131242-WST02-DR-IP-1444-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1444 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6660 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1445 | B | 131242-WST02-DR-IP-1445-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1445 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6661 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1446 | B | 131242-WST02-DR-IP-1446-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1446 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6662 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1447 | B | 131242-WST02-DR-IP-1447-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1447 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6663 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1448 | B | 131242-WST02-DR-IP-1448-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1448 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6664 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1449 | B | 131242-WST02-DR-IP-1449-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1449 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6665 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1450 | B | 131242-WST02-DR-IP-1450-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1450 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6666 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1451 | B | 131242-WST02-DR-IP-1451-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1451 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6667 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1452 | B | 131242-WST02-DR-IP-1452-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1452 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6668 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1453 | B | 131242-WST02-DR-IP-1453-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1453 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6669 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1454 | B | 131242-WST02-DR-IP-1454-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1454 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6670 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1455 | B | 131242-WST02-DR-IP-1455-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1455 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6671 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1456 | B | 131242-WST02-DR-IP-1456-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1456 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6672 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1457 | B | 131242-WST02-DR-IP-1457-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1457 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6673 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1458 | B | 131242-WST02-DR-IP-1458-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1458 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6674 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1459 | B | 131242-WST02-DR-IP-1459-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1459 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6675 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1460 | B | 131242-WST02-DR-IP-1460-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1460 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6676 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1461 | B | 131242-WST02-DR-IP-1461-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1461 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6677 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1462 | B | 131242-WST02-DR-IP-1462-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1462 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6678 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1463 | B | 131242-WST02-DR-IP-1463-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1463 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6679 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1464 | B | 131242-WST02-DR-IP-1464-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1464 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6680 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1465 | B | 131242-WST02-DR-IP-1465-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1465 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6681 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1466 | B | 131242-WST02-DR-IP-1466-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1466 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6682 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1467 | B | 131242-WST02-DR-IP-1467-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1467 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6683 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1468 | B | 131242-WST02-DR-IP-1468-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1468 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6684 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1469 | B | 131242-WST02-DR-IP-1469-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1469 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6685 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1470 | B | 131242-WST02-DR-IP-1470-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1470 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6686 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1471 | B | 131242-WST02-DR-IP-1471-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1471 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6687 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1472 | B | 131242-WST02-DR-IP-1472-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1472 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6688 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1473 | B | 131242-WST02-DR-IP-1473-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1473 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6689 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1474 | B | 131242-WST02-DR-IP-1474-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1474 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6690 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1475 | B | 131242-WST02-DR-IP-1475-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1475 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6691 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1476 | B | 131242-WST02-DR-IP-1476-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1476 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6692 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1477 | B | 131242-WST02-DR-IP-1477-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1477 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6693 | 001148 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1478 | B | 131242-WST02-DR-IP-1478-B | 2025-03-21 | SSN RIO 0202 GA & Wiring Diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-18 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-DR-1478 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 111 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
6694 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1351 | B | 131242-WST02-DR-IP-1351-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1351 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6695 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1352 | B | 131242-WST02-DR-IP-1352-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1352 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6696 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1353 | B | 131242-WST02-DR-IP-1353-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1353 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6697 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1354 | B | 131242-WST02-DR-IP-1354-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1354 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6698 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1355 | B | 131242-WST02-DR-IP-1355-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1355 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6699 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1356 | B | 131242-WST02-DR-IP-1356-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1356 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6700 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1357 | B | 131242-WST02-DR-IP-1357-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1357 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6701 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1358 | B | 131242-WST02-DR-IP-1358-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1358 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6702 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1359 | B | 131242-WST02-DR-IP-1359-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1359 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6703 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1360 | B | 131242-WST02-DR-IP-1360-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1360 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6704 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1361 | B | 131242-WST02-DR-IP-1361-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1361 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6705 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1362 | B | 131242-WST02-DR-IP-1362-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1362 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6706 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1363 | B | 131242-WST02-DR-IP-1363-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1363 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6707 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1364 | B | 131242-WST02-DR-IP-1364-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1364 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6708 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1365 | B | 131242-WST02-DR-IP-1365-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1365 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6709 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1366 | B | 131242-WST02-DR-IP-1366-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1366 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6710 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1367 | B | 131242-WST02-DR-IP-1367-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1367 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6711 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1368 | B | 131242-WST02-DR-IP-1368-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1368 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6712 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1369 | B | 131242-WST02-DR-IP-1369-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1369 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6713 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1370 | B | 131242-WST02-DR-IP-1370-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1370 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6714 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1371 | B | 131242-WST02-DR-IP-1371-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1371 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6715 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1372 | B | 131242-WST02-DR-IP-1372-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1372 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6716 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1373 | B | 131242-WST02-DR-IP-1373-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1373 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6717 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1374 | B | 131242-WST02-DR-IP-1374-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1374 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6718 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1375 | B | 131242-WST02-DR-IP-1375-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1375 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6719 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1376 | B | 131242-WST02-DR-IP-1376-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1376 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6720 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1377 | B | 131242-WST02-DR-IP-1377-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1377 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6721 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1378 | B | 131242-WST02-DR-IP-1378-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1378 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6722 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1379 | B | 131242-WST02-DR-IP-1379-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1379 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6723 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1380 | B | 131242-WST02-DR-IP-1380-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1380 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6724 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1381 | B | 131242-WST02-DR-IP-1381-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1381 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6725 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1382 | B | 131242-WST02-DR-IP-1382-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1382 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6726 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1383 | B | 131242-WST02-DR-IP-1383-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1383 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6727 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1384 | B | 131242-WST02-DR-IP-1384-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1384 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6728 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1385 | B | 131242-WST02-DR-IP-1385-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1385 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6729 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1386 | B | 131242-WST02-DR-IP-1386-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1386 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6730 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1387 | B | 131242-WST02-DR-IP-1387-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1387 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6731 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1388 | B | 131242-WST02-DR-IP-1388-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1388 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6732 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1389 | B | 131242-WST02-DR-IP-1389-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1389 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6733 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1390 | B | 131242-WST02-DR-IP-1390-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1390 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6734 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1391 | B | 131242-WST02-DR-IP-1391-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1391 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6735 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1392 | B | 131242-WST02-DR-IP-1392-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1392 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6736 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1393 | B | 131242-WST02-DR-IP-1393-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1393 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6737 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1394 | B | 131242-WST02-DR-IP-1394-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1394 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6738 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1395 | B | 131242-WST02-DR-IP-1395-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1395 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6739 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1396 | B | 131242-WST02-DR-IP-1396-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1396 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6740 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1397 | B | 131242-WST02-DR-IP-1397-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1397 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6741 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1398 | B | 131242-WST02-DR-IP-1398-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1398 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6742 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1399 | B | 131242-WST02-DR-IP-1399-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1399 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6743 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1400 | B | 131242-WST02-DR-IP-1400-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1400 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-12-18 | H | 000753&&000836&&001148&&001730&&001914 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
6744 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1401 | B | 131242-WST02-DR-IP-1401-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1401 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-12-18 | H | 001148&&001730&&001914 | 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
6745 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1402 | B | 131242-WST02-DR-IP-1402-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1402 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-12-18 | C | 001148&&001914 | 2025-03-21, 2025-07-29, 2025-12-18 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6746 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1403 | B | 131242-WST02-DR-IP-1403-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1403 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-12-18 | C | 001148&&001914 | 2025-03-21, 2025-07-29, 2025-12-18 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
6747 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1404 | B | 131242-WST02-DR-IP-1404-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1404 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6748 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1405 | B | 131242-WST02-DR-IP-1405-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1405 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6749 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1406 | B | 131242-WST02-DR-IP-1406-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1406 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6750 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1407 | B | 131242-WST02-DR-IP-1407-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1407 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6751 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1408 | B | 131242-WST02-DR-IP-1408-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1408 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6752 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1409 | B | 131242-WST02-DR-IP-1409-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1409 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6753 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1410 | B | 131242-WST02-DR-IP-1410-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1410 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6754 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1411 | B | 131242-WST02-DR-IP-1411-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1411 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6755 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1412 | B | 131242-WST02-DR-IP-1412-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1412 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6756 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1413 | B | 131242-WST02-DR-IP-1413-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1413 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6757 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1414 | B | 131242-WST02-DR-IP-1414-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1414 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6758 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1415 | B | 131242-WST02-DR-IP-1415-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1415 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6759 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1416 | B | 131242-WST02-DR-IP-1416-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1416 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6760 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1417 | B | 131242-WST02-DR-IP-1417-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1417 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6761 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1418 | B | 131242-WST02-DR-IP-1418-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1418 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6762 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1419 | B | 131242-WST02-DR-IP-1419-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1419 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6763 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1420 | B | 131242-WST02-DR-IP-1420-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1420 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6764 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1421 | B | 131242-WST02-DR-IP-1421-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1421 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6765 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1422 | B | 131242-WST02-DR-IP-1422-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1422 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6766 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1423 | B | 131242-WST02-DR-IP-1423-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1423 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6767 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1424 | B | 131242-WST02-DR-IP-1424-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1424 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6768 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1425 | B | 131242-WST02-DR-IP-1425-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1425 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6769 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1426 | B | 131242-WST02-DR-IP-1426-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1426 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6770 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1427 | B | 131242-WST02-DR-IP-1427-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1427 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6771 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1428 | B | 131242-WST02-DR-IP-1428-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1428 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6772 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1429 | B | 131242-WST02-DR-IP-1429-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1429 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6773 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1430 | B | 131242-WST02-DR-IP-1430-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1430 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6774 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1431 | B | 131242-WST02-DR-IP-1431-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1431 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6775 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1432 | B | 131242-WST02-DR-IP-1432-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1432 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6776 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1433 | B | 131242-WST02-DR-IP-1433-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1433 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6777 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1434 | B | 131242-WST02-DR-IP-1434-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1434 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6778 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1435 | B | 131242-WST02-DR-IP-1435-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1435 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6779 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1436 | B | 131242-WST02-DR-IP-1436-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1436 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6780 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1437 | B | 131242-WST02-DR-IP-1437-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1437 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6781 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1438 | B | 131242-WST02-DR-IP-1438-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1438 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6782 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1439 | B | 131242-WST02-DR-IP-1439-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1439 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6783 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1440 | B | 131242-WST02-DR-IP-1440-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1440 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6784 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1441 | B | 131242-WST02-DR-IP-1441-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1441 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6785 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1442 | B | 131242-WST02-DR-IP-1442-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1442 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6786 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1443 | B | 131242-WST02-DR-IP-1443-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1443 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6787 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1444 | B | 131242-WST02-DR-IP-1444-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1444 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6788 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1445 | B | 131242-WST02-DR-IP-1445-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1445 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6789 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1446 | B | 131242-WST02-DR-IP-1446-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1446 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6790 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1447 | B | 131242-WST02-DR-IP-1447-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1447 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6791 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1448 | B | 131242-WST02-DR-IP-1448-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1448 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6792 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1449 | B | 131242-WST02-DR-IP-1449-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1449 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6793 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1450 | B | 131242-WST02-DR-IP-1450-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1450 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6794 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1451 | B | 131242-WST02-DR-IP-1451-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1451 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6795 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1452 | B | 131242-WST02-DR-IP-1452-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1452 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6796 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1453 | B | 131242-WST02-DR-IP-1453-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1453 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6797 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1454 | B | 131242-WST02-DR-IP-1454-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1454 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6798 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1455 | B | 131242-WST02-DR-IP-1455-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1455 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6799 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1456 | B | 131242-WST02-DR-IP-1456-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1456 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6800 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1457 | B | 131242-WST02-DR-IP-1457-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1457 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6801 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1458 | B | 131242-WST02-DR-IP-1458-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1458 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6802 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1459 | B | 131242-WST02-DR-IP-1459-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1459 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6803 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1460 | B | 131242-WST02-DR-IP-1460-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1460 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6804 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1461 | B | 131242-WST02-DR-IP-1461-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1461 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6805 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1462 | B | 131242-WST02-DR-IP-1462-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1462 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6806 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1463 | B | 131242-WST02-DR-IP-1463-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1463 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6807 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1464 | B | 131242-WST02-DR-IP-1464-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1464 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6808 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1465 | B | 131242-WST02-DR-IP-1465-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1465 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6809 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1466 | B | 131242-WST02-DR-IP-1466-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1466 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6810 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1467 | B | 131242-WST02-DR-IP-1467-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1467 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6811 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1468 | B | 131242-WST02-DR-IP-1468-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1468 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6812 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1469 | B | 131242-WST02-DR-IP-1469-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1469 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6813 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1470 | B | 131242-WST02-DR-IP-1470-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1470 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6814 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1471 | B | 131242-WST02-DR-IP-1471-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1471 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6815 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1472 | B | 131242-WST02-DR-IP-1472-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1472 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6816 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1473 | B | 131242-WST02-DR-IP-1473-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1473 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6817 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1474 | B | 131242-WST02-DR-IP-1474-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1474 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6818 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1475 | B | 131242-WST02-DR-IP-1475-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1475 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6819 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1476 | B | 131242-WST02-DR-IP-1476-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1476 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6820 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1477 | B | 131242-WST02-DR-IP-1477-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1477 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6821 | 001148 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1478 | B | 131242-WST02-DR-IP-1478-B | 2025-07-29 | SSN RIO 0202 GA & Wiring Diagram | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1478 | NA | "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 135 | NAP | 2025-07-29 | B | 001148 | 2025-03-21, 2025-07-29 | 00, 01 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
6822 | 001149 | 00 | Dhanapal.S | QAQC | NA | 131242 | WSW41 | DS | B | 1397 | 0 | 131242-WSW41-DS-B-1397-0 | 2025-03-21 | Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance) | Approved | 2025-04-18 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WSW41-DS-1397 | NA | "Sample Board Submission for Trunking, Conduit and Accessories, Field Devices for Clean gas System and Cables for Various Fire Protection and Smoke detection and Speakers for one -way EVC Public Address System(Pacific Reliance)" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-10 | 65 | APP | 2025-03-21 | 0 | 001149 | 2025-03-21 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
6823 | 001150 | 00 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 0 | 131242-WSD11-RT-S-0002-0 | 2025-03-24 | Report of Project Safety Review for THP Trains Installation | Approved with Comments | 2025-04-21 | 2025-05-13 | Approved with Comments | 2025-06-02 | YES | Resubmitted |  | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 50 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6824 | 001150 | 01 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 1 | 131242-WSD11-RT-S-0002-1 | 2025-06-18 | Report of Project Safety Review for THP Trains Installation | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-08 | 2025-07-04 | Approved with Comments | 2025-07-24 | YES | Resubmitted |  | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 16 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6825 | 001150 | 02 | Max | CSA | NA | 131242 | WSD11 | RT | S | 0002 | 2 | 131242-WSD11-RT-S-0002-2 | 2025-09-03 | Report of Project Safety Review for THP Trains Installation | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-10-14 | Approved with Comments | 2025-11-03 | NO | Overdue |  | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-17 | 41 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6826 | 001151 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0059 | 0 | 131242-WSW41-QA-M-0059-0 | 2025-03-24 | FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch) | NA | 2025-04-21 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSW41-QA-0059 | NA | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" && "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | 2025-03-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-13 | 162 | AWC | 2025-12-18 | 1 | 001151&&001799&&001860 | 2025-03-24, 2025-10-29, 2025-11-24, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
6827 | 001152 | 00 | N.Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0028 | 0 | 131242-WSW41-SP-C-0028-0 | 2025-03-24 | Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) | Approved | 2025-04-21 | 2025-05-09 | Approved |  | YES | NA |  | 131242-WSW41-SP-0028 | NA | "Material submission - Steel Structure Normal Paint Coating System (Sanhe – Singapore fabrication) " | 2025-03-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-13 | 46 | APP | 2025-03-24 | 0 | 001152 | 2025-03-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
6828 | 001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | CL | S | 0003 | 0 | 131242-WST02-CL-S-0003-0 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | Approved |  | YES | NA |  | 131242-WST02-CL-0003 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-07 | 35 | APP | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | Approved | APP |  |  | 0 | APP | APP
6829 | 001153 | 00 | Yibo | QAQC | NA | 131242 | WST02 | DR | S | 5603 | A.3 | 131242-WST02-DR-S-5603-A.3 | 2025-03-24 | Design Calculation and Drawings for Hyperbolic Mixer Anchor | Approved | 2025-04-21 | 2025-04-28 | Approved |  | YES | NA |  | 131242-WST02-DR-5603 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-03-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-13 | 35 | APP | 2025-07-24 | A | 001153&&001528 | 2025-03-24, 2025-07-24 | 00 | 2 | Not Approved | NAP |  |  | 0 | APP | APP
6830 | 001154 | 00 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 0 | 131242-WST02-VI-BF-0001-0 | 2025-03-24 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-04-21 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 43 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
6831 | 001154 | 01 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 1 | 131242-WST02-VI-BF-0001-1 | 2025-06-04 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-06-24 | 2025-07-08 | Not Approved | 2025-07-28 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 34 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
6832 | 001154 | 02 | K. Balaji | BS | NA | 131242 | WST02 | VI | BF | 0001 | 2 | 131242-WST02-VI-BF-0001-2 | 2025-08-12 | Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow) | Rev 0: Not approved - Revise and Resubmit | 2025-09-01 | 2026-01-05 | Approved |  | YES | NA |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-26 | 146 | APP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | APP | APP
6833 | 001155 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 0 | 131242-WST02-CD-I-0012-0 | 2025-03-24 | SSN -RIO PANEL 0203- I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-21 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-CD-0012 | NA | "SSN -RIO PANEL 0203- I/O List " && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 34 | NAP | 2025-06-25 | 1 | 000183&&001155 | 2023-11-10, 2025-03-24, 2025-06-25 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6834 | 001155 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0012 | 1 | 131242-WST02-CD-I-0012-1 | 2025-06-25 | SSN -RIO PANEL 0203- I/O List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-15 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WST02-CD-0012 | NA | "SSN -RIO PANEL 0203- I/O List " && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-09 | 69 | AWC | 2025-06-25 | 1 | 000183&&001155 | 2023-11-10, 2025-03-24, 2025-06-25 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
6835 | 001156 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | A | 0005 | 0 | 131242-WSW41-MS-A-0005-0 | 2025-03-24 | MSRA for Waterproofing Works | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-21 | 2025-04-15 | Not Approved | 2025-05-05 | NO | Overdue |  | 131242-WSW41-MS-0005 | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 22 | NAP | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | Not Approved | NAP | 2025-05-05 | Overdue | 0 | NAP | NAP
6836 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | A | 131242-WST02-DR-EI-7200-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7200 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001806 | 2025-03-25, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6837 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7201 | A | 131242-WST02-DR-EI-7201-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7201 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6838 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7202 | A | 131242-WST02-DR-EI-7202-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7202 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6839 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7203 | A | 131242-WST02-DR-EI-7203-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7203 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6840 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7204 | A | 131242-WST02-DR-EI-7204-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7204 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6841 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7205 | A | 131242-WST02-DR-EI-7205-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7205 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6842 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7206 | A | 131242-WST02-DR-EI-7206-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7206 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6843 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7207 | A | 131242-WST02-DR-EI-7207-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7207 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6844 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7208 | A | 131242-WST02-DR-EI-7208-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7208 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6845 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7209 | A | 131242-WST02-DR-EI-7209-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7209 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN PMS Network Architecture Drawings" | 2025-03-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 56 | NAP | 2025-08-07 | 1 | 001112&&001157 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6846 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7220 | A | 131242-WST02-DR-EI-7220-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7220 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6847 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7221 | A | 131242-WST02-DR-EI-7221-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7221 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6848 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7222 | A | 131242-WST02-DR-EI-7222-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7222 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6849 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7223 | A | 131242-WST02-DR-EI-7223-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7223 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6850 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7224 | A | 131242-WST02-DR-EI-7224-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7224 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6851 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7225 | A | 131242-WST02-DR-EI-7225-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7225 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6852 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7226 | A | 131242-WST02-DR-EI-7226-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7226 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6853 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7227 | A | 131242-WST02-DR-EI-7227-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7227 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6854 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7228 | A | 131242-WST02-DR-EI-7228-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7228 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6855 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7229 | A | 131242-WST02-DR-EI-7229-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7229 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6856 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3066 | A | 131242-WST02-DR-EP-3066-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3066 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6857 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3067 | A | 131242-WST02-DR-EP-3067-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3067 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6858 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3068 | A | 131242-WST02-DR-EP-3068-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3068 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6859 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3069 | A | 131242-WST02-DR-EP-3069-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3069 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6860 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3070 | A | 131242-WST02-DR-EP-3070-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3070 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6861 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3071 | A | 131242-WST02-DR-EP-3071-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3071 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6862 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3072 | A | 131242-WST02-DR-EP-3072-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3072 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6863 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3073 | A | 131242-WST02-DR-EP-3073-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3073 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6864 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3074 | A | 131242-WST02-DR-EP-3074-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3074 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6865 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3075 | A | 131242-WST02-DR-EP-3075-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3075 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6866 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3076 | A | 131242-WST02-DR-EP-3076-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3076 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6867 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3077 | A | 131242-WST02-DR-EP-3077-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3077 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6868 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3078 | A | 131242-WST02-DR-EP-3078-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3078 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6869 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3079 | A | 131242-WST02-DR-EP-3079-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3079 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6870 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7148 | A | 131242-WST02-DR-EP-7148-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7148 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 56 | NAP | 2025-07-21 | B | 000867&&001157 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6871 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7149 | A | 131242-WST02-DR-EP-7149-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7149 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 000867&&001157 | 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6872 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7150 | A | 131242-WST02-DR-EP-7150-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7150 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6873 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7151 | A | 131242-WST02-DR-EP-7151-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7151 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6874 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7152 | A | 131242-WST02-DR-EP-7152-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7152 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6875 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7153 | A | 131242-WST02-DR-EP-7153-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7153 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6876 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7154 | A | 131242-WST02-DR-EP-7154-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7154 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6877 | 001157 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7155 | A | 131242-WST02-DR-EP-7155-A | 2025-03-25 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Not Approved - Revise and resubmit | 2025-04-22 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-7155 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 56 | NAP | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6878 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7200 | B | 131242-WST02-DR-EI-7200-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7200 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001806 | 2025-03-25, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6879 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7201 | B | 131242-WST02-DR-EI-7201-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7201 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6880 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7202 | B | 131242-WST02-DR-EI-7202-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7202 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6881 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7203 | B | 131242-WST02-DR-EI-7203-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7203 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6882 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7204 | B | 131242-WST02-DR-EI-7204-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7204 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6883 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7205 | B | 131242-WST02-DR-EI-7205-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7205 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6884 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7206 | B | 131242-WST02-DR-EI-7206-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7206 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6885 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7207 | B | 131242-WST02-DR-EI-7207-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7207 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6886 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7208 | B | 131242-WST02-DR-EI-7208-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7208 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6887 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7209 | B | 131242-WST02-DR-EI-7209-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7209 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN PMS Network Architecture Drawings" | 2025-03-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-08-07 | 1 | 001112&&001157 | 2025-03-10, 2025-03-25, 2025-07-21, 2025-08-07 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6888 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7220 | B | 131242-WST02-DR-EI-7220-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7220 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6889 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7221 | B | 131242-WST02-DR-EI-7221-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7221 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6890 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7222 | B | 131242-WST02-DR-EI-7222-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7222 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6891 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7223 | B | 131242-WST02-DR-EI-7223-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7223 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6892 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7224 | B | 131242-WST02-DR-EI-7224-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7224 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6893 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7225 | B | 131242-WST02-DR-EI-7225-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7225 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6894 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7226 | B | 131242-WST02-DR-EI-7226-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7226 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6895 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7227 | B | 131242-WST02-DR-EI-7227-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7227 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6896 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7228 | B | 131242-WST02-DR-EI-7228-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7228 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6897 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7229 | B | 131242-WST02-DR-EI-7229-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7229 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6898 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3066 | B | 131242-WST02-DR-EP-3066-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3066 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6899 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3067 | B | 131242-WST02-DR-EP-3067-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3067 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6900 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3068 | B | 131242-WST02-DR-EP-3068-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3068 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6901 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3069 | B | 131242-WST02-DR-EP-3069-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3069 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6902 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3070 | B | 131242-WST02-DR-EP-3070-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3070 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6903 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3071 | B | 131242-WST02-DR-EP-3071-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3071 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6904 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3072 | B | 131242-WST02-DR-EP-3072-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3072 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6905 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3073 | B | 131242-WST02-DR-EP-3073-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3073 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6906 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3074 | B | 131242-WST02-DR-EP-3074-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3074 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6907 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3075 | B | 131242-WST02-DR-EP-3075-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3075 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6908 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3076 | B | 131242-WST02-DR-EP-3076-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3076 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6909 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3077 | B | 131242-WST02-DR-EP-3077-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3077 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6910 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3078 | B | 131242-WST02-DR-EP-3078-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3078 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6911 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3079 | B | 131242-WST02-DR-EP-3079-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-3079 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6912 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7148 | B | 131242-WST02-DR-EP-7148-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7148 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 000867&&001157 | 2024-12-02, 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6913 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7149 | B | 131242-WST02-DR-EP-7149-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7149 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 000867&&001157 | 2025-03-25, 2025-03-28, 2025-07-21 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6914 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7150 | B | 131242-WST02-DR-EP-7150-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7150 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6915 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7151 | B | 131242-WST02-DR-EP-7151-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7151 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6916 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7152 | B | 131242-WST02-DR-EP-7152-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7152 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6917 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7153 | B | 131242-WST02-DR-EP-7153-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7153 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6918 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7154 | B | 131242-WST02-DR-EP-7154-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7154 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6919 | 001157 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7155 | B | 131242-WST02-DR-EP-7155-B | 2025-07-21 | SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-18 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-DR-7155 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 45 | AWC | 2025-07-21 | B | 001157 | 2025-03-25, 2025-07-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
6920 | 001158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | E | 0010 | 0 | 131242-WST02-RT-E-0010-0 | 2025-03-25 | SSN Protection Coordination Study Report | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-22 | 2025-05-27 | Approved with Comments | 2025-06-16 | NO | Overdue |  | 131242-WST02-RT-0010 | NA | "SSN Protection Coordination Study Report" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 63 | AWC | 2025-03-25 | 0 | 001158 | 2025-03-25 | 00 | 1 | Approved with Comments | AWC | 2025-06-16 | Overdue | 0 | AWC | AWC
6921 | 001159 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | E | 0005 | 0 | 131242-WSD11-RT-E-0005-0 | 2025-03-25 | THP Protection Coordination Study Report | : Rev 0: Approved with comments. To revise and resubmit | 2025-04-22 | 2025-05-27 | Approved with Comments | 2025-06-16 | NO | Overdue |  | 131242-WSD11-RT-0005 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "THP Protection Coordination Study Report" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 63 | AWC | 2025-07-01 | 0 | 001159&&001420 | 2025-03-25, 2025-07-01 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6922 | 001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7201 | A | 131242-WSD11-DR-I-7201-A | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue |  | 131242-WSD11-DR-7201 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 51 | AWC | 2026-01-27 | B | 001160&&001758 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6923 | 001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7202 | A | 131242-WSD11-DR-I-7202-A | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue |  | 131242-WSD11-DR-7202 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 51 | AWC | 2026-01-27 | B | 001160&&001758 | 2025-03-25, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
6924 | 001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7203 | A | 131242-WSD11-DR-I-7203-A | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue |  | 131242-WSD11-DR-7203 | NA | "THP UPS DB SLD Drawing " | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 51 | AWC | 2025-03-25 | A | 001160 | 2025-03-25 | 00 | 1 | Approved with Comments | AWC | 2025-06-04 | Overdue | 0 | AWC | AWC
6925 | 001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7204 | A | 131242-WSD11-DR-I-7204-A | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue |  | 131242-WSD11-DR-7204 | NA | "THP UPS DB SLD Drawing " | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 51 | AWC | 2025-03-25 | A | 001160 | 2025-03-25 | 00 | 1 | Approved with Comments | AWC | 2025-06-04 | Overdue | 0 | AWC | AWC
6926 | 001160 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | DR | I | 7205 | A | 131242-WSD11-DR-I-7205-A | 2025-03-25 | THP UPS DB SLD Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue |  | 131242-WSD11-DR-7205 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 51 | AWC | 2026-01-27 | B | 001160&&001759 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
6927 | 001161 | 00 | Charles | CSA | NA | 131242 | WSW41 | MS | A | 0001 | 0 | 131242-WSW41-MS-A-0001-0 | 2025-03-25 | MSRA and SWP for MEICA OPENING on Block-wall | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 | Approved with Comments | 2025-05-05 | NO | Overdue |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 21 | AWC | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | AWC | AWC
6928 | 001162 | 00 | N.Kumar | CSA | NA | 131242 | WSW41 | MS | C | 0027 | 0 | 131242-WSW41-MS-C-0027-0 | 2025-03-25 | Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-04-22 | 2025-04-15 | Not Approved | 2025-05-05 | NO | Overdue |  | 131242-WSW41-MS-0027 | NA | "Proposed Test Method (UPV) to find the quality of concrete in-situ Strength at low concrete cube strength locations SSN Watertank walls GL D4-F4/2-4 (+4.78 to +10.78) " | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 21 | NAP | 2025-03-25 | 0 | 001162 | 2025-03-25 | 00 | 1 | Not Approved | NAP | 2025-05-05 | Overdue | 0 | NAP | NAP
6929 | 001163 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0008 | 0 | 131242-WSW41-PO-E-0008-0 | 2025-03-25 | Unpriced PO for Cable Raceway (Jiangsu HDMann) | Rev 0: For information. | 2025-04-22 | 2025-05-06 | For Information |  | YES | NA |  | 131242-WSW41-PO-0008 | NA | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" && "Unpriced PO for Centrifugal Pump (KSB)" && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-08 | 42 | INF | 2025-08-01 | 0 | 000608&&001163&&001507 | 2024-08-01, 2025-03-25, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
6930 | 001164 | 00 | Aaron | CSA | NA | 131242 | WSW41 | VI | A | 0005 | 0 | 131242-WSW41-VI-A-0005-0 | 2025-03-25 | Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd) | R0: Approved | 2025-04-22 | 2025-04-15 | Approved |  | YES | NA |  | 131242-WSW41-VI-0005 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-08 | 21 | APP | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
6931 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | A | 131242-WST02-DR-IC-3001-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6932 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3002 | A | 131242-WST02-DR-IC-3002-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6933 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3003 | A | 131242-WST02-DR-IC-3003-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6934 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3004 | A | 131242-WST02-DR-IC-3004-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6935 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3005 | A | 131242-WST02-DR-IC-3005-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6936 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3006 | A | 131242-WST02-DR-IC-3006-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6937 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3007 | A | 131242-WST02-DR-IC-3007-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
6938 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3008 | A | 131242-WST02-DR-IC-3008-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
6939 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3009 | A | 131242-WST02-DR-IC-3009-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
6940 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3010 | A | 131242-WST02-DR-IC-3010-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6941 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3011 | A | 131242-WST02-DR-IC-3011-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6942 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3012 | A | 131242-WST02-DR-IC-3012-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
6943 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3013 | A | 131242-WST02-DR-IC-3013-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
6944 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3014 | A | 131242-WST02-DR-IC-3014-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
6945 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3015 | A | 131242-WST02-DR-IC-3015-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6946 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3016 | A | 131242-WST02-DR-IC-3016-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6947 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3017 | A | 131242-WST02-DR-IC-3017-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
6948 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3018 | A | 131242-WST02-DR-IC-3018-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6949 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3019 | A | 131242-WST02-DR-IC-3019-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6950 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3020 | A | 131242-WST02-DR-IC-3020-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6951 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3021 | A | 131242-WST02-DR-IC-3021-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6952 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3022 | A | 131242-WST02-DR-IC-3022-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6953 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3023 | A | 131242-WST02-DR-IC-3023-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6954 | 001165 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3024 | A | 131242-WST02-DR-IC-3024-A | 2025-03-25 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-18 | Not Approved | 2025-05-08 | YES | Resubmitted |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 24 | NAP | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6955 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3001 | B | 131242-WST02-DR-IC-3001-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6956 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3002 | B | 131242-WST02-DR-IC-3002-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6957 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3003 | B | 131242-WST02-DR-IC-3003-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6958 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3004 | B | 131242-WST02-DR-IC-3004-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6959 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3005 | B | 131242-WST02-DR-IC-3005-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6960 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3006 | B | 131242-WST02-DR-IC-3006-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6961 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3007 | B | 131242-WST02-DR-IC-3007-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6962 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3008 | B | 131242-WST02-DR-IC-3008-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6963 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3009 | B | 131242-WST02-DR-IC-3009-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6964 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3010 | B | 131242-WST02-DR-IC-3010-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6965 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3011 | B | 131242-WST02-DR-IC-3011-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6966 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3012 | B | 131242-WST02-DR-IC-3012-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6967 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3013 | B | 131242-WST02-DR-IC-3013-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6968 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3014 | B | 131242-WST02-DR-IC-3014-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6969 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3015 | B | 131242-WST02-DR-IC-3015-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6970 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3016 | B | 131242-WST02-DR-IC-3016-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6971 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3017 | B | 131242-WST02-DR-IC-3017-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
6972 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3018 | B | 131242-WST02-DR-IC-3018-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6973 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3019 | B | 131242-WST02-DR-IC-3019-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6974 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3020 | B | 131242-WST02-DR-IC-3020-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6975 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3021 | B | 131242-WST02-DR-IC-3021-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6976 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3022 | B | 131242-WST02-DR-IC-3022-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6977 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3023 | B | 131242-WST02-DR-IC-3023-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6978 | 001165 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3024 | B | 131242-WST02-DR-IC-3024-B | 2025-08-22 | SSN Panel(FIOP,FFOTP)- GA &Wiring drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 109 | NAP | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6979 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | A | 131242-WST02-DR-IP-2101-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2101 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6980 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2102 | A | 131242-WST02-DR-IP-2102-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2102 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6981 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2103 | A | 131242-WST02-DR-IP-2103-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2103 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6982 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2104 | A | 131242-WST02-DR-IP-2104-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2104 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6983 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2105 | A | 131242-WST02-DR-IP-2105-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2105 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6984 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2106 | A | 131242-WST02-DR-IP-2106-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2106 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6985 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2107 | A | 131242-WST02-DR-IP-2107-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2107 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6986 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2108 | A | 131242-WST02-DR-IP-2108-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2108 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6987 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2109 | A | 131242-WST02-DR-IP-2109-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2109 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6988 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2110 | A | 131242-WST02-DR-IP-2110-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2110 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6989 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2111 | A | 131242-WST02-DR-IP-2111-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2111 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6990 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2112 | A | 131242-WST02-DR-IP-2112-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2112 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6991 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2113 | A | 131242-WST02-DR-IP-2113-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2113 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6992 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2114 | A | 131242-WST02-DR-IP-2114-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2114 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6993 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2115 | A | 131242-WST02-DR-IP-2115-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2115 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6994 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2116 | A | 131242-WST02-DR-IP-2116-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2116 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6995 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2117 | A | 131242-WST02-DR-IP-2117-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2117 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6996 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2118 | A | 131242-WST02-DR-IP-2118-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2118 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
6997 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2119 | A | 131242-WST02-DR-IP-2119-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2119 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-03-25 | A | 001166 | 2025-03-25 | 00 | 1 | Not Approved | NAP | 2025-05-15 | Overdue | 0 | NAP | NAP
6998 | 001166 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2120 | A | 131242-WST02-DR-IP-2120-A | 2025-03-25 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-DR-2120 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-14 | 33 | NAP | 2025-03-25 | A | 001166 | 2025-03-25 | 00 | 1 | Not Approved | NAP | 2025-05-15 | Overdue | 0 | NAP | NAP
6999 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2101 | D | 131242-WST02-DR-IP-2101-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-02 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2101 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7000 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2102 | D | 131242-WST02-DR-IP-2102-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2102 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7001 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2103 | D | 131242-WST02-DR-IP-2103-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2103 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7002 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2104 | D | 131242-WST02-DR-IP-2104-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2104 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7003 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2105 | D | 131242-WST02-DR-IP-2105-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2105 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7004 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2106 | D | 131242-WST02-DR-IP-2106-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2106 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7005 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2107 | D | 131242-WST02-DR-IP-2107-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2107 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7006 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2108 | D | 131242-WST02-DR-IP-2108-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2108 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7007 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2109 | D | 131242-WST02-DR-IP-2109-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2109 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7008 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2110 | D | 131242-WST02-DR-IP-2110-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2110 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7009 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2111 | D | 131242-WST02-DR-IP-2111-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2111 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7010 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2112 | D | 131242-WST02-DR-IP-2112-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2112 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7011 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2113 | D | 131242-WST02-DR-IP-2113-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2113 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7012 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2114 | D | 131242-WST02-DR-IP-2114-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2114 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7013 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2115 | D | 131242-WST02-DR-IP-2115-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2115 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7014 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2116 | D | 131242-WST02-DR-IP-2116-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2116 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7015 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2117 | D | 131242-WST02-DR-IP-2117-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2117 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7016 | 001166 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2118 | D | 131242-WST02-DR-IP-2118-D | 2025-12-15 | SSN Panel (FIOP) - GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-2118 | NA | "SSN Panel (FIOP) - GA & Wiring Drawings" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 43 | AWC | 2025-12-15 | D | 001166 | 2025-03-25, 2025-12-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7017 | 001167 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 0 | 131242-WSD11-DS-I-0006-0 | 2025-03-25 | Datasheet for Electromagnetic Flow Meter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-22 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WSD11-DS-0006 | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 107 | NAP | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7018 | 001167 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0006 | 1 | 131242-WSD11-DS-I-0006-1 | 2025-10-16 | Datasheet for Electromagnetic Flow Meter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WSD11-DS-0006 | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-30 | 42 | AWC | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
7019 | 001168 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0006 | 0 | 131242-WST02-VI-A-0006-0 | 2025-03-26 | Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd. | Approved | 2025-04-23 | 2025-04-11 | Approved |  | YES | NA |  | 131242-WST02-VI-0006 | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-09 | 16 | APP | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
7020 | 001169 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0058 | 0 | 131242-WSW41-LT-PM-0058-0 | 2025-03-26 | Consent to Potential Acquisition of CES Construction by OKH | For Information | 2025-04-23 | 2025-04-05 | For Information |  | YES | NA |  | 131242-WSW41-LT-0058 | NA | "Consent to Potential Acquisition of CES Construction by OKH " | 2025-03-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 10 | INF | 2025-03-26 | 0 | 001169 | 2025-03-26 | 00 | 1 | For Information | INF | 2025-04-24 | Overdue | 0 | INF | INF
7021 | 001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 0 | 131242-WST02-CL-P-5701-0 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | Approved with Comments | 2025-05-15 | YES | Resubmitted |  | 131242-WST02-CL-5701 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 31 | AWC | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7022 | 001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5702 | 0 | 131242-WST02-CL-P-5702-0 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-CL-5702 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 31 | AWC | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7023 | 001170 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5703 | 0 | 131242-WST02-CL-P-5703-0 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-CL-5703 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 31 | AWC | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7024 | 001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5701 | 0 | 131242-WST02-DS-M-5701-0 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DS-5701 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 31 | AWC | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7025 | 001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5702 | 0 | 131242-WST02-DS-M-5702-0 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DS-5702 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 31 | AWC | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7026 | 001170 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 5703 | 0 | 131242-WST02-DS-M-5703-0 | 2025-03-27 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-24 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DS-5703 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 31 | AWC | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7027 | 001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5701 | 1 | 131242-WST02-CL-P-5701-1 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CL-5701 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
7028 | 001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5702 | 1 | 131242-WST02-CL-P-5702-1 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CL-5702 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
7029 | 001170 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5703 | 1 | 131242-WST02-CL-P-5703-1 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CL-5703 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
7030 | 001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5701 | 1 | 131242-WST02-DS-M-5701-1 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5701 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
7031 | 001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5702 | 1 | 131242-WST02-DS-M-5702-1 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5702 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
7032 | 001170 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 5703 | 1 | 131242-WST02-DS-M-5703-1 | 2025-07-07 | SSN FCV Calculation and Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5703 | NA | "SSN FCV Calculation and Datasheet" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 273 | PEN | 2025-07-07 | 1 | 001170 | 2025-03-27, 2025-07-07 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-22 |  | 0 | PEN | PEN
7033 | 001171 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 0 | 131242-WSD11-DS-I-0007-0 | 2025-03-27 | Datasheet for Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | Not Approved | 2025-08-01 | YES | Resubmitted |  | 131242-WSD11-DS-0007 | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 109 | NAP | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7034 | 001171 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0007 | 1 | 131242-WSD11-DS-I-0007-1 | 2025-10-16 | Datasheet for Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-11-05 | Approved with Comments | 2025-11-25 | NO | Overdue |  | 131242-WSD11-DS-0007 | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-30 | 20 | AWC | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2025-11-25 | Overdue | 0 | AWC | AWC
7035 | 001172 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 0 | 131242-WST02-DS-M-5391-0 | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | Approved with Comments | 2025-06-10 | YES | Resubmitted |  | 131242-WST02-DS-5391 | NA | "Datasheet & GA drawing for sampling pump" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 55 | AWC | 2025-10-18 | 1 | 001172 | 2025-03-27, 2025-10-18 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7036 | 001172 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5391 | A | 131242-WST02-DR-M-5391-A | 2025-03-27 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-04-24 | 2025-05-21 | Approved with Comments | 2025-06-10 | YES | Resubmitted |  | 131242-WST02-DR-5391 | NA | "Datasheet & GA drawing for sampling pump" && "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 55 | AWC | 2025-10-18 | B | 001172&&001632 | 2025-03-27, 2025-08-27, 2025-10-18 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7037 | 001172 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5391 | 1 | 131242-WST02-DS-M-5391-1 | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5391 | NA | "Datasheet & GA drawing for sampling pump" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-11-01 | 170 | PEN | 2025-10-18 | 1 | 001172 | 2025-03-27, 2025-10-18 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-04 |  | 0 | PEN | PEN
7038 | 001172 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5391 | B | 131242-WST02-DR-M-5391-B | 2025-10-18 | Datasheet & GA drawing for sampling pump | Approved with Comments | 2025-11-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5391 | NA | "Datasheet & GA drawing for sampling pump" && "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-11-01 | 170 | PEN | 2025-10-18 | B | 001172&&001632 | 2025-03-27, 2025-08-27, 2025-10-18 | 00, 01 | 3 | Approved with Comments | AWC | 2025-12-04 |  | 0 | PEN | PEN
7039 | 001173 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 0 | 131242-WSD11-DS-I-0011-0 | 2025-03-27 | Datasheet for Temperature Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-24 | 2025-07-14 | Not Approved | 2025-08-01 | YES | Resubmitted |  | 131242-WSD11-DS-0011 | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 109 | NAP | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
7040 | 001173 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1_Superceded | 131242-WSD11-DS-I-0011-1_Superceded | 2025-10-27 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2025-11-14 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DS-0011 | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 43 | NAP | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
7041 | 001173 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0011 | 1 | 131242-WSD11-DS-I-0011-1 | 2026-01-21 | Datasheet for Temperature Transmitter | Rev 01: Not Approved. To revise and resubmit. No SRC file | 2026-02-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0011 | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-04 | 75 | PEN | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-03-10 |  | 0 | PEN | PEN
7042 | 001174 | 00 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-E-0029-0 | 2025-03-27 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 0: Approved with comments. To revise and resubmit. | 2025-04-24 | 2025-06-17 | Approved with Comments | 2025-07-07 | YES | Resubmitted |  | 131242-WST02-QA-0029 | NA | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " && "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 82 | AWC | 2025-07-11 | 0 | 001174&&001465 | 2025-03-27, 2025-07-10, 2025-07-11 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7043 | 001174 | 01 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0029 | 0 | 131242-WST02-QA-E-0029-0 | 2025-07-10 | SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached filed for comments. | 2025-07-30 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-QA-0029 | NA | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " && "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 7 | AWC | 2025-07-11 | 0 | 001174&&001465 | 2025-03-27, 2025-07-10, 2025-07-11 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7044 | 001175 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0060 | 0 | 131242-WSW41-QA-M-0060-0 | 2025-03-27 | FAT Report for Compressor Pipe support in Bio solid building | NA | 2025-04-24 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSW41-QA-0060 | NA | " FAT Report for Compressor Pipe support in Bio solid building" && "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" && "Factory Acceptance Test Report for Pressure Switch" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-16 | 159 | AWC | 2026-01-13 | 1 | 001175&&001823&&001861 | 2025-03-27, 2025-11-05, 2025-11-24, 2026-01-13 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
7045 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | A | 131242-WST02-DR-IP-1025-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 40 | NAP | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | NAP | NAP
7046 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | A | 131242-WST02-DR-IP-1026-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 40 | NAP | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | NAP | NAP
7047 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | A | 131242-WST02-DR-IP-1027-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 40 | NAP | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7048 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | A | 131242-WST02-DR-IP-1028-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1028 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7049 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | A | 131242-WST02-DR-IP-1029-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1029 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7050 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | A | 131242-WST02-DR-IP-1030-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1030 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7051 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | A | 131242-WST02-DR-IP-1031-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1031 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7052 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | A | 131242-WST02-DR-IP-1032-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1032 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7053 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | A | 131242-WST02-DR-IP-1033-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1033 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7054 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | A | 131242-WST02-DR-IP-1034-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1034 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7055 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | A | 131242-WST02-DR-IP-1035-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1035 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7056 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | A | 131242-WST02-DR-IP-1036-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1036 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7057 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | A | 131242-WST02-DR-IP-1037-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1037 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7058 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | A | 131242-WST02-DR-IP-1038-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1038 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7059 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | A | 131242-WST02-DR-IP-1039-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1039 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7060 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | A | 131242-WST02-DR-IP-1040-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1040 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7061 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | A | 131242-WST02-DR-IP-1041-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1041 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7062 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | A | 131242-WST02-DR-IP-1042-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1042 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7063 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | A | 131242-WST02-DR-IP-1043-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1043 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7064 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | A | 131242-WST02-DR-IP-1044-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1044 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7065 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | A | 131242-WST02-DR-IP-1045-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1045 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7066 | 001176 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | A | 131242-WST02-DR-IP-1046-A | 2025-03-28 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-04-25 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1046 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 40 | NAP | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7067 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-IP-1025-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
7068 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | B | 131242-WST02-DR-IP-1026-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | AWC | AWC
7069 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | B | 131242-WST02-DR-IP-1027-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7070 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | B | 131242-WST02-DR-IP-1028-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1028 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7071 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | B | 131242-WST02-DR-IP-1029-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1029 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7072 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | B | 131242-WST02-DR-IP-1030-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1030 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7073 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | B | 131242-WST02-DR-IP-1031-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1031 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7074 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | B | 131242-WST02-DR-IP-1032-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1032 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7075 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | B | 131242-WST02-DR-IP-1033-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1033 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7076 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | B | 131242-WST02-DR-IP-1034-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1034 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7077 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | B | 131242-WST02-DR-IP-1035-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1035 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7078 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | B | 131242-WST02-DR-IP-1036-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1036 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7079 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | B | 131242-WST02-DR-IP-1037-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1037 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7080 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | B | 131242-WST02-DR-IP-1038-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1038 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7081 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | B | 131242-WST02-DR-IP-1039-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1039 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7082 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | B | 131242-WST02-DR-IP-1040-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1040 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7083 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | B | 131242-WST02-DR-IP-1041-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1041 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7084 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | B | 131242-WST02-DR-IP-1042-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1042 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7085 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | B | 131242-WST02-DR-IP-1043-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1043 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7086 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | B | 131242-WST02-DR-IP-1044-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1044 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7087 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | B | 131242-WST02-DR-IP-1045-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1045 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7088 | 001176 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | B | 131242-WST02-DR-IP-1046-B | 2025-07-11 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-1046 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 82 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7089 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1025 | B | 131242-WST02-DR-IP-1025-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
7090 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1026 | B | 131242-WST02-DR-IP-1026-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | AWC | AWC
7091 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1027 | B | 131242-WST02-DR-IP-1027-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7092 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1028 | B | 131242-WST02-DR-IP-1028-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1028 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7093 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1029 | B | 131242-WST02-DR-IP-1029-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1029 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7094 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1030 | B | 131242-WST02-DR-IP-1030-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1030 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7095 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1031 | B | 131242-WST02-DR-IP-1031-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1031 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7096 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1032 | B | 131242-WST02-DR-IP-1032-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1032 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7097 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1033 | B | 131242-WST02-DR-IP-1033-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1033 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7098 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1034 | B | 131242-WST02-DR-IP-1034-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1034 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7099 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1035 | B | 131242-WST02-DR-IP-1035-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1035 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7100 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1036 | B | 131242-WST02-DR-IP-1036-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1036 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7101 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1037 | B | 131242-WST02-DR-IP-1037-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1037 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7102 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1038 | B | 131242-WST02-DR-IP-1038-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1038 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7103 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1039 | B | 131242-WST02-DR-IP-1039-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1039 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7104 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1040 | B | 131242-WST02-DR-IP-1040-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1040 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7105 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1041 | B | 131242-WST02-DR-IP-1041-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1041 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7106 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1042 | B | 131242-WST02-DR-IP-1042-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1042 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7107 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1043 | B | 131242-WST02-DR-IP-1043-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1043 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7108 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1044 | B | 131242-WST02-DR-IP-1044-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1044 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7109 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1045 | B | 131242-WST02-DR-IP-1045-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1045 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7110 | 001176 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1046 | B | 131242-WST02-DR-IP-1046-B | 2025-11-17 | SSN Panel (ECCP-1001)- GA & Wiring Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WST02-DR-1046 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 29 | AWC | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7111 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | A | 131242-WST02-DR-IP-1901-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1901 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7112 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | A | 131242-WST02-DR-IP-1902-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1902 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7113 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | A | 131242-WST02-DR-IP-1903-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1903 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7114 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | A | 131242-WST02-DR-IP-1904-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1904 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7115 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | A | 131242-WST02-DR-IP-1905-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1905 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7116 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | A | 131242-WST02-DR-IP-1906-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1906 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7117 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | A | 131242-WST02-DR-IP-1907-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1907 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7118 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | A | 131242-WST02-DR-IP-1908-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1908 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7119 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | A | 131242-WST02-DR-IP-1909-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1909 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7120 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | A | 131242-WST02-DR-IP-1910-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1910 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7121 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | A | 131242-WST02-DR-IP-1911-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1911 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7122 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | A | 131242-WST02-DR-IP-1912-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1912 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7123 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | A | 131242-WST02-DR-IP-1913-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1913 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7124 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | A | 131242-WST02-DR-IP-1914-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1914 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7125 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | A | 131242-WST02-DR-IP-1915-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1915 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7126 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | A | 131242-WST02-DR-IP-1916-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1916 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7127 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | A | 131242-WST02-DR-IP-1917-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1917 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7128 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | A | 131242-WST02-DR-IP-1918-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1918 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7129 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | A | 131242-WST02-DR-IP-1919-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1919 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7130 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | A | 131242-WST02-DR-IP-1920-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1920 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7131 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | A | 131242-WST02-DR-IP-1921-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1921 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7132 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | A | 131242-WST02-DR-IP-1922-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1922 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7133 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | A | 131242-WST02-DR-IP-1923-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1923 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7134 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | A | 131242-WST02-DR-IP-1924-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1924 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7135 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | A | 131242-WST02-DR-IP-1925-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1925 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7136 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | A | 131242-WST02-DR-IP-1926-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1926 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7137 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | A | 131242-WST02-DR-IP-1927-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1927 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7138 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | A | 131242-WST02-DR-IP-1928-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1928 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7139 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | A | 131242-WST02-DR-IP-1929-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1929 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7140 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | A | 131242-WST02-DR-IP-1930-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1930 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7141 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | A | 131242-WST02-DR-IP-1931-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1931 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7142 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | A | 131242-WST02-DR-IP-1932-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1932 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7143 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | A | 131242-WST02-DR-IP-1933-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1933 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7144 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | A | 131242-WST02-DR-IP-1934-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1934 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7145 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | A | 131242-WST02-DR-IP-1935-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1935 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7146 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | A | 131242-WST02-DR-IP-1936-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1936 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7147 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | A | 131242-WST02-DR-IP-1937-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1937 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7148 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | A | 131242-WST02-DR-IP-1938-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1938 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7149 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | A | 131242-WST02-DR-IP-1939-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1939 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7150 | 001177 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | A | 131242-WST02-DR-IP-1940-A | 2025-03-28 | SSN Panel (FBTB-0101) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-04-25 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1940 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 49 | NAP | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7151 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1901 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7152 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1902 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7153 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1903 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7154 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1904 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7155 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1905 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7156 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1906 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7157 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1907 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7158 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1908 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7159 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1909 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7160 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1910 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7161 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1911 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7162 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1912 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7163 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1913 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7164 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1914 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7165 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1915 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7166 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1916 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7167 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | B | 131242-WST02-DR-IP-1917-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1917 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7168 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | B | 131242-WST02-DR-IP-1918-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1918 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7169 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | B | 131242-WST02-DR-IP-1919-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1919 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7170 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | B | 131242-WST02-DR-IP-1920-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1920 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7171 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | B | 131242-WST02-DR-IP-1921-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1921 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7172 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | B | 131242-WST02-DR-IP-1922-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1922 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7173 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | B | 131242-WST02-DR-IP-1923-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1923 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7174 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | B | 131242-WST02-DR-IP-1924-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1924 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7175 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | B | 131242-WST02-DR-IP-1925-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1925 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7176 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | B | 131242-WST02-DR-IP-1926-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1926 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7177 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | B | 131242-WST02-DR-IP-1927-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1927 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7178 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | B | 131242-WST02-DR-IP-1928-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1928 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7179 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | B | 131242-WST02-DR-IP-1929-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1929 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7180 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | B | 131242-WST02-DR-IP-1930-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1930 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7181 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | B | 131242-WST02-DR-IP-1931-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1931 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7182 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | B | 131242-WST02-DR-IP-1932-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1932 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7183 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | B | 131242-WST02-DR-IP-1933-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1933 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7184 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | B | 131242-WST02-DR-IP-1934-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1934 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7185 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | B | 131242-WST02-DR-IP-1935-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1935 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7186 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | B | 131242-WST02-DR-IP-1936-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1936 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7187 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | B | 131242-WST02-DR-IP-1937-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1937 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7188 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | B | 131242-WST02-DR-IP-1938-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1938 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7189 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | B | 131242-WST02-DR-IP-1939-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1939 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7190 | 001177 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | B | 131242-WST02-DR-IP-1940-B | 2025-07-10 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1940 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-24 | 75 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7191 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1901 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7192 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1902 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7193 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1903 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7194 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1904 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7195 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1905 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7196 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1906 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7197 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1907 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7198 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1908 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7199 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1909 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7200 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1910 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7201 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1911 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7202 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1912 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7203 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1913 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7204 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1914 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7205 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1915 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7206 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1916 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7207 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1917 | B | 131242-WST02-DR-IP-1917-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1917 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7208 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1918 | B | 131242-WST02-DR-IP-1918-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1918 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7209 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1919 | B | 131242-WST02-DR-IP-1919-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1919 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7210 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1920 | B | 131242-WST02-DR-IP-1920-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1920 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7211 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1921 | B | 131242-WST02-DR-IP-1921-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1921 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7212 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1922 | B | 131242-WST02-DR-IP-1922-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1922 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7213 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1923 | B | 131242-WST02-DR-IP-1923-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1923 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7214 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1924 | B | 131242-WST02-DR-IP-1924-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1924 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7215 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1925 | B | 131242-WST02-DR-IP-1925-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1925 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7216 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1926 | B | 131242-WST02-DR-IP-1926-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1926 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7217 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1927 | B | 131242-WST02-DR-IP-1927-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1927 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7218 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1928 | B | 131242-WST02-DR-IP-1928-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1928 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7219 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1929 | B | 131242-WST02-DR-IP-1929-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1929 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7220 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1930 | B | 131242-WST02-DR-IP-1930-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1930 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7221 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1931 | B | 131242-WST02-DR-IP-1931-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1931 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7222 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1932 | B | 131242-WST02-DR-IP-1932-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1932 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7223 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1933 | B | 131242-WST02-DR-IP-1933-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1933 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7224 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1934 | B | 131242-WST02-DR-IP-1934-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1934 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7225 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1935 | B | 131242-WST02-DR-IP-1935-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1935 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7226 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1936 | B | 131242-WST02-DR-IP-1936-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1936 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7227 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1937 | B | 131242-WST02-DR-IP-1937-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1937 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7228 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1938 | B | 131242-WST02-DR-IP-1938-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1938 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7229 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1939 | B | 131242-WST02-DR-IP-1939-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1939 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7230 | 001177 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1940 | B | 131242-WST02-DR-IP-1940-B | 2025-11-17 | SSN Panel RIO-204 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1940 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001177 | 2025-03-28, 2025-07-10, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7231 | 001178 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0061 | 0 | 131242-WSD11-QA-M-0061-0 | 2025-03-28 | Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI) | NA | 2025-04-25 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSD11-QA-0061 | NA | "Vendor Manufacturing Inspection and test plan and FAT procedure for Steam Sparger (CAMBI)" | 2025-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 164 | AWC | 2025-03-28 | 0 | 001178 | 2025-03-28 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
7232 | 001179 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0008 | 0 | 131242-WSD11-DS-I-0008-0 | 2025-04-01 | Datasheet for Pressure Transmitter | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DS-0008 | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-15 | 71 | NAP | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
7233 | 001179 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0008 | 1 | 131242-WSD11-DS-I-0008-1 | 2025-10-16 | Datasheet for Pressure Transmitter | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-05 | 2025-12-02 | Not Approved | 2025-12-22 | NO | Overdue |  | 131242-WSD11-DS-0008 | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-30 | 47 | NAP | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | Not Approved | NAP | 2025-12-22 | Overdue | 0 | NAP | NAP
7234 | 001180 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0009 | 0 | 131242-WSD11-DS-I-0009-0 | 2025-04-01 | Datasheet for Tuning Fork Level Switch | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DS-0009 | NA | "Datasheet for Tuning Fork Level Switch " && "THP Plant Safety Valve" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-15 | 71 | NAP | 2025-09-10 | 1 | 000223&&001180 | 2023-12-01, 2024-07-28, 2025-04-01, 2025-09-10 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7235 | 001180 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0009 | 1 | 131242-WSD11-DS-I-0009-1 | 2025-09-10 | Datasheet for Tuning Fork Level Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-09-30 | 2025-12-02 | Not Approved | 2025-12-22 | NO | Overdue |  | 131242-WSD11-DS-0009 | NA | "Datasheet for Tuning Fork Level Switch " && "THP Plant Safety Valve" | 2023-12-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 83 | NAP | 2025-09-10 | 1 | 000223&&001180 | 2023-12-01, 2024-07-28, 2025-04-01, 2025-09-10 | 00, 01 | 4 | Not Approved | NAP | 2025-12-22 | Overdue | 0 | NAP | NAP
7236 | 001181 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 0 | 131242-WSD11-DS-I-0010-0 | 2025-04-01 | Datasheet for Pressure Switch | Not Approved - Revise and resubmit | 2025-04-29 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DS-0010 | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-15 | 71 | NAP | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
7237 | 001181 | 01 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 1 | 131242-WSD11-DS-I-0010-1 | 2025-09-10 | Datasheet for Pressure Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-30 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WSD11-DS-0010 | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 83 | NAP | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
7238 | 001181 | 02 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0010 | 2 | 131242-WSD11-DS-I-0010-2 | 2026-01-30 | Datasheet for Pressure Switch | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0010 | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-13 | 66 | PEN | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-03-19 |  | 0 | PEN | PEN
7239 | 001182 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1017 | 0 | 131242-WSW41-VI-M-1017-0 | 2025-04-01 | Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-29 | 2025-06-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1017 | NA | "Preliminary design and Vendor Approval for Flange Adaptor (SynChong Hoe)" | 2025-04-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 83 | AWC | 2025-04-01 | 0 | 001182 | 2025-04-01 | 00 | 1 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
7240 | 001183 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1007 | 0 | 131242-WSW41-SH-M-1007-0 | 2025-04-01 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | Rev 0: Not approved - Revise and Resubmit | 2025-04-29 | 2025-06-23 | Not Approved | 2025-07-11 | YES | Resubmitted |  | 131242-WSW41-SH-1007 | NA | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 83 | NAP | 2025-07-22 | 1 | 001183 | 2025-04-01, 2025-07-22 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
7241 | 001183 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1007 | 1 | 131242-WSW41-SH-M-1007-1 | 2025-07-22 | Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen) | Approved | 2025-08-11 | 2025-08-01 | Approved |  | YES | NA |  | 131242-WSW41-SH-1007 | NA | "Piping Valve GA & Datasheet – Metallic Non-Return Check Valve (Breen)" | 2025-04-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 10 | APP | 2025-07-22 | 1 | 001183 | 2025-04-01, 2025-07-22 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
7242 | 001184 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0061 | 0 | 131242-WSW41-QA-M-0061-0 | 2025-04-02 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch) | Approved | 2025-04-30 | 2025-05-21 | Approved |  | YES | NA |  | 131242-WSW41-QA-0061 | NA | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-22 | 49 | APP | 2025-12-02 | 0 | 001184&&001877 | 2025-04-02, 2025-12-02 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
7243 | 001185 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0062 | 0 | 131242-WSW41-QA-M-0062-0 | 2025-04-02 | FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch) | NA | 2025-04-30 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSW41-QA-0062 | NA | "FAT Report for SS Pipes in sitewide pipe rack (Cyclect - 3rd batch)" | 2025-04-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 153 | AWC | 2025-04-02 | 0 | 001185 | 2025-04-02 | 00 | 1 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
7244 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A1 | 131242-WST02-DR-A-1000_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7245 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A1 | 131242-WST02-DR-A-1001_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7246 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A1 | 131242-WST02-DR-A-1002_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.4 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7247 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A1 | 131242-WST02-DR-A-1003_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7248 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A1 | 131242-WST02-DR-A-1004_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1004_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7249 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A1 | 131242-WST02-DR-A-1006_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1006_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7250 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A1 | 131242-WST02-DR-A-1009_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1009_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7251 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A1 | 131242-WST02-DR-A-2000_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7252 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A1 | 131242-WST02-DR-A-2001_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7253 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A1 | 131242-WST02-DR-A-2002_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7254 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A1 | 131242-WST02-DR-A-2003_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7255 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A | 131242-WST02-DR-A-2007_BCA_BP-A | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2007_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.1 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7256 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A | 131242-WST02-DR-A-3000_BCA_BP-A | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-3000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7257 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9000_BCA_BP | A1 | 131242-WST02-DR-A-9000_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-9000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2025-04-02 | A1 | 001186 | 2025-04-02 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
7258 | 001186 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9001_BCA_BP | A1 | 131242-WST02-DR-A-9001_BCA_BP-A1 | 2025-04-02 | SSN BCA BP Submission | Not Approved - Revise and resubmit | 2025-04-30 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-9001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 70 | NAP | 2025-04-02 | A1 | 001186 | 2025-04-02 | 00 | 1 | Not Approved | NAP | 2025-07-01 | Overdue | 0 | NAP | NAP
7259 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7260 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7261 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP-A.4 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.4 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7262 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7263 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1004_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7264 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP-A | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1005_BCA_BP | NA | "SSN BCA BP Submission" | 2025-11-18 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-08 | 29 | NAP | 2026-01-20 | A | 001186 | 2025-11-18, 2025-12-23, 2026-01-20 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
7265 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP-A | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1006_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7266 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1009_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7267 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7268 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7269 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7270 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7271 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP-A.1 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2007_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.1 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7272 | 001186 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP-A.2 | 2025-11-18 | SSN BCA BP Submission | R1: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Not Approved | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-3000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7273 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7274 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7275 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP-A.4 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.4 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7276 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7277 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1004_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7278 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP-A | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1005_BCA_BP | NA | "SSN BCA BP Submission" | 2025-11-18 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A | 001186 | 2025-11-18, 2025-12-23, 2026-01-20 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
7279 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP-A | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1006_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7280 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1009_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7281 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7282 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7283 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7284 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7285 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP-A.1 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2007_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.1 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7286 | 001186 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP-A.2 | 2025-12-23 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-01-12 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-3000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-06 | 20 | NAP | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
7287 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_BCA_BP | A.2 | 131242-WST02-DR-A-1000_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7288 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_BCA_BP | A.2 | 131242-WST02-DR-A-1001_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7289 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_BCA_BP | A.4 | 131242-WST02-DR-A-1002_BCA_BP-A.4 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.4 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7290 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_BCA_BP | A.2 | 131242-WST02-DR-A-1003_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7291 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_BCA_BP | A.2 | 131242-WST02-DR-A-1004_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7292 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_BCA_BP | A | 131242-WST02-DR-A-1005_BCA_BP-A | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005_BCA_BP | NA | "SSN BCA BP Submission" | 2025-11-18 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A | 001186 | 2025-11-18, 2025-12-23, 2026-01-20 | 01, 02, 03 | 3 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7293 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_BCA_BP | A | 131242-WST02-DR-A-1006_BCA_BP-A | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7294 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_BCA_BP | A.2 | 131242-WST02-DR-A-1009_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7295 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_BCA_BP | A.2 | 131242-WST02-DR-A-2000_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7296 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_BCA_BP | A.2 | 131242-WST02-DR-A-2001_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2001_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7297 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_BCA_BP | A.2 | 131242-WST02-DR-A-2002_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2002_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7298 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_BCA_BP | A.2 | 131242-WST02-DR-A-2003_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2003_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7299 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_BCA_BP | A.1 | 131242-WST02-DR-A-2007_BCA_BP-A.1 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2007_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.1 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7300 | 001186 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_BCA_BP | A.2 | 131242-WST02-DR-A-3000_BCA_BP-A.2 | 2026-01-20 | SSN BCA BP Submission | Rev 2: Not Approved. Revise and resubmit. C4B to update drawings based on the latest comments for FSSD plan Rev.7. | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3000_BCA_BP | NA | "SSN BCA BP Submission" | 2025-04-02 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | A.2 | 001186 | 2025-04-02, 2025-11-18, 2025-12-23, 2026-01-20 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
7301 | 001187 | 00 | K Balaji | CSA | NA | 131242 | WSD11 | VI | S | 0001 | 0 | 131242-WSD11-VI-S-0001-0 | 2025-04-03 | Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-01 | 2025-04-15 | Approved with Comments | 2025-05-05 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 12 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7302 | 001187 | 01 | K Balaji | CSA | NA | 131242 | WSD11 | VI | S | 0001 | 1 | 131242-WSD11-VI-S-0001-1 | 2025-04-18 | Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd) | Approved with Comments | 2025-05-08 | 2025-05-16 | Approved with Comments | 2025-06-05 | NO | Overdue |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-02 | 28 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC | 2025-06-05 | Overdue | 0 | AWC | AWC
7303 | 001188 | 00 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0001 | 0 | 131242-WST02-MM-E-0001-0 | 2025-04-03 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | Rev 0: Rejected. To revise and resubmit. | 2025-05-01 | 2025-05-30 | Rejected | 2025-06-19 | YES | Resubmitted |  | 131242-WST02-MM-0001 | NA | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " && "SSN Reactor Floor flat Design Memo" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 57 | REJ | 2025-07-22 | 1 | 000621&&001188 | 2024-08-05, 2025-04-03, 2025-07-22 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
7304 | 001188 | 01 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0001 | 1 | 131242-WST02-MM-E-0001-1 | 2025-07-22 | Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer | Rev 1: Not Approved. To revise and resubmit. Refer to the comment sheet, after incorporating comments, please submit hardcopy to S.O. prior to resubmission. | 2025-08-11 | 2025-10-01 | Not Approved | 2025-10-21 | NO | Overdue |  | 131242-WST02-MM-0001 | NA | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " && "SSN Reactor Floor flat Design Memo" | 2024-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 71 | NAP | 2025-07-22 | 1 | 000621&&001188 | 2024-08-05, 2025-04-03, 2025-07-22 | 00, 01 | 3 | Not Approved | NAP | 2025-10-21 | Overdue | 0 | NAP | NAP
7305 | 001189 | 00 | Freedomer | EICA | NA | 131242 | WST02 | MM | E | 0002 | 0 | 131242-WST02-MM-E-0002-0 | 2025-04-03 | Memo-Installation Letter of TMS for Sivacon S8 | Rev 0: Accepted for Information | 2025-05-01 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WST02-MM-0002 | NA | "Memo-Installation Letter of TMS for Sivacon S8" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-23 | 32 | INF | 2025-04-03 | 0 | 001189 | 2025-04-03 | 00 | 1 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7306 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7201 | A | 131242-WST02-DR-I-7201-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DR-7201 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | AWC | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7307 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7202 | A | 131242-WST02-DR-I-7202-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7202 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7308 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7203 | A | 131242-WST02-DR-I-7203-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7203 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7309 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7204 | A | 131242-WST02-DR-I-7204-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7204 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7310 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7205 | A | 131242-WST02-DR-I-7205-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7205 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7311 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7206 | A | 131242-WST02-DR-I-7206-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7206 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7312 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7207 | A | 131242-WST02-DR-I-7207-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7207 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7313 | 001190 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7208 | A | 131242-WST02-DR-I-7208-A | 2025-04-03 | SSN UPSDB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-01 | 2025-04-27 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7208 | NA | "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 24 | PEN | 2025-07-21 | B | 001157&&001190 | 2025-03-25, 2025-04-03, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
7314 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | A | 131242-WST02-DR-IP-1941-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1941 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7315 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | A | 131242-WST02-DR-IP-1942-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1942 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7316 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | A | 131242-WST02-DR-IP-1943-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1943 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7317 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | A | 131242-WST02-DR-IP-1944-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1944 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7318 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | A | 131242-WST02-DR-IP-1945-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1945 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7319 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | A | 131242-WST02-DR-IP-1946-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1946 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7320 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | A | 131242-WST02-DR-IP-1947-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1947 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7321 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | A | 131242-WST02-DR-IP-1948-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1948 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7322 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | A | 131242-WST02-DR-IP-1949-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1949 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7323 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | A | 131242-WST02-DR-IP-1950-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1950 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7324 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | A | 131242-WST02-DR-IP-1951-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1951 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7325 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | A | 131242-WST02-DR-IP-1952-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1952 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7326 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | A | 131242-WST02-DR-IP-1953-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1953 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7327 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | A | 131242-WST02-DR-IP-1954-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1954 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7328 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | A | 131242-WST02-DR-IP-1955-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1955 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7329 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | A | 131242-WST02-DR-IP-1956-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1956 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7330 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | A | 131242-WST02-DR-IP-1957-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1957 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7331 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | A | 131242-WST02-DR-IP-1958-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1958 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7332 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | A | 131242-WST02-DR-IP-1959-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1959 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7333 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | A | 131242-WST02-DR-IP-1960-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1960 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7334 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | A | 131242-WST02-DR-IP-1961-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1961 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7335 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | A | 131242-WST02-DR-IP-1962-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1962 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7336 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | A | 131242-WST02-DR-IP-1963-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1963 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7337 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | A | 131242-WST02-DR-IP-1964-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1964 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7338 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | A | 131242-WST02-DR-IP-1965-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1965 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7339 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | A | 131242-WST02-DR-IP-1966-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1966 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7340 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | A | 131242-WST02-DR-IP-1967-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1967 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7341 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | A | 131242-WST02-DR-IP-1968-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1968 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7342 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | A | 131242-WST02-DR-IP-1969-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1969 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7343 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | A | 131242-WST02-DR-IP-1970-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1970 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7344 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | A | 131242-WST02-DR-IP-1971-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1971 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7345 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | A | 131242-WST02-DR-IP-1972-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1972 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7346 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | A | 131242-WST02-DR-IP-1973-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1973 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7347 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | A | 131242-WST02-DR-IP-1974-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1974 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7348 | 001191 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | A | 131242-WST02-DR-IP-1975-A | 2025-04-03 | SSN Panel (FBTB-0201) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1975 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7349 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | B | 131242-WST02-DR-IP-1941-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1941 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7350 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | B | 131242-WST02-DR-IP-1942-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1942 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7351 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | B | 131242-WST02-DR-IP-1943-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1943 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7352 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | B | 131242-WST02-DR-IP-1944-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1944 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7353 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | B | 131242-WST02-DR-IP-1945-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1945 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7354 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | B | 131242-WST02-DR-IP-1946-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1946 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7355 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | B | 131242-WST02-DR-IP-1947-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1947 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7356 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | B | 131242-WST02-DR-IP-1948-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1948 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7357 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | B | 131242-WST02-DR-IP-1949-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1949 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7358 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | B | 131242-WST02-DR-IP-1950-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1950 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7359 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | B | 131242-WST02-DR-IP-1951-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1951 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7360 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | B | 131242-WST02-DR-IP-1952-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1952 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7361 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | B | 131242-WST02-DR-IP-1953-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1953 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7362 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | B | 131242-WST02-DR-IP-1954-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1954 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7363 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | B | 131242-WST02-DR-IP-1955-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1955 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7364 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | B | 131242-WST02-DR-IP-1956-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1956 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7365 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | B | 131242-WST02-DR-IP-1957-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1957 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7366 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | B | 131242-WST02-DR-IP-1958-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1958 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7367 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | B | 131242-WST02-DR-IP-1959-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1959 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7368 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | B | 131242-WST02-DR-IP-1960-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1960 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7369 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | B | 131242-WST02-DR-IP-1961-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1961 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7370 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | B | 131242-WST02-DR-IP-1962-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1962 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7371 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | B | 131242-WST02-DR-IP-1963-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1963 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7372 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | B | 131242-WST02-DR-IP-1964-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1964 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7373 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | B | 131242-WST02-DR-IP-1965-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1965 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7374 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | B | 131242-WST02-DR-IP-1966-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1966 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7375 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | B | 131242-WST02-DR-IP-1967-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1967 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7376 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | B | 131242-WST02-DR-IP-1968-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1968 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7377 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | B | 131242-WST02-DR-IP-1969-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1969 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7378 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | B | 131242-WST02-DR-IP-1970-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1970 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7379 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | B | 131242-WST02-DR-IP-1971-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1971 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7380 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | B | 131242-WST02-DR-IP-1972-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1972 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7381 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | B | 131242-WST02-DR-IP-1973-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1973 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7382 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | B | 131242-WST02-DR-IP-1974-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1974 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7383 | 001191 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | B | 131242-WST02-DR-IP-1975-B | 2025-07-11 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-1975 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7384 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1941 | B | 131242-WST02-DR-IP-1941-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1941 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7385 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1942 | B | 131242-WST02-DR-IP-1942-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1942 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7386 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1943 | B | 131242-WST02-DR-IP-1943-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1943 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7387 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1944 | B | 131242-WST02-DR-IP-1944-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1944 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7388 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1945 | B | 131242-WST02-DR-IP-1945-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1945 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7389 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1946 | B | 131242-WST02-DR-IP-1946-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1946 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7390 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1947 | B | 131242-WST02-DR-IP-1947-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1947 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7391 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1948 | B | 131242-WST02-DR-IP-1948-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1948 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7392 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1949 | B | 131242-WST02-DR-IP-1949-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1949 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7393 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1950 | B | 131242-WST02-DR-IP-1950-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1950 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7394 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1951 | B | 131242-WST02-DR-IP-1951-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1951 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7395 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1952 | B | 131242-WST02-DR-IP-1952-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1952 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7396 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1953 | B | 131242-WST02-DR-IP-1953-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1953 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7397 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1954 | B | 131242-WST02-DR-IP-1954-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1954 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7398 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1955 | B | 131242-WST02-DR-IP-1955-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1955 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7399 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1956 | B | 131242-WST02-DR-IP-1956-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1956 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7400 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1957 | B | 131242-WST02-DR-IP-1957-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1957 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7401 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1958 | B | 131242-WST02-DR-IP-1958-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1958 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7402 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1959 | B | 131242-WST02-DR-IP-1959-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1959 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7403 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1960 | B | 131242-WST02-DR-IP-1960-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1960 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7404 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1961 | B | 131242-WST02-DR-IP-1961-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1961 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7405 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1962 | B | 131242-WST02-DR-IP-1962-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1962 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7406 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1963 | B | 131242-WST02-DR-IP-1963-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1963 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7407 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1964 | B | 131242-WST02-DR-IP-1964-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1964 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7408 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1965 | B | 131242-WST02-DR-IP-1965-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1965 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7409 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1966 | B | 131242-WST02-DR-IP-1966-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1966 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7410 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1967 | B | 131242-WST02-DR-IP-1967-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1967 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7411 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1968 | B | 131242-WST02-DR-IP-1968-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1968 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7412 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1969 | B | 131242-WST02-DR-IP-1969-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1969 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7413 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1970 | B | 131242-WST02-DR-IP-1970-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1970 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7414 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1971 | B | 131242-WST02-DR-IP-1971-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1971 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7415 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1972 | B | 131242-WST02-DR-IP-1972-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1972 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7416 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1973 | B | 131242-WST02-DR-IP-1973-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1973 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7417 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1974 | B | 131242-WST02-DR-IP-1974-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1974 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7418 | 001191 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1975 | B | 131242-WST02-DR-IP-1975-B | 2025-11-17 | SSN Panel RIO-205 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1975 | NA | " SSN Panel RIO-205 - GA & Schematic Drawings" && "SSN Panel (FBTB-0201) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 71 | AWC | 2025-11-17 | B | 001191 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
7419 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | A | 131242-WST02-DR-IP-2021-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2021 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7420 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | A | 131242-WST02-DR-IP-2022-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2022 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7421 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | A | 131242-WST02-DR-IP-2023-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2023 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7422 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | A | 131242-WST02-DR-IP-2024-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2024 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7423 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | A | 131242-WST02-DR-IP-2025-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2025 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7424 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | A | 131242-WST02-DR-IP-2026-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2026 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7425 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | A | 131242-WST02-DR-IP-2027-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2027 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7426 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | A | 131242-WST02-DR-IP-2028-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2028 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7427 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | A | 131242-WST02-DR-IP-2029-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2029 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7428 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | A | 131242-WST02-DR-IP-2030-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2030 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7429 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | A | 131242-WST02-DR-IP-2031-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2031 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7430 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | A | 131242-WST02-DR-IP-2032-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2032 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7431 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | A | 131242-WST02-DR-IP-2033-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2033 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7432 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | A | 131242-WST02-DR-IP-2034-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2034 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7433 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | A | 131242-WST02-DR-IP-2035-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2035 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7434 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | A | 131242-WST02-DR-IP-2036-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2036 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7435 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | A | 131242-WST02-DR-IP-2037-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2037 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7436 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | A | 131242-WST02-DR-IP-2038-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2038 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7437 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | A | 131242-WST02-DR-IP-2039-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2039 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7438 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | A | 131242-WST02-DR-IP-2040-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2040 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7439 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | A | 131242-WST02-DR-IP-2041-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2041 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7440 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | A | 131242-WST02-DR-IP-2042-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2042 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7441 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | A | 131242-WST02-DR-IP-2043-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2043 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7442 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | A | 131242-WST02-DR-IP-2044-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2044 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7443 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | A | 131242-WST02-DR-IP-2045-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2045 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7444 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | A | 131242-WST02-DR-IP-2046-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2046 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7445 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | A | 131242-WST02-DR-IP-2047-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2047 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7446 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | A | 131242-WST02-DR-IP-2048-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2048 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7447 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | A | 131242-WST02-DR-IP-2049-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2049 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7448 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | A | 131242-WST02-DR-IP-2050-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2050 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7449 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | A | 131242-WST02-DR-IP-2051-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2051 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7450 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | A | 131242-WST02-DR-IP-2052-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2052 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7451 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | A | 131242-WST02-DR-IP-2053-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2053 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7452 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | A | 131242-WST02-DR-IP-2054-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2054 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7453 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | A | 131242-WST02-DR-IP-2055-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2055 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7454 | 001192 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | A | 131242-WST02-DR-IP-2056-A | 2025-04-03 | SSN Panel (FBTB-0301) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2056 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7455 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | B | 131242-WST02-DR-IP-2021-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2021 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7456 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | B | 131242-WST02-DR-IP-2022-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2022 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7457 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | B | 131242-WST02-DR-IP-2023-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2023 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7458 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | B | 131242-WST02-DR-IP-2024-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2024 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7459 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | B | 131242-WST02-DR-IP-2025-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2025 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7460 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | B | 131242-WST02-DR-IP-2026-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2026 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7461 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | B | 131242-WST02-DR-IP-2027-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2027 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7462 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | B | 131242-WST02-DR-IP-2028-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2028 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7463 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | B | 131242-WST02-DR-IP-2029-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2029 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7464 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | B | 131242-WST02-DR-IP-2030-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2030 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7465 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | B | 131242-WST02-DR-IP-2031-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2031 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7466 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | B | 131242-WST02-DR-IP-2032-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2032 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7467 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | B | 131242-WST02-DR-IP-2033-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2033 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7468 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | B | 131242-WST02-DR-IP-2034-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2034 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7469 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | B | 131242-WST02-DR-IP-2035-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2035 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7470 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | B | 131242-WST02-DR-IP-2036-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2036 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7471 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | B | 131242-WST02-DR-IP-2037-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2037 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7472 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | B | 131242-WST02-DR-IP-2038-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2038 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7473 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | B | 131242-WST02-DR-IP-2039-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2039 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7474 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | B | 131242-WST02-DR-IP-2040-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2040 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7475 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | B | 131242-WST02-DR-IP-2041-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2041 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7476 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | B | 131242-WST02-DR-IP-2042-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2042 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7477 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | B | 131242-WST02-DR-IP-2043-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2043 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7478 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | B | 131242-WST02-DR-IP-2044-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2044 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7479 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | B | 131242-WST02-DR-IP-2045-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2045 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7480 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | B | 131242-WST02-DR-IP-2046-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2046 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7481 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | B | 131242-WST02-DR-IP-2047-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2047 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7482 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | B | 131242-WST02-DR-IP-2048-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2048 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7483 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | B | 131242-WST02-DR-IP-2049-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2049 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7484 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | B | 131242-WST02-DR-IP-2050-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2050 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7485 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | B | 131242-WST02-DR-IP-2051-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2051 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7486 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | B | 131242-WST02-DR-IP-2052-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2052 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7487 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | B | 131242-WST02-DR-IP-2053-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2053 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7488 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | B | 131242-WST02-DR-IP-2054-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2054 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7489 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | B | 131242-WST02-DR-IP-2055-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2055 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7490 | 001192 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | B | 131242-WST02-DR-IP-2056-B | 2025-08-07 | SSN RIO-206 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-04 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WST02-DR-2056 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 84 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7491 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2021 | B | 131242-WST02-DR-IP-2021-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2021 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7492 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2022 | B | 131242-WST02-DR-IP-2022-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2022 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7493 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2023 | B | 131242-WST02-DR-IP-2023-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2023 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7494 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2024 | B | 131242-WST02-DR-IP-2024-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2024 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7495 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2025 | B | 131242-WST02-DR-IP-2025-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2025 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7496 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2026 | B | 131242-WST02-DR-IP-2026-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2026 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7497 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2027 | B | 131242-WST02-DR-IP-2027-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2027 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7498 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2028 | B | 131242-WST02-DR-IP-2028-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2028 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7499 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2029 | B | 131242-WST02-DR-IP-2029-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2029 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7500 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2030 | B | 131242-WST02-DR-IP-2030-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2030 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7501 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2031 | B | 131242-WST02-DR-IP-2031-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2031 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7502 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2032 | B | 131242-WST02-DR-IP-2032-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2032 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7503 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2033 | B | 131242-WST02-DR-IP-2033-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2033 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7504 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2034 | B | 131242-WST02-DR-IP-2034-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2034 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7505 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2035 | B | 131242-WST02-DR-IP-2035-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2035 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7506 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2036 | B | 131242-WST02-DR-IP-2036-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2036 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7507 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2037 | B | 131242-WST02-DR-IP-2037-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2037 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7508 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2038 | B | 131242-WST02-DR-IP-2038-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2038 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7509 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2039 | B | 131242-WST02-DR-IP-2039-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2039 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7510 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2040 | B | 131242-WST02-DR-IP-2040-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2040 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7511 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2041 | B | 131242-WST02-DR-IP-2041-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2041 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7512 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2042 | B | 131242-WST02-DR-IP-2042-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2042 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7513 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2043 | B | 131242-WST02-DR-IP-2043-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2043 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7514 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2044 | B | 131242-WST02-DR-IP-2044-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2044 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7515 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2045 | B | 131242-WST02-DR-IP-2045-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2045 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7516 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2046 | B | 131242-WST02-DR-IP-2046-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2046 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7517 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2047 | B | 131242-WST02-DR-IP-2047-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2047 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7518 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2048 | B | 131242-WST02-DR-IP-2048-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2048 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7519 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2049 | B | 131242-WST02-DR-IP-2049-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2049 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7520 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2050 | B | 131242-WST02-DR-IP-2050-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2050 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7521 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2051 | B | 131242-WST02-DR-IP-2051-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2051 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7522 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2052 | B | 131242-WST02-DR-IP-2052-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2052 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7523 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2053 | B | 131242-WST02-DR-IP-2053-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2053 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7524 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2054 | B | 131242-WST02-DR-IP-2054-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2054 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7525 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2055 | B | 131242-WST02-DR-IP-2055-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2055 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7526 | 001192 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2056 | B | 131242-WST02-DR-IP-2056-B | 2025-11-17 | SSN RIO-206 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2056 | NA | "SSN Panel (FBTB-0301) - GA & Schematic Drawings" && "SSN RIO-206 - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001192 | 2025-04-03, 2025-08-07, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7527 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | A | 131242-WST02-DR-IP-2061-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2061 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7528 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | A | 131242-WST02-DR-IP-2062-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2062 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7529 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | A | 131242-WST02-DR-IP-2063-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2063 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7530 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | A | 131242-WST02-DR-IP-2064-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2064 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7531 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | A | 131242-WST02-DR-IP-2065-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2065 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7532 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | A | 131242-WST02-DR-IP-2066-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2066 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7533 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | A | 131242-WST02-DR-IP-2067-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2067 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7534 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | A | 131242-WST02-DR-IP-2068-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2068 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7535 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | A | 131242-WST02-DR-IP-2069-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2069 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7536 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | A | 131242-WST02-DR-IP-2070-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2070 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7537 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | A | 131242-WST02-DR-IP-2071-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2071 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7538 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | A | 131242-WST02-DR-IP-2072-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2072 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7539 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | A | 131242-WST02-DR-IP-2073-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2073 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7540 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | A | 131242-WST02-DR-IP-2074-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2074 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7541 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | A | 131242-WST02-DR-IP-2075-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2075 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7542 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | A | 131242-WST02-DR-IP-2076-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2076 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7543 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | A | 131242-WST02-DR-IP-2077-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2077 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7544 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | A | 131242-WST02-DR-IP-2078-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2078 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7545 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | A | 131242-WST02-DR-IP-2079-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2079 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7546 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | A | 131242-WST02-DR-IP-2080-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2080 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7547 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | A | 131242-WST02-DR-IP-2081-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2081 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7548 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | A | 131242-WST02-DR-IP-2082-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2082 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7549 | 001193 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | A | 131242-WST02-DR-IP-2083-A | 2025-04-03 | SSN Panel (FBTB-0401) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | NO | Overdue |  | 131242-WST02-DR-2083 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7550 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | B | 131242-WST02-DR-IP-2061-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-28 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2061 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7551 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | B | 131242-WST02-DR-IP-2062-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2062 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7552 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | B | 131242-WST02-DR-IP-2063-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2063 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7553 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | B | 131242-WST02-DR-IP-2064-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2064 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7554 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | B | 131242-WST02-DR-IP-2065-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2065 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7555 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | B | 131242-WST02-DR-IP-2066-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2066 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7556 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | B | 131242-WST02-DR-IP-2067-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2067 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7557 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | B | 131242-WST02-DR-IP-2068-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2068 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7558 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | B | 131242-WST02-DR-IP-2069-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2069 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7559 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | B | 131242-WST02-DR-IP-2070-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2070 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7560 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | B | 131242-WST02-DR-IP-2071-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2071 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7561 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | B | 131242-WST02-DR-IP-2072-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2072 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7562 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | B | 131242-WST02-DR-IP-2073-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2073 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7563 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | B | 131242-WST02-DR-IP-2074-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2074 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7564 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | B | 131242-WST02-DR-IP-2075-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2075 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7565 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | B | 131242-WST02-DR-IP-2076-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2076 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7566 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | B | 131242-WST02-DR-IP-2077-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2077 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7567 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | B | 131242-WST02-DR-IP-2078-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2078 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7568 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | B | 131242-WST02-DR-IP-2079-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2079 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7569 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | B | 131242-WST02-DR-IP-2080-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2080 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7570 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | B | 131242-WST02-DR-IP-2081-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2081 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7571 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | B | 131242-WST02-DR-IP-2082-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2082 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7572 | 001193 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | B | 131242-WST02-DR-IP-2083-B | 2025-07-08 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-DR-2083 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 77 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7573 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2061 | B | 131242-WST02-DR-IP-2061-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2061 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7574 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2062 | B | 131242-WST02-DR-IP-2062-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2062 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7575 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2063 | B | 131242-WST02-DR-IP-2063-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2063 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7576 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2064 | B | 131242-WST02-DR-IP-2064-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2064 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7577 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2065 | B | 131242-WST02-DR-IP-2065-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2065 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7578 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2066 | B | 131242-WST02-DR-IP-2066-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2066 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7579 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2067 | B | 131242-WST02-DR-IP-2067-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2067 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7580 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2068 | B | 131242-WST02-DR-IP-2068-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2068 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7581 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2069 | B | 131242-WST02-DR-IP-2069-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2069 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7582 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2070 | B | 131242-WST02-DR-IP-2070-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2070 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7583 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2071 | B | 131242-WST02-DR-IP-2071-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2071 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7584 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2072 | B | 131242-WST02-DR-IP-2072-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2072 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7585 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2073 | B | 131242-WST02-DR-IP-2073-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2073 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7586 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2074 | B | 131242-WST02-DR-IP-2074-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2074 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7587 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2075 | B | 131242-WST02-DR-IP-2075-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2075 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7588 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2076 | B | 131242-WST02-DR-IP-2076-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2076 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7589 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2077 | B | 131242-WST02-DR-IP-2077-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2077 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7590 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2078 | B | 131242-WST02-DR-IP-2078-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2078 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7591 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2079 | B | 131242-WST02-DR-IP-2079-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2079 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7592 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2080 | B | 131242-WST02-DR-IP-2080-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2080 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7593 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2081 | B | 131242-WST02-DR-IP-2081-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2081 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7594 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2082 | B | 131242-WST02-DR-IP-2082-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2082 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7595 | 001193 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2083 | B | 131242-WST02-DR-IP-2083-B | 2025-11-17 | SSN Panel (RIO-207) - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2083 | NA | "SSN Panel (FBTB-0401) - GA & Schematic Drawings" && "SSN Panel (RIO-207) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001193 | 2025-04-03, 2025-07-08, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7596 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | A | 131242-WST02-DR-IP-1981-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1981 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7597 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | A | 131242-WST02-DR-IP-1982-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1982 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7598 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | A | 131242-WST02-DR-IP-1983-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1983 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7599 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | A | 131242-WST02-DR-IP-1984-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1984 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7600 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | A | 131242-WST02-DR-IP-1985-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1985 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7601 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | A | 131242-WST02-DR-IP-1986-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1986 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7602 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | A | 131242-WST02-DR-IP-1987-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1987 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7603 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | A | 131242-WST02-DR-IP-1988-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1988 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7604 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | A | 131242-WST02-DR-IP-1989-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1989 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7605 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | A | 131242-WST02-DR-IP-1990-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1990 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7606 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | A | 131242-WST02-DR-IP-1991-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1991 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7607 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | A | 131242-WST02-DR-IP-1992-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1992 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7608 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | A | 131242-WST02-DR-IP-1993-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1993 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7609 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | A | 131242-WST02-DR-IP-1994-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1994 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7610 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | A | 131242-WST02-DR-IP-1995-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1995 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7611 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | A | 131242-WST02-DR-IP-1996-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1996 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7612 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | A | 131242-WST02-DR-IP-1997-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1997 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7613 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | A | 131242-WST02-DR-IP-1998-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1998 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7614 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | A | 131242-WST02-DR-IP-1999-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-1999 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7615 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | A | 131242-WST02-DR-IP-2000-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 43 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | NAP | NAP
7616 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | A | 131242-WST02-DR-IP-2001-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 43 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
7617 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | A | 131242-WST02-DR-IP-2002-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 43 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
7618 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | A | 131242-WST02-DR-IP-2003-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 43 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
7619 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | A | 131242-WST02-DR-IP-2004-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2004 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7620 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | A | 131242-WST02-DR-IP-2005-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2005 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7621 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | A | 131242-WST02-DR-IP-2006-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2006 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7622 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | A | 131242-WST02-DR-IP-2007-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2007 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 43 | NAP | 2026-02-03 | A.2 | 000812&&001194&&001924 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
7623 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | A | 131242-WST02-DR-IP-2008-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2008 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "Shop Drawing for Louvre Door and Window" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194&&001604 | 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7624 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | A | 131242-WST02-DR-IP-2009-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2009 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7625 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | A | 131242-WST02-DR-IP-2010-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2010 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7626 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | A | 131242-WST02-DR-IP-2011-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2011 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7627 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | A | 131242-WST02-DR-IP-2012-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2012 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7628 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | A | 131242-WST02-DR-IP-2013-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2013 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7629 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | A | 131242-WST02-DR-IP-2014-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2014 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7630 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | A | 131242-WST02-DR-IP-2015-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2015 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7631 | 001194 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | A | 131242-WST02-DR-IP-2016-A | 2025-04-03 | SSN Panel (FBTB-0501) - GA & Schematic Drawings | Not Approved - Revise and resubmit | 2025-05-01 | 2025-05-16 | Not Approved | 2025-06-05 | YES | Resubmitted |  | 131242-WST02-DR-2016 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 43 | NAP | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7632 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | B | 131242-WST02-DR-IP-1981-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-31 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1981 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7633 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | B | 131242-WST02-DR-IP-1982-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1982 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7634 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | B | 131242-WST02-DR-IP-1983-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1983 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7635 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | B | 131242-WST02-DR-IP-1984-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1984 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7636 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | B | 131242-WST02-DR-IP-1985-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1985 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7637 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | B | 131242-WST02-DR-IP-1986-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1986 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7638 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | B | 131242-WST02-DR-IP-1987-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1987 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7639 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | B | 131242-WST02-DR-IP-1988-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1988 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7640 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | B | 131242-WST02-DR-IP-1989-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1989 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7641 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | B | 131242-WST02-DR-IP-1990-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1990 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7642 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | B | 131242-WST02-DR-IP-1991-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1991 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7643 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | B | 131242-WST02-DR-IP-1992-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1992 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7644 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | B | 131242-WST02-DR-IP-1993-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1993 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7645 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | B | 131242-WST02-DR-IP-1994-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1994 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7646 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | B | 131242-WST02-DR-IP-1995-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1995 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7647 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | B | 131242-WST02-DR-IP-1996-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1996 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7648 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | B | 131242-WST02-DR-IP-1997-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1997 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7649 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | B | 131242-WST02-DR-IP-1998-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1998 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7650 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | B | 131242-WST02-DR-IP-1999-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1999 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7651 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | B | 131242-WST02-DR-IP-2000-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | AWC | AWC
7652 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | B | 131242-WST02-DR-IP-2001-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
7653 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | B | 131242-WST02-DR-IP-2002-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
7654 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | B | 131242-WST02-DR-IP-2003-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
7655 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | B | 131242-WST02-DR-IP-2004-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2004 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7656 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | B | 131242-WST02-DR-IP-2005-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2005 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7657 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | B | 131242-WST02-DR-IP-2006-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2006 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7658 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | B | 131242-WST02-DR-IP-2007-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2007 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2026-02-03 | A.2 | 000812&&001194&&001924 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02 | 6 | Not Approved | NAP |  |  | 0 | AWC | AWC
7659 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | B | 131242-WST02-DR-IP-2008-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2008 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "Shop Drawing for Louvre Door and Window" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194&&001604 | 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7660 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | B | 131242-WST02-DR-IP-2009-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2009 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7661 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | B | 131242-WST02-DR-IP-2010-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2010 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7662 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | B | 131242-WST02-DR-IP-2011-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2011 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7663 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | B | 131242-WST02-DR-IP-2012-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2012 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7664 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | B | 131242-WST02-DR-IP-2013-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2013 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7665 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | B | 131242-WST02-DR-IP-2014-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2014 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7666 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | B | 131242-WST02-DR-IP-2015-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2015 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7667 | 001194 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | B | 131242-WST02-DR-IP-2016-B | 2025-07-11 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-2016 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 74 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7668 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1981 | B | 131242-WST02-DR-IP-1981-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1981 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7669 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1982 | B | 131242-WST02-DR-IP-1982-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-05 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1982 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7670 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1983 | B | 131242-WST02-DR-IP-1983-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1983 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7671 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1984 | B | 131242-WST02-DR-IP-1984-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1984 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7672 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1985 | B | 131242-WST02-DR-IP-1985-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1985 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7673 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1986 | B | 131242-WST02-DR-IP-1986-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1986 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7674 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1987 | B | 131242-WST02-DR-IP-1987-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1987 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7675 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1988 | B | 131242-WST02-DR-IP-1988-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1988 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7676 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1989 | B | 131242-WST02-DR-IP-1989-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1989 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7677 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1990 | B | 131242-WST02-DR-IP-1990-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1990 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7678 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1991 | B | 131242-WST02-DR-IP-1991-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1991 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7679 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1992 | B | 131242-WST02-DR-IP-1992-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1992 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7680 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1993 | B | 131242-WST02-DR-IP-1993-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1993 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7681 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1994 | B | 131242-WST02-DR-IP-1994-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1994 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7682 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1995 | B | 131242-WST02-DR-IP-1995-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1995 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7683 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1996 | B | 131242-WST02-DR-IP-1996-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1996 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7684 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1997 | B | 131242-WST02-DR-IP-1997-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1997 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7685 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1998 | B | 131242-WST02-DR-IP-1998-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1998 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7686 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1999 | B | 131242-WST02-DR-IP-1999-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-1999 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7687 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2000 | B | 131242-WST02-DR-IP-2000-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | AWC | AWC
7688 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2001 | B | 131242-WST02-DR-IP-2001-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
7689 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2002 | B | 131242-WST02-DR-IP-2002-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
7690 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2003 | B | 131242-WST02-DR-IP-2003-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
7691 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2004 | B | 131242-WST02-DR-IP-2004-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2004 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7692 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2005 | B | 131242-WST02-DR-IP-2005-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2005 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7693 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2006 | B | 131242-WST02-DR-IP-2006-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2006 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7694 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2007 | B | 131242-WST02-DR-IP-2007-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2007 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2026-02-03 | A.2 | 000812&&001194&&001924 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02 | 6 | Not Approved | NAP |  |  | 0 | AWC | AWC
7695 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2008 | B | 131242-WST02-DR-IP-2008-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2008 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "Shop Drawing for Louvre Door and Window" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194&&001604 | 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7696 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2009 | B | 131242-WST02-DR-IP-2009-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2009 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7697 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2010 | B | 131242-WST02-DR-IP-2010-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2010 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7698 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2011 | B | 131242-WST02-DR-IP-2011-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2011 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7699 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2012 | B | 131242-WST02-DR-IP-2012-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2012 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7700 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2013 | B | 131242-WST02-DR-IP-2013-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2013 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7701 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2014 | B | 131242-WST02-DR-IP-2014-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2014 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7702 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2015 | B | 131242-WST02-DR-IP-2015-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2015 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7703 | 001194 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 2016 | B | 131242-WST02-DR-IP-2016-B | 2025-11-17 | SSN Panel RIO-208 - GA & Schematic Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-15 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-2016 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 28 | AWC | 2025-11-17 | B | 001194 | 2025-04-03, 2025-07-11, 2025-11-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
7704 | 001195 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 0 | 131242-WSW41-SH-M-1006-0 | 2025-04-03 | Manual Butterfly Valve | Rev 0: Not approved - Revise and Resubmit | 2025-05-01 | 2025-06-23 | Not Approved | 2025-07-11 | YES | Resubmitted |  | 131242-WSW41-SH-1006 | NA | "Manual Butterfly Valve " | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 81 | NAP | 2025-11-26 | 2 | 001195 | 2025-04-03, 2025-08-06, 2025-11-26 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7705 | 001195 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 1 | 131242-WSW41-SH-M-1006-1 | 2025-08-06 | Manual Butterfly Valve | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-08-26 | 2025-09-04 | Approved with Comments |  | YES | NA |  | 131242-WSW41-SH-1006 | NA | "Manual Butterfly Valve " | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-20 | 29 | AWC | 2025-11-26 | 2 | 001195 | 2025-04-03, 2025-08-06, 2025-11-26 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7706 | 001195 | 02 | Joo Kwan | Mech | NA | 131242 | WSW41 | SH | M | 1006 | 2 | 131242-WSW41-SH-M-1006-2 | 2025-11-26 | Manual Butterfly Valve | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-12-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SH-1006 | NA | "Manual Butterfly Valve " | 2025-04-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-10 | 131 | PEN | 2025-11-26 | 2 | 001195 | 2025-04-03, 2025-08-06, 2025-11-26 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-13 |  | 0 | PEN | PEN
7707 | 001196 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0021 | 0 | 131242-WSW41-QA-A-0021-0 | 2025-04-03 | Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-01 | 2025-04-15 | Not Approved | 2025-05-05 | NO | Overdue |  | 131242-WSW41-QA-0021 | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 12 | NAP | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | Not Approved | NAP | 2025-05-05 | Overdue | 0 | NAP | NAP
7708 | 001197 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0003 | 0 | 131242-WSW41-MS-A-0003-0 | 2025-04-03 | MSRA and SWP for Plastering and Skim Coat | Rev.0: Approved with comments. No resubmission is required. | 2025-05-01 | 2025-05-12 | Approved with Comments |  | YES | NA |  | 131242-WSW41-MS-0003 | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-17 | 39 | AWC | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2025-05-30 | Overdue | 0 | AWC | AWC
7709 | 001198 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0004 | 0 | 131242-WSW41-MS-A-0004-0 | 2025-04-03 | MSRA and SWP for Floor Screeding and Tiles Laying | Rev.0: Approved with comments. | 2025-05-01 | 2025-05-12 | Approved with Comments | 2025-05-30 | NO | Overdue |  | 131242-WSW41-MS-0004 | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 39 | AWC | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | Approved with Comments | AWC | 2025-05-30 | Overdue | 0 | AWC | AWC
7710 | 001199 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0068 | 0 | 131242-WST02-QA-M-0068-0 | 2025-04-03 | FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) | NA | 2025-05-01 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WST02-QA-0068 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) " && "SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) " | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-23 | 158 | APP | 2026-02-25 | 0 | 001199&&002019 | 2025-04-03, 2026-02-25 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
7711 | 001200 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0028 | 0 | 131242-WSW41-VI-M-0028-0 | 2025-04-03 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | Approved with Comments | 2025-05-01 | 2025-05-21 | Approved with Comments | 2025-06-10 | YES | Resubmitted |  | 131242-WSW41-VI-0028 | NA | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 48 | AWC | 2025-07-02 | 1 | 001200 | 2025-04-03, 2025-07-02 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7712 | 001200 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0028 | 1 | 131242-WSW41-VI-M-0028-1 | 2025-07-02 | Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-07-22 | 2026-01-07 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0028 | NA | "Preliminary Design and Vendor Approval for Splitter Box, Chute, Sink, Cabinet" | 2025-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-16 | 189 | AWC | 2025-07-02 | 1 | 001200 | 2025-04-03, 2025-07-02 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-27 | Overdue | 0 | AWC | AWC
7713 | 001201 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1015 | 0 | 131242-WSW41-VI-M-1015-0 | 2025-04-04 | Preliminary design and Vendor Approval – Strainer (Bliss) | Rev 0: Not approved - Revise and Resubmit | 2025-05-02 | 2025-06-23 | Not Approved | 2025-07-11 | NO | Overdue |  | 131242-WSW41-VI-1015 | NA | "Preliminary design and Vendor Approval – Strainer (Bliss)" | 2025-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 80 | NAP | 2025-04-04 | 0 | 001201 | 2025-04-04 | 00 | 1 | Not Approved | NAP | 2025-07-11 | Overdue | 0 | NAP | NAP
7714 | 001202 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0059 | 0 | 131242-WSW41-LT-PM-0059-0 | 2025-04-04 | Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors | Rev (0): Received for information. Please refer to S.O. correspondence no. 399 dated 10 Sep 2025. | 2025-05-02 | 2025-09-23 | For Information |  | YES | NA |  | 131242-WSW41-LT-0059 | NA | "Notice for Extension of Time and Cost for Delays for Power Turn On to the Electrical and Transformer Buildings due to Delays by other Projects’ Contractors" | 2025-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-24 | 172 | INF | 2025-04-04 | 0 | 001202 | 2025-04-04 | 00 | 1 | For Information | INF | 2025-10-13 | Overdue | 0 | INF | INF
7715 | 001203 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | A | 0007 | 0 | 131242-WSW41-MS-A-0007-0 | 2025-04-07 | MSRA, SWP for Door Installation | Approved | 2025-05-05 | 2025-04-15 | Approved |  | YES | NA |  | 131242-WSW41-MS-0007 | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-21 | 8 | APP | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
7716 | 001204 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0021 | 0 | 131242-WSW41-PC-W-0021-0 | 2025-04-07 | Payment Claim No.21 | Rev (0): For Information. Please refer to S.O. correspondence no. 322 dated 8 April 2025 | 2025-05-05 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSW41-PC-0021 | NA | "Payment Claim No.21" | 2025-04-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-27 | 20 | INF | 2025-04-07 | 0 | 001204 | 2025-04-07 | 00 | 1 | For Information | INF | 2025-05-15 | Overdue | 0 | INF | INF
7717 | 001205 | 00 | N. Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0024 | 0 | 131242-WSW41-QA-C-0024-0 | 2025-04-07 | Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) | Approved with Comments | 2025-05-05 | 2025-06-04 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0024 | NA | "Aluminium handrail & cat ladder fabrication Vendor details and Quality documents (ITP, Quality control procedure, NDTprocedure, WPS/PQR) (SanHe – Jiangsu HDmann Electric group Co.,Ltd.) " | 2025-04-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-27 | 58 | AWC | 2025-04-07 | 0 | 001205 | 2025-04-07 | 00 | 1 | Approved with Comments | AWC | 2025-06-24 | Overdue | 0 | AWC | AWC
7718 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7000 | A | 131242-WSW41-DR-EI-7000-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | YES | Resubmitted |  | 131242-WSW41-DR-7000 | NA | "LCS GA and Schematic Drawing" | 2025-04-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-27 | 65 | REJ | 2025-04-07 | A | 001206 | 2025-04-07 | 00 | 1 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7719 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7001 | A | 131242-WSW41-DR-EI-7001-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-7001 | NA | "LCS GA and Schematic Drawing" | 2025-04-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-27 | 65 | REJ | 2025-04-07 | A | 001206 | 2025-04-07 | 00 | 1 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7720 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EI | 7002 | A | 131242-WSW41-DR-EI-7002-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-7002 | NA | "LCS GA and Schematic Drawing" | 2025-04-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-27 | 65 | REJ | 2025-04-07 | A | 001206 | 2025-04-07 | 00 | 1 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7721 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3000 | A | 131242-WSW41-DR-EP-3000-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 65 | REJ | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
7722 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3001 | A | 131242-WSW41-DR-EP-3001-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-3001 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 65 | REJ | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7723 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3002 | A | 131242-WSW41-DR-EP-3002-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-3002 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 65 | REJ | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7724 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3003 | A | 131242-WSW41-DR-EP-3003-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-3003 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 65 | REJ | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7725 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3004 | A | 131242-WSW41-DR-EP-3004-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-3004 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 65 | REJ | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7726 | 001206 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EP | 3005 | A | 131242-WSW41-DR-EP-3005-A | 2025-04-07 | LCS GA and Schematic Drawing | Rev 0: Rejected. To revise and resubmit, along with other perquisite submissions. Refer to attached file for comments. | 2025-05-05 | 2025-06-11 | Rejected | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-3005 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-21 | 65 | REJ | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ | 2025-07-01 | Overdue | 0 | REJ | REJ
7727 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7400 | B | 131242-WSD11-DR-EI-7400-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7400 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7728 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7401 | B | 131242-WSD11-DR-EI-7401-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7401 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7729 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7402 | B | 131242-WSD11-DR-EI-7402-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7402 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7730 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3180 | B | 131242-WSD11-DR-EP-3180-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3180 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7731 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3181 | B | 131242-WSD11-DR-EP-3181-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3181 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7732 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3182 | B | 131242-WSD11-DR-EP-3182-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3182 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7733 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3183 | B | 131242-WSD11-DR-EP-3183-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3183 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7734 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3184 | B | 131242-WSD11-DR-EP-3184-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3184 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7735 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3185 | B | 131242-WSD11-DR-EP-3185-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3185 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7736 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3186 | B | 131242-WSD11-DR-EP-3186-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3186 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7737 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3187 | B | 131242-WSD11-DR-EP-3187-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3187 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7738 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3188 | B | 131242-WSD11-DR-EP-3188-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-3188 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7739 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7180 | B | 131242-WSD11-DR-EP-7180-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7180 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7740 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7181 | B | 131242-WSD11-DR-EP-7181-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7181 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7741 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7182 | B | 131242-WSD11-DR-EP-7182-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7182 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7742 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7183 | B | 131242-WSD11-DR-EP-7183-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-7183 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7743 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7400 | B | 131242-WST02-DR-EI-7400-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7400 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7744 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7401 | B | 131242-WST02-DR-EI-7401-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7401 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7745 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7402 | B | 131242-WST02-DR-EI-7402-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7402 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7746 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3180 | B | 131242-WST02-DR-EP-3180-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3180 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7747 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3181 | B | 131242-WST02-DR-EP-3181-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3181 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7748 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3182 | B | 131242-WST02-DR-EP-3182-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3182 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7749 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3183 | B | 131242-WST02-DR-EP-3183-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3183 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7750 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3184 | B | 131242-WST02-DR-EP-3184-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3184 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7751 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3185 | B | 131242-WST02-DR-EP-3185-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3185 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7752 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3186 | B | 131242-WST02-DR-EP-3186-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3186 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7753 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3187 | B | 131242-WST02-DR-EP-3187-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3187 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7754 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3188 | B | 131242-WST02-DR-EP-3188-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-3188 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 85 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7755 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7180 | B | 131242-WST02-DR-EP-7180-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7180 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7756 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7181 | B | 131242-WST02-DR-EP-7181-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7181 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7757 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7182 | B | 131242-WST02-DR-EP-7182-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7182 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7758 | 001206 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7183 | B | 131242-WST02-DR-EP-7183-B | 2025-07-08 | LCS GA and Schematic Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-28 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7183 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 85 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7759 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7400 | C | 131242-WSD11-DR-EI-7400-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7400 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7760 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7401 | C | 131242-WSD11-DR-EI-7401-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7401 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7761 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7402 | C | 131242-WSD11-DR-EI-7402-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7402 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7762 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3180 | C | 131242-WSD11-DR-EP-3180-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3180 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7763 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3181 | C | 131242-WSD11-DR-EP-3181-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3181 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7764 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3182 | C | 131242-WSD11-DR-EP-3182-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3182 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7765 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3183 | C | 131242-WSD11-DR-EP-3183-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3183 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7766 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3184 | C | 131242-WSD11-DR-EP-3184-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3184 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7767 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3185 | C | 131242-WSD11-DR-EP-3185-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3185 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7768 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3186 | C | 131242-WSD11-DR-EP-3186-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3186 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7769 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3187 | C | 131242-WSD11-DR-EP-3187-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3187 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7770 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3188 | C | 131242-WSD11-DR-EP-3188-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3188 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7771 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7180 | C | 131242-WSD11-DR-EP-7180-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7180 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7772 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7181 | C | 131242-WSD11-DR-EP-7181-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7181 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7773 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7182 | C | 131242-WSD11-DR-EP-7182-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7182 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7774 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7183 | C | 131242-WSD11-DR-EP-7183-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7183 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7775 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7400 | C | 131242-WST02-DR-EI-7400-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7400 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7776 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7401 | C | 131242-WST02-DR-EI-7401-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7401 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7777 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7402 | C | 131242-WST02-DR-EI-7402-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7402 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7778 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3180 | C | 131242-WST02-DR-EP-3180-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3180 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7779 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3181 | C | 131242-WST02-DR-EP-3181-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3181 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7780 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3182 | C | 131242-WST02-DR-EP-3182-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3182 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7781 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3183 | C | 131242-WST02-DR-EP-3183-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3183 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7782 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3184 | C | 131242-WST02-DR-EP-3184-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3184 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7783 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3185 | C | 131242-WST02-DR-EP-3185-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3185 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7784 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3186 | C | 131242-WST02-DR-EP-3186-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3186 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7785 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3187 | C | 131242-WST02-DR-EP-3187-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3187 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7786 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3188 | C | 131242-WST02-DR-EP-3188-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-3188 | NA | "LCS GA and Schematic Drawing" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001206 | 2025-07-08, 2025-10-08 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7787 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7180 | C | 131242-WST02-DR-EP-7180-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7180 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7788 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7181 | C | 131242-WST02-DR-EP-7181-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7181 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7789 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7182 | C | 131242-WST02-DR-EP-7182-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7182 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7790 | 001206 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7183 | C | 131242-WST02-DR-EP-7183-C | 2025-10-08 | LCS GA and Schematic Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-DR-7183 | NA | "LCS GA and Schematic Drawing" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 139 | AWC | 2025-10-08 | C | 001140&&001206 | 2025-03-21, 2025-07-08, 2025-07-21, 2025-10-08 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
7791 | 001207 | 00 | N Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0028 | 0 | 131242-WSW41-MS-C-0028-0 | 2025-04-07 | MSRA SWP for Concrete Coring | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-05 | 2025-05-12 | Not Approved | 2025-05-30 | YES | Resubmitted |  | 131242-WSW41-MS-0028 | NA | "MSRA SWP for Concrete Coring " | 2025-04-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-27 | 35 | NAP | 2025-05-18 | 1 | 001207 | 2025-04-07, 2025-05-18 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7792 | 001207 | 01 | N Kumar | QAQC | NA | 131242 | WSW41 | MS | C | 0028 | 1 | 131242-WSW41-MS-C-0028-1 | 2025-05-18 | MSRA SWP for Concrete Coring | Rev.1: Approved with Comments: Please refer to comment sheet for resubmission. | 2025-06-05 | 2025-06-13 | Approved with Comments | 2025-07-03 | NO | Overdue |  | 131242-WSW41-MS-0028 | NA | "MSRA SWP for Concrete Coring " | 2025-04-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 26 | AWC | 2025-05-18 | 1 | 001207 | 2025-04-07, 2025-05-18 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-03 | Overdue | 0 | AWC | AWC
7793 | 001208 | 00 | Aaron | CSA | NA | 131242 | WSW41 | SD | S | - | 0 | 131242-WSW41-SD-S---0 | 2025-04-08 | Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614) | R0: For Information. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-06-30 | For Information |  | YES | NA |  | 131242-WSW41-SD-- | NA | "Site Wide Pipe Rack-03 Fabrication Details_GL J-M, GL M-V & GL V-AB (ST614)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema | 2025-04-28 | 83 | INF | 2025-04-08 | 0 | 001208 | 2025-04-08 | 00 | 1 | For Information | INF | 2025-07-18 | Overdue | 0 | INF | INF
7794 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1101 | A | 131242-WST02-SD-S-1101-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-1101 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7795 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1102 | A | 131242-WST02-SD-S-1102-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-1102 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7796 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 2100 | A | 131242-WST02-SD-S-2100-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-2100 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7797 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 2103 | A | 131242-WST02-SD-S-2103-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-2103 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7798 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3100 | A | 131242-WST02-SD-S-3100-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-3100 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7799 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5100 | A | 131242-WST02-SD-S-5100-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-5100 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 118 | NAP | 2025-04-08 | A | 000615&&001209 | 2024-08-05, 2024-08-27, 2025-04-08 | 00, 01 | 3 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7800 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5101 | A | 131242-WST02-SD-S-5101-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-5101 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-22 | 118 | NAP | 2025-04-08 | A | 000615&&001209 | 2024-08-05, 2024-08-27, 2025-04-08 | 00, 01 | 3 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7801 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5105 | A | 131242-WST02-SD-S-5105-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-5105 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7802 | 001209 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8004 | A | 131242-WST02-SD-S-8004-A | 2025-04-08 | Steel Shop Drawings For SSN PR-001 (ST609) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-06 | 2025-08-04 | Not Approved | 2025-08-22 | NO | Overdue |  | 131242-WST02-SD-8004 | NA | "Steel Shop Drawings For SSN PR-001 (ST609)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 118 | NAP | 2025-04-08 | A | 001209 | 2025-04-08 | 00 | 1 | Not Approved | NAP | 2025-08-22 | Overdue | 0 | NAP | NAP
7803 | 001210 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0054 | 0 | 131242-WSW41-CD-IM-0054-0 | 2025-04-08 | Submission of BIM Coordination VCM Model (Mar 2025) | For Information. Score= 71/100 | 2025-05-06 | 2025-04-27 | For Information |  | YES | NA |  | 131242-WSW41-CD-0054 | NA | " Submission of BIM Coordination VCM Model (Mar 2025) " | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-28 | 19 | INF | 2025-04-08 | 0 | 001210 | 2025-04-08 | 00 | 1 | For Information | INF | 2025-05-15 | Overdue | 0 | INF | INF
7804 | 001211 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0015 | 0 | 131242-WSW41-PO-M-0015-0 | 2025-04-08 | Unpriced LOA for MEICA installer (Cyclect Engineering) | Rev 0: For Information | 2025-05-06 | 2025-10-06 | For Information |  | YES | NA |  | 131242-WSW41-PO-0015 | NA | "Unpriced LOA for MEICA installer (Cyclect Engineering)" && "Unpriced PO for Pressure Switch (IFM) " && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-28 | 181 | INF | 2025-08-22 | 0 | 001211&&001505&&001613 | 2025-04-08, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
7805 | 001212 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0023 | 0 | 131242-WSW41-RT-PM-0023-0 | 2025-04-09 | C4B Monthly Progress Report Number No.23 (03 25) | Rev. 0 - Approved with comments (need to re-submit, see attached comment sheet) | 2025-05-07 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WSW41-RT-0023 | NA | "C4B Monthly Progress Report Number No.23 (03 25) " | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 18 | AWC | 2025-04-09 | 0 | 001212 | 2025-04-09 | 00 | 1 | Approved with Comments | AWC | 2025-05-15 | Overdue | 0 | AWC | AWC
7806 | 001213 | 00 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 0 | 131242-WSD11-CD-I-0005-0 | 2025-04-09 | Electrical Signal List for THP -MCC-0101A/0101B | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 | 2025-04-27 | Not Approved | 2025-05-15 | YES | Resubmitted |  | 131242-WSD11-CD-0005 | NA | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 18 | NAP | 2025-07-07 | 0 | 001213&&001440 | 2025-04-09, 2025-05-09, 2025-07-07 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7807 | 001213 | 01 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 1 | 131242-WSD11-CD-I-0005-1 | 2025-05-09 | Electrical Signal List for THP -MCC-0101A/0101B | Rev 1: Approved with comments. To revise and resubmit. | 2025-05-29 | 2025-06-17 | Approved with Comments | 2025-07-07 | NO | Overdue |  | 131242-WSD11-CD-0005 | NA | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 39 | AWC | 2025-07-07 | 0 | 001213&&001440 | 2025-04-09, 2025-05-09, 2025-07-07 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7808 | 001214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0016 | 0 | 131242-WSW41-PO-M-0016-0 | 2025-04-09 | Unpriced LOA for Fire Protection System | Rev 0: For Information | 2025-05-07 | 2025-10-06 | For Information |  | YES | NA |  | 131242-WSW41-PO-0016 | NA | "Unpriced LOA for Fire Protection System" && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Rotameter (Krohne) " | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-29 | 180 | INF | 2025-08-22 | 0 | 001214&&001506&&001614 | 2025-04-09, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
7809 | 001215 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0063 | 0 | 131242-WSD11-QA-M-0063-0 | 2025-04-09 | Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3 | Approved | 2025-05-07 | 2025-05-21 | Approved |  | YES | NA |  | 131242-WSD11-QA-0063 | NA | "Installation of Compressed Air System Piping c/w Supports & Gravity Testing @ BSB Level 2 & 3" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-29 | 42 | APP | 2025-04-09 | 0 | 001215 | 2025-04-09 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
7810 | 001216 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0067 | 0 | 131242-WSD11-QA-M-0067-0 | 2025-04-09 | Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 | Rev 0: Approved | 2025-05-07 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-QA-0067 | NA | "Installation of Compressed Air System Piping c/w Supports & Hydrotesting @ BSB Level 2 & 3 " | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-29 | 180 | APP | 2025-04-09 | 0 | 001216 | 2025-04-09 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
7811 | 001217 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0029 | 0 | 131242-WSW41-QA-EI-0029-0 | 2025-04-10 | FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch | Approved | 2025-05-08 | 2025-05-12 | Approved |  | YES | NA |  | 131242-WSW41-QA-0029 | NA | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" && "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" && "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" && "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-24 | 32 | APP | 2025-10-13 | 0 | 000940&&001217&&001238&&001745 | 2025-01-02, 2025-04-10, 2025-04-21, 2025-10-13 | 00 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
7812 | 001218 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 1008 | 0 | 131242-WSW41-SH-M-1008-0 | 2025-04-10 | ON OFF Butterfly Valve Data sheet (OVS) | Rev 0: Not approved - Revise and Resubmit | 2025-05-08 | 2025-06-23 | Not Approved | 2025-07-11 | YES | Resubmitted |  | 131242-WSW41-SH-1008 | NA | "ON OFF Butterfly Valve Data sheet (OVS)" | 2025-04-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 74 | NAP | 2025-04-10 | 0 | 001218 | 2025-04-10 | 00 | 1 | Not Approved | NAP | 2025-07-11 | Overdue | 0 | NAP | NAP
7813 | 001218 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | SH | M | 1008 | 1 | 131242-WST02-SH-M-1008-1 | 2025-07-11 | ON OFF Butterfly Valve Data sheet (OVS) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-31 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WST02-SH-1008 | NA | "ON OFF Butterfly Valve Data sheet (OVS)" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 55 | AWC | 2025-07-11 | 1 | 001218 | 2025-07-11 | 01 | 1 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
7814 | 001219 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 0 | 131242-WST02-QA-BS-0001-0 | 2025-04-10 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | Not Approved - Revise and resubmit | 2025-05-08 | 2025-05-25 | Not Approved | 2025-06-12 | YES | Resubmitted |  | 131242-WST02-QA-0001 | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 45 | NAP | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
7815 | 001219 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 1 | 131242-WST02-QA-BS-0001-1 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | Not Approved - Revise and resubmit | 2025-07-22 | 2025-08-06 | Not Approved | 2025-08-26 | YES | Resubmitted |  | 131242-WST02-QA-0001 | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 35 | NAP | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
7816 | 001219 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 2 | 131242-WST02-QA-BS-0001-2 | 2025-08-19 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-08 | 2025-08-28 | Not Approved | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-QA-0001 | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 9 | NAP | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
7817 | 001219 | 03 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0001 | 3 | 131242-WST02-QA-BS-0001-3 | 2025-10-07 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services) | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-27 | 2025-12-05 | Not Approved | 2025-12-25 | NO | Overdue |  | 131242-WST02-QA-0001 | NA | "Renders, Bonding agent, Corner bead, Frame tie, Wire Mesh materials submissions" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV works (Building Services)" | 2024-12-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-21 | 59 | NAP | 2025-10-07 | 3 | 000876&&001219 | 2024-12-05, 2025-04-10, 2025-04-11, 2025-07-02, 2025-08-19, 2025-10-07 | 00, 01, 02, 03 | 6 | Not Approved | NAP | 2025-12-25 | Overdue | 0 | NAP | NAP
7818 | 001220 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0065 | 0 | 131242-WSW41-QA-M-0065-0 | 2025-04-10 | Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve | Approved | 2025-05-08 | 2025-05-21 | Approved |  | YES | NA |  | 131242-WSW41-QA-0065 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve" && "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP)" | 2025-04-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-30 | 41 | APP | 2026-01-05 | 0 | 001220&&001933 | 2025-04-10, 2026-01-05 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
7819 | 001221 | 00 | N Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0025 | 0 | 131242-WSW41-QA-C-0025-0 | 2025-04-11 | Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces | Approved with Comments | 2025-05-09 | 2025-05-09 | Approved with Comments | 2025-05-29 | NO | Overdue |  | 131242-WSW41-QA-0025 | NA | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" && "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" && "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-25 | 28 | AWC | 2025-07-08 | 0 | 000881&&001221&&001446 | 2024-12-10, 2025-03-13, 2025-04-11, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7820 | 001222 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0021 | 0 | 131242-WSW41-PS-HS-0021-0 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Dec 2024 | For Information | 2025-04-14 | 2025-05-12 | For Information |  | YES | NA |  | 131242-WSW41-PS-0021 | NA | "Incentive/ Disincentive Audit Scheme for Dec 2024" && "Monthly Progress Presentation No. 21 (0225)" | 2025-03-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-06 | 56 | INF | 2025-04-21 | 0 | 001222&&001242 | 2025-03-17, 2025-04-21 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7821 | 001223 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0022 | 0 | 131242-WSW41-PS-HS-0022-0 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Jan 2025 | For Information | 2025-04-14 | 2025-05-12 | For Information |  | YES | NA |  | 131242-WSW41-PS-0022 | NA | "Incentive/ Disincentive Audit Scheme for Jan 2025" && "Monthly Progress Presentation No. 22 (0325)" | 2025-03-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-06 | 56 | INF | 2025-04-21 | 0 | 001223&&001244 | 2025-03-17, 2025-04-21 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7822 | 001224 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0023 | 0 | 131242-WSW41-PS-HS-0023-0 | 2025-03-17 | Incentive/ Disincentive Audit Scheme for Feb 2025 | For Information | 2025-04-14 | 2025-05-12 | For Information |  | YES | NA |  | 131242-WSW41-PS-0023 | NA | "Incentive/ Disincentive Audit Scheme for Feb 2025" | 2025-03-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-06 | 56 | INF | 2025-03-17 | 0 | 001224 | 2025-03-17 | 00 | 1 | For Information | INF | 2025-05-30 | Overdue | 0 | INF | INF
7823 | 001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0042 | 0 | 131242-WSW41-MI-C-0042-0 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0042 | NA | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 69 | INF | 2025-02-25 | 0 | 001225 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7824 | 001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0043 | 0 | 131242-WSW41-MI-C-0043-0 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0043 | NA | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 69 | INF | 2025-02-25 | 0 | 001225 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7825 | 001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0044 | 0 | 131242-WSW41-MI-C-0044-0 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0044 | NA | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 69 | INF | 2025-02-25 | 0 | 001225 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7826 | 001225 | 00 | Leslie | PCM | NA | 131242 | WSW41 | MI | C | 0045 | 0 | 131242-WSW41-MI-C-0045-0 | 2025-02-25 | CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025 | For Information | 2025-03-25 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0045 | NA | "CSA Meeting Minutes 0042,43,44,45_1902, 0603, 2003, 0304 2025" | 2025-02-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-17 | 69 | INF | 2025-02-25 | 0 | 001225 | 2025-02-25 | 00 | 1 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7827 | 001226 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5200 | A | 131242-WSW41-DR-S-5200-A | 2025-04-14 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Not Approved - Revise and resubmit | 2025-05-12 | 2025-05-19 | Not Approved | 2025-06-06 | YES | Resubmitted |  | 131242-WSW41-DR-5200 | NA | "SWPR _Platform A and B- Cat ladders" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " | 2025-04-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-04 | 35 | NAP | 2025-08-13 | E | 001226&&001586 | 2025-04-14, 2025-08-13 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
7828 | 001226 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1210 | A | 131242-WSW41-DR-S-1210-A | 2025-04-14 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Not Approved - Revise and resubmit | 2025-05-12 | 2025-05-19 | Not Approved | 2025-06-06 | YES | Resubmitted |  | 131242-WSW41-DR-1210 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " | 2025-04-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-04 | 35 | NAP | 2025-09-15 | B | 001226 | 2025-04-14, 2025-09-15 | 00, 01 | 2 | Rejected | REJ |  |  | 0 | NAP | NAP
7829 | 001226 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | B | 131242-WSD11-DR-S-5200-B | 2025-09-15 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Rev.1:Rejected. Resubmission is not required. | 2025-10-03 | 2025-10-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-5200 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-29 | 30 | REJ | 2025-12-14 | A | 000861&&001226&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | REJ | REJ
7830 | 001226 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1210 | B | 131242-WSW41-DR-S-1210-B | 2025-09-15 | THP Courtyard - Valve Pit, Sump and Kerb Detail | Rev.1:Rejected. Resubmission is not required. | 2025-10-03 | 2025-10-15 | Rejected |  | YES | NA |  | 131242-WSW41-DR-1210 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " | 2025-04-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-29 | 30 | REJ | 2025-09-15 | B | 001226 | 2025-04-14, 2025-09-15 | 00, 01 | 2 | Rejected | REJ | 2025-11-04 | Overdue | 0 | REJ | REJ
7831 | 001227 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | EI | 0011 | 0 | 131242-WSW41-MS-EI-0011-0 | 2025-04-14 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-12 | 2025-05-30 | Approved with Comments | 2025-06-19 | YES | Resubmitted |  | 131242-WSW41-MS-0011 | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-28 | 46 | AWC | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7832 | 001227 | 01 | Bryan | EICA | NA | 131242 | WSW41 | MS | EI | 0011 | 1 | 131242-WSW41-MS-EI-0011-1 | 2025-12-08 | MSRA for HV Power and Pilot Cable Laying, Testing & Termination | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-26 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WSW41-MS-0011 | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-22 | 74 | AWC | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
7833 | 001228 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0029 | 0 | 131242-WSW41-SP-C-0029-0 | 2025-04-16 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-14 | 2025-05-07 | Approved with Comments | 2025-05-27 | YES | Resubmitted |  | 131242-WSW41-SP-0029 | NA | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" | 2025-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 21 | AWC | 2025-06-27 | 1 | 001228 | 2025-04-16, 2025-06-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
7834 | 001228 | 01 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0029 | 1 | 131242-WSW41-SP-C-0029-1 | 2025-06-27 | SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material) | R1: Approved | 2025-07-17 | 2025-07-04 | Approved |  | YES | NA |  | 131242-WSW41-SP-0029 | NA | "SSN Water tanks wall openings Boxout Non-Shrink Concrete Design mix C35/45 (PanU) (Alternative material)" | 2025-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-11 | 7 | APP | 2025-06-27 | 1 | 001228 | 2025-04-16, 2025-06-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
7835 | 001229 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0006 | 0 | 131242-WST02-DS-I-0006-0 | 2025-04-16 | Datasheet for Tuning Fork Level Switch | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DS-0006 | NA | "Datasheet for Tuning Fork Level Switch " | 2025-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 56 | NAP | 2025-12-08 | 1 | 001229 | 2025-04-16, 2025-12-08 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7836 | 001229 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0006 | 1 | 131242-WST02-DS-I-0006-1 | 2025-12-08 | Datasheet for Tuning Fork Level Switch | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-26 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WST02-DS-0006 | NA | "Datasheet for Tuning Fork Level Switch " | 2025-04-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-22 | 63 | AWC | 2025-12-08 | 1 | 001229 | 2025-04-16, 2025-12-08 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
7837 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3001 | A | 131242-WSD11-DR-IC-3001-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7838 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3002 | A | 131242-WSD11-DR-IC-3002-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7839 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3003 | A | 131242-WSD11-DR-IC-3003-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7840 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3004 | A | 131242-WSD11-DR-IC-3004-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7841 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3005 | A | 131242-WSD11-DR-IC-3005-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7842 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3006 | A | 131242-WSD11-DR-IC-3006-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7843 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3007 | A | 131242-WSD11-DR-IC-3007-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7844 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3008 | A | 131242-WSD11-DR-IC-3008-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7845 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3009 | A | 131242-WSD11-DR-IC-3009-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7846 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3010 | A | 131242-WSD11-DR-IC-3010-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7847 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3011 | A | 131242-WSD11-DR-IC-3011-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7848 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3012 | A | 131242-WSD11-DR-IC-3012-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7849 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3013 | A | 131242-WSD11-DR-IC-3013-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7850 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3014 | A | 131242-WSD11-DR-IC-3014-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7851 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3015 | A | 131242-WSD11-DR-IC-3015-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7852 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3016 | A | 131242-WSD11-DR-IC-3016-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7853 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3017 | A | 131242-WSD11-DR-IC-3017-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7854 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3018 | A | 131242-WSD11-DR-IC-3018-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7855 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3019 | A | 131242-WSD11-DR-IC-3019-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7856 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3020 | A | 131242-WSD11-DR-IC-3020-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7857 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3021 | A | 131242-WSD11-DR-IC-3021-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7858 | 001230 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3022 | A | 131242-WSD11-DR-IC-3022-A | 2025-04-16 | THP WAP FFOTP_GA & Wiring Diagram | Not Approved - Revise and resubmit | 2025-05-14 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 56 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7859 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3001 | A | 131242-WSD11-DR-IC-3001-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7860 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3002 | A | 131242-WSD11-DR-IC-3002-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7861 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3003 | A | 131242-WSD11-DR-IC-3003-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7862 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3004 | A | 131242-WSD11-DR-IC-3004-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7863 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3005 | A | 131242-WSD11-DR-IC-3005-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7864 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3006 | A | 131242-WSD11-DR-IC-3006-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7865 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3007 | A | 131242-WSD11-DR-IC-3007-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7866 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3008 | A | 131242-WSD11-DR-IC-3008-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7867 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3009 | A | 131242-WSD11-DR-IC-3009-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7868 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3010 | A | 131242-WSD11-DR-IC-3010-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7869 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3011 | A | 131242-WSD11-DR-IC-3011-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7870 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3012 | A | 131242-WSD11-DR-IC-3012-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7871 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3013 | A | 131242-WSD11-DR-IC-3013-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7872 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3014 | A | 131242-WSD11-DR-IC-3014-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7873 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3015 | A | 131242-WSD11-DR-IC-3015-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7874 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3016 | A | 131242-WSD11-DR-IC-3016-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7875 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3017 | A | 131242-WSD11-DR-IC-3017-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7876 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3018 | A | 131242-WSD11-DR-IC-3018-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7877 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3019 | A | 131242-WSD11-DR-IC-3019-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7878 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3020 | A | 131242-WSD11-DR-IC-3020-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7879 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3021 | A | 131242-WSD11-DR-IC-3021-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7880 | 001230 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3022 | A | 131242-WSD11-DR-IC-3022-A | 2025-08-22 | THP WAP FFOTP_GA & Wiring Diagram | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-19 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 11 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7881 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3001 | B | 131242-WSD11-DR-IP-3001-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7882 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3002 | B | 131242-WSD11-DR-IP-3002-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7883 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3003 | B | 131242-WSD11-DR-IP-3003-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7884 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3004 | B | 131242-WSD11-DR-IP-3004-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7885 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3005 | B | 131242-WSD11-DR-IP-3005-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7886 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3006 | B | 131242-WSD11-DR-IP-3006-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7887 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3007 | B | 131242-WSD11-DR-IP-3007-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7888 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3008 | B | 131242-WSD11-DR-IP-3008-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7889 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3009 | B | 131242-WSD11-DR-IP-3009-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7890 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3010 | B | 131242-WSD11-DR-IP-3010-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7891 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3011 | B | 131242-WSD11-DR-IP-3011-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7892 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3012 | B | 131242-WSD11-DR-IP-3012-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7893 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3013 | B | 131242-WSD11-DR-IP-3013-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7894 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3014 | B | 131242-WSD11-DR-IP-3014-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7895 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3015 | B | 131242-WSD11-DR-IP-3015-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7896 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3016 | B | 131242-WSD11-DR-IP-3016-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7897 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3017 | B | 131242-WSD11-DR-IP-3017-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-01-05 | Overdue | 0 | AWC | AWC
7898 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3018 | B | 131242-WSD11-DR-IP-3018-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7899 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3019 | B | 131242-WSD11-DR-IP-3019-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7900 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3020 | B | 131242-WSD11-DR-IP-3020-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7901 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3021 | B | 131242-WSD11-DR-IP-3021-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7902 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3022 | B | 131242-WSD11-DR-IP-3022-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7903 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3023 | B | 131242-WSD11-DR-IP-3023-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7904 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3024 | B | 131242-WSD11-DR-IP-3024-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7905 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3025 | B | 131242-WSD11-DR-IP-3025-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7906 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3026 | B | 131242-WSD11-DR-IP-3026-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3026 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7907 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3027 | B | 131242-WSD11-DR-IP-3027-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3027 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7908 | 001230 | 02 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 3028 | B | 131242-WSD11-DR-IP-3028-B | 2025-11-11 | THP WAP FFOTP_GA & Wiring Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-01 | 2025-12-16 | Approved with Comments | 2026-01-05 | NO | Overdue |  | 131242-WSD11-DR-3028 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 35 | AWC | 2025-11-28 | A | 000292&&001230 | 2025-05-09, 2025-11-11, 2025-11-28 | 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7909 | 001231 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0007 | 0 | 131242-WST02-DS-I-0007-0 | 2025-04-16 | Datasheet for Radar Level Transmitter | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-05-14 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WST02-DS-0007 | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 75 | NAP | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7910 | 001231 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0007 | 1 | 131242-WST02-DS-I-0007-1 | 2025-07-22 | Datasheet for Radar Level Transmitter | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-08-06 | Approved with Comments | 2025-08-26 | NO | Overdue |  | 131242-WST02-DS-0007 | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 15 | AWC | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-08-26 | Overdue | 0 | AWC | AWC
7911 | 001232 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | QA | M | 0070 | 0 | 131242-WSD11-QA-M-0070-0 | 2025-04-17 | MSRA & SWP for NDT Activities | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-05-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSD11-QA-0070 | NA | "MSRA & SWP for NDT Activities " | 2025-04-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-07 | 172 | AWC | 2025-04-17 | 0 | 001232 | 2025-04-17 | 00 | 1 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
7912 | 001233 | 00 | Balaji | EICA | NA | 131242 | WST02 | BQ | I | 0005 | 0 | 131242-WST02-BQ-I-0005-0 | 2025-04-17 | SSN ICA Cable List | Not Approved - Revise and resubmit | 2025-05-15 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-BQ-0005 | NA | "SSN ICA Cable List " | 2025-04-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-07 | 55 | NAP | 2025-10-28 | 1 | 001233 | 2025-04-17, 2025-10-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
7913 | 001233 | 01 | Balaji | EICA | NA | 131242 | WST02 | BQ | I | 0005 | 1 | 131242-WST02-BQ-I-0005-1 | 2025-10-28 | SSN ICA Cable List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2026-01-26 | Not Approved | 2026-02-13 | NO | Overdue |  | 131242-WST02-BQ-0005 | NA | "SSN ICA Cable List " | 2025-04-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 90 | NAP | 2025-10-28 | 1 | 001233 | 2025-04-17, 2025-10-28 | 00, 01 | 2 | Not Approved | NAP | 2026-02-13 | Overdue | 0 | NAP | NAP
7914 | 001234 | 00 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 0 | 131242-WST02-DS-BS-0003-0 | 2025-04-17 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | Rev 0: Not approved - Revise and Resubmit | 2025-05-15 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DS-0003 | NA | " Data Sheets for Clean Gas System" && "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 19 | NAP | 2025-06-06 | 2 | 000511&&001234&&001298 | 2024-06-05, 2025-04-17, 2025-05-15, 2025-06-06 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7915 | 001234 | 01 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 1 | 131242-WST02-DS-BS-0003-1 | 2025-04-17 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | Rev 1: Not approved - Revise and Resubmit | 2025-05-07 | 2025-05-25 | Not Approved | 2025-06-12 | YES | Resubmitted |  | 131242-WST02-DS-0003 | NA | " Data Sheets for Clean Gas System" && "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 38 | NAP | 2025-06-06 | 2 | 000511&&001234&&001298 | 2024-06-05, 2025-04-17, 2025-05-15, 2025-06-06 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
7916 | 001234 | 02 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0003 | 2 | 131242-WST02-DS-BS-0003-2 | 2025-06-06 | ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-26 | 2025-07-04 | Approved with Comments | 2025-07-24 | NO | Overdue |  | 131242-WST02-DS-0003 | NA | " Data Sheets for Clean Gas System" && "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 28 | AWC | 2025-06-06 | 2 | 000511&&001234&&001298 | 2024-06-05, 2025-04-17, 2025-05-15, 2025-06-06 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-07-24 | Overdue | 0 | AWC | AWC
7917 | 001235 | 00 | Balaji | EICA | NA | 131242 | WSW41 | DR | IP | 1001 | A | 131242-WSW41-DR-IP-1001-A | 2025-04-18 | Panel Base Frame Drawing | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-05-16 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSW41-DR-1001 | NA | "Panel Base Frame Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2025-04-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-08 | 54 | INF | 2026-01-19 | F | 001235&&001963 | 2025-04-18, 2026-01-19 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7918 | 001236 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | DS | C | 0001 | 0 | 131242-WST02-DS-C-0001-0 | 2025-04-18 | Epoxy Coating System | Approved | 2025-05-16 | 2025-06-04 | Approved |  | YES | NA |  | 131242-WST02-DS-0001 | NA | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for ACMV Equipment" && "Epoxy Coating System" && "FRP TANK DATA SHEET" | 2023-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-02 | 47 | APP | 2025-10-13 | 0 | 000016&&001236&&001296&&001740 | 2023-05-26, 2025-04-18, 2025-05-15, 2025-10-13 | 00 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
7919 | 001237 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0030 | 0 | 131242-WSW41-QA-C-0030-0 | 2025-04-21 | Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps) | For Information | 2025-05-19 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-QA-0030 | NA | "FAT Report for Control Cable and Power Cables" && "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" && "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" | 2024-12-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 14 | INF | 2025-04-25 | 0 | 000929&&001237&&001253 | 2024-12-24, 2025-04-21, 2025-04-25 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
7920 | 001238 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0029 | 0 | 131242-WSW41-QA-C-0029-0 | 2025-04-21 | Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing | For Information | 2025-05-19 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-QA-0029 | NA | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" && "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" && "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" && "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 14 | INF | 2025-10-13 | 0 | 000940&&001217&&001238&&001745 | 2025-01-02, 2025-04-10, 2025-04-21, 2025-10-13 | 00 | 4 | Not Approved | NAP |  |  | 0 | INF | INF
7921 | 001239 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0028 | 0 | 131242-WSW41-QA-C-0028-0 | 2025-04-21 | Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports) | For information | 2025-05-19 | 2025-06-04 | For Information |  | YES | NA |  | 131242-WSW41-QA-0028 | NA | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" && "SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team)" && "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" | 2025-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 44 | INF | 2025-10-06 | 0 | 001138&&001239&&001723 | 2025-03-20, 2025-04-21, 2025-10-06 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
7922 | 001240 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0027 | 0 | 131242-WSW41-QA-C-0027-0 | 2025-04-21 | Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps) | For Information | 2025-05-19 | 2025-05-30 | For Information | 2025-06-19 | NO | Overdue |  | 131242-WSW41-QA-0027 | NA | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" && "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" && "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-05 | 39 | INF | 2025-08-26 | 0 | 000889&&001240&&001626 | 2024-12-12, 2025-04-21, 2025-08-26 | 00, 01 | 4 | Approved | APP |  |  | 0 | INF | INF
7923 | 001241 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0026 | 0 | 131242-WSW41-QA-C-0026-0 | 2025-04-21 | Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024 | For information | 2025-05-19 | 2025-05-16 | For Information |  | YES | NA |  | 131242-WSW41-QA-0026 | NA | "Factory Acceptance Test Report for pH Analyser" && "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" | 2024-12-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 25 | INF | 2025-07-08 | 0 | 000872&&001241&&001447 | 2024-12-04, 2025-04-21, 2025-07-08 | 00 | 3 | Rejected | REJ |  |  | 0 | INF | INF
7924 | 001242 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0021 | 0 | 131242-WSW41-PS-PM-0021-0 | 2025-04-21 | Monthly Progress Presentation No. 21 (0225) | For information and record. | 2025-05-19 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-PS-0021 | NA | "Incentive/ Disincentive Audit Scheme for Dec 2024" && "Monthly Progress Presentation No. 21 (0225)" | 2025-03-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 14 | INF | 2025-04-21 | 0 | 001222&&001242 | 2025-03-17, 2025-04-21 | 00 | 2 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7925 | 001243 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0021 | 0 | 131242-WSW41-MI-PM-0021-0 | 2025-04-21 | Monthly Progress Meeting Minutes 0021_20250226 | For information and record. | 2025-05-19 | 2025-05-07 | For Information |  | YES | NA |  | 131242-WSW41-MI-0021 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0021_20250226" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 16 | INF | 2025-04-21 | 0 | 000388&&000460&&000684&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF | 2025-05-27 | Overdue | 0 | INF | INF
7926 | 001244 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | PS | PM | 0022 | 0 | 131242-WSW41-PS-PM-0022-0 | 2025-04-21 | Monthly Progress Presentation No. 22 (0325) | For information and record. | 2025-05-19 | 2025-05-05 | For Information |  | YES | NA |  | 131242-WSW41-PS-0022 | NA | "Incentive/ Disincentive Audit Scheme for Jan 2025" && "Monthly Progress Presentation No. 22 (0325)" | 2025-03-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 14 | INF | 2025-04-21 | 0 | 001223&&001244 | 2025-03-17, 2025-04-21 | 00 | 2 | For Information | INF | 2025-05-23 | Overdue | 0 | INF | INF
7927 | 001245 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | MI | PM | 0022 | 0 | 131242-WSW41-MI-PM-0022-0 | 2025-04-21 | Monthly Progress Meeting Minutes 0022_20250324 | For information and record | 2025-05-19 | 2025-05-07 | For Information |  | YES | NA |  | 131242-WSW41-MI-0022 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 16 | INF | 2025-04-21 | 0 | 000470&&000472&&000684&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF | 2025-05-27 | Overdue | 0 | INF | INF
7928 | 001246 | 00 | Danapal | QAQC | NA | 131242 | WSD11 | QA | I | 0009 | 0 | 131242-WSD11-QA-I-0009-0 | 2025-04-22 | FAT report for MCP panel WSD11-006-MCP-1000 | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-11 | Approved with Comments | 2025-07-01 | NO | Overdue |  | 131242-WSD11-QA-0009 | NA | "FAT report for MCP panel WSD11-006-MCP-1000 " && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 50 | AWC | 2026-01-28 | 1 | 000993&&001246 | 2025-01-20, 2025-03-06, 2025-04-08, 2025-04-22, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7929 | 001247 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0005 | 0 | 131242-WSD11-VI-I-0005-0 | 2025-04-22 | Vendor Approval for THP Electromagnetic Flowmeters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-05-20 | 2025-06-30 | Approved with Comments | 2025-07-18 | NO | Overdue |  | 131242-WSD11-VI-0005 | NA | "Vendor Approval for THP Electromagnetic Flowmeters" | 2025-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 69 | AWC | 2025-04-22 | 0 | 001247 | 2025-04-22 | 00 | 1 | Approved with Comments | AWC | 2025-07-18 | Overdue | 0 | AWC | AWC
7930 | 001248 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0046 | 0 | 131242-WSW41-MI-C-0046-0 | 2025-04-22 | CSA Meeting Minutes 0046_17042025 | For information. | 2025-05-20 | 2025-05-30 | For Information |  | YES | NA |  | 131242-WSW41-MI-0046 | NA | "CSA Meeting Minutes 0046_17042025" | 2025-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-12 | 38 | INF | 2025-04-22 | 0 | 001248 | 2025-04-22 | 00 | 1 | For Information | INF | 2025-06-19 | Overdue | 0 | INF | INF
7931 | 001249 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0060 | 0 | 131242-WSW41-LT-PM-0060-0 | 2025-04-23 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building | Rev (0): Rejected. Please refer to S.O. correspondence no. 355 dated 3 June 2025. | 2025-05-21 | 2025-08-22 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0060 | NA | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New BioSolids Building " | 2025-04-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-13 | 121 | REJ | 2025-04-23 | 0 | 001249 | 2025-04-23 | 00 | 1 | Rejected | REJ | 2025-09-11 | Overdue | 0 | REJ | REJ
7932 | 001250 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0066 | 0 | 131242-WSD11-QA-M-0066-0 | 2025-04-24 | FAT report for THP Sludge cooler B Stage 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-22 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-QA-0066 | NA | "FAT report for THP Sludge cooler B Stage 1" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-04-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-14 | 69 | AWC | 2025-12-18 | 0 | 001250&&001920 | 2025-04-24, 2025-12-02, 2025-12-18 | 00, 01 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
7933 | 001250 | 01 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0066 | 1 | 131242-WSD11-QA-M-0066-1 | 2025-12-02 | FAT report for THP Sludge cooler B Stage 1 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSD11-QA-0066 | NA | "FAT report for THP Sludge cooler B Stage 1" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-04-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 21 | APP | 2025-12-18 | 0 | 001250&&001920 | 2025-04-24, 2025-12-02, 2025-12-18 | 00, 01 | 3 | Rejected | REJ |  |  | 0 | APP | APP
7934 | 001251 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | C | 0031 | 0 | 131242-WST02-MS-C-0031-0 | 2025-04-24 | MSRA, SWP for Water Testing of Liquid Retaining Structure | Approved with Comments | 2025-05-22 | 2025-06-02 | Approved with Comments | 2025-06-20 | NO | Overdue |  | 131242-WST02-MS-0031 | NA | "MSRA, SWP for Water Testing of Liquid Retaining Structure" | 2025-04-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-14 | 39 | AWC | 2025-04-24 | 0 | 001251 | 2025-04-24 | 00 | 1 | Approved with Comments | AWC | 2025-06-20 | Overdue | 0 | AWC | AWC
7935 | 001252 | 00 | Danapal | QAQC | NA | 131242 | WST02 | DS | BS | 0004 | 0 | 131242-WST02-DS-BS-0004-0 | 2025-04-25 | Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance | Not Approved - Revise and resubmit | 2025-05-23 | 2025-05-25 | Not Approved | 2025-06-12 | NO | Overdue |  | 131242-WST02-DS-0004 | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-09 | 30 | NAP | 2025-04-25 | 0 | 000553&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | Not Approved | NAP | 2025-06-12 | Overdue | 0 | NAP | NAP
7936 | 001253 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | E | 0030 | 0 | 131242-WSW41-QA-E-0030-0 | 2025-04-25 | FAT Report for Control Cable and Power Cables | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-23 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WSW41-QA-0030 | NA | "FAT Report for Control Cable and Power Cables" && "FAT Report for Stainless Steel Pipes, Fittings, Flanges (SSN, THP) from Froch Enterprise Co. Ltd & Zhenjiang Jndia Industry Co. Ltd. 2nd Delivery" && "Test Report submission for HDG Anchor rods, washer & Nuts (SSN Piperacks & Shelters stumps)" | 2024-12-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-09 | 35 | AWC | 2025-04-25 | 0 | 000929&&001237&&001253 | 2024-12-24, 2025-04-21, 2025-04-25 | 00 | 3 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
7937 | 001254 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | BQ | I | 0001 | 0 | 131242-WSD11-BQ-I-0001-0 | 2025-04-25 | THP ICA Cable List | Rev 0: Approved with comments. To revise and resubmit. | 2025-05-23 | 2025-06-11 | Approved with Comments | 2025-07-01 | NO | Overdue |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-09 | 47 | AWC | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7938 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618_BCA | 0 | 131242-WSD11-DR-S-0302_ST618_BCA-0 | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information |  | YES | NA |  | 131242-WSD11-DR-0302_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7939 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618_BCA | C | 131242-WSD11-DR-S-1300_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7940 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618_BCA | C | 131242-WSD11-DR-S-1301_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1301_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7941 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618_BCA | C | 131242-WSD11-DR-S-1302_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1302_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7942 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618_BCA | C | 131242-WSD11-DR-S-1303_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1303_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7943 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618_BCA | C | 131242-WSD11-DR-S-1304_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1304_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7944 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618_BCA | C | 131242-WSD11-DR-S-1305_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1305_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7945 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1306_ST618_BCA | C | 131242-WSD11-DR-S-1306_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1306_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7946 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618_BCA | C | 131242-WSD11-DR-S-2300_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-2300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7947 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618_BCA | C | 131242-WSD11-DR-S-3300_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-3300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7948 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3301_ST618_BCA | C | 131242-WSD11-DR-S-3301_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-3301_ST618_BCA | NA | "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-04-25 | C | 001255 | 2025-04-25 | 00 | 1 | For Information | INF | 2025-07-01 | Overdue | 0 | INF | INF
7949 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618_BCA | C | 131242-WSD11-DR-S-5300_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7950 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618_BCA | C | 131242-WSD11-DR-S-5301_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5301_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7951 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618_BCA | C | 131242-WSD11-DR-S-5302_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5302_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7952 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618_BCA | C | 131242-WSD11-DR-S-5303_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5303_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7953 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618_BCA | C | 131242-WSD11-DR-S-5304_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5304_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7954 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618_BCA | C | 131242-WSD11-DR-S-5305_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5305_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7955 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618_BCA | C | 131242-WSD11-DR-S-5306_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5306_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7956 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618_BCA | C | 131242-WSD11-DR-S-5307_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5307_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7957 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618_BCA | C | 131242-WSD11-DR-S-5308_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5308_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7958 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618_BCA | C | 131242-WSD11-DR-S-5309_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5309_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7959 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618_BCA | C | 131242-WSD11-DR-S-5310_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5310_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7960 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5311_ST618_BCA | C | 131242-WSD11-DR-S-5311_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5311_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7961 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5312_ST618_BCA | C | 131242-WSD11-DR-S-5312_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5312_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7962 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5313_ST618_BCA | C | 131242-WSD11-DR-S-5313_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5313_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7963 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5314_ST618_BCA | C | 131242-WSD11-DR-S-5314_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5314_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7964 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5315_ST618_BCA | C | 131242-WSD11-DR-S-5315_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5315_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7965 | 001255 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5316_ST618_BCA | C | 131242-WSD11-DR-S-5316_ST618_BCA-C | 2025-04-25 | ST618 WD Response For THP Train Cambi Structures | For Information | 2025-05-23 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5316_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-15 | 47 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
7966 | 001256 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0069 | 0 | 131242-WSD11-QA-M-0069-0 | 2025-04-28 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-26 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-QA-0069 | NA | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" && "Factory Acceptance Test Report for Pressure Gauges (THP)" | 2025-04-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 65 | AWC | 2026-01-26 | 0 | 001256&&001977 | 2025-04-28, 2025-12-04, 2026-01-26 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7967 | 001256 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0069 | 1 | 131242-WSD11-QA-M-0069-1 | 2025-12-04 | FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2 | Rev 1: Approved | 2025-12-24 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSD11-QA-0069 | NA | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" && "Factory Acceptance Test Report for Pressure Gauges (THP)" | 2025-04-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-18 | 19 | APP | 2026-01-26 | 0 | 001256&&001977 | 2025-04-28, 2025-12-04, 2026-01-26 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
7968 | 001257 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0068 | 0 | 131242-WSW41-QA-M-0068-0 | 2025-04-29 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-08-01 | Approved with Comments | 2025-08-21 | YES | Resubmitted |  | 131242-WSW41-QA-0068 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" | 2025-04-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 94 | AWC | 2025-08-25 | 1 | 001257 | 2025-04-29, 2025-08-25 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7969 | 001257 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0068 | 1 | 131242-WSW41-QA-M-0068-1 | 2025-08-25 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB) | Rev 1: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-09-12 | 2025-12-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0068 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Flow Control Valve (KSB)" | 2025-04-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-08 | 120 | AWC | 2025-08-25 | 1 | 001257 | 2025-04-29, 2025-08-25 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-12 | Overdue | 0 | AWC | AWC
7970 | 001258 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0073 | 0 | 131242-WST02-QA-M-0073-0 | 2025-04-29 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-QA-0073 | NA | "FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN" && "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-04-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 55 | AWC | 2026-01-30 | 0 | 001258&&001998 | 2025-04-29, 2026-01-30 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7971 | 001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5731 | 0 | 131242-WST02-DS-M-5731-0 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WST02-DS-5731 | NA | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 31 | AWC | 2025-04-29 | 0 | 001259 | 2025-04-29 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
7972 | 001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5732 | 0 | 131242-WST02-DS-M-5732-0 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WST02-DS-5732 | NA | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 31 | AWC | 2025-04-29 | 0 | 001259 | 2025-04-29 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
7973 | 001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5733 | 0 | 131242-WST02-DS-M-5733-0 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WST02-DS-5733 | NA | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 31 | AWC | 2025-04-29 | 0 | 001259 | 2025-04-29 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
7974 | 001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5734 | 0 | 131242-WST02-DS-M-5734-0 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WST02-DS-5734 | NA | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 31 | AWC | 2025-04-29 | 0 | 001259 | 2025-04-29 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
7975 | 001259 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5735 | 0 | 131242-WST02-DS-M-5735-0 | 2025-04-29 | SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-27 | 2025-05-30 | Approved with Comments | 2025-06-19 | NO | Overdue |  | 131242-WST02-DS-5735 | NA | "SSN SRV Safety Relief Valve Data Sheets Submission (Sampling Pump,Waste Sludge Pump AB,Waste Sludge Pump CD,Granular Sludge Pump ABC,Sludge Transfer Pump AB)" | 2025-04-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-19 | 31 | AWC | 2025-04-29 | 0 | 001259 | 2025-04-29 | 00 | 1 | Approved with Comments | AWC | 2025-06-19 | Overdue | 0 | AWC | AWC
7976 | 001260 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0005 | 0 | 131242-WST02-QA-BS-0005-0 | 2025-04-30 | Inspection and test Plan for fire protection system | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-28 | 2025-05-30 | Approved with Comments | 2025-06-19 | YES | Resubmitted |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-14 | 30 | AWC | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | AWC | AWC
7977 | 001260 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0005 | 1 | 131242-WST02-QA-BS-0005-1 | 2025-07-04 | Inspection and test Plan for fire protection system | R1: Approved | 2025-07-24 | 2025-12-29 | Approved |  | YES | NA |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-18 | 178 | APP | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | APP | APP
7978 | 001261 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0071 | 0 | 131242-WSD11-QA-M-0071-0 | 2025-04-30 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-28 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-QA-0071 | NA | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" | 2025-04-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-20 | 63 | AWC | 2025-12-03 | 1 | 001261 | 2025-04-30, 2025-12-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
7979 | 001261 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0071 | 1 | 131242-WSD11-QA-M-0071-1 | 2025-12-03 | FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2 | Rev 1: Approved | 2025-12-23 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSD11-QA-0071 | NA | "FAT report for THP Train 2 (Pulper module, Pulper pump skid frame & Flash tank pump skid frame, Upper platform module ) Part-2" | 2025-04-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-17 | 20 | APP | 2025-12-03 | 1 | 001261 | 2025-04-30, 2025-12-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
7980 | 001262 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0006 | 0 | 131242-WST02-QA-BS-0006-0 | 2025-05-02 | Inspection and test Plan and Factory Acceptance Test for Public Address System | R0: Approved with comments. No resubmission is required. | 2025-05-30 | 2025-05-30 | Approved with Comments |  | YES | NA |  | 131242-WST02-QA-0006 | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-16 | 28 | AWC | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
7981 | 001262 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0006 | 1 | 131242-WST02-QA-BS-0006-1 | 2025-07-05 | Inspection and test Plan and Factory Acceptance Test for Public Address System | R0: Approved with comments. No resubmission is required. | 2025-07-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0006 | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-19 | 275 | PEN | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | PEN | PEN
7982 | 001263 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0007 | 0 | 131242-WST02-QA-BS-0007-0 | 2025-05-02 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-05-30 | 2025-05-30 | Approved with Comments | 2025-06-19 | YES | Resubmitted |  | 131242-WST02-QA-0007 | NA | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " && "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " && "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2024-12-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-16 | 28 | AWC | 2025-08-27 | 0 | 000884&&001263&&001629 | 2024-12-11, 2025-05-02, 2025-07-07, 2025-08-27 | 00, 01 | 4 | For Information | INF |  |  | 0 | AWC | AWC
7983 | 001263 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0007 | 1 | 131242-WST02-QA-BS-0007-1 | 2025-07-07 | Inspection and test Plan and Factory Acceptance Test for Fire Alarm System | R1: Approved | 2025-07-25 | 2025-12-29 | Approved |  | YES | NA |  | 131242-WST02-QA-0007 | NA | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " && "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " && "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2024-12-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-21 | 175 | APP | 2025-08-27 | 0 | 000884&&001263&&001629 | 2024-12-11, 2025-05-02, 2025-07-07, 2025-08-27 | 00, 01 | 4 | For Information | INF |  |  | 0 | APP | APP
7984 | 001264 | 00 | Danapal | QAQC | NA | 131242 | WSW41 | QA | I | 0011 | 0 | 131242-WSW41-QA-I-0011-0 | 2025-05-02 | Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-05-30 | 2025-06-30 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0011 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-16 | 59 | AWC | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
7985 | 001265 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0030 | 0 | 131242-WSW41-MS-C-0030-0 | 2025-05-04 | Application of Novolac Epoxy Coating | R0: Approved | 2025-05-30 | 2025-05-30 | Approved |  | YES | NA |  | 131242-WSW41-MS-0030 | NA | "Application of Novolac Epoxy Coating " | 2025-05-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-24 | 26 | APP | 2025-05-04 | 0 | 001265 | 2025-05-04 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
7986 | 001266 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | E | 0014 | 0 | 131242-WSW41-MS-E-0014-0 | 2025-05-04 | MSRA for Protection Relay Replacement Works | Rev 0: Rejected. Resubmission not required, refer to attached file for comments to note | 2025-05-30 | 2025-06-17 | Rejected |  | YES | NA |  | 131242-WSW41-MS-0014 | NA | "MSRA & SWP of Civil & Structure Work (Substructure)" && "MSRA for Protection Relay Replacement Works " | 2024-06-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 44 | REJ | 2025-05-04 | 0 | 000525&&001266 | 2024-06-18, 2025-05-04 | 00 | 2 | Rejected | REJ | 2025-07-07 | Overdue | 0 | REJ | REJ
7987 | 001267 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0031 | 0 | 131242-WSW41-QA-C-0031-0 | 2025-05-04 | Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 | For Information | 2025-05-30 | 2025-06-09 | For Information |  | YES | NA |  | 131242-WSW41-QA-0031 | NA | "FAT report for LVSG Panels (Sunlight)" && "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " && "SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team)" | 2025-05-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-24 | 36 | INF | 2026-01-08 | 0 | 001267&&001303&&001439&&001940 | 2025-05-04, 2025-05-18, 2025-07-07, 2026-01-08 | 00 | 4 | Approved | APP |  |  | 0 | INF | INF
7988 | 001268 | 00 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0008 | 0 | 131242-WST02-QA-BS-0008-0 | 2025-05-04 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-05-30 | 2025-05-30 | Not Approved | 2025-06-19 | YES | Resubmitted |  | 131242-WST02-QA-0008 | NA | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" && "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " && "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 26 | NAP | 2025-09-04 | 0 | 000883&&001268&&001654 | 2024-12-10, 2025-05-04, 2025-07-05, 2025-09-04 | 00, 01 | 4 | For Information | INF |  |  | 0 | NAP | NAP
7989 | 001268 | 01 | Danapal | QAQC | NA | 131242 | WST02 | QA | BS | 0008 | 1 | 131242-WST02-QA-BS-0008-1 | 2025-07-05 | Inspection and test Plan and Factory Acceptance Test for Clean Gas System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-24 | 2025-09-23 | Approved |  | YES | NA |  | 131242-WST02-QA-0008 | NA | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" && "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " && "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-19 | 80 | APP | 2025-09-04 | 0 | 000883&&001268&&001654 | 2024-12-10, 2025-05-04, 2025-07-05, 2025-09-04 | 00, 01 | 4 | For Information | INF |  |  | 0 | APP | APP
7990 | 001269 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5487 | 0 | 131242-WST02-DS-M-5487-0 | 2025-05-04 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | Rev 0: For Information Only | 2025-05-30 | 2026-01-30 | For Information | 2026-02-19 | NO | Overdue |  | 131242-WST02-DS-5487 | NA | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" | 2025-05-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-24 | 271 | INF | 2025-05-04 | 0 | 001269 | 2025-05-04 | 00 | 1 | For Information | INF | 2026-02-19 | Overdue | 0 | INF | INF
7991 | 001269 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5487 | 0 | 131242-WST02-DR-M-5487-0 | 2025-05-04 | Data Sheet and Drawing for Hyperbolic Mixer Gearbox | Rev 0: For Information Only | 2025-05-30 | 2026-01-30 | For Information | 2026-02-19 | NO | Overdue |  | 131242-WST02-DR-5487 | NA | "Data Sheet and Drawing for Hyperbolic Mixer Gearbox" | 2025-05-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-24 | 271 | INF | 2025-05-04 | 0 | 001269 | 2025-05-04 | 00 | 1 | For Information | INF | 2026-02-19 | Overdue | 0 | INF | INF
7992 | 001270 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0059 | 0 | 131242-WST02-CD-IM-0059-0 | 2025-05-09 | Submission of BIM Coordination VCM Model (Apr 2025) | For Information | 2025-06-06 | 2025-05-29 | For Information |  | YES | NA |  | 131242-WST02-CD-0059 | NA | "Submission of BIM Coordination VCM Model (Apr 2025) " | 2025-05-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-29 | 20 | INF | 2025-05-09 | 0 | 001270 | 2025-05-09 | 00 | 1 | For Information | INF | 2025-06-18 | Overdue | 0 | INF | INF
7993 | 001271 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0080 | 0 | 131242-WST02-QA-M-0080-0 | 2025-05-09 | FAT Report for Discharge Transfer Pumps (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-07-01 | Approved with Comments | 2025-07-21 | NO | Overdue |  | 131242-WST02-QA-0080 | NA | "FAT Report for Discharge Transfer Pumps (KSB)" | 2025-05-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 53 | AWC | 2025-05-09 | 0 | 001271 | 2025-05-09 | 00 | 1 | Approved with Comments | AWC | 2025-07-21 | Overdue | 0 | AWC | AWC
7994 | 001272 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0077 | 0 | 131242-WSD11-QA-M-0077-0 | 2025-05-09 | Final FAT report for THP train 1 & Train 2 Feed pumps | Rev 0: Approved | 2025-06-06 | 2025-07-02 | Approved |  | YES | NA |  | 131242-WSD11-QA-0077 | NA | "Final FAT report for THP train 1 & Train 2 Feed pumps" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-29 | 54 | APP | 2025-05-09 | 0 | 001272 | 2025-05-09 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
7995 | 001273 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0075 | 0 | 131242-WSW41-QA-M-0075-0 | 2025-05-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen) | Rev 0: Approved | 2025-06-06 | 2025-07-14 | Approved |  | YES | NA |  | 131242-WSW41-QA-0075 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Non-return check valve (Single disc PFA swing check valve & Dual disc check valve (Breen)" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-29 | 66 | APP | 2025-05-09 | 0 | 001273 | 2025-05-09 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
7996 | 001274 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0004 | 0 | 131242-WSD11-VI-M-0004-0 | 2025-05-10 | Preliminary Design and Vendor Approval Document for Steam Equiptment Package | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WSD11-VI-0004 | NA | "Preliminary Design and Vendor Approval Document for Steam Equiptment Package" && "Vendor Approval for THP Air Compressor System (Pressure Transmitter)" | 2025-02-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-24 | 44 | AWC | 2025-05-10 | 0 | 001033&&001274 | 2025-02-10, 2025-03-17, 2025-05-10 | 00, 01 | 3 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
7997 | 001275 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0016 | 0 | 131242-WSD11-CL-P-0016-0 | 2025-05-10 | HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard | Rev 0: Approved | 2025-06-06 | 2025-07-04 | Approved |  | YES | NA |  | 131242-WSD11-CL-0016 | NA | "HWR Bypass Control Vavle Sizing Calculation in C4B Courtyard" | 2025-05-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-30 | 55 | APP | 2025-05-10 | 0 | 001275 | 2025-05-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
7998 | 001276 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0040 | 0 | 131242-WSD11-DS-M-0040-0 | 2025-05-10 | THP HWR Bypass Control Valve | Approved with Comments | 2025-06-06 | 2025-05-21 | Approved with Comments | 2025-06-10 | NO | Overdue |  | 131242-WSD11-DS-0040 | NA | "THP HWR Bypass Control Valve" | 2025-05-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-30 | 11 | AWC | 2025-05-10 | 0 | 001276 | 2025-05-10 | 00 | 1 | Approved with Comments | AWC | 2025-06-10 | Overdue | 0 | AWC | AWC
7999 | 001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5721 | 0 | 131242-WST02-DS-M-5721-0 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DS-5721 | NA | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-30 | 44 | AWC | 2025-05-10 | 0 | 001277 | 2025-05-10 | 00 | 1 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8000 | 001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5722 | 0 | 131242-WST02-DS-M-5722-0 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DS-5722 | NA | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-30 | 44 | AWC | 2025-05-10 | 0 | 001277 | 2025-05-10 | 00 | 1 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8001 | 001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5723 | 0 | 131242-WST02-DS-M-5723-0 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DS-5723 | NA | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-30 | 44 | AWC | 2025-05-10 | 0 | 001277 | 2025-05-10 | 00 | 1 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8002 | 001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5724 | 0 | 131242-WST02-DS-M-5724-0 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DS-5724 | NA | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-30 | 44 | AWC | 2025-05-10 | 0 | 001277 | 2025-05-10 | 00 | 1 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8003 | 001277 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5725 | 0 | 131242-WST02-DS-M-5725-0 | 2025-05-10 | SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-06 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DS-5725 | NA | "SSN ARV Air Relief Valve Data Sheets Submission (Plant Drain pipe, ILM 1 & 2 PSI pipe line, ILM 1 & 2 WASI Pipeline, Dewatering Centrate pipeline, Discharge Transfer Pump Outlet)" | 2025-05-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-30 | 44 | AWC | 2025-05-10 | 0 | 001277 | 2025-05-10 | 00 | 1 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8004 | 001278 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0032 | 0 | 131242-WSW41-QA-C-0032-0 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Mar 2024 | For information | 2025-06-10 | 2025-05-20 | For Information |  | YES | NA |  | 131242-WSW41-QA-0032 | NA | "Issue for Information-Monthly reinforcement steel delivery records for Mar 2024" && "QA Document for CSEL Piping (WPS/PQR, Welder Certificates, FBE Coating, Liquid Epoxy Coating Details)" | 2025-01-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 7 | INF | 2025-05-13 | 0 | 000939&&001278 | 2025-01-02, 2025-05-13 | 00 | 2 | For Information | INF | 2025-06-09 | Overdue | 0 | INF | INF
8005 | 001279 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0033 | 0 | 131242-WSW41-QA-C-0033-0 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Apr 2024 | For Information | 2025-06-10 | 2025-06-02 | For Information |  | YES | NA |  | 131242-WSW41-QA-0033 | NA | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" && "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 20 | INF | 2025-07-08 | 0 | 000941&&001279&&001448 | 2025-01-02, 2025-04-21, 2025-05-13, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | INF | INF
8006 | 001280 | 00 | Kumar N | QAQC | NA | 131242 | WSW41 | QA | C | 0034 | 0 | 131242-WSW41-QA-C-0034-0 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024 | For Information | 2025-06-10 | 2025-06-02 | For Information |  | YES | NA |  | 131242-WSW41-QA-0034 | NA | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" && "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" && "Site Acceptance Test Procedure for 22KV HV Cable" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 20 | INF | 2025-07-08 | 0 | 000937&&001280&&001449 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
8007 | 001281 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0082 | 0 | 131242-WSW41-QA-M-0082-0 | 2025-05-13 | FAT report for THP Sludge cooler D Stage 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-QA-0082 | NA | "FAT report for THP Sludge cooler D Stage 2" | 2025-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 50 | AWC | 2025-12-02 | 1 | 001281 | 2025-05-13, 2025-12-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
8008 | 001281 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0082 | 1 | 131242-WSW41-QA-M-0082-1 | 2025-12-02 | FAT report for THP Sludge cooler D Stage 2 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0082 | NA | "FAT report for THP Sludge cooler D Stage 2" | 2025-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 21 | APP | 2025-12-02 | 1 | 001281 | 2025-05-13, 2025-12-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
8009 | 001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1600_ST620 | E | 131242-WSD11-DR-S-1600_ST620-E | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1600_ST620 | NA | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 29 | INF | 2025-05-13 | E | 001282 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-07-01 | Overdue | 0 | INF | INF
8010 | 001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1601_ST620 | E | 131242-WSD11-DR-S-1601_ST620-E | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-1601_ST620 | NA | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 29 | INF | 2025-05-13 | E | 001282 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-07-01 | Overdue | 0 | INF | INF
8011 | 001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5600_ST620 | E | 131242-WSD11-DR-S-5600_ST620-E | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5600_ST620 | NA | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 29 | INF | 2025-05-13 | E | 001282 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-07-01 | Overdue | 0 | INF | INF
8012 | 001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5601_ST620 | E | 131242-WSD11-DR-S-5601_ST620-E | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5601_ST620 | NA | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 29 | INF | 2025-05-13 | E | 001282 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-07-01 | Overdue | 0 | INF | INF
8013 | 001282 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5602_ST620 | E | 131242-WSD11-DR-S-5602_ST620-E | 2025-05-13 | ST620 Pipe Supports and Duct Supports Redesign | For Information | 2025-06-10 | 2025-06-11 | For Information | 2025-07-01 | NO | Overdue |  | 131242-WSD11-DR-5602_ST620 | NA | "ST620 Pipe Supports and Duct Supports Redesign" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 29 | INF | 2025-05-13 | E | 001282 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-07-01 | Overdue | 0 | INF | INF
8014 | 001283 | 00 | Aaron | CSA | NA | New WD | NA | NA | NA | 9999 | E | New WD ----- | 2025-05-13 | NEW WD from BCA for ST618 - THP Train Cambi Structures | For information | 2025-06-10 | 2025-05-21 | For Information |  | YES | NA |  | New WD -NA-NA-9999 | NA | "NEW WD from BCA for ST618 - THP Train Cambi Structures" | 2025-05-13 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-06-02 | 8 | INF | 2025-05-13 | E | 001283 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-06-10 | Overdue | 0 | INF | INF
8015 | 001284 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011 | E | 131242-WST02-DR-S-1011-E | 2025-05-13 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-10 | 2025-06-30 | Approved with Comments | 2025-07-18 | NO | Overdue |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-27 | 48 | AWC | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8016 | 001284 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004 | E | 131242-WST02-DR-S-7004-E | 2025-05-13 | SSN Water Tank Wier 1 and 2 TOC and Rebar Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-10 | 2025-06-30 | Approved with Comments | 2025-07-18 | NO | Overdue |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-27 | 48 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8017 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1203 | F | 131242-WST02-DR-S-1203-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information |  | YES | NA |  | 131242-WST02-DR-1203 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 86 | INF | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | INF | INF
8018 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1204 | F | 131242-WST02-DR-S-1204-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-1204 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-27 | 86 | INF | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | INF | INF
8019 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 2202 | F | 131242-WST02-DR-S-2202-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-2202 | NA | "ST608 drawings Connection Details" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 86 | INF | 2025-05-13 | F | 001285 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-08-27 | Overdue | 0 | INF | INF
8020 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3202 | F | 131242-WST02-DR-S-3202-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-3202 | NA | "ST608 drawings Connection Details" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 86 | INF | 2025-05-13 | F | 001285 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-08-27 | Overdue | 0 | INF | INF
8021 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5205 | F | 131242-WST02-DR-S-5205-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-5205 | NA | "ST608 drawings Connection Details" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 86 | INF | 2025-05-13 | F | 001285 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-08-27 | Overdue | 0 | INF | INF
8022 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5206 | F | 131242-WST02-DR-S-5206-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-5206 | NA | "ST608 drawings Connection Details" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 86 | INF | 2025-05-13 | F | 001285 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-08-27 | Overdue | 0 | INF | INF
8023 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5207 | F | 131242-WST02-DR-S-5207-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-5207 | NA | "ST608 drawings Connection Details" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 86 | INF | 2025-05-13 | F | 001285 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-08-27 | Overdue | 0 | INF | INF
8024 | 001285 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5208 | F | 131242-WST02-DR-S-5208-F | 2025-05-13 | ST608 drawings Connection Details | For Information | 2025-06-10 | 2025-08-07 | For Information | 2025-08-27 | NO | Overdue |  | 131242-WST02-DR-5208 | NA | "ST608 drawings Connection Details" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 86 | INF | 2025-05-13 | F | 001285 | 2025-05-13 | 00 | 1 | For Information | INF | 2025-08-27 | Overdue | 0 | INF | INF
8025 | 001286 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0009 | 0 | 131242-WSW41-PO-E-0009-0 | 2025-05-13 | Unpriced PO for Accessories for Lighting Protection (SkyPRO) | For information | 2025-06-10 | 2025-05-20 | For Information |  | YES | NA |  | 131242-WSW41-PO-0009 | NA | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" && "Unpriced PO for FRP Tank (Jizhou Zhongyi)" && "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 7 | INF | 2025-08-01 | 0 | 000609&&001286&&001508 | 2024-08-01, 2025-05-13, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
8026 | 001287 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0017 | 0 | 131242-WSW41-PO-M-0017-0 | 2025-05-13 | Unpriced LOA for Electric Hoist (Helmsion Engineering) | Rev 0: For Information Only. | 2025-06-10 | 2025-11-21 | For Information |  | YES | NA |  | 131242-WSW41-PO-0017 | NA | "Unpriced LOA for Electric Hoist (Helmsion Engineering) " && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " && "Unpriced PO for Raised Floor (Momentum Construction)" | 2025-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-02 | 192 | INF | 2025-09-09 | 0 | 001287&&001507&&001663 | 2025-05-13, 2025-07-22, 2025-09-09 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
8027 | 001288 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0078 | 0 | 131242-WSW41-QA-M-0078-0 | 2025-05-13 | Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) | NA | 2025-06-10 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0078 | NA | "Vendor Manufacturing Inspection Test Plan CPVC Manual Valves (Ball Valves, Check Valves & Butterfly Valves) " | 2025-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-02 | 118 | APP | 2025-05-13 | 0 | 001288 | 2025-05-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8028 | 001289 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0079 | 0 | 131242-WSW41-QA-M-0079-0 | 2025-05-13 | Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WSW41-QA-0079 | NA | "Vendor Manufacturing Inspection Test Plan Electric Actuated CPVC Ball Valve" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 80 | AWC | 2025-05-13 | 0 | 001289 | 2025-05-13 | 00 | 1 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
8029 | 001290 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0022 | 0 | 131242-WSW41-PC-W-0022-0 | 2025-05-13 | Payment Claim No.22 | Rev (0): Approved. Please refer to S.O. correspondence no. 350 date 16 May 2025. | 2025-06-10 | 2025-08-22 | Approved |  | YES | NA |  | 131242-WSW41-PC-0022 | NA | "Payment Claim No.22" | 2025-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-02 | 101 | APP | 2025-05-13 | 0 | 001290 | 2025-05-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8030 | 001291 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0024 | 0 | 131242-WSW41-RT-PM-0024-0 | 2025-05-13 | C4B Monthly Progress Report Number No.24 (04 25) | Approved with Comments No resubmission is required | 2025-06-10 | 2025-05-16 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0024 | NA | "C4B Monthly Progress Report Number No.24 (04 25)" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-02 | 3 | AWC | 2025-05-13 | 0 | 001291 | 2025-05-13 | 00 | 1 | Approved with Comments | AWC | 2025-06-05 | Overdue | 0 | AWC | AWC
8031 | 001292 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0035 | 0 | 131242-WSW41-QA-C-0035-0 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 | For information | 2025-06-10 | 2025-06-02 | For Information |  | YES | NA |  | 131242-WSW41-QA-0035 | NA | "Inspection and Test Plan for Cable Laying, Installation, Testing and Termination " && "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " && "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 20 | INF | 2025-07-08 | 0 | 000938&&001292&&001450 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | INF | INF
8032 | 001293 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0036 | 0 | 131242-WSW41-QA-C-0036-0 | 2025-05-13 | Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024 | For information | 2025-06-10 | 2025-06-02 | For Information |  | YES | NA |  | 131242-WSW41-QA-0036 | NA | "FAT/MDR Report for Side Manway (9 no;)" && "Issue for Information-Monthly reinforcement steel delivery records for Nov & Dec 2024" | 2025-01-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 20 | INF | 2025-05-13 | 0 | 000955&&001293 | 2025-01-07, 2025-05-13 | 00 | 2 | For Information | INF | 2025-06-20 | Overdue | 0 | INF | INF
8033 | 001294 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0037 | 0 | 131242-WSW41-QA-C-0037-0 | 2025-05-14 | Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025 | For information | 2025-06-11 | 2025-06-02 | For Information |  | YES | NA |  | 131242-WSW41-QA-0037 | NA | "Issue for Information-Monthly reinforcement steel delivery records for Jan to Apr 2025" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Centrifugal pumps (KSB) " | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-28 | 19 | INF | 2025-05-14 | 0 | 001029&&001294 | 2025-02-07, 2025-04-21, 2025-05-14 | 00, 01 | 3 | For Information | INF | 2025-06-20 | Overdue | 0 | INF | INF
8034 | 001295 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0030 | 0 | 131242-WSW41-SP-C-0030-0 | 2025-05-14 | Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) | For information | 2025-06-11 | 2025-06-02 | For Information |  | YES | NA |  | 131242-WSW41-SP-0030 | NA | "Reinforcement Bar Frequency Test Reports – Rebar Size (H10, H13, H16, H20, H25 & H32) " | 2025-05-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-03 | 19 | INF | 2025-05-14 | 0 | 001295 | 2025-05-14 | 00 | 1 | For Information | INF | 2025-06-20 | Overdue | 0 | INF | INF
8035 | 001296 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BS | 0001 | 0 | 131242-WST02-DS-BS-0001-0 | 2025-05-15 | Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories) | Approved with Comments | 2025-06-12 | 2025-05-25 | Approved with Comments | 2025-06-12 | NO | Overdue |  | 131242-WST02-DS-0001 | NA | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for ACMV Equipment" && "Epoxy Coating System" && "FRP TANK DATA SHEET" | 2023-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 10 | AWC | 2025-10-13 | 0 | 000016&&001236&&001296&&001740 | 2023-05-26, 2025-04-18, 2025-05-15, 2025-10-13 | 00 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
8036 | 001297 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BF | 0002 | 0 | 131242-WST02-DS-BF-0002-0 | 2025-05-15 | Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories) | Approved with Comments | 2025-06-12 | 2025-05-25 | Approved with Comments | 2025-06-12 | NO | Overdue |  | 131242-WST02-DS-0002 | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 10 | AWC | 2025-06-26 | 1 | 000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8037 | 001298 | 00 | Karthik | BS | NA | 131242 | WST02 | DS | BF | 0003 | 0 | 131242-WST02-DS-BF-0003-0 | 2025-05-15 | Data Sheets for Clean Gas System | Approved with Comments | 2025-06-12 | 2025-05-25 | Approved with Comments | 2025-06-12 | NO | Overdue |  | 131242-WST02-DS-0003 | NA | " Data Sheets for Clean Gas System" && "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 10 | AWC | 2025-06-06 | 2 | 000511&&001234&&001298 | 2024-06-05, 2025-04-17, 2025-05-15, 2025-06-06 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8038 | 001299 | 00 | Karthik | BS | NA | 131242 | WST02 | DR | BF | 5000 | 0 | 131242-WST02-DR-BF-5000-0 | 2025-05-15 | Typical installation drawing for PA & Fire Alarm System | Approved with Comments | 2025-06-12 | 2025-05-25 | Approved with Comments | 2025-06-12 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 10 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8039 | 001300 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0030 | 0 | 131242-WST02-QA-E-0030-0 | 2025-05-15 | Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-12 | 2025-06-09 | Approved with Comments | 2025-06-27 | NO | Overdue |  | 131242-WST02-QA-0030 | NA | "Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) " && "Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical" | 2025-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 25 | AWC | 2025-11-27 | 0 | 001300&&001469&&001869 | 2025-05-15, 2025-07-11, 2025-11-27 | 00 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
8040 | 001301 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | BS | 1398 | 0 | 131242-WST02-DS-BS-1398-0 | 2025-05-15 | Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance) | Rev 0: For Information | 2025-06-12 | 2025-06-23 | For Information |  | YES | NA |  | 131242-WST02-DS-1398 | NA | "Sample Board Submission for SB-05 Fire Alarm Field Devices Optica Smoke Detector, GIVRF Strobe Light, Kobishi MBA-6 Alaram Bell, Breakglass Callpoint (Pacific Reliance)" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-04 | 39 | INF | 2025-05-15 | 0 | 001301 | 2025-05-15 | 00 | 1 | For Information | INF | 2025-07-11 | Overdue | 0 | INF | INF
8041 | 001302 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0038 | 0 | 131242-WSW41-QA-C-0038-0 | 2025-05-18 | Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025 | For Information | 2025-06-13 | 2025-06-04 | For Information |  | YES | NA |  | 131242-WSW41-QA-0038 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Mar 2025" | 2025-05-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-07 | 17 | INF | 2025-05-18 | 0 | 001302 | 2025-05-18 | 00 | 1 | For Information | INF | 2025-06-24 | Overdue | 0 | INF | INF
8042 | 001303 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0031 | 0 | 131242-WSW41-QA-E-0031-0 | 2025-05-18 | FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN) | Rev 0: Approved | 2025-06-13 | 2025-05-29 | Approved |  | YES | NA |  | 131242-WSW41-QA-0031 | NA | "FAT report for LVSG Panels (Sunlight)" && "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " && "SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team)" | 2025-05-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-01 | 11 | APP | 2026-01-08 | 0 | 001267&&001303&&001439&&001940 | 2025-05-04, 2025-05-18, 2025-07-07, 2026-01-08 | 00 | 4 | Approved | APP |  |  | 0 | APP | APP
8043 | 001304 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0012 | 0 | 131242-WSW41-QA-I-0012-0 | 2025-05-18 | Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-13 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-QA-0012 | NA | "FAT Report for Power Cable, Control Cable, MV Cable" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 57 | AWC | 2026-01-28 | 0 | 000936&&001304&&001636&&001712 | 2024-12-31, 2025-05-18, 2025-09-30, 2026-01-28 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8044 | 001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7001 | A | 131242-WST02-DR-BF-7001-A | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 36 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8045 | 001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-BF-7002-A | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 36 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8046 | 001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7004 | A | 131242-WST02-DR-BF-7004-A | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 36 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8047 | 001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7005 | A | 131242-WST02-DR-BF-7005-A | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 36 | AWC | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2025-07-11 | Overdue | 0 | AWC | AWC
8048 | 001305 | 00 | Karthik | EICA | NA | 131242 | WST02 | DR | BF | 7104 | A | 131242-WST02-DR-BF-7104-A | 2025-05-18 | Panel GA & Wiring drawing for BS Systems | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-13 | 2025-06-23 | Approved with Comments | 2025-07-11 | NO | Overdue |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-01 | 36 | AWC | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8049 | 001306 | 00 | Karthik | BS | NA | 131242 | WST02 | DR | BF | 5000 | A | 131242-WST02-DR-BF-5000-A | 2025-05-18 | Typical Installation drawing For PA & Fire Alarm | Approved | 2025-06-13 | 2025-06-30 | Approved |  | YES | NA |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-01 | 43 | APP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | APP | APP
8050 | 001307 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | 9999 | A |  | 2025-05-18 | ST609 SSN-PR001 Fabrication Drawing and Model | For information. Subject mentioned 'model' however no models were included in the submittal. Also, all drawings are not as per TWRP standard, including file naming and title block. | 2025-06-13 | 2025-08-05 | For Information |  | YES | NA |  | Fabrication drawing-NA-NA-9999 | NA | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-05-18 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-06-07 | 79 | INF | 2025-06-12 | G | 001307&&001364&&001365&&001366 | 2025-05-18, 2025-06-12 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
8051 | 001308 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0017 | 0 | 131242-WSD11-CL-P-0017-0 | 2025-05-19 | G1 Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-07-07 | Approved with Comments | 2025-07-25 | YES | Resubmitted |  | 131242-WSD11-CL-0017 | NA | "G1 Booster Pump Hydraulics Calculation " | 2025-05-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-08 | 49 | AWC | 2025-08-25 | 1 | 001308 | 2025-05-19, 2025-08-25 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8052 | 001308 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0017 | 1 | 131242-WSD11-CL-P-0017-1 | 2025-08-25 | G1 Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-CL-0017 | NA | "G1 Booster Pump Hydraulics Calculation " | 2025-05-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-09-08 | 224 | PEN | 2025-08-25 | 1 | 001308 | 2025-05-19, 2025-08-25 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-10 |  | 0 | PEN | PEN
8053 | 001309 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0018 | 0 | 131242-WSD11-CL-P-0018-0 | 2025-05-19 | G2D Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-07-07 | Approved with Comments | 2025-07-25 | YES | Resubmitted |  | 131242-WSD11-CL-0018 | NA | "G2D Booster Pump Hydraulics Calculation " | 2025-05-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-08 | 49 | AWC | 2025-07-28 | 1 | 001309 | 2025-05-19, 2025-07-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8054 | 001309 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0018 | 1 | 131242-WSD11-CL-P-0018-1 | 2025-07-28 | G2D Booster Pump Hydraulics Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-15 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-CL-0018 | NA | "G2D Booster Pump Hydraulics Calculation " | 2025-05-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-08-11 | 252 | PEN | 2025-07-28 | 1 | 001309 | 2025-05-19, 2025-07-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-12 |  | 0 | PEN | PEN
8055 | 001310 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5711 | 0 | 131242-WST02-DS-M-5711-0 | 2025-05-19 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-16 | 2025-05-30 | Approved with Comments | 2025-06-19 | YES | Resubmitted |  | 131242-WST02-DS-5711 | NA | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" | 2025-05-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-08 | 11 | AWC | 2025-07-15 | 1 | 001310 | 2025-05-19, 2025-07-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8056 | 001310 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5711 | 1 | 131242-WST02-DS-M-5711-1 | 2025-07-15 | Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5711 | NA | "Data Sheet for Annamox Reactor 1/2/3/4 Aeration Flow Control valve" | 2025-05-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-07-29 | 265 | PEN | 2025-07-15 | 1 | 001310 | 2025-05-19, 2025-07-15 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-01 |  | 0 | PEN | PEN
8057 | 001311 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0004 | 0 | 131242-WSD11-RT-P-0004-0 | 2025-05-19 | H2S Dispersion Simulation And Risk Assessement Report | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-RT-0004 | NA | "H2S Dispersion Simulation And Risk Assessement Report" && "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" && "THP Harmonics Study Report" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-02 | 44 | AWC | 2025-09-03 | 1 | 000908&&001311&&001419 | 2024-12-16, 2025-05-19, 2025-07-01, 2025-07-28, 2025-09-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
8058 | 001311 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0004 | 1 | 131242-WSD11-RT-P-0004-1 | 2025-07-28 | H2S Dispersion Simulation And Risk Assessement Report | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-15 | 2025-09-24 | Approved with Comments | 2025-10-14 | NO | Overdue |  | 131242-WSD11-RT-0004 | NA | "H2S Dispersion Simulation And Risk Assessement Report" && "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" && "THP Harmonics Study Report" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 58 | AWC | 2025-09-03 | 1 | 000908&&001311&&001419 | 2024-12-16, 2025-05-19, 2025-07-01, 2025-07-28, 2025-09-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
8059 | 001312 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501 | A | 131242-WSD11-DR-S-3501-A | 2025-05-19 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WSD11-DR-3501 | NA | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" | 2025-05-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-08 | 52 | NAP | 2025-06-12 | F | 001312&&001363 | 2025-05-19, 2025-06-12 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
8060 | 001312 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501_Endorsed | - | 131242-WSD11-DR-S-3501_Endorsed-- | 2025-05-19 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-06-16 | 2025-07-10 | Not Approved | 2025-07-30 | YES | Resubmitted |  | 131242-WSD11-DR-3501_Endorsed | NA | "Revised Design of THP Steel Structure Plinths" | 2025-05-19 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-08 | 52 | NAP | 2025-05-19 | - | 001312 | 2025-05-19 | 00 | 1 | Not Approved | NAP | 2025-07-30 | Overdue | 0 | NAP | NAP
8061 | 001312 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | Comment reply | - | 131242-WSD11-DR-S-Comment reply- | 2025-08-22 | Revised Design of THP Steel Structure Plinths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-09-17 | For Information |  | YES | NA |  | 131242-WSD11-DR-Comment reply | NA | "Revised Design of THP Steel Structure Plinths" | 2025-08-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$) | 2025-09-11 | 26 | INF | 2025-08-22 | - | 001312 | 2025-08-22 | 01 | 1 | For Information | INF | 2025-10-07 | Overdue | 0 | INF | INF
8062 | 001313 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0013 | 0 | 131242-WSW41-QA-I-0013-0 | 2025-05-20 | Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-17 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-03 | 55 | AWC | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8063 | 001314 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 2008 | 0 | 131242-WSW41-VI-M-2008-0 | 2025-05-20 | Preliminary Design and Vendor Approval for Solenoid Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-17 | 2025-06-20 | Approved with Comments | 2025-07-10 | YES | Resubmitted |  | 131242-WSW41-VI-2008 | NA | "Preliminary Design and Vendor Approval for Solenoid Valve " | 2025-05-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-09 | 31 | AWC | 2025-07-28 | 1 | 001314 | 2025-05-20, 2025-07-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8064 | 001314 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | VI | M | 2008 | 1 | 131242-WSW41-VI-M-2008-1 | 2025-07-28 | Preliminary Design and Vendor Approval for Solenoid Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-15 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-VI-2008 | NA | "Preliminary Design and Vendor Approval for Solenoid Valve " | 2025-05-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-08-11 | 252 | PEN | 2025-07-28 | 1 | 001314 | 2025-05-20, 2025-07-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-12 |  | 0 | PEN | PEN
8065 | 001315 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0081 | 0 | 131242-WSD11-QA-M-0081-0 | 2025-05-23 | FAT Report for THP Sludge Cooler C Stage 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-20 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-QA-0081 | NA | "FAT Report for THP Sludge Cooler C Stage 2" | 2025-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-12 | 40 | AWC | 2025-12-02 | 1 | 001315 | 2025-05-23, 2025-12-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
8066 | 001315 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0081 | 1 | 131242-WSD11-QA-M-0081-1 | 2025-12-02 | FAT Report for THP Sludge Cooler C Stage 2 | Rev 1: Approved | 2025-12-22 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSD11-QA-0081 | NA | "FAT Report for THP Sludge Cooler C Stage 2" | 2025-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 21 | APP | 2025-12-02 | 1 | 001315 | 2025-05-23, 2025-12-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
8067 | 001316 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0074 | 0 | 131242-WSW41-QA-M-0074-0 | 2025-05-23 | Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson) | NA | 2025-06-20 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0074 | NA | "Vendor Manufacturing Inspection Test Plan and Test procedure for Lifting Equipment - Electric Hoist & Davit JIB crane (Helmson)" | 2025-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-12 | 102 | APP | 2025-05-23 | 0 | 001316 | 2025-05-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8068 | 001317 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | E | 0031 | 0 | 131242-WSD11-QA-E-0031-0 | 2025-05-23 | SAT Report for WSD11-MCC-0101A&B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-20 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WSD11-QA-0031 | NA | "Material and Test Certificate EN 10204-3.1 For Metallic Ball Valves compressed air system (OVS-HEATON) " && "SAT Report for WSD11-MCC-0101A&B" | 2024-12-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-06 | 61 | AWC | 2025-05-23 | 0 | 000930&&001317 | 2024-12-26, 2025-05-23 | 00 | 2 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
8069 | 001318 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0002 | 0 | 131242-WST02-OM-M-0002-0 | 2025-05-26 | O&M Manual for Aeration Blower | NA | 2025-06-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0002 | NA | "O&M Manual for Aeration Blower" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-09 | 315 | PEN | 2025-05-26 | 0 | 000511&&001318 | 2024-06-05, 2025-05-26 | 00 | 2 | Not Approved | NAP | 2025-07-11 |  | 0 | PEN | PEN
8070 | 001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5624 | A | 131242-WST02-DR-M-5624-A | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5624 | NA | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-15 | 120 | NAP | 2025-11-26 | B | 001319 | 2025-05-26, 2025-11-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
8071 | 001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5625 | A | 131242-WST02-DR-M-5625-A | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5625 | NA | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-15 | 120 | NAP | 2025-11-26 | B | 001319 | 2025-05-26, 2025-11-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
8072 | 001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5624 | 0 | 131242-WST02-DS-M-5624-0 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DS-5624 | NA | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-15 | 120 | NAP | 2025-05-26 | 0 | 001319 | 2025-05-26 | 00 | 1 | Not Approved | NAP | 2025-10-13 | Overdue | 0 | NAP | NAP
8073 | 001319 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5625 | 0 | 131242-WST02-DS-M-5625-0 | 2025-05-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-06-23 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DS-5625 | NA | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-15 | 120 | NAP | 2025-05-26 | 0 | 001319 | 2025-05-26 | 00 | 1 | Not Approved | NAP | 2025-10-13 | Overdue | 0 | NAP | NAP
8074 | 001319 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5624 | B | 131242-WST02-DR-M-5624-B | 2025-11-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-12-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5624 | NA | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-10 | 131 | PEN | 2025-11-26 | B | 001319 | 2025-05-26, 2025-11-26 | 00, 01 | 2 | Not Approved | NAP | 2026-01-13 |  | 0 | PEN | PEN
8075 | 001319 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5625 | B | 131242-WST02-DR-M-5625-B | 2025-11-26 | Data Sheet and Drawing for Davit Crane | Rev 0: Not approved - Revise and Resubmit | 2025-12-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5625 | NA | "Data Sheet and Drawing for Davit Crane" | 2025-05-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-10 | 131 | PEN | 2025-11-26 | B | 001319 | 2025-05-26, 2025-11-26 | 00, 01 | 2 | Not Approved | NAP | 2026-01-13 |  | 0 | PEN | PEN
8076 | 001320 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0083 | 0 | 131242-WSW41-QA-M-0083-0 | 2025-05-26 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-23 | 2025-07-31 | Approved with Comments | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-QA-0083 | NA | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " | 2025-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-15 | 66 | AWC | 2025-10-01 | 1 | 001320 | 2025-05-26, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8077 | 001320 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0083 | 1 | 131242-WSW41-QA-M-0083-1 | 2025-10-01 | Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0083 | NA | "Inspection and Test Plan for Metallic Butterfly Valve (Manual & Auto) " | 2025-05-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-10-15 | 187 | PEN | 2025-10-01 | 1 | 001320 | 2025-05-26, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2025-11-18 |  | 0 | PEN | PEN
8078 | 001321 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0032 | 0 | 131242-WSW41-MS-C-0032-0 | 2025-05-26 | MSRA and SWP for RC Sub & Super-Structural Work (TechGems) | Rev 0: Approved | 2025-06-23 | 2025-06-20 | Approved |  | YES | NA |  | 131242-WSW41-MS-0032 | NA | "MSRA and SWP for RC Sub & Super-Structural Work (TechGems)" | 2025-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-15 | 25 | APP | 2025-05-26 | 0 | 001321 | 2025-05-26 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8079 | 001322 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | MS | M | 0008 | 0 | 131242-WSD11-MS-M-0008-0 | 2025-05-27 | Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building | Rev 0: Approved | 2025-06-24 | 2025-08-11 | Approved |  | YES | NA |  | 131242-WSD11-MS-0008 | NA | "Method Statement for Installation of THP Cambi Equipments, Interconnecting Piping with THP Equipments and piping works inside biosolid building " | 2025-05-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-16 | 76 | APP | 2025-05-27 | 0 | 001322 | 2025-05-27 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8080 | 001323 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0084 | 0 | 131242-WST02-QA-M-0084-0 | 2025-05-28 | FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank) | Rev 0: Approved | 2025-06-25 | 2025-07-02 | Approved |  | YES | NA |  | 131242-WST02-QA-0084 | NA | "FAT Report for FRP tanks (Ferric Chloride Storage Tank & Sodium Hydroxide Storage Tank)" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-17 | 35 | APP | 2025-05-28 | 0 | 001323 | 2025-05-28 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8081 | 001324 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0085 | 0 | 131242-WSD11-QA-M-0085-0 | 2025-05-28 | FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps | Rev 0: Approved | 2025-06-25 | 2025-07-04 | Approved |  | YES | NA |  | 131242-WSD11-QA-0085 | NA | "FAT report for THP Train 1 & Train 2 Cooler Pumps, Digester Feed pumps" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-17 | 37 | APP | 2025-05-28 | 0 | 001324 | 2025-05-28 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8082 | 001325 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-A-0002-0 | 2025-05-28 | Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. | Approved | 2025-06-25 | 2025-06-04 | Approved |  | YES | NA |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-11 | 7 | APP | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | APP | APP
8083 | 001326 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | CL | A | 0002 | 0 | 131242-WST02-CL-A-0002-0 | 2025-05-28 | Siphonic System Schematic and Calculation | Approved | 2025-06-25 | 2025-07-09 | Approved |  | YES | NA |  | 131242-WST02-CL-0002 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-11 | 42 | APP | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
8084 | 001327 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0004 | 0 | 131242-WST02-VI-A-0004-0 | 2025-05-28 | Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. | Approved | 2025-06-25 | 2025-06-04 | Approved |  | YES | NA |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-11 | 7 | APP | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | APP | APP
8085 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1541 | A | 131242-WSD11-DR-IP-1541-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1541 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8086 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1542 | A | 131242-WSD11-DR-IP-1542-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1542 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8087 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1543 | A | 131242-WSD11-DR-IP-1543-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1543 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8088 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1544 | A | 131242-WSD11-DR-IP-1544-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1544 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8089 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1545 | A | 131242-WSD11-DR-IP-1545-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1545 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8090 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1546 | A | 131242-WSD11-DR-IP-1546-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1546 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8091 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1547 | A | 131242-WSD11-DR-IP-1547-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1547 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8092 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1548 | A | 131242-WSD11-DR-IP-1548-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1548 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8093 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1549 | A | 131242-WSD11-DR-IP-1549-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1549 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8094 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1550 | A | 131242-WSD11-DR-IP-1550-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1550 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8095 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1551 | A | 131242-WSD11-DR-IP-1551-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1551 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8096 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1552 | A | 131242-WSD11-DR-IP-1552-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1552 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8097 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1553 | A | 131242-WSD11-DR-IP-1553-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1553 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8098 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1554 | A | 131242-WSD11-DR-IP-1554-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1554 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8099 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1555 | A | 131242-WSD11-DR-IP-1555-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1555 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8100 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1556 | A | 131242-WSD11-DR-IP-1556-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1556 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8101 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1557 | A | 131242-WSD11-DR-IP-1557-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1557 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8102 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1091 | A | 131242-WSD11-DR-IP-1091-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1091 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8103 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1092 | A | 131242-WSD11-DR-IP-1092-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1092 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8104 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1093 | A | 131242-WSD11-DR-IP-1093-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1093 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8105 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1094 | A | 131242-WSD11-DR-IP-1094-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1094 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8106 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1095 | A | 131242-WSD11-DR-IP-1095-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1095 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8107 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1096 | A | 131242-WSD11-DR-IP-1096-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1096 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8108 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1097 | A | 131242-WSD11-DR-IP-1097-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1097 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8109 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1098 | A | 131242-WSD11-DR-IP-1098-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1098 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8110 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1099 | A | 131242-WSD11-DR-IP-1099-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1099 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8111 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1100 | A | 131242-WSD11-DR-IP-1100-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
8112 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1101 | A | 131242-WSD11-DR-IP-1101-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | NAP | NAP
8113 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1102 | A | 131242-WSD11-DR-IP-1102-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1102 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
8114 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1103 | A | 131242-WSD11-DR-IP-1103-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1103 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
8115 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1104 | A | 131242-WSD11-DR-IP-1104-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1104 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
8116 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1105 | A | 131242-WSD11-DR-IP-1105-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1105 | NA | "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-05-28 | A | 000236&&001328 | 2024-08-13, 2025-03-28, 2025-05-28 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8117 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1106 | A | 131242-WSD11-DR-IP-1106-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1106 | NA | "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-05-28 | A | 000236&&001328 | 2024-08-13, 2025-03-28, 2025-05-28 | 00, 01, 02 | 3 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8118 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1107 | A | 131242-WSD11-DR-IP-1107-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1107 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8119 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1108 | A | 131242-WSD11-DR-IP-1108-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1108 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8120 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1109 | A | 131242-WSD11-DR-IP-1109-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1109 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8121 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1110 | A | 131242-WSD11-DR-IP-1110-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1110 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8122 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1111 | A | 131242-WSD11-DR-IP-1111-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1111 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8123 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1112 | A | 131242-WSD11-DR-IP-1112-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1112 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8124 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1113 | A | 131242-WSD11-DR-IP-1113-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1113 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8125 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1114 | A | 131242-WSD11-DR-IP-1114-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1114 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8126 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1115 | A | 131242-WSD11-DR-IP-1115-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1115 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8127 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1116 | A | 131242-WSD11-DR-IP-1116-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1116 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8128 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1117 | A | 131242-WSD11-DR-IP-1117-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1117 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8129 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1118 | A | 131242-WSD11-DR-IP-1118-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1118 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8130 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1119 | A | 131242-WSD11-DR-IP-1119-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1119 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8131 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1120 | A | 131242-WSD11-DR-IP-1120-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1120 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8132 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1121 | A | 131242-WSD11-DR-IP-1121-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1121 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8133 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1122 | A | 131242-WSD11-DR-IP-1122-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1122 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8134 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1123 | A | 131242-WSD11-DR-IP-1123-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1123 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8135 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1124 | A | 131242-WSD11-DR-IP-1124-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1124 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8136 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1125 | A | 131242-WSD11-DR-IP-1125-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1125 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8137 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1031 | A | 131242-WSD11-DR-IP-1031-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1031 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8138 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1032 | A | 131242-WSD11-DR-IP-1032-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1032 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8139 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1033 | A | 131242-WSD11-DR-IP-1033-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1033 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8140 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1034 | A | 131242-WSD11-DR-IP-1034-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1034 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8141 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1035 | A | 131242-WSD11-DR-IP-1035-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1035 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8142 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1036 | A | 131242-WSD11-DR-IP-1036-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1036 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8143 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1037 | A | 131242-WSD11-DR-IP-1037-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1037 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8144 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1038 | A | 131242-WSD11-DR-IP-1038-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1038 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8145 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1039 | A | 131242-WSD11-DR-IP-1039-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1039 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8146 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1040 | A | 131242-WSD11-DR-IP-1040-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1040 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8147 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1041 | A | 131242-WSD11-DR-IP-1041-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1041 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8148 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1042 | A | 131242-WSD11-DR-IP-1042-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1042 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
8149 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1043 | A | 131242-WSD11-DR-IP-1043-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1043 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
8150 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1044 | A | 131242-WSD11-DR-IP-1044-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1044 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8151 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1045 | A | 131242-WSD11-DR-IP-1045-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1045 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8152 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1046 | A | 131242-WSD11-DR-IP-1046-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1046 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8153 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1047 | A | 131242-WSD11-DR-IP-1047-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1047 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8154 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1048 | A | 131242-WSD11-DR-IP-1048-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1048 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8155 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1049 | A | 131242-WSD11-DR-IP-1049-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1049 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8156 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1050 | A | 131242-WSD11-DR-IP-1050-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1050 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8157 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1051 | A | 131242-WSD11-DR-IP-1051-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1051 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8158 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1052 | A | 131242-WSD11-DR-IP-1052-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1052 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8159 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1053 | A | 131242-WSD11-DR-IP-1053-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1053 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8160 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1054 | A | 131242-WSD11-DR-IP-1054-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1054 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8161 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1055 | A | 131242-WSD11-DR-IP-1055-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1055 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8162 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1056 | A | 131242-WSD11-DR-IP-1056-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1056 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8163 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1057 | A | 131242-WSD11-DR-IP-1057-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1057 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8164 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1058 | A | 131242-WSD11-DR-IP-1058-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1058 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8165 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1059 | A | 131242-WSD11-DR-IP-1059-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1059 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8166 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1060 | A | 131242-WSD11-DR-IP-1060-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1060 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8167 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1061 | A | 131242-WSD11-DR-IP-1061-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1061 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8168 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1062 | A | 131242-WSD11-DR-IP-1062-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1062 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8169 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1063 | A | 131242-WSD11-DR-IP-1063-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1063 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8170 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1064 | A | 131242-WSD11-DR-IP-1064-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1064 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8171 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1065 | A | 131242-WSD11-DR-IP-1065-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1065 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-05-28 | A | 001328 | 2025-05-28 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
8172 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1001 | A | 131242-WSD11-DR-IP-1001-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
8173 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1002 | A | 131242-WSD11-DR-IP-1002-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
8174 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1003 | A | 131242-WSD11-DR-IP-1003-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
8175 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1004 | A | 131242-WSD11-DR-IP-1004-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
8176 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1005 | A | 131242-WSD11-DR-IP-1005-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1005 | NA | "THP Compartmentalization Lighting and Ventilation Fan" && "THP ICA GA & Wiring drawings" | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-10-28 | B | 001012&&001328 | 2025-01-26, 2025-05-28, 2025-10-28 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8177 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1006 | A | 131242-WSD11-DR-IP-1006-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1006 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8178 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1007 | A | 131242-WSD11-DR-IP-1007-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1007 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8179 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1008 | A | 131242-WSD11-DR-IP-1008-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1008 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8180 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1009 | A | 131242-WSD11-DR-IP-1009-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1009 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8181 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1010 | A | 131242-WSD11-DR-IP-1010-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1010 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8182 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1011 | A | 131242-WSD11-DR-IP-1011-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1011 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8183 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1012 | A | 131242-WSD11-DR-IP-1012-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1012 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8184 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1013 | A | 131242-WSD11-DR-IP-1013-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1013 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8185 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1014 | A | 131242-WSD11-DR-IP-1014-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1014 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8186 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1015 | A | 131242-WSD11-DR-IP-1015-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1015 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8187 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1016 | A | 131242-WSD11-DR-IP-1016-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1016 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8188 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1017 | A | 131242-WSD11-DR-IP-1017-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1017 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8189 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1018 | A | 131242-WSD11-DR-IP-1018-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1018 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8190 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1019 | A | 131242-WSD11-DR-IP-1019-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1019 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 97 | NAP | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8191 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1020 | A | 131242-WSD11-DR-IP-1020-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-1020 | NA | "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-10-28 | B | 000302&&001328 | 2024-10-18, 2025-05-28, 2025-10-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8192 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3001 | A | 131242-WSD11-DR-IP-3001-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8193 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3002 | A | 131242-WSD11-DR-IP-3002-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8194 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3003 | A | 131242-WSD11-DR-IP-3003-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8195 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3004 | A | 131242-WSD11-DR-IP-3004-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8196 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3005 | A | 131242-WSD11-DR-IP-3005-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8197 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3006 | A | 131242-WSD11-DR-IP-3006-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8198 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3007 | A | 131242-WSD11-DR-IP-3007-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8199 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3008 | A | 131242-WSD11-DR-IP-3008-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8200 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3009 | A | 131242-WSD11-DR-IP-3009-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8201 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3010 | A | 131242-WSD11-DR-IP-3010-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8202 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3011 | A | 131242-WSD11-DR-IP-3011-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8203 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3012 | A | 131242-WSD11-DR-IP-3012-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8204 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3013 | A | 131242-WSD11-DR-IP-3013-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8205 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3014 | A | 131242-WSD11-DR-IP-3014-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3014 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8206 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3015 | A | 131242-WSD11-DR-IP-3015-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8207 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3016 | A | 131242-WSD11-DR-IP-3016-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8208 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3017 | A | 131242-WSD11-DR-IP-3017-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3017 | NA | "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-11 | B | 001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8209 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3018 | A | 131242-WSD11-DR-IP-3018-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8210 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3019 | A | 131242-WSD11-DR-IP-3019-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8211 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3020 | A | 131242-WSD11-DR-IP-3020-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8212 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3021 | A | 131242-WSD11-DR-IP-3021-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8213 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3022 | A | 131242-WSD11-DR-IP-3022-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8214 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3023 | A | 131242-WSD11-DR-IP-3023-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8215 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3024 | A | 131242-WSD11-DR-IP-3024-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8216 | 001328 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 3025 | A | 131242-WSD11-DR-IP-3025-A | 2025-05-28 | THP ICA GA & Wiring drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-25 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-11 | 97 | NAP | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8217 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1001 | B | 131242-WSD11-DR-IP-1001-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
8218 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1002 | B | 131242-WSD11-DR-IP-1002-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
8219 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1003 | B | 131242-WSD11-DR-IP-1003-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
8220 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1004 | B | 131242-WSD11-DR-IP-1004-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | AWC | AWC
8221 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1005 | B | 131242-WSD11-DR-IP-1005-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1005 | NA | "THP Compartmentalization Lighting and Ventilation Fan" && "THP ICA GA & Wiring drawings" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001012&&001328 | 2025-01-26, 2025-05-28, 2025-10-28 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8222 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1006 | B | 131242-WSD11-DR-IP-1006-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1006 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8223 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1007 | B | 131242-WSD11-DR-IP-1007-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1007 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8224 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1008 | B | 131242-WSD11-DR-IP-1008-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1008 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8225 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1009 | B | 131242-WSD11-DR-IP-1009-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1009 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8226 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1010 | B | 131242-WSD11-DR-IP-1010-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1010 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8227 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1011 | B | 131242-WSD11-DR-IP-1011-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1011 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8228 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1012 | B | 131242-WSD11-DR-IP-1012-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1012 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8229 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1013 | B | 131242-WSD11-DR-IP-1013-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1013 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8230 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1014 | B | 131242-WSD11-DR-IP-1014-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1014 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8231 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1015 | B | 131242-WSD11-DR-IP-1015-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1015 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8232 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1016 | B | 131242-WSD11-DR-IP-1016-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1016 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8233 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1017 | B | 131242-WSD11-DR-IP-1017-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1017 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8234 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1018 | B | 131242-WSD11-DR-IP-1018-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1018 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8235 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1019 | B | 131242-WSD11-DR-IP-1019-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1019 | NA | "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 001328 | 2025-05-28, 2025-10-28 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8236 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1020 | B | 131242-WSD11-DR-IP-1020-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1020 | NA | "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" | 2024-10-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 000302&&001328 | 2024-10-18, 2025-05-28, 2025-10-28 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8237 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1021 | B | 131242-WSD11-DR-IP-1021-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1021 | NA | "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" | 2024-10-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 |  | AWC | 2025-10-28 | B | 000302&&001328 | 2024-10-18, 2025-10-28 | 01, 02 | 2 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8238 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1022 | B | 131242-WSD11-DR-IP-1022-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1022 | NA | "THP ICA GA & Wiring drawings" | 2025-10-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-17 |  | AWC | 2025-10-28 | B | 001328 | 2025-10-28 | 01 | 1 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8239 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1023 | B | 131242-WSD11-DR-IP-1023-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1023 | NA | "THP ICA GA & Wiring drawings" | 2025-10-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-17 |  | AWC | 2025-10-28 | B | 001328 | 2025-10-28 | 01 | 1 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8240 | 001328 | 01 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1024 | B | 131242-WSD11-DR-IP-1024-B | 2025-10-28 | THP ICA GA & Wiring drawings | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-10-12 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSD11-DR-1024 | NA | "THP ICA GA & Wiring drawings" | 2025-10-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-17 |  | AWC | 2025-10-28 | B | 001328 | 2025-10-28 | 01 | 1 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | AWC | AWC
8241 | 001329 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0023 | 0 | 131242-WSW41-PC-W-0023-0 | 2025-05-30 | Payment Claim No.23 | Rev(0): Approved. Please refer to S.O. correspondence no. 354 dated 30 May 2025. | 2025-06-27 | 2025-06-02 | Approved |  | YES | NA |  | 131242-WSW41-PC-0023 | NA | "Payment Claim No.23" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-19 | 3 | APP | 2025-05-30 | 0 | 001329 | 2025-05-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8242 | 001330 | 00 | Karthik | EICA | NA | 131242 | NA | NA | NA | 9999 | VOID |  | 2025-05-30 | THP ICA GA & Wiring Drawings | Rev 0: For Information. No resubmission required. | 2025-06-27 | 2025-12-05 | For Information |  | YES | NA | Dublicate submission. Please refer to 1328. | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema | 2025-06-19 | 189 | INF | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | INF | INF
8243 | 001331 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0013 | 0 | 131242-WST02-CD-I-0013-0 | 2025-05-30 | Electrical Signal List for SSN -LVSG-0101A/0101B | Not Approved - Revise and resubmit | 2025-06-27 | 2025-06-17 | Not Approved | 2025-07-07 | YES | Resubmitted |  | 131242-WST02-CD-0013 | NA | "Electrical Signal List for SSN -LVSG-0101A/0101B" && "Milestone 1.1 SSN Overall Area" | 2024-01-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 18 | NAP | 2025-06-09 | 1 | 000260&&001331 | 2024-01-05, 2025-05-30, 2025-06-09 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8244 | 001331 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0013 | 1 | 131242-WST02-CD-I-0013-1 | 2025-06-09 | Electrical Signal List for SSN -LVSG-0101A/0101B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-30 | Approved with Comments | 2025-07-18 | NO | Overdue |  | 131242-WST02-CD-0013 | NA | "Electrical Signal List for SSN -LVSG-0101A/0101B" && "Milestone 1.1 SSN Overall Area" | 2024-01-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-23 | 21 | AWC | 2025-06-09 | 1 | 000260&&001331 | 2024-01-05, 2025-05-30, 2025-06-09 | 00, 01 | 3 | Approved with Comments | AWC | 2025-07-18 | Overdue | 0 | AWC | AWC
8245 | 001332 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0086 | 0 | 131242-WSW41-QA-M-0086-0 | 2025-05-30 | FAT Report for CSEL piping DN 750mm (2nd batch) | NA | 2025-06-27 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0086 | NA | "FAT Report for CSEL piping DN 750mm (2nd batch)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-19 | 95 | APP | 2025-05-30 | 0 | 001332 | 2025-05-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
8246 | 001333 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7001 | A | 131242-WST02-DR-I-7001-A | 2025-05-30 | SSN Over All Network Archtecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-06-27 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 47 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8247 | 001333 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7010 | A | 131242-WST02-DR-I-7010-A | 2025-05-30 | SSN Over All Network Archtecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-06-27 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 47 | NAP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8248 | 001333 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7011 | A | 131242-WST02-DR-I-7011-A | 2025-05-30 | SSN Over All Network Archtecture Drawings | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-06-27 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 47 | NAP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8249 | 001333 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7001 | B | 131242-WST02-DR-II-7001-B | 2025-08-25 | SSN Over All Network Archtecture Drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 37 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8250 | 001333 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7010 | B | 131242-WST02-DR-II-7010-B | 2025-08-25 | SSN Over All Network Archtecture Drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 37 | NAP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8251 | 001333 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7011 | B | 131242-WST02-DR-II-7011-B | 2025-08-25 | SSN Over All Network Archtecture Drawings | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 37 | NAP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8252 | 001333 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7001 | C | 131242-WST02-DR-II-7001-C | 2025-10-27 | SSN Over All Network Archtecture Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-14 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 30 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8253 | 001333 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7010 | C | 131242-WST02-DR-II-7010-C | 2025-10-27 | SSN Over All Network Archtecture Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-14 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 30 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8254 | 001333 | 02 | Balaji | EICA | NA | 131242 | WST02 | DR | II | 7011 | C | 131242-WST02-DR-II-7011-C | 2025-10-27 | SSN Over All Network Archtecture Drawings | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-14 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 30 | AWC | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8255 | 001334 | 00 | Bryan | Mech | NA | 131242 | WSD11 | MS | C | 0007 | 0 | 131242-WSD11-MS-C-0007-0 | 2025-05-30 | Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard | Rev 0: Approved | 2025-06-27 | 2025-12-29 | Approved |  | YES | NA |  | 131242-WSD11-MS-0007 | NA | "Method Statement for Installation of THP Equipment and Piping at C4A Biosolid Building & THP Courtyard " && "Method Statement for Installation of THP Equipments and Piping at C4A Biosolid Building & THP Courtyard " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-13 | 213 | APP | 2025-05-30 | 0 | 001143&&001334 | 2025-03-21, 2025-04-10, 2025-05-30 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
8256 | 001335 | 00 | Jun | EICA | NA | 131242 | WSW41 | MM | E | 0003 | 0 | 131242-WSW41-MM-E-0003-0 | 2025-05-30 | Memo-Appointment of LEW Representatives | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-06-20 | Approved with Comments | 2025-07-10 | NO | Overdue |  | 131242-WSW41-MM-0003 | NA | "Memo-Appointment of LEW Representatives" | 2025-05-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-19 | 21 | AWC | 2025-05-30 | 0 | 001335 | 2025-05-30 | 00 | 1 | Approved with Comments | AWC | 2025-07-10 | Overdue | 0 | AWC | AWC
8257 | 001336 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0014 | 0 | 131242-WSW41-QA-I-0014-0 | 2025-05-30 | FAT Report for Radar Level Transmitter 1st Batch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-06-27 | 2025-07-14 | Not Approved | 2025-08-01 | YES | Resubmitted |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 45 | NAP | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8258 | 001336 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0014 | 1 | 131242-WSW41-QA-I-0014-1 | 2025-07-22 | FAT Report for Radar Level Transmitter 1st Batch | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-08-06 | Approved with Comments | 2025-08-26 | NO | Overdue |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 15 | AWC | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8259 | 001337 | 00 | K Balaji | Const; | NA | 131242 | WSW41 | MS | M | 0008 | 0 | 131242-WSW41-MS-M-0008-0 | 2025-05-30 | Method Statement & Risk Assessment for Piping Installation at SWPR | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-27 | 2025-08-11 | Approved with Comments | 2025-08-29 | YES | Resubmitted |  | 131242-WSW41-MS-0008 | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" && "MSRA, SWP for Time Lapse Camera Steel Pole Erection" && "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2024-03-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 73 | AWC | 2025-12-05 | 1 | 000347&&001046&&001337 | 2024-03-08, 2025-02-17, 2025-05-30, 2025-12-05 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8260 | 001337 | 01 | K Balaji | Const; | NA | 131242 | WSW41 | MS | M | 0008 | 1 | 131242-WSW41-MS-M-0008-1 | 2025-12-05 | Method Statement & Risk Assessment for Piping Installation at SWPR | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-25 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WSW41-MS-0008 | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" && "MSRA, SWP for Time Lapse Camera Steel Pole Erection" && "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2024-03-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 24 | AWC | 2025-12-05 | 1 | 000347&&001046&&001337 | 2024-03-08, 2025-02-17, 2025-05-30, 2025-12-05 | 00, 01 | 4 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
8261 | 001338 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0015 | 0 | 131242-WST02-QA-I-0015-0 | 2025-06-03 | Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WST02-QA-0015 | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 43 | NAP | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8262 | 001338 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0015 | 1 | 131242-WST02-QA-I-0015-1 | 2025-08-21 | Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-10 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WST02-QA-0015 | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 12 | AWC | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8263 | 001339 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0018 | 0 | 131242-WSW41-QA-I-0018-0 | 2025-06-03 | Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 44 | AWC | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8264 | 001340 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0016 | 0 | 131242-WSW41-QA-I-0016-0 | 2025-06-03 | Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-07-20 | Not Approved | 2025-08-07 | YES | Resubmitted |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 47 | NAP | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8265 | 001340 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0016 | 1 | 131242-WSW41-QA-I-0016-1 | 2025-08-25 | Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 8 | AWC | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8266 | 001341 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0076 | 0 | 131242-WSW41-QA-M-0076-0 | 2025-06-03 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2025-07-01 | 2025-08-01 | Approved with Comments | 2025-08-21 | YES | Resubmitted |  | 131242-WSW41-QA-0076 | NA | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | 2025-06-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-23 | 59 | AWC | 2025-09-17 | 2 | 001341 | 2025-06-03, 2025-08-27, 2025-09-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8267 | 001341 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0076 | 1 | 131242-WSW41-QA-M-0076-1 | 2025-08-27 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2025-09-16 | 2025-09-02 | Approved with Comments | 2025-09-22 | YES | Resubmitted |  | 131242-WSW41-QA-0076 | NA | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | 2025-06-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 6 | AWC | 2025-09-17 | 2 | 001341 | 2025-06-03, 2025-08-27, 2025-09-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8268 | 001341 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0076 | 2 | 131242-WSW41-QA-M-0076-2 | 2025-09-17 | Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger) | Rev 2: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-10-07 | 2025-12-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0076 | NA | "Vendor Manufacturing Inspection Test Plan and test procedure for Air flow control valve (Effectiv/Emile Egger)" | 2025-06-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-01 | 97 | AWC | 2025-09-17 | 2 | 001341 | 2025-06-03, 2025-08-27, 2025-09-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-01-12 | Overdue | 0 | AWC | AWC
8269 | 001342 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0017 | 0 | 131242-WSW41-QA-I-0017-0 | 2025-06-03 | FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-01 | 2025-06-20 | Approved with Comments | 2025-07-10 | NO | Overdue |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-17 | 17 | AWC | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8270 | 001343 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0019 | 0 | 131242-WSW41-QA-I-0019-0 | 2025-06-04 | Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-02 | 2025-08-04 | Approved with Comments | 2025-08-22 | NO | Overdue |  | 131242-WSW41-QA-0019 | NA | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" && "Monthly Concrete Cube Records for Structural works for August 2024" && "T&C Check List " && "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-18 | 61 | AWC | 2025-09-30 | 0 | 000738&&000814&&001343&&001712 | 2024-09-28, 2024-11-14, 2025-06-04, 2025-09-30 | 00 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8271 | 001344 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | M | 0072 | 0 | 131242-WSW41-QA-M-0072-0 | 2025-06-04 | Vendor Manufacturing Inspection Test Plan for Parabolic Screen | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-QA-0072 | NA | "FAT Report for FOIP Panel SSN & THP (FOX)" && "Vendor Manufacturing Inspection Test Plan for Parabolic Screen" | 2025-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-24 | 40 | AWC | 2026-01-30 | 0 | 001344&&001997 | 2025-06-04, 2026-01-30 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8272 | 001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0011 | 0 | 131242-WST02-OM-M-0011-0 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0011 | NA | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-06-26 | 304 | PEN | 2025-06-06 | 0 | 001345 | 2025-06-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-24 |  | 0 | PEN | PEN
8273 | 001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0012 | 0 | 131242-WST02-OM-M-0012-0 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0012 | NA | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-06-26 | 304 | PEN | 2025-06-06 | 0 | 001345 | 2025-06-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-24 |  | 0 | PEN | PEN
8274 | 001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0013 | 0 | 131242-WST02-OM-M-0013-0 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0013 | NA | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-06-26 | 304 | PEN | 2025-06-06 | 0 | 001345 | 2025-06-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-24 |  | 0 | PEN | PEN
8275 | 001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0014 | 0 | 131242-WST02-OM-M-0014-0 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0014 | NA | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-06-26 | 304 | PEN | 2025-06-06 | 0 | 001345 | 2025-06-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-24 |  | 0 | PEN | PEN
8276 | 001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0015 | 0 | 131242-WST02-OM-M-0015-0 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0015 | NA | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-06-26 | 304 | PEN | 2025-06-06 | 0 | 001345 | 2025-06-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-24 |  | 0 | PEN | PEN
8277 | 001345 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0016 | 0 | 131242-WST02-OM-M-0016-0 | 2025-06-06 | Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump | NA | 2025-07-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0016 | NA | "Operation and Maintenance Manual for Anammox Reactor NAOH Dosing Pump, Antifoam Dosing Pump, Antiscalant Dosing Pump, Equalization Tank NaOH Dosing Pump, Micronutrients Dosing Pump, FeCl3 Dosing Pump" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-06-26 | 304 | PEN | 2025-06-06 | 0 | 001345 | 2025-06-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-24 |  | 0 | PEN | PEN
8278 | 001346 | 00 | Yibo | Mech | NA | 131242 | WST02 | CL | M | 5624 | 0 | 131242-WST02-CL-M-5624-0 | 2025-06-06 | Crane Calculation for Davit Crane 1and 2 | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2026-02-27 | Not Approved | 2026-03-19 | NO | NA |  | 131242-WST02-CL-5624 | NA | "Crane Calculation for Davit Crane 1and 2" | 2025-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 266 | NAP | 2025-06-06 | 0 | 001346 | 2025-06-06 | 00 | 1 | Not Approved | NAP | 2026-03-19 | Overdue | 0 | NAP | NAP
8279 | 001346 | 00 | Yibo | Mech | NA | 131242 | WST02 | CL | M | 5625 | 0 | 131242-WST02-CL-M-5625-0 | 2025-06-06 | Crane Calculation for Davit Crane 1and 2 | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-04 | 2026-02-27 | Not Approved | 2026-03-19 | NO | NA |  | 131242-WST02-CL-5625 | NA | "Crane Calculation for Davit Crane 1and 2" | 2025-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 266 | NAP | 2025-06-06 | 0 | 001346 | 2025-06-06 | 00 | 1 | Not Approved | NAP | 2026-03-19 | Overdue | 0 | NAP | NAP
8280 | 001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5620 | A | 131242-WST02-DR-M-5620-A | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-5620 | NA | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 83 | AWC | 2025-09-29 | B | 001347 | 2025-06-06, 2025-09-29 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8281 | 001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5622 | A | 131242-WST02-DR-M-5622-A | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-5622 | NA | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 83 | AWC | 2025-09-29 | B | 001347 | 2025-06-06, 2025-09-29 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8282 | 001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5620 | 0 | 131242-WST02-DS-M-5620-0 | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DS-5620 | NA | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 83 | AWC | 2025-06-06 | 0 | 001347 | 2025-06-06 | 00 | 1 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
8283 | 001347 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5622 | 0 | 131242-WST02-DS-M-5622-0 | 2025-06-06 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DS-5622 | NA | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 83 | AWC | 2025-06-06 | 0 | 001347 | 2025-06-06 | 00 | 1 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
8284 | 001347 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5620 | B | 131242-WST02-DR-M-5620-B | 2025-09-29 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-10-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5620 | NA | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 189 | PEN | 2025-09-29 | B | 001347 | 2025-06-06, 2025-09-29 | 00, 01 | 2 | Approved with Comments | AWC | 2025-11-14 |  | 0 | PEN | PEN
8285 | 001347 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5622 | B | 131242-WST02-DR-M-5622-B | 2025-09-29 | Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2 | NA | 2025-10-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5622 | NA | "Data Sheet and GA Drawing for Lifting Equipment - Monorail Hoist 1 & 2" | 2025-06-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 189 | PEN | 2025-09-29 | B | 001347 | 2025-06-06, 2025-09-29 | 00, 01 | 2 | Approved with Comments | AWC | 2025-11-14 |  | 0 | PEN | PEN
8286 | 001348 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | C | 0022 | 0 | 131242-WST02-QA-C-0022-0 | 2025-06-06 | Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-07-28 | Approved with Comments | 2025-08-15 | NO | Overdue |  | 131242-WST02-QA-0022 | NA | "Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) " && "Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector" | 2025-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 52 | AWC | 2025-06-23 | 0 | 001348&&001395 | 2025-06-06, 2025-06-23 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8287 | 001349 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0060 | 0 | 131242-WST02-CD-IM-0060-0 | 2025-06-09 | Submission of BIM Coordination VCM Model (May 2025) | For Information | 2025-07-07 | 2025-06-30 | For Information |  | YES | NA |  | 131242-WST02-CD-0060 | NA | "Submission of BIM Coordination VCM Model (May 2025) " | 2025-06-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-29 | 21 | INF | 2025-06-09 | 0 | 001349 | 2025-06-09 | 00 | 1 | For Information | INF | 2025-07-18 | Overdue | 0 | INF | INF
8288 | 001350 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | CD | I | 0001 | 0 | 131242-WSW41-CD-I-0001-0 | 2025-06-10 | Electrical Signal List for MCC - TYPICAL | NA | 2025-07-08 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-CD-0001 | NA | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " && "Submission Of BIM Coordination VCM Model (July – 2023)" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-24 | 300 | PEN | 2025-07-25 | 1 | 000066&&001350&&001467 | 2023-08-08, 2025-06-10, 2025-07-25 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
8289 | 001351 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5101 | A | 131242-WSD11-DR-I-5101-A | 2025-06-10 | Hookup Drawing for PIT at Air Receiver | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5101 | NA | "Hookup Drawing for PIT at Air Receiver " && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2025-06-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 182 | AWC | 2026-01-12 | C | 001351&&001944 | 2025-06-10, 2026-01-12 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
8290 | 001352 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5102 | A | 131242-WSD11-DR-I-5102-A | 2025-06-10 | Hook up Drawing for PDSH - CAS | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5102 | NA | "Hook up Drawing for PDSH - CAS" && "Hook-up drawing for PDSH for CAS (THP)" | 2025-06-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 182 | AWC | 2025-12-16 | B | 001352&&001904 | 2025-06-10, 2025-12-16 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8291 | 001353 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0025 | 0 | 131242-WST02-VI-I-0025-0 | 2025-06-10 | Vendor Approval of SSN Package - Magnetic Level Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-08 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-VI-0025 | NA | "Vendor Approval of SSN Package - Magnetic Level Gauge" | 2025-06-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 105 | NAP | 2025-11-05 | 1 | 001353 | 2025-06-10, 2025-11-05 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8292 | 001353 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0025 | 1 | 131242-WST02-VI-I-0025-1 | 2025-11-05 | Vendor Approval of SSN Package - Magnetic Level Gauge | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-VI-0025 | NA | "Vendor Approval of SSN Package - Magnetic Level Gauge" | 2025-06-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-19 | 21 | AWC | 2025-11-05 | 1 | 001353 | 2025-06-10, 2025-11-05 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-16 | Overdue | 0 | AWC | AWC
8293 | 001354 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0061 | 0 | 131242-WSW41-LT-PM-0061-0 | 2025-06-11 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 2024 to April 2025 | For Information. Please refer to S.O. correspondence no. 380 dated 30 July 2025. | 2025-07-09 | 2025-08-25 | For Information |  | YES | NA |  | 131242-WSW41-LT-0061 | NA | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 2024 to April 2025" | 2025-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-01 | 75 | INF | 2025-06-11 | 0 | 001354 | 2025-06-11 | 00 | 1 | For Information | INF | 2025-09-12 | Overdue | 0 | INF | INF
8294 | 001355 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0025 | 0 | 131242-WSW41-RT-PM-0025-0 | 2025-06-12 | C4B Monthly Progress Report Number No.25 (05 25) | Approved with comments which to be addressed in the next MPR submission. | 2025-07-10 | 2025-07-20 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0025 | NA | "C4B Monthly Progress Report Number No.25 (05 25)" | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-02 | 38 | AWC | 2025-06-12 | 0 | 001355 | 2025-06-12 | 00 | 1 | Approved with Comments | AWC | 2025-08-07 | Overdue | 0 | AWC | AWC
8295 | 001356 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | A | 131242-WST02-SD-A-3014-A | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | Not Approved | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-SD-3014 | NA | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 20 | NAP | 2025-08-27 | D | 001050&&001356 | 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8296 | 001356 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3015 | A | 131242-WST02-SD-A-3015-A | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | Not Approved | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-SD-3015 | NA | "Shop Drawings for Siphonic System (Fast Flow)" && "Waterproofing Shop Drawing Submission " | 2025-03-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 20 | NAP | 2025-06-12 | A | 001114&&001356 | 2025-03-11, 2025-06-12 | 00 | 2 | Not Approved | NAP | 2025-07-22 | Overdue | 0 | NAP | NAP
8297 | 001356 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | A | 131242-WST02-SD-A-1014-A | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | Not Approved | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-SD-1014 | NA | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 20 | NAP | 2025-08-27 | C | 001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8298 | 001356 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | B | 131242-WST02-SD-A-3014-B | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-02 | 2025-07-11 | Not Approved | 2025-07-31 | YES | Resubmitted |  | 131242-WST02-SD-3014 | NA | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 29 | NAP | 2025-08-27 | D | 001050&&001356 | 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8299 | 001356 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | A | 131242-WST02-SD-A-3016-A | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-11 | Not Approved | 2025-07-31 | YES | Resubmitted |  | 131242-WST02-SD-3016 | NA | "Raised Floor Shop Drawings submission (Momentum)" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 29 | NAP | 2025-08-27 | C | 001356&&001367 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8300 | 001356 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3017 | A | 131242-WST02-SD-A-3017-A | 2025-06-12 | Waterproofing Shop Drawing Submission | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-11 | Not Approved | 2025-07-31 | YES | Resubmitted |  | 131242-WST02-SD-3017 | NA | "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 29 | NAP | 2025-08-27 | C | 001356&&001530 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8301 | 001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | B | 131242-WST02-SD-A-1014-B | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-04 | Approved with Comments | 2025-08-22 | YES | Resubmitted |  | 131242-WST02-SD-1014 | NA | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 5 | AWC | 2025-08-27 | C | 001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8302 | 001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | C | 131242-WST02-SD-A-3014-C | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-27 | 2025-08-04 | Approved with Comments | 2025-08-22 | YES | Resubmitted |  | 131242-WST02-SD-3014 | NA | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 5 | AWC | 2025-08-27 | D | 001050&&001356 | 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8303 | 001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | B | 131242-WST02-SD-A-3016-B | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-04 | Approved with Comments | 2025-08-22 | YES | Resubmitted |  | 131242-WST02-SD-3016 | NA | "Raised Floor Shop Drawings submission (Momentum)" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 5 | AWC | 2025-08-27 | C | 001356&&001367 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8304 | 001356 | 02 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3017 | B | 131242-WST02-SD-A-3017-B | 2025-07-30 | Waterproofing Shop Drawing Submission | Rev 2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-04 | Approved with Comments | 2025-08-22 | YES | Resubmitted |  | 131242-WST02-SD-3017 | NA | "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 5 | AWC | 2025-08-27 | C | 001356&&001530 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8305 | 001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1014 | C | 131242-WST02-SD-A-1014-C | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-SD-1014 | NA | "Shop Drawing for Raised Floor Layout Plan & Detail for 1st & 2nd Storey" && "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 40 | AWC | 2025-08-27 | C | 001026&&001050&&001356 | 2025-02-07, 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 02, 03 | 5 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
8306 | 001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3014 | D | 131242-WST02-SD-A-3014-D | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-SD-3014 | NA | "Shop Drawings for SSN Electrical Building Roof Waterproofing" && "Waterproofing Shop Drawing Submission " | 2025-02-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 40 | AWC | 2025-08-27 | D | 001050&&001356 | 2025-02-18, 2025-06-12, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
8307 | 001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | C | 131242-WST02-SD-A-3016-C | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-SD-3016 | NA | "Raised Floor Shop Drawings submission (Momentum)" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 40 | AWC | 2025-08-27 | C | 001356&&001367 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
8308 | 001356 | 03 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3017 | C | 131242-WST02-SD-A-3017-C | 2025-08-27 | Waterproofing Shop Drawing Submission | Rev 3: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-SD-3017 | NA | "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 40 | AWC | 2025-08-27 | C | 001356&&001530 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
8309 | 001357 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0018 | 0 | 131242-WSW41-QA-I-0018-0 | 2025-06-12 | Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-10 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 32 | AWC | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8310 | 001358 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0087 | 0 | 131242-WSW41-QA-M-0087-0 | 2025-06-12 | FAT Report for Spray Nozzles | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-10 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WSW41-QA-0087 | NA | "FAT Report for Spray Nozzles" | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 41 | AWC | 2025-06-12 | 0 | 001358 | 2025-06-12 | 00 | 1 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
8311 | 001359 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | VI | B | 0004 | 0 | 131242-WST02-VI-B-0004-0 | 2025-06-12 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-14 | Not Approved | 2025-08-01 | YES | Resubmitted |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 32 | NAP | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | NAP | NAP
8312 | 001359 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | VI | B | 0004 | 1 | 131242-WST02-VI-B-0004-1 | 2025-07-22 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | R1: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-11 | 2025-10-10 | Not Approved | 2025-10-30 | YES | Resubmitted |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 80 | NAP | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | NAP | NAP
8313 | 001359 | 02 | Dhanapal | QAQC | NA | 131242 | WST02 | VI | B | 0004 | 2 | 131242-WST02-VI-B-0004-2 | 2025-11-13 | Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV | R2: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-03 | 2025-12-29 | Not Approved | 2026-01-16 | NO | Overdue |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-27 | 46 | NAP | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP | 2026-01-16 | Overdue | 0 | NAP | NAP
8314 | 001360 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | BS | 1399 | 0 | 131242-WST02-DS-BS-1399-0 | 2025-06-12 | Sample Board Submission for ACMV Sample Materials (Pho Meng Engineering) | R0: Approve with comments. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-08 | Approved with Comments | 2025-07-28 | NO | Overdue |  | 131242-WST02-DS-1399 | NA | "Sample Board Submission for ACMV Sample Materials (Pho Meng Engineering) " | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 26 | AWC | 2025-06-12 | 0 | 001360 | 2025-06-12 | 00 | 1 | Approved with Comments | AWC | 2025-07-28 | Overdue | 0 | AWC | AWC
8315 | 001361 | 00 | Dhanapal | QAQC | NA | 131424 | WSD11 | QA | I | 0020 | 0 | 131424-WSD11-QA-I-0020-0 | 2025-06-12 | FAT report for THP Train 1 (Pulper module, Reactor 1 to 4 module, Upper platform module) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-12-23 | Approved with Comments | 2026-01-12 | NO | Overdue |  | 131424-WSD11-QA-0020 | NA | "FAT report for THP Train 1 (Pulper module, Reactor 1 to 4 module, Upper platform module)" | 2025-06-12 | NO | YES | Project_Code not in project_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 194 | AWC | 2025-06-12 | 0 | 001361 | 2025-06-12 | 00 | 1 | Approved with Comments | AWC | 2026-01-12 | Overdue | 0 | AWC | AWC
8316 | 001362 | 00 | Dhanapal | QAQC | NA | 131424 | WSD11 | QA | I | 0021 | 0 | 131424-WSD11-QA-I-0021-0 | 2025-06-12 | FAT report for THP Train 2 (Pulper module, Upper platform module) (ICA) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-07-10 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131424-WSD11-QA-0021 | NA | "FAT report for THP Train 2 (Pulper module, Upper platform module) (ICA)" | 2025-06-12 | NO | YES | Project_Code not in project_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 180 | NAP | 2025-06-12 | 0 | 001362 | 2025-06-12 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
8317 | 001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1500 | F | 131242-WSD11-DR-S-1500-F | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | Not Approved | 2025-08-07 | YES | Resubmitted |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 38 | NAP | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8318 | 001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1501 | F | 131242-WSD11-DR-S-1501-F | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | Not Approved | 2025-08-07 | YES | Resubmitted |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 38 | NAP | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8319 | 001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3500 | F | 131242-WSD11-DR-S-3500-F | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | Not Approved | 2025-08-07 | YES | Resubmitted |  | 131242-WSD11-DR-3500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 38 | NAP | 2025-09-24 | G | 000844&&000845&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8320 | 001363 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3501 | F | 131242-WSD11-DR-S-3501-F | 2025-06-12 | Revised Design of THP Steel Structure Plinths (Rev F) | NA | 2025-07-10 | 2025-07-20 | Not Approved | 2025-08-07 | YES | Resubmitted |  | 131242-WSD11-DR-3501 | NA | "Revised Design of THP Steel Structure Plinths" && "Revised Design of THP Steel Structure Plinths (Rev F)" | 2025-05-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 38 | NAP | 2025-06-12 | F | 001312&&001363 | 2025-05-19, 2025-06-12 | 00 | 2 | Not Approved | NAP | 2025-08-07 | Overdue | 0 | NAP | NAP
8321 | 001363 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1500 | G | 131242-WSD11-DR-S-1500-G | 2025-08-22 | Revised Design of THP Steel Structure Plinths (Rev G) | NA | 2025-09-11 | 2025-09-24 | Approved with Comments | 2025-10-14 | YES | Resubmitted |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 33 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8322 | 001363 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1501 | G | 131242-WSD11-DR-S-1501-G | 2025-08-22 | Revised Design of THP Steel Structure Plinths (Rev G) | NA | 2025-09-19 | 2025-09-24 | Approved with Comments | 2025-10-14 | NO | Overdue |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 33 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8323 | 001363 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3500 | G | 131242-WSD11-DR-S-3500-G | 2025-08-22 | Revised Design of THP Steel Structure Plinths (Rev G) | NA | 2025-09-19 | 2025-09-24 | Approved with Comments | 2025-10-14 | NO | Overdue |  | 131242-WSD11-DR-3500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 33 | AWC | 2025-09-24 | G | 000844&&000845&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8324 | 001363 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1500 | G | 131242-WSD11-DR-S-1500-G | 2025-09-24 | Revised Design of THP Steel Structure Plinths (Rev G) | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-14 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-08 | 110 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
8325 | 001363 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1501 | G | 131242-WSD11-DR-S-1501-G | 2025-09-24 | Revised Design of THP Steel Structure Plinths (Rev G) | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-14 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-08 | 110 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
8326 | 001363 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3500 | G | 131242-WSD11-DR-S-3500-G | 2025-09-24 | Revised Design of THP Steel Structure Plinths (Rev G) | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-14 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WSD11-DR-3500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" | 2024-11-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-08 | 110 | AWC | 2025-09-24 | G | 000844&&000845&&001363 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-08-22, 2025-09-24 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
8327 | 001364 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | 9999 | G |  | 2025-06-12 | ST609-SSN-PR002 PE Endorsed Fabrication Drawings | NA | 2025-07-10 | 2025-09-26 | For Information |  | YES | NA |  | Fabrication drawing-NA-NA-9999 | NA | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-05-18 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-06-26 | 106 | INF | 2025-06-12 | G | 001307&&001364&&001365&&001366 | 2025-05-18, 2025-06-12 | 00 | 4 | For Information | INF | 2025-10-16 | Overdue | 0 | INF | INF
8328 | 001365 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | 9999 | G |  | 2025-06-12 | ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings | NA | 2025-07-10 | 2025-09-26 | For Information |  | YES | NA |  | Fabrication drawing-NA-NA-9999 | NA | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-05-18 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-06-26 | 106 | INF | 2025-06-12 | G | 001307&&001364&&001365&&001366 | 2025-05-18, 2025-06-12 | 00 | 4 | For Information | INF | 2025-10-16 | Overdue | 0 | INF | INF
8329 | 001366 | 00 | Aaron | CSA | NA | Fabrication drawing | NA | NA | NA | 9999 | G |  | 2025-06-12 | ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings | NA | 2025-07-10 | 2025-09-26 | For Information |  | YES | NA |  | Fabrication drawing-NA-NA-9999 | NA | " ST609 SSN-PR001 Fabrication Drawing and Model" && "ST609-SSN-PR 04&05 PE Endorsed Fabrication Drawings " && "ST609-SSN-PR002 PE Endorsed Fabrication Drawings " && "ST619-THP-PIPE RACK-01 PE Endorsed Fabrication Drawings " | 2025-05-18 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-06-26 | 106 | INF | 2025-06-12 | G | 001307&&001364&&001365&&001366 | 2025-05-18, 2025-06-12 | 00 | 4 | For Information | INF | 2025-10-16 | Overdue | 0 | INF | INF
8330 | 001367 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1016 | A | 131242-WST02-SD-A-1016-A | 2025-06-12 | Raised Floor Shop Drawings submission (Momentum) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | Not Approved | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-SD-1016 | NA | "Raised Floor Shop Drawings submission (Momentum)" | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 20 | NAP | 2025-07-24 | B | 001367 | 2025-06-12, 2025-07-24 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8331 | 001367 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | A | 131242-WST02-SD-A-3016-A | 2025-06-12 | Raised Floor Shop Drawings submission (Momentum) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-10 | 2025-07-02 | Not Approved |  | YES | Resubmitted |  | 131242-WST02-SD-3016 | NA | "Raised Floor Shop Drawings submission (Momentum)" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 20 | NAP | 2025-08-27 | C | 001356&&001367 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8332 | 001367 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 1016 | B | 131242-WST02-SD-A-1016-B | 2025-07-24 | Raised Floor Shop Drawings submission (Momentum) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-13 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WST02-SD-1016 | NA | "Raised Floor Shop Drawings submission (Momentum)" | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 8 | AWC | 2025-07-24 | B | 001367 | 2025-06-12, 2025-07-24 | 00, 01 | 2 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
8333 | 001367 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 3016 | B | 131242-WST02-SD-A-3016-B | 2025-07-24 | Raised Floor Shop Drawings submission (Momentum) | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-13 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WST02-SD-3016 | NA | "Raised Floor Shop Drawings submission (Momentum)" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 8 | AWC | 2025-08-27 | C | 001356&&001367 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8334 | 001368 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0016 | 0 | 131242-WST02-VI-E-0016-0 | 2025-06-12 | Vendor Approval for Active Harmonic Filter (DANFOSS) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-07-04 | Approved with Comments | 2025-07-24 | YES | Resubmitted |  | 131242-WST02-VI-0016 | NA | "Vendor Approval for Active Harmonic Filter (DANFOSS)" && "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-26 | 22 | AWC | 2025-08-05 | 1 | 000476&&001368 | 2024-05-21, 2025-03-17, 2025-06-12, 2025-08-05 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8335 | 001368 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0016 | 1 | 131242-WST02-VI-E-0016-1 | 2025-08-05 | Vendor Approval for Active Harmonic Filter (DANFOSS) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-25 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WST02-VI-0016 | NA | "Vendor Approval for Active Harmonic Filter (DANFOSS)" && "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | AWC | 2025-08-05 | 1 | 000476&&001368 | 2024-05-21, 2025-03-17, 2025-06-12, 2025-08-05 | 00, 01 | 4 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
8336 | 001369 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | BQ | E | 0001 | 0 | 131242-WSW41-BQ-E-0001-0 | 2025-06-12 | Electrical As Built Drawing List | Rev 0: Not Approved. To revise and resubmit. | 2025-07-10 | 2025-07-23 | Not Approved | 2025-08-12 | NO | Overdue |  | 131242-WSW41-BQ-0001 | NA | "Electrical As Built Drawing List" | 2025-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 41 | NAP | 2025-06-12 | 0 | 001369 | 2025-06-12 | 00 | 1 | Not Approved | NAP | 2025-08-12 | Overdue | 0 | NAP | NAP
8337 | 001370 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5701 | A | 131242-WST02-DR-M-5701-A | 2025-06-12 | General Arrangement for TCI Flow Control valve | NA | 2025-07-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5701 | NA | "General Arrangement for TCI Flow Control valve" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | A | 001370 | 2025-06-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
8338 | 001371 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5702 | A | 131242-WST02-DR-M-5702-A | 2025-06-12 | General Arrangement for DC Partial Bypass Line Flow Control Valve | NA | 2025-07-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5702 | NA | "General Arrangement for DC Partial Bypass Line Flow Control Valve" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | A | 001371 | 2025-06-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
8339 | 001372 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5703 | A | 131242-WST02-DR-M-5703-A | 2025-06-12 | General Arrangement for Lamella Clarifier Flow Control Valve | NA | 2025-07-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5703 | NA | "General Arrangement for Lamella Clarifier Flow Control Valve" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | A | 001372 | 2025-06-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
8340 | 001373 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5711 | A | 131242-WST02-DR-M-5711-A | 2025-06-12 | General Arrangement for IRIS Diaphragm Flow Control Valve | NA | 2025-07-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5711 | NA | "General Arrangement for IRIS Diaphragm Flow Control Valve" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | A | 001373 | 2025-06-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
8341 | 001374 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5602 | A | 131242-WST02-DR-M-5602-A | 2025-06-16 | GA Drawing for Static Screen - Plinth Opening & Seal plate | NA | 2025-07-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5602 | NA | "GA Drawing for Static Screen - Plinth Opening & Seal plate" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-06 | 294 | PEN | 2025-07-24 | A | 001374&&001528 | 2025-06-16, 2025-07-24 | 00 | 2 | Not Approved | NAP |  |  | 0 | PEN | PEN
8342 | 001375 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0041 | 0 | 131242-WSD11-DS-M-0041-0 | 2025-06-16 | G1 Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-07-14 | 2025-07-08 | Not Approved | 2025-07-28 | YES | Resubmitted |  | 131242-WSD11-DS-0041 | NA | "G1 Booster Pump Data Sheet" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 22 | NAP | 2025-08-25 | 1 | 001375 | 2025-06-16, 2025-08-25 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8343 | 001375 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0041 | 1 | 131242-WSD11-DS-M-0041-1 | 2025-08-25 | G1 Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-09-12 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSD11-DS-0041 | NA | "G1 Booster Pump Data Sheet" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 14 | AWC | 2025-08-25 | 1 | 001375 | 2025-06-16, 2025-08-25 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
8344 | 001376 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5751 | A | 131242-WST02-DR-M-5751-A | 2025-06-16 | GA for SSN G2D PRV | NA | 2025-07-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5751 | NA | "GA for SSN G2D PRV" | 2025-06-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-06 | 294 | PEN | 2025-06-16 | A | 001376 | 2025-06-16 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-08-01 |  | 0 | PEN | PEN
8345 | 001377 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5103 | A | 131242-WSD11-DR-I-5103-A | 2025-06-16 | Hook-up Drawing for Pressure Transmitter (HS) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-12-10 | Not Approved | 2025-12-30 | NO | Overdue |  | 131242-WSD11-DR-5103 | NA | "Hook-up Drawing for Pressure Transmitter (HS)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 177 | NAP | 2025-06-16 | A | 001377 | 2025-06-16 | 00 | 1 | Not Approved | NAP | 2025-12-30 | Overdue | 0 | NAP | NAP
8346 | 001378 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0011 | 0 | 131242-WST02-DS-I-0011-0 | 2025-06-16 | Data sheet for Autosampler | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-10-24 | Approved with Comments | 2025-11-13 | NO | Overdue |  | 131242-WST02-DS-0011 | NA | "Data sheet for Autosampler" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 130 | AWC | 2025-06-16 | 0 | 000511&&001378 | 2024-06-05, 2025-06-16 | 00 | 2 | Approved with Comments | AWC | 2025-11-13 | Overdue | 0 | AWC | AWC
8347 | 001379 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0008 | 0 | 131242-WST02-DS-I-0008-0 | 2025-06-16 | Data sheet for Capacitive Level Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-11-05 | Approved with Comments | 2025-11-25 | NO | Overdue |  | 131242-WST02-DS-0008 | NA | "Data sheet for Capacitive Level Switch" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 142 | AWC | 2025-06-16 | 0 | 001379 | 2025-06-16 | 00 | 1 | Approved with Comments | AWC | 2025-11-25 | Overdue | 0 | AWC | AWC
8348 | 001380 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0009 | 0 | 131242-WST02-DS-I-0009-0 | 2025-06-16 | Datasheet for Thermal Mass Flowmeter | NA | 2025-07-14 | 2025-09-24 | Approved with Comments | 2025-10-14 | NO | Overdue |  | 131242-WST02-DS-0009 | NA | "Datasheet for Thermal Mass Flowmeter" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 100 | AWC | 2025-06-16 | 0 | 001380 | 2025-06-16 | 00 | 1 | Approved with Comments | AWC | 2025-10-14 | Overdue | 0 | AWC | AWC
8349 | 001381 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0042 | 0 | 131242-WSD11-DS-M-0042-0 | 2025-06-16 | G2D Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-07-14 | 2025-07-08 | Not Approved | 2025-07-28 | YES | Resubmitted |  | 131242-WSD11-DS-0042 | NA | "G2D Booster Pump Data Sheet" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 22 | NAP | 2025-08-22 | 1 | 001381 | 2025-06-16, 2025-08-22 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8350 | 001381 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0042 | 1 | 131242-WSD11-DS-M-0042-1 | 2025-08-22 | G2D Booster Pump Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2025-09-11 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSD11-DS-0042 | NA | "G2D Booster Pump Data Sheet" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 17 | AWC | 2025-08-22 | 1 | 001381 | 2025-06-16, 2025-08-22 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
8351 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1221 | A | 131242-WSD11-DR-IP-1221-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1221 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8352 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1222 | A | 131242-WSD11-DR-IP-1222-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1222 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8353 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1223 | A | 131242-WSD11-DR-IP-1223-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1223 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8354 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1224 | A | 131242-WSD11-DR-IP-1224-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1224 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8355 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1225 | A | 131242-WSD11-DR-IP-1225-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1225 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8356 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1226 | A | 131242-WSD11-DR-IP-1226-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1226 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8357 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1227 | A | 131242-WSD11-DR-IP-1227-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1227 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8358 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1228 | A | 131242-WSD11-DR-IP-1228-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1228 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8359 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1229 | A | 131242-WSD11-DR-IP-1229-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1229 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8360 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1230 | A | 131242-WSD11-DR-IP-1230-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1230 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8361 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1231 | A | 131242-WSD11-DR-IP-1231-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1231 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8362 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1232 | A | 131242-WSD11-DR-IP-1232-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1232 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8363 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1233 | A | 131242-WSD11-DR-IP-1233-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1233 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8364 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1234 | A | 131242-WSD11-DR-IP-1234-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1234 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8365 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1235 | A | 131242-WSD11-DR-IP-1235-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1235 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8366 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1236 | A | 131242-WSD11-DR-IP-1236-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1236 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8367 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1237 | A | 131242-WSD11-DR-IP-1237-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1237 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8368 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1238 | A | 131242-WSD11-DR-IP-1238-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1238 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8369 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1239 | A | 131242-WSD11-DR-IP-1239-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1239 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8370 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1240 | A | 131242-WSD11-DR-IP-1240-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1240 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8371 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1241 | A | 131242-WSD11-DR-IP-1241-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1241 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8372 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1242 | A | 131242-WSD11-DR-IP-1242-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1242 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8373 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1243 | A | 131242-WSD11-DR-IP-1243-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1243 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8374 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1244 | A | 131242-WSD11-DR-IP-1244-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1244 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8375 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1245 | A | 131242-WSD11-DR-IP-1245-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1245 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8376 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1246 | A | 131242-WSD11-DR-IP-1246-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1246 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8377 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1247 | A | 131242-WSD11-DR-IP-1247-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1247 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8378 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1248 | A | 131242-WSD11-DR-IP-1248-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1248 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8379 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1249 | A | 131242-WSD11-DR-IP-1249-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1249 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8380 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1250 | A | 131242-WSD11-DR-IP-1250-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1250 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8381 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1251 | A | 131242-WSD11-DR-IP-1251-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1251 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8382 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1252 | A | 131242-WSD11-DR-IP-1252-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1252 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8383 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1253 | A | 131242-WSD11-DR-IP-1253-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1253 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8384 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1254 | A | 131242-WSD11-DR-IP-1254-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1254 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8385 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1255 | A | 131242-WSD11-DR-IP-1255-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1255 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8386 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1256 | A | 131242-WSD11-DR-IP-1256-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1256 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8387 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1257 | A | 131242-WSD11-DR-IP-1257-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1257 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8388 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1258 | A | 131242-WSD11-DR-IP-1258-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1258 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8389 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1259 | A | 131242-WSD11-DR-IP-1259-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1259 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8390 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1260 | A | 131242-WSD11-DR-IP-1260-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1260 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8391 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1261 | A | 131242-WSD11-DR-IP-1261-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1261 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8392 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1262 | A | 131242-WSD11-DR-IP-1262-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1262 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8393 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1263 | A | 131242-WSD11-DR-IP-1263-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1263 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8394 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1264 | A | 131242-WSD11-DR-IP-1264-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1264 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8395 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1265 | A | 131242-WSD11-DR-IP-1265-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1265 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8396 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1266 | A | 131242-WSD11-DR-IP-1266-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1266 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8397 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1267 | A | 131242-WSD11-DR-IP-1267-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1267 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8398 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1268 | A | 131242-WSD11-DR-IP-1268-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1268 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8399 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1269 | A | 131242-WSD11-DR-IP-1269-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1269 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8400 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1270 | A | 131242-WSD11-DR-IP-1270-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1270 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8401 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1271 | A | 131242-WSD11-DR-IP-1271-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1271 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8402 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1272 | A | 131242-WSD11-DR-IP-1272-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1272 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8403 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1273 | A | 131242-WSD11-DR-IP-1273-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1273 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8404 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1274 | A | 131242-WSD11-DR-IP-1274-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1274 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8405 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1275 | A | 131242-WSD11-DR-IP-1275-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1275 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8406 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1276 | A | 131242-WSD11-DR-IP-1276-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1276 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8407 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1277 | A | 131242-WSD11-DR-IP-1277-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1277 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8408 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1278 | A | 131242-WSD11-DR-IP-1278-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1278 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8409 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1279 | A | 131242-WSD11-DR-IP-1279-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1279 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8410 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1280 | A | 131242-WSD11-DR-IP-1280-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1280 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8411 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1281 | A | 131242-WSD11-DR-IP-1281-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1281 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8412 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1282 | A | 131242-WSD11-DR-IP-1282-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1282 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8413 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1283 | A | 131242-WSD11-DR-IP-1283-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1283 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8414 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1284 | A | 131242-WSD11-DR-IP-1284-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1284 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8415 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1285 | A | 131242-WSD11-DR-IP-1285-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1285 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8416 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1286 | A | 131242-WSD11-DR-IP-1286-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1286 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8417 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1287 | A | 131242-WSD11-DR-IP-1287-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1287 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8418 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1288 | A | 131242-WSD11-DR-IP-1288-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1288 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8419 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1289 | A | 131242-WSD11-DR-IP-1289-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1289 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8420 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1290 | A | 131242-WSD11-DR-IP-1290-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1290 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8421 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1291 | A | 131242-WSD11-DR-IP-1291-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1291 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8422 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1292 | A | 131242-WSD11-DR-IP-1292-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1292 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8423 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1293 | A | 131242-WSD11-DR-IP-1293-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1293 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8424 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1294 | A | 131242-WSD11-DR-IP-1294-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1294 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8425 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1295 | A | 131242-WSD11-DR-IP-1295-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1295 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8426 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1296 | A | 131242-WSD11-DR-IP-1296-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1296 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8427 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1297 | A | 131242-WSD11-DR-IP-1297-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1297 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8428 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1298 | A | 131242-WSD11-DR-IP-1298-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1298 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8429 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1299 | A | 131242-WSD11-DR-IP-1299-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1299 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8430 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1300 | A | 131242-WSD11-DR-IP-1300-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1300 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8431 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1301 | A | 131242-WSD11-DR-IP-1301-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1301 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8432 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1302 | A | 131242-WSD11-DR-IP-1302-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1302 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8433 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1303 | A | 131242-WSD11-DR-IP-1303-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1303 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8434 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1304 | A | 131242-WSD11-DR-IP-1304-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1304 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8435 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1305 | A | 131242-WSD11-DR-IP-1305-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1305 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8436 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1306 | A | 131242-WSD11-DR-IP-1306-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1306 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8437 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1307 | A | 131242-WSD11-DR-IP-1307-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1307 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8438 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1308 | A | 131242-WSD11-DR-IP-1308-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1308 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8439 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1309 | A | 131242-WSD11-DR-IP-1309-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1309 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8440 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1310 | A | 131242-WSD11-DR-IP-1310-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1310 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8441 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1311 | A | 131242-WSD11-DR-IP-1311-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1311 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8442 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1312 | A | 131242-WSD11-DR-IP-1312-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1312 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8443 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1313 | A | 131242-WSD11-DR-IP-1313-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1313 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8444 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1314 | A | 131242-WSD11-DR-IP-1314-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1314 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8445 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1315 | A | 131242-WSD11-DR-IP-1315-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1315 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8446 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1316 | A | 131242-WSD11-DR-IP-1316-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1316 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8447 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1317 | A | 131242-WSD11-DR-IP-1317-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1317 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8448 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1318 | A | 131242-WSD11-DR-IP-1318-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1318 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8449 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1319 | A | 131242-WSD11-DR-IP-1319-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1319 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8450 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1320 | A | 131242-WSD11-DR-IP-1320-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1320 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8451 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1321 | A | 131242-WSD11-DR-IP-1321-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1321 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8452 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1322 | A | 131242-WSD11-DR-IP-1322-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1322 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8453 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1323 | A | 131242-WSD11-DR-IP-1323-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1323 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8454 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1324 | A | 131242-WSD11-DR-IP-1324-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1324 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8455 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1325 | A | 131242-WSD11-DR-IP-1325-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1325 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8456 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1326 | A | 131242-WSD11-DR-IP-1326-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1326 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8457 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1327 | A | 131242-WSD11-DR-IP-1327-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1327 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8458 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1328 | A | 131242-WSD11-DR-IP-1328-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1328 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8459 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1329 | A | 131242-WSD11-DR-IP-1329-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1329 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8460 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1330 | A | 131242-WSD11-DR-IP-1330-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1330 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8461 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1331 | A | 131242-WSD11-DR-IP-1331-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1331 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8462 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1332 | A | 131242-WSD11-DR-IP-1332-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1332 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8463 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1333 | A | 131242-WSD11-DR-IP-1333-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1333 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8464 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1334 | A | 131242-WSD11-DR-IP-1334-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1334 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8465 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1335 | A | 131242-WSD11-DR-IP-1335-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1335 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8466 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1336 | A | 131242-WSD11-DR-IP-1336-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1336 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8467 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1337 | A | 131242-WSD11-DR-IP-1337-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1337 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8468 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1338 | A | 131242-WSD11-DR-IP-1338-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1338 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8469 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1339 | A | 131242-WSD11-DR-IP-1339-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1339 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8470 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1351 | A | 131242-WSD11-DR-IP-1351-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1351 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8471 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1352 | A | 131242-WSD11-DR-IP-1352-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1352 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8472 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1353 | A | 131242-WSD11-DR-IP-1353-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1353 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8473 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1354 | A | 131242-WSD11-DR-IP-1354-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1354 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8474 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1355 | A | 131242-WSD11-DR-IP-1355-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1355 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8475 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1356 | A | 131242-WSD11-DR-IP-1356-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1356 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8476 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1357 | A | 131242-WSD11-DR-IP-1357-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1357 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8477 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1358 | A | 131242-WSD11-DR-IP-1358-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1358 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8478 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1359 | A | 131242-WSD11-DR-IP-1359-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1359 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8479 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1360 | A | 131242-WSD11-DR-IP-1360-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1360 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8480 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1361 | A | 131242-WSD11-DR-IP-1361-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1361 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8481 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1362 | A | 131242-WSD11-DR-IP-1362-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1362 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8482 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1363 | A | 131242-WSD11-DR-IP-1363-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1363 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8483 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1364 | A | 131242-WSD11-DR-IP-1364-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1364 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8484 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1365 | A | 131242-WSD11-DR-IP-1365-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1365 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8485 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1366 | A | 131242-WSD11-DR-IP-1366-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1366 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8486 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1367 | A | 131242-WSD11-DR-IP-1367-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1367 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8487 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1368 | A | 131242-WSD11-DR-IP-1368-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1368 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8488 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1369 | A | 131242-WSD11-DR-IP-1369-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1369 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8489 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1370 | A | 131242-WSD11-DR-IP-1370-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1370 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8490 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1371 | A | 131242-WSD11-DR-IP-1371-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1371 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8491 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1372 | A | 131242-WSD11-DR-IP-1372-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1372 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8492 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1373 | A | 131242-WSD11-DR-IP-1373-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1373 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8493 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1374 | A | 131242-WSD11-DR-IP-1374-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1374 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8494 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1375 | A | 131242-WSD11-DR-IP-1375-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1375 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8495 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1376 | A | 131242-WSD11-DR-IP-1376-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1376 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8496 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1377 | A | 131242-WSD11-DR-IP-1377-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1377 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8497 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1378 | A | 131242-WSD11-DR-IP-1378-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1378 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8498 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1379 | A | 131242-WSD11-DR-IP-1379-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1379 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8499 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1380 | A | 131242-WSD11-DR-IP-1380-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1380 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8500 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1381 | A | 131242-WSD11-DR-IP-1381-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1381 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8501 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1382 | A | 131242-WSD11-DR-IP-1382-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1382 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8502 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1383 | A | 131242-WSD11-DR-IP-1383-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1383 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8503 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1384 | A | 131242-WSD11-DR-IP-1384-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1384 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8504 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1385 | A | 131242-WSD11-DR-IP-1385-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1385 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8505 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1386 | A | 131242-WSD11-DR-IP-1386-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1386 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8506 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1387 | A | 131242-WSD11-DR-IP-1387-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1387 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8507 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1388 | A | 131242-WSD11-DR-IP-1388-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1388 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8508 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1389 | A | 131242-WSD11-DR-IP-1389-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1389 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8509 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1390 | A | 131242-WSD11-DR-IP-1390-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1390 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8510 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1391 | A | 131242-WSD11-DR-IP-1391-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1391 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8511 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1392 | A | 131242-WSD11-DR-IP-1392-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1392 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8512 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1393 | A | 131242-WSD11-DR-IP-1393-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1393 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8513 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1394 | A | 131242-WSD11-DR-IP-1394-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1394 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8514 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1395 | A | 131242-WSD11-DR-IP-1395-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1395 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8515 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1396 | A | 131242-WSD11-DR-IP-1396-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1396 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8516 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1397 | A | 131242-WSD11-DR-IP-1397-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1397 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8517 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1398 | A | 131242-WSD11-DR-IP-1398-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1398 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8518 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1399 | A | 131242-WSD11-DR-IP-1399-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1399 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8519 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1400 | A | 131242-WSD11-DR-IP-1400-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8520 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1401 | A | 131242-WSD11-DR-IP-1401-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1401 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8521 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1402 | A | 131242-WSD11-DR-IP-1402-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1402 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8522 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1403 | A | 131242-WSD11-DR-IP-1403-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1403 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8523 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1404 | A | 131242-WSD11-DR-IP-1404-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1404 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8524 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1405 | A | 131242-WSD11-DR-IP-1405-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1405 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8525 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1406 | A | 131242-WSD11-DR-IP-1406-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1406 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8526 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1407 | A | 131242-WSD11-DR-IP-1407-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1407 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8527 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1408 | A | 131242-WSD11-DR-IP-1408-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1408 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8528 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1409 | A | 131242-WSD11-DR-IP-1409-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1409 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8529 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1410 | A | 131242-WSD11-DR-IP-1410-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1410 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8530 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1411 | A | 131242-WSD11-DR-IP-1411-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1411 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8531 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1412 | A | 131242-WSD11-DR-IP-1412-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1412 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8532 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1413 | A | 131242-WSD11-DR-IP-1413-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1413 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8533 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1414 | A | 131242-WSD11-DR-IP-1414-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1414 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8534 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1415 | A | 131242-WSD11-DR-IP-1415-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1415 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8535 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1416 | A | 131242-WSD11-DR-IP-1416-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1416 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8536 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1417 | A | 131242-WSD11-DR-IP-1417-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1417 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8537 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1418 | A | 131242-WSD11-DR-IP-1418-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1418 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8538 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1419 | A | 131242-WSD11-DR-IP-1419-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1419 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8539 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1420 | A | 131242-WSD11-DR-IP-1420-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1420 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8540 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1421 | A | 131242-WSD11-DR-IP-1421-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1421 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8541 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1422 | A | 131242-WSD11-DR-IP-1422-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1422 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8542 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1423 | A | 131242-WSD11-DR-IP-1423-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1423 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8543 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1424 | A | 131242-WSD11-DR-IP-1424-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1424 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8544 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1425 | A | 131242-WSD11-DR-IP-1425-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1425 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8545 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1426 | A | 131242-WSD11-DR-IP-1426-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1426 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8546 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1427 | A | 131242-WSD11-DR-IP-1427-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1427 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8547 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1428 | A | 131242-WSD11-DR-IP-1428-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1428 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8548 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1429 | A | 131242-WSD11-DR-IP-1429-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1429 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8549 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1430 | A | 131242-WSD11-DR-IP-1430-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1430 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8550 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1431 | A | 131242-WSD11-DR-IP-1431-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1431 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8551 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1432 | A | 131242-WSD11-DR-IP-1432-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1432 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8552 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1433 | A | 131242-WSD11-DR-IP-1433-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1433 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8553 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1434 | A | 131242-WSD11-DR-IP-1434-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1434 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8554 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1435 | A | 131242-WSD11-DR-IP-1435-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1435 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8555 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1436 | A | 131242-WSD11-DR-IP-1436-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1436 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8556 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1437 | A | 131242-WSD11-DR-IP-1437-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1437 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8557 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1438 | A | 131242-WSD11-DR-IP-1438-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1438 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8558 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1439 | A | 131242-WSD11-DR-IP-1439-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1439 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8559 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1440 | A | 131242-WSD11-DR-IP-1440-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1440 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8560 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1441 | A | 131242-WSD11-DR-IP-1441-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1441 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8561 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1442 | A | 131242-WSD11-DR-IP-1442-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1442 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8562 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1443 | A | 131242-WSD11-DR-IP-1443-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1443 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8563 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1444 | A | 131242-WSD11-DR-IP-1444-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1444 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8564 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1445 | A | 131242-WSD11-DR-IP-1445-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1445 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8565 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1446 | A | 131242-WSD11-DR-IP-1446-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1446 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8566 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1447 | A | 131242-WSD11-DR-IP-1447-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1447 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8567 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1448 | A | 131242-WSD11-DR-IP-1448-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1448 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8568 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1449 | A | 131242-WSD11-DR-IP-1449-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1449 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8569 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1450 | A | 131242-WSD11-DR-IP-1450-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1450 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8570 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1451 | A | 131242-WSD11-DR-IP-1451-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1451 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8571 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1452 | A | 131242-WSD11-DR-IP-1452-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1452 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8572 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1453 | A | 131242-WSD11-DR-IP-1453-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1453 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8573 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1454 | A | 131242-WSD11-DR-IP-1454-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1454 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8574 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1455 | A | 131242-WSD11-DR-IP-1455-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1455 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8575 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1456 | A | 131242-WSD11-DR-IP-1456-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1456 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8576 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1457 | A | 131242-WSD11-DR-IP-1457-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1457 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8577 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1458 | A | 131242-WSD11-DR-IP-1458-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1458 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8578 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1459 | A | 131242-WSD11-DR-IP-1459-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1459 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8579 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1460 | A | 131242-WSD11-DR-IP-1460-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1460 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8580 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1461 | A | 131242-WSD11-DR-IP-1461-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1461 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8581 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1462 | A | 131242-WSD11-DR-IP-1462-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1462 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8582 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1463 | A | 131242-WSD11-DR-IP-1463-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1463 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8583 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1464 | A | 131242-WSD11-DR-IP-1464-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1464 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8584 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1465 | A | 131242-WSD11-DR-IP-1465-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1465 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8585 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1466 | A | 131242-WSD11-DR-IP-1466-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1466 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8586 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1467 | A | 131242-WSD11-DR-IP-1467-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1467 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8587 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1468 | A | 131242-WSD11-DR-IP-1468-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1468 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8588 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1469 | A | 131242-WSD11-DR-IP-1469-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1469 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8589 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1470 | A | 131242-WSD11-DR-IP-1470-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1470 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8590 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1151 | A | 131242-WSD11-DR-IP-1151-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1151 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8591 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1152 | A | 131242-WSD11-DR-IP-1152-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1152 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8592 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1153 | A | 131242-WSD11-DR-IP-1153-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1153 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8593 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1154 | A | 131242-WSD11-DR-IP-1154-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1154 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8594 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1155 | A | 131242-WSD11-DR-IP-1155-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1155 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8595 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1156 | A | 131242-WSD11-DR-IP-1156-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1156 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8596 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1157 | A | 131242-WSD11-DR-IP-1157-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1157 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8597 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1158 | A | 131242-WSD11-DR-IP-1158-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1158 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8598 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1159 | A | 131242-WSD11-DR-IP-1159-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1159 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8599 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1160 | A | 131242-WSD11-DR-IP-1160-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1160 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8600 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1161 | A | 131242-WSD11-DR-IP-1161-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1161 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8601 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1162 | A | 131242-WSD11-DR-IP-1162-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1162 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8602 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1163 | A | 131242-WSD11-DR-IP-1163-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1163 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8603 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1164 | A | 131242-WSD11-DR-IP-1164-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1164 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8604 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1165 | A | 131242-WSD11-DR-IP-1165-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1165 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8605 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1166 | A | 131242-WSD11-DR-IP-1166-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1166 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8606 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1167 | A | 131242-WSD11-DR-IP-1167-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1167 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8607 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1168 | A | 131242-WSD11-DR-IP-1168-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1168 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8608 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1169 | A | 131242-WSD11-DR-IP-1169-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1169 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8609 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1170 | A | 131242-WSD11-DR-IP-1170-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8610 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1171 | A | 131242-WSD11-DR-IP-1171-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8611 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1172 | A | 131242-WSD11-DR-IP-1172-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1172 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8612 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1173 | A | 131242-WSD11-DR-IP-1173-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1173 | NA | "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000681&&001382 | 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8613 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1174 | A | 131242-WSD11-DR-IP-1174-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1174 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8614 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1175 | A | 131242-WSD11-DR-IP-1175-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1175 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8615 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1176 | A | 131242-WSD11-DR-IP-1176-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1176 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8616 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1177 | A | 131242-WSD11-DR-IP-1177-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1177 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8617 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1178 | A | 131242-WSD11-DR-IP-1178-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1178 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8618 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1179 | A | 131242-WSD11-DR-IP-1179-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1179 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8619 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1180 | A | 131242-WSD11-DR-IP-1180-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1180 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8620 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1181 | A | 131242-WSD11-DR-IP-1181-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1181 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8621 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1182 | A | 131242-WSD11-DR-IP-1182-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1182 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8622 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1183 | A | 131242-WSD11-DR-IP-1183-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1183 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8623 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1184 | A | 131242-WSD11-DR-IP-1184-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1184 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8624 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1185 | A | 131242-WSD11-DR-IP-1185-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1185 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8625 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1186 | A | 131242-WSD11-DR-IP-1186-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1186 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8626 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1187 | A | 131242-WSD11-DR-IP-1187-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1187 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8627 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1188 | A | 131242-WSD11-DR-IP-1188-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1188 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8628 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1189 | A | 131242-WSD11-DR-IP-1189-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1189 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8629 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1190 | A | 131242-WSD11-DR-IP-1190-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1190 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" && "THP Underground Piping and Cast in Details" | 2024-10-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000789&&001382 | 2024-10-30, 2025-06-16, 2025-08-13 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8630 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1191 | A | 131242-WSD11-DR-IP-1191-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1191 | NA | "THP Cast in Layout Inside Bio-solid Building" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-07-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000580&&001382 | 2024-07-23, 2025-06-16, 2025-08-13 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8631 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1192 | A | 131242-WSD11-DR-IP-1192-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1192 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8632 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1193 | A | 131242-WSD11-DR-IP-1193-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1193 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8633 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1194 | A | 131242-WSD11-DR-IP-1194-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1194 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8634 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1195 | A | 131242-WSD11-DR-IP-1195-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1195 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8635 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1196 | A | 131242-WSD11-DR-IP-1196-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1196 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8636 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1197 | A | 131242-WSD11-DR-IP-1197-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1197 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8637 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1198 | A | 131242-WSD11-DR-IP-1198-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1198 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8638 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1199 | A | 131242-WSD11-DR-IP-1199-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1199 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8639 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1481 | A | 131242-WSD11-DR-IP-1481-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1481 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8640 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1482 | A | 131242-WSD11-DR-IP-1482-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1482 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8641 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1483 | A | 131242-WSD11-DR-IP-1483-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1483 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8642 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1484 | A | 131242-WSD11-DR-IP-1484-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1484 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8643 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1485 | A | 131242-WSD11-DR-IP-1485-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1485 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8644 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1486 | A | 131242-WSD11-DR-IP-1486-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1486 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8645 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1487 | A | 131242-WSD11-DR-IP-1487-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1487 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8646 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1488 | A | 131242-WSD11-DR-IP-1488-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1488 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8647 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1489 | A | 131242-WSD11-DR-IP-1489-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1489 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8648 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1490 | A | 131242-WSD11-DR-IP-1490-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1490 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8649 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1491 | A | 131242-WSD11-DR-IP-1491-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1491 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8650 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1492 | A | 131242-WSD11-DR-IP-1492-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1492 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8651 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1493 | A | 131242-WSD11-DR-IP-1493-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1493 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8652 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1494 | A | 131242-WSD11-DR-IP-1494-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1494 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8653 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1495 | A | 131242-WSD11-DR-IP-1495-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1495 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8654 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1496 | A | 131242-WSD11-DR-IP-1496-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1496 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8655 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1497 | A | 131242-WSD11-DR-IP-1497-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1497 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8656 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1498 | A | 131242-WSD11-DR-IP-1498-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1498 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8657 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1499 | A | 131242-WSD11-DR-IP-1499-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1499 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8658 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1500 | A | 131242-WSD11-DR-IP-1500-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8659 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1501 | A | 131242-WSD11-DR-IP-1501-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8660 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1502 | A | 131242-WSD11-DR-IP-1502-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1502 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8661 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1503 | A | 131242-WSD11-DR-IP-1503-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1503 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8662 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1504 | A | 131242-WSD11-DR-IP-1504-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1504 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8663 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1505 | A | 131242-WSD11-DR-IP-1505-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1505 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 30 | NAP | 2025-08-13 | B | 000845&&001382 | 2024-12-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8664 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1506 | A | 131242-WSD11-DR-IP-1506-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1506 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8665 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1507 | A | 131242-WSD11-DR-IP-1507-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1507 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8666 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1508 | A | 131242-WSD11-DR-IP-1508-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1508 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8667 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1509 | A | 131242-WSD11-DR-IP-1509-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1509 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8668 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1510 | A | 131242-WSD11-DR-IP-1510-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1510 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8669 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1511 | A | 131242-WSD11-DR-IP-1511-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1511 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8670 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1512 | A | 131242-WSD11-DR-IP-1512-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1512 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8671 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1513 | A | 131242-WSD11-DR-IP-1513-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1513 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8672 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1514 | A | 131242-WSD11-DR-IP-1514-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1514 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8673 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1515 | A | 131242-WSD11-DR-IP-1515-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1515 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8674 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1516 | A | 131242-WSD11-DR-IP-1516-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1516 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8675 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1517 | A | 131242-WSD11-DR-IP-1517-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1517 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8676 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1518 | A | 131242-WSD11-DR-IP-1518-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1518 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8677 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1519 | A | 131242-WSD11-DR-IP-1519-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1519 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8678 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1520 | A | 131242-WSD11-DR-IP-1520-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1520 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8679 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1521 | A | 131242-WSD11-DR-IP-1521-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1521 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8680 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1522 | A | 131242-WSD11-DR-IP-1522-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1522 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8681 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1523 | A | 131242-WSD11-DR-IP-1523-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1523 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8682 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1524 | A | 131242-WSD11-DR-IP-1524-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1524 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8683 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1525 | A | 131242-WSD11-DR-IP-1525-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1525 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8684 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1526 | A | 131242-WSD11-DR-IP-1526-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1526 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8685 | 001382 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1527 | A | 131242-WSD11-DR-IP-1527-A | 2025-06-16 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-14 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-DR-1527 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-06 | 30 | NAP | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
8686 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1221 | B | 131242-WSD11-DR-IP-1221-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1221 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8687 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1222 | B | 131242-WSD11-DR-IP-1222-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1222 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8688 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1223 | B | 131242-WSD11-DR-IP-1223-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1223 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8689 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1224 | B | 131242-WSD11-DR-IP-1224-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1224 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8690 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1225 | B | 131242-WSD11-DR-IP-1225-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1225 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8691 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1226 | B | 131242-WSD11-DR-IP-1226-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1226 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8692 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1227 | B | 131242-WSD11-DR-IP-1227-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1227 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8693 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1228 | B | 131242-WSD11-DR-IP-1228-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1228 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8694 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1229 | B | 131242-WSD11-DR-IP-1229-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1229 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8695 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1230 | B | 131242-WSD11-DR-IP-1230-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1230 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8696 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1231 | B | 131242-WSD11-DR-IP-1231-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1231 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8697 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1232 | B | 131242-WSD11-DR-IP-1232-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1232 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8698 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1233 | B | 131242-WSD11-DR-IP-1233-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1233 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8699 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1234 | B | 131242-WSD11-DR-IP-1234-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1234 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8700 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1235 | B | 131242-WSD11-DR-IP-1235-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1235 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8701 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1236 | B | 131242-WSD11-DR-IP-1236-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1236 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8702 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1237 | B | 131242-WSD11-DR-IP-1237-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1237 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8703 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1238 | B | 131242-WSD11-DR-IP-1238-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1238 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8704 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1239 | B | 131242-WSD11-DR-IP-1239-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1239 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8705 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1240 | B | 131242-WSD11-DR-IP-1240-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1240 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8706 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1241 | B | 131242-WSD11-DR-IP-1241-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1241 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8707 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1242 | B | 131242-WSD11-DR-IP-1242-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1242 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8708 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1243 | B | 131242-WSD11-DR-IP-1243-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1243 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8709 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1244 | B | 131242-WSD11-DR-IP-1244-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1244 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8710 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1245 | B | 131242-WSD11-DR-IP-1245-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1245 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8711 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1246 | B | 131242-WSD11-DR-IP-1246-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1246 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8712 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1247 | B | 131242-WSD11-DR-IP-1247-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1247 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8713 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1248 | B | 131242-WSD11-DR-IP-1248-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1248 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8714 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1249 | B | 131242-WSD11-DR-IP-1249-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1249 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8715 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1250 | B | 131242-WSD11-DR-IP-1250-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1250 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8716 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1251 | B | 131242-WSD11-DR-IP-1251-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1251 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8717 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1252 | B | 131242-WSD11-DR-IP-1252-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1252 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8718 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1253 | B | 131242-WSD11-DR-IP-1253-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1253 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8719 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1254 | B | 131242-WSD11-DR-IP-1254-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1254 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8720 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1255 | B | 131242-WSD11-DR-IP-1255-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1255 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8721 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1256 | B | 131242-WSD11-DR-IP-1256-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1256 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8722 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1257 | B | 131242-WSD11-DR-IP-1257-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1257 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8723 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1258 | B | 131242-WSD11-DR-IP-1258-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1258 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8724 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1259 | B | 131242-WSD11-DR-IP-1259-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1259 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8725 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1260 | B | 131242-WSD11-DR-IP-1260-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1260 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8726 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1261 | B | 131242-WSD11-DR-IP-1261-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1261 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8727 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1262 | B | 131242-WSD11-DR-IP-1262-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1262 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8728 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1263 | B | 131242-WSD11-DR-IP-1263-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1263 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8729 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1264 | B | 131242-WSD11-DR-IP-1264-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1264 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8730 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1265 | B | 131242-WSD11-DR-IP-1265-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1265 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8731 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1266 | B | 131242-WSD11-DR-IP-1266-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1266 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8732 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1267 | B | 131242-WSD11-DR-IP-1267-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1267 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8733 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1268 | B | 131242-WSD11-DR-IP-1268-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1268 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8734 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1269 | B | 131242-WSD11-DR-IP-1269-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1269 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8735 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1270 | B | 131242-WSD11-DR-IP-1270-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1270 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8736 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1271 | B | 131242-WSD11-DR-IP-1271-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1271 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8737 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1272 | B | 131242-WSD11-DR-IP-1272-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1272 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8738 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1273 | B | 131242-WSD11-DR-IP-1273-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1273 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8739 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1274 | B | 131242-WSD11-DR-IP-1274-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1274 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8740 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1275 | B | 131242-WSD11-DR-IP-1275-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1275 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8741 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1276 | B | 131242-WSD11-DR-IP-1276-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1276 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8742 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1277 | B | 131242-WSD11-DR-IP-1277-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1277 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8743 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1278 | B | 131242-WSD11-DR-IP-1278-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1278 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8744 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1279 | B | 131242-WSD11-DR-IP-1279-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1279 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8745 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1280 | B | 131242-WSD11-DR-IP-1280-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1280 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8746 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1281 | B | 131242-WSD11-DR-IP-1281-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1281 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8747 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1282 | B | 131242-WSD11-DR-IP-1282-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1282 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8748 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1283 | B | 131242-WSD11-DR-IP-1283-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1283 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8749 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1284 | B | 131242-WSD11-DR-IP-1284-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1284 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8750 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1285 | B | 131242-WSD11-DR-IP-1285-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1285 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8751 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1286 | B | 131242-WSD11-DR-IP-1286-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1286 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8752 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1287 | B | 131242-WSD11-DR-IP-1287-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1287 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8753 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1288 | B | 131242-WSD11-DR-IP-1288-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1288 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8754 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1289 | B | 131242-WSD11-DR-IP-1289-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1289 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8755 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1290 | B | 131242-WSD11-DR-IP-1290-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1290 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8756 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1291 | B | 131242-WSD11-DR-IP-1291-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1291 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8757 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1292 | B | 131242-WSD11-DR-IP-1292-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1292 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8758 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1293 | B | 131242-WSD11-DR-IP-1293-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1293 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8759 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1294 | B | 131242-WSD11-DR-IP-1294-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1294 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8760 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1295 | B | 131242-WSD11-DR-IP-1295-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1295 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8761 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1296 | B | 131242-WSD11-DR-IP-1296-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1296 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8762 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1297 | B | 131242-WSD11-DR-IP-1297-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1297 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8763 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1298 | B | 131242-WSD11-DR-IP-1298-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1298 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8764 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1299 | B | 131242-WSD11-DR-IP-1299-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1299 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8765 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1300 | B | 131242-WSD11-DR-IP-1300-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1300 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8766 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1301 | B | 131242-WSD11-DR-IP-1301-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1301 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8767 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1302 | B | 131242-WSD11-DR-IP-1302-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1302 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8768 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1303 | B | 131242-WSD11-DR-IP-1303-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1303 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8769 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1304 | B | 131242-WSD11-DR-IP-1304-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1304 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8770 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1305 | B | 131242-WSD11-DR-IP-1305-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1305 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8771 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1306 | B | 131242-WSD11-DR-IP-1306-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1306 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8772 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1307 | B | 131242-WSD11-DR-IP-1307-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1307 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8773 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1308 | B | 131242-WSD11-DR-IP-1308-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1308 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8774 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1309 | B | 131242-WSD11-DR-IP-1309-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1309 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8775 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1310 | B | 131242-WSD11-DR-IP-1310-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1310 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8776 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1311 | B | 131242-WSD11-DR-IP-1311-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1311 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8777 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1312 | B | 131242-WSD11-DR-IP-1312-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1312 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8778 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1313 | B | 131242-WSD11-DR-IP-1313-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1313 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8779 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1314 | B | 131242-WSD11-DR-IP-1314-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1314 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8780 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1315 | B | 131242-WSD11-DR-IP-1315-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1315 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8781 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1316 | B | 131242-WSD11-DR-IP-1316-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1316 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8782 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1317 | B | 131242-WSD11-DR-IP-1317-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1317 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8783 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1318 | B | 131242-WSD11-DR-IP-1318-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1318 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8784 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1319 | B | 131242-WSD11-DR-IP-1319-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1319 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8785 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1320 | B | 131242-WSD11-DR-IP-1320-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1320 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8786 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1321 | B | 131242-WSD11-DR-IP-1321-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1321 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8787 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1322 | B | 131242-WSD11-DR-IP-1322-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1322 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8788 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1323 | B | 131242-WSD11-DR-IP-1323-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1323 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8789 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1324 | B | 131242-WSD11-DR-IP-1324-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1324 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8790 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1325 | B | 131242-WSD11-DR-IP-1325-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1325 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8791 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1326 | B | 131242-WSD11-DR-IP-1326-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1326 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8792 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1327 | B | 131242-WSD11-DR-IP-1327-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1327 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8793 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1328 | B | 131242-WSD11-DR-IP-1328-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1328 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8794 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1329 | B | 131242-WSD11-DR-IP-1329-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1329 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8795 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1330 | B | 131242-WSD11-DR-IP-1330-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1330 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8796 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1331 | B | 131242-WSD11-DR-IP-1331-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1331 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8797 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1332 | B | 131242-WSD11-DR-IP-1332-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1332 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8798 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1333 | B | 131242-WSD11-DR-IP-1333-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1333 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8799 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1334 | B | 131242-WSD11-DR-IP-1334-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1334 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8800 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1335 | B | 131242-WSD11-DR-IP-1335-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1335 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8801 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1336 | B | 131242-WSD11-DR-IP-1336-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1336 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8802 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1337 | B | 131242-WSD11-DR-IP-1337-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1337 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8803 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1338 | B | 131242-WSD11-DR-IP-1338-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1338 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8804 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1339 | B | 131242-WSD11-DR-IP-1339-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1339 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8805 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1351 | B | 131242-WSD11-DR-IP-1351-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1351 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8806 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1352 | B | 131242-WSD11-DR-IP-1352-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1352 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8807 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1353 | B | 131242-WSD11-DR-IP-1353-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1353 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8808 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1354 | B | 131242-WSD11-DR-IP-1354-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1354 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8809 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1355 | B | 131242-WSD11-DR-IP-1355-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1355 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8810 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1356 | B | 131242-WSD11-DR-IP-1356-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1356 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8811 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1357 | B | 131242-WSD11-DR-IP-1357-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1357 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8812 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1358 | B | 131242-WSD11-DR-IP-1358-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1358 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8813 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1359 | B | 131242-WSD11-DR-IP-1359-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1359 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8814 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1360 | B | 131242-WSD11-DR-IP-1360-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1360 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8815 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1361 | B | 131242-WSD11-DR-IP-1361-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1361 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8816 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1362 | B | 131242-WSD11-DR-IP-1362-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1362 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8817 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1363 | B | 131242-WSD11-DR-IP-1363-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1363 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8818 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1364 | B | 131242-WSD11-DR-IP-1364-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1364 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8819 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1365 | B | 131242-WSD11-DR-IP-1365-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1365 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8820 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1366 | B | 131242-WSD11-DR-IP-1366-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1366 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8821 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1367 | B | 131242-WSD11-DR-IP-1367-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1367 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8822 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1368 | B | 131242-WSD11-DR-IP-1368-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1368 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8823 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1369 | B | 131242-WSD11-DR-IP-1369-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1369 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8824 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1370 | B | 131242-WSD11-DR-IP-1370-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1370 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8825 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1371 | B | 131242-WSD11-DR-IP-1371-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1371 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8826 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1372 | B | 131242-WSD11-DR-IP-1372-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1372 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8827 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1373 | B | 131242-WSD11-DR-IP-1373-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1373 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8828 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1374 | B | 131242-WSD11-DR-IP-1374-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1374 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8829 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1375 | B | 131242-WSD11-DR-IP-1375-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1375 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8830 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1376 | B | 131242-WSD11-DR-IP-1376-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1376 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8831 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1377 | B | 131242-WSD11-DR-IP-1377-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1377 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8832 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1378 | B | 131242-WSD11-DR-IP-1378-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1378 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8833 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1379 | B | 131242-WSD11-DR-IP-1379-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1379 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8834 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1380 | B | 131242-WSD11-DR-IP-1380-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1380 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8835 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1381 | B | 131242-WSD11-DR-IP-1381-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1381 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8836 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1382 | B | 131242-WSD11-DR-IP-1382-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1382 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8837 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1383 | B | 131242-WSD11-DR-IP-1383-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1383 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8838 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1384 | B | 131242-WSD11-DR-IP-1384-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1384 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8839 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1385 | B | 131242-WSD11-DR-IP-1385-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1385 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8840 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1386 | B | 131242-WSD11-DR-IP-1386-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1386 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8841 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1387 | B | 131242-WSD11-DR-IP-1387-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1387 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8842 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1388 | B | 131242-WSD11-DR-IP-1388-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1388 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8843 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1389 | B | 131242-WSD11-DR-IP-1389-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1389 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8844 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1390 | B | 131242-WSD11-DR-IP-1390-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1390 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8845 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1391 | B | 131242-WSD11-DR-IP-1391-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1391 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8846 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1392 | B | 131242-WSD11-DR-IP-1392-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1392 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8847 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1393 | B | 131242-WSD11-DR-IP-1393-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1393 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8848 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1394 | B | 131242-WSD11-DR-IP-1394-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1394 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8849 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1395 | B | 131242-WSD11-DR-IP-1395-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1395 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8850 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1396 | B | 131242-WSD11-DR-IP-1396-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1396 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8851 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1397 | B | 131242-WSD11-DR-IP-1397-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1397 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8852 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1398 | B | 131242-WSD11-DR-IP-1398-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1398 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8853 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1399 | B | 131242-WSD11-DR-IP-1399-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1399 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8854 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1400 | B | 131242-WSD11-DR-IP-1400-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8855 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1401 | B | 131242-WSD11-DR-IP-1401-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1401 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8856 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1402 | B | 131242-WSD11-DR-IP-1402-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1402 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8857 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1403 | B | 131242-WSD11-DR-IP-1403-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1403 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8858 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1404 | B | 131242-WSD11-DR-IP-1404-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1404 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8859 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1405 | B | 131242-WSD11-DR-IP-1405-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1405 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8860 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1406 | B | 131242-WSD11-DR-IP-1406-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1406 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8861 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1407 | B | 131242-WSD11-DR-IP-1407-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1407 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8862 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1408 | B | 131242-WSD11-DR-IP-1408-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1408 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8863 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1409 | B | 131242-WSD11-DR-IP-1409-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1409 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8864 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1410 | B | 131242-WSD11-DR-IP-1410-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1410 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8865 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1411 | B | 131242-WSD11-DR-IP-1411-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1411 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8866 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1412 | B | 131242-WSD11-DR-IP-1412-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1412 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8867 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1413 | B | 131242-WSD11-DR-IP-1413-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1413 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8868 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1414 | B | 131242-WSD11-DR-IP-1414-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1414 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8869 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1415 | B | 131242-WSD11-DR-IP-1415-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1415 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8870 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1416 | B | 131242-WSD11-DR-IP-1416-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1416 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8871 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1417 | B | 131242-WSD11-DR-IP-1417-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1417 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8872 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1418 | B | 131242-WSD11-DR-IP-1418-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1418 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8873 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1419 | B | 131242-WSD11-DR-IP-1419-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1419 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8874 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1420 | B | 131242-WSD11-DR-IP-1420-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1420 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8875 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1421 | B | 131242-WSD11-DR-IP-1421-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1421 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8876 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1422 | B | 131242-WSD11-DR-IP-1422-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1422 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8877 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1423 | B | 131242-WSD11-DR-IP-1423-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1423 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8878 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1424 | B | 131242-WSD11-DR-IP-1424-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1424 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8879 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1425 | B | 131242-WSD11-DR-IP-1425-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1425 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8880 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1426 | B | 131242-WSD11-DR-IP-1426-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1426 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8881 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1427 | B | 131242-WSD11-DR-IP-1427-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1427 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8882 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1428 | B | 131242-WSD11-DR-IP-1428-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1428 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8883 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1429 | B | 131242-WSD11-DR-IP-1429-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1429 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8884 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1430 | B | 131242-WSD11-DR-IP-1430-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1430 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8885 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1431 | B | 131242-WSD11-DR-IP-1431-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1431 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8886 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1432 | B | 131242-WSD11-DR-IP-1432-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1432 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8887 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1433 | B | 131242-WSD11-DR-IP-1433-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1433 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8888 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1434 | B | 131242-WSD11-DR-IP-1434-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1434 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8889 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1435 | B | 131242-WSD11-DR-IP-1435-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1435 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8890 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1436 | B | 131242-WSD11-DR-IP-1436-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1436 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8891 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1437 | B | 131242-WSD11-DR-IP-1437-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1437 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8892 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1438 | B | 131242-WSD11-DR-IP-1438-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1438 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8893 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1439 | B | 131242-WSD11-DR-IP-1439-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1439 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8894 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1440 | B | 131242-WSD11-DR-IP-1440-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1440 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8895 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1441 | B | 131242-WSD11-DR-IP-1441-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1441 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8896 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1442 | B | 131242-WSD11-DR-IP-1442-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1442 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8897 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1443 | B | 131242-WSD11-DR-IP-1443-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1443 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8898 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1444 | B | 131242-WSD11-DR-IP-1444-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1444 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8899 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1445 | B | 131242-WSD11-DR-IP-1445-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1445 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8900 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1446 | B | 131242-WSD11-DR-IP-1446-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1446 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8901 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1447 | B | 131242-WSD11-DR-IP-1447-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1447 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8902 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1448 | B | 131242-WSD11-DR-IP-1448-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1448 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8903 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1449 | B | 131242-WSD11-DR-IP-1449-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1449 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8904 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1450 | B | 131242-WSD11-DR-IP-1450-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1450 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8905 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1451 | B | 131242-WSD11-DR-IP-1451-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1451 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8906 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1452 | B | 131242-WSD11-DR-IP-1452-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1452 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8907 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1453 | B | 131242-WSD11-DR-IP-1453-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1453 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8908 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1454 | B | 131242-WSD11-DR-IP-1454-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1454 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8909 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1455 | B | 131242-WSD11-DR-IP-1455-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1455 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8910 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1456 | B | 131242-WSD11-DR-IP-1456-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1456 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8911 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1457 | B | 131242-WSD11-DR-IP-1457-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1457 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8912 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1458 | B | 131242-WSD11-DR-IP-1458-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1458 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8913 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1459 | B | 131242-WSD11-DR-IP-1459-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1459 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8914 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1460 | B | 131242-WSD11-DR-IP-1460-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1460 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8915 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1461 | B | 131242-WSD11-DR-IP-1461-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1461 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8916 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1462 | B | 131242-WSD11-DR-IP-1462-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1462 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8917 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1463 | B | 131242-WSD11-DR-IP-1463-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1463 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8918 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1464 | B | 131242-WSD11-DR-IP-1464-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1464 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8919 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1465 | B | 131242-WSD11-DR-IP-1465-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1465 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8920 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1466 | B | 131242-WSD11-DR-IP-1466-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1466 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8921 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1467 | B | 131242-WSD11-DR-IP-1467-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1467 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8922 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1468 | B | 131242-WSD11-DR-IP-1468-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1468 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8923 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1469 | B | 131242-WSD11-DR-IP-1469-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1469 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8924 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1470 | B | 131242-WSD11-DR-IP-1470-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1470 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8925 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1151 | B | 131242-WSD11-DR-IP-1151-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1151 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8926 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1152 | B | 131242-WSD11-DR-IP-1152-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1152 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8927 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1153 | B | 131242-WSD11-DR-IP-1153-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1153 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8928 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1154 | B | 131242-WSD11-DR-IP-1154-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1154 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8929 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1155 | B | 131242-WSD11-DR-IP-1155-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1155 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8930 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1156 | B | 131242-WSD11-DR-IP-1156-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1156 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8931 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1157 | B | 131242-WSD11-DR-IP-1157-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1157 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8932 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1158 | B | 131242-WSD11-DR-IP-1158-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1158 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8933 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1159 | B | 131242-WSD11-DR-IP-1159-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1159 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8934 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1160 | B | 131242-WSD11-DR-IP-1160-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1160 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8935 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1161 | B | 131242-WSD11-DR-IP-1161-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1161 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8936 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1162 | B | 131242-WSD11-DR-IP-1162-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1162 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8937 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1163 | B | 131242-WSD11-DR-IP-1163-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1163 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8938 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1164 | B | 131242-WSD11-DR-IP-1164-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1164 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8939 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1165 | B | 131242-WSD11-DR-IP-1165-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1165 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8940 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1166 | B | 131242-WSD11-DR-IP-1166-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1166 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8941 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1167 | B | 131242-WSD11-DR-IP-1167-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1167 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8942 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1168 | B | 131242-WSD11-DR-IP-1168-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1168 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8943 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1169 | B | 131242-WSD11-DR-IP-1169-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1169 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8944 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1170 | B | 131242-WSD11-DR-IP-1170-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8945 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1171 | B | 131242-WSD11-DR-IP-1171-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8946 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1172 | B | 131242-WSD11-DR-IP-1172-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1172 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8947 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1173 | B | 131242-WSD11-DR-IP-1173-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1173 | NA | "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000681&&001382 | 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 4 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8948 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1174 | B | 131242-WSD11-DR-IP-1174-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1174 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8949 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1175 | B | 131242-WSD11-DR-IP-1175-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1175 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8950 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1176 | B | 131242-WSD11-DR-IP-1176-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1176 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8951 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1177 | B | 131242-WSD11-DR-IP-1177-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1177 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8952 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1178 | B | 131242-WSD11-DR-IP-1178-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1178 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8953 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1179 | B | 131242-WSD11-DR-IP-1179-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1179 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8954 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1180 | B | 131242-WSD11-DR-IP-1180-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1180 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8955 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1181 | B | 131242-WSD11-DR-IP-1181-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1181 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8956 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1182 | B | 131242-WSD11-DR-IP-1182-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1182 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8957 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1183 | B | 131242-WSD11-DR-IP-1183-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1183 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8958 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1184 | B | 131242-WSD11-DR-IP-1184-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1184 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8959 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1185 | B | 131242-WSD11-DR-IP-1185-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1185 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8960 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1186 | B | 131242-WSD11-DR-IP-1186-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1186 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8961 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1187 | B | 131242-WSD11-DR-IP-1187-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1187 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8962 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1188 | B | 131242-WSD11-DR-IP-1188-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1188 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8963 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1189 | B | 131242-WSD11-DR-IP-1189-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1189 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8964 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1190 | B | 131242-WSD11-DR-IP-1190-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1190 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" && "THP Underground Piping and Cast in Details" | 2024-10-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000789&&001382 | 2024-10-30, 2025-06-16, 2025-08-13 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8965 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1191 | B | 131242-WSD11-DR-IP-1191-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1191 | NA | "THP Cast in Layout Inside Bio-solid Building" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-07-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000580&&001382 | 2024-07-23, 2025-06-16, 2025-08-13 | 00, 01 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8966 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1192 | B | 131242-WSD11-DR-IP-1192-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1192 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8967 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1193 | B | 131242-WSD11-DR-IP-1193-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1193 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8968 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1194 | B | 131242-WSD11-DR-IP-1194-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1194 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8969 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1195 | B | 131242-WSD11-DR-IP-1195-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1195 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8970 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1196 | B | 131242-WSD11-DR-IP-1196-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1196 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8971 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1197 | B | 131242-WSD11-DR-IP-1197-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1197 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8972 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1198 | B | 131242-WSD11-DR-IP-1198-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1198 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8973 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1199 | B | 131242-WSD11-DR-IP-1199-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1199 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8974 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1481 | B | 131242-WSD11-DR-IP-1481-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1481 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8975 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1482 | B | 131242-WSD11-DR-IP-1482-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1482 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8976 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1483 | B | 131242-WSD11-DR-IP-1483-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1483 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8977 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1484 | B | 131242-WSD11-DR-IP-1484-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1484 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8978 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1485 | B | 131242-WSD11-DR-IP-1485-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1485 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8979 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1486 | B | 131242-WSD11-DR-IP-1486-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1486 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8980 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1487 | B | 131242-WSD11-DR-IP-1487-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1487 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8981 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1488 | B | 131242-WSD11-DR-IP-1488-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1488 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8982 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1489 | B | 131242-WSD11-DR-IP-1489-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1489 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8983 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1490 | B | 131242-WSD11-DR-IP-1490-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1490 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8984 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1491 | B | 131242-WSD11-DR-IP-1491-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1491 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8985 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1492 | B | 131242-WSD11-DR-IP-1492-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1492 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8986 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1493 | B | 131242-WSD11-DR-IP-1493-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1493 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8987 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1494 | B | 131242-WSD11-DR-IP-1494-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1494 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8988 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1495 | B | 131242-WSD11-DR-IP-1495-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1495 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8989 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1496 | B | 131242-WSD11-DR-IP-1496-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1496 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8990 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1497 | B | 131242-WSD11-DR-IP-1497-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1497 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8991 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1498 | B | 131242-WSD11-DR-IP-1498-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1498 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8992 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1499 | B | 131242-WSD11-DR-IP-1499-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1499 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8993 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1500 | B | 131242-WSD11-DR-IP-1500-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1500 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8994 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1501 | B | 131242-WSD11-DR-IP-1501-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1501 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "Revised Design of THP Steel Structure Plinths (Rev F)" && "Revised Design of THP Steel Structure Plinths (Rev G)" && "THP Courtyard RC Plinth Detail" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-11-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-09-24 | G | 000844&&000845&&001363&&001382 | 2024-11-25, 2024-12-06, 2025-06-12, 2025-06-16, 2025-08-13, 2025-08-22, 2025-09-24 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
8995 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1502 | B | 131242-WSD11-DR-IP-1502-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1502 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8996 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1503 | B | 131242-WSD11-DR-IP-1503-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1503 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8997 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1504 | B | 131242-WSD11-DR-IP-1504-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1504 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8998 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1505 | B | 131242-WSD11-DR-IP-1505-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1505 | NA | " THP Courtyard Equipment Anchor Bolt Details" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 000845&&001382 | 2024-12-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
8999 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1506 | B | 131242-WSD11-DR-IP-1506-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1506 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9000 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1507 | B | 131242-WSD11-DR-IP-1507-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1507 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9001 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1508 | B | 131242-WSD11-DR-IP-1508-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1508 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9002 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1509 | B | 131242-WSD11-DR-IP-1509-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1509 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9003 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1510 | B | 131242-WSD11-DR-IP-1510-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1510 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9004 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1511 | B | 131242-WSD11-DR-IP-1511-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1511 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9005 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1512 | B | 131242-WSD11-DR-IP-1512-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1512 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9006 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1513 | B | 131242-WSD11-DR-IP-1513-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1513 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9007 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1514 | B | 131242-WSD11-DR-IP-1514-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1514 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9008 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1515 | B | 131242-WSD11-DR-IP-1515-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1515 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9009 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1516 | B | 131242-WSD11-DR-IP-1516-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1516 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9010 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1517 | B | 131242-WSD11-DR-IP-1517-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1517 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9011 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1518 | B | 131242-WSD11-DR-IP-1518-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1518 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9012 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1519 | B | 131242-WSD11-DR-IP-1519-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1519 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9013 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1520 | B | 131242-WSD11-DR-IP-1520-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1520 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9014 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1521 | B | 131242-WSD11-DR-IP-1521-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1521 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9015 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1522 | B | 131242-WSD11-DR-IP-1522-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1522 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9016 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1523 | B | 131242-WSD11-DR-IP-1523-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1523 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9017 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1524 | B | 131242-WSD11-DR-IP-1524-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1524 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9018 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1525 | B | 131242-WSD11-DR-IP-1525-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1525 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9019 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1526 | B | 131242-WSD11-DR-IP-1526-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1526 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9020 | 001382 | 01 | Karthik | EICA | NA | 131242 | WSD11 | DR | IP | 1527 | B | 131242-WSD11-DR-IP-1527-B | 2025-08-13 | THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-02 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-DR-1527 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 20 | AWC | 2025-08-13 | B | 001382 | 2025-06-16, 2025-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9021 | 001383 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5201 | 0 | 131242-WSD11-DR-M-5201-0 | 2025-06-16 | GA for Bypass Control Valve 1 | NA | 2025-07-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5201 | NA | "GA for Bypass Control Valve 1" | 2025-06-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-06 | 294 | PEN | 2025-06-16 | 0 | 001383 | 2025-06-16 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-08-01 |  | 0 | PEN | PEN
9022 | 001384 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5202 | 0 | 131242-WSD11-DR-M-5202-0 | 2025-06-16 | GA for Bypass Control Valve 2 | NA | 2025-07-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5202 | NA | "GA for Bypass Control Valve 2" | 2025-06-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-06 | 294 | PEN | 2025-06-16 | 0 | 001384 | 2025-06-16 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-08-01 |  | 0 | PEN | PEN
9023 | 001385 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0089 | 0 | 131242-WSD11-QA-M-0089-0 | 2025-06-16 | FAT report-THP train 1 & 2 flash tank discharge pumps, reactor feed pumps typical test report | NA | 2025-07-14 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSD11-QA-0089 | NA | "FAT report-THP train 1 & 2 flash tank discharge pumps, reactor feed pumps typical test report" | 2025-06-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-06 | 84 | APP | 2025-06-16 | 0 | 001385 | 2025-06-16 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9024 | 001386 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0088 | 0 | 131242-WSD11-QA-M-0088-0 | 2025-06-18 | FAT Report for SS Pipes in Sitewide Pipe rack (Cyclect - 4th batch) | NA | 2025-07-16 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-QA-0088 | NA | "FAT Report for SS Pipes in Sitewide Pipe rack (Cyclect - 4th batch)" | 2025-06-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-08 | 76 | AWC | 2025-06-18 | 0 | 001386 | 2025-06-18 | 00 | 1 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
9025 | 001387 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | BS | 0009 | 0 | 131242-WSW41-QA-BS-0009-0 | 2025-06-18 | Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-16 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-QA-0009 | NA | "Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation)" && "Monthly Concrete Cube Records for Structural works (02 24)" | 2024-06-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-02 | 26 | AWC | 2025-06-18 | 0 | 000532&&001387 | 2024-06-25, 2025-06-18 | 00 | 2 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9026 | 001388 | 00 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0003 | 0 | 131242-WSD11-RT-S-0003-0 | 2025-06-18 | Project Safety Review Report for THP Installation | Approved | 2025-07-16 | 2025-08-25 | Approved |  | YES | NA |  | 131242-WSD11-RT-0003 | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-02 | 68 | APP | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
9027 | 001389 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0090 | 0 | 131242-WSW41-QA-M-0090-0 | 2025-06-18 | FAT Report for Top Manway (900x900mm & 400x400mm) | NA | 2025-07-16 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0090 | NA | "FAT Report for Top Manway (900x900mm & 400x400mm) " | 2025-06-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-08 | 76 | APP | 2025-06-18 | 0 | 001389 | 2025-06-18 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9028 | 001390 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0014 | 0 | 131242-WST02-CD-I-0014-0 | 2025-06-18 | Electrical Signal List for SSN -MCC-1001A/1001B | Rev 0: Rejected. Refer to attached file for comments. | 2025-07-16 | 2025-07-16 | Rejected | 2025-08-05 | NO | Overdue |  | 131242-WST02-CD-0014 | NA | "Electrical Signal List for SSN -MCC-1001A/1001B " | 2025-06-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-08 | 28 | REJ | 2025-06-18 | 0 | 001390 | 2025-06-18 | 00 | 1 | Rejected | REJ | 2025-08-05 | Overdue | 0 | REJ | REJ
9029 | 001391 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8002 | 0 | 131242-WST02-CL-BF-8002-0 | 2025-06-19 | Trust Block Calculation Report for Fire Hydrant | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-17 | 2025-06-30 | Not Approved | 2025-07-18 | YES | Resubmitted |  | 131242-WST02-CL-8002 | NA | "Thrust Block Calculation Report for Fire Hydrant " && "Trust Block Calculation Report for Fire Hydrant " | 2025-06-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-09 | 11 | NAP | 2025-07-11 | 0 | 001391 | 2025-06-19, 2025-07-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9030 | 001391 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8002 | 0 | 131242-WST02-CL-BF-8002-0 | 2025-07-11 | Thrust Block Calculation Report for Fire Hydrant | R1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-31 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-CL-8002 | NA | "Thrust Block Calculation Report for Fire Hydrant " && "Trust Block Calculation Report for Fire Hydrant " | 2025-06-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 171 | AWC | 2025-07-11 | 0 | 001391 | 2025-06-19, 2025-07-11 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
9031 | 001392 | 00 | Muthu | BIM | NA | 131242 | WSW41 | MS | IM | 0001 | 0 | 131242-WSW41-MS-IM-0001-0 | 2025-06-19 | Laser Scanning Method of Statement | NA | 2025-07-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-03 | 291 | PEN | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | PEN | PEN
9032 | 001393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0001 | 0 | 131242-WSD11-RT-EL-0001-0 | 2025-06-20 | THP Protected Corridor Lux Simulation Report | Rev 0: Approved with comments. To revise and resubmit. | 2025-07-18 | 2025-08-11 | Approved with Comments | 2025-08-29 | NO | Overdue |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-04 | 52 | AWC | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC | 2025-08-29 | Overdue | 0 | AWC | AWC
9033 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-1000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9034 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-1001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9035 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-1002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9036 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-1003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9037 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-1004_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9038 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-2000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9039 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 5002_URA | A | 131242-WSD11-DR-A-5002_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-5002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-13 | 35 | NAP | 2025-06-23 | A | 001394 | 2025-06-23 | 00 | 1 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9040 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 5003_URA | A | 131242-WSD11-DR-A-5003_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-5003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-13 | 35 | NAP | 2025-06-23 | A | 001394 | 2025-06-23 | 00 | 1 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9041 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 5004_URA | A | 131242-WSD11-DR-A-5004_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-5004_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-13 | 35 | NAP | 2025-06-23 | A | 001394 | 2025-06-23 | 00 | 1 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9042 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-0001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9043 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-0002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9044 | 001394 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA-A | 2025-06-23 | ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSD11-DR-0003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 35 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9045 | 001395 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0022 | 0 | 131242-WST02-QA-EI-0022-0 | 2025-06-23 | Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-21 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-QA-0022 | NA | "Material Submission - Galvanized steel Louvers doors, Windows & Ironmongery. (Hang Hong Contractor Pte Ltd) " && "Vendor Manufacturing Inspection Test Plan For Conductive Probe Level Switches/ Leak Detector" | 2025-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 21 | AWC | 2025-06-23 | 0 | 001348&&001395 | 2025-06-06, 2025-06-23 | 00 | 2 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9046 | 001396 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0023 | 0 | 131242-WST02-QA-I-0023-0 | 2025-06-23 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-21 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-QA-0023 | NA | "Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd)" && "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-13 | 21 | AWC | 2025-12-09 | 0 | 001396&&001415&&001891 | 2025-06-23, 2025-06-27, 2025-12-09 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9047 | 001397 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | M | 0091 | 0 | 131242-WST02-QA-M-0091-0 | 2025-06-23 | FAT Report for Progressive Cavity Pumps (NETZSCH) | Rev 0: Approved | 2025-07-21 | 2025-07-23 | Approved |  | YES | NA |  | 131242-WST02-QA-0091 | NA | "FAT Report for Progressive Cavity Pumps (NETZSCH)" | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-13 | 30 | APP | 2025-06-23 | 0 | 001397 | 2025-06-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9048 | 001398 | 00 | Bryan | BS | NA | 131242 | WSW41 | MS | BS | 0001 | 0 | 131242-WSW41-MS-BS-0001-0 | 2025-06-23 | MSRA, SWP for fire protection services | Approved | 2025-07-21 | 2025-08-06 | Approved |  | YES | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-07 | 44 | APP | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | APP | APP
9049 | 001398 | 01 | Bryan | BS | NA | 131242 | WSW41 | MS | BS | 0001 | 1 | 131242-WSW41-MS-BS-0001-1 | 2025-12-04 | MSRA, SWP for fire protection services | Approved | 2025-12-24 | 2025-12-17 | Approved |  | YES | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-18 | 13 | APP | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | APP | APP
9050 | 001398 | 02 | Bryan | BS | NA | 131242 | WSW41 | MS | BS | 0001 | 2 | 131242-WSW41-MS-BS-0001-2 | 2026-02-13 | MSRA, SWP for fire protection services | Approved | 2026-03-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-27 | 52 | PEN | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | PEN | PEN
9051 | 001399 | 00 | Bryan | CSA | NA | 131242 | WSW41 | MS | C | 0033 | 0 | 131242-WSW41-MS-C-0033-0 | 2025-06-23 | MSRA SWP for Wet blasting Linabond Works | R0: Approved | 2025-07-21 | 2025-06-30 | Approved |  | YES | NA |  | 131242-WSW41-MS-0033 | NA | "MSRA SWP for Wet blasting Linabond Works" | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-13 | 7 | APP | 2025-06-23 | 0 | 001399 | 2025-06-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9052 | 001400 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0047 | 0 | 131242-WSW41-MI-C-0047-0 | 2025-06-23 | CSA Meeting Minutes 0047 & 0048_15052025 and10062025 | For information | 2025-07-21 | 2025-07-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0047 | NA | "CSA Meeting Minutes 0047 & 0048_15052025 and10062025" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-13 | 11 | INF | 2025-06-23 | 0 | 001400 | 2025-06-23 | 00 | 1 | For Information | INF | 2025-07-24 | Overdue | 0 | INF | INF
9053 | 001400 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0048 | 0 | 131242-WSW41-MI-C-0048-0 | 2025-06-23 | CSA Meeting Minutes 0047 & 0048_15052025 and10062025 | For information | 2025-07-21 | 2025-07-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0048 | NA | "CSA Meeting Minutes 0047 & 0048_15052025 and10062025" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-13 | 11 | INF | 2025-06-23 | 0 | 001400 | 2025-06-23 | 00 | 1 | For Information | INF | 2025-07-24 | Overdue | 0 | INF | INF
9054 | 001401 | 00 | Jun | EICA | NA | 131242 | WSW41 | VI | E | 0025 | 0 | 131242-WSW41-VI-E-0025-0 | 2025-06-23 | Vendor Approval for Lighting and Small Power Material (Hong An) | Rev 0: Rejected. To resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-07-20 | Rejected | 2025-08-07 | YES | Resubmitted |  | 131242-WSW41-VI-0025 | NA | "Vendor Approval for Lighting and Small Power Material (Hong An)" | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-13 | 27 | REJ | 2025-08-14 | 1 | 001401 | 2025-06-23, 2025-08-14 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
9055 | 001401 | 01 | Jun | EICA | NA | 131242 | WSW41 | VI | E | 0025 | 1 | 131242-WSW41-VI-E-0025-1 | 2025-08-14 | Vendor Approval for Lighting and Small Power Material (Hong An) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-03 | 2025-09-03 | Approved with Comments | 2025-09-23 | NO | Overdue |  | 131242-WSW41-VI-0025 | NA | "Vendor Approval for Lighting and Small Power Material (Hong An)" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-28 | 20 | AWC | 2025-08-14 | 1 | 001401 | 2025-06-23, 2025-08-14 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-23 | Overdue | 0 | AWC | AWC
9056 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 0 | 131242-WST02-DR-BH-1002-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
9057 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 0 | 131242-WST02-DR-BH-1003-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
9058 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 0 | 131242-WST02-DR-BH-1004-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
9059 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 0 | 131242-WST02-DR-BH-1005-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
9060 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 0 | 131242-WST02-DR-BH-1006-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | NAP | NAP
9061 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 0 | 131242-WST02-DR-BH-1007-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9062 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 0 | 131242-WST02-DR-BH-1008-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9063 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 0 | 131242-WST02-DR-BH-1009-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | NAP | NAP
9064 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 0 | 131242-WST02-DR-BH-1010-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9065 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 0 | 131242-WST02-DR-BH-1011-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9066 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 0 | 131242-WST02-DR-BH-1012-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9067 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 0 | 131242-WST02-DR-BH-1013-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9068 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 0 | 131242-WST02-DR-BH-1014-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9069 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 0 | 131242-WST02-DR-BH-1015-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9070 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 0 | 131242-WST02-DR-BH-1016-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9071 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 0 | 131242-WST02-DR-BH-1017-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9072 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 0 | 131242-WST02-DR-BH-1018-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9073 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 0 | 131242-WST02-DR-BH-1019-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9074 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 0 | 131242-WST02-DR-BH-1020-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9075 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 0 | 131242-WST02-DR-BH-1022-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9076 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 0 | 131242-WST02-DR-BH-1023-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9077 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 0 | 131242-WST02-DR-BH-1024-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | NAP | NAP
9078 | 001402 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 0 | 131242-WST02-DR-BH-1021-0 | 2025-06-23 | ACMV LCP GA & Wiring Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-21 | 2025-07-31 | Not Approved | 2025-08-20 | YES | Resubmitted |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 38 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9079 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 1 | 131242-WST02-DR-BH-1002-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
9080 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 1 | 131242-WST02-DR-BH-1003-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
9081 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 1 | 131242-WST02-DR-BH-1004-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
9082 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 1 | 131242-WST02-DR-BH-1005-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
9083 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 1 | 131242-WST02-DR-BH-1006-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | NAP | NAP
9084 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 1 | 131242-WST02-DR-BH-1007-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9085 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 1 | 131242-WST02-DR-BH-1008-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9086 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 1 | 131242-WST02-DR-BH-1009-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | NAP | NAP
9087 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 1 | 131242-WST02-DR-BH-1010-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9088 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 1 | 131242-WST02-DR-BH-1011-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9089 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 1 | 131242-WST02-DR-BH-1012-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9090 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 1 | 131242-WST02-DR-BH-1013-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9091 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 1 | 131242-WST02-DR-BH-1014-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9092 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 1 | 131242-WST02-DR-BH-1015-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9093 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 1 | 131242-WST02-DR-BH-1016-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9094 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 1 | 131242-WST02-DR-BH-1017-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9095 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 1 | 131242-WST02-DR-BH-1018-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9096 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 1 | 131242-WST02-DR-BH-1019-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9097 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 1 | 131242-WST02-DR-BH-1020-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9098 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 1 | 131242-WST02-DR-BH-1022-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9099 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 1 | 131242-WST02-DR-BH-1023-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9100 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 1 | 131242-WST02-DR-BH-1024-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | NAP | NAP
9101 | 001402 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 1 | 131242-WST02-DR-BH-1021-1 | 2025-08-27 | ACMV LCP GA & Wiring Drawing | Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-10-22 | Not Approved | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 56 | NAP | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9102 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 1 | 131242-WST02-DR-BH-1002-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
9103 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 1 | 131242-WST02-DR-BH-1003-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
9104 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 1 | 131242-WST02-DR-BH-1004-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
9105 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 1 | 131242-WST02-DR-BH-1005-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
9106 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 1 | 131242-WST02-DR-BH-1006-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
9107 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 1 | 131242-WST02-DR-BH-1007-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9108 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 1 | 131242-WST02-DR-BH-1008-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9109 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 1 | 131242-WST02-DR-BH-1009-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | AWC | AWC
9110 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 1 | 131242-WST02-DR-BH-1010-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9111 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 1 | 131242-WST02-DR-BH-1011-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9112 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 1 | 131242-WST02-DR-BH-1012-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9113 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 1 | 131242-WST02-DR-BH-1013-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9114 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 1 | 131242-WST02-DR-BH-1014-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9115 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 1 | 131242-WST02-DR-BH-1015-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9116 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 1 | 131242-WST02-DR-BH-1016-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9117 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 1 | 131242-WST02-DR-BH-1017-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9118 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 1 | 131242-WST02-DR-BH-1018-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9119 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 1 | 131242-WST02-DR-BH-1019-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9120 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 1 | 131242-WST02-DR-BH-1020-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9121 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 1 | 131242-WST02-DR-BH-1021-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9122 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 1 | 131242-WST02-DR-BH-1022-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9123 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 1 | 131242-WST02-DR-BH-1023-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
9124 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 1 | 131242-WST02-DR-BH-1024-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
9125 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1025 | 1 | 131242-WST02-DR-BH-1025-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
9126 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1026 | 1 | 131242-WST02-DR-BH-1026-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | AWC | AWC
9127 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1027 | 1 | 131242-WST02-DR-BH-1027-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9128 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1028 | 1 | 131242-WST02-DR-BH-1028-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1028 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9129 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1029 | 1 | 131242-WST02-DR-BH-1029-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1029 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9130 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1030 | 1 | 131242-WST02-DR-BH-1030-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1030 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9131 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1031 | 1 | 131242-WST02-DR-BH-1031-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1031 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9132 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1032 | 1 | 131242-WST02-DR-BH-1032-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1032 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9133 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1033 | 1 | 131242-WST02-DR-BH-1033-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1033 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9134 | 001402 | 02 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1034 | 1 | 131242-WST02-DR-BH-1034-1 | 2025-11-21 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-11 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-1034 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-05 | 20 | AWC | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9135 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1002 | 1 | 131242-WST02-DR-BH-1002-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP | 2026-03-24 |  | 0 | PEN | PEN
9136 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1003 | 1 | 131242-WST02-DR-BH-1003-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP | 2026-03-24 |  | 0 | PEN | PEN
9137 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1004 | 1 | 131242-WST02-DR-BH-1004-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | PEN | PEN
9138 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1005 | 1 | 131242-WST02-DR-BH-1005-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | PEN | PEN
9139 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1006 | 1 | 131242-WST02-DR-BH-1006-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | PEN | PEN
9140 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1007 | 1 | 131242-WST02-DR-BH-1007-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
9141 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1008 | 1 | 131242-WST02-DR-BH-1008-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
9142 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1009 | 1 | 131242-WST02-DR-BH-1009-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | PEN | PEN
9143 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1010 | 1 | 131242-WST02-DR-BH-1010-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
9144 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1011 | 1 | 131242-WST02-DR-BH-1011-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9145 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1012 | 1 | 131242-WST02-DR-BH-1012-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9146 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1013 | 1 | 131242-WST02-DR-BH-1013-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9147 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1014 | 1 | 131242-WST02-DR-BH-1014-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9148 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1015 | 1 | 131242-WST02-DR-BH-1015-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9149 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1016 | 1 | 131242-WST02-DR-BH-1016-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9150 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1017 | 1 | 131242-WST02-DR-BH-1017-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9151 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1018 | 1 | 131242-WST02-DR-BH-1018-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9152 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1019 | 1 | 131242-WST02-DR-BH-1019-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9153 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1020 | 1 | 131242-WST02-DR-BH-1020-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9154 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1021 | 1 | 131242-WST02-DR-BH-1021-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9155 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1022 | 1 | 131242-WST02-DR-BH-1022-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9156 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1023 | 1 | 131242-WST02-DR-BH-1023-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2026-03-24 |  | 0 | PEN | PEN
9157 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1024 | 1 | 131242-WST02-DR-BH-1024-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP | 2026-03-24 |  | 0 | PEN | PEN
9158 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1025 | 1 | 131242-WST02-DR-BH-1025-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | PEN | PEN
9159 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1026 | 1 | 131242-WST02-DR-BH-1026-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP | 2026-03-24 |  | 0 | PEN | PEN
9160 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1027 | 1 | 131242-WST02-DR-BH-1027-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9161 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1028 | 1 | 131242-WST02-DR-BH-1028-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1028 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9162 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1029 | 1 | 131242-WST02-DR-BH-1029-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1029 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9163 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1030 | 1 | 131242-WST02-DR-BH-1030-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1030 | NA | "ACMV LCP GA & Wiring Drawing" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-02-04 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9164 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1031 | 1 | 131242-WST02-DR-BH-1031-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1031 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9165 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1032 | 1 | 131242-WST02-DR-BH-1032-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1032 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9166 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1033 | 1 | 131242-WST02-DR-BH-1033-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1033 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9167 | 001402 | 03 | Yuen Fatt | EICA | NA | 131242 | WST02 | DR | BH | 1034 | 1 | 131242-WST02-DR-BH-1034-1 | 2026-02-04 | ACMV LCP GA & Wiring Drawing | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1034 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
9168 | 001403 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 0 | 131242-WST02-QA-M-0092-0 | 2025-06-23 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-21 | 2025-08-01 | Approved with Comments | 2025-08-21 | YES | Resubmitted |  | 131242-WST02-QA-0092 | NA | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-13 | 39 | AWC | 2026-01-08 | 3 | 001403 | 2025-06-23, 2025-09-09, 2025-11-10, 2026-01-08 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
9169 | 001403 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 1 | 131242-WST02-QA-M-0092-1 | 2025-09-09 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-29 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-QA-0092 | NA | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-23 | 62 | AWC | 2026-01-08 | 3 | 001403 | 2025-06-23, 2025-09-09, 2025-11-10, 2026-01-08 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
9170 | 001403 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 2 | 131242-WST02-QA-M-0092-2 | 2025-11-10 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-23 | Approved with Comments | 2026-01-12 | YES | Resubmitted |  | 131242-WST02-QA-0092 | NA | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-24 | 43 | AWC | 2026-01-08 | 3 | 001403 | 2025-06-23, 2025-09-09, 2025-11-10, 2026-01-08 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
9171 | 001403 | 03 | Radha | QAQC | NA | 131242 | WST02 | QA | M | 0092 | 3 | 131242-WST02-QA-M-0092-3 | 2026-01-08 | FAT Report for Chemical Dosing Pumps (PROMINENT) | Rev 3: Approved | 2026-01-28 | 2030-01-01 | Approved |  | YES | NA |  | 131242-WST02-QA-0092 | NA | "FAT Report for Chemical Dosing Pumps (PROMINENT) " | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365) | 2026-01-22 | 1454 | APP | 2026-01-08 | 3 | 001403 | 2025-06-23, 2025-09-09, 2025-11-10, 2026-01-08 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
9172 | 001404 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PO | M | 0023 | 0 | 131242-WSW41-PO-M-0023-0 | 2025-06-23 | Unpriced PO for Flow Control Valve for TCI & DC Stream (KSB) | Rev 0: For Information | 2025-07-21 | 2025-07-31 | For Information |  | YES | NA |  | 131242-WSW41-PO-0023 | NA | "Unpriced PO for Flow Control Valve for TCI & DC Stream (KSB)" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-13 | 38 | INF | 2025-06-23 | 0 | 001404 | 2025-06-23 | 00 | 1 | For Information | INF | 2025-08-20 | Overdue | 0 | INF | INF
9173 | 001405 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PO | M | 0024 | 0 | 131242-WSW41-PO-M-0024-0 | 2025-06-23 | Unpriced PO for Air Flow Control Valve (Emile Egger) (Effektiv) | Rev 0: For Information Only. | 2025-07-21 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0024 | NA | "Unpriced PO for Air Flow Control Valve (Emile Egger) (Effektiv)" | 2025-06-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-13 | 154 | INF | 2025-06-23 | 0 | 001405 | 2025-06-23 | 00 | 1 | For Information | INF | 2025-12-12 | Overdue | 0 | INF | INF
9174 | 001406 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0010 | 0 | 131242-WST02-DS-I-0010-0 | 2025-06-25 | Datasheet for Temperature Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-23 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DS-0010 | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-09 | 103 | AWC | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9175 | 001407 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0043 | 0 | 131242-WSD11-DS-M-0043-0 | 2025-06-25 | Steam Safety Relief Valve Datasheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-23 | 2025-07-08 | Approved with Comments | 2025-07-28 | YES | Resubmitted |  | 131242-WSD11-DS-0043 | NA | "Steam Safety Relief Valve Datasheet" | 2025-06-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 13 | AWC | 2025-10-23 | 1 | 001407 | 2025-06-25, 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9176 | 001407 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0043 | 1 | 131242-WSD11-DS-M-0043-1 | 2025-10-23 | Steam Safety Relief Valve Datasheet | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-12 | 2026-01-07 | Approved with Comments | 2026-01-27 | NO | Overdue |  | 131242-WSD11-DS-0043 | NA | "Steam Safety Relief Valve Datasheet" | 2025-06-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 76 | AWC | 2025-10-23 | 1 | 001407 | 2025-06-25, 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-27 | Overdue | 0 | AWC | AWC
9177 | 001408 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0044 | 0 | 131242-WSD11-DS-M-0044-0 | 2025-06-25 | Steam Strainer Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-23 | 2025-07-08 | Approved with Comments | 2025-07-28 | NO | Overdue |  | 131242-WSD11-DS-0044 | NA | "Steam Strainer Data Sheet" | 2025-06-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 13 | AWC | 2025-06-25 | 0 | 001408 | 2025-06-25 | 00 | 1 | Approved with Comments | AWC | 2025-07-28 | Overdue | 0 | AWC | AWC
9178 | 001409 | 00 | Jun | EICA | NA | 131242 | WST02 | MS | E | 0015 | 0 | 131242-WST02-MS-E-0015-0 | 2025-06-26 | MSRA for LVSG, MCC, MDB, DB & MCP Shifting and Installation Works at SSN Electrical Building | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-24 | 2025-08-20 | Approved with Comments | 2025-09-09 | NO | Overdue |  | 131242-WST02-MS-0015 | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting and Installation Works at SSN Electrical Building" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 55 | AWC | 2025-06-26 | 0 | 001409 | 2025-06-26 | 00 | 1 | Approved with Comments | AWC | 2025-09-09 | Overdue | 0 | AWC | AWC
9179 | 001410 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5104 | A | 131242-WSD11-DR-I-5104-A | 2025-06-26 | Hook-up Drawing for Pressure Switch (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5104 | NA | "Hook-up Drawing for Pressure Switch (Cambi Loose Items)" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 166 | NAP | 2025-06-26 | A | 001410 | 2025-06-26 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9180 | 001410 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5105 | A | 131242-WSD11-DR-I-5105-A | 2025-06-26 | Hook-up Drawing for Pressure Switch (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5105 | NA | "Hook-up Drawing for Pressure Switch (Cambi Loose Items)" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 166 | NAP | 2025-06-26 | A | 001410 | 2025-06-26 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9181 | 001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5106 | A | 131242-WSD11-DR-I-5106-A | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5106 | NA | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 166 | NAP | 2025-06-26 | A | 001411 | 2025-06-26 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9182 | 001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5107 | A | 131242-WSD11-DR-I-5107-A | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5107 | NA | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 166 | NAP | 2025-06-26 | A | 001411 | 2025-06-26 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9183 | 001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5108 | A | 131242-WSD11-DR-I-5108-A | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5108 | NA | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 166 | NAP | 2025-06-26 | A | 001411 | 2025-06-26 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9184 | 001411 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5109 | A | 131242-WSD11-DR-I-5109-A | 2025-06-26 | Hook-up Drawing for Temperature Transmitter (Cambi Loose Items) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-07-24 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-5109 | NA | "Hook-up Drawing for Temperature Transmitter (Cambi Loose Items)" | 2025-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 166 | NAP | 2025-06-26 | A | 001411 | 2025-06-26 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9185 | 001412 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PC | W | 0024 | 0 | 131242-WSW41-PC-W-0024-0 | 2025-06-27 | Payment Claim No.24 | Rev (0): Approved. Please refer to S.O. correspondence no. 366 dated 30 June 2025. | 2025-07-25 | 2025-07-08 | Approved |  | YES | NA |  | 131242-WSW41-PC-0024 | NA | " Payment Claim No.24" | 2025-06-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-17 | 11 | APP | 2025-06-27 | 0 | 001412 | 2025-06-27 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9186 | 001413 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | S | 0001 | 0 | 131242-WSW41-QA-S-0001-0 | 2025-06-27 | ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission | For Information | 2025-07-25 | 2025-08-07 | For Information |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-11 | 41 | INF | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | INF | INF
9187 | 001414 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0024 | 0 | 131242-WST02-QA-A-0024-0 | 2025-06-27 | Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-25 | 2025-07-04 | Approved with Comments | 2025-07-24 | NO | Overdue |  | 131242-WST02-QA-0024 | NA | "Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction)" && "Vendor Manufacturing Inspection test plan for Pressure Gauges " | 2025-06-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-17 | 7 | AWC | 2025-07-02 | 0 | 001414&&001427 | 2025-06-27, 2025-07-02 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9188 | 001415 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0023 | 0 | 131242-WST02-QA-A-0023-0 | 2025-06-27 | Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-25 | 2025-07-28 | Approved with Comments | 2025-08-15 | NO | Overdue |  | 131242-WST02-QA-0023 | NA | "Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd)" && "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | 2025-06-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-11 | 31 | AWC | 2025-12-09 | 0 | 001396&&001415&&001891 | 2025-06-23, 2025-06-27, 2025-12-09 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9189 | 001416 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | RT | C | 0015 | 0 | 131242-WSW41-RT-C-0015-0 | 2025-06-27 | Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report | For Information. Please submit pile ecc report with licensed surveyor endorsement. | 2025-07-25 | 2025-07-14 | For Information | 2025-08-01 | NO | Overdue |  | 131242-WSW41-RT-0015 | NA | "Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report " && "C4B Monthly Progress Report Number No.15 (07 24)" | 2024-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-11 | 17 | INF | 2025-06-27 | 0 | 000658&&001416 | 2024-08-19, 2025-06-27 | 00 | 2 | For Information | INF | 2025-08-01 | Overdue | 0 | INF | INF
9190 | 001417 | 00 | K Balaji | Mech | NA | 131242 | WST02 | MS | M | 0003 | 0 | 131242-WST02-MS-M-0003-0 | 2025-06-28 | Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-08-11 | Approved with Comments | 2025-08-29 | YES | Resubmitted |  | 131242-WST02-MS-0003 | NA | "Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack" | 2025-06-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-18 | 44 | AWC | 2025-08-29 | 1 | 001417 | 2025-06-28, 2025-08-29 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9191 | 001417 | 01 | K Balaji | Mech | NA | 131242 | WST02 | MS | M | 0003 | 1 | 131242-WST02-MS-M-0003-1 | 2025-08-29 | Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-18 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-MS-0003 | NA | "Method Statement for the Installation of Equipment and Piping at C4B SSN Tank Area and SSN Piperack" | 2025-06-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-12 | 122 | AWC | 2025-08-29 | 1 | 001417 | 2025-06-28, 2025-08-29 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
9192 | 001418 | 00 | Aaron | CSA | NA | NA | NA | NA | NA | 9999 | 1 | NA-NA-NA-NA-NA-NA | 2025-07-01 | Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement | R0: Not Approved. Please refer to comment sheet for submission. | 2025-07-29 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | NA-NA-NA-9999 | NA | "NA" && "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | 2025-07-01 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 27 | NAP | 2025-07-01 | 1 | 001418&&002022&&002023&&002024 | 2025-07-01 | 00 | 4 | Not Approved | NAP | 2025-08-15 | Overdue | 0 | NAP | NAP
9193 | 001419 | 00 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0004 | 0 | 131242-WSD11-RT-S-0004-0 | 2025-07-01 | Project Safety Review for SSN Steel Structure and MEICA Equipment Installation | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-16 | Not Approved | 2025-08-05 | YES | Resubmitted |  | 131242-WSD11-RT-0004 | NA | "H2S Dispersion Simulation And Risk Assessement Report" && "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" && "THP Harmonics Study Report" | 2024-12-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 15 | NAP | 2025-09-03 | 1 | 000908&&001311&&001419 | 2024-12-16, 2025-05-19, 2025-07-01, 2025-07-28, 2025-09-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
9194 | 001419 | 01 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0004 | 1 | 131242-WSD11-RT-S-0004-1 | 2025-09-03 | Project Safety Review for SSN Steel Structure and MEICA Equipment Installation | R1: Not Approved. Please refer to comment sheet for resubmission | 2025-09-23 | 2025-10-06 | Not Approved | 2025-10-24 | NO | Overdue |  | 131242-WSD11-RT-0004 | NA | "H2S Dispersion Simulation And Risk Assessement Report" && "Project Safety Review for SSN Steel Structure and MEICA Equipment Installation" && "THP Harmonics Study Report" | 2024-12-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-17 | 33 | NAP | 2025-09-03 | 1 | 000908&&001311&&001419 | 2024-12-16, 2025-05-19, 2025-07-01, 2025-07-28, 2025-09-03 | 00, 01 | 5 | Not Approved | NAP | 2025-10-24 | Overdue | 0 | NAP | NAP
9195 | 001420 | 00 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0012 | 1 | 131242-WSW41-RT-C-0012-1 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-RT-0012 | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 13 | AWC | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9196 | 001420 | 00 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0013 | 1 | 131242-WSW41-RT-C-0013-1 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSW41-RT-0013 | NA | "C4B Monthly Progress Report Number No.13 (05 24)" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Quarterly Safety Review Follow Up on SSN RC Works" | 2024-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 13 | AWC | 2025-07-01 | 1 | 000520&&000852&&001420 | 2024-06-12, 2024-11-28, 2025-07-01 | 00 | 3 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9197 | 001420 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0003 | 0 | 131242-WST02-RT-S-0003-0 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-RT-0003 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 13 | AWC | 2025-07-01 | 0 | 000490&&000752&&001420 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9198 | 001420 | 00 | Max | HSE | NA | 131242 | WSD11 | RT | S | 0005 | 0 | 131242-WSD11-RT-S-0005-0 | 2025-07-01 | Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-29 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WSD11-RT-0005 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "THP Protection Coordination Study Report" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-15 | 13 | AWC | 2025-07-01 | 0 | 001159&&001420 | 2025-03-25, 2025-07-01 | 00 | 2 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9199 | 001421 | 00 | Aaron | CSA | NA | WD | WSW41 | NA | NA | 9999 | 0 | WD-WSW41-NA-NA-NA-NA | 2025-07-01 | C4B ST621 (Site Wide Pipe Rack) - BCA WD | For information | 2025-07-29 | 2025-07-28 | For Information |  | YES | NA |  | WD-WSW41-NA-9999 | NA | "C4B ST621 (Site Wide Pipe Rack) - BCA WD" | 2025-07-01 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-07-21 | 27 | INF | 2025-07-01 | 0 | 001421 | 2025-07-01 | 00 | 1 | For Information | INF | 2025-08-15 | Overdue | 0 | INF | INF
9200 | 001422 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0094 | 0 | 131242-WSW41-QA-M-0094-0 | 2025-07-02 | FAT Report for Parabolic Screen | NA | 2025-07-30 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0094 | NA | "FAT Report for Parabolic Screen" | 2025-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-22 | 68 | APP | 2025-07-02 | 0 | 001422 | 2025-07-02 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9201 | 001423 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0093 | 0 | 131242-WSW41-QA-M-0093-0 | 2025-07-02 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 5th batch) | NA | 2025-07-30 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0093 | NA | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 5th batch)" | 2025-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-22 | 62 | APP | 2025-07-02 | 0 | 001423 | 2025-07-02 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9202 | 001424 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0010 | 0 | 131242-WST02-QA-BS-0010-0 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services) | R0: Approve with comments. Please refer to comment sheet for resubmission. | 2025-07-30 | 2025-08-19 | Approved with Comments | 2025-09-08 | NO | Overdue |  | 131242-WST02-QA-0010 | NA | "FAT report for Earth cable, LV Power cable (Unwitnessed)" && "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2024-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 48 | AWC | 2025-09-26 | 0 | 000913&&000935&&001424&&001699 | 2024-12-18, 2024-12-31, 2025-07-02, 2025-09-26 | 00 | 4 | For Information | INF |  |  | 0 | AWC | AWC
9203 | 001425 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | BS | 0011 | 0 | 131242-WST02-QA-BS-0011-0 | 2025-07-02 | Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-07-30 | 2025-08-19 | Not Approved | 2025-09-08 | NO | Overdue |  | 131242-WST02-QA-0011 | NA | "FAT Report for Cable Ladder 1st Batch (United ULI)" && "FAT report for Cable Ladder 1st batch (United ULI)" && "Samples Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan and Test procedure for ACMV T & C works (Building Services)" | 2024-12-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 48 | NAP | 2025-07-02 | 0 | 000927&&000951&&001087&&001425 | 2024-12-23, 2025-01-04, 2025-03-05, 2025-07-02 | 00 | 4 | Not Approved | NAP | 2025-09-08 | Overdue | 0 | NAP | NAP
9204 | 001426 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | B | 1401 | 0 | 131242-WST02-DS-B-1401-0 | 2025-07-02 | Sample board Submission for PA Conduit ,Saddle,Junction box | For information | 2025-07-30 | 2025-08-19 | For Information |  | YES | NA |  | 131242-WST02-DS-1401 | NA | "Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118" && "Sample board Submission for PA Conduit ,Saddle,Junction box" | 2025-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-22 | 48 | INF | 2025-07-23 | 0 | 001426&&001523 | 2025-07-02, 2025-07-23 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
9205 | 001427 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0024 | 0 | 131242-WST02-QA-I-0024-0 | 2025-07-02 | Vendor Manufacturing Inspection test plan for Pressure Gauges | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-QA-0024 | NA | "Samples Submission for Raised access floor system – HPL panel with Colour code, vinyl skirting, 25mm thick thermal insulation and stringer 570mm (Momentum Construction)" && "Vendor Manufacturing Inspection test plan for Pressure Gauges " | 2025-06-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-16 | 12 | AWC | 2025-07-02 | 0 | 001414&&001427 | 2025-06-27, 2025-07-02 | 00 | 2 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
9206 | 001428 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | BF | 0002 | 0 | 131242-WST02-VI-BF-0002-0 | 2025-07-02 | Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik | NA | 2025-07-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-16 | 278 | PEN | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | PEN | PEN
9207 | 001429 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0039 | 0 | 131242-WSW41-QA-C-0039-0 | 2025-07-02 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025 | For information | 2025-07-30 | 2025-07-17 | For Information |  | YES | NA |  | 131242-WSW41-QA-0039 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025" && "Material Submission for HV Plug and Transformer Termination Kit " | 2025-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-22 | 15 | INF | 2025-07-29 | 0 | 001429&&001534 | 2025-07-02, 2025-07-29 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
9208 | 001430 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0006 | 0 | 131242-WSD11-CD-I-0006-0 | 2025-07-02 | THP RIO Panel 002A I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-30 | 2025-10-24 | Approved with Comments | 2025-11-13 | NO | Overdue |  | 131242-WSD11-CD-0006 | NA | "THP RIO Panel 002A I/O List" | 2025-07-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 114 | AWC | 2025-07-02 | 0 | 001430 | 2025-07-02 | 00 | 1 | Approved with Comments | AWC | 2025-11-13 | Overdue | 0 | AWC | AWC
9209 | 001431 | 00 | Yuen Fatt | BS | NA | 131242 | WST02 | VI | BF | 0002 | 0 | 131242-WST02-VI-BF-0002-0 | 2025-07-03 | Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik | NA | 2025-07-31 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-17 | 277 | PEN | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | PEN | PEN
9210 | 001432 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0018 | 0 | 131242-WSW41-VI-E-0018-0 | 2025-07-04 | Vendor Approval for Distribution Boards (ZPA) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-08-01 | 2025-07-17 | Not Approved | 2025-08-06 | YES | Resubmitted |  | 131242-WSW41-VI-0018 | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-18 | 13 | NAP | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | Approved | APP |  |  | 0 | NAP | NAP
9211 | 001432 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0018 | 1 | 131242-WSW41-VI-E-0018-1 | 2025-08-21 | Vendor Approval for Distribution Boards (ZPA) | Rev 1: Approved. | 2025-09-10 | 2025-10-01 | Approved |  | YES | NA |  | 131242-WSW41-VI-0018 | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-04 | 41 | APP | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
9212 | 001433 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0031 | 0 | 131242-WSW41-SP-C-0031-0 | 2025-07-04 | Material Submission - Steel Structure Base Plate Grouting (Sanhe) | Approved | 2025-08-01 | 2025-07-17 | Approved |  | YES | NA |  | 131242-WSW41-SP-0031 | NA | "Material Submission - Steel Structure Base Plate Grouting (Sanhe)" | 2025-07-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-24 | 13 | APP | 2025-07-04 | 0 | 001433 | 2025-07-04 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9213 | 001434 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0007 | 0 | 131242-WST02-VI-A-0007-0 | 2025-07-04 | VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD. | R0: Approved with comments. Pleas refer to comment sheet. | 2025-08-01 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-18 | 10 | AWC | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9214 | 001435 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0096 | 0 | 131242-WSW41-QA-M-0096-0 | 2025-07-05 | Material and Test Certificate EN10204-3.1 For Butterfly Valves (OVS-Heaton) | NA | 2025-08-01 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSW41-QA-0096 | NA | "Material and Test Certificate EN10204-3.1 For Butterfly Valves (OVS-Heaton)" | 2025-07-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 65 | AWC | 2025-07-05 | 0 | 001435 | 2025-07-05 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
9215 | 001436 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0032 | 0 | 131242-WSW41-SP-C-0032-0 | 2025-07-05 | Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-01 | 2025-07-28 | Not Approved | 2025-08-15 | NO | Overdue |  | 131242-WSW41-SP-0032 | NA | "Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe)" && "Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe)" | 2025-07-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 23 | NAP | 2025-09-09 | 0 | 001436&&001660 | 2025-07-05, 2025-09-09 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
9216 | 001437 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0015 | 0 | 131242-WSW41-VI-E-0015-0 | 2025-07-07 | Vendor Approval for Distribution Boards (GSM) | Rev 0: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-07-17 | Not Approved | 2025-08-06 | YES | Resubmitted |  | 131242-WSW41-VI-0015 | NA | "Vendor Approval for Distribution Boards (GSM)" && "Vendor Approval of Testing Laboratory (TUV)" | 2024-05-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 10 | NAP | 2025-10-01 | 1 | 000493&&001437 | 2024-05-29, 2025-07-07, 2025-10-01 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9217 | 001437 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0015 | 1 | 131242-WSW41-VI-E-0015-1 | 2025-10-01 | Vendor Approval for Distribution Boards (GSM) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2025-10-15 | Approved with Comments | 2025-11-04 | NO | Overdue |  | 131242-WSW41-VI-0015 | NA | "Vendor Approval for Distribution Boards (GSM)" && "Vendor Approval of Testing Laboratory (TUV)" | 2024-05-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 14 | AWC | 2025-10-01 | 1 | 000493&&001437 | 2024-05-29, 2025-07-07, 2025-10-01 | 00, 01 | 3 | Approved with Comments | AWC | 2025-11-04 | Overdue | 0 | AWC | AWC
9218 | 001438 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0017 | 0 | 131242-WSD11-VI-E-0017-0 | 2025-07-07 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | Rev 0: Rejected. To revise and submit. Refer to attached file for comments. | 2025-08-04 | 2025-09-02 | Rejected | 2025-09-22 | YES | Resubmitted |  | 131242-WSD11-VI-0017 | NA | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | 2025-07-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-27 | 57 | REJ | 2026-02-24 | 2 | 001438 | 2025-07-07, 2025-10-01, 2026-02-24 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
9219 | 001438 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0017 | 1 | 131242-WSD11-VI-E-0017-1 | 2025-10-01 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | Rev 1: Not Approved. To revise and submit. Refer to attached file for comments. | 2025-10-21 | 2025-10-15 | Not Approved | 2025-11-04 | YES | Resubmitted |  | 131242-WSD11-VI-0017 | NA | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | 2025-07-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 14 | NAP | 2026-02-24 | 2 | 001438 | 2025-07-07, 2025-10-01, 2026-02-24 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9220 | 001438 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0017 | 2 | 131242-WSD11-VI-E-0017-2 | 2026-02-24 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps | Rev 1: Not Approved. To revise and submit. Refer to attached file for comments. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-VI-0017 | NA | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps" | 2025-07-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | 2 | 001438 | 2025-07-07, 2025-10-01, 2026-02-24 | 00, 01, 02 | 3 | Not Approved | NAP | 2026-04-13 |  | 0 | PEN | PEN
9221 | 001439 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0031 | 0 | 131242-WSW41-QA-EI-0031-0 | 2025-07-07 | FAT report for LVSG Panels (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSW41-QA-0031 | NA | "FAT report for LVSG Panels (Sunlight)" && "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " && "SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team)" | 2025-05-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 10 | AWC | 2026-01-08 | 0 | 001267&&001303&&001439&&001940 | 2025-05-04, 2025-05-18, 2025-07-07, 2026-01-08 | 00 | 4 | Approved | APP |  |  | 0 | AWC | AWC
9222 | 001440 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0005 | 0 | 131242-WSD11-CD-I-0005-0 | 2025-07-07 | THP RIO Panel 0101 I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-08-06 | Approved with Comments | 2025-08-26 | NO | Overdue |  | 131242-WSD11-CD-0005 | NA | "Electrical Signal List for THP -MCC-0101A/0101B " && "THP RIO Panel 0101 I/O List" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 30 | AWC | 2025-07-07 | 0 | 001213&&001440 | 2025-04-09, 2025-05-09, 2025-07-07 | 00, 01 | 3 | Approved with Comments | AWC | 2025-08-26 | Overdue | 0 | AWC | AWC
9223 | 001441 | 00 | Mohan | EICA | NA | 131242 | WST02 | QA | M | 0097 | 0 | 131242-WST02-QA-M-0097-0 | 2025-07-07 | FAT Report for SSN Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WST02-QA-0097 | NA | "FAT Report for SSN Flow Control Valve (KSB)" | 2025-07-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-27 | 25 | AWC | 2025-07-07 | 0 | 001441 | 2025-07-07 | 00 | 1 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
9224 | 001442 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0008 | 0 | 131242-WSD11-CD-I-0008-0 | 2025-07-07 | THP RIO Panel 001A-I/O list | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-CD-0008 | NA | "THP RIO Panel 001A-I/O list" | 2025-07-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-27 | 92 | AWC | 2025-07-07 | 0 | 001442 | 2025-07-07 | 00 | 1 | Approved with Comments | AWC | 2025-10-27 | Overdue | 0 | AWC | AWC
9225 | 001443 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0009 | 0 | 131242-WSD11-CD-I-0009-0 | 2025-07-07 | THP RIO Panel 001B-I/O list | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-CD-0009 | NA | "THP RIO Panel 001B-I/O list" | 2025-07-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-27 | 92 | AWC | 2025-07-07 | 0 | 001443 | 2025-07-07 | 00 | 1 | Approved with Comments | AWC | 2025-10-27 | Overdue | 0 | AWC | AWC
9226 | 001444 | 00 | Karthikeyan | EICA | NA | 131242 | WSD11 | CD | I | 0007 | 0 | 131242-WSD11-CD-I-0007-0 | 2025-07-07 | THP RIO Panel 002B-I/O list | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-04 | 2025-10-24 | Approved with Comments | 2025-11-13 | NO | Overdue |  | 131242-WSD11-CD-0007 | NA | "THP RIO Panel 002B-I/O list" | 2025-07-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-27 | 109 | AWC | 2025-07-07 | 0 | 001444 | 2025-07-07 | 00 | 1 | Approved with Comments | AWC | 2025-11-13 | Overdue | 0 | AWC | AWC
9227 | 001445 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5024 | A | 131242-WSD11-DR-M-5024-A | 2025-07-07 | GA for G2D Booster Pump | NA | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5024 | NA | "GA for G2D Booster Pump" | 2025-07-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-27 | 273 | PEN | 2025-07-07 | A | 001445 | 2025-07-07 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-08-22 |  | 0 | PEN | PEN
9228 | 001446 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0025 | 0 | 131242-WSW41-QA-I-0025-0 | 2025-07-08 | Vendor Manufacturing Inspection Test Plan for pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-08-05 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSW41-QA-0025 | NA | "Inspection Test Plan for Epoxy Coatings to Concrete and Rendered Surfaces" && "Vendor Manufacturing Inspection Test Plan for CSEL pipe spools, fittings, flanges fabrication" && "Vendor Manufacturing Inspection Test Plan for pH Analyser" | 2024-12-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 154 | AWC | 2025-07-08 | 0 | 000881&&001221&&001446 | 2024-12-10, 2025-03-13, 2025-04-11, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
9229 | 001447 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0026 | 0 | 131242-WSW41-QA-I-0026-0 | 2025-07-08 | Factory Acceptance Test Report for pH Analyser | Contractor requests to reject, email attached. | 2025-08-05 | 2025-07-11 | Rejected | 2025-07-31 | NO | Overdue |  | 131242-WSW41-QA-0026 | NA | "Factory Acceptance Test Report for pH Analyser" && "Inspection Test Plan for Stainless Steel piping spools Fabrication, Installation (Cyclect)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for December 2024" | 2024-12-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 3 | REJ | 2025-07-08 | 0 | 000872&&001241&&001447 | 2024-12-04, 2025-04-21, 2025-07-08 | 00 | 3 | Rejected | REJ | 2025-07-31 | Overdue | 0 | REJ | REJ
9230 | 001448 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | EI | 0033 | 0 | 131242-WSW41-QA-EI-0033-0 | 2025-07-08 | FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-05 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WSW41-QA-0033 | NA | "FAT Report for MCC Panels WST02-MCC-1001 A & B (Sunlight)" && "Issue for Information-Monthly reinforcement steel delivery records for Apr 2024" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for FRP Tank (Jizhou Zhongyi FRP Co. Ltd)" | 2025-01-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 9 | AWC | 2025-07-08 | 0 | 000941&&001279&&001448 | 2025-01-02, 2025-04-21, 2025-05-13, 2025-07-08 | 00, 01 | 4 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
9231 | 001449 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0034 | 0 | 131242-WSW41-QA-E-0034-0 | 2025-07-08 | Site Acceptance Test Procedure for 22KV HV Cable | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-05 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WSW41-QA-0034 | NA | "Inspection Certificates for HDPE Pipes, Fittings (Underground Pipeline in SSN Site)" && "Issue for Information-Monthly reinforcement steel delivery records for May, Jun, Jul & Aug 2024" && "Site Acceptance Test Procedure for 22KV HV Cable" | 2024-12-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 15 | AWC | 2025-07-08 | 0 | 000937&&001280&&001449 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
9232 | 001450 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0035 | 0 | 131242-WSW41-QA-E-0035-0 | 2025-07-08 | Inspection and Test Plan for Cable Laying, Installation, Testing and Termination | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-05 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WSW41-QA-0035 | NA | "Inspection and Test Plan for Cable Laying, Installation, Testing and Termination " && "Issue for Information-Monthly reinforcement steel delivery records for Sep & Oct 2024 " && "Test Report for CPVC Pipes and Fittings (Underground Pipeline in SSN Site)" | 2024-12-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-22 | 15 | AWC | 2025-07-08 | 0 | 000938&&001292&&001450 | 2024-12-31, 2025-05-13, 2025-07-08 | 00 | 3 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
9233 | 001451 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0098 | 0 | 131242-WSW41-QA-M-0098-0 | 2025-07-08 | FAT Report for G2D Water Pressure Reducing Valve (Pipeline-Elite) | NA | 2025-08-05 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0098 | NA | "FAT Report for G2D Water Pressure Reducing Valve (Pipeline-Elite)" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-28 | 56 | APP | 2025-07-08 | 0 | 001451 | 2025-07-08 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9234 | 001452 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0061 | 0 | 131242-WST02-CD-IM-0061-0 | 2025-07-08 | VCM Submission for 2025-06 | For Information. Please refer to the comment sheet. | 2025-08-05 | 2025-07-30 | For Information |  | YES | NA |  | 131242-WST02-CD-0061 | NA | "VCM Submission for 2025-06" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-28 | 22 | INF | 2025-07-08 | 0 | 001452 | 2025-07-08 | 00 | 1 | For Information | INF | 2025-08-19 | Overdue | 0 | INF | INF
9235 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1551 | C | 131242-WST02-DR-IP-1551-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1551 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9236 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1552 | C | 131242-WST02-DR-IP-1552-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1552 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9237 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1553 | C | 131242-WST02-DR-IP-1553-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1553 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9238 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1554 | C | 131242-WST02-DR-IP-1554-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1554 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9239 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1555 | C | 131242-WST02-DR-IP-1555-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1555 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9240 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1556 | C | 131242-WST02-DR-IP-1556-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1556 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9241 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1557 | C | 131242-WST02-DR-IP-1557-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1557 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9242 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1558 | C | 131242-WST02-DR-IP-1558-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1558 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9243 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1559 | C | 131242-WST02-DR-IP-1559-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1559 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9244 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1560 | C | 131242-WST02-DR-IP-1560-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1560 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9245 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1561 | C | 131242-WST02-DR-IP-1561-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1561 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9246 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1562 | C | 131242-WST02-DR-IP-1562-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1562 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9247 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1563 | C | 131242-WST02-DR-IP-1563-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1563 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9248 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1564 | C | 131242-WST02-DR-IP-1564-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1564 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9249 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1565 | C | 131242-WST02-DR-IP-1565-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1565 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9250 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1566 | C | 131242-WST02-DR-IP-1566-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1566 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9251 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1567 | C | 131242-WST02-DR-IP-1567-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1567 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9252 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1568 | C | 131242-WST02-DR-IP-1568-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1568 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9253 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1569 | C | 131242-WST02-DR-IP-1569-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1569 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9254 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1570 | C | 131242-WST02-DR-IP-1570-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1570 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9255 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1571 | C | 131242-WST02-DR-IP-1571-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1571 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9256 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1572 | C | 131242-WST02-DR-IP-1572-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1572 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9257 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1573 | C | 131242-WST02-DR-IP-1573-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1573 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9258 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1574 | C | 131242-WST02-DR-IP-1574-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1574 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9259 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1575 | C | 131242-WST02-DR-IP-1575-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1575 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9260 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1576 | C | 131242-WST02-DR-IP-1576-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1576 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9261 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1577 | C | 131242-WST02-DR-IP-1577-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1577 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9262 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1578 | C | 131242-WST02-DR-IP-1578-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1578 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9263 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1579 | C | 131242-WST02-DR-IP-1579-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1579 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9264 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1580 | C | 131242-WST02-DR-IP-1580-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1580 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9265 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1581 | C | 131242-WST02-DR-IP-1581-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1581 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9266 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1582 | C | 131242-WST02-DR-IP-1582-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1582 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9267 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1583 | C | 131242-WST02-DR-IP-1583-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1583 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9268 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1584 | C | 131242-WST02-DR-IP-1584-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1584 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9269 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1585 | C | 131242-WST02-DR-IP-1585-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1585 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9270 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1586 | C | 131242-WST02-DR-IP-1586-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1586 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9271 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1587 | C | 131242-WST02-DR-IP-1587-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1587 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9272 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1588 | C | 131242-WST02-DR-IP-1588-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1588 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9273 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1589 | C | 131242-WST02-DR-IP-1589-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1589 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9274 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1590 | C | 131242-WST02-DR-IP-1590-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1590 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9275 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1591 | C | 131242-WST02-DR-IP-1591-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1591 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9276 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1592 | C | 131242-WST02-DR-IP-1592-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1592 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9277 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1593 | C | 131242-WST02-DR-IP-1593-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1593 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9278 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1594 | C | 131242-WST02-DR-IP-1594-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1594 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9279 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1595 | C | 131242-WST02-DR-IP-1595-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1595 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9280 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1596 | C | 131242-WST02-DR-IP-1596-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1596 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9281 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1597 | C | 131242-WST02-DR-IP-1597-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1597 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9282 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1598 | C | 131242-WST02-DR-IP-1598-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1598 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9283 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1599 | C | 131242-WST02-DR-IP-1599-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1599 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9284 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1600 | C | 131242-WST02-DR-IP-1600-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1600 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9285 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1601 | C | 131242-WST02-DR-IP-1601-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1601 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9286 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1602 | C | 131242-WST02-DR-IP-1602-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1602 | NA | "SSN Chemical Dosing Platform Design" && "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-08-25 | A | 001453&&001623 | 2025-07-08, 2025-08-25 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9287 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1603 | C | 131242-WST02-DR-IP-1603-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1603 | NA | "SSN Chemical Dosing Platform Design" && "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-08-25 | A | 001453&&001623 | 2025-07-08, 2025-08-25 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9288 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1604 | C | 131242-WST02-DR-IP-1604-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1604 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9289 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1605 | C | 131242-WST02-DR-IP-1605-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1605 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9290 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1606 | C | 131242-WST02-DR-IP-1606-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1606 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9291 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1607 | C | 131242-WST02-DR-IP-1607-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1607 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-12-18 | F | 001453&&001914 | 2025-07-08, 2025-12-18 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
9292 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1608 | C | 131242-WST02-DR-IP-1608-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1608 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9293 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1609 | C | 131242-WST02-DR-IP-1609-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1609 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9294 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1610 | C | 131242-WST02-DR-IP-1610-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1610 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9295 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1611 | C | 131242-WST02-DR-IP-1611-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1611 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9296 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1612 | C | 131242-WST02-DR-IP-1612-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1612 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9297 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1613 | C | 131242-WST02-DR-IP-1613-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1613 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9298 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1614 | C | 131242-WST02-DR-IP-1614-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1614 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9299 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1615 | C | 131242-WST02-DR-IP-1615-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1615 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9300 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1616 | C | 131242-WST02-DR-IP-1616-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1616 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9301 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1617 | C | 131242-WST02-DR-IP-1617-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1617 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9302 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1618 | C | 131242-WST02-DR-IP-1618-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1618 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9303 | 001453 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1619 | C | 131242-WST02-DR-IP-1619-C | 2025-07-08 | SSN RIO - 203 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-05 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1619 | NA | "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 125 | AWC | 2025-07-08 | C | 001453 | 2025-07-08 | 00 | 1 | Approved with Comments | AWC | 2025-11-28 | Overdue | 0 | AWC | AWC
9304 | 001454 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0040 | 0 | 131242-WSW41-QA-C-0040-0 | 2025-07-09 | Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-06 | 2025-08-07 | Not Approved | 2025-08-27 | YES | Resubmitted |  | 131242-WSW41-QA-0040 | NA | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " && "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | 2025-01-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-23 | 29 | NAP | 2025-08-18 | 1 | 000974&&001454&&001491 | 2025-01-14, 2025-07-09, 2025-07-21, 2025-08-18 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9305 | 001454 | 01 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0040 | 1 | 131242-WSW41-QA-C-0040-1 | 2025-08-18 | Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) | R1: Approved with comments. Please refer to comment sheet for resubmission | 2025-09-05 | 2025-10-13 | Approved with Comments | 2025-10-31 | NO | Overdue |  | 131242-WSW41-QA-0040 | NA | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " && "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | 2025-01-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-01 | 56 | AWC | 2025-08-18 | 1 | 000974&&001454&&001491 | 2025-01-14, 2025-07-09, 2025-07-21, 2025-08-18 | 00, 01 | 4 | Approved with Comments | AWC | 2025-10-31 | Overdue | 0 | AWC | AWC
9306 | 001455 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | VI | E | 0019 | 0 | 131242-WSD11-VI-E-0019-0 | 2025-07-09 | Vendor Approval for Local Control Panel for THP G1 Booster Pumps (ZPA) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-08-06 | 2025-09-02 | Not Approved | 2025-09-22 | NO | Overdue |  | 131242-WSD11-VI-0019 | NA | "Vendor Approval for Local Control Panel for THP G1 Booster Pumps (ZPA)" | 2025-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-29 | 55 | NAP | 2025-07-09 | 0 | 001455 | 2025-07-09 | 00 | 1 | Not Approved | NAP | 2025-09-22 | Overdue | 0 | NAP | NAP
9307 | 001456 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0045 | 0 | 131242-WSD11-QA-M-0045-0 | 2025-07-10 | Steam Motorized Valve Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-07 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WSD11-QA-0045 | NA | " Steam Motorized Valve Data Sheet" | 2025-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-30 | 56 | AWC | 2025-07-10 | 0 | 001456 | 2025-07-10 | 00 | 1 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
9308 | 001457 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0099 | 0 | 131242-WSD11-QA-M-0099-0 | 2025-07-10 | FAT Report for THP Flow Control Valve (KSB) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-07 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WSD11-QA-0099 | NA | " FAT Report for THP Flow Control Valve (KSB)" | 2025-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-30 | 22 | AWC | 2025-07-10 | 0 | 001457 | 2025-07-10 | 00 | 1 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
9309 | 001458 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A | 131242-WST02-SD-S-8600-A | 2025-07-11 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-08 | 2025-08-01 | Not Approved | 2025-08-21 | YES | Resubmitted |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 21 | NAP | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9310 | 001458 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5602 | A | 131242-WST02-SD-S-5602-A | 2025-07-11 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-08 | 2025-08-01 | Not Approved | 2025-08-21 | YES | Resubmitted |  | 131242-WST02-SD-5602 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Typical Railing Details" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 21 | NAP | 2025-08-13 | A | 001458&&001589 | 2025-07-11, 2025-08-13 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9311 | 001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.3 | 131242-WST02-SD-S-8600-A.3 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | Not Approved | 2025-09-04 | YES | Resubmitted |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 2 | NAP | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9312 | 001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3001 | A.3 | 131242-WST02-SD-S-3001-A.3 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | Not Approved | 2025-09-04 | YES | Resubmitted |  | 131242-WST02-SD-3001 | NA | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 2 | NAP | 2025-08-22 | A.5 | 001458 | 2025-08-13, 2025-08-22 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9313 | 001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1002 | A.3 | 131242-WST02-SD-S-1002-A.3 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | Not Approved | 2025-09-04 | YES | Resubmitted |  | 131242-WST02-SD-1002 | NA | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 2 | NAP | 2025-08-22 | A.5 | 001458 | 2025-08-13, 2025-08-22 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9314 | 001458 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1003 | A.3 | 131242-WST02-SD-S-1003-A.3 | 2025-08-13 | Railing Shop Drawing For Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-08-15 | Not Approved | 2025-09-04 | YES | Resubmitted |  | 131242-WST02-SD-1003 | NA | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 2 | NAP | 2025-08-22 | A.5 | 001458 | 2025-08-13, 2025-08-22 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9315 | 001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.5 | 131242-WST02-SD-S-8600-A.5 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 6 | AWC | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9316 | 001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3001 | A.5 | 131242-WST02-SD-S-3001-A.5 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WST02-SD-3001 | NA | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 6 | AWC | 2025-08-22 | A.5 | 001458 | 2025-08-13, 2025-08-22 | 01, 02 | 2 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
9317 | 001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1002 | A.5 | 131242-WST02-SD-S-1002-A.5 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WST02-SD-1002 | NA | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 6 | AWC | 2025-08-22 | A.5 | 001458 | 2025-08-13, 2025-08-22 | 01, 02 | 2 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
9318 | 001458 | 02 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1003 | A.5 | 131242-WST02-SD-S-1003-A.5 | 2025-08-22 | Railing Shop Drawing For Electrical Building | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WST02-SD-1003 | NA | " Railing Shop Drawing For Electrical Building" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 6 | AWC | 2025-08-22 | A.5 | 001458 | 2025-08-13, 2025-08-22 | 01, 02 | 2 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
9319 | 001459 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | ST610 | A.5 | 131242-WST02-DR-C-ST610- | 2025-07-10 | Valve Chamber Design for SSN- Portable Water Line | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-11 | 2025-09-17 | Not Approved | 2025-10-07 | NO | Overdue |  | 131242-WST02-DR-ST610 | NA | "Valve Chamber Design for SSN- Portable Water Line" | 2025-07-10 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-30 | 69 | NAP | 2025-11-28 | A.5 | 001459 | 2025-07-10, 2025-11-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9320 | 001459 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | C | ST610 | A.5 | 131242-WST02-DR-C-ST610- | 2025-11-28 | Valve Chamber Design for SSN- Portable Water Line | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-18 | 2026-01-15 | Approved with Comments | 2026-02-04 | NO | Overdue |  | 131242-WST02-DR-ST610 | NA | "Valve Chamber Design for SSN- Portable Water Line" | 2025-07-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-12 | 48 | AWC | 2025-11-28 | A.5 | 001459 | 2025-07-10, 2025-11-28 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-04 | Overdue | 0 | AWC | AWC
9321 | 001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611 | A | 131242-WST02-DR-S-5600_ST611-A | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | For Information |  | YES | NA |  | 131242-WST02-DR-5600_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-07-31 | 104 | INF | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP |  |  | 0 | INF | INF
9322 | 001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611 | A | 131242-WST02-DR-S-1601_ST611-A | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | For Information |  | YES | NA |  | 131242-WST02-DR-1601_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-07-31 | 104 | INF | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP |  |  | 0 | INF | INF
9323 | 001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611 | A | 131242-WST02-DR-S-5601_ST611-A | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | For Information |  | YES | NA |  | 131242-WST02-DR-5601_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-07-31 | 104 | INF | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP |  |  | 0 | INF | INF
9324 | 001460 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611 | A | 131242-WST02-DR-S-1600_ST611-A | 2025-07-11 | ST611 Pipe Supports Redesign | For Information | 2025-08-08 | 2025-10-23 | For Information |  | YES | NA |  | 131242-WST02-DR-1600_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-07-31 | 104 | INF | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP |  |  | 0 | INF | INF
9325 | 001461 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0041 | 0 | 131242-WSW41-QA-C-0041-0 | 2025-07-11 | Issue for Information - Monthly Concrete Cube Records for Structural Works for May 2025 | For Information | 2025-08-08 | 2025-08-05 | For Information |  | YES | NA |  | 131242-WSW41-QA-0041 | NA | "Issue for Information - Monthly Concrete Cube Records for Structural Works for May 2025" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-31 | 25 | INF | 2025-07-11 | 0 | 001461 | 2025-07-11 | 00 | 1 | For Information | INF | 2025-08-25 | Overdue | 0 | INF | INF
9326 | 001462 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | ST607 | - | 131242-WST02-DR-S-ST607-- | 2025-07-11 | Updated Drawings ST607 - SSN Water Tank | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-08 | 2025-10-23 | Not Approved | 2025-11-12 | NO | Overdue |  | 131242-WST02-DR-ST607 | NA | " Updated Drawings ST607 - SSN Water Tank" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 104 | NAP | 2025-07-11 | - | 001462 | 2025-07-11 | 00 | 1 | Not Approved | NAP | 2025-11-12 | Overdue | 0 | NAP | NAP
9327 | 001463 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0027 | 0 | 131242-WST02-QA-I-0027-0 | 2025-07-11 | Vendor Manufacturing Inspection Test Plan for Conductive Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-08-15 | Approved with Comments | 2025-09-04 | NO | Overdue |  | 131242-WST02-QA-0027 | NA | " FAT Procedure for MDB Panels (Sunlight)" && "Factory Acceptance Test Report for Pressure Gauges" && "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" | 2025-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 35 | AWC | 2025-07-14 | 0 | 001133&&001463&&001476 | 2025-03-18, 2025-07-11, 2025-07-14 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9328 | 001464 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0100 | 0 | 131242-WST02-QA-M-0100-0 | 2025-07-11 | FAT Report for EQ Tank Transfer Pumps (KSB) | Rev 0: Approved | 2025-08-08 | 2025-08-11 | Approved |  | YES | NA |  | 131242-WST02-QA-0100 | NA | " FAT Report for EQ Tank Transfer Pumps (KSB)" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-31 | 31 | APP | 2025-07-11 | 0 | 001464 | 2025-07-11 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9329 | 001465 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0029 | 0 | 131242-WST02-QA-I-0029-0 | 2025-07-11 | Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-08-08 | 2025-10-01 | Approved with Comments |  | YES | NA |  | 131242-WST02-QA-0029 | NA | "SAT Procedure for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) " && "Vendor Manufacturing Inspection Test Plan for Dissolved Oxygen Analyser" | 2025-03-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-25 | 82 | AWC | 2025-07-11 | 0 | 001174&&001465 | 2025-03-27, 2025-07-10, 2025-07-11 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
9330 | 001466 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0026 | 0 | 131242-WST02-QA-I-0026-0 | 2025-07-11 | Factory Acceptance Test Report for Conductivity Analyser | NA | 2025-08-08 | 2025-08-26 | Approved with Comments | 2025-09-15 | NO | Overdue |  | 131242-WST02-QA-0026 | NA | " Factory Acceptance Test Report for Conductivity Analyser" && "FAT Procedure for LVSG Panels (Sunlight)" && "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 46 | AWC | 2025-08-06 | 0 | 001132&&001466&&001568 | 2025-03-18, 2025-05-23, 2025-07-11, 2025-08-06 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9331 | 001467 | 00 | Karthikeyan | EICA | NA | 131242 | WST02 | CD | I | 0015 | 0 | 131242-WST02-CD-I-0015-0 | 2025-07-11 | Electrical Signal List for SSN -MCC-0102A/0102B | Rev 0: Rejected. Refer to attached file for comments. | 2025-08-08 | 2025-07-16 | Rejected |  | YES | NA |  | 131242-WST02-CD-0015 | NA | "Electrical Signal List for SSN -MCC-0102A/0102B " | 2025-07-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-31 | 5 | REJ | 2025-07-11 | 0 | 001467 | 2025-07-11 | 00 | 1 | Rejected | REJ | 2025-08-05 | Overdue | 0 | REJ | REJ
9332 | 001467 | 01 | Karthikeyan | EICA | NA | 131242 | WSW41 | CD | I | 0001 | 1 | 131242-WSW41-CD-I-0001-1 | 2025-07-25 | Electrical Signal List for SSN -MCC-0102A/0102B | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. Please update and amend the Prolog document title to "Electrical Signal List for MCC-TYPICAL". | 2025-08-14 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WSW41-CD-0001 | NA | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " && "Submission Of BIM Coordination VCM Model (July – 2023)" | 2023-08-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-08 | 68 | AWC | 2025-07-25 | 1 | 000066&&001350&&001467 | 2023-08-08, 2025-06-10, 2025-07-25 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
9333 | 001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7213 | A | 131242-WST02-DR-IP-7213-A | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-7213 | NA | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 151 | NAP | 2025-07-11 | A | 001468 | 2025-07-11 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9334 | 001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7214 | A | 131242-WST02-DR-IP-7214-A | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-7214 | NA | "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 151 | NAP | 2025-07-11 | A | 001468 | 2025-07-11 | 00 | 1 | Not Approved | NAP | 2025-12-29 | Overdue | 0 | NAP | NAP
9335 | 001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7215 | A | 131242-WST02-DR-IP-7215-A | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-7215 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 151 | NAP | 2026-02-03 | B | 001468&&001772 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9336 | 001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7210 | A | 131242-WST02-DR-IP-7210-A | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-7210 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 151 | NAP | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9337 | 001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7211 | A | 131242-WST02-DR-IP-7211-A | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-7211 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 151 | NAP | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9338 | 001468 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 7212 | A | 131242-WST02-DR-IP-7212-A | 2025-07-11 | SSN-Chemical Unloading LCP - GA and Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-12-09 | Not Approved | 2025-12-29 | NO | Overdue |  | 131242-WST02-DR-7212 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-31 | 151 | NAP | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
9339 | 001469 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0030 | 0 | 131242-WST02-QA-I-0030-0 | 2025-07-11 | Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-08 | 2025-08-15 | Approved with Comments | 2025-09-04 | NO | Overdue |  | 131242-WST02-QA-0030 | NA | "Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) " && "Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical" | 2025-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 35 | AWC | 2025-11-27 | 0 | 001300&&001469&&001869 | 2025-05-15, 2025-07-11, 2025-11-27 | 00 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
9340 | 001470 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1016 | 0 | 131242-WSW41-VI-M-1016-0 | 2025-07-11 | Preliminary design and Vendor Approval for Strainer (Spirax) | Approved | 2025-08-08 | 2025-08-01 | Approved |  | YES | NA |  | 131242-WSW41-VI-1016 | NA | " Preliminary design and Vendor Approval for Strainer (Spirax)" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-31 | 21 | APP | 2025-07-11 | 0 | 001470 | 2025-07-11 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9341 | 001471 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0026 | 0 | 131242-WSW41-RT-PM-0026-0 | 2025-07-12 | C4B Monthly Progress Report Number No.26 (06 25) | Approved with comments which will be addressed in the next MPR submission. | 2025-08-08 | 2025-08-04 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0026 | NA | "C4B Monthly Progress Report Number No.26 (06 25)" | 2025-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-01 | 23 | AWC | 2025-07-12 | 0 | 001471 | 2025-07-12 | 00 | 1 | Approved with Comments | AWC | 2025-08-22 | Overdue | 0 | AWC | AWC
9342 | 001472 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0031 | 0 | 131242-WST02-QA-I-0031-0 | 2025-07-14 | Vendor Manufacturing Inspection Test Plan for Temperature Transmitters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-QA-0031 | NA | "Vendor Manufacturing Inspection Test Plan for Temperature Transmitters" | 2025-07-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-03 | 84 | AWC | 2025-07-14 | 0 | 001472 | 2025-07-14 | 00 | 1 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9343 | 001473 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5025 | A | 131242-WSD11-DR-M-5025-A | 2025-07-14 | GA for G1 Booster Pump | NA | 2025-08-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5025 | NA | "GA for G1 Booster Pump" | 2025-07-14 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-08-03 | 266 | PEN | 2025-07-14 | A | 001473 | 2025-07-14 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-08-29 |  | 0 | PEN | PEN
9344 | 001474 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0033 | 0 | 131242-WST02-QA-I-0033-0 | 2025-07-14 | Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-QA-0033 | NA | " Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter" && "Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal)" | 2025-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-03 | 84 | AWC | 2026-01-12 | 0 | 001474&&001950 | 2025-07-14, 2026-01-12 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
9345 | 001475 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0034 | 0 | 131242-WST02-QA-I-0034-0 | 2025-07-14 | Factory Acceptance Test Report for Thermal Flow/Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WST02-QA-0034 | NA | " Factory Acceptance Test Report for Thermal Flow/Mass Flowmeter" | 2025-07-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-03 | 148 | AWC | 2025-07-14 | 0 | 001475 | 2025-07-14 | 00 | 1 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
9346 | 001476 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0027 | 0 | 131242-WST02-QA-I-0027-0 | 2025-07-14 | Factory Acceptance Test Report for Pressure Gauges | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-11 | 2025-10-15 | Approved with Comments | 2025-11-04 | NO | Overdue |  | 131242-WST02-QA-0027 | NA | " FAT Procedure for MDB Panels (Sunlight)" && "Factory Acceptance Test Report for Pressure Gauges" && "Vendor Manufacturing Inspection Test Plan for Conductive Analyser" | 2025-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-28 | 93 | AWC | 2025-07-14 | 0 | 001133&&001463&&001476 | 2025-03-18, 2025-07-11, 2025-07-14 | 00 | 3 | Approved with Comments | AWC | 2025-11-04 | Overdue | 0 | AWC | AWC