## Sheet1
Row_Index | Submission_Session | Submission_Session_Revision | Submitted_By | Department | Transmittal_Number | Project_Code | Facility_Code | Document_Type | Discipline | Document_Sequence_Number | Document_Revision | CES_SALCON-SDC JV Cor Ref No | Submission_Date | Submission_Session_Subject | Review_Comments | Date S.O. to Response (20 Working Days/ 14 Working Days) | Review_Return_Actual_Date | Review_Status | Date CES to Response (14 Working Days) | Closed | Resubmission_Forecast_Date | Notes | Document_ID | Document_Title | Consolidated_Submission_Session_Subject | First_Submission_Date | Submission_Closed | Resubmission_Required | Validation_Errors | Review_Return_Plan_Date | Duration_of_Review | Approval_Code | Latest_Submission_Date | Latest_Revision | All_Submission_Sessions | All_Submission_Dates | All_Submission_Session_Revisions | Count_of_Submissions | Latest_Approval_Status | Latest_Approval_Code | Resubmission_Plan_Date | Resubmission_Overdue_Status | Delay_of_Resubmission | This_Submission_Approval_Code | Review_Status_Code
1 | 000001 | 00 | Soe Myat | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 0 | 131242-WST00-PP-PM-0001-0 | 2023-05-15 | Project Quality Plan | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-13 | 2023-12-05 | Approved with Comments | 2023-12-26 | YES | Resubmitted |  | 131242-WST00-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-04 | 204 | AWC | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2 | 000001 | 01 | Radha | PMT | NA | 131242 | WST00 | PP | PM | 0001 | 1 | 131242-WST00-PP-PM-0001-1 | 2024-05-13 | Project Quality Plan | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-03 | 2024-09-10 | Approved with Comments | 2024-09-30 | NO | Overdue |  | 131242-WST00-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 120 | AWC | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | Approved with Comments | AWC | 2024-09-30 | Overdue | 0 | AWC | AWC
3 | 000002 | 00 | Shena | PMT | NA | 131242 | WST00 | PP | PC | 0001 | 0 | 131242-WST00-PP-PC-0001-0 | 2023-05-15 | Project Risk Management Plan | Rev 0: Approved with Comments. Refer to comment sheet and resubmit. | 2023-06-13 | 2023-06-14 | Approved with Comments | 2023-07-05 | YES | Resubmitted |  | 131242-WST00-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-04 | 30 | AWC | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4 | 000002 | 01 | Max/Edwin | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 1 | 131242-WSW41-PP-PC-0001-1 | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-09-25 | 2023-09-13 | Approved with Comments | 2023-10-03 | YES | Resubmitted |  | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-19 | 8 | AWC | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
5 | 000002 | 01 | Max/Edwin | PMT | NA | #000002.0_ Reply_2023 08 31 | NA | NA | NA | 9999 | 1 | #000002.0_ Reply_2023 08 31----- | 2023-09-05 | Project Risk Management Plan | Rev. 1: Approved with Comments. Refer to comment sheet and re-submit. | 2023-10-03 | 2023-09-13 | Approved with Comments | 2023-10-03 | YES | Resubmitted |  | #000002.0_ Reply_2023 08 31-NA-NA-9999 | NA | "Project Risk Management Plan" | 2023-09-05 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-25 | 8 | AWC | 2023-09-05 | 1 | 000002 | 2023-09-05 | 01 | 1 | Approved with Comments | AWC | 2023-10-03 | Overdue | 0 | AWC | AWC
6 | 000002 | 02 | Max | PMT | NA | 131242 | WSW41 | PP | PC | 0001 | 2 | 131242-WSW41-PP-PC-0001-2 | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-20 | 2023-11-07 | Approved |  | YES | NA |  | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-13 | 8 | APP | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
7 | 000002 | 02 | Max | PMT | NA | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025 | NA | NA | NA | 9999 | 2 | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025----- | 2023-10-30 | Project Risk Management Plan | Approved | 2023-11-28 | 2023-11-07 | Approved |  | YES | NA |  | #000002.0_ Reply_2023 09 13 (002)_CES reply_20231025-NA-NA-9999 | NA | "Project Risk Management Plan" | 2023-10-30 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2023-11-19 | 8 | APP | 2023-10-30 | 2 | 000002 | 2023-10-30 | 02 | 1 | Approved | APP |  |  | 0 | APP | APP
8 | 000003 | 00 | Heng Peng | BIM | NA | 131242 | WST00 | PP | IM | 0001 | 0 | 131242-WST00-PP-IM-0001-0 | 2023-05-16 | BIM Execution Plan (BEP) | R0- Not Approved, please refer to comment sheet | 2023-06-14 | 2023-07-03 | Not Approved | 2023-07-21 | YES | Resubmitted |  | 131242-WST00-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-05-30 | 48 | NAP | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9 | 000003 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 1 | 131242-WSW41-PP-IM-0001-1 | 2023-08-21 | BIM Execution Plan (BEP) | R1- Not Approved. Please refer to "Comment Sheet_Submittal-0003-1". | 2023-09-08 | 2023-10-20 | Not Approved | 2023-11-09 | YES | Resubmitted |  | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-10 | 60 | NAP | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | NAP | NAP
10 | 000003 | 02 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 2 | 131242-WSW41-PP-IM-0001-2 | 2023-12-12 | BIM Execution Plan (BEP) | R2- Not Approved, revise and resubmit. Please refer to "Comment Sheet_Submittal-0003-2". | 2024-01-03 | 2024-03-14 | Not Approved | 2024-04-04 | YES | Resubmitted |  | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 93 | NAP | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | NAP | NAP
11 | 000003 | 03 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 3 | 131242-WSW41-PP-IM-0001-3 | 2024-03-15 | BIM Execution Plan (BEP) | R3- Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet | 2024-04-05 | 2024-03-20 | Approved with Comments | 2024-04-11 | YES | Resubmitted |  | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-29 | 5 | AWC | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
12 | 000003 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 4 | 131242-WSW41-PP-IM-0001-4 | 2024-06-28 | BIM Execution Plan (BEP) | Approved with comments. Kindly amend items/comments that is still open. Please refer to comment sheet. | 2024-07-18 | 2024-08-07 | Approved with Comments | 2024-08-28 | YES | Resubmitted | R3_AWC | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-12 | 40 | AWC | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
13 | 000003 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | PP | IM | 0001 | 5 | 131242-WSW41-PP-IM-0001-5 | 2024-09-18 | BIM Execution Plan (BEP) | Approved | 2024-10-08 | 2024-10-02 | Approved |  | YES | NA |  | 131242-WSW41-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project Risk Management Plan" | 2023-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-02 | 14 | APP | 2024-09-18 | 5 | 000002&&000003 | 2023-08-21, 2023-09-05, 2023-10-30, 2023-12-12, 2024-03-15, 2024-06-28, 2024-09-18 | 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
14 | 000004 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 0 | 131242-WST00-PP-HS-0001-0 | 2023-05-16 | Project HSE Plan | Names are not as proposed. Signatory also not as proposed for HSEM. Review and resubmit. | 2023-06-14 | 2023-07-24 | Not Approved | 2023-08-14 | YES | Resubmitted |  | 131242-WST00-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-05-30 | 69 | NAP | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
15 | 000004 | 01 | Dharmen | HSE | NA | 131242 | WST00 | PP | HS | 0001 | 1 | 131242-WST00-PP-HS-0001-1 | 2023-09-27 | Project HSE Plan | Approved from HSE standpoint. | 2023-10-17 | 2023-10-04 | Approved |  | YES | NA |  | 131242-WST00-PP-0001 | NA | "BIM Execution Plan (BEP)" && "Project HSE Plan" && "Project Quality Plan" && "Project Risk Management Plan" | 2023-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-11 | 7 | APP | 2024-05-13 | 1 | 000001&&000002&&000003&&000004 | 2023-05-15, 2023-05-16, 2023-09-27, 2024-05-13 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
16 | 000005 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 0 | 131242-WST00-PG-PC-0001-0 | 2023-05-17 | PROGRAMME OF THE WORKS | Rev. 0 - Not Approved, need to re-submit (see comments sheet) | 2023-06-15 | 2023-06-14 | Not Approved | 2023-07-05 | YES | Resubmitted |  | 131242-WST00-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-06 | 28 | NAP | 2023-07-13 | 1 | 000005 | 2023-05-17, 2023-07-13 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
17 | 000005 | 01 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0001 | 1 | 131242-WST00-PG-PC-0001-1 | 2023-07-13 | PROGRAMME OF THE WORKS | Rev. 1 - Not Approved, need to re-submit (see attached comments sheet R1) | 2023-08-02 | 2023-07-31 | Not Approved | 2023-08-21 | YES | Resubmitted |  | 131242-WST00-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-05-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-27 | 18 | NAP | 2023-07-13 | 1 | 000005 | 2023-05-17, 2023-07-13 | 00, 01 | 2 | Not Approved | NAP | 2023-08-18 | Overdue | 0 | NAP | NAP
18 | 000005 | 02 | Thomas | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 2 | 131242-WSW41-PG-PC-0001-2 | 2023-09-07 | PROGRAMME OF THE WORKS | Rev. 2 Approved with comments. Need to re-submit (see attached comment sheet) | 2023-09-27 | 2023-09-18 | Approved with Comments | 2023-10-06 | YES | Resubmitted |  | 131242-WSW41-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-27 | 11 | AWC | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
19 | 000005 | 03 | Thomas | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 | 131242-WSW41-LT-PM-0003-0 | 2023-09-26 | PROGRAMME OF THE WORKS | For Information | 2023-10-16 | 2023-10-03 | For Information | 2023-10-23 | YES | Resubmitted | 000040 | 131242-WSW41-LT-0003 | NA | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | 2023-07-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-10 | 7 | INF | 2023-09-26 | 0 | 000005&&000040 | 2023-07-06, 2023-09-26 | 00, 03 | 2 | For Information | INF | 2023-10-23 | Overdue | 0 | INF | INF
20 | 000005 | 04 | Krishanthy | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 3 | 131242-WSW41-PG-PC-0001-3 | 2023-10-27 | PROGRAMME OF THE WORKS | Rev. 4 Approved with comments. | 2023-11-17 | 2023-11-14 | Approved with Comments | 2023-12-04 | YES | Resubmitted | To be resubmitted when there is a major change in the program of works. Thomas checked with S.O. in the meeting on 18 Jan. | 131242-WSW41-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-10 | 18 | AWC | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
21 | 000005 | 05 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 4 | 131242-WSW41-PG-PC-0001-4 | 2024-10-19 | PROGRAMME OF THE WORKS | Rev. 5. Not-Approved need to re-submit (see attached comment sheet) - new Rebaseline of the Programme Rev.1 need to re-submit with a new Prolog Submittal Number | 2024-11-08 | 2024-11-04 | Not Approved | 2024-11-22 | YES | Resubmitted |  | 131242-WSW41-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-02 | 16 | NAP | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
22 | 000005 | 06 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5 | 131242-WSW41-PG-PC-0001-5 | 2025-03-14 | PROGRAMME OF THE WORKS | Rev. 6 - Approved with comments (need to re-submit - see attached comments sheet rev.1) | 2025-04-03 | 2025-04-15 | Approved with Comments | 2025-05-05 | YES | Resubmitted |  | 131242-WSW41-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 32 | AWC | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
23 | 000005 | 07 | Leslie | PCM | NA | 131242 | WSW41 | PG | PC | 0001 | 5.1 | 131242-WSW41-PG-PC-0001-5.1 | 2025-04-16 | PROGRAMME OF THE WORKS | Rev. 7 - Approved with comments (No resubmission needed - See attached comments sheet rev.7) | 2025-05-06 | 2025-04-27 | Approved with Comments |  | YES | NA |  | 131242-WSW41-PG-0001 | NA | "PROGRAMME OF THE WORKS" | 2023-09-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-04-30 | 11 | AWC | 2025-04-16 | 5.1 | 000005 | 2023-09-07, 2023-10-27, 2024-10-19, 2025-03-14, 2025-04-16 | 02, 04, 05, 06, 07 | 5 | Approved with Comments | AWC | 2025-05-15 | Overdue | 0 | AWC | AWC
24 | 000006 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 0 | 131242-WST00-VI-C-0001-0 | 2023-05-17 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-15 | 2023-06-12 | Approved with Comments | 2023-07-03 | YES | Resubmitted |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-06 | 26 | AWC | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | AWC | AWC
25 | 000006 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0001 | 1 | 131242-WST00-VI-C-0001-1 | 2023-06-23 | Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.) | Approved | 2023-07-14 | 2023-06-30 | Approved |  | YES | NA |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-07 | 7 | APP | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | APP | APP
26 | 000007 | 00 | Thomas | PCM | NA | 131242 | WST00 | PG | PC | 0002 | 0 | 131242-WST00-PG-PC-0002-0 | 2023-05-18 | MOBILIZATION PROGRAMME | Rev. 0 - Not Approved need to re-submit Refer Comment sheet) | 2023-06-16 | 2023-06-13 | Not Approved | 2023-07-04 | YES | Resubmitted | Reply to S.O. Comment Sheet Only | 131242-WST00-PG-0002 | NA | "MOBILIZATION PROGRAMME " | 2023-05-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-07 | 26 | NAP | 2023-05-18 | 0 | 000007 | 2023-05-18 | 00 | 1 | Not Approved | NAP | 2023-07-03 | Overdue | 0 | NAP | NAP
27 | 000007 | 01 | Thomas | PCM | NA | Reply to Comment Sheet_#000007 | NA | NA | NA | 9999 | 0 | Reply to Comment Sheet_#000007----- | 2023-09-13 | MOBILIZATION PROGRAMME | Approved | 2023-10-03 | 2023-09-20 | Approved |  | YES | NA |  | Reply to Comment Sheet_#000007-NA-NA-9999 | NA | "MOBILIZATION PROGRAMME " | 2023-09-13 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2023-10-03 | 7 | APP | 2023-09-13 | 0 | 000007 | 2023-09-13 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
28 | 000008 | 00 | Frank/ Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 0 | 131242-WST00-RG-Z-0001-0 | 2023-05-18 | Engineering Deliverable Lists | Rev 0: Not approved - Revise and Resubmit | 2023-06-16 | 2023-11-21 | Not Approved | 2023-12-11 | YES | Resubmitted |  | 131242-WST00-RG-0001 | NA | "Engineering Deliverable Lists" | 2023-05-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-07 | 187 | NAP | 2024-01-15 | 1 | 000008 | 2023-05-18, 2024-01-15 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
29 | 000008 | 01 | Franklin | PMT | NA | 131242 | WST00 | RG | Z | 0001 | 1 | 131242-WST00-RG-Z-0001-1 | 2024-01-15 | Engineering Deliverable Lists | For Information To revise and resubmit. Refer to attached file for comments. | 2024-02-02 | 2024-08-29 | For Information | 2024-09-18 | NO | Overdue | R1_Not APP | 131242-WST00-RG-0001 | NA | "Engineering Deliverable Lists" | 2023-05-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-29 | 227 | INF | 2024-01-15 | 1 | 000008 | 2023-05-18, 2024-01-15 | 00, 01 | 2 | For Information | INF | 2024-09-18 | Overdue | 0 | INF | INF
30 | 000009 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 0 | 131242-WST00-VI-C-0002-0 | 2023-05-19 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-12 | Not Approved | 2023-07-03 | YES | Resubmitted |  | 131242-WST00-VI-0002 | NA | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | 2023-05-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-08 | 24 | NAP | 2023-07-03 | 1 | 000009 | 2023-05-19, 2023-07-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
31 | 000009 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0002 | 1 | 131242-WST00-VI-C-0002-1 | 2023-07-03 | Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.) | Approved | 2023-07-21 | 2023-07-12 | Approved |  | YES | NA |  | 131242-WST00-VI-0002 | NA | "Vendor Approval for Pre-Construction Survey (Xpress Surveys & FMC Pte. Ltd.)" | 2023-05-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-17 | 9 | APP | 2023-07-03 | 1 | 000009 | 2023-05-19, 2023-07-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
32 | 000010 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | S | 0001 | 0 | 131242-WST00-VI-S-0001-0 | 2023-05-19 | Vendor Approval for CSA Consultant QP (Tenwit) | Approved | 2023-06-19 | 2023-06-12 | Approved |  | YES | NA |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-06-02 | 24 | APP | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | APP | APP
33 | 000011 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | G | 0001 | 0 | 131242-WST00-VI-G-0001-0 | 2023-05-19 | Vendor Approval for Temp ERSS QPD,QPS (Tenwit ) | Approved | 2023-06-19 | 2023-06-12 | Approved |  | YES | NA |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-06-02 | 24 | APP | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | APP | APP
34 | 000012 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 0 | 131242-WST00-VI-HS-0001-0 | 2023-05-19 | Vendor Approval for QECP Consultant (Tenwit ) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-19 | 2023-06-14 | Not Approved | 2023-07-05 | YES | Resubmitted |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-02 | 26 | NAP | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | NAP | NAP
35 | 000012 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | HS | 0001 | 1 | 131242-WST00-VI-HS-0001-1 | 2023-06-23 | Vendor Approval for QECP Consultant (Tenwit ) | Approved | 2023-07-14 | 2023-07-24 | Approved |  | YES | NA |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-07 | 31 | APP | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | APP | APP
36 | 000013 | 00 | Freedomer | EICA | NA | 131242 | WST00 | VI | B | 0001 | 0 | 131242-WST00-VI-B-0001-0 | 2023-05-21 | Vendor Approval for M&E QP (C2D Solutions Pte. LTD ) | Approved | 2023-06-19 | 2024-03-18 | Approved |  | YES | NA |  | 131242-WST00-VI-0001 | NA | "Vendor Approval for CSA Consultant QP (Tenwit)" && "Vendor Approval for Licence Surveyor (Nanyang Survey Pte. Ltd.)" && "Vendor Approval for M&E QP (C2D Solutions Pte. LTD )" && "Vendor Approval for QECP Consultant (Tenwit )" && "Vendor Approval for Temp ERSS QPD,QPS (Tenwit )" | 2023-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-06-04 | 302 | APP | 2023-06-23 | 1 | 000006&&000010&&000011&&000012&&000013 | 2023-05-17, 2023-05-19, 2023-05-21, 2023-06-23 | 00, 01 | 7 | Approved | APP |  |  | 0 | APP | APP
37 | 000014 | 00 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 0 | 131242-WST00-VI-C-0003-0 | 2023-05-22 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-06-20 | 2023-06-12 | Not Approved | 2023-07-03 | YES | Resubmitted |  | 131242-WST00-VI-0003 | NA | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-11 | 21 | NAP | 2023-07-31 | 2 | 000014 | 2023-05-22, 2023-06-23, 2023-07-31 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
38 | 000014 | 01 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 1 | 131242-WST00-VI-C-0003-1 | 2023-06-23 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Rev.1: Not Approved. Please refer to attached comment sheet for resubmission. | 2023-07-14 | 2023-07-12 | Not Approved | 2023-08-01 | YES | Resubmitted |  | 131242-WST00-VI-0003 | NA | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-07 | 19 | NAP | 2023-07-31 | 2 | 000014 | 2023-05-22, 2023-06-23, 2023-07-31 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
39 | 000014 | 02 | Zora | CSA | NA | 131242 | WST00 | VI | C | 0003 | 2 | 131242-WST00-VI-C-0003-2 | 2023-07-31 | Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD) | Approved | 2023-08-21 | 2023-08-11 | Approved |  | YES | NA |  | 131242-WST00-VI-0003 | NA | "Vendor Approval for Dfs Professional Dr. George Zhou Tongquan (Tenwit Consultant Pte. LTD)" | 2023-05-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-14 | 11 | APP | 2023-07-31 | 2 | 000014 | 2023-05-22, 2023-06-23, 2023-07-31 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
40 | 000015 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0001 | 0 | 131242-WST00-MI-C-0001-0 | 2023-05-23 | CSA Meeting Minutes 0001 | For Information | 2023-06-21 | 2023-06-12 | For Information |  | YES | NA |  | 131242-WST00-MI-0001 | NA | "CSA Meeting Minutes 0001" && "Engineering Kick Off Meeting Minutes 0001" && "Process & MEICA Meeting Minutes 0001" | 2023-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-06-12 | 20 | INF | 2023-06-19 | 0 | 000015&&000021&&000031 | 2023-05-23, 2023-06-11, 2023-06-19 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
41 | 000016 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 0001 | 0 | 131242-WST02-DS-M-0001-0 | 2023-05-26 | FRP TANK DATA SHEET | Not approved - Revise and Resubmit | 2023-06-26 | 2023-10-16 | Not Approved | 2023-11-03 | YES | Resubmitted |  | 131242-WST02-DS-0001 | NA | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for ACMV Equipment" && "Epoxy Coating System" && "FRP TANK DATA SHEET" | 2023-05-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-15 | 143 | NAP | 2025-10-13 | 0 | 000016&&001236&&001296&&001740 | 2023-05-26, 2025-04-18, 2025-05-15, 2025-10-13 | 00 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
42 | 000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 0 | 131242-WST02-DS-M-5401-0 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted | In Progress | 131242-WST02-DS-5401 | NA | "FRP TANK DATA SHEET" | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 24 | AWC | 2025-04-01 | 1 | 000016 | 2024-09-20, 2025-04-01 | 01, 02 | 2 | Approved | APP |  |  | 0 | AWC | AWC
43 | 000016 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5416 | 0 | 131242-WST02-DS-M-5416-0 | 2024-09-20 | FRP TANK DATA SHEET | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted |  | 131242-WST02-DS-5416 | NA | "FRP TANK DATA SHEET" | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 24 | AWC | 2025-04-01 | 1 | 000016 | 2024-09-20, 2025-04-01 | 01, 02 | 2 | Approved | APP |  |  | 0 | AWC | AWC
44 | 000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5401 | 1 | 131242-WST02-DS-M-5401-1 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DS-5401 | NA | "FRP TANK DATA SHEET" | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | 1 | 000016 | 2024-09-20, 2025-04-01 | 01, 02 | 2 | Approved | APP |  |  | 0 | APP | APP
45 | 000016 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5416 | 1 | 131242-WST02-DS-M-5416-1 | 2025-04-01 | FRP TANK DATA SHEET | Rev 2: Approved | 2025-04-21 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DS-5416 | NA | "FRP TANK DATA SHEET" | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-15 | 188 | APP | 2025-04-01 | 1 | 000016 | 2024-09-20, 2025-04-01 | 01, 02 | 2 | Approved | APP |  |  | 0 | APP | APP
46 | 000017 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 0 | 131242-WST00-LT-PM-0001-0 | 2023-05-27 | CVs of Team Member | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-26 | 2023-06-27 | Approved with Comments | 2023-07-18 | YES | Resubmitted |  | 131242-WST00-LT-0001 | NA | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | 2023-05-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-16 | 31 | AWC | 2023-07-12 | 1 | 000017 | 2023-05-27, 2023-07-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
47 | 000017 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0001 | 1 | 131242-WST00-LT-PM-0001-1 | 2023-07-12 | CVs of Team Member Part 1 (14 Members) | Rev.1: Approved with comments. Please refer to attached comment sheet. | 2023-08-01 | 2023-07-25 | Approved with Comments | 2023-08-15 | YES | Resubmitted |  | 131242-WST00-LT-0001 | NA | "CVs of Team Member" && "CVs of Team Member Part 1 (14 Members)" | 2023-05-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-26 | 13 | AWC | 2023-07-12 | 1 | 000017 | 2023-05-27, 2023-07-12 | 00, 01 | 2 | Approved with Comments | AWC | 2023-08-14 | Overdue | 0 | AWC | AWC
48 | 000017 | 02 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000017 | 2 | 131242-WSW41-LT-PM- Reply to Comment Sheet_#000017-2 | 2023-09-04 | CVs of Team Member Part 1 (14 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-22 | 2023-10-10 | Approved with Comments | 2023-10-30 | NO | Overdue | To obtain S.O. evaluation & final approval based on the probation period. To check with S.O during CSA bi-weekly meeting | 131242-WSW41-LT- Reply to Comment Sheet_#000017 | NA | "CVs of Team Member Part 1 (14 Members)" | 2023-09-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-24 | 36 | AWC | 2023-09-04 | 2 | 000017 | 2023-09-04 | 02 | 1 | Approved with Comments | AWC | 2023-10-30 | Overdue | 0 | AWC | AWC
49 | 000018 | 00 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-Z-0001-0 | 2023-05-31 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-30 | 2023-06-06 | Not Approved | 2023-06-26 | YES | Resubmitted |  | 131242-WST00-DR-0001 | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "Shop Drawings for Lintel and Stiffener " && "THP Process Flow Diagram" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-20 | 6 | NAP | 2025-01-26 | A | 000018&&000143&&001008 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
50 | 000018 | 01 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 1 | 131242-WST00-DR-Z-0001-1 | 2023-06-06 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-06-26 | 2023-06-23 | Not Approved | 2023-07-14 | YES | Resubmitted |  | 131242-WST00-DR-0001 | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "Shop Drawings for Lintel and Stiffener " && "THP Process Flow Diagram" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-20 | 17 | NAP | 2025-01-26 | A | 000018&&000143&&001008 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
51 | 000018 | 02 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 2 | 131242-WST00-DR-Z-0001-2 | 2023-06-27 | Title Block Template (CAD) | Rev.0- Not Approved. Submitted Native File was not in BIM Authoring Tools under P2C.8 | 2023-07-18 | 2023-07-03 | Not Approved | 2023-07-21 | YES | Resubmitted |  | 131242-WST00-DR-0001 | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "Shop Drawings for Lintel and Stiffener " && "THP Process Flow Diagram" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-11 | 6 | NAP | 2025-01-26 | A | 000018&&000143&&001008 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
52 | 000018 | 03 | REY | PMT | NA | 131242 | WST00 | DR | Z | 0001 | 3 | 131242-WST00-DR-Z-0001-3 | 2023-07-04 | Title Block Template (CAD) | Approved | 2023-07-24 | 2023-07-03 | Approved |  | YES | NA |  | 131242-WST00-DR-0001 | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "Shop Drawings for Lintel and Stiffener " && "THP Process Flow Diagram" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-18 |  | APP | 2025-01-26 | A | 000018&&000143&&001008 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | APP | APP
53 | 000019 | 00 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 0 | 131242-WST00-VI-C-0004-0 | 2023-05-31 | Vendor Approval for Cable Dectector (JLCD) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-06-30 | 2023-06-16 | Approved with Comments | 2023-07-07 | YES | Resubmitted |  | 131242-WST00-VI-0004 | NA | "Vendor Approval for Cable Dectector (JLCD)" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-06-20 | 16 | AWC | 2023-06-23 | 1 | 000019 | 2023-05-31, 2023-06-23 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
54 | 000019 | 01 | Keith | PMT | NA | 131242 | WST00 | VI | C | 0004 | 1 | 131242-WST00-VI-C-0004-1 | 2023-06-23 | Vendor Approval for Cable Dectector (JLCD) | Approved | 2023-07-14 | 2023-06-30 | Approved |  | YES | NA |  | 131242-WST00-VI-0004 | NA | "Vendor Approval for Cable Dectector (JLCD)" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-07 | 7 | APP | 2023-06-23 | 1 | 000019 | 2023-05-31, 2023-06-23 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
55 | 000020 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | FM | HS | 0001 | 0 | 131242-WST00-FM-HS-0001-0 | 2023-06-05 | HSE Stickers for Machineries and SIC Induction | Approved | 2023-07-04 | 2023-06-14 | Approved |  | YES | NA |  | 131242-WST00-FM-0001 | NA | "HSE Stickers for Machineries and SIC Induction" | 2023-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-06-25 | 9 | APP | 2023-06-05 | 0 | 000020 | 2023-06-05 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
56 | 000021 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0001 | 0 | 131242-WST00-MI-P-0001-0 | 2023-06-11 | Process & MEICA Meeting Minutes 0001 | For Information | 2023-07-10 | 2023-10-18 | For Information |  | YES | NA |  | 131242-WST00-MI-0001 | NA | "CSA Meeting Minutes 0001" && "Engineering Kick Off Meeting Minutes 0001" && "Process & MEICA Meeting Minutes 0001" | 2023-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-06-25 | 129 | INF | 2023-06-19 | 0 | 000015&&000021&&000031 | 2023-05-23, 2023-06-11, 2023-06-19 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
57 | 000022 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0002 | 0 | 131242-WST00-MI-P-0002-0 | 2023-06-11 | Process & MEICA Meeting Minutes 0002 | For Information | 2023-07-10 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WST00-MI-0002 | NA | "CSA Meeting Minutes 0002" && "Process & MEICA Meeting Minutes 0002" | 2023-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-01 | 281 | INF | 2023-06-16 | 0 | 000022&&000029 | 2023-06-11, 2023-06-16 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
58 | 000023 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0003 | 0 | 131242-WST00-MI-P-0003-0 | 2023-06-11 | Process & MEICA Meeting Minutes 0003 | For Information | 2023-07-10 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WST00-MI-0003 | NA | "CSA Meeting Minutes 0003" && "Process & MEICA Meeting Minutes 0003" | 2023-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-01 | 281 | INF | 2023-06-16 | 0 | 000023&&000030 | 2023-06-11, 2023-06-16 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
59 | 000024 | 00 | Qili | Process | NA | 131242 | WST00 | MI | P | 0004 | 0 | 131242-WST00-MI-P-0004-0 | 2023-06-11 | Process & MEICA Meeting Minutes 0004 | For Information | 2023-07-10 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WST00-MI-0004 | NA | "CSA Meeting Minutes 0004_20230614" && "Process & MEICA Meeting Minutes 0004" | 2023-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-01 | 281 | INF | 2023-06-28 | 0 | 000024&&000036 | 2023-06-11, 2023-06-28 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
60 | 000025 | 00 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 0 | 131242-WST00-LT-PM-0002-0 | 2023-06-12 | CVs of Team Member | Approved with comments. Please refer to comment sheet for resubmission. | 2023-07-11 | 2023-06-20 | Approved with Comments | 2023-07-11 | YES | Resubmitted |  | 131242-WST00-LT-0002 | NA | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | 2023-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-02 | 8 | AWC | 2023-07-12 | 1 | 000025 | 2023-06-12, 2023-07-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
61 | 000025 | 01 | Shena | PMT | NA | 131242 | WST00 | LT | PM | 0002 | 1 | 131242-WST00-LT-PM-0002-1 | 2023-07-12 | CVs of Team Member Part 2 (7 Members) | Rev.1: Approved with comments. Please refer to S.O. comment sheet. | 2023-08-01 | 2023-07-25 | Approved with Comments | 2023-08-15 | YES | Resubmitted | Reply to S.O. Comment Sheet Only | 131242-WST00-LT-0002 | NA | "CVs of Team Member" && "CVs of Team Member Part 2 (7 Members)" | 2023-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-26 | 13 | AWC | 2023-07-12 | 1 | 000025 | 2023-06-12, 2023-07-12 | 00, 01 | 2 | Approved with Comments | AWC | 2023-08-14 | Overdue | 0 | AWC | AWC
62 | 000025 | 02 | Shena/ Htet | PMT | NA | 131242 | NA | LT | PM | Reply to Comment Sheet_#000025 | 1 | 131242--LT-PM-Reply to Comment Sheet_#000025- | 2023-09-11 | CVs of Team Member Part 2 (7 Members) | Rev.2: Approved with comments. Please refer to attached comment sheet. | 2023-09-29 | 2024-09-10 | Approved with Comments | 2024-09-30 | NO | Overdue |  | 131242-NA-LT-Reply to Comment Sheet_#000025 | NA | "CVs of Team Member Part 2 (7 Members)" | 2023-09-11 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-01 | 365 | AWC | 2023-09-11 | 1 | 000025 | 2023-09-11 | 02 | 1 | Approved with Comments | AWC | 2024-09-30 | Overdue | 0 | AWC | AWC
63 | 000026 | 00 | Bryan | HSE | NA | 131242 | WST00 | MS | C | 0001 | 0 | 131242-WST00-MS-C-0001-0 | 2023-06-13 | Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-29 | Not Approved | 2023-07-19 | NO | Overdue | In Progress | 131242-WST00-MS-0001 | NA | "Risk Assessment, Safe Work Procedure and Method Statement for Cable Detection work (JLCD)" | 2023-06-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-03 | 16 | NAP | 2023-06-13 | 0 | 000026 | 2023-06-13 | 00 | 1 | Not Approved | NAP | 2023-07-19 | Overdue | 0 | NAP | NAP
64 | 000027 | 00 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 0 | 131242-WST00-RT-PM-0001-0 | 2023-06-13 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-12 | 2023-06-16 | Not Approved | 2023-07-07 | YES | Resubmitted |  | 131242-WST00-RT-0001 | NA | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-03 | 3 | NAP | 2023-07-14 | 2 | 000027 | 2023-06-13, 2023-07-04, 2023-07-14 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
65 | 000027 | 01 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 1 | 131242-WST00-RT-PM-0001-1 | 2023-07-04 | C4B Monthly Progress Report Number No.01 (05/23) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-24 | 2023-07-13 | Not Approved | 2023-08-02 | YES | Resubmitted |  | 131242-WST00-RT-0001 | NA | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-18 | 9 | NAP | 2023-07-14 | 2 | 000027 | 2023-06-13, 2023-07-04, 2023-07-14 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
66 | 000027 | 02 | Thomas | PCM | NA | 131242 | WST00 | RT | PM | 0001 | 2 | 131242-WST00-RT-PM-0001-2 | 2023-07-14 | C4B Monthly Progress Report Number No.01 (05/23) | Approved | 2023-08-03 | 2023-10-18 | Approved |  | YES | NA |  | 131242-WST00-RT-0001 | NA | "C4B Monthly Progress Report Number No.01 (05/23)" | 2023-06-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-28 | 96 | APP | 2023-07-14 | 2 | 000027 | 2023-06-13, 2023-07-04, 2023-07-14 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
67 | 000028 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 0 | 131242-WSD11-VI-M-0001-0 | 2023-06-14 | Vendor Approval for THP Package | Rev 0: Not approved - Revise and Resubmit | 2023-07-13 | 2023-07-14 | Not Approved | 2023-08-03 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-04 | 30 | NAP | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
68 | 000028 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 1 | 131242-WSD11-VI-M-0001-1 | 2023-07-28 | Vendor Approval for THP Package | Rev 1: Rejected as per contractor requested email dated on 31-Jul-2023 as there has few changes and will resubmit to include the comment sheet in next revision. | 2023-08-18 | 2023-08-01 | Not Approved | 2023-08-22 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-11 | 4 | NAP | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
69 | 000028 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 2 | 131242-WSD11-VI-M-0001-2 | 2023-08-02 | Preliminary design and Vendor Approval | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-08-23 | 2023-08-31 | Approved with Comments | 2023-09-20 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-16 | 29 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
70 | 000028 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 3 | 131242-WSD11-VI-M-0001-3 | 2023-11-10 | Preliminary design and Vendor Approval - THP Package | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-01 | 2023-12-20 | Approved with Comments | 2024-01-11 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-24 | 40 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
71 | 000028 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0001 | 4 | 131242-WSD11-VI-M-0001-4 | 2024-03-01 | Preliminary design and Vendor Approval - THP Package | Rev 4: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-03-21 | 2024-04-26 | Approved with Comments |  | YES | NA | Rev3: AWC | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-15 | 56 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
72 | 000029 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0002 | 0 | 131242-WST00-MI-C-0002-0 | 2023-06-16 | CSA Meeting Minutes 0002 | For information | 2023-07-17 | 2023-06-28 | For Information |  | YES | NA |  | 131242-WST00-MI-0002 | NA | "CSA Meeting Minutes 0002" && "Process & MEICA Meeting Minutes 0002" | 2023-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-06-30 | 12 | INF | 2023-06-16 | 0 | 000022&&000029 | 2023-06-11, 2023-06-16 | 00 | 2 | For Information | INF | 2023-07-18 | Overdue | 0 | INF | INF
73 | 000030 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0003 | 0 | 131242-WST00-MI-C-0003-0 | 2023-06-16 | CSA Meeting Minutes 0003 | For information | 2023-07-17 | 2023-06-28 | For Information |  | YES | NA |  | 131242-WST00-MI-0003 | NA | "CSA Meeting Minutes 0003" && "Process & MEICA Meeting Minutes 0003" | 2023-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-06-30 | 12 | INF | 2023-06-16 | 0 | 000023&&000030 | 2023-06-11, 2023-06-16 | 00 | 2 | For Information | INF | 2023-07-18 | Overdue | 0 | INF | INF
74 | 000031 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | Z | 0001 | 0 | 131242-WST00-MI-Z-0001-0 | 2023-06-19 | Engineering Kick Off Meeting Minutes 0001 | For Information | 2023-07-18 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WST00-MI-0001 | NA | "CSA Meeting Minutes 0001" && "Engineering Kick Off Meeting Minutes 0001" && "Process & MEICA Meeting Minutes 0001" | 2023-05-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-07-03 | 273 | INF | 2023-06-19 | 0 | 000015&&000021&&000031 | 2023-05-23, 2023-06-11, 2023-06-19 | 00 | 3 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
75 | 000032 | 00 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 0 | 131242-WST00-MS-C-0002-0 | 2023-06-19 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev. 0 - Not Approved need to re-submit (see comment sheet) | 2023-07-18 | 2023-06-29 | Not Approved | 2023-07-19 | YES | Resubmitted | In Progress | 131242-WST00-MS-0002 | NA | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | 2023-06-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-09 | 10 | NAP | 2024-04-12 | 1 | 000032 | 2023-06-19, 2024-04-12 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
76 | 000032 | 01 | Anuar | HSE | NA | 131242 | WST00 | MS | C | 0002 | 1 | 131242-WST00-MS-C-0002-1 | 2024-04-12 | Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | Approved |  | YES | NA |  | 131242-WST00-MS-0002 | NA | "Risk Assessment, SWP and Method Statement for Land Survey Work (Nanyang Survey Pte Ltd) " | 2023-06-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-26 | 55 | APP | 2024-04-12 | 1 | 000032 | 2023-06-19, 2024-04-12 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
77 | 000033 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PS | HS | 0001 | 0 | 131242-WST00-PS-HS-0001-0 | 2023-06-20 | C4B HSE Induction Course | Noted for information | 2023-07-19 | 2023-07-24 | For Information |  | YES | NA |  | 131242-WST00-PS-0001 | NA | "C4B HSE Induction Course" | 2023-06-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-07-10 | 34 | INF | 2023-06-20 | 0 | 000033 | 2023-06-20 | 00 | 1 | For Information | INF | 2023-08-11 | Overdue | 0 | INF | INF
78 | 000034 | 00 | Kristnnan | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 0 | 131242-WSW41-PP-HS-0003-0 | 2023-06-21 | Emergency Response Plan | Reporting timeline is not in sequence with what we have. Please use information in your KOM slides when preparing. Review and resubmit. | 2023-07-20 | 2023-08-02 | Not Approved | 2023-08-23 | YES | Resubmitted |  | 131242-WSW41-PP-0003 | NA | "Emergency Response Plan" && "Project Execution Plan" | 2023-06-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-11 | 42 | NAP | 2023-10-10 | 0 | 000034&&000124 | 2023-06-21, 2023-09-07, 2023-10-10 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
79 | 000034 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0003 | 1 | 131242-WSW41-PP-HS-0003-1 | 2023-09-07 | Emergency Response Plan | Approved | 2023-09-27 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-PP-0003 | NA | "Emergency Response Plan" && "Project Execution Plan" | 2023-06-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-21 | 18 | APP | 2023-10-10 | 0 | 000034&&000124 | 2023-06-21, 2023-09-07, 2023-10-10 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | APP | APP
80 | 000035 | 00 | Kristnnan | HSE | NA | 131242 | WST00 | PP | HS | 0002 | 0 | 131242-WST00-PP-HS-0002-0 | 2023-06-22 | Project Accident Statistic Board and BCA Board | Rev.0: Not Approved. Please find attached comment sheet for resubmission. | 2023-07-21 | 2023-08-18 | Not Approved | 2023-09-07 | YES | Resubmitted |  | 131242-WST00-PP-0002 | NA | "Project Accident Statistic Board and BCA Board" | 2023-06-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-12 | 57 | NAP | 2023-06-22 | 0 | 000035 | 2023-06-22 | 00 | 1 | Not Approved | NAP | 2023-09-07 | Overdue | 0 | NAP | NAP
81 | 000035 | 01 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0002 | 1 | 131242-WSW41-PP-HS-0002-1 | 2023-10-13 | Project Accident Statistic Board and BCA Board | Approved | 2023-11-02 | 2023-10-23 | Approved |  | YES | NA |  | 131242-WSW41-PP-0002 | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-27 | 10 | APP | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
82 | 000036 | 00 | Zora | CSA | NA | 131242 | WST00 | MI | C | 0004 | 0 | 131242-WST00-MI-C-0004-0 | 2023-06-28 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-07-27 | 2023-07-12 | For Information |  | YES | NA |  | 131242-WST00-MI-0004 | NA | "CSA Meeting Minutes 0004_20230614" && "Process & MEICA Meeting Minutes 0004" | 2023-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-07-12 | 14 | INF | 2023-06-28 | 0 | 000024&&000036 | 2023-06-11, 2023-06-28 | 00 | 2 | For Information | INF | 2023-08-01 | Overdue | 0 | INF | INF
83 | 000037 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0001 | 0 | 131242-WSW41-MI-IM-0001-0 | 2023-06-28 | BIM Bi-Weekly Meeting Minutes 0001_20230614 | For Information | 2023-07-27 | 2023-07-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0001 | NA | "BIM Bi-Weekly Meeting Minutes 0001_20230614" && "BS Meeting Minutes 0001_20230706" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-06-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-18 | 6 | INF | 2023-09-04 | 0 | 000037&&000048&&000087 | 2023-06-28, 2023-07-14, 2023-09-04 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
84 | 000038 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | B | 0001 | 0 | 131242-WSW41-CL-B-0001-0 | 2023-07-05 | Temporary Utilities for Contractor’s Site Office | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-02 | 2023-07-21 | Approved with Comments | 2023-08-11 | NO | Overdue |  | 131242-WSW41-CL-0001 | NA | "ECM Plan and Calculation" && "Temporary Utilities for Contractor’s Site Office" | 2023-07-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-25 | 16 | AWC | 2023-08-31 | 0 | 000038&&000086 | 2023-07-05, 2023-08-31 | 00 | 2 | Approved | APP |  |  | 0 | AWC | AWC
85 | 000039 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | MI | P | 0001 | 0 | 131242-WSD11-MI-P-0001-0 | 2023-07-05 | MI-Process & MEICA Meeting Minutes with THP (CAMBI) | For Information | 2023-08-02 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSD11-MI-0001 | NA | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" && "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2023-07-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-25 | 257 | INF | 2024-02-28 | 0 | 000039&&000330 | 2023-07-05, 2024-02-28 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
86 | 000040 | 00 | Stanley | PCM | NA | 131242 | WSW41 | LT | PM | 0003 | 0 |  | 2023-07-06 | Request for time extension_Programme of works resubmission | The Prolog Submittals number 000040 (need to void) should not be created as new submission, this submission should under Prologs number 000005 because this extension request is referring from Rev. 0 to Rev. 1 - Programme of the Works | 2023-08-03 | 2023-09-22 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WSW41-LT-0003 | NA | "PROGRAMME OF THE WORKS" && "Request for time extension_Programme of works resubmission" | 2023-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2023-07-26 | 78 | VOID | 2023-09-26 | 0 | 000005&&000040 | 2023-07-06, 2023-09-26 | 00, 03 | 2 | For Information | INF |  |  | 0 | VOID | VOID
87 | 000041 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0005 | 0 | 131242-WSW41-MI-C-0005-0 | 2023-07-06 | CSA Meeting Minutes 0004_20230614 | For Information | 2023-08-03 | 2023-10-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0005 | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-26 | 104 | INF | 2023-11-20 | 0 | 000041&&000068&&000073&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
88 | 000042 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0004 | 0 | 131242-WSW41-LT-PM-0004-0 | 2023-07-06 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-08-03 | 2023-08-21 | Approved with Comments | 2023-09-08 | YES | Resubmitted |  | 131242-WSW41-LT-0004 | NA | "CVs of Team Members (Part 3)" | 2023-07-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-26 | 46 | AWC | 2023-07-06 | 0 | 000042 | 2023-07-06 | 00 | 1 | Approved with Comments | AWC | 2023-09-08 | Overdue | 0 | AWC | AWC
89 | 000042 | 01 | Shena/ Htet | PMT | NA | 131242 | WSW41 | LT | PM | Reply to Comment Sheet_#000042 | 0 | 131242-WSW41-LT-PM-Reply to Comment Sheet_#000042- | 2023-09-04 | CVs of Team Members (Part 3) | Approved with comments. Please refer to the comment sheet. | 2023-09-22 | 2024-02-01 | Approved with Comments | 2024-02-22 | NO | Overdue |  | 131242-WSW41-LT-Reply to Comment Sheet_#000042 | NA | "CVs of Team Members (Part 3)" | 2023-09-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-24 | 150 | AWC | 2023-09-04 | 0 | 000042 | 2023-09-04 | 01 | 1 | Approved with Comments | AWC | 2024-02-21 | Overdue | 0 | AWC | AWC
90 | 000043 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0001 | 0 | 131242-WSW41-PS-PM-0001-0 | 2023-07-07 | Presentation Slide for Monthly Progress Meeting No. 01(0523) | For information only | 2023-08-04 | 2023-07-13 | For Information |  | YES | NA |  | 131242-WSW41-PS-0001 | NA | "Presentation Slide for Monthly Progress Meeting No. 01(0523)" | 2023-07-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-07-27 | 6 | INF | 2023-07-07 | 0 | 000043 | 2023-07-07 | 00 | 1 | For Information | INF | 2023-08-02 | Overdue | 0 | INF | INF
91 | 000044 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0005 | 0 | 131242-WSW41-LT-PM-0005-0 | 2023-07-07 | CVs of Team Members (Part 4) | Approved | 2023-08-04 | 2023-07-24 | Approved |  | YES | NA |  | 131242-WSW41-LT-0005 | NA | "CVs of Team Members (Part 4)" | 2023-07-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-27 | 17 | APP | 2023-07-07 | 0 | 000044 | 2023-07-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
92 | 000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0002 | 0 | 131242-WSW41-DR-Z-0002-0 | 2023-07-10 | SITE UTILIZATION PLAN | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 | Approved with Comments | 2023-08-11 | YES | Resubmitted |  | 131242-WSW41-DR-0002 | NA | "SITE UTILIZATION PLAN" | 2023-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-30 | 11 | AWC | 2023-07-10 | 0 | 000045 | 2023-07-10 | 00 | 1 | Approved with Comments | AWC | 2023-08-10 | Overdue | 0 | AWC | AWC
93 | 000045 | 00 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 0 | 131242-WSW41-DR-Z-0003-0 | 2023-07-10 | SITE OFFICE LAYOUT (Rev1) | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-07 | 2023-07-21 | Approved with Comments | 2023-08-11 | YES | Resubmitted |  | 131242-WSW41-DR-0003 | NA | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | 2023-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-30 | 11 | AWC | 2023-07-26 | 1 | 000045 | 2023-07-10, 2023-07-26 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
94 | 000045 | 01 | Edwin | PMT | NA | 131242 | WSW41 | DR | Z | 0003 | 1 | 131242-WSW41-DR-Z-0003-1 | 2023-07-26 | SITE OFFICE LAYOUT (Rev2) | Approved | 2023-08-16 | 2023-08-02 | Approved |  | YES | NA |  | 131242-WSW41-DR-0003 | NA | "SITE OFFICE LAYOUT (Rev1)" && "SITE OFFICE LAYOUT (Rev2)" | 2023-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-09 | 7 | APP | 2023-07-26 | 1 | 000045 | 2023-07-10, 2023-07-26 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
95 | 000046 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 0 | 131242-WSW41-RT-PM-0002-0 | 2023-07-12 | C4B Monthly Progress Report Number No.02 (06/23) | Rejected as informed by contractor email dated 12-Jul-2023 there has few changes/ corrections in the attached file. | 2023-08-10 | 2023-07-14 | Rejected | 2023-08-03 | YES | Resubmitted |  | 131242-WSW41-RT-0002 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-01 | 2 | REJ | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | For Information | INF |  |  | 0 | REJ | REJ
96 | 000046 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0002 | 1 | 131242-WSW41-RT-PM-0002-1 | 2023-07-14 | C4B Monthly Progress Report Number No.02 (06/23) | Rev. 1 - Approved with comments (see the comment sheet) Resubmission required | 2023-08-03 | 2023-10-18 | Approved with Comments | 2023-11-07 | YES | Resubmitted |  | 131242-WSW41-RT-0002 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-07-28 | 96 | AWC | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | For Information | INF |  |  | 0 | AWC | AWC
97 | 000046 | 02 | Thomas | PCM | NA | Comment Reply Sheet 08112023 | NA | NA | NA | 9999 | 1 | Comment Reply Sheet 08112023----- | 2023-11-09 | C4B Monthly Progress Report Number No.02 (06/23) | Approved | 2023-11-30 | 2023-11-15 | Approved |  | YES | NA |  | Comment Reply Sheet 08112023-NA-NA-9999 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" | 2023-11-09 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2023-11-29 | 6 | APP | 2023-11-09 | 1 | 000046 | 2023-11-09 | 02 | 1 | Approved | APP |  |  | 0 | APP | APP
98 | 000047 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0002 | 0 | 131242-WSW41-MI-IM-0002-0 | 2023-07-13 | BIM Bi-Weekly Meeting Minutes 0002_20230628 | For Information | 2023-08-11 | 2023-07-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0002 | NA | "BIM Bi-Weekly Meeting Minutes 0002_20230628" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-07-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-02 | 11 | INF | 2023-09-04 | 0 | 000047&&000087 | 2023-07-13, 2023-09-04 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
99 | 000048 | 00 | Matthew | Piping/ BS | NA | 131242 | WSW41 | MI | B | 0001 | 0 | 131242-WSW41-MI-B-0001-0 | 2023-07-14 | BS Meeting Minutes 0001_20230706 | For Information | 2023-08-14 | 2024-02-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0001 | NA | "BIM Bi-Weekly Meeting Minutes 0001_20230614" && "BS Meeting Minutes 0001_20230706" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-06-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-07-28 | 216 | INF | 2023-09-04 | 0 | 000037&&000048&&000087 | 2023-06-28, 2023-07-14, 2023-09-04 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
100 | 000049 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PP | PM | 0002 | 0 | 131242-WSW41-PP-PM-0002-0 | 2023-07-14 | C4B Manpower Deployment Plan | Approved as noted. Please note that acceptable of the manpower deployment plan shall not relieve the Contractor's responsibility to engage key personnel whenever is required or employ additional manpower to complete and successfully deliver the project timely and safely. | 2023-08-14 | 2023-07-24 | Approved |  | YES | NA |  | 131242-WSW41-PP-0002 | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-03 | 10 | APP | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
101 | 000050 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0006 | 0 | 131242-WSW41-MI-C-0006-0 | 2023-07-14 | CSA Meeting Minutes 0004_20230705 | For Information | 2023-08-14 | 2023-07-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0006 | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-03 | 10 | INF | 2023-11-15 | 0 | 000050&&000068&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
102 | 000051 | 00 | REY | PMT | NA | 131242 | WSW41 | DR | C | 1000 | 0 | 131242-WSW41-DR-C-1000-0 | 2023-07-18 | Drawing of Pre-Con Topographical Survey | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-08-16 | 2023-08-11 | Approved with Comments | 2023-08-31 | NO | Overdue | Heng Peng: To clear BIM comments | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-07 | 24 | AWC | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
103 | 000052 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0003 | 0 | 131242-WSW41-MI-IM-0003-0 | 2023-07-18 | BIM Bi-Weekly Meeting Minutes 0003_20230712 | For Information | 2023-08-16 | 2023-07-25 | For Information |  | YES | NA |  | 131242-WSW41-MI-0003 | NA | "BIM Bi-Weekly Meeting Minutes 0003_20230712" && "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-07 | 7 | INF | 2023-10-25 | 0 | 000052&&000138 | 2023-07-18, 2023-10-25 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
104 | 000053 | 00 | Heng Peng | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 0 | 131242-WSW41-LT-PM-0006-0 | 2023-07-19 | CV of Team Member (BIM Authoring Lead) | R0- Proposed candidate doesn’t meet the requirement. Please refer to "Comment sheet - Submittal 000053.0" | 2023-08-17 | 2023-10-23 | Not Approved | 2023-11-10 | YES | Resubmitted |  | 131242-WSW41-LT-0006 | NA | "CV of Team Member (BIM Authoring Lead)" | 2023-07-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-08 | 96 | NAP | 2023-12-11 | 1 | 000053 | 2023-07-19, 2023-12-11 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
105 | 000053 | 01 | Leon | PMT | NA | 131242 | WSW41 | LT | PM | 0006 | 1 | 131242-WSW41-LT-PM-0006-1 | 2023-12-11 | CV of Team Member (BIM Authoring Lead) | R1- Subject to 6 months' probation period. Please refer to "Comment sheet - Submittal 000053.1" | 2024-01-02 | 2023-12-22 | Not Approved |  | YES | NA |  | 131242-WSW41-LT-0006 | NA | "CV of Team Member (BIM Authoring Lead)" | 2023-07-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-25 | 11 | NAP | 2023-12-11 | 1 | 000053 | 2023-07-19, 2023-12-11 | 00, 01 | 2 | Not Approved | NAP | 2024-01-11 | Overdue | 0 | NAP | NAP
106 | 000054 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0007 | 0 | 131242-WSW41-MI-C-0007-0 | 2023-07-24 | CSA Meeting Minutes 0007_20230712 | For Information | 2023-08-22 | 2023-08-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0007 | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-13 | 17 | INF | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
107 | 000055 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0001 | 0 | 131242-WSW41-PC-W-0001-0 | 2023-07-24 | PROGRESS CLAIM NO.1 | Accepted. Please refer to S.O. Correspondence no. 25 dated 25 July 2023. | 2023-08-22 | 2023-08-30 | Approved |  | YES | NA |  | 131242-WSW41-PC-0001 | NA | "PROGRESS CLAIM NO.1" | 2023-07-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-13 | 37 | APP | 2023-07-24 | 0 | 000055 | 2023-07-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
108 | 000056 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0004 | 0 | 131242-WSW41-PP-HS-0004-0 | 2023-07-27 | Signboard Sticker for TWRP Main Gate route 3 entrance | For information | 2023-08-25 | 2023-08-02 | For Information |  | YES | NA |  | 131242-WSW41-PP-0004 | NA | "Signboard Sticker for TWRP Main Gate route 3 entrance" | 2023-07-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-08-16 | 6 | INF | 2023-07-27 | 0 | 000056 | 2023-07-27 | 00 | 1 | For Information | INF | 2023-08-22 | Overdue | 0 | INF | INF
109 | 000057 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0002 | 0 | 131242-WSW41-PS-PM-0002-0 | 2023-07-28 | Presentation Slide for Monthly Progress Meeting No. 02(0623) | For information | 2023-08-28 | 2023-08-01 | For Information |  | YES | NA |  | 131242-WSW41-PS-0002 | NA | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" && "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" | 2023-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-17 | 4 | INF | 2023-11-02 | 0 | 000057&&000157 | 2023-07-28, 2023-11-02 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
110 | 000058 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 0 | 131242-WSW41-MS-C-0003-0 | 2023-07-28 | MSRA, SWP for General Civil Works | Rev.0: Approved with comments. Please refer to attached comment sheet for resubmission. | 2023-08-28 | 2023-08-14 | Approved with Comments | 2023-09-01 | YES | Resubmitted |  | 131242-WSW41-MS-0003 | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-17 | 17 | AWC | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
111 | 000058 | 01 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 1 | 131242-WSW41-MS-C-0003-1 | 2024-01-22 | MSRA, SWP for General Civil Works | Rev.1: Approved with comments. Please refer to attached comment sheet for resubmission. | 2024-02-09 | 2024-02-21 | Approved with Comments | 2024-03-12 | YES | Resubmitted |  | 131242-WSW41-MS-0003 | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-05 | 30 | AWC | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
112 | 000058 | 02 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 2 | 131242-WSW41-MS-C-0003-2 | 2024-04-12 | MSRA, SWP for General Civil Works | Rev.2: Approved | 2024-05-03 | 2024-06-06 | Approved |  | YES | NA |  | 131242-WSW41-MS-0003 | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-26 | 55 | APP | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
113 | 000058 | 03 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0003 | 3 | 131242-WSW41-MS-C-0003-3 | 2025-03-20 | MSRA, SWP for General Civil Works | R3: Approved | 2025-04-09 | 2025-05-07 | Approved |  | YES | NA |  | 131242-WSW41-MS-0003 | NA | "MSRA and SWP for Installation of Compressor Package at C4A Biosolids Building " && "MSRA and SWP for Plastering and Skim Coat " && "MSRA, SWP for General Civil Works" | 2023-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-03 | 48 | APP | 2025-04-03 | 0 | 000058&&000818&&001197 | 2023-07-28, 2024-01-22, 2024-04-12, 2024-11-16, 2025-03-20, 2025-04-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
114 | 000059 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0005 | 0 | 131242-WSW41-VI-C-0005-0 | 2023-08-01 | Vendor Approval of Concrete Supplier-Alliance | Rev.0: Approved | 2023-08-30 | 2023-08-10 | Approved |  | YES | NA |  | 131242-WSW41-VI-0005 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-21 | 9 | APP | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
115 | 000060 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | Change it to PM0008 | 2023-08-01 | Adjustment of Stage Payment | Rejected as contractor would like to resubmit with the correct reference. | 2023-08-30 | 2023-08-02 | Rejected | 2023-08-23 | YES | Resubmitted |  | 131242-WSW41-PC-0002 | NA | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-21 | 1 | REJ | 2023-08-25 | 0 | 000060&&000080 | 2023-08-01, 2023-08-25 | 00 | 2 | Approved | APP |  |  | 0 | REJ | REJ
116 | 000060 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0008 | 0 | 131242-WSW41-LT-PM-0008-0 | 2023-08-02 | Adjustment of Stage Payment | Rejected. Contractor to re-submit. Please refer to S.O. correspondence no. 55 dated 13 Sep 2023. | 2023-08-23 | 2023-09-15 | Rejected | 2023-10-05 | YES | Resubmitted |  | 131242-WSW41-LT-0008 | NA | "Adjustment of Stage Payment" | 2023-08-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-22 | 44 | REJ | 2023-08-02 | 0 | 000060 | 2023-08-02 | 01 | 1 | Rejected | REJ | 2023-10-05 | Overdue | 0 | REJ | REJ
117 | 000060 | 02 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0014 | 0 | 131242-WSW41-LT-PM-0014-0 | 2023-10-18 | Adjustment of Stage Payment | For Information | 2023-11-07 | 2023-12-18 | For Information |  | YES | NA |  | 131242-WSW41-LT-0014 | NA | "Adjustment of Stage Payment" | 2023-10-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-07 | 61 | INF | 2023-10-18 | 0 | 000060 | 2023-10-18 | 02 | 1 | For Information | INF | 2024-01-05 | Overdue | 0 | INF | INF
118 | 000061 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0009 | 0 | 131242-WSW41-LT-PM-0009-0 | 2023-08-03 | CV of Team Member (CM) | Approved | 2023-09-01 | 2023-08-11 | Approved |  | YES | NA |  | 131242-WSW41-LT-0009 | NA | "CV of Team Member (CM)" | 2023-08-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-23 | 8 | APP | 2023-08-03 | 0 | 000061 | 2023-08-03 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
119 | 000062 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0007 | 0 | 131242-WSW41-LT-PM-0007-0 | 2023-08-03 | Request for Variable Site Management Team Payment | Rev(0) Accepted. Please refer to S.O. correspondence no. 84 dated 22 Nov 2023. | 2023-09-01 | 2024-01-30 | For Information |  | YES | NA |  | 131242-WSW41-LT-0007 | NA | "Request for Variable Site Management Team Payment" | 2023-08-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-08-23 | 180 | INF | 2023-08-03 | 0 | 000062 | 2023-08-03 | 00 | 1 | For Information | INF | 2024-02-19 | Overdue | 0 | INF | INF
120 | 000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0008 | 0 | 131242-WSW41-MI-C-0008-0 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 | For Information |  | YES | NA |  | 131242-WSW41-MI-0008 | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-27 | 4 | INF | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
121 | 000063 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0009 | 0 | 131242-WSW41-MI-C-0009-0 | 2023-08-07 | CSA Meeting Minutes 0008 and 0009_20230719 & 20230726 | For Information | 2023-09-05 | 2023-08-11 | For Information |  | YES | NA |  | 131242-WSW41-MI-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0009_20240220" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-27 | 4 | INF | 2024-03-01 | 0 | 000063&&000104&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
122 | 000064 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 0 | 131242-WSW41-VI-C-0006-0 | 2023-08-08 | Vendor Approval of Concrete Supplier-Pan United | Rev.0: Approved with comment. Please refer to attached comment sheet for resubmission. | 2023-09-06 | 2023-08-30 | Approved with Comments | 2023-09-19 | YES | Resubmitted |  | 131242-WSW41-VI-0006 | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-08-28 | 22 | AWC | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
123 | 000064 | 01 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0006 | 1 | 131242-WSW41-VI-C-0006-1 | 2023-09-22 | Vendor Approval of Concrete Supplier-Pan United | Approved | 2023-10-12 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-VI-0006 | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-06 | 3 | APP | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
124 | 000065 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | CN | E | 0001 | 0 | 131242-WSW41-CN-E-0001-0 | 2023-08-08 | RFC For HV Routing (from C3B1) to SSN Transformer Room | Approved. Refer comment sheet for more details. | 2023-09-06 | 2024-02-15 | Approved |  | YES | NA |  | 131242-WSW41-CN-0001 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-28 | 191 | APP | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | Rejected | REJ |  |  | 0 | APP | APP
125 | 000066 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0001 | 0 | 131242-WSW41-CD-IM-0001-0 | 2023-08-08 | Submission Of BIM Coordination VCM Model (July – 2023) | Approved with Comments. Please refer to "Comments Sheet_Sub-0066-0" | 2023-09-06 | 2023-08-24 | Approved with Comments |  | YES | NA |  | 131242-WSW41-CD-0001 | NA | "Electrical Signal List for MCC - TYPICAL" && "Electrical Signal List for SSN -MCC-0102A/0102B " && "Submission Of BIM Coordination VCM Model (July – 2023)" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-28 | 16 | AWC | 2025-07-25 | 1 | 000066&&001350&&001467 | 2023-08-08, 2025-06-10, 2025-07-25 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
126 | 000067 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0007 | 0 | 131242-WSW41-VI-C-0007-0 | 2023-08-11 | Vendor Approval of Rebar Supplier-BRC ASIA LIMITED | Approved | 2023-09-08 | 2023-08-30 | Approved |  | YES | NA |  | 131242-WSW41-VI-0007 | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-31 | 19 | APP | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
127 | 000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0005 | 0 | 131242-WSW41-MI-P-0005-0 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0005 | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-28 | 217 | INF | 2023-11-20 | 0 | 000041&&000068&&000073&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
128 | 000068 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0006 | 0 | 131242-WSW41-MI-P-0006-0 | 2023-08-14 | Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803 | For Information | 2023-09-11 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0006 | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-28 | 217 | INF | 2023-11-15 | 0 | 000050&&000068&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
129 | 000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0001 | 0 | 131242-WST02-MI-P-0001-0 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WST02-MI-0001 | NA | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | 2023-08-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-09-03 | 217 | INF | 2023-08-14 | 0 | 000069 | 2023-08-14 | 00 | 1 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
130 | 000069 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0002 | 0 | 131242-WST02-MI-P-0002-0 | 2023-08-14 | SSN Workshop Meeting Minutes 001&002-20230720 & 20230721 | For Information | 2023-09-11 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WST02-MI-0002 | NA | "SSN Workshop Meeting Minutes 001&002-20230720 & 20230721" | 2023-08-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-09-03 | 217 | INF | 2023-08-14 | 0 | 000069 | 2023-08-14 | 00 | 1 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
131 | 000070 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 0 | 131242-WSW41-RT-PM-0003-0 | 2023-08-14 | C4B Monthly Progress Report Number No.03 (07/23) | Rev. 0 - Approved with Comments . Refer to Comments sheet to re-submit. | 2023-09-11 | 2023-08-29 | Approved with Comments | 2023-09-18 | YES | Resubmitted |  | 131242-WSW41-RT-0003 | NA | "C4B Monthly Progress Report Number No.03 (07/23)" | 2023-08-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-03 | 15 | AWC | 2023-09-25 | 1 | 000070 | 2023-08-14, 2023-09-25 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
132 | 000070 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0003 | 1 | 131242-WSW41-RT-PM-0003-1 | 2023-09-25 | C4B Monthly Progress Report Number No.03 (07/23) | Approved | 2023-10-13 | 2023-09-27 | Approved |  | YES | NA |  | 131242-WSW41-RT-0003 | NA | "C4B Monthly Progress Report Number No.03 (07/23)" | 2023-08-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-09 | 2 | APP | 2023-09-25 | 1 | 000070 | 2023-08-14, 2023-09-25 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
133 | 000071 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0009 | 0 | 131242-WSW41-VI-C-0009-0 | 2023-08-15 | Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 | Approved |  | YES | NA |  | 131242-WSW41-VI-0009 | NA | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " && "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-04 | 15 | APP | 2024-10-26 | 0 | 000071&&000780 | 2023-08-15, 2024-10-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
134 | 000072 | 00 | Edwin | PMT | NA | 131242 | WSW41 | VI | C | 0010 | 0 | 131242-WSW41-VI-C-0010-0 | 2023-08-15 | Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd. | Approved | 2023-09-12 | 2023-08-30 | Approved |  | YES | NA |  | 131242-WSW41-VI-0010 | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-04 | 15 | APP | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
135 | 000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0004 | 0 | 131242-WSW41-MI-IM-0004-0 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0004 | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-04 | 6 | INF | 2023-10-25 | 0 | 000073&&000138 | 2023-08-15, 2023-10-25 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
136 | 000073 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0005 | 0 | 131242-WSW41-MI-IM-0005-0 | 2023-08-15 | BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810 | For Information | 2023-09-12 | 2023-08-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0005 | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-08-29 | 6 | INF | 2023-11-20 | 0 | 000041&&000068&&000073&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
137 | 000074 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | C | 0008 | 0 | 131242-WSW41-VI-C-0008-0 | 2023-08-16 | Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd | Approved | 2023-09-13 | 2023-08-30 | Approved |  | YES | NA |  | 131242-WSW41-VI-0008 | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-05 | 14 | APP | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
138 | 000075 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0011 | 0 | 131242-WSW41-LT-PM-0011-0 | 2023-08-22 | CV of Team Member (WSHC) | Approved | 2023-09-19 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-LT-0011 | NA | "CV of Team Member (WSHC)" | 2023-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-11 | 34 | APP | 2023-08-22 | 0 | 000075 | 2023-08-22 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
139 | 000076 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0010 | 0 | 131242-WSW41-LT-PM-0010-0 | 2023-08-22 | Delegation of Signing Authorities | For Information | 2023-09-19 | 2023-09-25 | For Information |  | YES | NA |  | 131242-WSW41-LT-0010 | NA | "Delegation of Signing Authorities" | 2023-08-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-09-11 | 34 | INF | 2023-08-22 | 0 | 000076 | 2023-08-22 | 00 | 1 | For Information | INF | 2023-10-13 | Overdue | 0 | INF | INF
140 | 000077 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0003 | 0 | 131242-WSW41-PS-PM-0003-0 | 2023-08-28 | Presentation Slide for Monthly Progress Meeting No. 03(0723) | For Information | 2023-09-25 | 2023-08-24 | For Information |  | YES | NA |  | 131242-WSW41-PS-0003 | NA | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" && "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-17 |  | INF | 2024-02-03 | 0 | 000077&&000300 | 2023-08-28, 2024-02-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
141 | 000078 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0001 | 0 | 131242-WSW41-RT-Z-0001-0 | 2023-08-24 | Photographic Survey Report for C4B | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-09-21 | 2023-08-30 | Not Approved | 2023-09-19 | NO | Overdue |  | 131242-WSW41-RT-0001 | NA | "1st CONSAAS Audit report_2023" && "Photographic Survey Report for C4B" && "UXO Scanning Report" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 6 | NAP | 2024-02-15 | 0 | 000078&&000228&&000314 | 2023-08-24, 2023-12-05, 2024-02-15 | 00 | 3 | For Information | INF |  |  | 0 | NAP | NAP
142 | 000079 | 00 | Zora | CSA | NA | 1.0 Design Brief | NA | NA | NA | 9999 | 0 | 1.0 Design Brief----- | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-08-31 | Not Approved | 2023-09-20 | YES | Resubmitted |  | 1.0 Design Brief-NA-NA-9999 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 7 | NAP | 2023-08-24 | 0 | 000079 | 2023-08-24 | 00 | 1 | Not Approved | NAP | 2023-09-20 | Overdue | 0 | NAP | NAP
143 | 000079 | 00 | Zora | CSA | NA | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003 | NA | NA | NA | 9999 | 0 | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003----- | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 2.0 SSN Pipe Rack Reaction Table_SSN-PR- 001 002 & 003-NA-NA-9999 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2023-08-24 | 0 | 000079 | 2023-08-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
144 | 000079 | 00 | Zora | CSA | NA | 3.0 Overall SSN area Loading Plan Marked up | NA | NA | NA | 9999 | 0 | 3.0 Overall SSN area Loading Plan Marked up----- | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 3.0 Overall SSN area Loading Plan Marked up-NA-NA-9999 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2023-08-24 | 0 | 000079 | 2023-08-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
145 | 000079 | 00 | Zora | CSA | NA | 4.0 SSN Overall Area Layout and Elevations | NA | NA | NA | 9999 | 0 | 4.0 SSN Overall Area Layout and Elevations----- | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 4.0 SSN Overall Area Layout and Elevations-NA-NA-9999 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2023-08-24 | 0 | 000079 | 2023-08-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
146 | 000079 | 00 | Zora | CSA | NA | 5.0 Soil Report | NA | NA | NA | 9999 | 0 | 5.0 Soil Report----- | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 5.0 Soil Report-NA-NA-9999 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2023-08-24 | 0 | 000079 | 2023-08-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
147 | 000079 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A | 131242-WST00-DR-C-8000_ST604-A | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 131242-WST00-DR-8000_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2023-11-07 | A1 | 000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
148 | 000079 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A | 131242-WST00-DR-S-1000_ST604-A | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 131242-WST00-DR-1000_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2023-11-07 | A1 | 000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
149 | 000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A | 131242-WST02-DR-C-1001_ST604-A | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 131242-WST02-DR-1001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2024-02-16 | B1 | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
150 | 000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A | 131242-WST02-DR-C-5001_ST604-A | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 131242-WST02-DR-5001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | APP | APP
151 | 000079 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A | 131242-WST02-DR-C-7000_ST604-A | 2023-08-24 | ST604 – Overall SSN area Piling Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-09-21 | 2023-09-07 | Approved |  | YES | Resubmitted |  | 131242-WST02-DR-7000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-13 | 14 | APP | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
152 | 000079 | 01 | Zora | CSA | NA | 1. C4B SSN Overall Piling Design Brief | NA | NA | NA | 9999 | A | 1. C4B SSN Overall Piling Design Brief----- | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-16 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 1. C4B SSN Overall Piling Design Brief-NA-NA-9999 | NA | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-16 | 21 | NAP | 2023-09-26 | A | 000079 | 2023-09-26 | 01 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
153 | 000079 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | C | 0001_ST604 | 0 | 131242-WST02-CL-C-0001_ST604-0 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-CL-0001_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-09-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-16 | 21 | NAP | 2023-09-26 | 0 | 000079 | 2023-09-26 | 01 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
154 | 000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A1 | 131242-WST02-DR-C-1001_ST604-A1 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-10 | 21 | NAP | 2024-02-16 | B1 | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
155 | 000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A1 | 131242-WST02-DR-C-5001_ST604-A1 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-5001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-10 | 21 | NAP | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
156 | 000079 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A1 | 131242-WST02-DR-C-7000_ST604-A1 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-7000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-10 | 21 | NAP | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
157 | 000079 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A1 | 131242-WST00-DR-C-8000_ST604-A1 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST00-DR-8000_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-10 | 21 | NAP | 2023-11-07 | A1 | 000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
158 | 000079 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-S-1000_ST604-A1 | 2023-09-26 | ST604 – Overall SSN area Piling Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2023-10-24 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST00-DR-1000_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-10 | 21 | NAP | 2023-11-07 | A1 | 000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
159 | 000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604 | A1 | 131242-WST00-DR-S-1000_ST604-A1 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-21 | Approved with Comments | 2023-12-11 | NO | Overdue | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | 131242-WST00-DR-1000_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 14 | AWC | 2023-11-07 | A1 | 000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-11 | Overdue | 0 | AWC | AWC
160 | 000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | A1 | 131242-WST02-DR-C-1001_ST604-A1 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | Approved with Comments | 2023-12-11 | NO | Overdue |  | 131242-WST02-DR-1001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 14 | AWC | 2024-02-16 | B1 | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
161 | 000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | A1 | 131242-WST02-DR-C-5001_ST604-A1 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | Approved with Comments | 2023-12-11 | NO | Overdue |  | 131242-WST02-DR-5001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 14 | AWC | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
162 | 000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | A1 | 131242-WST02-DR-C-7000_ST604-A1 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | Approved with Comments | 2023-12-11 | NO | Overdue |  | 131242-WST02-DR-7000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 14 | AWC | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
163 | 000079 | 02 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604 | A1 | 131242-WST00-DR-C-8000_ST604-A1 | 2023-11-07 | ST604 – Overall SSN area Piling Design | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-21 | Approved with Comments | 2023-12-11 | NO | Overdue |  | 131242-WST00-DR-8000_ST604 | NA | "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 14 | AWC | 2023-11-07 | A1 | 000079 | 2023-08-24, 2023-09-26, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-11 | Overdue | 0 | AWC | AWC
164 | 000080 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0002 | 0 | 131242-WSW41-PC-W-0002-0 | 2023-08-25 | PAYMENT CLAIM NO.2 | Accepted. Please refer to S.O. Correspondence no. 48 dated 29 August 2023. | 2023-09-22 | 2023-08-30 | Approved |  | YES | NA |  | 131242-WSW41-PC-0002 | NA | "Adjustment of Stage Payment" && "PAYMENT CLAIM NO.2" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-08 | 5 | APP | 2023-08-25 | 0 | 000060&&000080 | 2023-08-01, 2023-08-25 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
165 | 000081 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 0 | 131242-WSW41-SP-C-0001-0 | 2023-08-28 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-09-25 | Approved with Comments | 2023-10-13 | YES | Resubmitted |  | 131242-WSW41-SP-0001 | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-17 | 28 | AWC | 2023-10-05 | 1 | 000081 | 2023-08-28, 2023-10-05 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
166 | 000081 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0001 | 1 | 131242-WSW41-SP-C-0001-1 | 2023-10-05 | Concrete Design Mix for Bored Piling Work C40/50 (Alliance) | Rev.1: Approved | 2023-10-25 | 2023-10-18 | Approved |  | YES | NA |  | 131242-WSW41-SP-0001 | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Alliance) " | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-19 | 13 | APP | 2023-10-05 | 1 | 000081 | 2023-08-28, 2023-10-05 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
167 | 000082 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0006 | 0 | 131242-WSW41-MI-IM-0006-0 | 2023-08-28 | BIM Bi-Weekly Meeting Minutes 0006_20230823 | For Information | 2023-09-25 | 2023-09-06 | For Information |  | YES | NA |  | 131242-WSW41-MI-0006 | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-11 | 9 | INF | 2023-11-15 | 0 | 000050&&000068&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
168 | 000083 | 00 | Zora | CSA | NA | 131242 | WSW41 | SK | S | 0001 | 0 | 131242-WSW41-SK-S-0001-0 | 2023-08-28 | Sidewide Pipe Rack GA and Reactions | Not Approved. Please refer to comment sheet for resubmission. | 2023-09-25 | 2023-10-06 | Not Approved | 2023-10-26 | YES | Resubmitted |  | 131242-WSW41-SK-0001 | NA | "Sidewide Pipe Rack GA and Reactions" && "Time Lapse Camera Location" | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-17 | 39 | NAP | 2023-10-23 | 0 | 000083&&000136 | 2023-08-28, 2023-10-23 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
169 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A | 131242-WSW41-DR-S-1000_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-01 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-1000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
170 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A | 131242-WSW41-DR-S-1004_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-1004_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
171 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A | 131242-WSW41-DR-S-1007_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-1007_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
172 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A | 131242-WSW41-DR-S-1008_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-1008_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
173 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A | 131242-WSW41-DR-S-1009_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-1009_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
174 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A | 131242-WSW41-DR-S-1010_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-1010_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
175 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A | 131242-WSW41-DR-S-2000_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-2000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
176 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A | 131242-WSW41-DR-S-2001_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-2001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
177 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A | 131242-WSW41-DR-S-2002_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-2002_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
178 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A | 131242-WSW41-DR-S-3000_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-3000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
179 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A | 131242-WSW41-DR-S-3001_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-3001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
180 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A | 131242-WSW41-DR-S-5000_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-5000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
181 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A | 131242-WSW41-DR-S-5001_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-5001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
182 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A | 131242-WSW41-DR-S-5002_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-5002_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
183 | 000083 | 01 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A | 131242-WSW41-DR-S-8001_ST603-A | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | 131242-WSW41-DR-8001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
184 | 000083 | 01 | Zora | CSA | NA | Site wide PR Reactions for information | NA | NA | NA | 9999 | A |  | 2024-01-13 | ST603 - Site Wide Pipe Rack Details | Rev.1: Not Approved. Please resubmit with the response of the comment sheet. Submit Native Files using BIM Authoring tool as per Specs. | 2024-02-09 | 2024-01-25 | Not Approved | 2024-02-15 | YES | Resubmitted |  | Site wide PR Reactions for information-NA-NA-9999 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 12 | NAP | 2024-01-13 | A | 000083 | 2024-01-13 | 01 | 1 | Not Approved | NAP | 2024-02-14 | Overdue | 0 | NAP | NAP
185 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.1 | 131242-WSW41-DR-S-1000_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-01 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted | Rev 1 : Not Approved. | 131242-WSW41-DR-1000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
186 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A.1 | 131242-WSW41-DR-S-1004_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1004_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
187 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A.1 | 131242-WSW41-DR-S-1007_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1007_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
188 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A.1 | 131242-WSW41-DR-S-1008_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1008_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
189 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A.1 | 131242-WSW41-DR-S-1009_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1009_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
190 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A.1 | 131242-WSW41-DR-S-1010_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1010_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
191 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A.1 | 131242-WSW41-DR-S-2000_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-2000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
192 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A.1 | 131242-WSW41-DR-S-2001_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-2001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
193 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A.1 | 131242-WSW41-DR-S-2002_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-2002_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
194 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A.1 | 131242-WSW41-DR-S-3000_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-3000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
195 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A.1 | 131242-WSW41-DR-S-3001_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-3001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
196 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A.1 | 131242-WSW41-DR-S-5000_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-5000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
197 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A.1 | 131242-WSW41-DR-S-5001_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-5001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
198 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A.1 | 131242-WSW41-DR-S-5002_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-5002_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
199 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST603 | A.1 | 131242-WSW41-DR-S-5003_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-5003_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
200 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 5004_ST603 | A | 131242-WSW41-DR-S-5004_ST603-A | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-5004_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
201 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A.1 | 131242-WSW41-DR-S-8001_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-8001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
202 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST603 | A | 131242-WSW41-DR-S-0300_ST603-A | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-0300_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 52 | NAP | 2024-06-08 | A | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
203 | 000083 | 02 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST603 | A.1 | 131242-WSW41-DR-S-0301_ST603-A.1 | 2024-03-11 | ST603 - Site Wide Pipe Rack Details | Rev.2: Not Approved. Please resubmit with the response of the comment sheet. | 2024-04-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-0301_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 52 | NAP | 2024-06-08 | A.2 | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
204 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | CL | S | 1000_ST603 | 2 | 131242-WSW41-CL-S-1000_ST603-2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue | To clear technical comments first and Heng Peng to clear BIM comments. | 131242-WSW41-CL-1000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-28 | 23 | NAP | 2024-06-08 | 2 | 000083 | 2024-06-08 | 03 | 1 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
205 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST603 | A.2 | 131242-WSW41-DR-S-1000_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-1000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
206 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST603 | A.2 | 131242-WSW41-DR-S-1004_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-1004_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
207 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1007_ST603 | A.2 | 131242-WSW41-DR-S-1007_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-1007_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
208 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1008_ST603 | A.2 | 131242-WSW41-DR-S-1008_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-1008_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
209 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1009_ST603 | A.2 | 131242-WSW41-DR-S-1009_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-1009_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
210 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 1010_ST603 | A.2 | 131242-WSW41-DR-S-1010_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-1010_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
211 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST603 | A.2 | 131242-WSW41-DR-S-2000_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-2000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
212 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST603 | A.1 | 131242-WSW41-DR-S-2001_ST603-A.1 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-2001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
213 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST603 | A.2 | 131242-WSW41-DR-S-2002_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-2002_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
214 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST603 | A.1 | 131242-WSW41-DR-S-3000_ST603-A.1 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-3000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
215 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 3001_ST603 | A.2 | 131242-WSW41-DR-S-3001_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-3001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
216 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST603 | A.1 | 131242-WSW41-DR-S-5000_ST603-A.1 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-5000_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.1 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
217 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST603 | A.2 | 131242-WSW41-DR-S-5001_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-5001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
218 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST603 | A.2 | 131242-WSW41-DR-S-5002_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-5002_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
219 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST603 | A.2 | 131242-WSW41-DR-S-5003_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-5003_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
220 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 5004_ST603 | A.2 | 131242-WSW41-DR-S-5004_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-5004_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
221 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST603 | A.2 | 131242-WSW41-DR-S-8001_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-8001_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-01-13, 2024-03-11, 2024-06-08 | 01, 02, 03 | 3 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
222 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST603 | A | 131242-WSW41-DR-S-0300_ST603-A | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-0300_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
223 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST603 | A.2 | 131242-WSW41-DR-S-0301_ST603-A.2 | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-0301_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-03-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-22 | 23 | NAP | 2024-06-08 | A.2 | 000083 | 2024-03-11, 2024-06-08 | 02, 03 | 2 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
224 | 000083 | 03 | Aaron/HP | CSA | NA | 131242 | WSW41 | DR | S | 0302_ST603 | A | 131242-WSW41-DR-S-0302_ST603-A | 2024-06-08 | ST603 - Site Wide Pipe Rack Details | Rev.3: Not Approved. Please resubmit with the response of the comment sheet. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue |  | 131242-WSW41-DR-0302_ST603 | NA | "ST603 - Site Wide Pipe Rack Details" | 2024-06-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-28 | 23 | NAP | 2024-06-08 | A | 000083 | 2024-06-08 | 03 | 1 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
225 | 000084 | 00 | Zora | CSA | NA | 131242 | WSW41 | VI | S | 0002 | 0 | 131242-WSW41-VI-S-0002-0 | 2023-08-28 | Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd. | Approved | 2023-09-25 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-17 | 28 | APP | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | APP | APP
226 | 000085 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0002 | 0 | 131242-WSW41-SP-C-0002-0 | 2023-08-31 | Concrete Design Mix for ULT Test Pile C50/60 (Alliance) | Approved | 2023-09-28 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-SP-0002 | NA | "Concrete Design Mix for ULT Test Pile C50/60 (Alliance) " | 2023-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-20 | 25 | APP | 2023-08-31 | 0 | 000085 | 2023-08-31 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
227 | 000086 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | CL | Z | 0001 | 0 | 131242-WSW41-CL-Z-0001-0 | 2023-08-31 | ECM Plan and Calculation | Approved | 2023-09-28 | 2023-10-04 | Approved |  | YES | NA |  | 131242-WSW41-CL-0001 | NA | "ECM Plan and Calculation" && "Temporary Utilities for Contractor’s Site Office" | 2023-07-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-14 | 34 | APP | 2023-08-31 | 0 | 000038&&000086 | 2023-07-05, 2023-08-31 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
228 | 000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0001 | 0 | 131242-WSW41-MI-PM-0001-0 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 | For Information |  | YES | NA |  | 131242-WSW41-MI-0001 | NA | "BIM Bi-Weekly Meeting Minutes 0001_20230614" && "BS Meeting Minutes 0001_20230706" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-06-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-09-18 | 2 | INF | 2023-09-04 | 0 | 000037&&000048&&000087 | 2023-06-28, 2023-07-14, 2023-09-04 | 00 | 3 | For Information | INF | 2023-09-26 | Overdue | 0 | INF | INF
229 | 000087 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0002 | 0 | 131242-WSW41-MI-PM-0002-0 | 2023-09-04 | Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718 | For Information | 2023-10-02 | 2023-09-06 | For Information |  | YES | NA |  | 131242-WSW41-MI-0002 | NA | "BIM Bi-Weekly Meeting Minutes 0002_20230628" && "Monthly Progress Meeting Minutes 0001&0002_20230615 & 0718" | 2023-07-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-09-18 | 2 | INF | 2023-09-04 | 0 | 000047&&000087 | 2023-07-13, 2023-09-04 | 00 | 2 | For Information | INF | 2023-09-26 | Overdue | 0 | INF | INF
230 | 000088 | 00 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 0 | 131242-WST02-VI-M-0001-0 | 2023-09-05 | Preliminary design and Vendor Approval for SSN Package | Rev 0: Not approved - Revise and Resubmit | 2023-10-03 | 2023-09-25 | Not Approved | 2023-10-13 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-25 | 20 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
231 | 000088 | 01 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 1 | 131242-WST02-VI-M-0001-1 | 2023-10-05 | Preliminary design and Vendor Approval for SSN Package | Rev 1: Not approved - Revise and Resubmit Document not approved as requested by Contractor. | 2023-10-25 | 2023-10-23 | Not Approved | 2023-11-10 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
232 | 000088 | 02 | Qili | Process | NA | 131242 | WST02 | VI | M | 0001 | 2 | 131242-WST02-VI-M-0001-2 | 2023-10-31 | Preliminary design and Vendor Approval for SSN Package | Rev 2: Approved with Comments, subject to clarification of comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-21 | 2023-11-08 | Approved with Comments | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-14 | 8 | AWC | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | AWC | AWC
233 | 000088 | 03 | Joo kwan | Process | NA | 131242 | WST02 | VI | M | 0001 | 3 | 131242-WST02-VI-M-0001-3 | 2024-02-03 | Preliminary design and Vendor Approval for SSN Package | Rev 3: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-02-23 | 2024-04-29 | Approved with Comments |  | YES | NA | Rev 2: AWC | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-17 | 86 | AWC | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | AWC | AWC
234 | 000089 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0007 | 0 | 131242-WSW41-MI-P-0007-0 | 2023-09-05 | Process & MEICA Meeting Minutes 0007_20230718 | For Information | 2023-10-03 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0007 | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-19 | 195 | INF | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
235 | 000090 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | D | 0001 | 0 | 131242-WSW41-VI-D-0001-0 | 2023-09-07 | Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq) | Approved | 2023-10-05 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-VI-0001 | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-27 | 18 | APP | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
236 | 000091 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | RT | Z | 0002 | 0 | 131242-WSW41-RT-Z-0002-0 | 2023-09-07 | Cable Detection Report | Approved with comments. Please refer to comment sheet for resubmission. | 2023-10-05 | 2023-09-25 | Approved with Comments | 2023-10-13 | YES | Resubmitted |  | 131242-WSW41-RT-0002 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-21 | 18 | AWC | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | For Information | INF |  |  | 0 | AWC | AWC
237 | 000091 | 01 | Eng Bee | PMT | NA | Reply to Comment Sheet_#000091 | NA | NA | NA | 9999 | 0 | Reply to Comment Sheet_#000091----- | 2023-10-06 | Cable Detection Report | Approved | 2023-10-26 | 2023-10-18 | Approved |  | YES | NA |  | Reply to Comment Sheet_#000091-NA-NA-9999 | NA | "Cable Detection Report" | 2023-10-06 | YES | NO | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2023-10-26 | 12 | APP | 2023-10-06 | 0 | 000091 | 2023-10-06 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
238 | 000092 | 00 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 0 | 131242-WSW41-SP-M-8001-0 | 2023-09-08 | Piping Material Specification | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-10-06 | 2023-09-25 | Approved with Comments | 2023-10-13 | YES | Resubmitted |  | 131242-WSW41-SP-8001 | NA | "Piping Material Specification" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-28 | 17 | AWC | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
239 | 000092 | 01 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 1 | 131242-WSW41-SP-M-8001-1 | 2024-02-22 | Piping Material Specification | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-13 | 2024-04-17 | Approved with Comments | 2024-05-08 | YES | Resubmitted | Rev 0: AWC | 131242-WSW41-SP-8001 | NA | "Piping Material Specification" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-07 | 55 | AWC | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
240 | 000092 | 02 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 2 | 131242-WSW41-SP-M-8001-2 | 2024-08-07 | Piping Material Specification | Rev 2: Approved | 2024-08-28 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-SP-8001 | NA | "Piping Material Specification" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 26 | APP | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
241 | 000092 | 03 | Liying | Mech | NA | 131242 | WSW41 | SP | M | 8001 | 3 | 131242-WSW41-SP-M-8001-3 | 2024-12-13 | Piping Material Specification | Rev 3: Approved | 2025-01-03 | 2025-01-20 | Approved |  | YES | NA |  | 131242-WSW41-SP-8001 | NA | "Piping Material Specification" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-27 | 38 | APP | 2024-12-13 | 3 | 000092 | 2023-09-08, 2024-02-22, 2024-08-07, 2024-12-13 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
242 | 000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | 0 | 131242-WSW41-DR-P-6000-0 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | Approved with Comments | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-6000 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-28 | 80 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
243 | 000093 | 00 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | 0 | 131242-WSW41-DR-P-6001-0 | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | Approved with Comments | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-6001 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-28 | 80 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
244 | 000093 | 00 | Qili | Process | NA | Pipeline - All_Data Report | NA | NA | NA | 9999 | 0 | Pipeline - All_Data Report----- | 2023-09-08 | Piperack P&IDs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-06 | 2023-11-27 | Approved with Comments | 2023-12-15 | YES | Resubmitted |  | Pipeline - All_Data Report-NA-NA-9999 | NA | "Piperack P&IDs" | 2023-09-08 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-09-28 | 80 | AWC | 2023-09-08 | 0 | 000093 | 2023-09-08 | 00 | 1 | Approved with Comments | AWC | 2023-12-15 | Overdue | 0 | AWC | AWC
245 | 000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6000 | B | 131242-WSW41-DR-P-6000-B | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted | Rev 0: AWC | 131242-WSW41-DR-6000 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-19 | 51 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
246 | 000093 | 01 | Joo kwan | Process | NA | 131242 | WSW41 | DR | P | 6001 | B | 131242-WSW41-DR-P-6001-B | 2024-03-05 | Piperack P&IDs | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-25 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSW41-DR-6001 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-19 | 51 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
247 | 000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | C | 131242-WSW41-DR-P-6000-C | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSW41-DR-6000 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 70 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
248 | 000093 | 02 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | C | 131242-WSW41-DR-P-6001-C | 2024-08-20 | Piperack P&IDs | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSW41-DR-6001 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 70 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
249 | 000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | D | 131242-WSW41-DR-P-6000-D | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted | comments received on 14 Feb | 131242-WSW41-DR-6000 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 41 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
250 | 000093 | 03 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | D | 131242-WSW41-DR-P-6001-D | 2024-12-06 | Piperack P&IDs | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSW41-DR-6001 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 41 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
251 | 000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-P-6000-E | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | Approved with Comments | 2025-05-20 | YES | Resubmitted |  | 131242-WSW41-DR-6000 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 47 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
252 | 000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | E | 131242-WSW41-DR-P-6001-E | 2025-03-14 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-04-30 | Approved with Comments | 2025-05-20 | YES | Resubmitted |  | 131242-WSW41-DR-6001 | NA | "Piperack P&IDs" | 2023-09-08 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 47 | AWC | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
253 | 000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6000 | E | 131242-WSW41-DR-P-6000-E | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 | Awaiting S.O.'s response |  |  | Resubmitted |  | 131242-WSW41-DR-6000 | NA | "Piperack P&IDs" | 2023-09-08 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-03-10 |  | PEN | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC | 2025-05-20 | Overdue | 0 | PEN | PEN
254 | 000093 | 04 | Qili | Process | NA | 131242 | WSW41 | DR | P | 6001 | E | 131242-WSW41-DR-P-6001-E | 2026-02-24 | Piperack P&IDs | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-16 | 2025-04-30 | Awaiting S.O.'s response |  |  | Resubmitted |  | 131242-WSW41-DR-6001 | NA | "Piperack P&IDs" | 2023-09-08 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-03-10 |  | PEN | 2026-02-24 | E | 000093 | 2023-09-08, 2024-03-05, 2024-08-20, 2024-12-06, 2025-03-14, 2026-02-24 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC | 2025-05-20 | Overdue | 0 | PEN | PEN
255 | 000094 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0002 | 0 | 131242-WSW41-CD-IM-0002-0 | 2023-09-08 | Submission Of BIM Coordination VCM Model (Aug – 2023) | For Information | 2023-10-06 | 2023-09-21 | For Information |  | YES | NA |  | 131242-WSW41-CD-0002 | NA | "Submission Of BIM Coordination VCM Model (Aug – 2023)" | 2023-09-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-09-28 | 13 | INF | 2023-09-08 | 0 | 000094 | 2023-09-08 | 00 | 1 | For Information | INF | 2023-10-11 | Overdue | 0 | INF | INF
256 | 000095 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0007 | 0 | 131242-WSW41-MI-IM-0007-0 | 2023-09-11 | BIM Bi-Weekly Meeting Minutes 0007_20230906 | For Information | 2023-10-09 | 2023-10-03 | For Information |  | YES | NA |  | 131242-WSW41-MI-0007 | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-09-25 | 22 | INF | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
257 | 000096 | 00 | Darren | Piping/ BS | NA | 131242 | WST02 | CL | B | 0002 | 0 | 131242-WST02-CL-B-0002-0 | 2023-09-12 | Engineering Calculation Report For Fire Hydrant Pipe | Rev 0: Rejected as requested by contractor. | 2023-10-10 | 2023-11-10 | Rejected |  | YES | NA | Kindly refer to Submittal 000193 | 131242-WST02-CL-0002 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-02 | 59 | REJ | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | Approved | APP |  |  | 0 | REJ | REJ
258 | 000097 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0003 | 0 | 131242-WST02-CL-B-0003-0 | 2023-09-12 | Engineering Calculation Report For Potable Water Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-10-10 | 2023-11-10 | Not Approved | 2023-12-01 | YES | Resubmitted |  | 131242-WST02-CL-0003 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-02 | 59 | NAP | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | Approved | APP |  |  | 0 | NAP | NAP
259 | 000097 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 1 | 131242-WST02-CL-BP-8000-1 | 2024-05-30 | Engineering Calculation Report For Potable Water Pipe | Rev 1: Not approved - Revise and Resubmit | 2024-06-20 | 2024-07-09 | Not Approved | 2024-07-29 | YES | Resubmitted | To check with C2D for resubmission | 131242-WST02-CL-8000 | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-19 | 40 | NAP | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
260 | 000097 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 2 | 131242-WST02-CL-BP-8000-2 | 2024-10-17 | Engineering Calculation Report For Potable Water Pipe | Rev 2: Not approved - Revise and Resubmit | 2024-11-07 | 2024-11-25 | Not Approved | 2024-12-13 | YES | Resubmitted |  | 131242-WST02-CL-8000 | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 39 | NAP | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
261 | 000097 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BP | 8000 | 3 | 131242-WST02-CL-BP-8000-3 | 2025-02-18 | Engineering Calculation Report For Potable Water Pipe | Rev3: Approved | 2025-03-10 | 2025-03-25 | Approved |  | YES | NA |  | 131242-WST02-CL-8000 | NA | "Engineering Calculation Report For Potable Water Pipe" && "Fan Static Load Calculation (SSN Electrical Building)" && "Hydraulic Calculation (HOSEREEL)" | 2024-05-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 35 | APP | 2025-02-27 | 0 | 000097&&000918&&001076 | 2024-05-30, 2024-10-17, 2024-12-18, 2025-02-18, 2025-02-19, 2025-02-27 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
262 | 000098 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 0 | 131242-WSW41-RT-PM-0004-0 | 2023-09-13 | C4B Monthly Progress Report Number No.04 (08/23) | Rev. 0 - Not Approved need to re-submit (see attached comment sheet) | 2023-10-11 | 2023-09-20 | Not Approved | 2023-10-10 | YES | Resubmitted |  | 131242-WSW41-RT-0004 | NA | "C4B Monthly Progress Report Number No.04 (08/23)" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 7 | NAP | 2023-10-04 | 1 | 000098 | 2023-09-13, 2023-10-04 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
263 | 000098 | 01 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0004 | 1 | 131242-WSW41-RT-PM-0004-1 | 2023-10-04 | C4B Monthly Progress Report Number No.04 (08/23) | Approved | 2023-10-24 | 2023-10-06 | Approved |  | YES | NA |  | 131242-WSW41-RT-0004 | NA | "C4B Monthly Progress Report Number No.04 (08/23)" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-18 | 2 | APP | 2023-10-04 | 1 | 000098 | 2023-09-13, 2023-10-04 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
264 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | 0 | 131242-WSW41-DR-M-5002-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5002 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2026-01-19 | E | 000099&&001963 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
265 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5003 | 0 | 131242-WSW41-DR-M-5003-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5003 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2026-01-19 | E | 000099&&001963 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
266 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5004 | 0 | 131242-WSW41-DR-M-5004-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5004 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
267 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5005 | 0 | 131242-WSW41-DR-M-5005-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5005 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
268 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5006 | 0 | 131242-WSW41-DR-M-5006-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5006 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
269 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5007 | 0 | 131242-WSW41-DR-M-5007-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5007 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
270 | 000099 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5008 | 0 | 131242-WSW41-DR-M-5008-0 | 2023-09-13 | C4B Sitewide Piping GA Drawing | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-11 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-DR-5008 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-03 | 75 | NAP | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
271 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5001 | A1 | 131242-WSW41-DR-M-5001-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-01 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue | Under M2 submission (Shall be Submitted After M3 WT) | 131242-WSW41-DR-5001 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 52 | AWC | 2026-01-19 | E | 000099&&001963 | 2024-03-11, 2026-01-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
272 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5002 | A1 | 131242-WSW41-DR-M-5002-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5002 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2026-01-19 | E | 000099&&001963 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
273 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5003 | A1 | 131242-WSW41-DR-M-5003-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5003 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2023-09-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2026-01-19 | E | 000099&&001963 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
274 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5004 | A1 | 131242-WSW41-DR-M-5004-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5004 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
275 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5005 | A1 | 131242-WSW41-DR-M-5005-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5005 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
276 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5006 | A1 | 131242-WSW41-DR-M-5006-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5006 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
277 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5007 | A1 | 131242-WSW41-DR-M-5007-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5007 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
278 | 000099 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5008 | A1 | 131242-WSW41-DR-M-5008-A1 | 2024-03-11 | C4B Sitewide Piping GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-DR-5008 | NA | "C4B Sitewide Piping GA Drawing" | 2023-09-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 52 | AWC | 2024-03-11 | A1 | 000099 | 2023-09-13, 2024-03-11 | 00, 01 | 2 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
279 | 000100 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0001 | 0 | 131242-WSD11-PO-M-0001-0 | 2023-09-14 | Unpriced PO for THP Package (Cambi) | For Information | 2023-10-12 | 2023-11-27 | For Information |  | YES | NA |  | 131242-WSD11-PO-0001 | NA | "Unpriced PO for THP Package (Cambi)" && "Unpriced PO for Transformer (Hitachi)" | 2023-09-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-04 | 74 | INF | 2024-03-20 | 1 | 000100&&000326 | 2023-09-14, 2024-02-26, 2024-03-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
280 | 000101 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0005 | 0 | 131242-WSW41-PP-HS-0005-0 | 2023-09-14 | Heat Stress Prevention Program | Approved | 2023-10-12 | 2023-09-25 | Approved |  | YES | NA |  | 131242-WSW41-PP-0005 | NA | "Heat Stress Prevention Program" | 2023-09-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-04 | 11 | APP | 2023-09-14 | 0 | 000101 | 2023-09-14 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
281 | 000102 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 0 | 131242-WSW41-VI-M-0011-0 | 2023-09-18 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | Approved with Comments | 2023-12-11 | YES | Resubmitted |  | 131242-WSW41-VI-0011 | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-08 | 64 | AWC | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | AWC | AWC
282 | 000102 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 1 | 131242-WSW41-VI-M-0011-1 | 2024-01-04 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-24 | 2024-02-15 | Approved with Comments | 2024-03-06 | YES | Resubmitted | Drawings are ready to re-submit. Pending update data sheet from INGERSOLL-RAND. | 131242-WSW41-VI-0011 | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-18 | 42 | AWC | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | AWC | AWC
283 | 000102 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0011 | 2 | 131242-WSW41-VI-M-0011-2 | 2024-06-07 | Vendor Approval of Air Compressor System (INGERSOLL-RAND) | Rev 2: Approved | 2024-06-28 | 2024-07-12 | Approved |  | YES | NA | R1_AWC | 131242-WSW41-VI-0011 | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-21 | 35 | APP | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | APP | APP
284 | 000103 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 0 | 131242-WSW41-VI-M-0004-0 | 2023-09-18 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-10-16 | 2023-11-21 | Approved with Comments | 2023-12-11 | YES | Resubmitted |  | 131242-WSW41-VI-0004 | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-08 | 64 | AWC | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | Approved | APP |  |  | 0 | AWC | AWC
285 | 000103 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0004 | 1 | 131242-WSW41-VI-M-0004-1 | 2025-05-30 | Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd) | Rev1: Approved | 2025-06-19 | 2025-08-01 | Approved |  | YES | NA |  | 131242-WSW41-VI-0004 | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-13 | 63 | APP | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | Approved | APP |  |  | 0 | APP | APP
286 | 000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0008 | 0 | 131242-WSW41-MI-P-0008-0 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0008 | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-03 | 181 | INF | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
287 | 000104 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0009 | 0 | 131242-WSW41-MI-P-0009-0 | 2023-09-19 | Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914 | For Information | 2023-10-17 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0009_20240220" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-03 | 181 | INF | 2024-03-01 | 0 | 000063&&000104&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
288 | 000105 | 00 | Shena | PMT | NA | 131242 | WSW41 | LT | PM | 0012 | 0 | 131242-WSW41-LT-PM-0012-0 | 2023-09-19 | CV of Team Member (WSHO) | Approved | 2023-10-17 | 2023-10-18 | Approved |  | YES | NA |  | 131242-WSW41-LT-0012 | NA | "CV of Team Member (WSHO)" | 2023-09-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-09 | 29 | APP | 2023-09-19 | 0 | 000105 | 2023-09-19 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
289 | 000106 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0004 | 0 | 131242-WSW41-PS-PM-0004-0 | 2023-09-21 | Monthly Progress Presentation No. 04 (0823) | For Information | 2023-10-19 | 2023-09-25 | For Information |  | YES | NA |  | 131242-WSW41-PS-0004 | NA | "Incentive / Disincentive Audit Scheme for November 2023" && "Monthly Progress Presentation No. 04 (0823)" | 2023-09-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-11 | 4 | INF | 2024-03-12 | 0 | 000106&&000354 | 2023-09-21, 2024-03-12 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
290 | 000107 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 0 | 131242-WSW41-VI-M-0006-0 | 2023-09-25 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Approved with Comments. To revise and resubmit. Refer to comments file. | 2023-10-23 | 2023-10-16 | Approved with Comments | 2023-11-03 | YES | Resubmitted | In Progress | 131242-WSW41-VI-0006 | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-09 | 21 | AWC | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
291 | 000107 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0006 | 1 | 131242-WSW41-VI-M-0006-1 | 2024-07-31 | Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH) | Rev 1: Approved | 2024-08-21 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-VI-0006 | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 33 | APP | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
292 | 000108 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | Superceded | 131242-WSW41-CT-W-0001-Superceded | 2023-09-27 | On-Demand Bond for THP System | Rev(0): Rejected as requested by Contractor. Note Contractor need to attach a transmittal signed by PUB to the said submittal. | 2023-10-25 | 2023-10-02 | Rejected | 2023-10-20 | YES | Resubmitted |  | 131242-WSW41-CT-0001 | NA | "On-Demand Bond for THP System" | 2023-09-27 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-17 | 5 | REJ | 2023-10-03 | 0 | 000108 | 2023-09-27, 2023-10-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | REJ | REJ
293 | 000108 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0001 | 0 | 131242-WSW41-CT-W-0001-0 | 2023-10-03 | On-Demand Bond for THP System | Approved. | 2023-10-23 | 2023-10-09 | Approved |  | YES | NA |  | 131242-WSW41-CT-0001 | NA | "On-Demand Bond for THP System" | 2023-09-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-17 | 6 | APP | 2023-10-03 | 0 | 000108 | 2023-09-27, 2023-10-03 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
294 | 000109 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0010 | 0 | 131242-WSW41-MI-C-0010-0 | 2023-09-27 | CSA Meeting Minutes 0010_20230802 | For Information | 2023-10-25 | 2023-10-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" | 2023-09-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-17 | 21 | INF | 2024-04-04 | 0 | 000109&&000126&&000152&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
295 | 000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | 0 | 131242-WST00-DR-S-0001_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue | MEICA layout released on 29/02/2024. Updating as per latest Layout changes of SSN-SH-002 area with Pump pit. Tenwit updating In-Progress. | 131242-WST00-DR-0001_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
296 | 000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0002_ST606 | 0 | 131242-WST00-DR-S-0002_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST00-DR-0002_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
297 | 000110 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0003_ST606 | 0 | 131242-WST00-DR-S-0003_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST00-DR-0003_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
298 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606 | 0 | 131242-WST02-DR-S-1006_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-1006_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
299 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606 | 0 | 131242-WST02-DR-S-1007_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-1007_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
300 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606 | 0 | 131242-WST02-DR-S-1008_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-1008_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
301 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST606 | 0 | 131242-WST02-DR-S-1013_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-1013_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
302 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606 | 0 | 131242-WST02-DR-S-3000_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-3000_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
303 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3001_ST606 | 0 | 131242-WST02-DR-S-3001_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-3001_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
304 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5000_ST606 | 0 | 131242-WST02-DR-S-5000_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-5000_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
305 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606 | 0 | 131242-WST02-DR-S-5001_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-5001_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
306 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606 | 0 | 131242-WST02-DR-S-5002_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-5002_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
307 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST606 | 0 | 131242-WST02-DR-S-5005_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-5005_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
308 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606 | 0 | 131242-WST02-DR-S-7000_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-7000_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
309 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606 | 0 | 131242-WST02-DR-S-7001_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-7001_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
310 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606 | 0 | 131242-WST02-DR-S-7002_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-7002_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
311 | 000110 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST606 | 0 | 131242-WST02-DR-S-8001_ST606-0 | 2023-09-29 | ST606 : SSN Overall Sub-Structure Drawings | Rev.0: Not Approved. Please refer comment sheet for resubmission. | 2023-10-27 | 2023-10-18 | Not Approved | 2023-11-07 | NO | Overdue |  | 131242-WST02-DR-8001_ST606 | NA | "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 19 | NAP | 2023-09-29 | 0 | 000110 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-07 | Overdue | 0 | NAP | NAP
312 | 000111 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0003 | 0 | 131242-WSW41-PC-W-0003-0 | 2023-09-29 | PAYMENT CLAIM NO.3 | Approved | 2023-10-27 | 2023-10-23 | Approved |  | YES | NA |  | 131242-WSW41-PC-0003 | NA | "PAYMENT CLAIM NO.3" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-19 | 24 | APP | 2023-09-29 | 0 | 000111 | 2023-09-29 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
313 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-1_URA | 0 | 131242-WST02-DR-A-3D-1_URA-0 | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-3D-1_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-09-29 | 0 | 000112 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
314 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3D-2_URA | 0 | 131242-WST02-DR-A-3D-2_URA-0 | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-3D-2_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-09-29 | 0 | 000112 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
315 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A | 131242-WST02-DR-A-1000_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1000_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
316 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A | 131242-WST02-DR-A-1001_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
317 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A | 131242-WST02-DR-A-1002_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1002_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
318 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A | 131242-WST02-DR-A-1003_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1003_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
319 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A | 131242-WST02-DR-A-1004_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1004_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
320 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A | 131242-WST02-DR-A-1006_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1006_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
321 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A | 131242-WST02-DR-A-1009_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-1009_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
322 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A | 131242-WST02-DR-A-2000_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-2000_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
323 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A | 131242-WST02-DR-A-2001_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-2001_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
324 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A | 131242-WST02-DR-A-2002_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-2002_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
325 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A | 131242-WST02-DR-A-2003_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-2003_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
326 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-2007_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
327 | 000112 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA-A | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 131242-WST02-DR-3000_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-11-07 | A | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
328 | 000112 | 00 | Zora | CSA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf | NA | NA | NA | 9999 | A | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf----- | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.pdf-NA-NA-9999 | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-09-29 | A | 000112 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
329 | 000112 | 00 | Zora | CSA | NA | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx | NA | NA | NA | 9999 | A | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx----- | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | 2023 09 25_URA Set DDC Commented 20230830_Reply 2023 09 25.xlsx-NA-NA-9999 | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-09-29 | A | 000112 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
330 | 000112 | 00 | Zora | CSA | NA | GFA DWG Supporting Docs | NA | NA | NA | 9999 | A | GFA DWG Supporting Docs----- | 2023-09-29 | SSN URA Submission | Not Approved. Please refer to comment sheet for resubmission. | 2023-10-27 | 2023-10-17 | Not Approved | 2023-11-06 | YES | Resubmitted |  | GFA DWG Supporting Docs-NA-NA-9999 | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 18 | NAP | 2023-09-29 | A | 000112 | 2023-09-29 | 00 | 1 | Not Approved | NAP | 2023-11-06 | Overdue | 0 | NAP | NAP
331 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-A-1000_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-06 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1000_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
332 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A1 | 131242-WST02-DR-A-1001_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1001_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
333 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A1 | 131242-WST02-DR-A-1002_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1002_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
334 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A1 | 131242-WST02-DR-A-1003_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1003_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
335 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A1 | 131242-WST02-DR-A-1004_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1004_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
336 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A1 | 131242-WST02-DR-A-1006_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1006_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
337 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A1 | 131242-WST02-DR-A-1009_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-1009_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
338 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A1 | 131242-WST02-DR-A-2000_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-2000_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
339 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A1 | 131242-WST02-DR-A-2001_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-2001_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
340 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A1 | 131242-WST02-DR-A-2002_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-2002_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
341 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A1 | 131242-WST02-DR-A-2003_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-2003_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
342 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA-A | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-2007_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
343 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA-A | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-3000_URA | NA | "SSN URA Submission" | 2023-09-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-31 | 15 | AWC | 2023-11-07 | A | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
344 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 9000_URA | A1 | 131242-WST02-DR-A-9000_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-9000_URA | NA | "SSN URA Submission" | 2023-10-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-10-17, 2023-11-07 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
345 | 000112 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 9001_URA | A1 | 131242-WST02-DR-A-9001_URA-A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | 131242-WST02-DR-9001_URA | NA | "SSN URA Submission" | 2023-10-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 15 | AWC | 2023-11-07 | A1 | 000112 | 2023-10-17, 2023-11-07 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
346 | 000112 | 01 | Zora | CSA | NA | S000112.0_Reply_2023 10 17 | NA | NA | NA | 9999 | A1 | S000112.0_Reply_2023 10 17-----A1 | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | S000112.0_Reply_2023 10 17-NA-NA-9999 | NA | "SSN URA Submission" | 2023-10-17 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 15 | AWC | 2023-10-17 | A1 | 000112 | 2023-10-17 | 01 | 1 | Approved with Comments | AWC | 2023-11-21 | Overdue | 0 | AWC | AWC
347 | 000112 | 01 | Zora | CSA | NA | Supporting Docs | NA | NA | NA | 9999 | A1 | Supporting Docs----- | 2023-10-17 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | YES | Resubmitted |  | Supporting Docs-NA-NA-9999 | NA | "SSN URA Submission" | 2023-10-17 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 15 | AWC | 2023-10-17 | A1 | 000112 | 2023-10-17 | 01 | 1 | Approved with Comments | AWC | 2023-11-21 | Overdue | 0 | AWC | AWC
348 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1000_URA | A1 | 131242-WST02-DR-A-1000_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-28 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue | Tenwit to modify the annotation and then Heng Peng to clear BIM comments. Pending BIM updates | 131242-WST02-DR-1000_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
349 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1001_URA | A1 | 131242-WST02-DR-A-1001_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1001_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
350 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1002_URA | A1 | 131242-WST02-DR-A-1002_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1002_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
351 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1003_URA | A1 | 131242-WST02-DR-A-1003_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1003_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
352 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1004_URA | A1 | 131242-WST02-DR-A-1004_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1004_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
353 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1006_URA | A1 | 131242-WST02-DR-A-1006_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1006_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
354 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 1009_URA | A1 | 131242-WST02-DR-A-1009_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1009_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
355 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2000_URA | A1 | 131242-WST02-DR-A-2000_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-2000_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
356 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2001_URA | A1 | 131242-WST02-DR-A-2001_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-2001_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
357 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2002_URA | A1 | 131242-WST02-DR-A-2002_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-2002_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
358 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2003_URA | A1 | 131242-WST02-DR-A-2003_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-2003_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
359 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 2007_URA | A | 131242-WST02-DR-A-2007_URA-A | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-2007_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
360 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 3000_URA | A | 131242-WST02-DR-A-3000_URA-A | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-3000_URA | NA | "SSN URA Submission" | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A | 000112 | 2023-09-29, 2023-10-17, 2023-11-07 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
361 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 9000_URA | A1 | 131242-WST02-DR-A-9000_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-9000_URA | NA | "SSN URA Submission" | 2023-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-10-17, 2023-11-07 | 01, 02 | 2 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
362 | 000112 | 02 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | A | 9001_URA | A1 | 131242-WST02-DR-A-9001_URA-A1 | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-9001_URA | NA | "SSN URA Submission" | 2023-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-21 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-10-17, 2023-11-07 | 01, 02 | 2 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
363 | 000112 | 02 | Zora/ HP | CSA | NA | S000112.1_Reply_2023 10 17 | NA | NA | NA | 9999 | A1 | S000112.1_Reply_2023 10 17----- | 2023-11-07 | SSN URA Submission | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-12-06 | 2023-11-23 | Approved with Comments | 2023-12-13 | NO | Overdue |  | S000112.1_Reply_2023 10 17-NA-NA-9999 | NA | "SSN URA Submission" | 2023-11-07 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-27 | 16 | AWC | 2023-11-07 | A1 | 000112 | 2023-11-07 | 02 | 1 | Approved with Comments | AWC | 2023-12-13 | Overdue | 0 | AWC | AWC
364 | 000113 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | E | 0001 | 0 | 131242-WSW41-MS-E-0001-0 | 2023-10-04 | MSRA, SWP for Soil Resistivity Test | Approved with Comments | 2023-11-01 | 2023-10-13 | Approved with Comments | 2023-11-02 | NO | Overdue |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-24 | 9 | AWC | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | AWC | AWC
365 | 000114 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0008 | 0 | 131242-WSW41-MI-IM-0008-0 | 2023-10-05 | BIM Bi-Weekly Meeting Minutes 0008_20230920 | For Information | 2023-11-02 | 2023-10-16 | For Information |  | YES | NA |  | 131242-WSW41-MI-0008 | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-19 | 11 | INF | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
366 | 000115 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 0 | 131242-WSW41-PP-PC-0002-0 | 2023-10-05 | Project Control Plan | Rev. 0 - Approved with comments, need to re-submit (refer comment sheet) | 2023-11-02 | 2023-10-27 | Approved with Comments | 2023-11-17 | YES | Resubmitted |  | 131242-WSW41-PP-0002 | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-19 | 22 | AWC | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
367 | 000115 | 01 | Stanley | PCM | NA | 131242 | WSW41 | PP | PC | 0002 | 1 | 131242-WSW41-PP-PC-0002-1 | 2023-11-10 | Project Control Plan | Rev. 1 - Approved. | 2023-12-01 | 2023-11-15 | Approved |  | YES | NA |  | 131242-WSW41-PP-0002 | NA | "C4B Manpower Deployment Plan" && "Project Accident Statistic Board and BCA Board" && "Project Control Plan" | 2023-07-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-24 | 5 | APP | 2023-11-10 | 1 | 000035&&000049&&000115 | 2023-07-14, 2023-10-05, 2023-10-13, 2023-11-10 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
368 | 000116 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0002 | 0 | 131242-WSW41-CN-M-0002-0 | 2023-10-06 | Proposed change of Manufacturer for SSN Aeration blowers | Rejected as CES requested as No RFC is needed according to the discussion with S.O. | 2023-11-03 | 2023-10-25 | Rejected | 2023-11-15 | YES | Resubmitted |  | 131242-WSW41-CN-0002 | NA | "Proposed change of Manufacturer for SSN Aeration blowers" && "Request for Change of Cast-In Anchor Bolts material for Pipe Bridges and Pipe Racks" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-26 | 19 | REJ | 2025-01-13 | 0 | 000116&&000973 | 2023-10-06, 2025-01-13 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
369 | 000117 | 00 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 0 | 131242-WSW41-CN-M-0001-0 | 2023-10-06 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Rev 0: Not approved - Revise and Resubmit | 2023-11-03 | 2023-11-28 | Not Approved | 2023-12-18 | YES | Resubmitted |  | 131242-WSW41-CN-0001 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-20 | 53 | NAP | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | Rejected | REJ |  |  | 0 | NAP | NAP
370 | 000117 | 01 | Qili | Process | NA | 131242 | WSW41 | CN | M | 0001 | 1 | 131242-WSW41-CN-M-0001-1 | 2023-12-12 | Proposed change of Manufacturer for SSN Discharge Transfer Pumps | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-03 | 2024-01-29 | Approved with Comments |  | YES | NA |  | 131242-WSW41-CN-0001 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-26 | 48 | AWC | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | Rejected | REJ |  |  | 0 | AWC | AWC
371 | 000118 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 0 | 131242-WSW41-MS-C-0004-0 | 2023-10-06 | MSRA, SWP for Bored Piling Work | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-18 | Approved with Comments | 2023-11-07 | YES | Resubmitted |  | 131242-WSW41-MS-0004 | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-26 | 12 | AWC | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
372 | 000118 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0004 | 1 | 131242-WSW41-MS-C-0004-1 | 2023-11-01 | MSRA, SWP for Bored Piling Work | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-22 | 2023-12-01 | Approved with Comments | 2023-12-21 | NO | Overdue |  | 131242-WSW41-MS-0004 | NA | "MSRA and SWP for Floor Screeding and Tiles Laying " && "MSRA and SWP for Installation of Manway" && "MSRA, SWP for Bored Piling Work" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-15 | 30 | AWC | 2025-04-03 | 0 | 000118&&000815&&001198 | 2023-10-06, 2023-11-01, 2024-11-15, 2025-04-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
373 | 000119 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0005 | 0 | 131242-WSW41-MS-C-0005-0 | 2023-10-06 | MSRA, SWP for Site Set-Up & Associated Works (Seong) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-03 | 2023-10-19 | Approved with Comments | 2023-11-08 | NO | Overdue |  | 131242-WSW41-MS-0005 | NA | "MSRA and SWP for Delivery of 2000kVA Transformer " && "MSRA for Waterproofing Works" && "MSRA, SWP for Site Set-Up & Associated Works (Seong)" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-26 | 13 | AWC | 2025-03-24 | 0 | 000119&&000828&&001156 | 2023-10-06, 2024-11-21, 2024-12-11, 2025-03-24 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
374 | 000120 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-IM-0003-0 | 2023-10-06 | Milestone 1.1 (Sidewide piperack) | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-11-03 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSW41-CD-0003 | NA | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | 2023-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-26 | 174 | AWC | 2023-10-10 | 0 | 000120&&000121 | 2023-10-06, 2023-10-10 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
375 | 000120 | 01 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 0 | 131242-WSW41-CD-IM-0028-0 | 2024-05-27 | Milestone 1.2 Sitewide Pipe Rack | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | Not Approved | 2024-06-25 | YES | Resubmitted |  | 131242-WSW41-CD-0028 | NA | "Milestone 1.2 Sitewide Pipe Rack" | 2024-05-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-16 | 8 | NAP | 2024-06-05 | 1 | 000120 | 2024-05-27, 2024-06-05 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
376 | 000120 | 02 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0028 | 1 | 131242-WSW41-CD-IM-0028-1 | 2024-06-05 | Milestone 1.2 Sitewide Pipe Rack | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSW41-CD-0028 | NA | "Milestone 1.2 Sitewide Pipe Rack" | 2024-05-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-19 | 30 | AWC | 2024-06-05 | 1 | 000120 | 2024-05-27, 2024-06-05 | 01, 02 | 2 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
377 | 000120 | 03 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042-0 | 2024-08-24 | Milestone 2 Sitewide Pipe Rack | Rev3: Not Approved, as requested by contractor. | 2024-09-12 | 2024-10-01 | Rejected | 2024-10-21 | YES | Resubmitted |  | 131242-WSW41-CD-0042 | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-13 | 38 | REJ | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
378 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042-0 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-CD-0042 | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | NAP | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
379 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-EK-1000-B | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | NAP | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
380 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 3000 | B | 131242-WSW41-DR-EK-3000-B | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | NAP | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
381 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 1000 | A.2 | 131242-WSW41-DR-M-1000-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | NAP | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
382 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3000 | A.2 | 131242-WSW41-DR-M-3000-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | NAP | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
383 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3001 | A.2 | 131242-WSW41-DR-M-3001-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3001 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
384 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3002 | A.2 | 131242-WSW41-DR-M-3002-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3002 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
385 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3003 | A.2 | 131242-WSW41-DR-M-3003-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3003 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
386 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3004 | A.2 | 131242-WSW41-DR-M-3004-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3004 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
387 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3005 | A.2 | 131242-WSW41-DR-M-3005-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-3005 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
388 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4000 | A.2 | 131242-WSW41-DR-M-4000-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-4000 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
389 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4001 | A.2 | 131242-WSW41-DR-M-4001-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-4001 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
390 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4002 | A.2 | 131242-WSW41-DR-M-4002-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-4002 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
391 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4003 | A.2 | 131242-WSW41-DR-M-4003-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-4003 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
392 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4004 | A.2 | 131242-WSW41-DR-M-4004-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-4004 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
393 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4005 | A.2 | 131242-WSW41-DR-M-4005-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-4005 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
394 | 000120 | 04 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 8000 | A.2 | 131242-WSW41-DR-M-8000-A.2 | 2024-10-05 | Milestone 2 Sitewide Pipe Rack | Rev 4: Not approved - Revise and Resubmit Refer attached comment sheet. 2D Cutsheets for EICA is not provided. | 2024-10-24 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSW41-DR-8000 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | NAP | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
395 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 0 | 131242-WSW41-CD-IM-0042-0 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-CD-0042 | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
396 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 1000 | A.2 | 131242-WSW41-DR-EK-1000-A.2 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
397 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | EK | 3000 | A.2 | 131242-WSW41-DR-EK-3000-A.2 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
398 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 1000 | A.3 | 131242-WSW41-DR-M-1000-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
399 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3000 | A.3 | 131242-WSW41-DR-M-3000-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
400 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3001 | A.3 | 131242-WSW41-DR-M-3001-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3001 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
401 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3002 | A.3 | 131242-WSW41-DR-M-3002-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3002 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
402 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3003 | A.3 | 131242-WSW41-DR-M-3003-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3003 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
403 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3004 | A.3 | 131242-WSW41-DR-M-3004-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3004 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
404 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 3005 | A.3 | 131242-WSW41-DR-M-3005-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-3005 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-04-07 | A | 000120&&001206 | 2024-10-05, 2025-02-26, 2025-04-07 | 00, 04, 05 | 3 | Rejected | REJ |  |  | 0 | AWC | AWC
405 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4000 | A.3 | 131242-WSW41-DR-M-4000-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-4000 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
406 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4001 | A.3 | 131242-WSW41-DR-M-4001-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-4001 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
407 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4002 | A.3 | 131242-WSW41-DR-M-4002-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-4002 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
408 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4003 | A.3 | 131242-WSW41-DR-M-4003-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-4003 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
409 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4004 | A.3 | 131242-WSW41-DR-M-4004-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-4004 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
410 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 4005 | A.3 | 131242-WSW41-DR-M-4005-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-4005 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
411 | 000120 | 05 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | M | 8000 | A.3 | 131242-WSW41-DR-M-8000-A.3 | 2025-02-26 | Milestone 2 Sitewide Pipe Rack | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-DR-8000 | NA | "Milestone 2 Sitewide Pipe Rack" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-02-26 | A.3 | 000120 | 2024-10-05, 2025-02-26 | 04, 05 | 2 | Approved with Comments | AWC | 2025-07-22 | Overdue | 0 | AWC | AWC
412 | 000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0042 | 1 | 131242-WSW41-CD-IM-0042-1 | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-CD-0042 | NA | "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" | 2024-08-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 114 | AWC | 2025-10-08 | 1 | 000120 | 2024-08-24, 2024-10-05, 2025-02-26, 2025-10-08 | 03, 04, 05, 06 | 4 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
413 | 000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | E | 1130 | A | 131242-WSW41-DR-E-1130-A | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-DR-1130 | NA | "Milestone 3 Sitewide Pipe Rack" | 2025-10-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-28 | 114 | AWC | 2025-10-08 | A | 000120 | 2025-10-08 | 06 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
414 | 000120 | 06 | Heng Peng | BIM | NA | 131242 | WSW41 | DR | E | 3000 | A | 131242-WSW41-DR-E-3000-A | 2025-10-08 | Milestone 3 Sitewide Pipe Rack | Rev 6: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-10-28 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 114 | AWC | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
415 | 000121 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0003 | 0 | 131242-WSW41-CD-IM-0003-0 | 2023-10-10 | Submission Of BIM Coordination VCM Model (Sept – 2023) | For Information | 2023-11-07 | 2023-10-23 | For Information |  | YES | NA |  | 131242-WSW41-CD-0003 | NA | "Milestone 1.1 (Sidewide piperack)" && "Submission Of BIM Coordination VCM Model (Sept – 2023)" | 2023-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-10-24 | 13 | INF | 2023-10-10 | 0 | 000120&&000121 | 2023-10-06, 2023-10-10 | 00 | 2 | For Information | INF | 2023-11-10 | Overdue | 0 | INF | INF
416 | 000122 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0006 | 0 | 131242-WSW41-MS-C-0006-0 | 2023-10-10 | MSRA, SWP for Erection of Site Office (Cape) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-07 | 2023-10-18 | Approved with Comments | 2023-11-07 | NO | Overdue |  | 131242-WSW41-MS-0006 | NA | "Installation of Cable Container Support System" && "Installation of Compressor Air System Piping c/w Supports at C4A Biosolids Building Level 2 & 3 " && "MSRA, SWP for Erection of Site Office (Cape)" | 2023-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-30 | 8 | AWC | 2025-01-14 | 0 | 000122&&000920&&000975 | 2023-10-10, 2024-12-18, 2025-01-14 | 00 | 3 | Approved | APP |  |  | 0 | AWC | AWC
417 | 000123 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0006 | 0 | 131242-WSW41-PP-HS-0006-0 | 2023-10-10 | Traffic Management Plan | Approved | 2023-11-07 | 2023-10-18 | Approved |  | YES | NA |  | 131242-WSW41-PP-0006 | NA | "Traffic Management Plan " | 2023-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-30 | 8 | APP | 2023-10-10 | 0 | 000123 | 2023-10-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
418 | 000124 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | PP | PM | 0003 | 0 | 131242-WSW41-PP-PM-0003-0 | 2023-10-10 | Project Execution Plan | Rev. 0 - Not Approved - need to re-submit (refer comment sheet) | 2023-11-07 | 2023-10-27 | Not Approved | 2023-11-17 | NO | Overdue |  | 131242-WSW41-PP-0003 | NA | "Emergency Response Plan" && "Project Execution Plan" | 2023-06-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-10-24 | 17 | NAP | 2023-10-10 | 0 | 000034&&000124 | 2023-06-21, 2023-09-07, 2023-10-10 | 00, 01 | 3 | Not Approved | NAP | 2023-11-16 | Overdue | 0 | NAP | NAP
419 | 000125 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0011 | 0 | 131242-WSW41-VI-C-0011-0 | 2023-10-11 | Vendor Approval of UXO Survey – EXPLOMO | Approved | 2023-11-08 | 2023-10-18 | Approved |  | YES | NA |  | 131242-WSW41-VI-0011 | NA | "Vendor Approval of Air Compressor System (INGERSOLL-RAND)" && "Vendor Approval of UXO Survey – EXPLOMO" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-25 | 7 | APP | 2024-06-07 | 2 | 000102&&000125 | 2023-09-18, 2023-10-11, 2024-01-04, 2024-06-07 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | APP | APP
420 | 000126 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0010 | 0 | 131242-WSW41-MI-P-0010-0 | 2023-10-12 | Process & MEICA Meeting Minutes 0010_20230928 | For Information | 2023-11-09 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" | 2023-09-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-10-26 | 158 | INF | 2024-04-04 | 0 | 000109&&000126&&000152&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
421 | 000127 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0005 | 0 | 131242-WSW41-RT-PM-0005-0 | 2023-10-14 | C4B Monthly Progress Report Number No.05 (09/23) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-10 | 2023-10-27 | Not Approved | 2023-11-17 | NO | Overdue |  | 131242-WSW41-RT-0005 | NA | "C4B Monthly Progress Report Number No.05 (09/23)" | 2023-10-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-03 | 13 | NAP | 2023-10-14 | 0 | 000127 | 2023-10-14 | 00 | 1 | Not Approved | NAP | 2023-11-16 | Overdue | 0 | NAP | NAP
422 | 000128 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A | 131242-WST00-DR-C-8001_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
423 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A | 131242-WST02-DR-C-1023_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-1023_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
424 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A | 131242-WST02-DR-C-1024_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-1024_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
425 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A | 131242-WST02-DR-C-3000_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
426 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A | 131242-WST02-DR-C-5004_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-5004_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
427 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A | 131242-WST02-DR-C-5005_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
428 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A | 131242-WST02-DR-C-5006_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
429 | 000128 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A | 131242-WST02-DR-C-5007_ST610-A | 2023-10-16 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev. 0 - Not Approved (need to re-submit, refer comment sheet) | 2023-11-14 | 2023-11-08 | Not Approved | 2023-11-29 | YES | Resubmitted |  | 131242-WST02-DR-5007_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-05 | 23 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
430 | 000128 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | 1 | 131242-WST00-DR-C-8001_ST610-1 | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-19 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
431 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A | 131242-WST02-DR-C-5004_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5004_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
432 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A | 131242-WST02-DR-C-5005_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
433 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A | 131242-WST02-DR-C-5006_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
434 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A | 131242-WST02-DR-C-5007_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5007_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
435 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A | 131242-WST02-DR-C-1023_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1023_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
436 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A | 131242-WST02-DR-C-1024_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1024_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
437 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A | 131242-WST02-DR-C-3000_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-12 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
438 | 000128 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | A | 131242-WST02-DR-C-3001_ST610-A | 2023-12-29 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-29 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-3001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-12-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-18 | 47 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
439 | 000128 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | A.1 | 131242-WST00-DR-C-8001_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
440 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | A.1 | 131242-WST02-DR-C-5004_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-5004_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
441 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | A.1 | 131242-WST02-DR-C-5005_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
442 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | A.1 | 131242-WST02-DR-C-5006_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
443 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | A.1 | 131242-WST02-DR-C-5007_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-5007_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
444 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | A.1 | 131242-WST02-DR-C-1023_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1023_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
445 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | A.1 | 131242-WST02-DR-C-1024_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1024_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
446 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | A.1 | 131242-WST02-DR-C-3000_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
447 | 000128 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | A.1 | 131242-WST02-DR-C-3001_ST610-A.1 | 2024-03-28 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-3001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-12-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 35 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
448 | 000128 | 03 | Zora | CSA | NA | 131242 | NA | NA | NA | S# 128 Cmt Sheet Reply 2024 06 12 | A.1 | 131242----S# 128 Cmt Sheet Reply 2024 06 12- | 2024-06-12 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted | To close after addressing the comments of S#475 . Zora to follow up with Grace for JMH calculation | 131242-NA-NA-S# 128 Cmt Sheet Reply 2024 06 12 | NA | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2024-06-12 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-02 | 19 | NAP | 2024-06-12 | A.1 | 000128 | 2024-06-12 | 03 | 1 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
449 | 000128 | 04 | Aaron | CSA | NA | 131242 | WST02 | NA | C | S# 128 Cmt Sheet Reply 2024 10 08 | A.1 | 131242-WST02--C-S# 128 Cmt Sheet Reply 2024 10 08- | 2024-10-08 | ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-28 | 2024-10-29 | Not Approved | 2024-11-19 | NO | Overdue |  | 131242-WST02-NA-S# 128 Cmt Sheet Reply 2024 10 08 | NA | "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2024-10-08 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-28 | 21 | NAP | 2024-10-08 | A.1 | 000128 | 2024-10-08 | 04 | 1 | Not Approved | NAP | 2024-11-18 | Overdue | 0 | NAP | NAP
450 | 000129 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | MS | C | 0007 | 0 | 131242-WSW41-MS-C-0007-0 | 2023-10-17 | MSRA, SWP for Erection of Site Office (UXO) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-15 | 2023-11-01 | Approved with Comments | 2023-11-22 | NO | Overdue |  | 131242-WSW41-MS-0007 | NA | "MSRA, SWP for Door Installation" && "MSRA, SWP for Erection of Site Office (UXO)" && "Method Statement and Risk Assessment for LV Power and Control Cable Laying, Testing & Termination" | 2023-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 15 | AWC | 2025-04-07 | 0 | 000129&&000949&&001203 | 2023-10-17, 2025-01-03, 2025-02-27, 2025-04-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
451 | 000130 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0004 | 0 | 131242-WSW41-PC-W-0004-0 | 2023-10-18 | PAYMENT CLAIM NO.4 | Rev(0): Approved. Please refer to S.O. correspondence no. 73 dated 20 Oct 2023. | 2023-11-16 | 2023-10-23 | Approved |  | YES | NA |  | 131242-WSW41-PC-0004 | NA | "PAYMENT CLAIM NO.4" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-07 | 5 | APP | 2023-10-18 | 0 | 000130 | 2023-10-18 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
452 | 000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0011 | 0 | 131242-WSW41-MI-C-0011-0 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | For Information |  | YES | NA |  | 131242-WSW41-MI-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-07 | 30 | INF | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
453 | 000131 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0012 | 0 | 131242-WSW41-MI-C-0012-0 | 2023-10-18 | CSA Meeting Minutes 0011 & 0012_20230921 & 20231005 | For Information | 2023-11-16 | 2023-11-17 | For Information |  | YES | NA |  | 131242-WSW41-MI-0012 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0012_20240521" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-07 | 30 | INF | 2024-06-04 | 0 | 000131&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
454 | 000132 | 00 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 0 | 131242-WSW41-SP-C-0003-0 | 2023-10-19 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-17 | 2023-11-17 | Approved with Comments | 2023-12-07 | YES | Resubmitted |  | 131242-WSW41-SP-0003 | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | 2023-10-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-08 | 29 | AWC | 2023-12-21 | 1 | 000132 | 2023-10-19, 2023-12-21 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
455 | 000132 | 01 | Zora | CSA | NA | 131242 | WSW41 | SP | C | 0003 | 1 | 131242-WSW41-SP-C-0003-1 | 2023-12-21 | Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) | Approved | 2024-01-12 | 2024-01-15 | Approved |  | YES | NA |  | 131242-WSW41-SP-0003 | NA | "Concrete Design Mix for Bored Piling Work C40/50 (Pan-United) " | 2023-10-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-04 | 25 | APP | 2023-12-21 | 1 | 000132 | 2023-10-19, 2023-12-21 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
456 | 000133 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 0 | 131242-WSD11-BQ-P-0001-0 | 2023-10-20 | THP Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-11-20 | 2023-11-27 | Approved with Comments | 2023-12-15 | YES | Resubmitted |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-09 | 38 | AWC | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
457 | 000133 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0001 | 1 | 131242-WSD11-BQ-P-0001-1 | 2024-04-26 | THP Equipment List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-17 | 2024-05-27 | Approved with Comments | 2024-06-14 | NO | Overdue |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 31 | AWC | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
458 | 000134 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0012 | 0 | 131242-WSW41-VI-C-0012-0 | 2023-10-23 | Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-11-17 | Approved with Comments | 2023-12-07 | NO | Overdue |  | 131242-WSW41-VI-0012 | NA | "Vendor Approval of Rebar Testing Work - ELEMENT CONSTRUCTION TESTING (S) PTE. LTD." | 2023-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-12 | 25 | AWC | 2023-10-23 | 0 | 000134 | 2023-10-23 | 00 | 1 | Approved with Comments | AWC | 2023-12-07 | Overdue | 0 | AWC | AWC
459 | 000135 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 0 | 131242-WSW41-VI-M-0002-0 | 2023-10-23 | Preliminary Design and Vendor Approval of Blower (Robuschi) | Rev 0: Not approved - Revise and Resubmit | 2023-11-21 | 2023-11-27 | Not Approved | 2023-12-15 | YES | Resubmitted |  | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 35 | NAP | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
460 | 000135 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 1 | 131242-WSW41-VI-M-0002-1 | 2023-12-26 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-16 | 2024-01-29 | Approved with Comments | 2024-02-19 | YES | Resubmitted | To re-submit after vendor provide update data sheet and drawing. Kick-off meeting done on 26 March | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-09 | 34 | AWC | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
461 | 000135 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0002 | 2 | 131242-WSW41-VI-M-0002-2 | 2024-06-25 | Preliminary Design and Vendor Approval of Blower (Aerzen) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-07-15 | 2024-07-31 | Approved with Comments |  | YES | NA | R1_AWC | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-09 | 36 | AWC | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
462 | 000136 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SK | Z | 0001 | 0 | 131242-WSW41-SK-Z-0001-0 | 2023-10-23 | Time Lapse Camera Location | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2023-11-21 | 2023-12-18 | Approved with Comments | 2024-01-09 | NO | Overdue |  | 131242-WSW41-SK-0001 | NA | "Sidewide Pipe Rack GA and Reactions" && "Time Lapse Camera Location" | 2023-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-06 | 56 | AWC | 2023-10-23 | 0 | 000083&&000136 | 2023-08-28, 2023-10-23 | 00 | 2 | Approved with Comments | AWC | 2024-01-05 | Overdue | 0 | AWC | AWC
463 | 000137 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0005 | 0 | 131242-WSW41-PS-PM-0005-0 | 2023-10-25 | Monthly Progress Presentation No. 05 (0923) | For Information | 2023-11-23 | 2023-10-26 | For Information |  | YES | NA |  | 131242-WSW41-PS-0005 | NA | "Incentive / Disincentive Audit Scheme for December 2023" && "Monthly Progress Presentation No. 05 (0923)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-14 | 1 | INF | 2024-03-12 | 0 | 000137&&000355 | 2023-10-25, 2024-03-12 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
464 | 000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0003 | 0 | 131242-WSW41-MI-PM-0003-0 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 | For Information |  | YES | NA |  | 131242-WSW41-MI-0003 | NA | "BIM Bi-Weekly Meeting Minutes 0003_20230712" && "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-07-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-08 | 1 | INF | 2023-10-25 | 0 | 000052&&000138 | 2023-07-18, 2023-10-25 | 00 | 2 | For Information | INF | 2023-11-15 | Overdue | 0 | INF | INF
465 | 000138 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0004 | 0 | 131242-WSW41-MI-PM-0004-0 | 2023-10-25 | Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919 | For Information | 2023-11-23 | 2023-10-26 | For Information |  | YES | NA |  | 131242-WSW41-MI-0004 | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "Monthly Progress Meeting Minutes 0003&0004_20230822 & 0919" | 2023-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-08 | 1 | INF | 2023-10-25 | 0 | 000073&&000138 | 2023-08-15, 2023-10-25 | 00 | 2 | For Information | INF | 2023-11-15 | Overdue | 0 | INF | INF
466 | 000139 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 0 | 131242-WSW41-VI-M-0003-0 | 2023-10-25 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-11-23 | 2023-12-22 | Approved with Comments | 2024-01-15 | YES | Resubmitted | Yibo to check with JK for process data. Vendor need to provide revised design data and layout drawings once Process confirmed. | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-14 | 58 | AWC | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
467 | 000139 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0003 | 1 | 131242-WSW41-VI-M-0003-1 | 2024-11-06 | Preliminary Design and Vendor Approval of Diffuser (Xylem) | Rev 1: Approved | 2024-11-26 | 2025-03-04 | Approved |  | YES | NA |  | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-20 | 118 | APP | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
468 | 000140 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PS | P | 0001 | 0 | 131242-WSD11-PS-P-0001-0 | 2023-10-25 | Thermal Hydrolysis Process Presentation | For Information | 2023-11-23 | 2023-11-27 | For Information |  | YES | NA |  | 131242-WSD11-PS-0001 | NA | "Thermal Hydrolysis Process Presentation" | 2023-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-14 | 33 | INF | 2023-10-25 | 0 | 000140 | 2023-10-25 | 00 | 1 | For Information | INF | 2023-12-15 | Overdue | 0 | INF | INF
469 | 000141 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 0 | 131242-WSD11-CH-P-0001-0 | 2023-10-25 | Process Functional Description | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-23 | Approved with Comments | 2024-02-13 | YES | Resubmitted |  | 131242-WSD11-CH-0001 | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-14 | 90 | AWC | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
470 | 000141 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 1 | 131242-WSD11-CH-P-0001-1 | 2024-04-02 | Process Functional Description | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-04-26 | Approved with Comments | 2024-05-17 | YES | Resubmitted | R0: AWC | 131242-WSD11-CH-0001 | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 24 | AWC | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
471 | 000141 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 2 | 131242-WSD11-CH-P-0001-2 | 2024-07-28 | Process Functional Description | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WSD11-CH-0001 | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 32 | AWC | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
472 | 000141 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0001 | 3 | 131242-WSD11-CH-P-0001-3 | 2024-09-30 | Process Functional Description | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WSD11-CH-0001 | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-14 | 66 | AWC | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
473 | 000142 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 0 | 131242-WSD11-CH-P-0002-0 | 2023-10-25 | Process Design Basis | Approved with Comments. To revise and resubmit. Refer to comments sheet | 2023-11-23 | 2024-01-15 | Approved with Comments | 2024-02-02 | YES | Resubmitted |  | 131242-WSD11-CH-0002 | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-14 | 82 | AWC | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
474 | 000142 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 1 | 131242-WSD11-CH-P-0002-1 | 2024-03-20 | THP Process Design Basis | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-26 | Approved with Comments | 2024-05-17 | YES | Resubmitted | R0: AWC | 131242-WSD11-CH-0002 | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-03 | 37 | AWC | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
475 | 000142 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 2 | 131242-WSD11-CH-P-0002-2 | 2024-07-28 | THP Process Design Basis | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WSD11-CH-0002 | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 32 | AWC | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
476 | 000142 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | CH | P | 0002 | 3 | 131242-WSD11-CH-P-0002-3 | 2024-11-04 | THP Process Design Basis | Rev 3: Approved with Comments. No active comments on the document. Resubmittal is required if there are any changes during detail engineering. No resubmittal at the moment. | 2024-11-22 | 2025-01-02 | Approved with Comments |  | YES | NA |  | 131242-WSD11-CH-0002 | NA | "Process Design Basis" && "THP Process Design Basis" | 2023-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-18 | 59 | AWC | 2024-11-04 | 3 | 000142 | 2023-10-25, 2024-03-20, 2024-07-28, 2024-11-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-01-22 | Overdue | 0 | AWC | AWC
477 | 000143 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-P-7001-A | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | Not Approved | 2024-02-13 | YES | Resubmitted |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-15 | 89 | NAP | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | NAP | NAP
478 | 000143 | 00 | Joo Kwan | Process | NA | 131242 | WST00 | DR | Z | 0001 | 0 | 131242-WST00-DR-Z-0001-0 | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | Not Approved | 2024-02-13 | YES | Resubmitted |  | 131242-WST00-DR-0001 | NA | " Title Block Template (CAD)" && " Title Block Template (CAD) " && "Shop Drawings for Lintel and Stiffener " && "THP Process Flow Diagram" | 2023-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-09 | 89 | NAP | 2025-01-26 | A | 000018&&000143&&001008 | 2023-05-31, 2023-06-06, 2023-06-27, 2023-07-04, 2023-10-26, 2025-01-26 | 00, 01, 02, 03 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
479 | 000143 | 00 | Joo Kwan | Process | NA | DGN FILES | WSD11 | DR | P | 7001 | A | DGN FILES-WSD11-DR-P-7001-A | 2023-10-26 | THP Process Flow Diagram | Not approved - Revise and Resubmit | 2023-11-24 | 2024-01-23 | Not Approved | 2024-02-13 | YES | Resubmitted |  | DGN FILES-WSD11-DR-7001 | NA | "THP Process Flow Diagram" | 2023-10-26 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-15 | 89 | NAP | 2023-10-26 | A | 000143 | 2023-10-26 | 00 | 1 | Not Approved | NAP | 2024-02-12 | Overdue | 0 | NAP | NAP
480 | 000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | A | 131242-WSD11-DR-P-7001-A | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-08 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-01 | 10 | AWC | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | AWC | AWC
481 | 000143 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7002 | A | 131242-WSD11-DR-P-7002-A | 2024-03-18 | THP Process Flow Diagram | Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-17 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-07 | 10 | AWC | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | AWC | AWC
482 | 000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7001 | B | 131242-WSD11-DR-P-7001-B | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | Approved with Comments | 2024-10-30 | NO | Overdue |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 45 | AWC | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | AWC | AWC
483 | 000143 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 7002 | B | 131242-WSD11-DR-P-7002-B | 2024-08-26 | THP Process Flow Diagram | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-09-13 | 2024-10-10 | Approved with Comments | 2024-10-30 | NO | Overdue |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 45 | AWC | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | AWC | AWC
484 | 000144 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 0 | 131242-WSW41-QA-C-0001-0 | 2023-10-27 | Inspection Test Plan for Earthwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | YES | Resubmitted |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | NAP | NAP
485 | 000144 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0001 | 1 | 131242-WSW41-QA-C-0001-1 | 2023-12-21 | Inspection Test Plan for Earthwork | Approved | 2024-01-12 | 2024-01-15 | Approved |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-04 | 25 | APP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | APP | APP
486 | 000145 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 0 | 131242-WSW41-QA-C-0002-0 | 2023-10-27 | Inspection Test Plan for Bored piling work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | YES | Resubmitted |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
487 | 000145 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-C-0002-1 | 2023-12-21 | Inspection Test Plan for Bored piling work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | Approved with Comments | 2024-02-02 | YES | Resubmitted |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-04 | 25 | AWC | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
488 | 000145 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0002 | 1 | 131242-WSW41-QA-C-0002-1 | 2024-01-29 | Inspection Test Plan for Bored piling work | Approved | 2024-02-19 | 2024-02-21 | Approved |  | YES | NA |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-12 | 23 | APP | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
489 | 000146 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 0 | 131242-WSW41-QA-C-0003-0 | 2023-10-27 | Inspection Test Plan for Reinforcement work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | YES | Resubmitted |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | NAP | NAP
490 | 000146 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-C-0003-1 | 2023-12-21 | Inspection Test Plan for Reinforcement work | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | Approved with Comments | 2024-02-02 | YES | Resubmitted |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-04 | 25 | AWC | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | AWC | AWC
491 | 000146 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0003 | 1 | 131242-WSW41-QA-C-0003-1 | 2024-01-29 | Inspection Test Plan for Reinforcement work | Approved | 2024-02-19 | 2024-02-21 | Approved |  | YES | NA |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-12 | 23 | APP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | APP | APP
492 | 000147 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 0 | 131242-WSW41-QA-C-0004-0 | 2023-10-27 | Inspection Test Plan for Concreting Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | YES | Resubmitted |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
493 | 000147 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-C-0004-1 | 2023-12-21 | Inspection Test Plan for Concreting Work | Not Approved. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-12 | Not Approved | 2024-02-01 | YES | Resubmitted |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-04 | 22 | NAP | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
494 | 000147 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0004 | 1 | 131242-WSW41-QA-C-0004-1 | 2024-01-29 | Inspection Test Plan for Concreting Work | Approved | 2024-02-19 | 2024-02-21 | Approved |  | YES | NA |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-12 | 23 | APP | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | APP | APP
495 | 000148 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 0 | 131242-WSW41-QA-C-0005-0 | 2023-10-27 | Inspection Test Plan for Formwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | YES | Resubmitted |  | 131242-WSW41-QA-0005 | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
496 | 000148 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0005 | 1 | 131242-WSW41-QA-C-0005-1 | 2023-12-21 | Inspection Test Plan for Formwork | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-12 | 2024-01-15 | Approved with Comments | 2024-02-02 | NO | Overdue |  | 131242-WSW41-QA-0005 | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-04 | 25 | AWC | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
497 | 000149 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0006 | 0 | 131242-WSW41-QA-C-0006-0 | 2023-10-27 | Inspection Test Plan for Waterproofing Concrete and Application Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | NO | Overdue | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 131242-WSW41-QA-0006 | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | NAP | NAP
498 | 000150 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0007 | 0 | 131242-WSW41-QA-C-0007-0 | 2023-10-27 | Inspection Test Plan for Roadwork | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-11-27 | 2023-11-17 | Not Approved | 2023-12-07 | NO | Overdue | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 131242-WSW41-QA-0007 | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 21 | NAP | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | Approved | APP |  |  | 0 | NAP | NAP
499 | 000151 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | E | 0000 | 0 | 131242-WSD11-BQ-E-0000-0 | 2023-10-27 | THP-Electrical Load List | Approved with comments. To Revise and resubmit. Please refer to the comment sheet. | 2023-11-27 | 2024-02-02 | Approved with Comments | 2024-02-23 | YES | Resubmitted |  | 131242-WSD11-BQ-0000 | NA | "THP-Electrical Load List" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-16 | 98 | AWC | 2025-02-10 | 2 | 000151 | 2023-10-27, 2024-03-28, 2025-02-10 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
500 | 000151 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 1 | 131242-WSD11-BQ-E-0000-1 | 2024-03-28 | THP-Electrical Load List | Rev 0: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2024-04-19 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WSD11-BQ-0000 | NA | "THP-Electrical Load List" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 148 | AWC | 2025-02-10 | 2 | 000151 | 2023-10-27, 2024-03-28, 2025-02-10 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
501 | 000151 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0000 | 2 | 131242-WSD11-BQ-E-0000-2 | 2025-02-10 | THP-Electrical Load List | Rev 2: Approved with comments. To Revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WSD11-BQ-0000 | NA | "THP-Electrical Load List" | 2023-10-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-24 | 84 | AWC | 2025-02-10 | 2 | 000151 | 2023-10-27, 2024-03-28, 2025-02-10 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
502 | 000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0009 | 0 | 131242-WSW41-MI-IM-0009-0 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | For Information |  | YES | NA |  | 131242-WSW41-MI-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0009_20240220" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-13 | 10 | INF | 2024-03-01 | 0 | 000063&&000104&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
503 | 000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0009 | 0 | 131242-WSW41-PS-IM-0009-0 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | For Information |  | YES | NA |  | 131242-WSW41-PS-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Presentation No. 09 (0124)" && "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" | 2023-10-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-19 | 10 | INF | 2024-08-05 | 0 | 000152&&000319&&000617 | 2023-10-30, 2024-02-21, 2024-08-05 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
504 | 000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0010 | 0 | 131242-WSW41-MI-IM-0010-0 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | For Information |  | YES | NA |  | 131242-WSW41-MI-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" | 2023-09-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-13 | 10 | INF | 2024-04-04 | 0 | 000109&&000126&&000152&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
505 | 000152 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0010 | 0 | 131242-WSW41-PS-IM-0010-0 | 2023-10-30 | BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018 | For Information | 2023-11-28 | 2023-11-09 | For Information |  | YES | NA |  | 131242-WSW41-PS-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Incentive/ Disincentive Audit Scheme for Mar 2024" && "Monthly Progress Presentation No. 10 (0224)" | 2023-10-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-19 | 10 | INF | 2024-08-22 | 0 | 000152&&000387&&000666 | 2023-10-30, 2024-03-22, 2024-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
506 | 000153 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0011 | 0 | 131242-WSW41-MI-P-0011-0 | 2023-10-30 | Process & MEICA Meeting Minutes 0011_20231012 | For Information | 2023-11-28 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-MI-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-13 | 140 | INF | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
507 | 000154 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0015 | 0 | 131242-WSW41-LT-PM-0015-0 | 2023-10-31 | CV of Team Member (WSHC) | Approved | 2023-11-29 | 2023-12-04 | Approved |  | YES | NA |  | 131242-WSW41-LT-0015 | NA | "CV of Team Member (WSHC)" | 2023-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-20 | 34 | APP | 2023-10-31 | 0 | 000154 | 2023-10-31 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
508 | 000155 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0002 | 0 | 131242-WSW41-CT-W-0002-0 | 2023-10-31 | Professional Indemnity Insurance Letter | Acceptable for information. | 2023-11-29 | 2023-11-07 | For Information |  | YES | NA |  | 131242-WSW41-CT-0002 | NA | "Professional Indemnity Insurance Letter" | 2023-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-20 | 7 | INF | 2023-10-31 | 0 | 000155 | 2023-10-31 | 00 | 1 | For Information | INF | 2023-11-27 | Overdue | 0 | INF | INF
509 | 000156 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LT | AGC | 0001 | 0 | 131242-WSW41-LT-AGC-0001-0 | 2023-11-02 | Approval Letter to Commence Works Requiring Earth Control Measure | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-01 | 2023-11-09 | Approved with Comments | 2023-11-30 | NO | Overdue |  | 131242-WSW41-LT-0001 | NA | "Approval Letter to Commence Works Requiring Earth Control Measure" && "Common Data Environment (CDE) Set-Up and Rollout" | 2023-11-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-22 | 7 | AWC | 2024-01-12 | 0 | 000156&&000273 | 2023-11-02, 2024-01-12 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
510 | 000157 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0002 | 0 | 131242-WSW41-PS-HS-0002-0 | 2023-11-02 | Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023 | For Information | 2023-12-01 | 2023-12-01 | For Information |  | YES | NA |  | 131242-WSW41-PS-0002 | NA | "Presentation Slide for Monthly Progress Meeting No. 02(0623)" && "Quarterly Risk Management Workshop 1st Quarterly RM Workshop – 20 Oct 2023" | 2023-07-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-16 | 29 | INF | 2023-11-02 | 0 | 000057&&000157 | 2023-07-28, 2023-11-02 | 00 | 2 | For Information | INF | 2023-12-21 | Overdue | 0 | INF | INF
511 | 000158 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 0 | 131242-WST02-BQ-E-0000-0 | 2023-11-03 | SSN Electrical Load List | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2023-12-04 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-BQ-0000 | NA | "SSN Electrical Load List" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-23 | 178 | AWC | 2025-02-10 | 1 | 000158 | 2023-11-03, 2025-02-10 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
512 | 000158 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0000 | 1 | 131242-WST02-BQ-E-0000-1 | 2025-02-10 | SSN Electrical Load List | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-02-28 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-BQ-0000 | NA | "SSN Electrical Load List" | 2023-11-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-24 | 84 | AWC | 2025-02-10 | 1 | 000158 | 2023-11-03, 2025-02-10 | 00, 01 | 2 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
513 | 000159 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | PP | HS | 0007 | 0 | 131242-WSW41-PP-HS-0007-0 | 2023-11-03 | Haze Management Plan | Approved | 2023-12-04 | 2023-12-01 | Approved |  | YES | NA |  | 131242-WSW41-PP-0007 | NA | "Haze Management Plan " | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-23 | 28 | APP | 2023-11-03 | 0 | 000159 | 2023-11-03 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
514 | 000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | A | 131242-WST02-DR-EL-1000-A | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-23 | 105 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
515 | 000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | A | 131242-WST02-DR-EL-1001-A | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-23 | 105 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
516 | 000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | A | 131242-WST02-DR-EL-1002-A | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-23 | 105 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
517 | 000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | A | 131242-WST02-DR-EL-1003-A | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-23 | 105 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
518 | 000160 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | A | 131242-WST02-DR-EL-1004-A | 2023-11-03 | SSN Lighting Layout Plan | Not Approved. To revise and resubmit. | 2023-12-04 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-23 | 105 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
519 | 000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-EL-1000-B | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted | PENDING C2D | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
520 | 000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | B | 131242-WST02-DR-EL-1001-B | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
521 | 000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | B | 131242-WST02-DR-EL-1002-B | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
522 | 000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | B | 131242-WST02-DR-EL-1003-B | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
523 | 000160 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | B | 131242-WST02-DR-EL-1004-B | 2025-02-18 | SSN Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-03-10 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-04 | 77 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
524 | 000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | C | 131242-WST02-DR-EL-1000-C | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 29 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
525 | 000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | C | 131242-WST02-DR-EL-1001-C | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 29 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
526 | 000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | C | 131242-WST02-DR-EL-1002-C | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 29 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
527 | 000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | C | 131242-WST02-DR-EL-1003-C | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 29 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
528 | 000160 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | C | 131242-WST02-DR-EL-1004-C | 2025-08-04 | SSN Lighting Layout Plan | Rev 2: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-08-22 | 2025-09-02 | Not Approved | 2025-09-22 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 29 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
529 | 000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1000 | D | 131242-WST02-DR-EL-1000-D | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 49 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
530 | 000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1001 | D | 131242-WST02-DR-EL-1001-D | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 49 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
531 | 000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1002 | D | 131242-WST02-DR-EL-1002-D | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 49 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
532 | 000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1003 | D | 131242-WST02-DR-EL-1003-D | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 49 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
533 | 000160 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 1004 | D | 131242-WST02-DR-EL-1004-D | 2025-12-15 | SSN Lighting Layout Plan | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 49 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
534 | 000161 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0004 | D | 131242-WST02-CD-IM-0004-D | 2023-11-06 | Submission of Milestone 1.1 Underground Services Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WST02-CD-0004 | NA | "Submission of Milestone 1.1 Underground Services Model" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 143 | AWC | 2023-11-06 | D | 000161 | 2023-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
535 | 000161 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 | 131242-WST02-CD-IM-0022-0 | 2024-05-27 | Milestone 1.2 Underground Services | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | Not Approved | 2024-06-25 | YES | Resubmitted |  | 131242-WST02-CD-0022 | NA | "Milestone 1.2 - Underground Services" && "Milestone 1.2 Underground Services" | 2024-03-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-10 | 8 | NAP | 2024-06-05 | 1 | 000161&&000363 | 2024-03-15, 2024-05-27, 2024-06-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
536 | 000161 | 02 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 1 | 131242-WST02-CD-IM-0022-1 | 2024-06-05 | Milestone 1.2 Underground Services | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-CD-0022 | NA | "Milestone 1.2 - Underground Services" && "Milestone 1.2 Underground Services" | 2024-03-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-19 | 30 | AWC | 2024-06-05 | 1 | 000161&&000363 | 2024-03-15, 2024-05-27, 2024-06-05 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
537 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-IM-0044-0 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted | This M2 submission includes all discipline documents for the relevant area. | 131242-WST02-CD-0044 | NA | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | 2024-10-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | AWC | 2025-09-29 | 0 | 000161 | 2024-10-05, 2025-09-29 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
538 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-E-1100-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1100 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
539 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1101 | A | 131242-WST02-DR-E-1101-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1101 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
540 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1102 | A | 131242-WST02-DR-E-1102-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1102 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
541 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7750 | B | 131242-WST02-DR-E-7750-B | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-7750 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
542 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7751 | B | 131242-WST02-DR-E-7751-B | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-7751 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
543 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 7752 | B | 131242-WST02-DR-E-7752-B | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-7752 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
544 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1300 | A | 131242-WST02-DR-E-1300-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1300 | NA | "Milestone 2 Underground Services" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | AWC | 2024-10-05 | A | 000161 | 2024-10-05 | 03 | 1 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
545 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1301 | A | 131242-WST02-DR-E-1301-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1301 | NA | "Milestone 2 Underground Services" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | AWC | 2024-10-05 | A | 000161 | 2024-10-05 | 03 | 1 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
546 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1302 | A | 131242-WST02-DR-E-1302-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1302 | NA | "Milestone 2 Underground Services" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | AWC | 2024-10-05 | A | 000161 | 2024-10-05 | 03 | 1 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
547 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3300 | A | 131242-WST02-DR-E-3300-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-3300 | NA | "Milestone 2 Underground Services" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | AWC | 2024-10-05 | A | 000161 | 2024-10-05 | 03 | 1 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
548 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3301 | A | 131242-WST02-DR-E-3301-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-3301 | NA | "Milestone 2 Underground Services" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 61 | AWC | 2024-10-05 | A | 000161 | 2024-10-05 | 03 | 1 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
549 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-EK-1000-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
550 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1001 | A | 131242-WST02-DR-EK-1001-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
551 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1002 | A | 131242-WST02-DR-EK-1002-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
552 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1003 | A | 131242-WST02-DR-EK-1003-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
553 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004 | A | 131242-WST02-DR-EK-1004-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
554 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1005 | A | 131242-WST02-DR-EK-1005-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
555 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2000 | A | 131242-WST02-DR-EK-2000-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | AWC | AWC
556 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2001 | A | 131242-WST02-DR-EK-2001-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
557 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2002 | A | 131242-WST02-DR-EK-2002-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
558 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 2003 | A | 131242-WST02-DR-EK-2003-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
559 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5000 | A | 131242-WST02-DR-EK-5000-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
560 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5001 | A | 131242-WST02-DR-EK-5001-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
561 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 5002 | A | 131242-WST02-DR-EK-5002-A | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
562 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1022 | A.2 | 131242-WST02-DR-M-1022-A.2 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
563 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5011 | A.1 | 131242-WST02-DR-M-5011-A.1 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5011 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
564 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5012 | A.1 | 131242-WST02-DR-M-5012-A.1 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5012 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
565 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5013 | A.1 | 131242-WST02-DR-M-5013-A.1 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5013 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
566 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5014 | A.1 | 131242-WST02-DR-M-5014-A.1 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5014 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
567 | 000161 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 5015 | A.1 | 131242-WST02-DR-M-5015-A.1 | 2024-10-05 | Milestone 2 Underground Services | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-24 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5015 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-19 | 61 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
568 | 000161 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0044 | 0 | 131242-WST02-CD-IM-0044-0 | 2025-09-29 | Milestone 3 Underground Services | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-17 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue | This M2 submission includes all discipline documents for the relevant area. | 131242-WST02-CD-0044 | NA | "Milestone 2 Underground Services" && "Milestone 3 Underground Services" | 2024-10-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 120 | AWC | 2025-09-29 | 0 | 000161 | 2024-10-05, 2025-09-29 | 03, 04 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
569 | 000162 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-IM-0005-0 | 2023-11-06 | Submission of Milestone 1.1 Pump Stataion and Blower Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WST02-CD-0005 | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 143 | AWC | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
570 | 000162 | 01 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025-0 | 2024-05-27 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 1: Rejected as requested by Contractor. | 2024-06-14 | 2024-06-04 | Not Approved | 2024-06-25 | YES | Resubmitted |  | 131242-WST02-CD-0025 | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-10 | 8 | NAP | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
571 | 000162 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 1 | 131242-WST02-CD-IM-0025-1 | 2024-06-05 | Milestone 1.2 - SSN Pump Station and Blower Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-CD-0025 | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-19 | 30 | AWC | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
572 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025-0 | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-CD-0025 | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
573 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1314 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162&&000163 | 2025-04-09, 2025-04-28, 2025-10-27 | 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
574 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3329 | A | 131242-WST02-DR-E-3329-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3329 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
575 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3330 | A | 131242-WST02-DR-E-3330-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3330 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
576 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3331 | A | 131242-WST02-DR-E-3331-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3331 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
577 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3332 | A | 131242-WST02-DR-E-3332-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3332 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
578 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004_MS2 | C | 131242-WST02-DR-EK-1004_MS2-C | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1004_MS2 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | C | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
579 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1003_MS2 | B | 131242-WST02-DR-EL-1003_MS2-B | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1003_MS2 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | B | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
580 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1314 | A | 131242-WST02-DR-EP-1314-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1314 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162&&000163 | 2025-04-09, 2025-04-28, 2025-10-27 | 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
581 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1115 | A | 131242-WST02-DR-I-1115-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1115 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
582 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1116 | A | 131242-WST02-DR-I-1116-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1116 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
583 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1117 | A | 131242-WST02-DR-I-1117-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1117 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
584 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3035 | A | 131242-WST02-DR-I-3035-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3035 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-31 | A | 000162&&000870&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
585 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3036 | A | 131242-WST02-DR-I-3036-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3036 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2026-02-03 | B | 000162&&001813 | 2025-04-09, 2025-10-27, 2025-10-31, 2026-02-03 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
586 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3037 | A | 131242-WST02-DR-I-3037-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3037 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-29 | 84 | AWC | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
587 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1011 | A | 131242-WST02-DR-M-1011-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
588 | 000162 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4002 | A | 131242-WST02-DR-M-4002-A | 2025-04-09 | Milestone 2 - SSN Pump Station and Blower Area | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-4002 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-27 | A | 000162&&000461 | 2024-05-06, 2025-04-09, 2025-10-27 | 00, 03, 04 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
589 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 | 131242-WST02-CD-IM-0025-0 | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-CD-0025 | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
590 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1314 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162&&000163 | 2025-04-09, 2025-04-28, 2025-10-27 | 02, 03, 04 | 5 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
591 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3329 | A | 131242-WST02-DR-E-3329-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3329 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
592 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3330 | A | 131242-WST02-DR-E-3330-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3330 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
593 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3331 | A | 131242-WST02-DR-E-3331-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3331 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
594 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3332 | A | 131242-WST02-DR-E-3332-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3332 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
595 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1004_MS2 | C | 131242-WST02-DR-EK-1004_MS2-C | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1004_MS2 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | C | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
596 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1003_MS2 | B | 131242-WST02-DR-EL-1003_MS2-B | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1003_MS2 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | B | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
597 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1314 | A | 131242-WST02-DR-EP-1314-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1314 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162&&000163 | 2025-04-09, 2025-04-28, 2025-10-27 | 02, 03, 04 | 5 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
598 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1115 | A | 131242-WST02-DR-I-1115-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1115 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
599 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1116 | A | 131242-WST02-DR-I-1116-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1116 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
600 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1117 | A | 131242-WST02-DR-I-1117-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1117 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162&&001146 | 2025-03-21, 2025-04-09, 2025-08-19, 2025-10-27 | 00, 01, 03, 04 | 4 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
601 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3035 | A | 131242-WST02-DR-I-3035-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3035 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-31 | A | 000162&&000870&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
602 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3036 | A | 131242-WST02-DR-I-3036-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3036 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2026-02-03 | B | 000162&&001813 | 2025-04-09, 2025-10-27, 2025-10-31, 2026-02-03 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
603 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3037 | A | 131242-WST02-DR-I-3037-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3037 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162 | 2025-04-09, 2025-10-27 | 03, 04 | 2 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
604 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1011 | A | 131242-WST02-DR-M-1011-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
605 | 000162 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4002 | A | 131242-WST02-DR-M-4002-A | 2025-10-27 | Milestone 3 - SSN Pump Station and Blower Area | Rev 4: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-01-27 | Not Approved | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-4002 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 92 | NAP | 2025-10-27 | A | 000162&&000461 | 2024-05-06, 2025-04-09, 2025-10-27 | 00, 03, 04 | 3 | Not Approved | NAP | 2026-02-16 | Overdue | 0 | NAP | NAP
606 | 000163 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0007 | 0 | 131242-WST02-CD-IM-0007-0 | 2023-11-06 | Submission of Milestone 1.1 Water Tank | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-05 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 143 | AWC | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
607 | 000163 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 | 131242-WST02-CD-IM-0023-0 | 2024-06-03 | Milestone 1.2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-24 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-CD-0023 | NA | "Milestone 1.2 - SSN Water Tank" && "Milestone 1.2 SSN Water Tank" | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 32 | AWC | 2024-06-03 | 0 | 000163&&000367 | 2024-03-18, 2024-06-03 | 00, 01 | 2 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
608 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0055 | 0 | 131242-WST02-CD-IM-0055-0 | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-CD-0055 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | 0 | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
609 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1314 | A | 131242-WST02-DR-E-1314-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1314 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Water Tank" && "Milestone 3 - SSN Pump Station and Blower Area" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-10-27 | A | 000162&&000163 | 2025-04-09, 2025-04-28, 2025-10-27 | 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
610 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1315 | A | 131242-WST02-DR-E-1315-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1315 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | A | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
611 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3324 | A | 131242-WST02-DR-E-3324-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3324 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | A | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
612 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3325 | A | 131242-WST02-DR-E-3325-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3325 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | A | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
613 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3326 | A | 131242-WST02-DR-E-3326-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3326 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | A | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
614 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3327 | A | 131242-WST02-DR-E-3327-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3327 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | A | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
615 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3328 | A | 131242-WST02-DR-E-3328-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3328 | NA | "Milestone 2 SSN Water Tank" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-18 | 148 | AWC | 2025-04-28 | A | 000163 | 2025-04-28 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
616 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1004 | B | 131242-WST02-DR-EL-1004-B | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
617 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1004 | B | 131242-WST02-DR-EP-1004-B | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
618 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1005 | C | 131242-WST02-DR-EK-1005-C | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
619 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1112 | A | 131242-WST02-DR-I-1112-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1112 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
620 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1113 | A | 131242-WST02-DR-I-1113-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1113 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
621 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1114 | A | 131242-WST02-DR-I-1114-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1114 | NA | "Milestone 2 SSN Water Tank" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-08-19 | B | 000163&&001146 | 2025-03-21, 2025-04-28, 2025-08-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
622 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3028 | A | 131242-WST02-DR-I-3028-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3028 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
623 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3029 | A | 131242-WST02-DR-I-3029-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3029 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-07-24 | C | 000163&&000870 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
624 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3030 | A | 131242-WST02-DR-I-3030-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
625 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3031 | A | 131242-WST02-DR-I-3031-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
626 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3033 | A | 131242-WST02-DR-I-3033-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3033 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-09-29 | A | 000163&&000870&&001702 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
627 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1003 | A | 131242-WST02-DR-M-1003-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
628 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1006 | A | 131242-WST02-DR-M-1006-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
629 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3001 | A | 131242-WST02-DR-M-3001-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
630 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3002 | A | 131242-WST02-DR-M-3002-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
631 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3005 | A | 131242-WST02-DR-M-3005-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
632 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4001 | A | 131242-WST02-DR-M-4001-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-4001 | NA | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2025-04-28 | A | 000163&&000461 | 2024-05-06, 2025-04-28 | 00, 02 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
633 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1008 | A | 131242-WST02-DR-M-1008-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
634 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1010 | A | 131242-WST02-DR-M-1010-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
635 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1012 | A | 131242-WST02-DR-M-1012-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
636 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1015 | A | 131242-WST02-DR-M-1015-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
637 | 000163 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1016 | A | 131242-WST02-DR-M-1016-A | 2025-04-28 | Milestone 2 SSN Water Tank | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-16 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 148 | AWC | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
638 | 000163 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0052 | 0 | 131242-WST02-CD-IM-0052-0 | 2025-12-16 | Milestone 3 SSN Water Tank | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-CD-0052 | NA | "Milestone 3 SSN Water Tank" && "Submission of BIM Coordination VCM Model (Jan 2025)" | 2025-02-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-30 | 42 | AWC | 2025-12-16 | 0 | 000163&&001034 | 2025-02-10, 2025-12-16 | 00, 03 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
639 | 000164 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0005 | 0 | 131242-WST02-CD-IM-0005-0 | 2023-11-06 | Submission of Milestone 1.1 Astrea Separator Model | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WST02-CD-0005 | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 143 | AWC | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
640 | 000164 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 | 131242-WST02-CD-IM-0024-0 | 2024-06-04 | Milestone 1.2 SSN Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-CD-0024 | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-18 | 31 | AWC | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
641 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-IM-0024-1 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-CD-0024 | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
642 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1318 | A | 131242-WST02-DR-E-1318-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1318 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 71 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
643 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1319 | A | 131242-WST02-DR-E-1319-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1319 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 71 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
644 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3335 | A | 131242-WST02-DR-E-3335-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3335 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 71 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
645 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3336 | A | 131242-WST02-DR-E-3336-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3336 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-12 | 71 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
646 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1106 | A | 131242-WST02-DR-I-1106-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1106 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
647 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1107 | A | 131242-WST02-DR-I-1107-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1107 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
648 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1108 | A | 131242-WST02-DR-I-1108-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1108 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
649 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1109 | A | 131242-WST02-DR-I-1109-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1109 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
650 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3018 | A | 131242-WST02-DR-I-3018-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
651 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3019 | A | 131242-WST02-DR-I-3019-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
652 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3020 | A | 131242-WST02-DR-I-3020-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
653 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3021 | A | 131242-WST02-DR-I-3021-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
654 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3022 | A | 131242-WST02-DR-I-3022-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
655 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3023 | A | 131242-WST02-DR-I-3023-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
656 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1110 | A | 131242-WST02-DR-I-1110-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1110 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
657 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1111 | A | 131242-WST02-DR-I-1111-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1111 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
658 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3024 | A | 131242-WST02-DR-I-3024-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
659 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3026 | A | 131242-WST02-DR-I-3026-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
660 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000-0 | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-4000 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2025-10-31 | 0 | 000164&&000461 | 2024-05-06, 2025-04-22, 2025-10-31 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
661 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1014 | A | 131242-WST02-DR-M-1014-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
662 | 000164 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1009 | A | 131242-WST02-DR-M-1009-A | 2025-04-22 | Milestone 2 SSN Pump Station and Lamella Clarifier | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 71 | AWC | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | AWC | AWC
663 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 1 | 131242-WST02-CD-IM-0024-1 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-CD-0024 | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
664 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1318 | A | 131242-WST02-DR-E-1318-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1318 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
665 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1319 | A | 131242-WST02-DR-E-1319-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1319 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
666 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3335 | A | 131242-WST02-DR-E-3335-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3335 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
667 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3336 | A | 131242-WST02-DR-E-3336-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3336 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2025-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164 | 2025-04-22, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
668 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1106 | A | 131242-WST02-DR-I-1106-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1106 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
669 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1107 | A | 131242-WST02-DR-I-1107-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1107 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
670 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1108 | A | 131242-WST02-DR-I-1108-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1108 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
671 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1109 | A | 131242-WST02-DR-I-1109-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1109 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
672 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3018 | A | 131242-WST02-DR-I-3018-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
673 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3019 | A | 131242-WST02-DR-I-3019-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3019 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&000866&&001165 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
674 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3020 | A | 131242-WST02-DR-I-3020-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
675 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3021 | A | 131242-WST02-DR-I-3021-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
676 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3022 | A | 131242-WST02-DR-I-3022-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
677 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3023 | A | 131242-WST02-DR-I-3023-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
678 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1110 | A | 131242-WST02-DR-I-1110-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1110 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
679 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 1111 | A | 131242-WST02-DR-I-1111-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1111 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN RIO 0001B GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&001146 | 2025-03-21, 2025-04-22, 2025-08-19, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
680 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3024 | A | 131242-WST02-DR-I-3024-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3024 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | A | 000164&&000870&&001165 | 2024-12-03, 2025-03-25, 2025-04-08, 2025-04-22, 2025-07-24, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
681 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 3026 | A | 131242-WST02-DR-I-3026-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
682 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000-0 | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-4000 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | 0 | 000164&&000461 | 2024-05-06, 2025-04-22, 2025-10-31 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
683 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1014 | A | 131242-WST02-DR-M-1014-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
684 | 000164 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1009 | A | 131242-WST02-DR-M-1009-A | 2025-10-31 | Milestone 3 SSN Pump Station and Lamella Clarifier | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | AWC | AWC
685 | 000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | A | 131242-WST02-CL-EL-7000-A | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-CL-7000 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 102 | NAP | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
686 | 000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7001 | A | 131242-WST02-CL-EL-7001-A | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-CL-7001 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 102 | NAP | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
687 | 000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7002 | A | 131242-WST02-CL-EL-7002-A | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-CL-7002 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 102 | NAP | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
688 | 000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7003 | A | 131242-WST02-CL-EL-7003-A | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-CL-7003 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 102 | NAP | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
689 | 000165 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7004 | A | 131242-WST02-CL-EL-7004-A | 2023-11-06 | SSN-Lux Calculation and luminaire Schedule | Not Approved. Revise and resubmit. Refer to comments files | 2023-12-05 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-CL-7004 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 102 | NAP | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
690 | 000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7000 | B | 131242-WST02-CL-EL-7000-B | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-CL-7000 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-23 | 112 | INF | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
691 | 000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7001 | B | 131242-WST02-CL-EL-7001-B | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-CL-7001 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-23 | 112 | INF | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
692 | 000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7002 | B | 131242-WST02-CL-EL-7002-B | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-CL-7002 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-23 | 112 | INF | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
693 | 000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7003 | B | 131242-WST02-CL-EL-7003-B | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-CL-7003 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-23 | 112 | INF | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
694 | 000165 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | EL | 7004 | B | 131242-WST02-CL-EL-7004-B | 2024-07-09 | SSN-Lux Calculation and luminaire Schedule | Rev 1: For Information. | 2024-07-29 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-CL-7004 | NA | "SSN-Lux Calculation and luminaire Schedule" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-23 | 112 | INF | 2024-07-09 | B | 000165 | 2023-11-06, 2024-07-09 | 00, 01 | 2 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
695 | 000166 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 0 | 131242-WSW41-QA-A-0001-0 | 2023-11-06 | Inspection Test Plan for Architectural work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-07 | Not Approved | 2023-12-28 | YES | Resubmitted |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-20 | 31 | NAP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | NAP | NAP
696 | 000166 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0001 | 1 | 131242-WSW41-QA-A-0001-1 | 2024-12-05 | Inspection Test Plan for Architectural work | Rev.1: Approved | 2024-12-26 | 2024-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-19 | 18 | APP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | APP | APP
697 | 000167 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 0 | 131242-WSW41-QA-A-0002-0 | 2023-11-06 | Inspection Test Plan for Plastering and Painting Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | Not Approved | 2023-12-27 | YES | Resubmitted |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-20 | 30 | NAP | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
698 | 000167 | 01 | N.Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0002 | 1 | 131242-WSW41-QA-A-0002-1 | 2024-12-13 | Inspection Test Plan for Plastering and Painting Work | Rev 1 Approved | 2025-01-03 | 2024-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-27 | 10 | APP | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
699 | 000168 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0003 | 0 | 131242-WSW41-QA-A-0003-0 | 2023-11-06 | Inspection Test Plan for Installation of Raised Access Floor System Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-06 | Not Approved | 2023-12-27 | NO | Overdue | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-20 | 30 | NAP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | NAP | NAP
700 | 000169 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | A | 0004 | 0 | 131242-WSW41-QA-A-0004-0 | 2023-11-06 | Inspection Test Plan for Installation of Door and Window Work | Rev.0: Not approved. Please refer to comment sheet for resubmission. | 2023-12-05 | 2023-12-12 | Not Approved | 2024-01-03 | NO | Overdue | Overdue ITP will be submitted after the design drawing is ready. Boopathi discussed with S.O at CSA meeting-0018 dated on 11 Jan 2024 | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-20 | 36 | NAP | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
701 | 000170 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 0 | 131242-WSW41-VI-M-1001-0 | 2023-11-06 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-05 | 2024-02-14 | Approved with Comments | 2024-03-05 | YES | Resubmitted |  | 131242-WSW41-VI-1001 | NA | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 100 | AWC | 2025-01-21 | 2 | 000170 | 2023-11-06, 2024-11-23, 2025-01-21 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
702 | 000170 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 1 | 131242-WSW41-VI-M-1001-1 | 2024-11-23 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-12 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSW41-VI-1001 | NA | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-07 | 21 | AWC | 2025-01-21 | 2 | 000170 | 2023-11-06, 2024-11-23, 2025-01-21 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
703 | 000170 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1001 | 2 | 131242-WSW41-VI-M-1001-2 | 2025-01-21 | Preliminary design and Vendor Approval of HDPE Piping (AGRU) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-10 | 2025-04-27 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1001 | NA | "Preliminary design and Vendor Approval of HDPE Piping (AGRU)" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-02-04 | 96 | AWC | 2025-01-21 | 2 | 000170 | 2023-11-06, 2024-11-23, 2025-01-21 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-15 | Overdue | 0 | AWC | AWC
704 | 000171 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | A | 131242-WSD11-DR-I-7000-A | 2023-11-06 | THP Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2023-12-05 | 2023-11-21 | Not Approved | 2023-12-11 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-26 | 15 | NAP | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | NAP | NAP
705 | 000171 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7000 | B | 131242-WSD11-DR-I-7000-B | 2024-03-13 | THP Control System Architecture Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-03 | 2024-06-13 | Not Approved | 2024-07-04 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-27 | 92 | NAP | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | NAP | NAP
706 | 000171 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7000 | C | 131242-WSD11-DR-I-7000-C | 2024-07-29 | THP Control System Architecture Drawing | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-19 | 2024-08-30 | Approved with Comments | 2024-09-19 | NO | Overdue |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-12 | 32 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
707 | 000172 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 0 | 131242-WSD11-CL-P-0001-0 | 2023-11-08 | THP Compressed Air Calculation | Approved with Comments. To revise and resubmit. Refer to comments files | 2023-12-07 | 2024-01-17 | Approved with Comments | 2024-02-06 | YES | Resubmitted |  | 131242-WSD11-CL-0001 | NA | "THP Compressed Air Calculation" | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-28 | 70 | AWC | 2024-08-15 | 2 | 000172 | 2023-11-08, 2024-04-19, 2024-08-15 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
708 | 000172 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 1 | 131242-WSD11-CL-P-0001-1 | 2024-04-19 | THP Compressed Air Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-07-26 | Approved with Comments | 2024-08-16 | YES | Resubmitted |  | 131242-WSD11-CL-0001 | NA | "THP Compressed Air Calculation" | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 98 | AWC | 2024-08-15 | 2 | 000172 | 2023-11-08, 2024-04-19, 2024-08-15 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
709 | 000172 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0001 | 2 | 131242-WSD11-CL-P-0001-2 | 2024-08-15 | THP Compressed Air Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-11-07 | Approved with Comments | 2024-11-27 | NO | Overdue |  | 131242-WSD11-CL-0001 | NA | "THP Compressed Air Calculation" | 2023-11-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-29 | 84 | AWC | 2024-08-15 | 2 | 000172 | 2023-11-08, 2024-04-19, 2024-08-15 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-11-27 | Overdue | 0 | AWC | AWC
710 | 000173 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 0 | 131242-WST02-CL-P-0001-0 | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | Approved with Comments | 2024-02-09 | YES | Resubmitted |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-28 | 75 | AWC | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
711 | 000173 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | A | 131242-WST02-DR-P-7011-A | 2023-11-08 | SSN: Plant Drain Hydraulic Profile and calculation | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-07 | 2024-01-22 | Approved with Comments | 2024-02-09 | YES | Resubmitted |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-28 | 75 | AWC | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
712 | 000173 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 1 | 131242-WST02-CL-P-0001-1 | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | Approved |  | YES | NA |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-20 | 24 | APP | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
713 | 000173 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | B | 131242-WST02-DR-P-7011-B | 2024-05-06 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 1: Approved | 2024-05-27 | 2024-05-30 | Approved |  | YES | NA |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-20 | 24 | APP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | APP | APP
714 | 000173 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0001 | 2 | 131242-WST02-CL-P-0001-2 | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | Approved |  | YES | NA | Resubmitted as per SO comments | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 63 | APP | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
715 | 000173 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7011 | C | 131242-WST02-DR-P-7011-C | 2024-08-07 | SSN: Plant Drain Hydraulic Profile and calculation | Rev 2: Approved | 2024-08-28 | 2024-10-09 | Approved |  | YES | NA |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 63 | APP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | APP | APP
716 | 000174 | 00 | Thomas | PCM | NA | 131242 | WSW41 | RT | PM | 0006 | 0 | 131242-WSW41-RT-PM-0006-0 | 2023-11-08 | C4B Monthly Progress Report Number No.06 (10/23) | Rev. 0 - Approved | 2023-12-07 | 2023-11-21 | Approved |  | YES | NA |  | 131242-WSW41-RT-0006 | NA | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" && "C4B Monthly Progress Report Number No.06 (10/23)" | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-28 | 13 | APP | 2024-08-05 | 0 | 000174&&000619 | 2023-11-08, 2024-08-05 | 00 | 2 | Not Approved | NAP |  |  | 0 | APP | APP
717 | 000175 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0009 | 0 | 131242-WSW41-CD-IM-0009-0 | 2023-11-08 | Submission Of BIM Coordination VCM Model (Oct – 2023) | For Information | 2023-12-07 | 2023-11-21 | For Information |  | YES | NA |  | 131242-WSW41-CD-0009 | NA | "Submission Of BIM Coordination VCM Model (Oct – 2023)" | 2023-11-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-28 | 13 | INF | 2023-11-08 | 0 | 000175 | 2023-11-08 | 00 | 1 | For Information | INF | 2023-12-11 | Overdue | 0 | INF | INF
718 | 000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0011 | 0 | 131242-WSW41-MI-IM-0011-0 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 | For Information |  | YES | NA |  | 131242-WSW41-MI-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-23 | 5 | INF | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
719 | 000176 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | PS | IM | 0011 | 0 | 131242-WSW41-PS-IM-0011-0 | 2023-11-09 | BIM Bi-Weekly Meeting Minutes 0011_20231101 | For Information | 2023-12-08 | 2023-11-14 | For Information |  | YES | NA |  | 131242-WSW41-PS-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "Incentive/ Disincentive Audit Scheme for Apr 2024" && "Monthly Progress Presentation No. 11 (0324)" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-29 | 5 | INF | 2024-08-22 | 0 | 000176&&000453&&000667 | 2023-11-09, 2024-04-26, 2024-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
720 | 000177 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 0 | 131242-WSD11-DS-M-0001-0 | 2023-11-09 | Data Sheet of Air Compressor | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-08 | 2024-01-22 | Approved with Comments | 2024-02-09 | YES | Resubmitted |  | 131242-WSD11-DS-0001 | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 74 | AWC | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | AWC | AWC
721 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 1 | 131242-WSD11-DS-M-0001-1 | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted | Rev 0: AWC | 131242-WSD11-DS-0001 | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | AWC | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | AWC | AWC
722 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0161 | A | 131242-WSD11-DR-M-0161-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0161 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
723 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0101 | A | 131242-WSD11-DR-M-0101-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0101 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
724 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0102 | A | 131242-WSD11-DR-M-0102-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0102 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
725 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0103 | A | 131242-WSD11-DR-M-0103-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0103 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
726 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0104 | A | 131242-WSD11-DR-M-0104-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0104 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
727 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0131 | A | 131242-WSD11-DR-M-0131-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0131 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
728 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0132 | A | 131242-WSD11-DR-M-0132-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0132 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
729 | 000177 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0133 | A | 131242-WSD11-DR-M-0133-A | 2024-04-04 | Data Sheet and Drawing of Air Compressor System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-06 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-0133 | NA | " Data Sheet and Drawing of Air Compressor System " | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 42 | AWC | 2024-04-04 | A | 000177 | 2024-04-04 | 01 | 1 | Approved with Comments | AWC | 2024-06-05 | Overdue | 0 | AWC | AWC
730 | 000177 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 2 | 131242-WSD11-DS-M-0001-2 | 2024-08-12 | Data Sheet of Air Compressor System | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-25 | Approved with Comments | 2024-11-15 | YES | Resubmitted |  | 131242-WSD11-DS-0001 | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 74 | AWC | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | AWC | AWC
731 | 000177 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0001 | 3 | 131242-WSD11-DS-M-0001-3 | 2024-11-06 | Data Sheet of Air Compressor System | Rev 3: Approved | 2024-11-26 | 2024-12-05 | Approved |  | YES | NA |  | 131242-WSD11-DS-0001 | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-20 | 29 | APP | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | APP | APP
732 | 000178 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 0 | 131242-WSD11-DS-M-0005-0 | 2023-11-10 | Data Sheet of Pressure Vessel | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-18 | Approved with Comments | 2024-02-07 | YES | Resubmitted |  | 131242-WSD11-DS-0005 | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 69 | AWC | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
733 | 000178 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 1 | 131242-WSD11-DS-M-0005-1 | 2024-03-20 | Data Sheet of Pressure Vessel | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted | Related to Detailed Design Report. | 131242-WSD11-DS-0005 | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-03 | 40 | AWC | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
734 | 000178 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 2 | 131242-WSD11-DS-M-0005-2 | 2024-07-28 | Data Sheet of Pressure Vessel | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WSD11-DS-0005 | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 32 | AWC | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
735 | 000178 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 3 | 131242-WSD11-DS-M-0005-3 | 2024-11-22 | Data Sheet of Pressure Vessel | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. [Rev2 comments were not addressed by CES] | 2024-12-12 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DS-0005 | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-06 | 13 | AWC | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
736 | 000178 | 04 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0005 | 4 | 131242-WSD11-DS-M-0005-4 | 2025-03-04 | Data Sheet of Pressure Vessel | Rev 4: Approved. Please furnish PE Endorsement. | 2025-03-24 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0005 | NA | "Data Sheet of Pressure Vessel" && "Datasheet for Differential Pressure Switch (Compressed Air System)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | APP | 2025-03-17 | 0 | 000178&&001127 | 2023-11-10, 2024-03-20, 2024-07-28, 2024-11-22, 2025-03-04, 2025-03-17 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
737 | 000179 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 0 | 131242-WSD11-DS-M-0006-0 | 2023-11-10 | Data Sheet of PreCoolers | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-22 | Approved with Comments | 2024-02-09 | YES | Resubmitted |  | 131242-WSD11-DS-0006 | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 73 | AWC | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
738 | 000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0006 | 1 | 131242-WSD11-DS-M-0006-1 | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | Approved with Comments |  | YES | NA | No re-submission required | 131242-WSD11-DS-0006 | NA | "Data Sheet of PreCoolers" && "Datasheet for Electromagnetic Flow Meter " | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-02 | 41 | AWC | 2025-10-16 | 1 | 000179&&001167 | 2023-11-10, 2024-03-19, 2025-03-25, 2025-10-16 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
739 | 000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0007 | B | 131242-WSD11-DR-M-0007-B | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0007 | NA | "Data Sheet of PreCoolers" | 2024-03-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-08 | 41 | AWC | 2024-03-19 | B | 000179 | 2024-03-19 | 01 | 1 | Approved with Comments | AWC | 2024-05-17 | Overdue | 0 | AWC | AWC
740 | 000179 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 0008 | B | 131242-WSD11-DR-M-0008-B | 2024-03-19 | Data Sheet of PreCoolers | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0008 | NA | "Data Sheet of PreCoolers" | 2024-03-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-08 | 41 | AWC | 2024-03-19 | B | 000179 | 2024-03-19 | 01 | 1 | Approved with Comments | AWC | 2024-05-17 | Overdue | 0 | AWC | AWC
741 | 000180 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 0 | 131242-WSD11-DS-M-0007-0 | 2023-11-10 | Data Sheet of PGS | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | Approved with Comments | 2024-02-19 | YES | Resubmitted | Related to Detailed Design Report. | 131242-WSD11-DS-0007 | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 80 | AWC | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
742 | 000180 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 1 | 131242-WSD11-DS-M-0007-1 | 2024-03-25 | Data Sheet of PGS | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-16 | 2024-05-30 | Approved with Comments | 2024-06-20 | YES | Resubmitted | Rev 0: AWC | 131242-WSD11-DS-0007 | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-08 | 66 | AWC | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
743 | 000180 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 2 | 131242-WSD11-DS-M-0007-2 | 2024-07-28 | Data Sheet of PGS | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-09-02 | Approved with Comments | 2024-09-20 | YES | Resubmitted |  | 131242-WSD11-DS-0007 | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 36 | AWC | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
744 | 000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0007 | 3 | 131242-WSD11-DS-M-0007-3 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0007 | NA | "Data Sheet of PGS" && "Datasheet for Level Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-14 | 29 | AWC | 2025-10-16 | 1 | 000180&&001171 | 2023-11-10, 2024-03-25, 2024-07-28, 2024-09-30, 2025-03-27, 2025-10-16 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
745 | 000180 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0020 | 0 | 131242-WSD11-DS-E-0020-0 | 2024-09-30 | Data Sheet of PGS | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0020 | NA | "Data Sheet of PGS" | 2024-09-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-20 | 29 | AWC | 2024-09-30 | 0 | 000180 | 2024-09-30 | 03 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
746 | 000181 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 0 | 131242-WSD11-DS-M-0008-0 | 2023-11-10 | Data Sheet of PGC | Approved with Comments. To revise and resubmit. Refer to comment sheet. | 2023-12-11 | 2024-01-29 | Approved with Comments | 2024-02-19 | YES | Resubmitted |  | 131242-WSD11-DS-0008 | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 80 | AWC | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
747 | 000181 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 1 | 131242-WSD11-DS-M-0008-1 | 2024-03-19 | Data Sheet of PGC | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted | Related to Detailed Design Report. | 131242-WSD11-DS-0008 | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 41 | AWC | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
748 | 000181 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0008 | 2 | 131242-WSD11-DS-M-0008-2 | 2025-03-06 | Data Sheet of PGC | Rev 2: Approved. | 2025-03-26 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0008 | NA | "Data Sheet of PGC" && "Datasheet for Pressure Transmitter" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-20 | 214 | APP | 2025-10-16 | 1 | 000181&&001179 | 2023-11-10, 2024-03-19, 2025-03-06, 2025-04-01, 2025-10-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | APP | APP
749 | 000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD-A | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | Not Approved | 2024-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1000_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 32 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-01-04, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
750 | 000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD-A | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | Not Approved | 2024-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1001_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 32 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
751 | 000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD-A | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | Not Approved | 2024-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1002_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 32 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
752 | 000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD-A | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | Not Approved | 2024-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1003_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 32 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
753 | 000182 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD-A | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | Not Approved | 2024-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1004_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 32 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
754 | 000182 | 00 | Zora | CSA | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | 9999 | A | THP-FSSD-WA 01_20231109----- | 2023-11-10 | Draft Waiver Application of THP Layout (THP-FSSD-WA 01) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2023-12-11 | 2023-12-12 | Not Approved | 2024-01-03 | YES | Resubmitted |  | THP-FSSD-WA 01_20231109-NA-NA-9999 | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-30 | 32 | NAP | 2023-11-10 | A | 000182 | 2023-11-10 | 00, 01 | 2 | Not Approved | NAP | 2024-01-01 | Overdue | 0 | NAP | NAP
755 | 000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD-A | 2024-01-04 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2024-01-24 | 2024-02-15 | For Information |  | YES | NA |  | 131242-WSD11-DR-1000_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-01-18 | 42 | INF | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-01-04, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
756 | 000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD-A | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | For Information |  | YES | NA |  | 131242-WSD11-DR-1001_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2023-11-30 | 97 | INF | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
757 | 000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD-A | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | For Information |  | YES | NA |  | 131242-WSD11-DR-1002_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2023-11-30 | 97 | INF | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
758 | 000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD-A | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | For Information |  | YES | NA |  | 131242-WSD11-DR-1003_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2023-11-30 | 97 | INF | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
759 | 000182 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD-A | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | For Information |  | YES | NA |  | 131242-WSD11-DR-1004_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2023-11-30 | 97 | INF | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
760 | 000182 | 01 | Zora | CSA | NA | THP-FSSD-WA 01_20231109 | NA | NA | NA | 9999 | A | THP-FSSD-WA 01_20231109----- | 2023-11-10 | WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01) | For information. Please comply to BIM Requirement as per Specification. | 2023-12-11 | 2024-02-15 | For Information |  | YES | NA |  | THP-FSSD-WA 01_20231109-NA-NA-9999 | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2023-11-30 | 97 | INF | 2023-11-10 | A | 000182 | 2023-11-10 | 00, 01 | 2 | Not Approved | NAP | 2024-03-06 | Overdue | 0 | INF | INF
761 | 000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0010 | 0 | 131242-WST02-CD-IM-0010-0 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | Rejected |  | YES | NA |  | 131242-WST02-CD-0010 | NA | "SSN -RIO PANEL 0202- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-30 | 139 | REJ | 2025-06-18 | 1 | 000183&&001117 | 2023-11-10, 2025-03-12, 2025-06-18 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
762 | 000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0011 | 0 | 131242-WST02-CD-IM-0011-0 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | Rejected |  | YES | NA |  | 131242-WST02-CD-0011 | NA | "SSN -RIO PANEL 0401- I/O List" && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-30 | 139 | REJ | 2025-06-25 | 1 | 000183&&001142 | 2023-11-10, 2025-03-21, 2025-06-25 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
763 | 000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0012 | 0 | 131242-WST02-CD-IM-0012-0 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | Rejected |  | YES | NA |  | 131242-WST02-CD-0012 | NA | "SSN -RIO PANEL 0203- I/O List " && "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-11-30 | 139 | REJ | 2025-06-25 | 1 | 000183&&001155 | 2023-11-10, 2025-03-24, 2025-06-25 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
764 | 000183 | 00 | Nicolas | BIM | NA | 131242 | WST02 | M3 | Z | 8900 | 0 | 131242-WST02-M3-Z-8900-0 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | Rejected |  | YES | NA |  | 131242-WST02-M3-8900 | NA | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-30 | 139 | REJ | 2023-11-10 | 0 | 000183 | 2023-11-10 | 00 | 1 | Rejected | REJ | 2024-04-17 | Overdue | 0 | REJ | REJ
765 | 000183 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | RT | IM | 9005 | 0 | 131242-WSW41-RT-IM-9005-0 | 2023-11-10 | Submission of Milestone 1.1 Electrical Building | (Void/Not in use) | 2023-12-11 | 2024-03-28 | Rejected |  | YES | NA |  | 131242-WSW41-RT-9005 | NA | "Submission of Milestone 1.1 Electrical Building" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-30 | 139 | REJ | 2023-11-10 | 0 | 000183 | 2023-11-10 | 00 | 1 | Rejected | REJ | 2024-04-17 | Overdue | 0 | REJ | REJ
766 | 000184 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0013 | 0 | 131242-WSW41-MI-C-0013-0 | 2023-11-14 | CSA Meeting Minutes 0013_20231019 | For Information | 2023-12-12 | 2023-11-23 | For Information |  | YES | NA |  | 131242-WSW41-MI-0013 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" | 2023-11-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-04 | 9 | INF | 2024-08-07 | 0 | 000184&&000226&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
767 | 000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD | A | 131242-WST02-DR-A-1000_FSSD-A | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue | To follow up to submit Prolog | 131242-WST02-DR-1000_FSSD | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | A | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
768 | 000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD | A | 131242-WST02-DR-A-1001_FSSD-A | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-1001_FSSD | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | A | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
769 | 000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9000_FSSD | A1 | 131242-WST02-DR-A-9000_FSSD-A1 | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-9000_FSSD | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | A1 | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
770 | 000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 9001_FSSD | A1 | 131242-WST02-DR-A-9001_FSSD-A1 | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-9001_FSSD | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | A1 | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
771 | 000185 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | P | 7001_FSSD | SSN PFD | 131242-WST02-DR-P-7001_FSSD-SSN PFD | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | 131242-WST02-DR-7001_FSSD | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
772 | 000185 | 00 | Aaron | CSA | NA | AntiprexT AD 1020 XP_English | NA | NA | NA | 9999 | SSN PFD | AntiprexT AD 1020 XP_English----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | AntiprexT AD 1020 XP_English-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
773 | 000185 | 00 | Aaron | CSA | NA | Caustic Soda 50% SDS | NA | NA | NA | 9999 | SSN PFD | Caustic Soda 50% SDS----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | Caustic Soda 50% SDS-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
774 | 000185 | 00 | Aaron | CSA | NA | Ferric Chloride SDS | NA | NA | NA | 9999 | SSN PFD | Ferric Chloride SDS----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | Ferric Chloride SDS-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
775 | 000185 | 00 | Aaron | CSA | NA | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG | NA | NA | NA | 9999 | SSN PFD | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | SDS Paques Perfect Balance 500DF_V2.0_2020-04_ENG-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
776 | 000185 | 00 | Aaron | CSA | NA | SDS-ANA_Powermix_3100-NL-en-14_03_2022 | NA | NA | NA | 9999 | SSN PFD | SDS-ANA_Powermix_3100-NL-en-14_03_2022----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | SDS-ANA_Powermix_3100-NL-en-14_03_2022-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
777 | 000185 | 00 | Aaron | CSA | NA | TWRP C4B SSN_chemical inventory | NA | NA | NA | 9999 | SSN PFD | TWRP C4B SSN_chemical inventory----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | TWRP C4B SSN_chemical inventory-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
778 | 000185 | 00 | Aaron | CSA | NA | WST02_SSN-FSSD-WA 01 & 02 | NA | NA | NA | 9999 | SSN PFD | WST02_SSN-FSSD-WA 01 & 02----- | 2023-11-15 | Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01) | Rev.0: Not Approved. To revise and resubmit. Please submit the updated waiver application write up | 2023-12-13 | 2023-11-23 | Not Approved | 2023-12-13 | NO | Overdue |  | WST02_SSN-FSSD-WA 01 & 02-NA-NA-9999 | NA | "Draft Waiver Application of SSN Layout (SSN-FSSD-WA_01 & 01)" | 2023-11-15 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 8 | NAP | 2023-11-15 | SSN PFD | 000185 | 2023-11-15 | 00 | 1 | Not Approved | NAP | 2023-12-13 | Overdue | 0 | NAP | NAP
779 | 000186 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0006 | 0 | 131242-WSW41-PS-PM-0006-0 | 2023-11-15 | Monthly Progress Presentation No. 06 (1023) | For Information | 2023-12-13 | 2023-11-16 | For Information |  | YES | NA |  | 131242-WSW41-PS-0006 | NA | "Incentive / Disincentive Audit Scheme for Jan 2024" && "Monthly Progress Presentation No. 06 (1023)" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-05 | 1 | INF | 2024-03-14 | 0 | 000186&&000361 | 2023-11-15, 2024-03-14 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
780 | 000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | 0 | 131242-WST02-DR-P-6300-0 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | Approved with Comments | 2024-04-02 | YES | Resubmitted |  | 131242-WST02-DR-6300 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 118 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
781 | 000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | 0 | 131242-WST02-DR-P-6301-0 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | Approved with Comments | 2024-04-02 | YES | Resubmitted |  | 131242-WST02-DR-6301 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 118 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
782 | 000187 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | 0 | 131242-WST02-DR-P-6500-0 | 2023-11-15 | Plant Drain and Safety Shower P&ID | Rev 0: This revision is accepted as – Approved with comments, but in next version, DGN, i.DGN and data drop submission are must. | 2023-12-13 | 2024-03-12 | Approved with Comments | 2024-04-02 | YES | Resubmitted |  | 131242-WST02-DR-6500 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 118 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
783 | 000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | B | 131242-WST02-DR-P-6300-B | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-16 | 2024-05-27 | Approved with Comments | 2024-06-14 | YES | Resubmitted |  | 131242-WST02-DR-6300 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 32 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
784 | 000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | B | 131242-WST02-DR-P-6301-B | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-27 | 2024-05-27 | Approved with Comments | 2024-06-14 | YES | Resubmitted |  | 131242-WST02-DR-6301 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 32 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
785 | 000187 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | B | 131242-WST02-DR-P-6500-B | 2024-04-25 | Plant Drain and Safety Shower P&ID | Rev 1: Approved with comments, please incorporate all the comments and resubmit. | 2024-05-27 | 2024-05-27 | Approved with Comments | 2024-06-14 | YES | Resubmitted |  | 131242-WST02-DR-6500 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 32 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
786 | 000187 | 02 | Qili | Process | NA | 131242 | WST02 | NA | P | S#187 Cmt Reply Sheet | B | 131242-WST02--P-S#187 Cmt Reply Sheet- | 2024-10-01 | Plant Drain and Safety Shower P&ID | Rev 2: The submittal is merged with SRC 731. All the open comments from this submittal are transferred to SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WST02-NA-S#187 Cmt Reply Sheet | NA | "Plant Drain and Safety Shower P&ID" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Document_Type not in document_type_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-21 | 28 | APP | 2024-10-01 | B | 000187 | 2024-10-01 | 02 | 1 | Approved | APP |  |  | 0 | APP | APP
787 | 000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | A | 131242-WST02-DR-BF-1000-A | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 33 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
788 | 000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1001 | A | 131242-WST02-DR-BF-1001-A | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 33 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
789 | 000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A | 131242-WST02-DR-BF-7000-A | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 33 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
790 | 000188 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | A | 131242-WST02-DR-BF-7003-A | 2023-11-15 | Fire Alarm-Gas Suppression | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 33 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
791 | 000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7000 | A.1 | 131242-WST02-DR-BF-7000-A.1 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | Approved with Comments | 2024-12-13 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-12 | 58 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
792 | 000188 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | A.1 | 131242-WST02-DR-BF-7003-A.1 | 2024-09-28 | Fire Alarm-Gas Suppression | Rev 1: Approved with comments - Revise and Resubmit | 2024-10-17 | 2024-11-25 | Approved with Comments | 2024-12-13 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-12 | 58 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
793 | 000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1000 | B | 131242-WST02-DR-BF-1000-B | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-25 | 109 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
794 | 000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1001 | B | 131242-WST02-DR-BF-1001-B | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-25 | 109 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
795 | 000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1006 | B | 131242-WST02-DR-BF-1006-B | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-25 | 109 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
796 | 000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5003 | B | 131242-WST02-DR-BF-5003-B | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-25 | 109 | AWC | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
797 | 000188 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7003 | B | 131242-WST02-DR-BF-7003-B | 2025-09-11 | Fire Alarm-Gas Suppression | Rev 2: Approved with comments - Revise and Resubmit | 2025-10-01 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-25 | 109 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
798 | 000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A | 131242-WST02-DR-BP-1000-A | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-12 | Not Approved | 2024-04-02 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 118 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
799 | 000189 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A | 131242-WST02-DR-BP-7000-A | 2023-11-15 | Plumbing and Sanitary (SSN Area) | Rev 0: Not approved - Revise and Resubmit | 2023-12-13 | 2024-03-13 | Not Approved | 2024-04-03 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 119 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
800 | 000189 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.1 | 131242-WST02-DR-BP-7000-A.1 | 2024-09-26 | Plumbing and Sanitary (SSN Area) | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | Not Approved | 2024-12-13 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 60 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
801 | 000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-BP-7000-A.2 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 29 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
802 | 000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A.1 | 131242-WST02-DR-BP-1000-A.1 | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 29 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
803 | 000189 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 5000 | A | 131242-WST02-DR-BP-5000-A | 2025-02-24 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-14 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 29 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
804 | 000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 7000 | A.2 | 131242-WST02-DR-BP-7000-A.2 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-29 | 265 | PEN | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
805 | 000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 1000 | A.2 | 131242-WST02-DR-BP-1000-A.2 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-29 | 265 | PEN | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | PEN | PEN
806 | 000189 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BP | 5000 | A.1 | 131242-WST02-DR-BP-5000-A.1 | 2025-07-15 | SSN Plumbing and Sanitary | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-29 | 265 | PEN | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
807 | 000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A | 131242-WST02-DR-BF-1002-A | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | Approved with Comments | 2024-01-09 | YES | Resubmitted | Schemiatic to submit 27 Jul 24. Layout drawing shall be confirm with Digie | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 33 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
808 | 000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1003 | A | 131242-WST02-DR-BF-1003-A | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | Approved with Comments | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 33 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
809 | 000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1004 | A | 131242-WST02-DR-BF-1004-A | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | Approved with Comments | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-11-29 | 33 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
810 | 000190 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7001 | A | 131242-WST02-DR-BF-7001-A | 2023-11-15 | Hose Reel (SSN Area) | Rev 0: Approved with Comments. To revise and resubmit. Refer to comment Sheet | 2023-12-13 | 2023-12-18 | Approved with Comments | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 33 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
811 | 000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1002 | A.1 | 131242-WST02-DR-BF-1002-A.1 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | Approved with Comments | 2025-04-07 | NO | Overdue |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-07 | 25 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
812 | 000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1003 | A.1 | 131242-WST02-DR-BF-1003-A.1 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | Approved with Comments | 2025-04-07 | NO | Overdue |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-07 | 25 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
813 | 000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1004 | A.1 | 131242-WST02-DR-BF-1004-A.1 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | Approved with Comments | 2025-04-07 | NO | Overdue |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-07 | 25 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
814 | 000190 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7001 | A.1 | 131242-WST02-DR-BF-7001-A.1 | 2025-02-21 | Hose Reel (SSN Area) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-13 | 2025-03-18 | Approved with Comments | 2025-04-07 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-07 | 25 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
815 | 000191 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0010 | 0 | 131242-WSW41-CD-IM-0010-0 | 2023-11-17 | Electrical Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSW41-CD-0010 | NA | "Electrical Building" | 2023-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-07 | 132 | AWC | 2023-11-17 | 0 | 000191 | 2023-11-17 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
816 | 000191 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-IM-0027-0 | 2024-06-04 | Milestone 1.2 Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSW41-CD-0027 | NA | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-24 | 31 | AWC | 2026-01-16 | 0 | 000191 | 2024-06-04, 2026-01-16 | 01, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
817 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0059 | 0 | 131242-WSW41-CD-IM-0059-0 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WSW41-CD-0059 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | 0 | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
818 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1003 | B_MS2 | 131242-WST02-DR-B-1003-B_MS2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
819 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1004 | B_MS2 | 131242-WST02-DR-B-1004-B_MS2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
820 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1005 | B_MS2 | 131242-WST02-DR-B-1005-B_MS2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
821 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | B | 1006 | B_MS2 | 131242-WST02-DR-B-1006-B_MS2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
822 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1000 | A.1 | 131242-WST02-DR-BF-1000-A.1 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
823 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1001 | A.1 | 131242-WST02-DR-BF-1001-A.1 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
824 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1011 | A9 | 131242-WST02-DR-BF-1011-A9 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
825 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1012 | A9 | 131242-WST02-DR-BF-1012-A9 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
826 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BH | 1000 | A.1 | 131242-WST02-DR-BH-1000-A.1 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
827 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BH | 1001 | A.2 | 131242-WST02-DR-BH-1001-A.2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
828 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1002 | A.1_MS2 | 131242-WST02-DR-BF-1002-A.1_MS2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
829 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | BF | 1003 | A.1_MS2 | 131242-WST02-DR-BF-1003-A.1_MS2 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
830 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1310 | A | 131242-WST02-DR-E-1310-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1310 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
831 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1311 | A | 131242-WST02-DR-E-1311-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1311 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
832 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1312 | A | 131242-WST02-DR-E-1312-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1312 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
833 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1313 | A | 131242-WST02-DR-E-1313-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1313 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
834 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3310 | A | 131242-WST02-DR-E-3310-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3310 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
835 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3311 | A | 131242-WST02-DR-E-3311-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3311 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
836 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3312 | A | 131242-WST02-DR-E-3312-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3312 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
837 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3313 | A | 131242-WST02-DR-E-3313-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3313 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
838 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3314 | A | 131242-WST02-DR-E-3314-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3314 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
839 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3315 | A | 131242-WST02-DR-E-3315-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3315 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
840 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3316 | A | 131242-WST02-DR-E-3316-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3316 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
841 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3317 | A | 131242-WST02-DR-E-3317-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3317 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
842 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3318 | A | 131242-WST02-DR-E-3318-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3318 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
843 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3319 | A | 131242-WST02-DR-E-3319-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3319 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
844 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3320 | A | 131242-WST02-DR-E-3320-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3320 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
845 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3321 | A | 131242-WST02-DR-E-3321-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3321 | NA | "Milestone 2 SSN Electrical Building" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 131 | AWC | 2025-05-15 | A | 000191 | 2025-05-15 | 02 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
846 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-EP-1000-C | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
847 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1001 | C | 131242-WST02-DR-EP-1001-C | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
848 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-EK-1000-C | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
849 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1001 | C | 131242-WST02-DR-EK-1001-C | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
850 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EK | 1002 | C | 131242-WST02-DR-EK-1002-C | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
851 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1000 | B | 131242-WST02-DR-EL-1000-B | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
852 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EL | 1001 | B | 131242-WST02-DR-EL-1001-B | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
853 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-I-5000-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
854 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-I-5001-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
855 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5002 | A | 131242-WST02-DR-I-5002-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
856 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5003 | A | 131242-WST02-DR-I-5003-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
857 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5004 | A | 131242-WST02-DR-I-5004-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5004 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
858 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | I | 5005 | A | 131242-WST02-DR-I-5005-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-5005 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
859 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 4004 | 0 | 131242-WST02-DR-M-4004-0 | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-4004 | NA | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2025-05-15 | 0 | 000191&&000461 | 2024-05-06, 2025-05-15 | 00, 02 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
860 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1002 | A | 131242-WST02-DR-M-1002-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
861 | 000191 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3000 | A | 131242-WST02-DR-M-3000-A | 2025-05-15 | Milestone 2 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-09-23 | Approved with Comments | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 131 | AWC | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | AWC | AWC
862 | 000191 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0027 | 0 | 131242-WSW41-CD-IM-0027-0 | 2026-01-16 | Milestone 3 SSN Electrical Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-CD-0027 | NA | "Milestone 1.2 Electrical Building" && "Milestone 3 SSN Electrical Building" | 2024-06-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-30 | 80 | PEN | 2026-01-16 | 0 | 000191 | 2024-06-04, 2026-01-16 | 01, 03 | 2 | Approved with Comments | AWC | 2026-03-05 |  | 0 | PEN | PEN
863 | 000192 | 00 | Nicolas | BIM | NA | 131242 | WSW41 | CD | IM | 0008 | 0 | 131242-WSW41-CD-IM-0008-0 | 2023-11-17 | Chemical Dosing Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2023-12-15 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSW41-CD-0008 | NA | "Chemical Dosing Area" | 2023-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-07 | 132 | AWC | 2023-11-17 | 0 | 000192 | 2023-11-17 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
864 | 000192 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0026 | 1 | 131242-WSW41-CD-IM-0026-1 | 2024-06-04 | Milestone 1.2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSW41-CD-0026 | NA | "Milestone 1.2 SSN Chemical Dosing Area" | 2024-06-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-24 | 31 | AWC | 2024-06-04 | 1 | 000192 | 2024-06-04 | 01 | 1 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
865 | 000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-IM-0057-0 | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSW41-CD-0057 | NA | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | 2025-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 48 | AWC | 2026-01-16 | 0 | 000192 | 2025-05-15, 2026-01-16 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
866 | 000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | EP | 1002 | C | 131242-WST02-DR-EP-1002-C | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 48 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
867 | 000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 1004 | A | 131242-WST02-DR-M-1004-A | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 48 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
868 | 000192 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | M | 3003 | A | 131242-WST02-DR-M-3003-A | 2025-05-15 | Milestone 2 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 48 | AWC | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
869 | 000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0057 | 0 | 131242-WSW41-CD-IM-0057-0 | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-CD-0057 | NA | "Milestone 2 SSN Chemical Dosing Area" && "Milestone 3 SSN Chemical Dosing Area" | 2025-05-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-30 | 80 | PEN | 2026-01-16 | 0 | 000192 | 2025-05-15, 2026-01-16 | 02, 03 | 2 | Approved with Comments | AWC | 2026-03-05 |  | 0 | PEN | PEN
870 | 000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 1317 | C | 131242-WST02-DR-E-1317-C | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1317 | NA | "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-05 | 80 | PEN | 2026-01-16 | C | 000192 | 2026-01-16 | 03 | 1 | Awaiting S.O.'s response | PEN | 2026-03-05 |  | 0 | PEN | PEN
871 | 000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3333 | A | 131242-WST02-DR-E-3333-A | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3333 | NA | "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-05 | 80 | PEN | 2026-01-16 | A | 000192 | 2026-01-16 | 03 | 1 | Awaiting S.O.'s response | PEN | 2026-03-05 |  | 0 | PEN | PEN
872 | 000192 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | DR | E | 3334 | A | 131242-WST02-DR-E-3334-A | 2026-01-16 | Milestone 3 SSN Chemical Dosing Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3334 | NA | "Milestone 3 SSN Chemical Dosing Area" | 2026-01-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-05 | 80 | PEN | 2026-01-16 | A | 000192 | 2026-01-16 | 03 | 1 | Awaiting S.O.'s response | PEN | 2026-03-05 |  | 0 | PEN | PEN
873 | 000193 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0002 | 1 | 131242-WST02-CL-B-0002-1 | 2023-11-17 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 0: Not approved - Revise and Resubmit | 2023-12-15 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-CL-0002 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-01 | 31 | NAP | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | Approved | APP |  |  | 0 | NAP | NAP
874 | 000193 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BF | 8001 | 0 | 131242-WST02-CL-BF-8001-0 | 2024-04-04 | Engineering Calculation Report for Fire Hydrant Pipe | Rev 1: Approved | 2024-04-25 | 2024-04-26 | Approved |  | YES | NA |  | 131242-WST02-CL-8001 | NA | "Engineering Calculation Report for Fire Hydrant Pipe" && "Heat Load Calculation Report for ACMV" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-24 | 22 | APP | 2025-03-20 | 2 | 000193&&000244 | 2024-04-04, 2024-05-14, 2025-03-20 | 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
875 | 000194 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | CL | B | 0003 | 1 | 131242-WST02-CL-B-0003-1 | 2023-11-17 | Engineering Calculation Report for Potable Water Pipe | This submission is withdrown. As submitted wrongly as a new submission, which should be a Rev.1 for submittal no. 000097. | 2023-12-15 | 2023-12-06 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-CL-0003 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2023-12-01 | 19 | VOID | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | Approved | APP |  |  | 0 | VOID | VOID
876 | 000195 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0005 | 0 | 131242-WSW41-MI-PM-0005-0 | 2023-11-20 | Monthly Progress Meeting Minutes 0005_20231017 | For Information | 2023-12-18 | 2023-11-23 | For Information |  | YES | NA |  | 131242-WSW41-MI-0005 | NA | "BIM Bi-Weekly Meeting Minutes 0004&0005_20230726 & 20230810" && "CSA Meeting Minutes 0004_20230614" && "Monthly Progress Meeting Minutes 0005_20231017" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-04 | 3 | INF | 2023-11-20 | 0 | 000041&&000068&&000073&&000195 | 2023-07-06, 2023-08-14, 2023-08-15, 2023-11-20 | 00 | 4 | For Information | INF | 2023-12-13 | Overdue | 0 | INF | INF
877 | 000196 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0006 | 0 | 131242-WSW41-MI-PM-0006-0 | 2023-11-15 | Monthly Progress Meeting Minutes 0006_20231114 | For Information | 2023-12-13 | 2023-11-23 | For Information |  | YES | NA |  | 131242-WSW41-MI-0006 | NA | "BIM Bi-Weekly Meeting Minutes 0006_20230823" && "CSA Meeting Minutes 0004_20230705" && "Monthly Progress Meeting Minutes 0006_20231114" && "Process & MEICA Meeting Minutes 0005&0006_20230728 & 0803" | 2023-07-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-11-29 | 8 | INF | 2023-11-15 | 0 | 000050&&000068&&000082&&000196 | 2023-07-14, 2023-08-14, 2023-08-28, 2023-11-15 | 00 | 4 | For Information | INF | 2023-12-13 | Overdue | 0 | INF | INF
878 | 000197 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | A | 131242-WSD11-DR-E-7000-A | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 160 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
879 | 000197 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7000 | B | 131242-WSD11-DR-E-7000-B | 2025-01-21 | THP Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-02-10 | 2025-04-30 | Approved with Comments | 2025-05-20 | NO | Overdue |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 99 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
880 | 000198 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7001 | 0 | 131242-WSD11-DR-E-7001-0 | 2023-11-21 | THP Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-19 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted | To drop an email for combination of S198, S197. To reply the comment sheet as noted and to resubmit in order to close. | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-05 | 160 | AWC | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | AWC | AWC
881 | 000199 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 0 | 131242-WST02-CL-E-0001-0 | 2023-11-22 | SSN Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
882 | 000199 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 1 | 131242-WST02-CL-E-0001-1 | 2024-06-24 | SSN Cable Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | Approved with Comments | 2024-09-04 | YES | Resubmitted |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-08 | 52 | AWC | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
883 | 000199 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0001 | 2 | 131242-WST02-CL-E-0001-2 | 2025-05-30 | SSN Cable Sizing Calculations | Rev 2: Approved with comments. To revise and resubmit. | 2025-06-19 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 54 | AWC | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
884 | 000200 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 0 | 131242-WST02-VI-E-0000-0 | 2023-11-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet. | 2023-12-20 | 2023-12-22 | Approved with Comments | 2024-01-15 | YES | Resubmitted |  | 131242-WST02-VI-0000 | NA | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 30 | AWC | 2024-07-22 | 2 | 000200 | 2023-11-22, 2024-05-13, 2024-07-22 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
885 | 000200 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 1 | 131242-WST02-VI-E-0000-1 | 2024-05-13 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-03 | 2024-07-04 | Approved with Comments | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-VI-0000 | NA | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 52 | AWC | 2024-07-22 | 2 | 000200 | 2023-11-22, 2024-05-13, 2024-07-22 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
886 | 000200 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0000 | 2 | 131242-WST02-VI-E-0000-2 | 2024-07-22 | Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY) | Rev 2: Approved. | 2024-08-12 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WST02-VI-0000 | NA | "Vendor Approval - Oil Filled HV/LV Transformer (HITACHI ENERGY)" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 99 | APP | 2024-07-22 | 2 | 000200 | 2023-11-22, 2024-05-13, 2024-07-22 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
887 | 000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | A | 131242-WST02-DR-E-7000-A | 2023-11-22 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
888 | 000201 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7001 | A | 131242-WST02-DR-E-7001-A | 2023-11-23 | SSN Overall Single Line Diagram | Rev 0: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2023-12-21 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-07 | 158 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
889 | 000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7000 | B | 131242-WST02-DR-E-7000-B | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 81 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
890 | 000201 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7001 | B | 131242-WST02-DR-E-7001-B | 2025-02-14 | SSN Overall Single Line Diagram | Rev 1: Approved with Comment. To revise and resubmit. Please refer to attached file for comments. | 2025-03-06 | 2025-05-06 | Awaiting S.O.'s response |  |  | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-28 | 81 | PEN | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
891 | 000202 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 0 | 131242-WSD11-BQ-E-0001-0 | 2023-11-22 | THP Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
892 | 000202 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 1 | 131242-WSD11-BQ-E-0001-1 | 2024-06-12 | THP Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-03 | 2024-08-16 | Approved with Comments | 2024-09-05 | YES | Resubmitted |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-26 | 65 | AWC | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
893 | 000202 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 2 | 131242-WSD11-BQ-E-0001-2 | 2025-04-10 | THP Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-30 | 2025-05-08 | Approved with Comments | 2025-05-28 | YES | Resubmitted |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 28 | AWC | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
894 | 000202 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0001 | 3 | 131242-WSD11-BQ-E-0001-3 | 2025-07-21 | THP Cable List | Rev 3: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-BQ-0001 | NA | " THP ICA Cable List" && "THP Cable List" && "THP Equipment List" | 2023-10-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 43 | AWC | 2025-07-21 | 3 | 000133&&000202&&001254 | 2023-10-20, 2023-11-22, 2024-04-26, 2024-06-12, 2025-04-10, 2025-04-25, 2025-07-21 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-09-22 | Overdue | 0 | AWC | AWC
895 | 000203 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | A | 131242-WSD11-CL-E-0000-A | 2023-11-22 | THP Cable sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WSD11-CL-0000 | NA | "THP Cable sizing Calculations" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2024-06-12 | B | 000203 | 2023-11-22, 2024-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
896 | 000203 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | E | 0000 | B | 131242-WSD11-CL-E-0000-B | 2024-06-12 | THP Cable sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. | 2024-07-03 | 2024-08-16 | Approved with Comments | 2024-09-05 | NO | Overdue |  | 131242-WSD11-CL-0000 | NA | "THP Cable sizing Calculations" | 2023-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-26 | 65 | AWC | 2024-06-12 | B | 000203 | 2023-11-22, 2024-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2024-09-05 | Overdue | 0 | AWC | AWC
897 | 000204 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 0 | 131242-WST02-BQ-E-0001-0 | 2023-11-22 | SSN Cable List | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
898 | 000204 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 1 | 131242-WST02-BQ-E-0001-1 | 2024-06-24 | SSN Cable List | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-12 | 2024-08-15 | Approved with Comments | 2024-09-04 | YES | Resubmitted |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-08 | 52 | AWC | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
899 | 000204 | 02 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 2 | 131242-WST02-BQ-E-0001-2 | 2025-04-18 | SSN Cable List | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-08 | 2025-05-07 | Approved with Comments | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-02 | 19 | AWC | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
900 | 000204 | 03 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0001 | 3 | 131242-WST02-BQ-E-0001-3 | 2025-07-11 | SSN Cable List | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-07-31 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-25 | 12 | AWC | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
901 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | A | 131242-WST02-DR-EK-1000-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
902 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | A | 131242-WST02-DR-EK-1001-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
903 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | A | 131242-WST02-DR-EK-1002-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
904 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | A | 131242-WST02-DR-EK-1003-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
905 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | A | 131242-WST02-DR-EK-1004-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 159 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
906 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | A | 131242-WST02-DR-EK-1005-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
907 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | A | 131242-WST02-DR-EK-2000-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | NAP | NAP
908 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | A | 131242-WST02-DR-EK-2001-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
909 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | A | 131242-WST02-DR-EK-2002-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
910 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | A | 131242-WST02-DR-EK-2003-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
911 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | A | 131242-WST02-DR-EK-5000-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
912 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | A | 131242-WST02-DR-EK-5001-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
913 | 000205 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | A | 131242-WST02-DR-EK-5002-A | 2023-11-22 | Lightning Protection System | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-20 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 159 | NAP | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
914 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | B | 131242-WST02-DR-EK-1000-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
915 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | B | 131242-WST02-DR-EK-1001-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
916 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | B | 131242-WST02-DR-EK-1002-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
917 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | B | 131242-WST02-DR-EK-1003-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
918 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | B | 131242-WST02-DR-EK-1004-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
919 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | B | 131242-WST02-DR-EK-1005-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
920 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | B | 131242-WST02-DR-EK-2000-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | AWC | AWC
921 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | B | 131242-WST02-DR-EK-2001-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
922 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | B | 131242-WST02-DR-EK-2002-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
923 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | B | 131242-WST02-DR-EK-2003-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
924 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | B | 131242-WST02-DR-EK-5000-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
925 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | B | 131242-WST02-DR-EK-5001-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
926 | 000205 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | B | 131242-WST02-DR-EK-5002-B | 2024-07-06 | SSN Preliminary Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 48 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
927 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1000 | C | 131242-WST02-DR-EK-1000-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
928 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1001 | C | 131242-WST02-DR-EK-1001-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
929 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1002 | C | 131242-WST02-DR-EK-1002-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | AWC | AWC
930 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1003 | C | 131242-WST02-DR-EK-1003-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
931 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1004 | C | 131242-WST02-DR-EK-1004-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
932 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 1005 | C | 131242-WST02-DR-EK-1005-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
933 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2000 | C | 131242-WST02-DR-EK-2000-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | AWC | AWC
934 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2001 | C | 131242-WST02-DR-EK-2001-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
935 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2002 | C | 131242-WST02-DR-EK-2002-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
936 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 2003 | C | 131242-WST02-DR-EK-2003-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
937 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5000 | C | 131242-WST02-DR-EK-5000-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
938 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5001 | C | 131242-WST02-DR-EK-5001-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
939 | 000205 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EK | 5002 | C | 131242-WST02-DR-EK-5002-C | 2025-02-20 | SSN Preliminary Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-03-12 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-06 | 75 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
940 | 000206 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 0 | 131242-WST02-CL-P-0002-0 | 2023-11-22 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-02-26 | Approved with Comments | 2024-03-15 | YES | Resubmitted | pending Puriteq confirmation | 131242-WST02-CL-0002 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-06 | 96 | AWC | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
941 | 000206 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0002 | 1 | 131242-WST02-CL-P-0002-1 | 2025-03-04 | Preliminary Sizing Calculation for SSN Future OCF System | Rev 1: For Information | 2025-03-24 | 2025-10-06 | For Information |  | YES | NA |  | 131242-WST02-CL-0002 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | INF | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | Approved | APP |  |  | 0 | INF | INF
942 | 000207 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-P-0002-0 | 2023-11-22 | THP Equipment Sizing Calculation Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2023-12-20 | 2024-03-07 | Approved with Comments | 2024-03-27 | YES | Resubmitted |  | 131242-WSD11-CL-0002 | NA | "THP Equipment Sizing Calculation Sheet" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 106 | AWC | 2023-11-24 | 0 | 000207&&000212 | 2023-11-22, 2023-11-24 | 00 | 2 | (VOID NOT IN USE) | VOID |  |  | 0 | AWC | AWC
943 | 000207 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | Comment_CES Reply 2024 03 11 | 0 | 131242-WSD11-CL-P-Comment_CES Reply 2024 03 11- | 2024-03-11 | THP Equipment Sizing Calculation Sheet | Rev 1: Approved | 2024-04-01 | 2024-04-29 | Approved |  | YES | NA | Rev 0 : AWC | 131242-WSD11-CL-Comment_CES Reply 2024 03 11 | NA | "THP Equipment Sizing Calculation Sheet" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-03-31 | 49 | APP | 2024-03-11 | 0 | 000207 | 2024-03-11 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
944 | 000208 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 0 | 131242-WSD11-RT-E-0001-0 | 2023-11-22 | THP Atex Hazardous Area Assessment Report | Rev 0: For Information. Response to comment sheet required. | 2023-12-20 | 2024-05-15 | For Information | 2024-06-05 | YES | Resubmitted |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-12 | 175 | INF | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | INF | INF
945 | 000208 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | E | 0001 | 1 | 131242-WSD11-RT-E-0001-1 | 2024-09-11 | THP Atex Hazardous Area Assessment Report | Rev 1: For Information. | 2024-10-01 | 2024-10-25 | For Information |  | YES | NA |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-25 | 44 | INF | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | INF | INF
946 | 000209 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0012 | 0 | 131242-WSW41-MI-P-0012-0 | 2023-11-24 | C4B Minutes of Engineering Process & MEICA Meeting No.0012 | Rev 0: For Information | 2023-12-22 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0012 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0012_20240521" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-08 | 179 | INF | 2024-06-04 | 0 | 000131&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
947 | 000210 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0003 | 0 | 131242-WST02-MI-P-0003-0 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WST02-MI-0003 | NA | "C4B Minutes of SSN Ad Hoc Meeting" | 2023-11-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-14 | 179 | INF | 2023-11-24 | 0 | 000210 | 2023-11-24 | 00 | 1 | For Information | INF | 2024-06-10 | Overdue | 0 | INF | INF
948 | 000211 | 00 | Qili | Process | NA | 131242 | WST02 | MI | P | 0004 | 0 | 131242-WST02-MI-P-0004-0 | 2023-11-24 | C4B Minutes of SSN Ad Hoc Meeting | Rev 0: For Information | 2023-12-22 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WST02-MI-0004 | NA | "C4B Minutes of SSN Ad Hoc Meeting" | 2023-11-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-14 | 179 | INF | 2023-11-24 | 0 | 000211 | 2023-11-24 | 00 | 1 | For Information | INF | 2024-06-10 | Overdue | 0 | INF | INF
949 | 000212 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | CL | P | 0002 | 0 | 131242-WSD11-CL-P-0002-0 | 2023-11-24 | THP Equipment Sizing Calculation Sheet | This submittal is withdrawn. As already submitted these drawings under in the submittal 000207 on 22 Nov 2023. | 2023-12-22 | 2023-12-08 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WSD11-CL-0002 | NA | "THP Equipment Sizing Calculation Sheet" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2023-12-08 | 14 | VOID | 2023-11-24 | 0 | 000207&&000212 | 2023-11-22, 2023-11-24 | 00 | 2 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
950 | 000213 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0014 | 0 | 131242-WSW41-MI-C-0014-0 | 2023-11-27 | C4B Minutes of CSA Progress Meeting No.0014 | For Information | 2023-12-26 | 2023-12-13 | For Information |  | YES | NA |  | 131242-WSW41-MI-0014 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-17 | 16 | INF | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
951 | 000214 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0005 | 0 | 131242-WSW41-PC-W-0005-0 | 2023-11-27 | PAYMENT CLAIM NO.5 | Approved. Please refer to S.O. Correspondence No. 0089 dated 1 Dec 2023. | 2023-12-26 | 2023-12-06 | Approved |  | YES | NA |  | 131242-WSW41-PC-0005 | NA | "PAYMENT CLAIM NO.5" | 2023-11-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-17 | 9 | APP | 2023-11-27 | 0 | 000214 | 2023-11-27 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
952 | 000215 | 00 | Franklin | PMT | NA | 131242 | WSW41 | LT | PM | 0016 | 0 | 131242-WSW41-LT-PM-0016-0 | 2023-11-29 | Clarification on Anammox Reactor Design Capacity | Rev 0: For Information. Please find our respond as attached. | 2023-12-28 | 2024-07-26 | For Information |  | YES | NA |  | 131242-WSW41-LT-0016 | NA | "Clarification on Anammox Reactor Design Capacity" | 2023-11-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-19 | 240 | INF | 2023-11-29 | 0 | 000215 | 2023-11-29 | 00 | 1 | For Information | INF | 2024-08-15 | Overdue | 0 | INF | INF
953 | 000216 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 0 | 131242-WSW41-QA-C-0008-0 | 2023-11-30 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2023-12-29 | 2023-12-05 | Approved with Comments | 2023-12-26 | YES | Resubmitted |  | 131242-WSW41-QA-0008 | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 5 | AWC | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
954 | 000216 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0008 | 1 | 131242-WSW41-QA-C-0008-1 | 2023-12-12 | Material Submission for HDG Thread Rod, Flat Washer & Hex Nut | Approved | 2024-01-03 | 2024-01-12 | Approved |  | YES | NA |  | 131242-WSW41-QA-0008 | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-26 | 31 | APP | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
955 | 000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | 0 | 131242-WSD11-DR-EL-1000-0 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | Rejected | 2023-12-22 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 4 | REJ | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | REJ | REJ
956 | 000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | 0 | 131242-WSD11-DR-EL-1001-0 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | Rejected | 2023-12-22 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 4 | REJ | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | REJ | REJ
957 | 000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | 0 | 131242-WSD11-DR-EL-1002-0 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | Rejected | 2023-12-22 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 4 | REJ | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | REJ | REJ
958 | 000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | 0 | 131242-WSD11-DR-EL-1003-0 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | Rejected | 2023-12-22 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 4 | REJ | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | REJ | REJ
959 | 000217 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | 0 | 131242-WSD11-DR-EL-1004-0 | 2023-11-30 | THP Power Layout Plan | Rev.0: Rejected. As requested, C4B would like to withdraw this submittal. | 2023-12-29 | 2023-12-04 | Rejected | 2023-12-22 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 4 | REJ | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | REJ | REJ
960 | 000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | A | 131242-WSD11-DR-EP-1000-A | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-26 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
961 | 000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | A | 131242-WSD11-DR-EP-1001-A | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
962 | 000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | A | 131242-WSD11-DR-EP-1002-A | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
963 | 000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | A | 131242-WSD11-DR-EP-1003-A | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
964 | 000217 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | A | 131242-WSD11-DR-EP-1004-A | 2023-12-05 | THP Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
965 | 000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000-B | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
966 | 000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001-B | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
967 | 000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002-B | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
968 | 000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003-B | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
969 | 000217 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004-B | 2024-08-13 | THP Power Layout Plan | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | AWC | AWC
970 | 000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1000 | C | 131242-WSD11-DR-EP-1000-C | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 22 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
971 | 000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1001 | C | 131242-WSD11-DR-EP-1001-C | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 22 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
972 | 000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1002 | C | 131242-WSD11-DR-EP-1002-C | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 22 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
973 | 000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1003 | C | 131242-WSD11-DR-EP-1003-C | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 22 | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
974 | 000217 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 1004 | C | 131242-WSD11-DR-EP-1004-C | 2025-04-16 | THP Power Layout Plan | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-05-06 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-30 | 22 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | AWC | AWC
975 | 000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | A | 131242-WSD11-DR-EL-1000-A | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 77 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
976 | 000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | A | 131242-WSD11-DR-EL-1001-A | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 77 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
977 | 000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | A | 131242-WSD11-DR-EL-1002-A | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 77 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
978 | 000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | A | 131242-WSD11-DR-EL-1003-A | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 77 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
979 | 000218 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | A | 131242-WSD11-DR-EL-1004-A | 2023-11-30 | THP Lighting Layout Plan | Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 77 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
980 | 000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000-B | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 94 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
981 | 000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001-B | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 94 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
982 | 000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002-B | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 94 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
983 | 000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003-B | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 94 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
984 | 000218 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004-B | 2024-09-03 | THP Lighting Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-23 | 2024-12-06 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 94 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
985 | 000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000-C | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | Not Approved | 2025-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 21 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
986 | 000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001-C | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | Not Approved | 2025-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 21 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
987 | 000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002-C | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | Not Approved | 2025-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 21 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
988 | 000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003-C | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | Not Approved | 2025-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 21 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
989 | 000218 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004-C | 2025-04-17 | THP Lighting Layout Plan | Not Approved - Revise and resubmit | 2025-05-07 | 2025-05-08 | Not Approved | 2025-05-28 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-01 | 21 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
990 | 000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000-C | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
991 | 000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001-C | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
992 | 000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002-C | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
993 | 000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003-C | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 41 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
994 | 000218 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004-C | 2025-08-21 | THP Lighting Layout Plan | Rev 3: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2025-09-10 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-04 | 41 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
995 | 000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1000 | C | 131242-WSD11-DR-EL-1000-C | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-28 | 50 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
996 | 000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1001 | C | 131242-WSD11-DR-EL-1001-C | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-28 | 50 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
997 | 000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1002 | C | 131242-WSD11-DR-EL-1002-C | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-28 | 50 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
998 | 000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1003 | C | 131242-WSD11-DR-EL-1003-C | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-28 | 50 | NAP | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | NAP | NAP
999 | 000218 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EL | 1004 | C | 131242-WSD11-DR-EL-1004-C | 2025-12-14 | THP Lighting Layout Plan | Rev 4: Not approved - Revise and Resubmit Please refer to attached file for comments. | 2026-01-01 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-28 | 50 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | NAP | NAP
1000 | 000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A | 131242-WST02-DR-BH-1000-A | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 18 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
1001 | 000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A | 131242-WST02-DR-BH-1001-A | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 18 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1002 | 000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A | 131242-WST02-DR-BH-7000-A | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 18 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1003 | 000219 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A | 131242-WST02-DR-BH-7001-A | 2023-11-30 | Building Services ACMV | Rev 0: Not approved - Revise and Resubmit | 2023-12-29 | 2023-12-18 | Not Approved | 2024-01-09 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 18 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1004 | 000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.1 | 131242-WST02-DR-BH-7000-A.1 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | Not Approved | 2024-12-13 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 60 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1005 | 000219 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.1 | 131242-WST02-DR-BH-7001-A.1 | 2024-09-26 | Building Services ACMV | Rev 1: Not approved - Revise and Resubmit | 2024-10-16 | 2024-11-25 | Not Approved | 2024-12-13 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 60 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1006 | 000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.2 | 131242-WST02-DR-BH-5000-A.2 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 45 | NAP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1007 | 000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.2 | 131242-WST02-DR-BH-7000-A.2 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 45 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1008 | 000219 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.2 | 131242-WST02-DR-BH-7001-A.2 | 2024-12-24 | Building Services ACMV | Rev 2: Not approved - Revise and Resubmit | 2025-01-14 | 2025-02-07 | Not Approved | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-07 | 45 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1009 | 000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.3 | 131242-WST02-DR-BH-5000-A.3 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 40 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1010 | 000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.3 | 131242-WST02-DR-BH-7000-A.3 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 40 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1011 | 000219 | 03 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.3 | 131242-WST02-DR-BH-7001-A.3 | 2025-02-13 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-05 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-27 | 40 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1012 | 000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-BH-1000-A.4 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | Approved with Comments | 2025-09-26 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-29 | 55 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
1013 | 000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A.4 | 131242-WST02-DR-BH-1001-A.4 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-29 | 55 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
1014 | 000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.4 | 131242-WST02-DR-BH-5000-A.4 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-29 | 55 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1015 | 000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.4 | 131242-WST02-DR-BH-7000-A.4 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-29 | 55 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1016 | 000219 | 04 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.4 | 131242-WST02-DR-BH-7001-A.4 | 2025-07-15 | Building Services ACMV | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-04 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-29 | 55 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1017 | 000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1000 | A.4 | 131242-WST02-DR-BH-1000-A.4 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 61 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
1018 | 000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 1001 | A.4 | 131242-WST02-DR-BH-1001-A.4 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 61 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
1019 | 000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 5000 | A.4 | 131242-WST02-DR-BH-5000-A.4 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 61 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
1020 | 000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7000 | A.4 | 131242-WST02-DR-BH-7000-A.4 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 61 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
1021 | 000219 | 05 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BH | 7001 | A.4 | 131242-WST02-DR-BH-7001-A.4 | 2025-10-29 | Building Services ACMV | Rev 5: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-18 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 61 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
1022 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | A | 131242-WST02-DR-BE-7000-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 161 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1023 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7001 | A | 131242-WST02-DR-BE-7001-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 161 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1024 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7002 | A | 131242-WST02-DR-BE-7002-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 161 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1025 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7003 | A | 131242-WST02-DR-BE-7003-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-14 | 161 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1026 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7004 | A | 131242-WST02-DR-BE-7004-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 161 | NAP | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1027 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7005 | A | 131242-WST02-DR-BE-7005-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 161 | NAP | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1028 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7006 | A | 131242-WST02-DR-BE-7006-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 161 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | NAP | NAP
1029 | 000220 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7007 | A | 131242-WST02-DR-BE-7007-A | 2023-11-30 | SSN Distribution Board Single Line Diagram | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2023-12-29 | 2024-05-09 | Not Approved | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-20 | 161 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | NAP | NAP
1030 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7000 | B | 131242-WST02-DR-BE-7000-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue | Pending from C2D | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1031 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7001 | B | 131242-WST02-DR-BE-7001-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1032 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7002 | B | 131242-WST02-DR-BE-7002-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1033 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7003 | B | 131242-WST02-DR-BE-7003-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1034 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7004 | B | 131242-WST02-DR-BE-7004-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1035 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7005 | B | 131242-WST02-DR-BE-7005-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1036 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7006 | B | 131242-WST02-DR-BE-7006-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | NAP | NAP
1037 | 000220 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7007 | B | 131242-WST02-DR-BE-7007-B | 2025-04-03 | SSN Distribution Board Single Line Diagram | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2025-04-23 | 2025-06-17 | Not Approved | 2025-07-07 | NO | Overdue |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-17 | 75 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | NAP | NAP
1038 | 000221 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PO | M | 0002 | 0 | 131242-WSD11-PO-M-0002-0 | 2023-12-01 | Unpriced PO for Air Compressor System | For Information | 2024-01-02 | 2024-01-17 | For Information |  | YES | NA |  | 131242-WSD11-PO-0002 | NA | "Unpriced PO for Air Compressor System" | 2023-12-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-21 | 47 | INF | 2023-12-01 | 0 | 000221 | 2023-12-01 | 00 | 1 | For Information | INF | 2024-02-06 | Overdue | 0 | INF | INF
1039 | 000222 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0010 | 0 | 131242-WSD11-DS-M-0010-0 | 2023-12-01 | Progressive Cavity Pumps | Rev 0: Not approved - Revise and Resubmit | 2024-01-02 | 2024-03-07 | Not Approved | 2024-03-27 | YES | Resubmitted |  | 131242-WSD11-DS-0010 | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-21 | 97 | NAP | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
1040 | 000222 | 01 | Joo Kwan | Process | NA | 131242 | NA | DS | M | S222 Cmt Sheet Reply 2024 07 22 | 0 | 131242--DS-M-S222 Cmt Sheet Reply 2024 07 22- | 2024-07-22 | Progressive Cavity Pumps | Rev 1: Rejected based on contractor's request. Reply to contractor reply is attached herewith. | 2024-08-12 | 2024-08-29 | Rejected |  | YES | NA |  | 131242-NA-DS-S222 Cmt Sheet Reply 2024 07 22 | NA | "Progressive Cavity Pumps" | 2024-07-22 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-11 | 38 | REJ | 2024-07-22 | 0 | 000222 | 2024-07-22 | 01 | 1 | Rejected | REJ | 2024-09-18 | Overdue | 0 | REJ | REJ
1041 | 000223 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 0 | 131242-WSD11-DS-M-0009-0 | 2023-12-01 | THP Plant Safety Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet | 2024-01-02 | 2024-03-07 | Approved with Comments | 2024-03-27 | YES | Resubmitted | JV to follow up with JK to close the submittal | 131242-WSD11-DS-0009 | NA | "Datasheet for Tuning Fork Level Switch " && "THP Plant Safety Valve" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-21 | 97 | AWC | 2025-09-10 | 1 | 000223&&001180 | 2023-12-01, 2024-07-28, 2025-04-01, 2025-09-10 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1042 | 000223 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0009 | 1 | 131242-WSD11-DS-M-0009-1 | 2024-07-28 | THP Plant Safety Valve | Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-16 | 2024-08-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DS-0009 | NA | "Datasheet for Tuning Fork Level Switch " && "THP Plant Safety Valve" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-11 | 4 | AWC | 2025-09-10 | 1 | 000223&&001180 | 2023-12-01, 2024-07-28, 2025-04-01, 2025-09-10 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1043 | 000224 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 0 | 131242-WSD11-SP-P-0001-0 | 2023-12-01 | THP System Control Philosophy | The submittal is approved with comments, resubmittal is required. | 2024-01-02 | 2024-01-26 | Approved with Comments | 2024-02-16 | YES | Resubmitted |  | 131242-WSD11-SP-0001 | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-21 | 56 | AWC | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1044 | 000224 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | P | 0001 | 1 | 131242-WSD11-SP-P-0001-1 | 2024-03-01 | THP System Control Philosophy | Rev1- The submittal is approved with comments, resubmittal is required. The comments are | 2024-03-21 | 2024-04-26 | Approved with Comments | 2024-05-17 | YES | Resubmitted | JV to follow up with JK to close the submittal | 131242-WSD11-SP-0001 | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-15 | 56 | AWC | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1045 | 000224 | 02 | Joo Kwan | Process | NA | 131242 | NA | SP | P | Cmt Sheet Reply S224.0 2024 07 30 | 1 | 131242--SP-P-Cmt Sheet Reply S224.0 2024 07 30- | 2024-07-30 | THP System Control Philosophy | Rev2- Although there are no active comments on the document, the document is still approved as noted to accommodate for the changes if any during the detail engineering. | 2024-08-20 | 2024-09-24 | Approved with Comments |  | YES | NA |  | 131242-NA-SP-Cmt Sheet Reply S224.0 2024 07 30 | NA | "THP System Control Philosophy" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-19 | 56 | AWC | 2024-07-30 | 1 | 000224 | 2024-07-30 | 02 | 1 | Approved with Comments | AWC | 2024-10-14 | Overdue | 0 | AWC | AWC
1046 | 000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1000 | 0 |  | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2023-12-18 | 4 | VOID | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | VOID | VOID
1047 | 000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 1001 | 0 |  | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2023-12-18 | 4 | VOID | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | VOID | VOID
1048 | 000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 7000 | 0 |  | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2023-12-18 | 4 | VOID | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | VOID | VOID
1049 | 000225 | 00 | Emerson | Piping/ BS | NA | 131242 | WST02 | DR | BH | 7001 | 0 |  | 2023-12-04 | SSN Electrical Building ACMV layout & Schedule | This submittal is withdrawn. As already submitted these drawings under submittal 000219 on 30 Nov 2023. | 2024-01-03 | 2023-12-08 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2023-12-18 | 4 | VOID | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | VOID | VOID
1050 | 000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0012 | 0 | 131242-WSW41-MI-IM-0012-0 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 | For Information |  | YES | NA |  | 131242-WSW41-MI-0012 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0012_20240521" | 2023-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-19 | 8 | INF | 2024-06-04 | 0 | 000131&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1051 | 000226 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0013 | 0 | 131242-WSW41-MI-IM-0013-0 | 2023-12-05 | BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129 | For Information | 2024-01-04 | 2023-12-13 | For Information |  | YES | NA |  | 131242-WSW41-MI-0013 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" | 2023-11-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-19 | 8 | INF | 2024-08-07 | 0 | 000184&&000226&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1052 | 000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | A | 131242-WST02-DR-EP-1000-A | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
1053 | 000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | A | 131242-WST02-DR-EP-1001-A | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1054 | 000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | A | 131242-WST02-DR-EP-1002-A | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
1055 | 000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | A | 131242-WST02-DR-EP-1003-A | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
1056 | 000227 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | A | 131242-WST02-DR-EP-1004-A | 2023-12-05 | SSN Power Layout Plan | Rev 0: Not Approved. To revise and resubmit.Please refer to attached file for comments. | 2024-01-04 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 154 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1057 | 000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | B | 131242-WST02-DR-EP-1000-B | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
1058 | 000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | B | 131242-WST02-DR-EP-1001-B | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1059 | 000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | B | 131242-WST02-DR-EP-1002-B | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
1060 | 000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | B | 131242-WST02-DR-EP-1003-B | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
1061 | 000227 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | B | 131242-WST02-DR-EP-1004-B | 2024-08-13 | SSN Power Layout Plan | Rev 1: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 123 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1062 | 000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | C | 131242-WST02-DR-EP-1000-C | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 27 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
1063 | 000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | C | 131242-WST02-DR-EP-1001-C | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 27 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1064 | 000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | C | 131242-WST02-DR-EP-1002-C | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 27 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
1065 | 000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | C | 131242-WST02-DR-EP-1003-C | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 27 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
1066 | 000227 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | C | 131242-WST02-DR-EP-1004-C | 2025-04-10 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2025-04-30 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 27 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
1067 | 000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1000 | D | 131242-WST02-DR-EP-1000-D | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | PEN | PEN
1068 | 000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1001 | D | 131242-WST02-DR-EP-1001-D | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | PEN | PEN
1069 | 000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1002 | D | 131242-WST02-DR-EP-1002-D | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | PEN | PEN
1070 | 000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1003 | D | 131242-WST02-DR-EP-1003-D | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | PEN | PEN
1071 | 000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1004 | D | 131242-WST02-DR-EP-1004-D | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | PEN | PEN
1072 | 000227 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 1005 | D | 131242-WST02-DR-EP-1005-D | 2026-01-19 | SSN Power Layout Plan | Not Approved - Revise and resubmit | 2026-02-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | PEN | PEN
1073 | 000228 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | RT | C | 0001 | 0 | 131242-WSW41-RT-C-0001-0 | 2023-12-05 | UXO Scanning Report | Approved | 2024-01-04 | 2023-12-14 | For Information |  | YES | NA |  | 131242-WSW41-RT-0001 | NA | "1st CONSAAS Audit report_2023" && "Photographic Survey Report for C4B" && "UXO Scanning Report" | 2023-08-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2023-12-19 | 9 | INF | 2024-02-15 | 0 | 000078&&000228&&000314 | 2023-08-24, 2023-12-05, 2024-02-15 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
1074 | 000229 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 0 | 131242-WSW41-VI-M-0005-0 | 2023-12-05 | Preliminary Design and Vendor Approval of Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-04 | 2024-04-17 | Approved with Comments | 2024-05-08 | YES | Resubmitted | To provide Vendor drawings after PO issued. | 131242-WSW41-VI-0005 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-19 | 134 | AWC | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
1075 | 000229 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0005 | 1 | 131242-WSW41-VI-M-0005-1 | 2024-08-20 | Preliminary Design and Vendor Approval of Mixer | Rev 1: Approved | 2024-09-09 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-VI-0005 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-03 | 13 | APP | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
1076 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | 0 | 131242-WSD11-DR-P-6000-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted | To submit Detailed Design . Related to Detailed Design Report. | 131242-WSD11-DR-6000 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1077 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | 0 | 131242-WSD11-DR-P-6001-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6001 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1078 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | 0 | 131242-WSD11-DR-P-6002-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6002 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1079 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | 0 | 131242-WSD11-DR-P-6003-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6003 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1080 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | 0 | 131242-WSD11-DR-P-6004-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6004 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1081 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | 0 | 131242-WSD11-DR-P-6005-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6005 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1082 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | 0 | 131242-WSD11-DR-P-6006-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6006 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1083 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | 0 | 131242-WSD11-DR-P-6007-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6007 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1084 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | 0 | 131242-WSD11-DR-P-6008-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6008 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1085 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | 0 | 131242-WSD11-DR-P-6009-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6009 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1086 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | 0 | 131242-WSD11-DR-P-6010-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6010 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1087 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | 0 | 131242-WSD11-DR-P-6011-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6011 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1088 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | 0 | 131242-WSD11-DR-P-6012-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6012 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1089 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | 0 | 131242-WSD11-DR-P-6013-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6013 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1090 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | 0 | 131242-WSD11-DR-P-6014-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6014 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1091 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | 0 | 131242-WSD11-DR-P-6015-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6015 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1092 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | 0 | 131242-WSD11-DR-P-6016-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6016 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1093 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | 0 | 131242-WSD11-DR-P-6017-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6017 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1094 | 000230 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | 0 | 131242-WSD11-DR-P-6018-0 | 2023-12-06 | P&ID of THP Train 1 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-05 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6018 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 86 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1095 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | B | 131242-WSD11-DR-P-6000-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted | Heng Peng to provide DGN dwg | 131242-WSD11-DR-6000 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1096 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | B | 131242-WSD11-DR-P-6001-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6001 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1097 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | B | 131242-WSD11-DR-P-6002-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6002 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1098 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | B | 131242-WSD11-DR-P-6003-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6003 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1099 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | B | 131242-WSD11-DR-P-6004-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6004 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1100 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | B | 131242-WSD11-DR-P-6005-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6005 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1101 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | B | 131242-WSD11-DR-P-6006-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6006 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1102 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | B | 131242-WSD11-DR-P-6007-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6007 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1103 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | B | 131242-WSD11-DR-P-6008-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6008 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1104 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | B | 131242-WSD11-DR-P-6009-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6009 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1105 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | B | 131242-WSD11-DR-P-6010-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6010 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1106 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | B | 131242-WSD11-DR-P-6011-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6011 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1107 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | B | 131242-WSD11-DR-P-6012-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6012 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1108 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | B | 131242-WSD11-DR-P-6013-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6013 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1109 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | B | 131242-WSD11-DR-P-6014-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6014 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1110 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | B | 131242-WSD11-DR-P-6015-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6015 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1111 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | B | 131242-WSD11-DR-P-6016-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6016 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1112 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | B | 131242-WSD11-DR-P-6017-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6017 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1113 | 000230 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | B | 131242-WSD11-DR-P-6018-B | 2024-03-19 | P&ID of THP Train 1 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6018 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1114 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | C | 131242-WSD11-DR-P-6000-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6000 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1115 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | C | 131242-WSD11-DR-P-6001-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6001 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1116 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | C | 131242-WSD11-DR-P-6002-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6002 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1117 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | C | 131242-WSD11-DR-P-6003-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6003 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1118 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | C | 131242-WSD11-DR-P-6004-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6004 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1119 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | C | 131242-WSD11-DR-P-6005-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6005 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1120 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | C | 131242-WSD11-DR-P-6006-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6006 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1121 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | C | 131242-WSD11-DR-P-6007-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6007 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1122 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | C | 131242-WSD11-DR-P-6008-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6008 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1123 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | C | 131242-WSD11-DR-P-6009-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6009 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1124 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | C | 131242-WSD11-DR-P-6010-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6010 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1125 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | C | 131242-WSD11-DR-P-6011-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6011 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1126 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | C | 131242-WSD11-DR-P-6012-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6012 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1127 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | C | 131242-WSD11-DR-P-6013-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6013 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1128 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | C | 131242-WSD11-DR-P-6014-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6014 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1129 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | C | 131242-WSD11-DR-P-6015-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6015 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1130 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | C | 131242-WSD11-DR-P-6016-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6016 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1131 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | C | 131242-WSD11-DR-P-6017-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6017 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1132 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | C | 131242-WSD11-DR-P-6018-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6018 | NA | "P&ID of THP Train 1" | 2023-12-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1133 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | C | 131242-WSD11-DR-P-6019-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6019 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1134 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | C | 131242-WSD11-DR-P-6020-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6020 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1135 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | C | 131242-WSD11-DR-P-6021-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6021 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1136 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | C | 131242-WSD11-DR-P-6022-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6022 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1137 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | C | 131242-WSD11-DR-P-6023-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6023 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1138 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | C | 131242-WSD11-DR-P-6024-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6024 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1139 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | C | 131242-WSD11-DR-P-6025-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6025 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1140 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | C | 131242-WSD11-DR-P-6026-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6026 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1141 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | C | 131242-WSD11-DR-P-6027-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6027 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1142 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | C | 131242-WSD11-DR-P-6028-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6028 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1143 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | C | 131242-WSD11-DR-P-6029-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6029 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1144 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | C | 131242-WSD11-DR-P-6030-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6030 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1145 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | C | 131242-WSD11-DR-P-6031-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6031 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1146 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | C | 131242-WSD11-DR-P-6032-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6032 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1147 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | C | 131242-WSD11-DR-P-6033-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6033 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1148 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | C | 131242-WSD11-DR-P-6034-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6034 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1149 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | C | 131242-WSD11-DR-P-6035-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6035 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1150 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | C | 131242-WSD11-DR-P-6036-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6036 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1151 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | C | 131242-WSD11-DR-P-6050-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6050 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1152 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | C | 131242-WSD11-DR-P-6063-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6063 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1153 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | B | 131242-WSD11-DR-P-6070-B | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6070 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1154 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | C | 131242-WSD11-DR-P-6101-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6101 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2024-03-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2024-03-19, 2024-11-13, 2025-06-17 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1155 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | C | 131242-WSD11-DR-P-6121-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6121 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2024-03-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2024-03-19, 2024-11-13, 2025-06-17 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1156 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | C | 131242-WSD11-DR-P-6200-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6200 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1157 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | C | 131242-WSD11-DR-P-6300-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6300 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1158 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | C | 131242-WSD11-DR-P-6400-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6400 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1159 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | C | 131242-WSD11-DR-P-6600-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6600 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1160 | 000230 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | C | 131242-WSD11-DR-P-6601-C | 2024-11-13 | P&ID of THP Train 1 | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WSD11-DR-6601 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1161 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6000 | D | 131242-WSD11-DR-P-6000-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6000 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1162 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6001 | D | 131242-WSD11-DR-P-6001-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6001 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1163 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6002 | D | 131242-WSD11-DR-P-6002-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6002 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1164 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6003 | D | 131242-WSD11-DR-P-6003-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6003 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1165 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6004 | D | 131242-WSD11-DR-P-6004-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6004 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1166 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6005 | D | 131242-WSD11-DR-P-6005-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6005 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1167 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6006 | D | 131242-WSD11-DR-P-6006-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6006 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1168 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6007 | D | 131242-WSD11-DR-P-6007-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6007 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1169 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6008 | D | 131242-WSD11-DR-P-6008-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6008 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1170 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6009 | D | 131242-WSD11-DR-P-6009-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6009 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1171 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6010 | D | 131242-WSD11-DR-P-6010-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6010 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1172 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6011 | D | 131242-WSD11-DR-P-6011-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6011 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1173 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6012 | D | 131242-WSD11-DR-P-6012-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6012 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1174 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6013 | D | 131242-WSD11-DR-P-6013-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6013 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1175 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6014 | D | 131242-WSD11-DR-P-6014-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6014 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1176 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6015 | D | 131242-WSD11-DR-P-6015-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6015 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1177 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6016 | D | 131242-WSD11-DR-P-6016-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6016 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1178 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6017 | D | 131242-WSD11-DR-P-6017-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6017 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1179 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6018 | D | 131242-WSD11-DR-P-6018-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6018 | NA | "P&ID of THP Train 1" | 2023-12-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230 | 2023-12-06, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1180 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | D | 131242-WSD11-DR-P-6019-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6019 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1181 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | D | 131242-WSD11-DR-P-6020-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6020 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1182 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | D | 131242-WSD11-DR-P-6021-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6021 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1183 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | D | 131242-WSD11-DR-P-6022-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6022 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1184 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | D | 131242-WSD11-DR-P-6023-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6023 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1185 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | D | 131242-WSD11-DR-P-6024-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6024 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1186 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | D | 131242-WSD11-DR-P-6025-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6025 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1187 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | D | 131242-WSD11-DR-P-6026-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6026 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1188 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | D | 131242-WSD11-DR-P-6027-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6027 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1189 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | D | 131242-WSD11-DR-P-6028-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6028 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1190 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | D | 131242-WSD11-DR-P-6029-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6029 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1191 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | D | 131242-WSD11-DR-P-6030-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6030 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1192 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | D | 131242-WSD11-DR-P-6031-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6031 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1193 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | D | 131242-WSD11-DR-P-6032-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6032 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1194 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | D | 131242-WSD11-DR-P-6033-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6033 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1195 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | D | 131242-WSD11-DR-P-6034-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6034 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1196 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | D | 131242-WSD11-DR-P-6035-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6035 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1197 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | D | 131242-WSD11-DR-P-6036-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6036 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1198 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | D | 131242-WSD11-DR-P-6050-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6050 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1199 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6051 | D | 131242-WSD11-DR-P-6051-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6051 | NA | "P&ID of THP Train 1" | 2025-06-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-07 | 72 | AWC | 2025-06-17 | D | 000230 | 2025-06-17 | 03 | 1 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1200 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | D | 131242-WSD11-DR-P-6063-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6063 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1201 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | D | 131242-WSD11-DR-P-6070-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6070 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1202 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | D | 131242-WSD11-DR-P-6101-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6101 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2024-03-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2024-03-19, 2024-11-13, 2025-06-17 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1203 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | D | 131242-WSD11-DR-P-6121-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6121 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2024-03-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2024-03-19, 2024-11-13, 2025-06-17 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1204 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | D | 131242-WSD11-DR-P-6200-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6200 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1205 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | D | 131242-WSD11-DR-P-6300-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6300 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1206 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | D | 131242-WSD11-DR-P-6400-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6400 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1207 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | D | 131242-WSD11-DR-P-6600-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6600 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1208 | 000230 | 03 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | D | 131242-WSD11-DR-P-6601-D | 2025-06-17 | P&ID of THP Train 1 | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-07 | 2025-08-28 | Approved with Comments | 2025-09-17 | NO | Overdue |  | 131242-WSD11-DR-6601 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-01 | 72 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-09-17 | Overdue | 0 | AWC | AWC
1209 | 000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-S-1000_ST604_BCA-A1 | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | Approved with Comments | 2024-01-18 | YES | Resubmitted |  | 131242-WST00-DR-1000_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-27 | 21 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1210 | 000231 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST604_BCA | A1 | 131242-WST02-DR-S-1001_ST604_BCA-A1 | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | Approved with Comments | 2024-01-18 | YES | Resubmitted |  | 131242-WST02-DR-1001_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-27 | 21 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1211 | 000231 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST604_BCA | A1 | 131242-WST02-DR-S-5001_ST604_BCA-A1 | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | Approved with Comments | 2024-01-18 | YES | Resubmitted |  | 131242-WST02-DR-5001_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-27 | 21 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1212 | 000231 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | A1 | 131242-WST00-DR-C-8000_ST604_BCA-A1 | 2023-12-07 | ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-08 | 2023-12-28 | Approved with Comments | 2024-01-18 | YES | Resubmitted |  | 131242-WST00-DR-8000_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-27 | 21 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1213 | 000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 1000_ST604_BCA | A1 | 131242-WST00-DR-S-1000_ST604_BCA-A1 | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-05 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue | Heng Peng to provide latest DGN & PDF drawing | 131242-WST00-DR-1000_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1214 | 000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604_BCA | A1 | 131242-WST02-DR-C-1001_ST604_BCA-A1 | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue |  | 131242-WST02-DR-1001_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1215 | 000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604_BCA | A1 | 131242-WST02-DR-C-1002_ST604_BCA-A1 | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue |  | 131242-WST02-DR-1002_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-05 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2024-01-16 | 01 | 1 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1216 | 000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604_BCA | A1 | 131242-WST02-DR-C-5001_ST604_BCA-A1 | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue |  | 131242-WST02-DR-5001_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1217 | 000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604_BCA | A1 | 131242-WST02-DR-C-7000_ST604_BCA-A1 | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue |  | 131242-WST02-DR-7000_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-05 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2024-01-16 | 01 | 1 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1218 | 000231 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8000_ST604_BCA | A1 | 131242-WST00-DR-C-8000_ST604_BCA-A1 | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue |  | 131242-WST00-DR-8000_ST604_BCA | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" && "ST604_ SSN Piling Layout of Minor Buildings (BCA Submission for Information)" | 2023-12-07 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2023-12-07, 2024-01-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1219 | 000231 | 01 | Zora/ HP | CSA | NA | A1798-00002-2018-ST604_NOA | NA | NA | NA | 9999 | A1 | A1798-00002-2018-ST604_NOA----- | 2024-01-16 | ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. BIM Comments as per Submittal 000079 were not addressed and was not reflected to drawings for BCA Approval. | 2024-02-14 | 2024-02-14 | Approved with Comments | 2024-03-05 | NO | Overdue |  | A1798-00002-2018-ST604_NOA-NA-NA-9999 | NA | "ST604_ SSN Piling Layout of Minor Buildings (BCA Approved Drawings for Information)" | 2024-01-16 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-05 | 29 | AWC | 2024-01-16 | A1 | 000231 | 2024-01-16 | 01 | 1 | Approved with Comments | AWC | 2024-03-05 | Overdue | 0 | AWC | AWC
1220 | 000232 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 0 | 131242-WSW41-VI-M-0007-0 | 2023-12-08 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-01-09 | 2024-02-26 | Approved with Comments | 2024-03-15 | YES | Resubmitted | Yibo WIP | 131242-WSW41-VI-0007 | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-22 | 80 | AWC | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1221 | 000232 | 01 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 1 | 131242-WSW41-VI-M-0007-1 | 2024-07-29 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-19 | 2024-09-02 | Approved with Comments | 2024-09-20 | YES | Resubmitted | In progress. Only one ICA comment is open (s/n.19), will reconfirm with ICA team, Try resubmit in 1 week. | 131242-WSW41-VI-0007 | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-12 | 35 | AWC | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1222 | 000232 | 02 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0007 | 2 | 131242-WSW41-VI-M-0007-2 | 2025-02-28 | Preliminary Design and Vendor Approval For Chemical Dosing Pumps | Rev 2: Approved | 2025-03-20 | 2025-11-24 | Approved |  | YES | NA |  | 131242-WSW41-VI-0007 | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-14 | 269 | APP | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
1223 | 000233 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0012 | 0 | 131242-WSW41-CD-IM-0012-0 | 2023-12-08 | Submission Of BIM Coordination VCM Model (Nov – 2023) | For Information | 2024-01-09 | 2023-12-26 | For Information |  | YES | NA |  | 131242-WSW41-CD-0012 | NA | "Submission Of BIM Coordination VCM Model (Nov – 2023)" | 2023-12-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2023-12-28 | 18 | INF | 2023-12-08 | 0 | 000233 | 2023-12-08 | 00 | 1 | For Information | INF | 2024-01-15 | Overdue | 0 | INF | INF
1224 | 000234 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0007 | 0 | 131242-WSW41-RT-PM-0007-0 | 2023-12-11 | C4B Monthly Progress Report Number No.07 (11/23) | Rev. 0 - Approved with comments (need to re-submit) | 2024-01-10 | 2023-12-18 | Approved with Comments | 2024-01-09 | NO | Overdue |  | 131242-WSW41-RT-0007 | NA | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" && "C4B Monthly Progress Report Number No.07 (11/23)" | 2023-12-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-31 | 7 | AWC | 2024-09-06 | 0 | 000234&&000713 | 2023-12-11, 2024-09-06 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
1225 | 000235 | 00 | Zora | CSA | NA | 131242 | WSW41 | RT | C | 0002 | 0 | 131242-WSW41-RT-C-0002-0 | 2023-12-12 | ULT Test Report of 600mm Dia. Bored Pile | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-11 | 2023-12-18 | Approved with Comments | 2024-01-09 | YES | Resubmitted |  | 131242-WSW41-RT-0002 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 6 | AWC | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | For Information | INF |  |  | 0 | AWC | AWC
1226 | 000235 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0002 | 1 | 131242-WSW41-RT-C-0002-1 | 2023-12-22 | ULT Test Report of 600mm Dia. Bored Pile | Approved with comments. Please refer to comment sheet for resubmission. | 2024-01-15 | 2024-01-16 | Approved with Comments | 2024-02-05 | NO | Overdue |  | 131242-WSW41-RT-0002 | NA | "C4B Monthly Progress Report Number No.02 (06/23)" && "Cable Detection Report" && "Final Investigation Report (Incident on Leg Injury)" && "ULT Test Report of 600mm Dia. Bored Pile " | 2023-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-05 | 25 | AWC | 2025-01-16 | 0 | 000046&&000091&&000235&&000981 | 2023-07-12, 2023-07-14, 2023-09-07, 2023-12-12, 2023-12-22, 2025-01-16 | 00, 01 | 6 | For Information | INF |  |  | 0 | AWC | AWC
1227 | 000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | A | 131242-WSD11-DR-E-1100-A | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | Approved with Comments | 2024-04-11 | YES | Resubmitted |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-01 | 99 | AWC | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
1228 | 000236 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | A | 131242-WSD11-DR-E-1101-A | 2023-12-12 | THP Earthing Layout Plan | Rev 0: Approved with Comments. To revise and resubmit. Please refer to comment sheet for resubmission. | 2024-01-11 | 2024-03-20 | Approved with Comments | 2024-04-11 | YES | Resubmitted |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-01 | 99 | AWC | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | AWC | AWC
1229 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 116 | AWC | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
1230 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 116 | AWC | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | AWC | AWC
1231 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1102 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 116 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1232 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1103 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 116 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1233 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1104 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 116 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1234 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1105 | B | 131242-WSD11-DR-E-1105-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1105 | NA | "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 116 | AWC | 2025-05-28 | A | 000236&&001328 | 2024-08-13, 2025-03-28, 2025-05-28 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1235 | 000236 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1106 | B | 131242-WSD11-DR-E-1106-B | 2024-08-13 | THP Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-12-07 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-DR-1106 | NA | "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 116 | AWC | 2025-05-28 | A | 000236&&001328 | 2024-08-13, 2025-03-28, 2025-05-28 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1236 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1100 | C | 131242-WSD11-DR-E-1100-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
1237 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1101 | C | 131242-WSD11-DR-E-1101-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | AWC | AWC
1238 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1102 | C | 131242-WSD11-DR-E-1102-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1102 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1239 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1103 | C | 131242-WSD11-DR-E-1103-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1103 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1240 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1104 | C | 131242-WSD11-DR-E-1104-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1104 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1241 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1105 | C | 131242-WSD11-DR-E-1105-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1105 | NA | "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-05-28 | A | 000236&&001328 | 2024-08-13, 2025-03-28, 2025-05-28 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1242 | 000236 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 1106 | C | 131242-WSD11-DR-E-1106-C | 2025-03-28 | THP Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-DR-1106 | NA | "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-11 | 39 | AWC | 2025-05-28 | A | 000236&&001328 | 2024-08-13, 2025-03-28, 2025-05-28 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1243 | 000237 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0001 | 0 | 131242-WST02-VI-E-0001-0 | 2023-12-12 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | Not Approved. To revise and resubmit. Please refer to comment sheet | 2024-01-11 | 2024-01-24 | Not Approved | 2024-02-14 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-26 | 43 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
1244 | 000237 | 01 | Freedomer | EICA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S237.0 2024 07 22 | 0 | 131242----Cmt Sheet Reply S237.0 2024 07 22- | 2024-07-22 | Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM) | R1: Rejected as requested by C4B | 2024-08-12 | 2024-08-02 | Not Approved |  | YES | NA |  | 131242-NA-NA-Cmt Sheet Reply S237.0 2024 07 22 | NA | "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" | 2024-07-22 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-11 | 11 | NAP | 2024-07-22 | 0 | 000237 | 2024-07-22 | 01 | 1 | Not Approved | NAP | 2024-08-22 | Overdue | 0 | NAP | NAP
1245 | 000238 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 0 | 131242-WSW41-VI-M-1000-0 | 2023-12-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Not Approved. To revise and resubmit. | 2024-01-15 | 2024-02-19 | Not Approved | 2024-03-08 | YES | Resubmitted |  | 131242-WSW41-VI-1000 | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-03 | 67 | NAP | 2024-08-07 | 2 | 000238 | 2023-12-14, 2024-03-14, 2024-08-07 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
1246 | 000238 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 1 | 131242-WSW41-VI-M-1000-1 | 2024-03-14 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-04 | 2024-04-17 | Approved with Comments | 2024-05-08 | YES | Resubmitted |  | 131242-WSW41-VI-1000 | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-28 | 34 | AWC | 2024-08-07 | 2 | 000238 | 2023-12-14, 2024-03-14, 2024-08-07 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
1247 | 000238 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1000 | 2 | 131242-WSW41-VI-M-1000-2 | 2024-08-07 | Preliminary design and Vendor Approval – Stainless Steel Piping (AII) | Rev 2: Approved | 2024-08-28 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-VI-1000 | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (AII)" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 26 | APP | 2024-08-07 | 2 | 000238 | 2023-12-14, 2024-03-14, 2024-08-07 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
1248 | 000239 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 0 | 131242-WSW41-VI-M-1002-0 | 2023-12-14 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-02-19 | Not Approved | 2024-03-08 | YES | Resubmitted |  | 131242-WSW41-VI-1002 | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-03 | 67 | NAP | 2024-04-02 | 1 | 000239 | 2023-12-14, 2024-04-02 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1249 | 000239 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1002 | 1 | 131242-WSW41-VI-M-1002-1 | 2024-04-02 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. Please note, that the approval, corresponds to the brand/manufacturer proposed by contractor in this submittal. Approval does not include assessment for Trader/Distributor. | 2024-04-23 | 2024-04-15 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1002 | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (E Steel)" | 2023-12-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-16 | 13 | AWC | 2024-04-02 | 1 | 000239 | 2023-12-14, 2024-04-02 | 00, 01 | 2 | Approved with Comments | AWC | 2024-05-03 | Overdue | 0 | AWC | AWC
1250 | 000240 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0015 | 0 | 131242-WSW41-MI-C-0015-0 | 2023-12-14 | CSA Meeting Minutes 0015_20231116 | For Information | 2024-01-15 | 2024-01-25 | For Information |  | YES | NA |  | 131242-WSW41-MI-0015 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-03 | 42 | INF | 2024-09-04 | 0 | 000240&&000259&&000268&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1251 | 000241 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0001 | 0 | 131242-WST02-VI-I-0001-0 | 2023-12-14 | Preliminary design and Vendor Approval – SSN Package (ICA) | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-26 | Not Approved | 2024-02-16 | YES | Resubmitted |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-28 | 43 | NAP | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | NAP | NAP
1252 | 000241 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0001 | 1 | 131242-WST02-VI-I-0001-1 | 2024-05-02 | Preliminary design and Vendor Approval – SSN Package (ICA) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-23 | 2024-06-18 | Approved with Comments | 2024-07-08 | NO | Overdue | Pending from MP | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-16 | 47 | AWC | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | AWC | AWC
1253 | 000242 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 0 | 131242-WSD11-DS-I-0003-0 | 2023-12-14 | THP PLC RIO Component Datasheet | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | Not Approved | 2024-02-21 | YES | Resubmitted |  | 131242-WSD11-DS-0003 | NA | "THP PLC RIO Component Datasheet" && "THP and SSN Earthing Material Specifications" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-03 | 48 | NAP | 2026-01-12 | 0 | 000242&&001948 | 2023-12-14, 2024-03-11, 2026-01-12 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1254 | 000242 | 01 | Low | EICA | NA | 131242 | WSD11 | DS | I | 0003 | 1 | 131242-WSD11-DS-I-0003-1 | 2024-03-11 | THP PLC RIO Component Datasheet | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-01 | 2024-05-15 | Not Approved | 2024-06-05 | NO | Overdue |  | 131242-WSD11-DS-0003 | NA | "THP PLC RIO Component Datasheet" && "THP and SSN Earthing Material Specifications" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 65 | NAP | 2026-01-12 | 0 | 000242&&001948 | 2023-12-14, 2024-03-11, 2026-01-12 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1255 | 000243 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 0 | 131242-WSD11-CH-I-0001-0 | 2023-12-14 | THP IO List | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-15 | 2024-01-31 | Not Approved | 2024-02-21 | YES | Resubmitted |  | 131242-WSD11-CH-0001 | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2023-12-28 | 48 | NAP | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1256 | 000243 | 01 | Low | EICA | NA | 131242 | WSD11 | CH | I | 0001 | 1 | 131242-WSD11-CH-I-0001-1 | 2024-07-16 | THP IO List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. To revise and resubmit. | 2024-08-05 | 2024-09-17 | Not Approved | 2024-10-07 | NO | Overdue |  | 131242-WSD11-CH-0001 | NA | "Process Functional Description" && "THP IO List" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 63 | NAP | 2024-09-30 | 3 | 000141&&000243 | 2023-10-25, 2023-12-14, 2024-04-02, 2024-07-16, 2024-07-28, 2024-09-30 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1257 | 000244 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | B | 0004 | 0 | 131242-WST02-CL-B-0004-0 | 2023-12-14 | Heat Load Calculation Report for ACMV | Rev 0: Not approved - Revise and Resubmit | 2024-01-15 | 2024-03-12 | Not Approved | 2024-04-02 | YES | Resubmitted |  | 131242-WST02-CL-0004 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-03 | 89 | NAP | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1258 | 000244 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 0 | 131242-WST02-CL-BH-8001-0 | 2024-05-14 | Heat Load Calculation Report for ACMV | Not approved - Revise and Resubmit | 2024-06-04 | 2024-08-14 | Not Approved | 2024-09-03 | YES | Resubmitted |  | 131242-WST02-CL-8001 | NA | "Engineering Calculation Report for Fire Hydrant Pipe" && "Heat Load Calculation Report for ACMV" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 92 | NAP | 2025-03-20 | 2 | 000193&&000244 | 2024-04-04, 2024-05-14, 2025-03-20 | 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
1259 | 000244 | 02 | Kyaw Myo | BS | NA | 131242 | WST02 | CL | BH | 8001 | 2 | 131242-WST02-CL-BH-8001-2 | 2025-03-20 | Heat Load Calculation Report for ACMV | Rev 2: Approved | 2025-04-09 | 2025-05-25 | Approved |  | YES | NA | Doc name duplicate with S#193, Fire Hydrant Calculation/ Pending by EICA info and C2D . Freedomer follow up | 131242-WST02-CL-8001 | NA | "Engineering Calculation Report for Fire Hydrant Pipe" && "Heat Load Calculation Report for ACMV" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-03 | 66 | APP | 2025-03-20 | 2 | 000193&&000244 | 2024-04-04, 2024-05-14, 2025-03-20 | 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
1260 | 000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | A | 131242-WST02-DR-E-1100-A | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1100 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-07 | 60 | NAP | 2025-02-25 | B_endorsed | 000161&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1261 | 000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | A | 131242-WST02-DR-E-1101-A | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1101 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-07 | 60 | NAP | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1262 | 000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | A | 131242-WST02-DR-E-1102-A | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1102 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-07 | 60 | NAP | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1263 | 000245 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1103 | A | 131242-WST02-DR-E-1103-A | 2023-12-18 | SSN Earthing Layout Plan | Not Approved. To revise and resubmit. Refer to comments sheet. | 2024-01-17 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WST02-DR-1103 | NA | "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-07 | 60 | NAP | 2025-08-19 | B | 000245&&001146 | 2023-12-18, 2025-03-21, 2025-08-19 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1264 | 000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B | 131242-WST02-DR-E-1100-B | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | Approved with Comments | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-1100 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 50 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1265 | 000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | B | 131242-WST02-DR-E-1101-B | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | Approved with Comments | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-1101 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 50 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1266 | 000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | B | 131242-WST02-DR-E-1102-B | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | Approved with Comments | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-1102 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 50 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1267 | 000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7750 | B | 131242-WST02-DR-E-7750-B | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | Approved with Comments | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-7750 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 50 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1268 | 000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7751 | B | 131242-WST02-DR-E-7751-B | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | Approved with Comments | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-7751 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 50 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1269 | 000245 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7752 | B | 131242-WST02-DR-E-7752-B | 2024-06-11 | SSN Earthing Layout Plan | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-02 | 2024-07-31 | Approved with Comments | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-7752 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 50 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1270 | 000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1100 | B_endorsed | 131242-WST02-DR-E-1100-B_endorsed | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DR-1100 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2023-12-18 | NO | YES | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
1271 | 000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1101 | B_endorsed | 131242-WST02-DR-E-1101-B_endorsed | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DR-1101 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1272 | 000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 1102 | B_endorsed | 131242-WST02-DR-E-1102-B_endorsed | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DR-1102 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" && "SSN RIO 0001B GA & Wiring Diagram" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2025-08-19 | B | 000161&&000245&&001146 | 2023-12-18, 2024-06-11, 2024-10-05, 2025-02-25, 2025-03-21, 2025-08-19 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1273 | 000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7750 | B_endorsed | 131242-WST02-DR-E-7750-B_endorsed | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DR-7750 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
1274 | 000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7751 | B_endorsed | 131242-WST02-DR-E-7751-B_endorsed | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DR-7751 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
1275 | 000245 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7752 | B_endorsed | 131242-WST02-DR-E-7752-B_endorsed | 2025-02-25 | SSN Earthing Layout Plan | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WST02-DR-7752 | NA | "Milestone 2 Underground Services" && "SSN Earthing Layout Plan" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2025-02-25 | B_endorsed | 000161&&000245 | 2024-06-11, 2024-10-05, 2025-02-25 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-05-23 | Overdue | 0 | AWC | AWC
1276 | 000246 | 00 | Lilian | PMT | NA | 131242 | WSW41 | LT | PM | 0017 | 0 | 131242-WSW41-LT-PM-0017-0 | 2023-12-18 | THP Layout and Code Compliance | As requested by contractor via email dated 5 Feb 24 to withdraw the submission. | 2024-01-17 | 2024-02-06 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WSW41-LT-0017 | NA | "THP Layout and Code Compliance" | 2023-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2024-01-07 | 50 | VOID | 2023-12-18 | 0 | 000246 | 2023-12-18 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
1277 | 000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1011 | 0 | 131242-WSW41-SD-S-1011-0 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | Not Approved | 2024-02-02 | NO | Overdue | Zora checking comment sheet | 131242-WSW41-SD-1011 | NA | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-10 | 25 | NAP | 2023-12-21 | 0 | 000247 | 2023-12-21 | 00 | 1 | Not Approved | NAP | 2024-02-02 | Overdue | 0 | NAP | NAP
1278 | 000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1012 | 0 | 131242-WSW41-SD-S-1012-0 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | Not Approved | 2024-02-02 | NO | Overdue |  | 131242-WSW41-SD-1012 | NA | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-10 | 25 | NAP | 2023-12-21 | 0 | 000247 | 2023-12-21 | 00 | 1 | Not Approved | NAP | 2024-02-02 | Overdue | 0 | NAP | NAP
1279 | 000247 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SD | S | 1013 | 0 | 131242-WSW41-SD-S-1013-0 | 2023-12-21 | WSW41-PR-02 Column coordinates with Cast in Bolt Details | Not approved. Please refer to comment sheet for resubmission. | 2024-01-22 | 2024-01-15 | Not Approved | 2024-02-02 | NO | Overdue |  | 131242-WSW41-SD-1013 | NA | "WSW41-PR-02 Column coordinates with Cast in Bolt Details " | 2023-12-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-10 | 25 | NAP | 2023-12-21 | 0 | 000247 | 2023-12-21 | 00 | 1 | Not Approved | NAP | 2024-02-02 | Overdue | 0 | NAP | NAP
1280 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-8000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1281 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-0001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1282 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-0002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1283 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1284 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1285 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1286 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1003_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1287 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1004_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1288 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | CL | G | 0001_ST601 | A | 131242-WST00-CL-G-0001_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-CL-0001_ST601 | NA | "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2023-12-22 | A | 000248 | 2023-12-22 | 00 | 1 | Not Approved | NAP | 2024-02-05 | Overdue | 0 | NAP | NAP
1289 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601-A | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-3000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1290 | 000248 | 00 | Zora | CSA | NA | 131242 | WST00 | CH | IM | 0003_ST601 | A | 131242-WST00-CH-IM-0003_ST601- | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-CH-0003_ST601 | NA | "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2023-12-22 | A | 000248 | 2023-12-22 | 00 | 1 | Not Approved | NAP | 2024-02-05 | Overdue | 0 | NAP | NAP
1291 | 000248 | 00 | Zora | CSA | NA | DGN FILES | NA | NA | NA | 9999 | A | DGN FILES----- | 2023-12-22 | ST601 – ERSS Design < 4m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | DGN FILES-NA-NA-9999 | NA | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2023-12-22 | A | 000248&&000249 | 2023-12-22 | 00 | 2 | Not Approved | NAP | 2024-02-05 | Overdue | 0 | NAP | NAP
1292 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-0001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1293 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-0002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1294 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1295 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1296 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1297 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1003_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1298 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1004_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1299 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-8000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
1300 | 000248 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601-A | 2024-02-24 | ST601 – ERSS Design < 4m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-3000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1301 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | A | 131242-WST00-DR-G-0001_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-06 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue | Heng Peng to clear BIM comments. Pending BIM updates | 131242-WST00-DR-0001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
1302 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | A | 131242-WST00-DR-G-0002_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-0002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
1303 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | A | 131242-WST00-DR-G-1000_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-1000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
1304 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | A | 131242-WST00-DR-G-1001_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-1001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1305 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | A | 131242-WST00-DR-G-1002_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-1002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1306 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | A | 131242-WST00-DR-G-1003_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-1003_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1307 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | A | 131242-WST00-DR-G-1004_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-1004_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
1308 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | A | 131242-WST00-DR-G-8000_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-8000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
1309 | 000248 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | A | 131242-WST00-DR-G-3000_ST601-A | 2024-04-15 | ST601 – ERSS Design < 4m Depth | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-14 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST00-DR-3000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 35 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | AWC | AWC
1310 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST602 | A | 131242-WST00-DR-C-8001_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1311 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-0100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1312 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-0101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1313 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1314 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1315 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-1102_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1316 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | CL | G | 0002_ST602 | A | 131242-WST00-CL-G-0002_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-CL-0002_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2023-12-22 | A | 000249 | 2023-12-22 | 00 | 1 | Not Approved | NAP | 2024-02-05 | Overdue | 0 | NAP | NAP
1317 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602-A | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-DR-3100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1318 | 000249 | 00 | Zora | CSA | NA | 131242 | WST00 | CH | IM | 0004_ST602 | A | 131242-WST00-CH-IM-0004_ST602- | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | 131242-WST00-CH-0004_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2023-12-22 | A | 000249 | 2023-12-22 | 00 | 1 | Not Approved | NAP | 2024-02-05 | Overdue | 0 | NAP | NAP
1319 | 000249 | 00 | Zora | CSA | NA | DGN FILES | NA | NA | NA | 9999 | A | DGN FILES----- | 2023-12-22 | ST602 – ERSS Design < 6m Depth | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2024-01-23 | 2024-01-16 | Not Approved | 2024-02-05 | YES | Resubmitted |  | DGN FILES-NA-NA-9999 | NA | "ST601 – ERSS Design < 4m Depth" && "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-11 | 25 | NAP | 2023-12-22 | A | 000248&&000249 | 2023-12-22 | 00 | 2 | Not Approved | NAP | 2024-02-05 | Overdue | 0 | NAP | NAP
1320 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-G-8001_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-14 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1321 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-0100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1322 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-0101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1323 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1324 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1325 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-1102_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1326 | 000249 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602-A | 2024-02-24 | ST602 – ERSS Design < 6m Depth | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-22 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST00-DR-3100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-09 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1327 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A | 131242-WST00-DR-G-8001_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-11 | 2024-07-01 | Approved with Comments | 2024-07-19 | YES | Resubmitted | Pending Tenwit update. (Roobin) | 131242-WST00-DR-8001_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | AWC | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
1328 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A | 131242-WST00-DR-G-0100_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-0100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1329 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A | 131242-WST00-DR-G-0101_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-0101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1330 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A | 131242-WST00-DR-G-1100_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-1100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1331 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A | 131242-WST00-DR-G-1101_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-1101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1332 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A | 131242-WST00-DR-G-1102_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-1102_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1333 | 000249 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A | 131242-WST00-DR-G-3100_ST602-A | 2024-06-21 | ST602 – ERSS Design < 6m Depth | Rev.2: Approved with comment. Please refer to comment sheet for resubmission | 2024-07-19 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-3100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 10 | NAP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
1334 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602 | A.1 | 131242-WST00-DR-G-8001_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA | R2_APP | 131242-WST00-DR-8001_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1335 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602 | A.1 | 131242-WST00-DR-G-0100_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST00-DR-0100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1336 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602 | A.1 | 131242-WST00-DR-G-0101_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST00-DR-0101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1337 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602 | A.1 | 131242-WST00-DR-G-1100_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST00-DR-1100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1338 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602 | A.1 | 131242-WST00-DR-G-1101_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST00-DR-1101_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1339 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1102_ST602 | A.1 | 131242-WST00-DR-G-1102_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST00-DR-1102_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1340 | 000249 | 03 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602 | A.1 | 131242-WST00-DR-G-3100_ST602-A.1 | 2024-07-02 | ST602 – ERSS Design < 6m Depth | Rev.3: Approved | 2024-07-22 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST00-DR-3100_ST602 | NA | "ST602 – ERSS Design < 6m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-07-16 | 15 | APP | 2024-07-02 | A.1 | 000249 | 2023-12-22, 2024-02-24, 2024-06-21, 2024-07-02 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
1341 | 000250 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0001 | 0 | 131242-WSW41-VI-M-0001-0 | 2023-12-22 | Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-01-23 | 2024-02-26 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0001 | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-05 | 66 | AWC | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1342 | 000251 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 0 | 131242-WST02-BQ-I-0001-0 | 2023-12-26 | C4B SSN PLC/ RIO Panel Component Catalogue | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-24 | 2024-01-29 | Not Approved | 2024-02-19 | YES | Resubmitted |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-09 | 34 | NAP | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1343 | 000251 | 01 | Low | EICA | NA | 131242 | WST02 | BQ | I | 0001 | 1 | 131242-WST02-BQ-I-0001-1 | 2024-04-08 | C4B SSN PLC/ RIO Panel Component Catalogue | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-29 | 2024-05-15 | Not Approved | 2024-06-05 | NO | Overdue | Pending from MP | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 37 | NAP | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1344 | 000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | A | 131242-WSW41-DR-EK-1000-A | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-10 | 51 | NAP | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1345 | 000252 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | A | 131242-WSW41-DR-EK-3000-A | 2023-12-27 | Sitewide Piperack Lightning Protection System | Not Approved. To revise and resubmit. Refer to the comment sheet | 2024-01-25 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-16 | 51 | NAP | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1346 | 000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | B | 131242-WSW41-DR-EK-1000-B | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 66 | AWC | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1347 | 000252 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | B | 131242-WSW41-DR-EK-3000-B | 2024-07-06 | Sitewide Piperack Lightning Protection System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2024-07-25 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 66 | AWC | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1348 | 000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 1000 | C | 131242-WSW41-DR-EK-1000-C | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 70 | AWC | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1349 | 000252 | 02 | Freedomer | EICA | NA | 131242 | WSW41 | DR | EK | 3000 | C | 131242-WSW41-DR-EK-3000-C | 2025-02-25 | Sitewide Piperack Lightning Protection System | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached for comments. | 2025-03-17 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 70 | AWC | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1350 | 000253 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0013 | 0 | 131242-WSW41-MI-P-0013-0 | 2023-12-27 | Process & MEICA Meeting Minutes 0013_20231123 | Rev 0: For Information | 2024-01-25 | 2024-05-21 | For Information |  | YES | NA | Waiting for C2D reply | 131242-WSW41-MI-0013 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" | 2023-11-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-10 | 146 | INF | 2024-08-07 | 0 | 000184&&000226&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1351 | 000254 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0018 | 0 | 131242-WSW41-LT-PM-0018-0 | 2023-12-28 | CV of WSHS | Approved | 2024-01-26 | 2024-02-14 | Approved |  | YES | NA |  | 131242-WSW41-LT-0018 | NA | "CV of WSHS" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-17 | 48 | APP | 2023-12-28 | 0 | 000254 | 2023-12-28 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1352 | 000255 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0011 | 0 | 131242-WSD11-CD-IM-0011-0 | 2023-12-28 | Submission of Milestone 1.1 THP MCC Room | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-01-26 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-CD-0011 | NA | "Submission of Milestone 1.1 THP MCC Room" | 2023-12-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-17 | 91 | AWC | 2023-12-28 | 0 | 000255 | 2023-12-28 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
1353 | 000255 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-IM-0034-0 | 2024-06-04 | Milestone 1.2 THP MCC Room | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-CD-0034 | NA | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-24 | 184 | AWC | 2025-10-31 | 1 | 000255 | 2024-06-04, 2025-02-26, 2025-10-31 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1354 | 000255 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 0 | 131242-WSD11-CD-IM-0034-0 | 2025-02-26 | Milestone 2 THP MCC Room | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-CD-0034 | NA | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 126 | AWC | 2025-10-31 | 1 | 000255 | 2024-06-04, 2025-02-26, 2025-10-31 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1355 | 000255 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0034 | 1 | 131242-WSD11-CD-IM-0034-1 | 2025-10-31 | Milestone 3 THP MCC Room | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-CD-0034 | NA | "Milestone 1.2 THP MCC Room" && "Milestone 2 THP MCC Room" && "Milestone 3 THP MCC Room" | 2024-06-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-14 | 115 | AWC | 2025-10-31 | 1 | 000255 | 2024-06-04, 2025-02-26, 2025-10-31 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1356 | 000256 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | CT | W | 0003 | 0 | 131242-WSW41-CT-W-0003-0 | 2023-12-28 | On-Demand Bond for SSN | Approved. Address as per Chin Swee Rd address as the bond was submitted (in Nov 2023) was prior to the notice (in Dec 2023) of change of address. | 2024-01-26 | 2024-01-16 | Approved |  | YES | NA |  | 131242-WSW41-CT-0003 | NA | "On-Demand Bond for SSN" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-17 | 19 | APP | 2023-12-28 | 0 | 000256 | 2023-12-28 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1357 | 000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6200 | 0 | 131242-WSD11-DR-P-6200-0 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted | Related to Detailed Design Report. | 131242-WSD11-DR-6200 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-17 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1358 | 000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6300 | 0 | 131242-WSD11-DR-P-6300-0 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6300 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-17 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1359 | 000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6400 | 0 | 131242-WSD11-DR-P-6400-0 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6400 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-17 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1360 | 000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6600 | 0 | 131242-WSD11-DR-P-6600-0 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6600 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-17 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1361 | 000257 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6601 | 0 | 131242-WSD11-DR-P-6601-0 | 2023-12-28 | P&ID of THP General System | Rev 0: Approved with Comments. To revise and resubmit. | 2024-01-26 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6601 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-17 | 64 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1362 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6200 | B | 131242-WSD11-DR-P-6200-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue | Heng Peng to provide DGN dwg | 131242-WSD11-DR-6200 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1363 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6300 | B | 131242-WSD11-DR-P-6300-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6300 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1364 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6400 | B | 131242-WSD11-DR-P-6400-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6400 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1365 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6600 | B | 131242-WSD11-DR-P-6600-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6600 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1366 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6601 | B | 131242-WSD11-DR-P-6601-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6601 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2023-12-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2023-12-28, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1367 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6101 | B | 131242-WSD11-DR-P-6101-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6101 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2024-03-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-08 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2024-03-19, 2024-11-13, 2025-06-17 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1368 | 000257 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6121 | B | 131242-WSD11-DR-P-6121-B | 2024-03-19 | P&ID of THP General System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6121 | NA | "P&ID of THP General System" && "P&ID of THP Train 1" | 2024-03-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-08 | 37 | AWC | 2025-06-17 | D | 000230&&000257 | 2024-03-19, 2024-11-13, 2025-06-17 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1369 | 000258 | 00 | Yi Hao | Contracts | NA | 131242 | WST02 | PO | P | 0001 | 0 | 131242-WST02-PO-P-0001-0 | 2024-01-03 | Unpriced PO for SSN Package (MattenPlant) | For Information | 2024-01-31 | 2024-04-26 | For Information |  | YES | NA |  | 131242-WST02-PO-0001 | NA | "Unpriced PO for SSN Package (MattenPlant)" | 2024-01-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-01-23 | 114 | INF | 2024-01-03 | 0 | 000258 | 2024-01-03 | 00 | 1 | For Information | INF | 2024-05-16 | Overdue | 0 | INF | INF
1370 | 000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0014 | 0 | 131242-WSW41-MI-P-0014-0 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0014 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-17 | 139 | INF | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1371 | 000259 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0015 | 0 | 131242-WSW41-MI-P-0015-0 | 2024-01-03 | Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221 | Rev 0: For Information | 2024-01-31 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0015 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-17 | 139 | INF | 2024-09-04 | 0 | 000240&&000259&&000268&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1372 | 000260 | 00 | Nicolas | BIM | NA | 131242 | WST02 | CD | IM | 0013 | 0 | 131242-WST02-CD-IM-0013-0 | 2024-01-05 | Milestone 1.1 SSN Overall Area | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-02-02 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WST02-CD-0013 | NA | "Electrical Signal List for SSN -LVSG-0101A/0101B" && "Milestone 1.1 SSN Overall Area" | 2024-01-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-25 | 83 | AWC | 2025-06-09 | 1 | 000260&&001331 | 2024-01-05, 2025-05-30, 2025-06-09 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1373 | 000260 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0038 | 0 | 131242-WST02-CD-IM-0038-0 | 2024-06-11 | Milestone 1.2 SSN Overall Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-CD-0038 | NA | "Milestone 1.2 SSN Overall Area" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 24 | AWC | 2024-06-11 | 0 | 000260 | 2024-06-11 | 01 | 1 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
1374 | 000260 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-IM-0058-0 | 2025-05-15 | Milestone 2 SSN Overall Area | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-04 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WST02-CD-0058 | NA | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | 2025-05-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-04 | 48 | AWC | 2025-10-31 | 0 | 000260 | 2025-05-15, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1375 | 000260 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WST02 | CD | IM | 0058 | 0 | 131242-WST02-CD-IM-0058-0 | 2025-10-31 | Milestone 3 SSN Overall Area | Rev 3: Approved with Comments, to revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-01-27 | Approved with Comments | 2026-02-16 | NO | Overdue |  | 131242-WST02-CD-0058 | NA | "Milestone 2 SSN Overall Area" && "Milestone 3 SSN Overall Area" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 88 | AWC | 2025-10-31 | 0 | 000260 | 2025-05-15, 2025-10-31 | 02, 03 | 2 | Approved with Comments | AWC | 2026-02-16 | Overdue | 0 | AWC | AWC
1376 | 000261 | 00 | Lilian | PMT | NA | 131242 | WSW41 | PC | W | 0006 | 0 | 131242-WSW41-PC-W-0006-0 | 2024-01-08 | PAYMENT CLAIM NO.6 | Approved. Please refer to S.O. correspondence no. 103 dated 8 Jan 2024. | 2024-02-05 | 2024-01-30 | Approved |  | YES | NA |  | 131242-WSW41-PC-0006 | NA | "PAYMENT CLAIM NO.6" | 2024-01-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-28 | 22 | APP | 2024-01-08 | 0 | 000261 | 2024-01-08 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1377 | 000262 | 00 | Geno | Piping | NA | 131242 | WST02 | SH | M | 1002 | 0 | 131242-WST02-SH-M-1002-0 | 2024-01-08 | Tie in Schedule for SSN | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-05 | 2024-05-27 | Approved with Comments | 2024-06-14 | NO | Overdue | Waiting for SO RFI reply . KM & Qili to check with Karthic for the response | 131242-WST02-SH-1002 | NA | "Tie in Schedule for SSN" | 2024-01-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-28 | 140 | AWC | 2024-01-08 | 0 | 000262 | 2024-01-08 | 00 | 1 | Approved with Comments | AWC | 2024-06-14 | Overdue | 0 | AWC | AWC
1378 | 000263 | 00 | Geno | Piping | NA | 131242 | WSD11 | SH | M | 1001 | 0 | 131242-WSD11-SH-M-1001-0 | 2024-01-09 | Tie in Schedule for THP | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | Approved with Comments | 2024-06-14 | NO | Overdue |  | 131242-WSD11-SH-1001 | NA | "Tie in Schedule for THP" | 2024-01-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-29 | 139 | AWC | 2024-01-09 | 0 | 000263 | 2024-01-09 | 00 | 1 | Approved with Comments | AWC | 2024-06-14 | Overdue | 0 | AWC | AWC
1379 | 000264 | 00 | Geno | Piping | NA | 131242 | WSW41 | SH | M | 5000 | 0 | 131242-WSW41-SH-M-5000-0 | 2024-01-09 | Tie in Schedule for Side wide | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-02-06 | 2024-05-27 | Approved with Comments | 2024-06-14 | NO | Overdue |  | 131242-WSW41-SH-5000 | NA | "Tie in Schedule for Side wide" | 2024-01-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-29 | 139 | AWC | 2024-01-09 | 0 | 000264 | 2024-01-09 | 00 | 1 | Approved with Comments | AWC | 2024-06-14 | Overdue | 0 | AWC | AWC
1380 | 000265 | 00 | Lilian/ Yi Hao | PMT | NA | 131242 | WSW41 | LT | PM | 0019 | 0 | 131242-WSW41-LT-PM-0019-0 | 2024-01-09 | Notice of Office Relocation | For Information | 2024-02-06 | 2024-05-02 | For Information |  | YES | NA |  | 131242-WSW41-LT-0019 | NA | "Notice of Office Relocation" | 2024-01-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-01-29 | 114 | INF | 2024-01-09 | 0 | 000265 | 2024-01-09 | 00 | 1 | For Information | INF | 2024-05-22 | Overdue | 0 | INF | INF
1381 | 000266 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0013 | 0 | 131242-WSW41-CD-IM-0013-0 | 2024-01-09 | Submission Of BIM Coordination VCM Model (Dec – 2023) | For Information | 2024-02-06 | 2024-01-24 | For Information |  | YES | NA |  | 131242-WSW41-CD-0013 | NA | "Submission Of BIM Coordination VCM Model (Dec – 2023)" | 2024-01-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-01-29 | 15 | INF | 2024-01-09 | 0 | 000266 | 2024-01-09 | 00 | 1 | For Information | INF | 2024-02-13 | Overdue | 0 | INF | INF
1382 | 000267 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0016 | 0 | 131242-WSW41-MI-C-0016-0 | 2024-01-09 | CSA Meeting Minutes 0016_20231130 | For Information | 2024-02-06 | 2024-01-25 | For Information |  | YES | NA |  | 131242-WSW41-MI-0016 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-29 | 16 | INF | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1383 | 000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0014 | 0 | 131242-WSW41-MI-IM-0014-0 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 | For Information |  | YES | NA |  | 131242-WSW41-MI-0014 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-23 | 10 | INF | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1384 | 000268 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0015 | 0 | 131242-WSW41-MI-IM-0015-0 | 2024-01-09 | BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227 | For Information | 2024-02-06 | 2024-01-19 | For Information |  | YES | NA |  | 131242-WSW41-MI-0015 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-23 | 10 | INF | 2024-09-04 | 0 | 000240&&000259&&000268&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1385 | 000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6050 | A | 131242-WSD11-DR-P-6050-A | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted | Related to Detailed Design Report. | 131242-WSD11-DR-6050 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1386 | 000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6063 | A | 131242-WSD11-DR-P-6063-A | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6063 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1387 | 000269 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6070 | A | 131242-WSD11-DR-P-6070-A | 2024-01-10 | P&ID of THP General System [Part 2] | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WSD11-DR-6070 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1388 | 000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6050 | B | 131242-WSD11-DR-P-6050-B | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue | Heng Peng to provide DGN dwg | 131242-WSD11-DR-6050 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1389 | 000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6063 | B | 131242-WSD11-DR-P-6063-B | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6063 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1390 | 000269 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6070 | B | 131242-WSD11-DR-P-6070-B | 2024-03-19 | P&ID of THP General System [Part 2] | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WSD11-DR-6070 | NA | "P&ID of THP General System [Part 2]" && "P&ID of THP Train 1" | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000269 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1391 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6019 | A | 131242-WSD11-DR-P-6019-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA | Related to Detailed Design Report. | 131242-WSD11-DR-6019 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1392 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6020 | A | 131242-WSD11-DR-P-6020-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6020 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1393 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6021 | A | 131242-WSD11-DR-P-6021-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6021 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1394 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6022 | A | 131242-WSD11-DR-P-6022-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6022 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1395 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6023 | A | 131242-WSD11-DR-P-6023-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6023 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1396 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6024 | A | 131242-WSD11-DR-P-6024-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6024 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1397 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6025 | A | 131242-WSD11-DR-P-6025-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6025 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1398 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6026 | A | 131242-WSD11-DR-P-6026-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6026 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1399 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6027 | A | 131242-WSD11-DR-P-6027-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6027 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1400 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6028 | A | 131242-WSD11-DR-P-6028-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6028 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1401 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6029 | A | 131242-WSD11-DR-P-6029-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6029 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1402 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6030 | A | 131242-WSD11-DR-P-6030-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6030 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1403 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6031 | A | 131242-WSD11-DR-P-6031-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6031 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1404 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6032 | A | 131242-WSD11-DR-P-6032-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6032 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1405 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6033 | A | 131242-WSD11-DR-P-6033-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6033 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1406 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6034 | A | 131242-WSD11-DR-P-6034-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6034 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1407 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6035 | A | 131242-WSD11-DR-P-6035-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6035 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1408 | 000270 | 00 | Boon Kee | Process | NA | 131242 | WSD11 | DR | P | 6036 | A | 131242-WSD11-DR-P-6036-A | 2024-01-10 | P&ID of THP Train 2 | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-07 | 2024-03-01 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-6036 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-30 | 51 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1409 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6019 | B | 131242-WSD11-DR-P-6019-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-09 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue | Heng Peng to provide DGN dwg | 131242-WSD11-DR-6019 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1410 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6020 | B | 131242-WSD11-DR-P-6020-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6020 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1411 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6021 | B | 131242-WSD11-DR-P-6021-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6021 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1412 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6022 | B | 131242-WSD11-DR-P-6022-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6022 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1413 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6023 | B | 131242-WSD11-DR-P-6023-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6023 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1414 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6024 | B | 131242-WSD11-DR-P-6024-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6024 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1415 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6025 | B | 131242-WSD11-DR-P-6025-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6025 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1416 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6026 | B | 131242-WSD11-DR-P-6026-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6026 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1417 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6027 | B | 131242-WSD11-DR-P-6027-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6027 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1418 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6028 | B | 131242-WSD11-DR-P-6028-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6028 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1419 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6029 | B | 131242-WSD11-DR-P-6029-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6029 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1420 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6030 | B | 131242-WSD11-DR-P-6030-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6030 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1421 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6031 | B | 131242-WSD11-DR-P-6031-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6031 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1422 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6032 | B | 131242-WSD11-DR-P-6032-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6032 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1423 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6033 | B | 131242-WSD11-DR-P-6033-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6033 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1424 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6034 | B | 131242-WSD11-DR-P-6034-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6034 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1425 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6035 | B | 131242-WSD11-DR-P-6035-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6035 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1426 | 000270 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | P | 6036 | B | 131242-WSD11-DR-P-6036-B | 2024-03-19 | P&ID of THP Train 2 | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-25 | Approved with Comments | 2024-05-16 | NO | Overdue |  | 131242-WSD11-DR-6036 | NA | "P&ID of THP Train 1" && "P&ID of THP Train 2 " && "P&ID of THP Train 2 " | 2024-01-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-02 | 37 | AWC | 2025-06-17 | D | 000230&&000270 | 2024-01-10, 2024-03-19, 2024-11-13, 2025-06-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1427 | 000271 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0013 | 0 | 131242-WSW41-VI-C-0013-0 | 2024-01-11 | Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd) | Approved | 2024-02-08 | 2024-01-22 | Approved |  | YES | NA |  | 131242-WSW41-VI-0013 | NA | "Vendor Approval of Time Lapse Camera (Zectech Pte. Ltd)" | 2024-01-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-01-31 | 11 | APP | 2024-01-11 | 0 | 000271 | 2024-01-11 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1428 | 000272 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | E | 8001 | 0 | 131242-WSD11-DR-E-8001-0 | 2024-01-11 | THP ATEX Zone Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached files for comments. | 2024-02-08 | 2024-05-15 | Not Approved | 2024-06-05 | NO | Overdue |  | 131242-WSD11-DR-8001 | NA | "THP ATEX Zone Drawing" | 2024-01-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-31 | 125 | NAP | 2024-01-11 | 0 | 000272 | 2024-01-11 | 00 | 1 | Not Approved | NAP | 2024-06-04 | Overdue | 0 | NAP | NAP
1429 | 000273 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | LT | IM | 0001 | 0 | 131242-WSW41-LT-IM-0001-0 | 2024-01-12 | Common Data Environment (CDE) Set-Up and Rollout | For Information. This document should be part of BEP under CDE workflow | 2024-02-09 | 2024-02-27 | For Information |  | YES | NA |  | 131242-WSW41-LT-0001 | NA | "Approval Letter to Commence Works Requiring Earth Control Measure" && "Common Data Environment (CDE) Set-Up and Rollout" | 2023-11-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-01-26 | 46 | INF | 2024-01-12 | 0 | 000156&&000273 | 2023-11-02, 2024-01-12 | 00 | 2 | For Information | INF | 2024-03-18 | Overdue | 0 | INF | INF
1430 | 000274 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 0 | 131242-WST02-CL-S-0003_ST612-0 | 2024-01-13 | ST612_Typical Railing Design Calculation | Rev 0: Not Approved. Please refer to comment sheet for resubmission. Drawing attached should be for information not "shop drawing". | 2024-02-09 | 2024-02-01 | Not Approved | 2024-02-22 | YES | Resubmitted |  | 131242-WST02-CL-0003_ST612 | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 19 | NAP | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1431 | 000274 | 01 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 1 | 131242-WST02-CL-S-0003_ST612-1 | 2024-02-16 | ST612_Typical Railing Design Calculation | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-03-05 | Not Approved | 2024-03-25 | YES | Resubmitted |  | 131242-WST02-CL-0003_ST612 | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 | 18 | NAP | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1432 | 000274 | 02 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 2 | 131242-WST02-CL-S-0003_ST612-2 | 2024-03-20 | ST612_Typical Railing Design Calculation | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-11 | 2024-05-13 | Not Approved | 2024-06-03 | YES | Resubmitted |  | 131242-WST02-CL-0003_ST612 | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-03 | 54 | NAP | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1433 | 000274 | 03 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0003_ST612 | 3 | 131242-WST02-CL-S-0003_ST612-3 | 2024-06-06 | ST612_Typical Railing Design Calculation | Rev.3:Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-CL-0003_ST612 | NA | "ST612_Typical Railing Design Calculation" | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-20 | 29 | AWC | 2024-06-06 | 3 | 000274 | 2024-01-13, 2024-02-16, 2024-03-20, 2024-06-06 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
1434 | 000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612 | A | 131242-WST02-DR-S-8600_ST612-A | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-DR-8600_ST612 | NA | "ST612_Typical Railing Design Calculation" | 2024-07-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 19 | AWC | 2024-07-31 | A | 000274 | 2024-07-31 | 04 | 1 | Approved with Comments | AWC | 2024-09-06 | Overdue | 0 | AWC | AWC
1435 | 000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | E | 131242-WST02-DR-S-5600_ST612-E | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-DR-5600_ST612 | NA | "ST612_Typical Railing " && "ST612_Typical Railing Design Calculation" | 2024-07-31 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 19 | AWC | 2025-08-13 | I | 000274 | 2024-07-31, 2025-08-13 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1436 | 000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612 | E | 131242-WST02-DR-S-5601_ST612-E | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-DR-5601_ST612 | NA | "ST612_Typical Railing " && "ST612_Typical Railing Design Calculation" | 2024-07-31 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 19 | AWC | 2025-08-13 | J | 000274 | 2024-07-31, 2025-08-13 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1437 | 000274 | 04 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612 | C | 131242-WST02-DR-S-5602_ST612-C | 2024-07-31 | ST612_Typical Railing Design Calculation | Rev.4:Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-21 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-DR-5602_ST612 | NA | "ST612_Typical Railing " && "ST612_Typical Railing Design Calculation" | 2024-07-31 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 19 | AWC | 2025-08-13 | I | 000274 | 2024-07-31, 2025-08-13 | 04, 05 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1438 | 000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612 | I | 131242-WST02-DR-S-5600_ST612-I | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-5600_ST612 | NA | "ST612_Typical Railing " && "ST612_Typical Railing Design Calculation" | 2024-07-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 26 | AWC | 2025-08-13 | I | 000274 | 2024-07-31, 2025-08-13 | 04, 05 | 2 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
1439 | 000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612 | J | 131242-WST02-DR-S-5601_ST612-J | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-5601_ST612 | NA | "ST612_Typical Railing " && "ST612_Typical Railing Design Calculation" | 2024-07-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 26 | AWC | 2025-08-13 | J | 000274 | 2024-07-31, 2025-08-13 | 04, 05 | 2 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
1440 | 000274 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612 | I | 131242-WST02-DR-S-5602_ST612-I | 2025-08-13 | ST612_Typical Railing | Rev.5: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-02 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-DR-5602_ST612 | NA | "ST612_Typical Railing " && "ST612_Typical Railing Design Calculation" | 2024-07-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 26 | AWC | 2025-08-13 | I | 000274 | 2024-07-31, 2025-08-13 | 04, 05 | 2 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
1441 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A | 131242-WST02-DR-S-1000_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1000_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1442 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | A | 131242-WST02-DR-S-1006_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1006_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1443 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | A | 131242-WST02-DR-S-1007_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1007_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1444 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | A | 131242-WST02-DR-S-1008_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1008_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1445 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | A | 131242-WST02-DR-S-1013_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1013_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1446 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | A | 131242-WST02-DR-S-1014_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1014_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | B | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1447 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | A | 131242-WST02-DR-S-1015_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1015_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1448 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | A | 131242-WST02-DR-S-1016_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1016_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1449 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | A | 131242-WST02-DR-S-1017_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1017_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1450 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | A | 131242-WST02-DR-S-1018_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1018_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1451 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | A | 131242-WST02-DR-S-1019_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1019_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1452 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | A | 131242-WST02-DR-S-1020_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1020_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1453 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | A | 131242-WST02-DR-S-1021_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1021_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1454 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | A | 131242-WST02-DR-S-1022_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1022_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1455 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | A | 131242-WST02-DR-S-3005_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-3005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1456 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | A | 131242-WST02-DR-S-3008_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-3008_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1457 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | A | 131242-WST02-DR-S-3009_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-3009_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1458 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | A | 131242-WST02-DR-S-5005_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1459 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | A | 131242-WST02-DR-S-5006_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1460 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | A | 131242-WST02-DR-S-7002_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-7002_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1461 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | A | 131242-WST02-DR-S-7003_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-7003_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1462 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | A | 131242-WST02-DR-S-7004_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-7004_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1463 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | A | 131242-WST02-DR-S-7005_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-7005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1464 | 000275 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | A | 131242-WST02-DR-S-8003_ST613-A | 2024-01-13 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.0: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-02-09 | 2024-02-14 | Not Approved | 2024-03-05 | YES | Resubmitted |  | 131242-WST02-DR-8003_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-02 | 32 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1465 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | A.1 | 131242-WST02-DR-S-1000_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-04-25 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue | Heng Peng: BIM to clear Aaron comments | 131242-WST02-DR-1000_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1466 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | A.1 | 131242-WST02-DR-S-1006_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1006_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1467 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | A.1 | 131242-WST02-DR-S-1007_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1007_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1468 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | A.1 | 131242-WST02-DR-S-1008_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1008_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1469 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | A.1 | 131242-WST02-DR-S-1013_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1013_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1470 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | A.1 | 131242-WST02-DR-S-1014_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1014_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | B | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1471 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | A.1 | 131242-WST02-DR-S-1015_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1015_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1472 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | A.1 | 131242-WST02-DR-S-1016_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1016_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1473 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | A.1 | 131242-WST02-DR-S-1017_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1017_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1474 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | A.1 | 131242-WST02-DR-S-1018_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1018_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1475 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | A.1 | 131242-WST02-DR-S-1019_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1019_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1476 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | A.1 | 131242-WST02-DR-S-1020_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1020_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1477 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | A.1 | 131242-WST02-DR-S-1021_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1021_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1478 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | A.1 | 131242-WST02-DR-S-1022_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-1022_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1479 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | A.1 | 131242-WST02-DR-S-3005_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-3005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1480 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | A.1 | 131242-WST02-DR-S-3008_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-3008_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1481 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | A.1 | 131242-WST02-DR-S-3009_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-3009_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1482 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | A.1 | 131242-WST02-DR-S-5005_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-5005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1483 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | A.1 | 131242-WST02-DR-S-5006_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-5006_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1484 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | A.1 | 131242-WST02-DR-S-7002_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-7002_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1485 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | A.1 | 131242-WST02-DR-S-7003_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-7003_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1486 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | A.1 | 131242-WST02-DR-S-7004_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-7004_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1487 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | A.1 | 131242-WST02-DR-S-7005_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-7005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1488 | 000275 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | A.1 | 131242-WST02-DR-S-8003_ST613-A.1 | 2024-04-04 | ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building | Rev.1: Not Approved. Please refer to comment sheet and markup comment for resubmission. | 2024-05-06 | 2024-05-16 | Not Approved | 2024-06-06 | NO | Overdue |  | 131242-WST02-DR-8003_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 42 | NAP | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
1489 | 000276 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0008 | 0 | 131242-WSW41-RT-PM-0008-0 | 2024-01-16 | C4B Monthly Progress Report Number No.08 (12/23) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-02-14 | 2024-01-31 | Approved with Comments | 2024-02-21 | NO | Overdue |  | 131242-WSW41-RT-0008 | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-05 | 15 | AWC | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
1490 | 000277 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 0 | 131242-WSW41-LC-Z-0001-0 | 2024-01-16 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. Please append COS. | 2024-02-14 | 2024-01-22 | For Information | 2024-02-09 | YES | Resubmitted |  | 131242-WSW41-LC-0001 | NA | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" && "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-05 | 6 | INF | 2025-08-25 | 0 | 000277&&001620 | 2024-01-16, 2024-02-02, 2025-08-25 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
1491 | 000277 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | LC | Z | 0001 | 1 | 131242-WSW41-LC-Z-0001-1 | 2024-02-02 | Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter | For Information. | 2024-02-23 | 2024-02-19 | For Information |  | YES | NA |  | 131242-WSW41-LC-0001 | NA | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" && "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-16 | 17 | INF | 2025-08-25 | 0 | 000277&&001620 | 2024-01-16, 2024-02-02, 2025-08-25 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
1492 | 000278 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0001 | 0 | 131242-WSD11-RT-P-0001-0 | 2024-01-17 | THP - Basis of Design Report | Rev 0: Approved with Comments. To revise and resubmit. | 2024-02-15 | 2024-03-01 | Approved with Comments | 2024-03-21 | NO | Overdue |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-01-31 | 44 | AWC | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1493 | 000279 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0016 | 0 | 131242-WSW41-MI-P-0016-0 | 2024-01-18 | Process & MEICA Meeting Minutes 0016_20240104 | Rev 0: For Information | 2024-02-16 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0016 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-01 | 124 | INF | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1494 | 000280 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | LT | PM | 0020 | 0 | 131242-WSW41-LT-PM-0020-0 | 2024-01-20 | CV of Team Member (ECO cum ECMO) | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-19 | 2024-02-01 | Not Approved | 2024-02-22 | YES | Resubmitted |  | 131242-WSW41-LT-0020 | NA | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | 2024-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-09 | 12 | NAP | 2024-04-12 | 1 | 000280 | 2024-01-20, 2024-04-12 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
1495 | 000280 | 01 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0020 | 1 | 131242-WSW41-LT-PM-0020-1 | 2024-04-12 | CV of Team Member (ECO) | Rev.1: Approved | 2024-05-03 | 2024-06-06 | Approved |  | YES | NA |  | 131242-WSW41-LT-0020 | NA | "CV of Team Member (ECO cum ECMO)" && "CV of Team Member (ECO)" | 2024-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-26 | 55 | APP | 2024-04-12 | 1 | 000280 | 2024-01-20, 2024-04-12 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
1496 | 000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 1100 | A | 131242-WSW41-DR-E-1100-A | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | Approved with Comments | 2024-06-05 | YES | Resubmitted | Combined with Prolog 000252 - Sitewide Piperack Lightning Protection System | 131242-WSW41-DR-1100 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Sitewide Piperack Earthing System" | 2024-01-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-12 | 113 | AWC | 2026-01-19 | E | 000281&&001962 | 2024-01-23, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
1497 | 000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 2000 | A | 131242-WSW41-DR-E-2000-A | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | Approved with Comments | 2024-06-05 | NO | Overdue |  | 131242-WSW41-DR-2000 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Earthing System" | 2024-01-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-12 | 113 | AWC | 2026-01-19 | F | 000281&&001963 | 2024-01-23, 2026-01-19 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1498 | 000281 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | DR | E | 5000 | A | 131242-WSW41-DR-E-5000-A | 2024-01-23 | Sitewide Piperack Earthing System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-02-21 | 2024-05-15 | Approved with Comments | 2024-06-05 | NO | Overdue |  | 131242-WSW41-DR-5000 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Earthing System" && "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | 2024-01-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-12 | 113 | AWC | 2026-01-19 | F | 000281&&001136&&001963 | 2024-01-23, 2025-03-20, 2026-01-19 | 00 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1499 | 000282 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0021 | 0 | 131242-WSW41-LT-PM-0021-0 | 2024-01-23 | Assign of Builder License (CES_SDC Pte. Ltd.) | For Information | 2024-02-21 | 2024-05-10 | For Information |  | YES | NA |  | 131242-WSW41-LT-0021 | NA | "Assign of Builder License (CES_SDC Pte. Ltd.)" | 2024-01-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-02-12 | 108 | INF | 2024-01-23 | 0 | 000282 | 2024-01-23 | 00 | 1 | For Information | INF | 2024-05-30 | Overdue | 0 | INF | INF
1500 | 000283 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0007 | 0 | 131242-WSW41-MI-PM-0007-0 | 2024-01-23 | Monthly Progress Meeting Minutes 0007_20231219 | For Information | 2024-02-21 | 2024-01-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0007 | NA | "BIM Bi-Weekly Meeting Minutes 0007_20230906" && "CSA Meeting Minutes 0007_20230712" && "Monthly Progress Meeting Minutes 0007_20231219" && "Process & MEICA Meeting Minutes 0007_20230718" | 2023-07-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-02-06 | 1 | INF | 2024-01-23 | 0 | 000054&&000089&&000095&&000283 | 2023-07-24, 2023-09-05, 2023-09-11, 2024-01-23 | 00 | 4 | For Information | INF | 2024-02-13 | Overdue | 0 | INF | INF
1501 | 000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-S-1000_ST604-B | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WST02-DR-1000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-12 | 23 | NAP | 2024-02-16 | B | 000284 | 2024-01-23, 2024-02-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1502 | 000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8000_ST604 | A1 | 131242-WST02-DR-C-8000_ST604-A1 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WST02-DR-8000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-07 |  | NAP | 2024-02-16 | A1 | 000284 | 2024-02-16 | 00, 01 | 2 | Not Approved | NAP | 2024-03-06 | Overdue | 0 | NAP | NAP
1503 | 000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | B | 131242-WST02-DR-C-1001_ST604-B | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-06 | 23 | NAP | 2024-02-16 | B1 | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1504 | 000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604 | A1 | 131242-WST02-DR-C-1002_ST604-A1 | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WST02-DR-1002_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-12 | 23 | NAP | 2024-02-16 | A2 | 000284 | 2024-01-23, 2024-02-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1505 | 000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | B | 131242-WST02-DR-C-7000_ST604-B | 2024-01-23 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-02-21 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WST02-DR-7000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-06 | 23 | NAP | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1506 | 000284 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | B | 131242-WST02-DR-C-5001_ST604-B | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-15 | Not Approved | 2024-03-06 | YES | Resubmitted |  | 131242-WST02-DR-5001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 |  | NAP | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00, 01, 02 | 5 | Not Approved | NAP | 2024-03-06 | Overdue | 0 | NAP | NAP
1507 | 000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST604 | B | 131242-WST02-DR-S-1000_ST604-B | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-07 | 2024-02-29 | Approved with Comments | 2024-03-20 | NO | Overdue | Zora to reply. (Refer to submission 340 Amendment of ST604) | 131242-WST02-DR-1000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 | 13 | AWC | 2024-02-16 | B | 000284 | 2024-01-23, 2024-02-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-03-20 | Overdue | 0 | AWC | AWC
1508 | 000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8000_ST604 | A1 | 131242-WST02-DR-C-8000_ST604-A1 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | Approved with Comments | 2024-03-20 | NO | Overdue |  | 131242-WST02-DR-8000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-02-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-07 | 13 | AWC | 2024-02-16 | A1 | 000284 | 2024-02-16 | 00, 01 | 2 | Not Approved | NAP | 2024-03-20 | Overdue | 0 | AWC | AWC
1509 | 000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1001_ST604 | B1 | 131242-WST02-DR-C-1001_ST604-B1 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | Approved with Comments | 2024-03-20 | NO | Overdue |  | 131242-WST02-DR-1001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 | 13 | AWC | 2024-02-16 | B1 | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2024-03-20 | Overdue | 0 | AWC | AWC
1510 | 000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1002_ST604 | A2 | 131242-WST02-DR-C-1002_ST604-A2 | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | Approved with Comments | 2024-03-20 | NO | Overdue |  | 131242-WST02-DR-1002_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " | 2024-01-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 | 13 | AWC | 2024-02-16 | A2 | 000284 | 2024-01-23, 2024-02-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-03-20 | Overdue | 0 | AWC | AWC
1511 | 000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 7000_ST604 | B | 131242-WST02-DR-C-7000_ST604-B | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | Approved with Comments | 2024-03-20 | NO | Overdue |  | 131242-WST02-DR-7000_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 | 13 | AWC | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-01-23, 2024-02-16 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2024-03-20 | Overdue | 0 | AWC | AWC
1512 | 000284 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5001_ST604 | B | 131242-WST02-DR-C-5001_ST604-B | 2024-02-16 | IFC of ST604 : Piling design of Minor Structures | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-15 | 2024-02-29 | Approved with Comments | 2024-03-20 | NO | Overdue |  | 131242-WST02-DR-5001_ST604 | NA | "IFC of ST604 : Piling design of Minor Structures " && "ST604 – Overall SSN area Piling Design" | 2023-08-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-01 | 13 | AWC | 2024-02-16 | B | 000079&&000284 | 2023-08-24, 2023-09-26, 2023-11-07, 2024-02-16 | 00, 01, 02 | 5 | Not Approved | NAP | 2024-03-20 | Overdue | 0 | AWC | AWC
1513 | 000285 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0007 | 0 | 131242-WSW41-PS-PM-0007-0 | 2024-01-24 | Monthly Progress Presentation No. 07 (1123) | For Information | 2024-02-22 | 2024-01-29 | For Information |  | YES | NA |  | 131242-WSW41-PS-0007 | NA | "Incentive / Disincentive Audit Scheme for Feb 2024" && "Monthly Progress Presentation No. 07 (1123)" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-13 | 5 | INF | 2024-03-14 | 0 | 000285&&000362 | 2024-01-24, 2024-03-14 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
1514 | 000286 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0008 | 0 | 131242-WSW41-PS-PM-0008-0 | 2024-01-24 | Monthly Progress Presentation No. 08 (1223) | For Information | 2024-02-22 | 2024-01-25 | For Information |  | YES | NA |  | 131242-WSW41-PS-0008 | NA | "Monthly Progress Presentation No. 08 (1223)" && "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-13 | 1 | INF | 2024-04-30 | 0 | 000286&&000457 | 2024-01-24, 2024-04-30 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
1515 | 000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5000_ST604 | A | 131242-WST02-SD-C-5000_ST604-A | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-5000_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-04-18 | D | 000287 | 2024-01-24, 2024-02-26, 2024-04-18 | 00, 01, 03 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1516 | 000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5001_ST604 | A | 131242-WST02-SD-C-5001_ST604-A | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-5001_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1517 | 000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5002_ST604 | A | 131242-WST02-SD-C-5002_ST604-A | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-5002_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1518 | 000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5003_ST604 | A | 131242-WST02-SD-C-5003_ST604-A | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-5003_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1519 | 000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 5004_ST604 | A | 131242-WST02-SD-C-5004_ST604-A | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-5004_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1520 | 000287 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | C | 8000_ST604 | A | 131242-WST02-SD-C-8000_ST604-A | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-8000_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1521 | 000287 | 00 | Zora | CSA | NA | 131242-WST02-SD-ST 604 QPD Endorsed Drawing | NA | NA | NA | 9999 | A | 131242-WST02-SD-ST 604 QPD Endorsed Drawing ----- | 2024-01-24 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-02-22 | 2024-02-21 | Not Approved | 2024-03-12 | YES | Resubmitted |  | 131242-WST02-SD-ST 604 QPD Endorsed Drawing -NA-NA-9999 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-13 | 28 | NAP | 2024-01-24 | A | 000287 | 2024-01-24 | 00 | 1 | Not Approved | NAP | 2024-03-12 | Overdue | 0 | NAP | NAP
1522 | 000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5000_ST604 | B | 131242-WST02-SD-S-5000_ST604-B | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-15 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-SD-5000_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 1 | NAP | 2024-04-18 | D | 000287 | 2024-01-24, 2024-02-26, 2024-04-18 | 00, 01, 03 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1523 | 000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5001_ST604 | B | 131242-WST02-SD-S-5001_ST604-B | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-SD-5001_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 1 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP | 2024-03-18 | Overdue | 0 | NAP | NAP
1524 | 000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5002_ST604 | B | 131242-WST02-SD-S-5002_ST604-B | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-SD-5002_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 1 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP | 2024-03-18 | Overdue | 0 | NAP | NAP
1525 | 000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5003_ST604 | B | 131242-WST02-SD-S-5003_ST604-B | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-SD-5003_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 1 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP | 2024-03-18 | Overdue | 0 | NAP | NAP
1526 | 000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5004_ST604 | B | 131242-WST02-SD-S-5004_ST604-B | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-SD-5004_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 1 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP | 2024-03-18 | Overdue | 0 | NAP | NAP
1527 | 000287 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8000_ST604 | B | 131242-WST02-SD-S-8000_ST604-B | 2024-02-26 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1: Not Approved. Please submit the response of the comment sheet. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-SD-8000_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 1 | NAP | 2024-02-26 | B | 000287 | 2024-01-24, 2024-02-26 | 00, 01 | 2 | Not Approved | NAP | 2024-03-18 | Overdue | 0 | NAP | NAP
1528 | 000287 | 02 | Zora | CSA | NA | 131242 | NA | SD | S | Relpy to comment Sheet | B |  | 2024-02-28 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.1&2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-03-20 | Approved with Comments | 2024-04-11 | YES | Resubmitted |  | 131242-NA-SD-Relpy to comment Sheet | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-02-28 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-19 | 21 | AWC | 2024-02-28 | B | 000287 | 2024-02-28 | 02 | 1 | Approved with Comments | AWC | 2024-04-09 | Overdue | 0 | AWC | AWC
1529 | 000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5000_ST604 | D | 131242-WST02-SD-S-5000_ST604-D | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-21 | Approved with Comments | 2024-06-11 | NO | Overdue |  | 131242-WST02-SD-5000_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 33 | AWC | 2024-04-18 | D | 000287 | 2024-01-24, 2024-02-26, 2024-04-18 | 00, 01, 03 | 3 | Approved with Comments | AWC | 2024-06-10 | Overdue | 0 | AWC | AWC
1530 | 000287 | 03 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5012_ST604 | D | 131242-WST02-SD-S-5012_ST604-D | 2024-04-18 | Shop Drawings of ST604 : Piling Design of Minor Structures | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-21 | Approved with Comments | 2024-06-11 | NO | Overdue |  | 131242-WST02-SD-5012_ST604 | NA | "Shop Drawings of ST604 : Piling Design of Minor Structures" | 2024-04-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-08 | 33 | AWC | 2024-04-18 | D | 000287 | 2024-04-18 | 03 | 1 | Approved with Comments | AWC | 2024-06-10 | Overdue | 0 | AWC | AWC
1531 | 000288 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0007 | 0 | 131242-WSW41-PC-W-0007-0 | 2024-01-24 | PAYMENT CLAIM NO.7 | Approved. Please refer to S.O. correspondence no. 116 dated 25 Jan 2024. | 2024-02-22 | 2024-02-15 | Approved |  | YES | NA |  | 131242-WSW41-PC-0007 | NA | "PAYMENT CLAIM NO.7" | 2024-01-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-13 | 22 | APP | 2024-01-24 | 0 | 000288 | 2024-01-24 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1532 | 000289 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 0 | 131242-WSW41-CN-I-0001-0 | 2024-01-26 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-02-26 | 2024-04-17 | Not Approved | 2024-05-08 | YES | Resubmitted |  | 131242-WSW41-CN-0001 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-09 | 82 | NAP | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | Rejected | REJ |  |  | 0 | NAP | NAP
1533 | 000289 | 01 | Low | EICA | NA | 131242 | WSW41 | CN | I | 0001 | 1 | 131242-WSW41-CN-I-0001-1 | 2024-04-19 | RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD | Rev 1: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-05-21 | Rejected | 2024-06-11 | NO | Overdue | (RFC) NO.: 1230207-RFC-0004 R1 | 131242-WSW41-CN-0001 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 32 | REJ | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
1534 | 000290 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | I | 0002 | 0 | 131242-WSD11-DS-I-0002-0 | 2024-02-01 | Control Valves Data Sheet (THP) | Rev 0: Not approved - Revise and Resubmit | 2024-03-01 | 2024-04-29 | Not Approved | 2024-05-20 | NO | Overdue |  | 131242-WSD11-DS-0002 | NA | "Control Valves Data Sheet (THP)" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 88 | NAP | 2024-02-01 | 0 | 000290 | 2024-02-01 | 00 | 1 | Not Approved | NAP | 2024-05-17 | Overdue | 0 | NAP | NAP
1535 | 000291 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0015 | 0 | 131242-WSD11-CD-IM-0015-0 | 2024-02-01 | Milestone 1.1 THP EICA Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-CD-0015 | NA | "Milestone 1.1 THP EICA Silo Area inside Biosolid Building" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 56 | AWC | 2024-02-01 | 0 | 000291 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
1536 | 000291 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-IM-0033-0 | 2024-06-04 | Milestone 1.2 THP EICA Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-25 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSD11-CD-0033 | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-24 | 31 | AWC | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1537 | 000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0_wd | 131242-WSD11-CD-IM-0033-0_wd | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-CD-0033 | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 38 | REJ | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1538 | 000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A_wd | 131242-WSD11-DR-E-1030-A_wd | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1030 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-30 | 38 | REJ | 2025-10-28 | A | 000291 | 2024-12-10, 2025-01-22, 2025-10-28 | 02, 03, 04 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1539 | 000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A_wd | 131242-WSD11-DR-E-3010-A_wd | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 38 | REJ | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1540 | 000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A_wd | 131242-WSD11-DR-E-3011-A_wd | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 38 | REJ | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1541 | 000291 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A_wd | 131242-WSD11-DR-E-3012-A_wd | 2024-12-10 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 2: To reject and resubmit as per CES request. | 2024-12-31 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 38 | REJ | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1542 | 000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 0 | 131242-WSD11-CD-IM-0033-0 | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-CD-0033 | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 161 | AWC | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1543 | 000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A | 131242-WSD11-DR-E-1030-A | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1030 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-12-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 161 | AWC | 2025-10-28 | A | 000291 | 2024-12-10, 2025-01-22, 2025-10-28 | 02, 03, 04 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1544 | 000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010-A | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 161 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1545 | 000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011-A | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 161 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1546 | 000291 | 03 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A | 131242-WSD11-DR-E-3012-A | 2025-01-22 | Milestone 2 THP EICA Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-11 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 161 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1547 | 000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0033 | 1 | 131242-WSD11-CD-IM-0033-1 | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-CD-0033 | NA | "Milestone 1.2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-06-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 119 | AWC | 2025-10-28 | 1 | 000291 | 2024-06-04, 2024-12-10, 2025-01-22, 2025-10-28 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
1548 | 000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1030 | A | 131242-WSD11-DR-E-1030-A | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-1030 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" | 2024-12-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 119 | AWC | 2025-10-28 | A | 000291 | 2024-12-10, 2025-01-22, 2025-10-28 | 02, 03, 04 | 3 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
1549 | 000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010-A | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 119 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1550 | 000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011-A | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 119 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1551 | 000291 | 04 | Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3012 | A | 131242-WSD11-DR-E-3012-A | 2025-10-28 | Milestone 3 THP EICA Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-17 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 119 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1552 | 000292 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0017 | 0 | 131242-WSD11-CD-IM-0017-0 | 2024-02-01 | Milestone 1.1 THP Overall & Equipment Layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-CD-0017 | NA | "Milestone 1.1 THP Overall & Equipment Layout" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 56 | AWC | 2024-02-01 | 0 | 000292 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
1553 | 000292 | 01 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031-0 | 2024-06-11 | Milestone 1.2 THP Overall & Equipment Layout | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSD11-CD-0031 | NA | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 24 | AWC | 2025-11-28 | 0 | 000292 | 2024-06-11, 2025-05-09, 2025-11-28 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1554 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031-0 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-CD-0031 | NA | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | 0 | 000292 | 2024-06-11, 2025-05-09, 2025-11-28 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1555 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
1556 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
1557 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
1558 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1040 | A | 131242-WSD11-DR-E-1040-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1040 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1559 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1041 | A | 131242-WSD11-DR-E-1041-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1041 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1560 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1042 | A | 131242-WSD11-DR-E-1042-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1042 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1561 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1043 | A | 131242-WSD11-DR-E-1043-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1043 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1562 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3008 | A | 131242-WSD11-DR-E-3008-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1563 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3009 | A | 131242-WSD11-DR-E-3009-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1564 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1565 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1566 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 1043 | A | 131242-WSD11-DR-I-1043-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1043 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1567 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
1568 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | AWC | AWC
1569 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1102 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1570 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1103 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1571 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1104 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1572 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
1573 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
1574 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
1575 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
1576 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | AWC | AWC
1577 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
1578 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
1579 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
1580 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
1581 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004-B | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | AWC | AWC
1582 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3018 | A | 131242-WSD11-DR-I-3018-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1583 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3019 | A | 131242-WSD11-DR-I-3019-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1584 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3020 | A | 131242-WSD11-DR-I-3020-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1585 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3021 | A | 131242-WSD11-DR-I-3021-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1586 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3022 | A | 131242-WSD11-DR-I-3022-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1587 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3023 | A | 131242-WSD11-DR-I-3023-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1588 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3024 | A | 131242-WSD11-DR-I-3024-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1589 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3025 | A | 131242-WSD11-DR-I-3025-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1590 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3026 | A | 131242-WSD11-DR-I-3026-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3026 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1591 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3027 | A | 131242-WSD11-DR-I-3027-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3027 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1592 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3028 | A | 131242-WSD11-DR-I-3028-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3028 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001230 | 2025-05-09, 2025-11-11, 2025-11-28 | 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1593 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3029 | A | 131242-WSD11-DR-I-3029-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3029 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292 | 2025-05-09, 2025-11-28 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1594 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3030 | A | 131242-WSD11-DR-I-3030-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3030 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1595 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3031 | A | 131242-WSD11-DR-I-3031-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3031 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1596 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3032 | A | 131242-WSD11-DR-I-3032-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3032 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1597 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3033 | A | 131242-WSD11-DR-I-3033-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3033 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1598 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3034 | A | 131242-WSD11-DR-I-3034-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3034 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1599 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3035 | A | 131242-WSD11-DR-I-3035-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3035 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292 | 2025-05-09, 2025-11-28 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1600 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1120 | A | 131242-WSD11-DR-M-1120-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1120 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1601 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1121 | A | 131242-WSD11-DR-M-1121-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1121 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1602 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1122 | A | 131242-WSD11-DR-M-1122-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1122 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1603 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1123 | A | 131242-WSD11-DR-M-1123-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1123 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1604 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1200 | A.1 | 131242-WSD11-DR-M-1200-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1200 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1605 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1201 | A.1 | 131242-WSD11-DR-M-1201-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1201 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1606 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1202 | A.1 | 131242-WSD11-DR-M-1202-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1202 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1607 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1203 | A.1 | 131242-WSD11-DR-M-1203-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1203 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1608 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1204 | A.1 | 131242-WSD11-DR-M-1204-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1204 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1609 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1205 | A.1 | 131242-WSD11-DR-M-1205-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-1205 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-29 | 189 | AWC | 2025-11-28 | A.1 | 000292 | 2025-05-09, 2025-11-28 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1610 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 3000 | A | 131242-WSD11-DR-M-3000-A | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
1611 | 000292 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 8000 | A.1 | 131242-WSD11-DR-M-8000-A.1 | 2025-05-09 | Milestone 2 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-29 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WSD11-DR-8000 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-23 | 189 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1612 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0031 | 0 | 131242-WSD11-CD-IM-0031-0 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-CD-0031 | NA | "Milestone 1.2 THP Overall & Equipment Layout" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2024-06-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | 0 | 000292 | 2024-06-11, 2025-05-09, 2025-11-28 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1613 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1000 | A | 131242-WSD11-DR-BF-1000-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | PEN | PEN
1614 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 1001 | A | 131242-WSD11-DR-BF-1001-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | PEN | PEN
1615 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BF | 3000 | A | 131242-WSD11-DR-BF-3000-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | PEN | PEN
1616 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1040 | A | 131242-WSD11-DR-E-1040-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1040 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1617 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1041 | A | 131242-WSD11-DR-E-1041-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1041 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1618 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1042 | A | 131242-WSD11-DR-E-1042-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1042 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1619 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1043 | A | 131242-WSD11-DR-E-1043-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1043 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 5 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1620 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3008 | A | 131242-WSD11-DR-E-3008-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1621 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3009 | A | 131242-WSD11-DR-E-3009-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1622 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3010 | A | 131242-WSD11-DR-E-3010-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
1623 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 3011 | A | 131242-WSD11-DR-E-3011-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
1624 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 1043 | A | 131242-WSD11-DR-I-1043-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1043 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 5 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1625 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1100 | B | 131242-WSD11-DR-E-1100-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | PEN | PEN
1626 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1101 | B | 131242-WSD11-DR-E-1101-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | PEN | PEN
1627 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1102 | B | 131242-WSD11-DR-E-1102-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1102 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1628 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1103 | B | 131242-WSD11-DR-E-1103-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1103 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1629 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | E | 1104 | B | 131242-WSD11-DR-E-1104-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1104 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2024-08-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | B | 000236&&000292&&001328 | 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28 | 00, 01, 02, 03 | 5 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1630 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1000 | B | 131242-WSD11-DR-EL-1000-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | PEN | PEN
1631 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1001 | B | 131242-WSD11-DR-EL-1001-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | PEN | PEN
1632 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1002 | B | 131242-WSD11-DR-EL-1002-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | PEN | PEN
1633 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1003 | B | 131242-WSD11-DR-EL-1003-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | PEN | PEN
1634 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EL | 1004 | B | 131242-WSD11-DR-EL-1004-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | PEN | PEN
1635 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1000 | B | 131242-WSD11-DR-EP-1000-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | PEN | PEN
1636 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1001 | B | 131242-WSD11-DR-EP-1001-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | PEN | PEN
1637 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1002 | B | 131242-WSD11-DR-EP-1002-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | PEN | PEN
1638 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1003 | B | 131242-WSD11-DR-EP-1003-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | PEN | PEN
1639 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | EP | 1004 | B | 131242-WSD11-DR-EP-1004-B | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | PEN | PEN
1640 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3018 | A | 131242-WSD11-DR-I-3018-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3018 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1641 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3019 | A | 131242-WSD11-DR-I-3019-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3019 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1642 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3020 | A | 131242-WSD11-DR-I-3020-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
1643 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3021 | A | 131242-WSD11-DR-I-3021-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3021 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1644 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3022 | A | 131242-WSD11-DR-I-3022-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3022 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1645 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3023 | A | 131242-WSD11-DR-I-3023-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3023 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1646 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3024 | A | 131242-WSD11-DR-I-3024-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3024 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1647 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3025 | A | 131242-WSD11-DR-I-3025-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3025 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230&&001328 | 2025-02-07, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1648 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3026 | A | 131242-WSD11-DR-I-3026-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3026 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1649 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3027 | A | 131242-WSD11-DR-I-3027-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3027 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001027&&001230 | 2025-02-07, 2025-05-09, 2025-05-30, 2025-08-05, 2025-11-11, 2025-11-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1650 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3028 | A | 131242-WSD11-DR-I-3028-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3028 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP WAP FFOTP_GA & Wiring Diagram" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001230 | 2025-05-09, 2025-11-11, 2025-11-28 | 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1651 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3029 | A | 131242-WSD11-DR-I-3029-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3029 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292 | 2025-05-09, 2025-11-28 | 02, 03 | 2 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1652 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3030 | A | 131242-WSD11-DR-I-3030-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3030 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1653 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3031 | A | 131242-WSD11-DR-I-3031-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3031 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1654 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3032 | A | 131242-WSD11-DR-I-3032-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3032 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1655 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3033 | A | 131242-WSD11-DR-I-3033-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3033 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1656 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3034 | A | 131242-WSD11-DR-I-3034-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3034 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1657 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | I | 3035 | A | 131242-WSD11-DR-I-3035-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3035 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292 | 2025-05-09, 2025-11-28 | 02, 03 | 2 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1658 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1120 | A | 131242-WSD11-DR-M-1120-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1120 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1659 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1121 | A | 131242-WSD11-DR-M-1121-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1121 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1660 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1122 | A | 131242-WSD11-DR-M-1122-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1122 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1661 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1123 | A | 131242-WSD11-DR-M-1123-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1123 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A | 000292&&001328 | 2025-05-09, 2025-05-28, 2025-11-28 | 00, 02, 03 | 3 | Not Approved | NAP | 2026-01-15 |  | 0 | PEN | PEN
1662 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1200 | A.1 | 131242-WSD11-DR-M-1200-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1200 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1663 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1201 | A.1 | 131242-WSD11-DR-M-1201-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1201 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1664 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1202 | A.1 | 131242-WSD11-DR-M-1202-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1202 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1665 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1203 | A.1 | 131242-WSD11-DR-M-1203-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1203 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1666 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1204 | A.1 | 131242-WSD11-DR-M-1204-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1204 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1667 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1205 | A.1 | 131242-WSD11-DR-M-1205-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1205 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" | 2025-05-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292 | 2025-05-09, 2025-11-28 | 02, 03 | 2 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1668 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 3000 | A | 131242-WSD11-DR-M-3000-A | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | PEN | PEN
1669 | 000292 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 8000 | A.1 | 131242-WSD11-DR-M-8000-A.1 | 2025-11-28 | Milestone 3 THP Overall & Equipment Layout | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-8000 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-12 | 129 | PEN | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2026-01-15 |  | 0 | PEN | PEN
1670 | 000293 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0018 | 0 | 131242-WSD11-CD-IM-0018-0 | 2024-02-01 | Milestone 1.1 THP A100 Silo Area inside Biosolid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-CD-0018 | NA | "Milestone 1.1 THP A100 Silo Area inside Biosolid Building" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 56 | AWC | 2024-02-01 | 0 | 000293 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
1671 | 000293 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-IM-0030-0 | 2024-06-11 | Milestone 1.2 THP A100 Silo Area inside Biosolid Building | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSD11-CD-0030 | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 24 | AWC | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1672 | 000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 0 | 131242-WSD11-CD-IM-0030-0 | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 2: Not approved - Revise and Resubmit. No Electrical / ICA Cutsheets attached with submittal. | 2024-11-28 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-CD-0030 | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-23 | 26 | NAP | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1673 | 000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1130 | A | 131242-WSD11-DR-M-1130-A | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-1130 | NA | "Milestone 2 THP A100 Silo Area inside Biosolid Building" | 2024-11-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-29 | 26 | NAP | 2024-11-09 | A | 000293 | 2024-11-09 | 02 | 1 | Not Approved | NAP | 2024-12-25 | Overdue | 0 | NAP | NAP
1674 | 000293 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1131 | A | 131242-WSD11-DR-M-1131-A | 2024-11-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Please arrange discussion with S.O. team for MS2 cutsheet requirements used for inspections. PDF file for cutsheets shall be also attached for S.O. Review. | 2024-11-28 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-1131 | NA | "Milestone 2 THP A100 Silo Area inside Biosolid Building" | 2024-11-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-29 | 26 | NAP | 2024-11-09 | A | 000293 | 2024-11-09 | 02 | 1 | Not Approved | NAP | 2024-12-25 | Overdue | 0 | NAP | NAP
1675 | 000293 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-IM-0030-1 | 2025-04-09 | Milestone 2 THP A100 Silo Area inside Biosolid Building | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-29 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-CD-0030 | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 84 | AWC | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1676 | 000293 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0030 | 1 | 131242-WSD11-CD-IM-0030-1 | 2025-10-31 | Milestone 3 THP A100 Silo Area inside Biosolid Building | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WSD11-CD-0030 | NA | "Milestone 1.2 THP A100 Silo Area inside Biosolid Building" && "Milestone 2 THP A100 Silo Area inside Biosolid Building" && "Milestone 3 THP A100 Silo Area inside Biosolid Building" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 112 | AWC | 2025-10-31 | 1 | 000293 | 2024-06-11, 2024-11-09, 2025-04-09, 2025-10-31 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
1677 | 000294 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0019 | 0 | 131242-WSD11-CD-IM-0019-0 | 2024-02-01 | Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-CD-0019 | NA | "Milestone 1.1 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 56 | AWC | 2024-02-01 | 0 | 000294 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
1678 | 000294 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-IM-0032-0 | 2024-06-11 | Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSD11-CD-0032 | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 24 | AWC | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1679 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 0 | 131242-WSD11-CD-IM-0032-0 | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-CD-0032 | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-17 | 45 | REJ | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1680 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_WD | A | 131242-WSD11-DR-B-1003_WD-A | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1003_WD | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2024-12-03 | A | 000294 | 2024-12-03 | 02 | 1 | Rejected | REJ | 2025-02-06 | Overdue | 0 | REJ | REJ
1681 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_WD | A | 131242-WSD11-DR-BH-1000_WD-A | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1000_WD | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2024-12-03 | A | 000294 | 2024-12-03 | 02 | 1 | Rejected | REJ | 2025-02-06 | Overdue | 0 | REJ | REJ
1682 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_WD | A | 131242-WSD11-DR-BH-1001_WD-A | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1001_WD | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2024-12-03 | A | 000294 | 2024-12-03 | 02 | 1 | Rejected | REJ | 2025-02-06 | Overdue | 0 | REJ | REJ
1683 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_WD | A | 131242-WSD11-DR-BH-1002_WD-A | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1002_WD | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2024-12-03 | A | 000294 | 2024-12-03 | 02 | 1 | Rejected | REJ | 2025-02-06 | Overdue | 0 | REJ | REJ
1684 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_WD | A | 131242-WSD11-DR-BH-3000_WD-A | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-3000_WD | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2024-12-03 | A | 000294 | 2024-12-03 | 02 | 1 | Rejected | REJ | 2025-02-06 | Overdue | 0 | REJ | REJ
1685 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175 | A_WD | 131242-WSD11-DR-M-1175-A_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1175 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1686 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176 | A_WD | 131242-WSD11-DR-M-1176-A_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1176 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1687 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177 | A_WD | 131242-WSD11-DR-M-1177-A_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1177 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1688 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178 | A_WD | 131242-WSD11-DR-M-1178-A_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1178 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1689 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179 | A_WD | 131242-WSD11-DR-M-1179-A_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1179 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1690 | 000294 | 02 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180 | A_WD | 131242-WSD11-DR-M-1180-A_WD | 2024-12-03 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 2: To reject and resubmit as per CES request. | 2024-12-23 | 2025-01-17 | Rejected | 2025-02-06 | YES | Resubmitted |  | 131242-WSD11-DR-1180 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-23 | 45 | REJ | 2025-08-13 | B | 000294&&001382 | 2024-12-03, 2025-06-16, 2025-08-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1691 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-IM-0032-1 | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-CD-0032 | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 162 | AWC | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1692 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_MS2 | A | 131242-WSD11-DR-B-1003_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1003_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1693 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | A | 131242-WSD11-DR-BH-1000_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1000_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1694 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | A | 131242-WSD11-DR-BH-1001_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1001_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1695 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | A | 131242-WSD11-DR-BH-1002_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1002_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1696 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | A | 131242-WSD11-DR-BH-3000_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-3000_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1697 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175_MS2 | A | 131242-WSD11-DR-M-1175_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1175_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1698 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176_MS2 | A | 131242-WSD11-DR-M-1176_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1176_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1699 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177_MS2 | A | 131242-WSD11-DR-M-1177_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1177_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1700 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178_MS2 | A | 131242-WSD11-DR-M-1178_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1178_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1701 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179_MS2 | A | 131242-WSD11-DR-M-1179_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1179_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1702 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180_MS2 | A | 131242-WSD11-DR-M-1180_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1180_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1703 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1140_MS2 | A | 131242-WSD11-DR-M-1140_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1140_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1704 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1141_MS2 | A | 131242-WSD11-DR-M-1141_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1141_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1705 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1142_MS2 | A | 131242-WSD11-DR-M-1142_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1142_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1706 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1143_MS2 | A | 131242-WSD11-DR-M-1143_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1143_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1707 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1144_MS2 | A | 131242-WSD11-DR-M-1144_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1144_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1708 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1145_MS2 | A | 131242-WSD11-DR-M-1145_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1145_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1709 | 000294 | 03 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1146_MS2 | A | 131242-WSD11-DR-M-1146_MS2-A | 2025-01-21 | Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-DR-1146_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-10 | 162 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1710 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | CD | IM | 0032 | 1 | 131242-WSD11-CD-IM-0032-1 | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-CD-0032 | NA | "Milestone 1.2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | 1 | 000294 | 2024-06-11, 2024-12-03, 2025-01-21, 2025-10-27 | 01, 02, 03, 04 | 4 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1711 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | B | 1003_MS2 | A | 131242-WSD11-DR-B-1003_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1003_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1712 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1000_MS2 | A | 131242-WSD11-DR-BH-1000_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1000_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1713 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1001_MS2 | A | 131242-WSD11-DR-BH-1001_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1001_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1714 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 1002_MS2 | A | 131242-WSD11-DR-BH-1002_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1002_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1715 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | BH | 3000_MS2 | A | 131242-WSD11-DR-BH-3000_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-3000_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1716 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1175_MS2 | A | 131242-WSD11-DR-M-1175_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1175_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1717 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1176_MS2 | A | 131242-WSD11-DR-M-1176_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1176_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1718 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1177_MS2 | A | 131242-WSD11-DR-M-1177_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1177_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1719 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1178_MS2 | A | 131242-WSD11-DR-M-1178_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1178_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1720 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1179_MS2 | A | 131242-WSD11-DR-M-1179_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1179_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1721 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1180_MS2 | A | 131242-WSD11-DR-M-1180_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1180_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1722 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1140_MS2 | A | 131242-WSD11-DR-M-1140_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1140_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1723 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1141_MS2 | A | 131242-WSD11-DR-M-1141_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1141_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1724 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1142_MS2 | A | 131242-WSD11-DR-M-1142_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1142_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1725 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1143_MS2 | A | 131242-WSD11-DR-M-1143_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1143_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1726 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1144_MS2 | A | 131242-WSD11-DR-M-1144_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1144_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1727 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1145_MS2 | A | 131242-WSD11-DR-M-1145_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1145_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1728 | 000294 | 04 | Heng Peng/ Muthu | BIM | NA | 131242 | WSD11 | DR | M | 1146_MS2 | A | 131242-WSD11-DR-M-1146_MS2-A | 2025-10-27 | Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-DR-1146_MS2 | NA | "Milestone 2 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" && "Milestone 3 THP Interconnecting Piping, Underground Services, Fire Protection, A200 Coolers & Recirculation Pumps" | 2025-01-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | A | 000294 | 2025-01-21, 2025-10-27 | 03, 04 | 2 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1729 | 000295 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 0 | 131242-WSW41-VI-M-0017-0 | 2024-02-01 | Preliminary Design and Vendor Approval of Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-01 | 2024-04-16 | Approved with Comments | 2024-05-07 | YES | Resubmitted | Related to Tank accessories. In Progress. To check the lead time after PO issue to meet the ROS date (1st Wk of Oct 24) | 131242-WSW41-VI-0017 | NA | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" && "Vendor Approval for PVC Lining System - (Linabond)" | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 75 | AWC | 2024-07-31 | 1 | 000295&&000577 | 2024-02-01, 2024-07-17, 2024-07-31 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1730 | 000295 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0017 | 1 | 131242-WSW41-VI-M-0017-1 | 2024-07-31 | Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-08-21 | 2024-08-29 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0017 | NA | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" && "Vendor Approval for PVC Lining System - (Linabond)" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 29 | AWC | 2024-07-31 | 1 | 000295&&000577 | 2024-02-01, 2024-07-17, 2024-07-31 | 00, 01 | 3 | Approved with Comments | AWC | 2024-09-18 | Overdue | 0 | AWC | AWC
1731 | 000296 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 0 | 131242-WSW41-SP-C-0004-0 | 2024-02-01 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Not Approved. Please refer to comment sheet for resubmission. | 2024-03-01 | 2024-02-16 | Not Approved | 2024-03-07 | YES | Resubmitted |  | 131242-WSW41-SP-0004 | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 15 | NAP | 2024-07-15 | 2 | 000296 | 2024-02-01, 2024-06-13, 2024-07-15 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
1732 | 000296 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 1 | 131242-WSW41-SP-C-0004-1 | 2024-06-13 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-28 | Not Approved | 2024-07-18 | YES | Resubmitted |  | 131242-WSW41-SP-0004 | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-27 | 15 | NAP | 2024-07-15 | 2 | 000296 | 2024-02-01, 2024-06-13, 2024-07-15 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
1733 | 000296 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0004 | 2 | 131242-WSW41-SP-C-0004-2 | 2024-07-15 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance) | Rev.2: Approved | 2024-08-02 | 2024-08-12 | Approved |  | YES | NA |  | 131242-WSW41-SP-0004 | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (Alliance)" | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-29 | 28 | APP | 2024-07-15 | 2 | 000296 | 2024-02-01, 2024-06-13, 2024-07-15 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
1734 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A | 131242-WSW41-DR-M-5100-A | 2024-02-01 | Pipe Support Standard - General Notes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - General Notes" && "Pipe Support Standard- SWPR" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2026-01-19 | E | 000297&&000909&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1735 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A | 131242-WSW41-DR-M-5101-A | 2024-02-01 | Pipe Support Standard - S01 U-Bolt | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S01 U-Bolt" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1736 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5102 | A | 131242-WSW41-DR-M-5102-A | 2024-02-01 | Pipe Support Standard - S02 SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5102 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1737 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5103 | A | 131242-WSW41-DR-M-5103-A | 2024-02-01 | Pipe Support Standard - S03 PAD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5103 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S03 PAD" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1738 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A | 131242-WSW41-DR-M-5104-A | 2024-02-01 | Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5104 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1739 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5105 | A | 131242-WSW41-DR-M-5105-A | 2024-02-01 | Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5105 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-12-29 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1740 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5106 | A | 131242-WSW41-DR-M-5106-A | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5106 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S06 DUMMY PIPE SHEET 1" | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-12-29 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
1741 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5107 | A | 131242-WSW41-DR-M-5107-A | 2024-02-01 | Pipe Support Standard - S06 DUMMY PIPE SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5107 | NA | "Pipe Support Standard - S06 DUMMY PIPE SHEET 2" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1742 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5108 | A | 131242-WSW41-DR-M-5108-A | 2024-02-01 | Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5108 | NA | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1743 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5109 | A | 131242-WSW41-DR-M-5109-A | 2024-02-01 | Pipe Support Standard - S08 SLIDE STOOL | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5109 | NA | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1744 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5110 | A | 131242-WSW41-DR-M-5110-A | 2024-02-01 | Pipe Support Standard - S09 TIGHT STOOL | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5110 | NA | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1745 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A | 131242-WSW41-DR-M-5111-A | 2024-02-01 | Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5111 | NA | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-06-25 | A.2 | 000297 | 2024-02-01, 2025-03-13, 2025-06-25 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1746 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5112 | A | 131242-WSW41-DR-M-5112-A | 2024-02-01 | Pipe Support Standard - S11 GUIDE FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5112 | NA | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1747 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5113 | A | 131242-WSW41-DR-M-5113-A | 2024-02-01 | Pipe Support Standard - S12 STOPPER FOR SHOE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5113 | NA | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1748 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5114 | A | 131242-WSW41-DR-M-5114-A | 2024-02-01 | Pipe Support Standard - S13 BRACKET SUPPORT | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5114 | NA | "Pipe Support Standard - S13 BRACKET SUPPORT" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1749 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5115 | A | 131242-WSW41-DR-M-5115-A | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5115 | NA | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 1" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1750 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5116 | A | 131242-WSW41-DR-M-5116-A | 2024-02-01 | Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5116 | NA | "Pipe Support Standard - S14 U-TYPE SUPPORT SHEET 2" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1751 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5117 | A | 131242-WSW41-DR-M-5117-A | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5117 | NA | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 1" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1752 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5118 | A | 131242-WSW41-DR-M-5118-A | 2024-02-01 | Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2 | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5118 | NA | "Pipe Support Standard - S15 ANGLE SUPPORT SHEET 2" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1753 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5119 | A | 131242-WSW41-DR-M-5119-A | 2024-02-01 | Pipe Support Standard - S16 STANCHION | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5119 | NA | "Pipe Support Standard - S16 STANCHION" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1754 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5120 | A | 131242-WSW41-DR-M-5120-A | 2024-02-01 | Pipe Support Standard - S17 STANCHION (REINFORCED) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5120 | NA | "Pipe Support Standard - S17 STANCHION (REINFORCED)" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1755 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5121 | A | 131242-WSW41-DR-M-5121-A | 2024-02-01 | Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5121 | NA | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1756 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5122 | A | 131242-WSW41-DR-M-5122-A | 2024-02-01 | Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5122 | NA | "Pipe Support Standard - S19 FLANGE & VALVE SUPPORT FOR NON-METALLIC PIPING" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1757 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5123 | A | 131242-WSW41-DR-M-5123-A | 2024-02-01 | Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5123 | NA | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1758 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5124 | A | 131242-WSW41-DR-M-5124-A | 2024-02-01 | Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5124 | NA | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1759 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5125 | A | 131242-WSW41-DR-M-5125-A | 2024-02-01 | Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5125 | NA | "Pipe Support Standard - S22 LOW HEADROOM CLAMP SHOE (DN15 ~ DN450)" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1760 | 000297 | 00 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5126 | A | 131242-WSW41-DR-M-5126-A | 2024-02-01 | Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-01 | 2024-05-29 | Approved with Comments | 2024-06-19 | YES | Resubmitted |  | 131242-WSW41-DR-5126 | NA | "Pipe Support Standard - S23 LOW HEADROOM CLAMP SHOE (DN500 ~ DN1200)" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-21 | 118 | AWC | 2024-02-01 | A | 000297 | 2024-02-01 | 00 | 1 | Approved with Comments | AWC | 2024-06-18 | Overdue | 0 | AWC | AWC
1761 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5100 | A.1 | 131242-WSW41-DR-M-5100-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - General Notes" && "Pipe Support Standard- SWPR" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2026-01-19 | E | 000297&&000909&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1762 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.1 | 131242-WSW41-DR-M-5101-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S01 U-Bolt" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1763 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5102 | A.1 | 131242-WSW41-DR-M-5102-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5102 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1764 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5103 | A.1 | 131242-WSW41-DR-M-5103-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5103 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S03 PAD" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1765 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A.1 | 131242-WSW41-DR-M-5104-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5104 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1766 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5105 | A.1 | 131242-WSW41-DR-M-5105-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5105 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-12-29 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
1767 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5108 | A.1 | 131242-WSW41-DR-M-5108-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5108 | NA | "Pipe Support Standard - S07 TRUNNION FOR VERTICAL PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1768 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5109 | A.1 | 131242-WSW41-DR-M-5109-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5109 | NA | "Pipe Support Standard - S08 SLIDE STOOL" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1769 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5110 | A.1 | 131242-WSW41-DR-M-5110-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5110 | NA | "Pipe Support Standard - S09 TIGHT STOOL" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1770 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A.1 | 131242-WSW41-DR-M-5111-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5111 | NA | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-06-25 | A.2 | 000297 | 2024-02-01, 2025-03-13, 2025-06-25 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1771 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5112 | A.1 | 131242-WSW41-DR-M-5112-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5112 | NA | "Pipe Support Standard - S11 GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1772 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5113 | A.1 | 131242-WSW41-DR-M-5113-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5113 | NA | "Pipe Support Standard - S12 STOPPER FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1773 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5121 | A.1 | 131242-WSW41-DR-M-5121-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5121 | NA | "Pipe Support Standard - S18 U-BOLT FOR NON-METALLIC" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1774 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5123 | A.1 | 131242-WSW41-DR-M-5123-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5123 | NA | "Pipe Support Standard - S20 CLAMP SHOE (DN15 ~ DN450)" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1775 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5124 | A.1 | 131242-WSW41-DR-M-5124-A.1 | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5124 | NA | "Pipe Support Standard - S21 CLAMP SHOE (DN500 ~ DN1200)" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 20 | AWC | 2025-03-13 | A.1 | 000297 | 2024-02-01, 2025-03-13 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-22 | Overdue | 0 | AWC | AWC
1776 | 000297 | 01 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5140 | A | 131242-WSW41-DR-M-5140-A | 2025-03-13 | Standard Pipe Support - For All Area | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-02 | 2025-04-02 | Approved with Comments | 2025-04-22 | YES | Resubmitted |  | 131242-WSW41-DR-5140 | NA | "Standard Pipe Support - For All Area " | 2025-03-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-02 | 20 | AWC | 2025-06-25 | A.1 | 000297 | 2025-03-13, 2025-06-25 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1777 | 000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5101 | A.2 | 131242-WSW41-DR-M-5101-A.2 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DR-5101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S01 U-Bolt" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-09 | 103 | AWC | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
1778 | 000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5104 | A.2 | 131242-WSW41-DR-M-5104-A.2 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DR-5104 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-09 | 103 | AWC | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
1779 | 000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5111 | A.2 | 131242-WSW41-DR-M-5111-A.2 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DR-5111 | NA | "Pipe Support Standard - S10 HOLD DOWN GUIDE FOR SHOE" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-09 | 103 | AWC | 2025-06-25 | A.2 | 000297 | 2024-02-01, 2025-03-13, 2025-06-25 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
1780 | 000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5139 | A | 131242-WSW41-DR-M-5139-A | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DR-5139 | NA | "Standard Pipe Support - For All Area " | 2025-06-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-15 | 103 | AWC | 2025-06-25 | A | 000297 | 2025-06-25 | 02 | 1 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
1781 | 000297 | 02 | Kyaw Myo | Piping | NA | 131242 | WSW41 | DR | M | 5140 | A.1 | 131242-WSW41-DR-M-5140-A.1 | 2025-06-25 | Standard Pipe Support - For All Area | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-07-15 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WSW41-DR-5140 | NA | "Standard Pipe Support - For All Area " | 2025-03-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-07-09 | 103 | AWC | 2025-06-25 | A.1 | 000297 | 2025-03-13, 2025-06-25 | 01, 02 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
1782 | 000298 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0017 | 0 | 131242-WSW41-MI-P-0017-0 | 2024-02-02 | Process & MEICA Meeting Minutes 0017_20240118 | Rev 0: For Information | 2024-03-04 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0017 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-22 | 109 | INF | 2024-10-31 | 0 | 000298&&000320&&000339&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1783 | 000299 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 0 | 131242-WST02-VI-E-0002-0 | 2024-02-03 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-03-04 | 2024-03-01 | Approved with Comments | 2024-03-21 | YES | Resubmitted |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-23 | 27 | AWC | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
1784 | 000299 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 1 | 131242-WST02-VI-E-0002-1 | 2024-03-25 | Vendor Approval of MV Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-04-16 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-08 | 59 | AWC | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
1785 | 000299 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 2 | 131242-WST02-VI-E-0002-2 | 2024-06-07 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached for comments. | 2024-06-28 | 2024-08-15 | Approved with Comments | 2024-09-04 | YES | Resubmitted |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 69 | AWC | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
1786 | 000299 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0002 | 3 | 131242-WST02-VI-E-0002-3 | 2024-10-16 | Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab) | Rev 3: Approved. | 2024-11-06 | 2024-11-04 | Approved |  | YES | NA |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-30 | 19 | APP | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | APP | APP
1787 | 000300 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0003 | 0 | 131242-WSW41-PS-HS-0003-0 | 2024-02-03 | Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024 | Rev 0: Noted for information | 2024-03-04 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-PS-0003 | NA | "Presentation Slide for Monthly Progress Meeting No. 03(0723)" && "Quarterly Risk Management Workshop 2nd Quarterly RM Workshop – 26 Jan 2024" | 2023-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-02-17 | 44 | INF | 2024-02-03 | 0 | 000077&&000300 | 2023-08-28, 2024-02-03 | 00 | 2 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
1788 | 000301 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0008 | 0 | 131242-WSW41-MI-PM-0008-0 | 2024-02-05 | Monthly Progress Meeting Minutes 0008_20240123 | For Information | 2024-03-05 | 2024-02-07 | For Information |  | YES | NA |  | 131242-WSW41-MI-0008 | NA | "BIM Bi-Weekly Meeting Minutes 0008_20230920" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0008_20240123" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-02-19 | 2 | INF | 2024-02-05 | 0 | 000063&&000104&&000114&&000301 | 2023-08-07, 2023-09-19, 2023-10-05, 2024-02-05 | 00 | 4 | For Information | INF | 2024-02-27 | Overdue | 0 | INF | INF
1789 | 000302 | 00 | Leon | BIM | NA | 131242 | WSD11 | CD | IM | 0014 | 0 | 131242-WSD11-CD-IM-0014-0 | 2024-02-06 | Milestone 1.1 THP Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Refer to the comments sheet. | 2024-03-06 | 2024-03-28 | Approved with Comments | 2024-04-19 | YES | Resubmitted |  | 131242-WSD11-CD-0014 | NA | "Milestone 1.1 THP Compressed Air System" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 51 | AWC | 2024-02-06 | 0 | 000302 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-04-17 | Overdue | 0 | AWC | AWC
1790 | 000302 | 01 | Nicolas | BIM | NA | 131242 | WSD11 | CD | IM | 0029 | 0 | 131242-WSD11-CD-IM-0029-0 | 2024-06-11 | Milestone 1.2 THP Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-02 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WSD11-CD-0029 | NA | "Milestone 1.2 THP Compressed Air System" | 2024-06-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-01 | 24 | AWC | 2024-06-11 | 0 | 000302 | 2024-06-11 | 01 | 1 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
1791 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 0 | 131242-WSD11-CD-IM-0047-0 | 2024-10-17 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-CD-0047 | NA | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-06 | 49 | NAP | 2025-10-27 | 2 | 000302 | 2024-10-17, 2025-04-10, 2025-10-27 | 02, 03, 04 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1792 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1165 | A.1 | 131242-WSD11-DR-M-1165-A.1 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-1165 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1793 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | M | 1166 | A.1 | 131242-WSD11-DR-M-1166-A.1 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-1166 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1794 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1020 | A | 131242-WSD11-DR-E-1020-A | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-1020 | NA | "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" | 2024-10-18 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-07 | 48 | NAP | 2025-10-28 | B | 000302&&001328 | 2024-10-18, 2025-05-28, 2025-10-28 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1795 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 1021 | A | 131242-WSD11-DR-E-1021-A | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-1021 | NA | "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" | 2024-10-18 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-07 | 48 | NAP | 2025-10-28 | B | 000302&&001328 | 2024-10-18, 2025-10-28 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1796 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3000 | A | 131242-WSD11-DR-E-3000-A | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | NAP | NAP
1797 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSD11 | DR | E | 3001 | A | 131242-WSD11-DR-E-3001-A | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1798 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 1000 | A.1_MS2 | 131242-WSB01-DR-BH-1000-A.1_MS2 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSB01-DR-1000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1799 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 3000 | A.1_MS2 | 131242-WSB01-DR-BH-3000-A.1_MS2 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSB01-DR-3000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1800 | 000302 | 02 | Heng Peng | BIM | NA | 131242 | WSB01 | DR | BH | 5000 | A.1_MS2 | 131242-WSB01-DR-BH-5000-A.1_MS2 | 2024-10-18 | Milestone 2 THP Compressed Air System | Rev 2: Not approved - Revise and Resubmit Please refer attached sheet for comments. 2D cut sheets are not included for EICA. | 2024-11-07 | 2024-12-05 | Not Approved | 2024-12-26 | YES | Resubmitted |  | 131242-WSB01-DR-5000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 48 | NAP | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1801 | 000302 | 03 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 1 | 131242-WSD11-CD-IM-0047-1 | 2025-04-10 | Milestone 2 THP Compressed Air System | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-30 | 2025-07-02 | Approved with Comments | 2025-07-22 | YES | Resubmitted |  | 131242-WSD11-CD-0047 | NA | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-24 | 83 | AWC | 2025-10-27 | 2 | 000302 | 2024-10-17, 2025-04-10, 2025-10-27 | 02, 03, 04 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1802 | 000302 | 04 | Heng Peng | BIM | NA | 131242 | WSD11 | CD | IM | 0047 | 2 | 131242-WSD11-CD-IM-0047-2 | 2025-10-27 | Milestone 3 THP Compressed Air System | Rev 4: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WSD11-CD-0047 | NA | "Milestone 2 THP Compressed Air System" && "Milestone 3 THP Compressed Air System" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-10 | 119 | AWC | 2025-10-27 | 2 | 000302 | 2024-10-17, 2025-04-10, 2025-10-27 | 02, 03, 04 | 3 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
1803 | 000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1003_ST605_BCA | A1 | 131242-WST02-DR-C-1003_ST605_BCA-A1 | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | Approved with Comments | 2024-03-12 | NO | Overdue | Heng Peng to provide DGN drawing | 131242-WST02-DR-1003_ST605_BCA | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 15 | AWC | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-03-12 | Overdue | 0 | AWC | AWC
1804 | 000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 1004_ST605_BCA | A1 | 131242-WST02-DR-C-1004_ST605_BCA-A1 | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | Approved with Comments | 2024-03-12 | NO | Overdue |  | 131242-WST02-DR-1004_ST605_BCA | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 15 | AWC | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-03-12 | Overdue | 0 | AWC | AWC
1805 | 000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 5002_ST605_BCA | A1 | 131242-WST02-DR-C-5002_ST605_BCA-A1 | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | Approved with Comments | 2024-03-12 | NO | Overdue |  | 131242-WST02-DR-5002_ST605_BCA | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 15 | AWC | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-03-12 | Overdue | 0 | AWC | AWC
1806 | 000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | 7001_ST605_BCA | A1 | 131242-WST02-DR-C-7001_ST605_BCA-A1 | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | Approved with Comments | 2024-03-12 | NO | Overdue |  | 131242-WST02-DR-7001_ST605_BCA | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 15 | AWC | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-03-12 | Overdue | 0 | AWC | AWC
1807 | 000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | C | 8001_ST605_BCA | A1 | 131242-WST00-DR-C-8001_ST605_BCA-A1 | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | Approved with Comments | 2024-03-12 | NO | Overdue |  | 131242-WST00-DR-8001_ST605_BCA | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 15 | AWC | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-03-12 | Overdue | 0 | AWC | AWC
1808 | 000303 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | C | ST605-NOA | A1 | 131242-WST02-DR-C-ST605-NOA-A1 | 2024-02-06 | ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-03-06 | 2024-02-21 | Approved with Comments | 2024-03-12 | NO | Overdue |  | 131242-WST02-DR-ST605-NOA | NA | "ST605_SSN Piling Layout of Main Water Tanks (BCA Approved Drawings-PDF only)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-26 | 15 | AWC | 2024-02-06 | A1 | 000303 | 2024-02-06 | 00 | 1 | Approved with Comments | AWC | 2024-03-12 | Overdue | 0 | AWC | AWC
1809 | 000304 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0020 | 0 | 131242-WSW41-CD-IM-0020-0 | 2024-02-06 | Submission Of BIM Coordination VCM Model (Jan–2024) | For Information | 2024-03-06 | 2024-02-22 | For Information |  | YES | NA |  | 131242-WSW41-CD-0020 | NA | "Submission Of BIM Coordination VCM Model (Jan–2024)" | 2024-02-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-02-26 | 16 | INF | 2024-02-06 | 0 | 000304 | 2024-02-06 | 00 | 1 | For Information | INF | 2024-03-13 | Overdue | 0 | INF | INF
1810 | 000305 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0009 | 0 | 131242-WSW41-RT-PM-0009-0 | 2024-02-08 | C4B Monthly Progress Report Number No.09 (01 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-03-08 | 2024-03-08 | Approved with Comments | 2024-03-28 | NO | Overdue |  | 131242-WSW41-RT-0009 | NA | "C4B Monthly Progress Report Number No.09 (01 24)" | 2024-02-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-28 | 29 | AWC | 2024-02-08 | 0 | 000305 | 2024-02-08 | 00 | 1 | Approved with Comments | AWC | 2024-03-28 | Overdue | 0 | AWC | AWC
1811 | 000306 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0008 | 0 | 131242-WSW41-PC-W-0008-0 | 2024-02-08 | Payment Claim No. 8 | Rev(0): Approved. Refer to S.O. correspondence no. 121 dated 9 Feb 2024. | 2024-03-08 | 2024-05-10 | Approved |  | YES | NA |  | 131242-WSW41-PC-0008 | NA | "Payment Claim No. 8" | 2024-02-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-02-28 | 92 | APP | 2024-02-08 | 0 | 000306 | 2024-02-08 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1812 | 000307 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | A | 131242-WST02-DR-EP-5000-A | 2024-02-13 | Typical Installation Details for Power | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | Rejected | 2024-06-03 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-27 | 90 | REJ | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
1813 | 000307 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 5000 | B | 131242-WST02-DR-EP-5000-B | 2025-03-25 | Typical Installation Details for Power | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | Not Approved | 2025-05-26 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 42 | NAP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1814 | 000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7002 | A | 131242-WST02-DR-E-7002-A | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | Not Approved | 2024-05-29 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-27 | 85 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1815 | 000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | A | 131242-WST02-DR-E-7003-A | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | Not Approved | 2024-05-29 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-27 | 85 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1816 | 000308 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | A | 131242-WST02-DR-E-7004-A | 2024-02-13 | SSN Single Line Diagram for MOV DB | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for commments. | 2024-03-12 | 2024-05-08 | Not Approved | 2024-05-29 | YES | Resubmitted |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-27 | 85 | NAP | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1817 | 000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | B | 131242-WST02-DR-E-7003-B | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 115 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1818 | 000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | B | 131242-WST02-DR-E-7004-B | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 115 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1819 | 000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7005 | B | 131242-WST02-DR-E-7005-B | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 115 | AWC | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1820 | 000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7006 | B | 131242-WST02-DR-E-7006-B | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 115 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
1821 | 000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7007 | B | 131242-WST02-DR-E-7007-B | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 115 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | AWC | AWC
1822 | 000308 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7008 | B | 131242-WST02-DR-E-7008-B | 2024-07-06 | SSN Single Line Diagram for MOV DB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 115 | AWC | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | AWC | AWC
1823 | 000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7003 | C | 131242-WST02-DR-E-7003-C | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 42 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1824 | 000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7004 | C | 131242-WST02-DR-E-7004-C | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 42 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1825 | 000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7005 | C | 131242-WST02-DR-E-7005-C | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 42 | AWC | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1826 | 000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7006 | C | 131242-WST02-DR-E-7006-C | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 42 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
1827 | 000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7007 | C | 131242-WST02-DR-E-7007-C | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 42 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | AWC | AWC
1828 | 000308 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7008 | C | 131242-WST02-DR-E-7008-C | 2025-03-27 | SSN Single Line Diagram for MOV DB | Approved with comment. Please refer to comment sheet for resubmission. | 2025-04-16 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-10 | 42 | AWC | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | AWC | AWC
1829 | 000309 | 00 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | A | 131242-WST02-BQ-E-0003-A | 2024-02-13 | SSN Listing of Interface Points | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | Approved with Comments | 2024-06-05 | YES | Resubmitted |  | 131242-WST02-BQ-0003 | NA | "SSN Listing of Interface Points" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-04 | 92 | AWC | 2024-07-22 | B | 000309 | 2024-02-13, 2024-07-22 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1830 | 000309 | 01 | Freedomer | EICA | NA | 131242 | WST02 | BQ | E | 0003 | B | 131242-WST02-BQ-E-0003-B | 2024-07-22 | SSN Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted | No need to resubmit as there is no major updates made - "Please resubmit if there are major updates or changes to the information stated". | 131242-WST02-BQ-0003 | NA | "SSN Listing of Interface Points" | 2024-02-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 99 | AWC | 2024-07-22 | B | 000309 | 2024-02-13, 2024-07-22 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
1831 | 000310 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | A | 131242-WST02-DR-EL-5000-A | 2024-02-13 | Typical Installation Details for Lighting | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-13 | Not Approved | 2024-06-03 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-27 | 90 | NAP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1832 | 000310 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EL | 5000 | B | 131242-WST02-DR-EL-5000-B | 2025-03-25 | Typical Installation Details for Lighting | Rev 1: Not Approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-14 | 2025-05-06 | Not Approved | 2025-05-26 | NO | Overdue | To check with C2D | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-08 | 42 | NAP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1833 | 000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | A | 131242-WSD11-DR-EK-1000-A | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | Not Approved | 2024-06-05 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-02-27 | 92 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
1834 | 000311 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 3000 | A | 131242-WSD11-DR-EK-3000-A | 2024-02-13 | THP Lightning Protection System | Rev 0: Rejected. Refer to attached file for comments. | 2024-03-12 | 2024-05-15 | Not Approved | 2024-06-05 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-04 | 92 | NAP | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | NAP | NAP
1835 | 000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 1000 | B | 131242-WSD11-DR-EK-1000-B | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
1836 | 000311 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EK | 3000 | B | 131242-WSD11-DR-EK-3000-B | 2025-02-25 | THP Lightning Protection System | Rev 1: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-17 | 2025-05-05 | Approved with Comments | 2025-05-23 | NO | Overdue |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-11 | 69 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
1837 | 000312 | 00 | Soe Myat | PMT | NA | 131242 | WSW41 | LT | PM | 0022 | 0 | 131242-WSW41-LT-PM-0022-0 | 2024-02-14 | CV of Team Member (QA/QC Manager) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-03-13 | 2024-02-19 | Approved with Comments | 2024-03-08 | NO | Overdue |  | 131242-WSW41-LT-0022 | NA | "CV of Team Member (QA/QC Manager)" | 2024-02-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-05 | 5 | AWC | 2024-02-14 | 0 | 000312 | 2024-02-14 | 00 | 1 | Approved with Comments | AWC | 2024-03-08 | Overdue | 0 | AWC | AWC
1838 | 000313 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0018 | 0 | 131242-WSW41-MI-P-0018-0 | 2024-02-15 | Process & MEICA Meeting Minutes 0018_20240201 | Rev 0: For Information | 2024-03-14 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0018 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0018_20241113" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-06 | 96 | INF | 2024-11-30 | 0 | 000313&&000320&&000339&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1839 | 000314 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | RT | HS | 0001 | 0 | 131242-WSW41-RT-HS-0001-0 | 2024-02-15 | 1st CONSAAS Audit report_2023 | Rev 0: Noted for information | 2024-03-14 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-RT-0001 | NA | "1st CONSAAS Audit report_2023" && "Photographic Survey Report for C4B" && "UXO Scanning Report" | 2023-08-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-02-29 | 32 | INF | 2024-02-15 | 0 | 000078&&000228&&000314 | 2023-08-24, 2023-12-05, 2024-02-15 | 00 | 3 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
1840 | 000315 | 00 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 0 | 131242-WSW41-VI-I-0001-0 | 2024-02-19 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-03-18 | 2024-04-08 | Approved with Comments | 2024-04-29 | YES | Resubmitted |  | 131242-WSW41-VI-0001 | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-04 | 49 | AWC | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1841 | 000315 | 01 | Zuo Yu | EICA | NA | 131242 | WSW41 | VI | I | 0001 | 1 | 131242-WSW41-VI-I-0001-1 | 2024-04-15 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-05-15 | Approved with Comments | 2024-06-05 | YES | Resubmitted |  | 131242-WSW41-VI-0001 | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" && "Preliminary design and Vendor Approval for FRP Tank (JIZHOU ZHONGYI)" && "Vendor Approval of ALMOP & HAZOP Facilities studies and Workshops (Puri-Teq)" | 2023-09-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 30 | AWC | 2024-04-15 | 1 | 000090&&000250&&000315 | 2023-09-07, 2023-12-22, 2024-02-19, 2024-04-15 | 00, 01 | 4 | Approved with Comments | AWC | 2024-06-04 | Overdue | 0 | AWC | AWC
1842 | 000315 | 02 | Balaji/ Karthik | EICA | NA | Comment Reply Sheet 20240716 | NA | NA | NA | 9999 | A.C | Comment Reply Sheet 20240716-----A.C | 2024-07-17 | Preliminary Design and Vendor Approval of ICA Instrument ELV Cable | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | Approved with Comments | 2024-10-07 | NO | Overdue |  | Comment Reply Sheet 20240716-NA-NA-9999 | NA | "Preliminary Design and Vendor Approval of ICA Instrument ELV Cable" | 2024-07-17 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-06 | 62 | AWC | 2024-07-17 | A.C | 000315 | 2024-07-17 | 02 | 1 | Approved with Comments | AWC | 2024-10-07 | Overdue | 0 | AWC | AWC
1843 | 000316 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0001 | 0 | 131242-WSW41-QA-M-0001-0 | 2024-02-20 | Inspection Test Plan for Structural Steel Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-19 | 2024-08-14 | Not Approved | 2024-09-03 | NO | Overdue |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-05 | 176 | NAP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | NAP | NAP
1844 | 000317 | 00 | Dharmen | HSE | NA | 131242 | WSW41 | VI | HS | 0002 | 0 | 131242-WSW41-VI-HS-0002-0 | 2024-02-20 | Vendor Approval of CONSAAS Audit (ACE EHS) | Rev 0: Noted for information | 2024-03-19 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-05 | 27 | INF | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | INF | INF
1845 | 000318 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 0 | 131242-WST02-VI-E-0003-0 | 2024-02-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 0: Approved with Comments. To revise and resubmit. Please refer to the comment sheet | 2024-03-20 | 2024-03-20 | Approved with Comments | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-12 | 28 | AWC | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1846 | 000318 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 1 | 131242-WST02-VI-E-0003-1 | 2024-05-21 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-11 | 2024-07-04 | Approved with Comments | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-04 | 44 | AWC | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1847 | 000318 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0003 | 2 | 131242-WST02-VI-E-0003-2 | 2024-07-22 | Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab) | Rev 2: Approved. | 2024-08-12 | 2024-09-24 | Approved |  | YES | NA |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 64 | APP | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
1848 | 000319 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0009 | 0 | 131242-WSW41-PS-PM-0009-0 | 2024-02-21 | Monthly Progress Presentation No. 09 (0124) | For Information | 2024-03-20 | 2024-02-22 | For Information |  | YES | NA |  | 131242-WSW41-PS-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Presentation No. 09 (0124)" && "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" | 2023-10-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-06 | 1 | INF | 2024-08-05 | 0 | 000152&&000319&&000617 | 2023-10-30, 2024-02-21, 2024-08-05 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
1849 | 000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0017 | 0 | 131242-WSW41-MI-C-0017-0 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 | For Information |  | YES | NA |  | 131242-WSW41-MI-0017 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-07 | 8 | INF | 2024-10-31 | 0 | 000298&&000320&&000339&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1850 | 000320 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0018 | 0 | 131242-WSW41-MI-C-0018-0 | 2024-02-22 | CSA Meeting Minutes 0017 & 0018_20231228 20240111 | For Information | 2024-03-21 | 2024-03-01 | For Information |  | YES | NA |  | 131242-WSW41-MI-0018 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0018_20241113" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-07 | 8 | INF | 2024-11-30 | 0 | 000313&&000320&&000339&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1851 | 000321 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 0 | 131242-WSD11-BQ-E-0003-0 | 2024-02-23 | THP Listing of Interface Points | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-03-22 | 2024-05-15 | Not Approved | 2024-06-05 | YES | Resubmitted |  | 131242-WSD11-BQ-0003 | NA | "THP Line List" && "THP Listing of Interface Points" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 82 | NAP | 2025-07-21 | 1 | 000321&&000535 | 2024-02-23, 2024-06-26, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1852 | 000321 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | BQ | E | 0003 | 1 | 131242-WSD11-BQ-E-0003-1 | 2025-07-21 | THP Listing of Interface Points | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-08-08 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WSD11-BQ-0003 | NA | "THP Line List" && "THP Listing of Interface Points" | 2024-02-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 72 | AWC | 2025-07-21 | 1 | 000321&&000535 | 2024-02-23, 2024-06-26, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
1853 | 000322 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 0 | 131242-WST02-CH-P-0002-0 | 2024-02-23 | Process Functional Description | Rev 0 : There are no active comments on the submittal. However, if there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 2024-03-22 | 2024-03-13 | Approved with Comments | 2024-04-03 | YES | Resubmitted | If there will be any changes to the document during detail engineering, then same must be captured and resubmittal is required. | 131242-WST02-CH-0002 | NA | "Process Functional Description" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 19 | AWC | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1854 | 000322 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 1 | 131242-WST02-CH-P-0002-1 | 2024-07-23 | Process Functional Description | Rev 1: Approved | 2024-08-13 | 2024-08-29 | Approved |  | YES | NA |  | 131242-WST02-CH-0002 | NA | "Process Functional Description" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 37 | APP | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
1855 | 000322 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 2 | 131242-WST02-CH-P-0002-2 | 2024-10-15 | Process Functional Description | Rev 2: Approved with comments. Please address the comments and resubmit. | 2024-11-05 | 2024-12-18 | Approved with Comments | 2025-01-08 | YES | Resubmitted | Pending MP updates | 131242-WST02-CH-0002 | NA | "Process Functional Description" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 64 | AWC | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1856 | 000322 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0002 | 3 | 131242-WST02-CH-P-0002-3 | 2025-03-04 | Process Functional Description | Rev 3: Approved with comments. Resubmittal is required if there are any changes during the detail engineering. | 2025-03-24 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue | Pending MP updates | 131242-WST02-CH-0002 | NA | "Process Functional Description" | 2024-02-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-18 | 55 | AWC | 2025-03-04 | 3 | 000322 | 2024-02-23, 2024-07-23, 2024-10-15, 2025-03-04 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-05-16 | Overdue | 0 | AWC | AWC
1857 | 000323 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0019 | 0 | 131242-WSW41-MI-P-0019-0 | 2024-02-23 | Process & MEICA Meeting Minutes 0019_20240215 | Rev 0: For Information | 2024-03-22 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0019 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-14 | 88 | INF | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1858 | 000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0001 | 0 | 131242-WSD11-LT-P-0001-0 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | Rejected |  | YES | NA |  | 131242-WSD11-LT-0001 | NA | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | 2024-02-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-15 | 131 | REJ | 2024-02-24 | 0 | 000324 | 2024-02-24 | 00 | 1 | Rejected | REJ | 2024-07-24 | Overdue | 0 | REJ | REJ
1859 | 000324 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0002 | 0 | 131242-WSD11-LT-P-0002-0 | 2024-02-24 | THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument | Rev 0: Rejected. Refer to subsequence submissions for individual item. | 2024-03-22 | 2024-07-04 | Rejected |  | YES | NA |  | 131242-WSD11-LT-0002 | NA | "THP Letter for Materials of Cable tray & JB and Isolation Valve for Instrument" | 2024-02-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-15 | 131 | REJ | 2024-02-24 | 0 | 000324 | 2024-02-24 | 00 | 1 | Rejected | REJ | 2024-07-24 | Overdue | 0 | REJ | REJ
1860 | 000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-S-8001_ST605-B | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | Rejected | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-DR-8001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-17 | 1 | REJ | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | REJ | REJ
1861 | 000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | B | 131242-WST02-DR-S-1003_ST605-B | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-DR-1003_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-17 | 1 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
1862 | 000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST605 | B | 131242-WST02-DR-S-1004_ST605-B | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-DR-1004_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-17 | 1 | NAP | 2024-02-29 | B | 000325 | 2024-02-26, 2024-02-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1863 | 000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST605 | B | 131242-WST02-DR-S-5002_ST605-B | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-DR-5002_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-17 | 1 | NAP | 2024-02-29 | B | 000325 | 2024-02-26, 2024-02-29 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1864 | 000325 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | B | 131242-WST02-DR-S-7001_ST605-B | 2024-02-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | To resubmit as requested by C4B. | 2024-03-25 | 2024-02-27 | Not Approved | 2024-03-18 | YES | Resubmitted |  | 131242-WST02-DR-7001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-17 | 1 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
1865 | 000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | B | 131242-WST02-DR-S-8001_ST605-B | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-20 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-8001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 20 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
1866 | 000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A1 | 131242-WST02-DR-S-1003_ST605-A1 | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-1003_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 20 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
1867 | 000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST605 | B | 131242-WST02-DR-S-1004_ST605-B | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-1004_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 20 | NAP | 2024-02-29 | B | 000325 | 2024-02-26, 2024-02-29 | 00, 01 | 2 | Not Approved | NAP | 2024-04-09 | Overdue | 0 | NAP | NAP
1868 | 000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST605 | B | 131242-WST02-DR-S-5002_ST605-B | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-5002_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 20 | NAP | 2024-02-29 | B | 000325 | 2024-02-26, 2024-02-29 | 00, 01 | 2 | Not Approved | NAP | 2024-04-09 | Overdue | 0 | NAP | NAP
1869 | 000325 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | B | 131242-WST02-DR-S-7001_ST605-B | 2024-02-29 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-03-28 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-7001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-14 | 20 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
1870 | 000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-S-8001_ST605-A2 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-17 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WST02-DR-8001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 18 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1871 | 000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A2 | 131242-WST02-DR-S-1003_ST605-A2 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-28 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WST02-DR-1003_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 18 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1872 | 000325 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | A2 | 131242-WST02-DR-S-7001_ST605-A2 | 2024-04-26 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev.2: Not Approved. Response for comment is not submitted. | 2024-05-28 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WST02-DR-7001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 18 | NAP | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1873 | 000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST605 | A2 | 131242-WST02-DR-S-8001_ST605-A2 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-06 | 2024-06-03 | For Information |  | YES | NA |  | 131242-WST02-DR-8001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-04-29 | 49 | INF | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | INF | INF
1874 | 000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST605 | A2 | 131242-WST02-DR-S-1003_ST605-A2 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-14 | 2024-06-03 | For Information |  | YES | NA |  | 131242-WST02-DR-1003_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-04-29 | 49 | INF | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | INF | INF
1875 | 000325 | 03 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST605 | A2 | 131242-WST02-DR-S-7001_ST605-A2 | 2024-04-15 | IFC of ST605_SSN Piling Layout of Main Water Tanks | Rev,3: For Information | 2024-05-14 | 2024-06-03 | For Information |  | YES | NA |  | 131242-WST02-DR-7001_ST605 | NA | "IFC of ST605_SSN Piling Layout of Main Water Tanks " | 2024-02-26 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-04-29 | 49 | INF | 2024-04-26 | A2 | 000325 | 2024-02-26, 2024-02-29, 2024-04-15, 2024-04-26 | 00, 01, 02, 03 | 4 | Not Approved | NAP |  |  | 0 | INF | INF
1876 | 000326 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 0 | 131242-WSD11-PO-E-0001-0 | 2024-02-26 | Unpriced PO for Transformer (Hitachi) | Rev 0: Rejected. Please refer to attached file to comments. | 2024-03-25 | 2024-03-20 | Rejected | 2024-04-11 | YES | Resubmitted |  | 131242-WSD11-PO-0001 | NA | "Unpriced PO for THP Package (Cambi)" && "Unpriced PO for Transformer (Hitachi)" | 2023-09-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-11 | 23 | REJ | 2024-03-20 | 1 | 000100&&000326 | 2023-09-14, 2024-02-26, 2024-03-20 | 00, 01 | 3 | For Information | INF |  |  | 0 | REJ | REJ
1877 | 000326 | 01 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | E | 0001 | 1 | 131242-WSD11-PO-E-0001-1 | 2024-03-20 | Unpriced PO for Transformer (Hitachi) | For Information | 2024-04-11 | 2024-04-29 | For Information |  | YES | NA |  | 131242-WSD11-PO-0001 | NA | "Unpriced PO for THP Package (Cambi)" && "Unpriced PO for Transformer (Hitachi)" | 2023-09-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-03 | 40 | INF | 2024-03-20 | 1 | 000100&&000326 | 2023-09-14, 2024-02-26, 2024-03-20 | 00, 01 | 3 | For Information | INF | 2024-05-17 | Overdue | 0 | INF | INF
1878 | 000327 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0004 | 0 | 131242-WSD11-PO-M-0004-0 | 2024-02-26 | Unpriced PO for Blower (Aerzen) | For Information | 2024-03-25 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSD11-PO-0004 | NA | "Unpriced PO for Blower (Aerzen)" | 2024-02-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-17 | 85 | INF | 2024-02-26 | 0 | 000327 | 2024-02-26 | 00 | 1 | For Information | INF | 2024-06-10 | Overdue | 0 | INF | INF
1879 | 000328 | 00 | Yi Hao | Contracts | NA | 131242 | WSD11 | PO | M | 0003 | 0 | 131242-WSD11-PO-M-0003-0 | 2024-02-26 | Unpriced PO for Diffuser (Xylem) | For Information | 2024-03-25 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSD11-PO-0003 | NA | "Unpriced PO for Diffuser (Xylem)" | 2024-02-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-17 | 85 | INF | 2024-02-26 | 0 | 000328 | 2024-02-26 | 00 | 1 | For Information | INF | 2024-06-10 | Overdue | 0 | INF | INF
1880 | 000329 | 00 | Low | EICA | NA | 131242 | WST02 | VI | I | 0002 | 0 | 131242-WST02-VI-I-0002-0 | 2024-02-28 | Vendor Approval of SSN Package (ORP Analyser) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-04-08 | (VOID / NOT IN USE) | 2024-04-29 | YES | Resubmitted | To check with Qili whether ORP required or not. | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-13 | 40 | VOID | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | VOID | VOID
1881 | 000330 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | MI | I | 0001 | 0 | 131242-WSD11-MI-I-0001-0 | 2024-02-28 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 0: Accepted for information. To revise and resubmit. Refer attached file for comments. | 2024-03-27 | 2024-05-09 | Approved with Comments | 2024-05-30 | YES | Resubmitted |  | 131242-WSD11-MI-0001 | NA | "MI-Process & MEICA Meeting Minutes with THP (CAMBI)" && "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2023-07-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-13 | 71 | AWC | 2024-02-28 | 0 | 000039&&000330 | 2023-07-05, 2024-02-28 | 00 | 2 | Approved with Comments | AWC | 2024-05-29 | Overdue | 0 | AWC | AWC
1882 | 000330 | 01 | Freedomer | EICA | NA | 131242 | NA | MI | E | Comment Reply Sheet 20240716 S330.0 | 0 | 131242--MI-E-Comment Reply Sheet 20240716 S330.0- | 2024-07-17 | Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion | Rev 1: Accepted for information. No resubmission required. Refer attached file for comments. | 2024-08-06 | 2024-09-17 | For Information |  | YES | NA |  | 131242-NA-MI-Comment Reply Sheet 20240716 S330.0 | NA | "Minutes of Ad-Hoc Meeting for THP CAMBI PLC Model Discussion" | 2024-07-17 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-06 | 62 | INF | 2024-07-17 | 0 | 000330 | 2024-07-17 | 01 | 1 | For Information | INF | 2024-10-07 | Overdue | 0 | INF | INF
1883 | 000331 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | LT | P | 0003 | 0 | 131242-WSD11-LT-P-0003-0 | 2024-02-28 | THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-27 | 2024-03-20 | Not Approved | 2024-04-11 | NO | Overdue |  | 131242-WSD11-LT-0003 | NA | "THP letter for Not Providing Seperate Terminal Box for RTD & Heater in the mortor" | 2024-02-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-19 | 21 | NAP | 2024-02-28 | 0 | 000331 | 2024-02-28 | 00 | 1 | Not Approved | NAP | 2024-04-09 | Overdue | 0 | NAP | NAP
1884 | 000332 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | A.1 | 131242-WSW41-VI-M-0018-A.1 | 2024-02-29 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rejected as requested by Contractor as there still need to attach the document | 2024-03-28 | 2024-03-01 | Rejected | 2024-03-21 | YES | Resubmitted |  | 131242-WSW41-VI-0018 | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-20 | 1 | REJ | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | Approved | APP |  |  | 0 | REJ | REJ
1885 | 000332 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-M-0018-0 | 2024-03-04 | Vendor Approval of Mechanical Installer - JD Waters Pte Ltd | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-22 | 2024-04-15 | Approved with Comments | 2024-05-06 | NO | Overdue |  | 131242-WSW41-VI-0018 | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-18 | 42 | AWC | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
1886 | 000333 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | M | 0019 | 0 | 131242-WSW41-VI-M-0019-0 | 2024-02-29 | Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd. | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-03-28 | 2024-04-16 | Approved with Comments | 2024-05-07 | NO | Overdue |  | 131242-WSW41-VI-0019 | NA | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." && "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-20 | 47 | AWC | 2024-09-06 | 0 | 000333&&000705 | 2024-02-29, 2024-09-06 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
1887 | 000334 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 0 | 131242-WST02-VI-E-0004-0 | 2024-02-29 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 0: Not Approved. To revise and resubmit. Please refer to comments sheet. | 2024-03-28 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-20 | 20 | NAP | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | NAP | NAP
1888 | 000334 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 1 | 131242-WST02-VI-E-0004-1 | 2024-03-26 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-17 | 2024-04-29 | Approved with Comments | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 34 | AWC | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
1889 | 000334 | 02 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 2 | 131242-WST02-VI-E-0004-2 | 2024-05-16 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-06 | 2024-07-04 | Approved with Comments | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 49 | AWC | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
1890 | 000334 | 03 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0004 | 3 | 131242-WST02-VI-E-0004-3 | 2024-07-28 | Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight) | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-16 | 2024-08-16 | Approved with Comments | 2024-09-05 | NO | Overdue |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 19 | AWC | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
1891 | 000335 | 00 | Thomas | PCM | NA | 131242 | WSW41 | MI | PM | 0009 | 0 | 131242-WSW41-MI-PM-0009-0 | 2024-03-01 | Monthly Progress Meeting Minutes 0009_20240220 | For Information | 2024-04-01 | 2024-03-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0008 and 0009_20230719 & 20230726" && "Monthly Progress Meeting Minutes 0009_20240220" && "Process & MEICA Meeting Minutes 0008 & 0009_20230908 & 0914" | 2023-08-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-15 | 3 | INF | 2024-03-01 | 0 | 000063&&000104&&000152&&000335 | 2023-08-07, 2023-09-19, 2023-10-30, 2024-03-01 | 00 | 4 | For Information | INF | 2024-03-22 | Overdue | 0 | INF | INF
1892 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | A | 131242-WST02-SD-S-8001_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-8001_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | C | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1893 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5005_ST605 | A | 131242-WST02-SD-S-5005_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5005_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | D | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1894 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5006_ST605 | A | 131242-WST02-SD-S-5006_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5006_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | B | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1895 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5007_ST605 | A | 131242-WST02-SD-S-5007_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5007_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | D | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1896 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5008_ST605 | A | 131242-WST02-SD-S-5008_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5008_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | D | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1897 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5009_ST605 | A | 131242-WST02-SD-S-5009_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5009_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | B | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1898 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5010_ST605 | A | 131242-WST02-SD-S-5010_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5010_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | B | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1899 | 000336 | 00 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5011_ST605 | A | 131242-WST02-SD-S-5011_ST605-A | 2024-03-01 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-SD-5011_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2024-05-17 | A.1 | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1900 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 8001_ST605 | C | 131242-WST02-SD-S-8001_ST605-C | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue | Heng Peng to clear BIM comments. | 131242-WST02-SD-8001_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | C | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1901 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5005_ST605 | D | 131242-WST02-SD-S-5005_ST605-D | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5005_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | D | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1902 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5006_ST605 | B | 131242-WST02-SD-S-5006_ST605-B | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5006_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | B | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1903 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5007_ST605 | D | 131242-WST02-SD-S-5007_ST605-D | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5007_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | D | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1904 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5008_ST605 | D | 131242-WST02-SD-S-5008_ST605-D | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5008_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | D | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1905 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5009_ST605 | B | 131242-WST02-SD-S-5009_ST605-B | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5009_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | B | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1906 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5010_ST605 | B | 131242-WST02-SD-S-5010_ST605-B | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5010_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | B | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1907 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5011_ST605 | A.1 | 131242-WST02-SD-S-5011_ST605-A.1 | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5011_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-03-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-31 | 17 | NAP | 2024-05-17 | A.1 | 000336 | 2024-03-01, 2024-05-17 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1908 | 000336 | 01 | Zora | CSA | NA | 131242 | WST02 | SD | S | 5013_ST605 | B | 131242-WST02-SD-S-5013_ST605-B | 2024-05-17 | Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-SD-5013_ST605 | NA | "Shop Drawing of ST605_SSN Piling Layout of Main Water Tanks" | 2024-05-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-06 | 17 | NAP | 2024-05-17 | B | 000336 | 2024-05-17 | 01 | 1 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
1909 | 000337 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1003 | 0 | 131242-WSW41-VI-M-1003-0 | 2024-03-01 | Vendor Approval of cPVC Pipes & Fittings (GF) | Approved | 2024-04-01 | 2024-04-17 | Approved |  | YES | NA |  | 131242-WSW41-VI-1003 | NA | "Vendor Approval of cPVC Pipes & Fittings (GF)" | 2024-03-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-21 | 47 | APP | 2024-03-01 | 0 | 000337 | 2024-03-01 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
1910 | 000338 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB-A | 2024-03-01 | PUB DC Drainage Submission | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-01 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-21 | 19 | NAP | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | NAP | NAP
1911 | 000338 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB-A | 2024-03-28 | PUB DC Drainage Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-13 | Not Approved | 2024-06-03 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 46 | NAP | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | NAP | NAP
1912 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A | 131242-WST02-DR-A-1000_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1913 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A | 131242-WST02-DR-A-1001_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-03 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | NAP | NAP
1914 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A | 131242-WST02-DR-A-1002_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1915 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A | 131242-WST02-DR-A-1003_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1916 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A | 131242-WST02-DR-A-1004_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1917 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A | 131242-WST02-DR-A-1009_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1918 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A | 131242-WST02-DR-A-2000_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1919 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | A | 131242-WST02-DR-A-2001_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2001_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1920 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | A | 131242-WST02-DR-A-2002_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1921 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | A | 131242-WST02-DR-A-2003_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1922 | 000338 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | A | 131242-WST02-DR-A-2007_PUB-A | 2024-05-20 | PUB DC Drainage Submission | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-10 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2007_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-09 | 17 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1923 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_PUB | B | 131242-WST02-DR-A-0001_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-0001_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2024-10-30 | B | 000338 | 2024-10-30 | 03 | 1 | Not Approved | NAP | 2025-02-05 | Overdue | 0 | NAP | NAP
1924 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0002_PUB | B | 131242-WST02-DR-A-0002_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-0002_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2024-10-30 | B | 000338 | 2024-10-30 | 03 | 1 | Not Approved | NAP | 2025-02-05 | Overdue | 0 | NAP | NAP
1925 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | B | 131242-WST02-DR-A-1000_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1926 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | B | 131242-WST02-DR-A-1001_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | NAP | NAP
1927 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | B | 131242-WST02-DR-A-1002_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1928 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | B | 131242-WST02-DR-A-1003_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1929 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | B | 131242-WST02-DR-A-1004_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1930 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_PUB | B | 131242-WST02-DR-A-1006_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1006_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-12 | A | 000338 | 2024-10-30, 2026-01-12 | 03, 08 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1931 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | B | 131242-WST02-DR-A-1009_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1932 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | B | 131242-WST02-DR-A-2000_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1933 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | B | 131242-WST02-DR-A-2001_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2001_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1934 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | B | 131242-WST02-DR-A-2002_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1935 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | B | 131242-WST02-DR-A-2003_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1936 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | B | 131242-WST02-DR-A-2007_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2007_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 78 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
1937 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_PUB | B | 131242-WST02-DR-A-3000_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-3000_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-12 | A.2 | 000338 | 2024-10-30, 2026-01-12 | 03, 08 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
1938 | 000338 | 03 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 5004_PUB | B | 131242-WST02-DR-A-5004_PUB-B | 2024-10-30 | PUB DC Drainage Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5004_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2024-10-30 | B | 000338 | 2024-10-30 | 03 | 1 | Not Approved | NAP | 2025-02-05 | Overdue | 0 | NAP | NAP
1939 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB-A.1 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1940 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB-A.2 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | REJ | REJ
1941 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.2 | 131242-WST02-DR-A-1002_PUB-A.2 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1942 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.2 | 131242-WST02-DR-A-1003_PUB-A.2 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1943 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.1 | 131242-WST02-DR-A-1004_PUB-A.1 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1944 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.2 | 131242-WST02-DR-A-1009_PUB-A.2 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1945 | 000338 | 04 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB-A.2 | 2025-03-10 | PUB DC Drainage Submission | Rev 4: Rejected (as requested by contractor via email dated 19 March 2025 | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1946 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB-A.1 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1947 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB-A.2 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | NAP | NAP
1948 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.2 | 131242-WST02-DR-A-1002_PUB-A.2 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1949 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.2 | 131242-WST02-DR-A-1003_PUB-A.2 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1950 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.1 | 131242-WST02-DR-A-1004_PUB-A.1 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1951 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.2 | 131242-WST02-DR-A-1009_PUB-A.2 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1952 | 000338 | 05 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB-A.2 | 2025-03-21 | PUB DC Drainage Submission | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1953 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB-A.1 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1954 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB-A.2 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | NAP | NAP
1955 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.3 | 131242-WST02-DR-A-1002_PUB-A.3 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1956 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.3 | 131242-WST02-DR-A-1003_PUB-A.3 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1957 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.3 | 131242-WST02-DR-A-1004_PUB-A.3 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1958 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.3 | 131242-WST02-DR-A-1009_PUB-A.3 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1959 | 000338 | 06 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB-A.2 | 2025-08-12 | PUB DC Drainage Submission | Rev.6: Not Approved. Please refer to markup comment for resubmission. | 2025-09-01 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 63 | NAP | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
1960 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.1 | 131242-WST02-DR-A-1000_PUB-A.1 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1961 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.2 | 131242-WST02-DR-A-1001_PUB-A.2 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ |  |  | 0 | REJ | REJ
1962 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.3 | 131242-WST02-DR-A-1002_PUB-A.3 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1963 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.3 | 131242-WST02-DR-A-1003_PUB-A.3 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1964 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.3 | 131242-WST02-DR-A-1004_PUB-A.3 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1965 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.3 | 131242-WST02-DR-A-1009_PUB-A.3 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1966 | 000338 | 07 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.2 | 131242-WST02-DR-A-2000_PUB-A.2 | 2025-11-17 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2025-12-05 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-01 | 30 | REJ | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
1967 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_PUB | A.2 | 131242-WST02-DR-A-1000_PUB-A.2 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.2 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1968 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_PUB | A.4 | 131242-WST02-DR-A-1001_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001_PUB | NA | "PUB DC Drainage Submission " | 2024-03-01 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-03-01, 2024-03-28, 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1969 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_PUB | A.4 | 131242-WST02-DR-A-1002_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1970 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_PUB | A.4 | 131242-WST02-DR-A-1003_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1971 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_PUB | A.4 | 131242-WST02-DR-A-1004_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1972 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1005_PUB | A | 131242-WST02-DR-A-1005_PUB-A | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005_PUB | NA | "PUB DC Drainage Submission " | 2026-01-12 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-01 | 84 | PEN | 2026-01-12 | A | 000338 | 2026-01-12 | 08 | 1 | Awaiting S.O.'s response | PEN | 2026-02-27 |  | 0 | PEN | PEN
1973 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_PUB | A | 131242-WST02-DR-A-1006_PUB-A | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A | 000338 | 2024-10-30, 2026-01-12 | 03, 08 | 2 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
1974 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_PUB | A.4 | 131242-WST02-DR-A-1009_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1975 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_PUB | A.4 | 131242-WST02-DR-A-2000_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2000_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-17, 2026-01-12 | 02, 03, 04, 05, 06, 07, 08 | 7 | Rejected | REJ | 2026-02-27 |  | 0 | PEN | PEN
1976 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_PUB | A.4 | 131242-WST02-DR-A-2001_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2001_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
1977 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_PUB | A.4 | 131242-WST02-DR-A-2002_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2002_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
1978 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_PUB | A.4 | 131242-WST02-DR-A-2003_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2003_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
1979 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_PUB | A.4 | 131242-WST02-DR-A-2007_PUB-A.4 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2007_PUB | NA | "PUB DC Drainage Submission " | 2024-05-20 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.4 | 000338 | 2024-05-20, 2024-10-30, 2026-01-12 | 02, 03, 08 | 3 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
1980 | 000338 | 08 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_PUB | A.2 | 131242-WST02-DR-A-3000_PUB-A.2 | 2026-01-12 | PUB DC Drainage Submission | R7: Contractor requested for rejection as per attached email. | 2026-01-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3000_PUB | NA | "PUB DC Drainage Submission " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | A.2 | 000338 | 2024-10-30, 2026-01-12 | 03, 08 | 2 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
1981 | 000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0016 | 0 | 131242-WSW41-MI-IM-0016-0 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0016 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-19 | 0 | INF | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1982 | 000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0017 | 0 | 131242-WSW41-MI-IM-0017-0 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0017 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-19 | 0 | INF | 2024-10-31 | 0 | 000298&&000320&&000339&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1983 | 000339 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0018 | 0 | 131242-WSW41-MI-IM-0018-0 | 2024-03-05 | BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207 | For Information | 2024-04-03 | 2024-03-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0018 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0018_20241113" && "Process & MEICA Meeting Minutes 0018_20240201" | 2024-02-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-19 | 0 | INF | 2024-11-30 | 0 | 000313&&000320&&000339&&000863 | 2024-02-15, 2024-02-22, 2024-03-05, 2024-11-30 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
1984 | 000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA-C | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-1000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
1985 | 000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA-C | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-1001_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
1986 | 000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA-C | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-1002_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
1987 | 000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA-C | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-5001_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
1988 | 000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA-C | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-7000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
1989 | 000340 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA-C | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-DR-8000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
1990 | 000340 | 00 | Zora | CSA | NA | 131242 | NA | DR | S | Submission Acknowledgement | A.1 | 131242--DR-S-Submission Acknowledgement-A.1 | 2024-03-05 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.0: For Information. Native Files was not submitted. Please refer to comment sheet. | 2024-04-03 | 2024-03-20 | For Information | 2024-04-11 | YES | Resubmitted |  | 131242-NA-DR-Submission Acknowledgement | NA | "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | INF | 2024-03-05 | A.1 | 000340 | 2024-03-05 | 00 | 1 | For Information | INF | 2024-04-09 | Overdue | 0 | INF | INF
1991 | 000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA-C | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue | Heng Peng to clear BIM comments and to provide Native files | 131242-WST02-DR-1000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 19 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1992 | 000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA-C | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-1001_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 19 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1993 | 000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA-C | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-1002_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 19 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1994 | 000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA-C | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-5001_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 19 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1995 | 000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA-C | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-7000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 19 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1996 | 000340 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA-C | 2024-04-25 | ST615 – Amendment of ST604 (BCA Submission for Information) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-8000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 19 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
1997 | 000341 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 0 | 131242-WSD11-CD-I-0004-0 | 2024-03-05 | THP UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WSD11-CD-0004 | NA | "THP UPS Loading List" | 2024-03-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-25 | 15 | NAP | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1998 | 000341 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 1 | 131242-WSD11-CD-I-0004-1 | 2024-04-19 | THP UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | Not Approved | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-CD-0004 | NA | "THP UPS Loading List" | 2024-03-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 60 | NAP | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
1999 | 000341 | 02 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 2 | 131242-WSD11-CD-I-0004-2 | 2024-10-22 | THP UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2024-12-18 | Not Approved | 2025-01-08 | YES | Resubmitted |  | 131242-WSD11-CD-0004 | NA | "THP UPS Loading List" | 2024-03-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 57 | NAP | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2000 | 000341 | 03 | Low | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 3 | 131242-WSD11-CD-I-0004-3 | 2025-01-21 | THP UPS Loading List | Not Approved - Revise and resubmit | 2025-02-10 | 2025-05-15 | Not Approved | 2025-06-04 | YES | Resubmitted |  | 131242-WSD11-CD-0004 | NA | "THP UPS Loading List" | 2024-03-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 114 | NAP | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2001 | 000341 | 04 | Karthik | EICA | NA | 131242 | WSD11 | CD | I | 0004 | 4 | 131242-WSD11-CD-I-0004-4 | 2025-05-27 | THP UPS Loading List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-16 | 2025-09-11 | Approved with Comments | 2025-10-01 | NO | Overdue |  | 131242-WSD11-CD-0004 | NA | "THP UPS Loading List" | 2024-03-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-10 | 107 | AWC | 2025-05-27 | 4 | 000341 | 2024-03-05, 2024-04-19, 2024-10-22, 2025-01-21, 2025-05-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC | 2025-10-01 | Overdue | 0 | AWC | AWC
2002 | 000342 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | CD | I | 0007 | 0 | 131242-WST02-CD-I-0007-0 | 2024-03-05 | SSN UPS Loading List | Rev 0: Not Approved. To revise and resubmit. Refer to the comments sheet | 2024-04-03 | 2024-03-20 | Not Approved | 2024-04-11 | YES | Resubmitted |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-19 | 15 | NAP | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2003 | 000342 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0007 | 1 | 131242-WST02-CD-I-0007-1 | 2024-04-19 | SSN UPS Loading List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-10 | 2024-06-18 | Not Approved | 2024-07-08 | YES | Resubmitted |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 60 | NAP | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2004 | 000342 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 2 | 131242-WST02-CD-I-0007-2 | 2024-11-20 | SSN UPS Loading List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-10 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-04 | 40 | NAP | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2005 | 000342 | 03 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 3 | 131242-WST02-CD-I-0007-3 | 2025-01-21 | SSN UPS Loading List | Rev 3: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-02-10 | 2025-03-04 | Not Approved | 2025-03-24 | YES | Resubmitted |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 42 | NAP | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2006 | 000342 | 04 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 4 | 131242-WST02-CD-I-0007-4 | 2025-03-06 | SSN UPS Loading List | Not Approved - Revise and resubmit | 2025-03-26 | 2025-05-15 | Not Approved | 2025-06-04 | YES | Resubmitted |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 70 | NAP | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2007 | 000342 | 05 | Low | EICA | NA | 131242 | WST02 | CD | I | 0007 | 5 | 131242-WST02-CD-I-0007-5 | 2025-06-16 | SSN UPS Loading List | Rev 5: Approved with comments. No need resubmission. Refer attached file for comments. | 2025-07-04 | 2025-09-11 | Approved with Comments |  | YES | NA |  | 131242-WST02-CD-0007 | NA | "SSN UPS Loading List" && "Submission of Milestone 1.1 Water Tank" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-06-30 | 87 | AWC | 2025-06-16 | 5 | 000163&&000342 | 2023-11-06, 2024-03-05, 2024-04-19, 2024-11-20, 2025-01-21, 2025-03-06, 2025-06-16 | 00, 01, 02, 03, 04, 05 | 7 | Approved with Comments | AWC | 2025-10-01 | Overdue | 0 | AWC | AWC
2008 | 000343 | 00 | Yuen Fatt | PMT | NA | 131242 | WSW41 | LT | PM | 0023 | 0 | 131242-WSW41-LT-PM-0023-0 | 2024-03-06 | CV of Team Member (LEW) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-04 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WSW41-LT-0023 | NA | "CV of Team Member (LEW)" | 2024-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-26 | 75 | AWC | 2024-03-06 | 0 | 000343 | 2024-03-06 | 00 | 1 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2009 | 000344 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 0 | 131242-WST02-VI-I-0004-0 | 2024-03-06 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-09 | Approved with Comments | 2024-05-30 | YES | Resubmitted |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-20 | 64 | AWC | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
2010 | 000344 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0004 | 1 | 131242-WST02-VI-I-0004-1 | 2024-12-05 | Vendor Approval of SSN Package (Conductivity Analyser) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0004 | NA | "Preliminary Design and Poh Meng Engineering Vendor Approval Document-ACMV " && "Vendor Approval of LV Switchgear, MCC panel, MDB and LCS (Sunlight)" && "Vendor Approval of SSN Package (Conductivity Analyser)" && "Vendor Approval of Waterproofing Vendor – Pro-werkze Pte. Ltd. " && "Vendor Approval of Wet Trades Vendor – Huayu Construction Pte. Ltd." | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-19 | 152 | AWC | 2025-11-13 | 2 | 000334&&000344&&000855&&001327&&001359 | 2024-02-29, 2024-03-06, 2024-03-26, 2024-05-16, 2024-07-28, 2024-11-28, 2024-12-05, 2025-05-28, 2025-06-12, 2025-07-22, 2025-11-13 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
2011 | 000345 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-I-0003-0 | 2024-03-06 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-04 | 2024-05-15 | Approved with Comments | 2024-06-05 | YES | Resubmitted |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-20 | 70 | AWC | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2012 | 000345 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 0 | 131242-WST02-VI-I-0003-NA | 2024-10-04 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rejected as requested | 2024-10-24 | 2024-10-18 | Rejected | 2024-11-08 | YES | Resubmitted |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-18 | 14 | REJ | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
2013 | 000345 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 1 | 131242-WST02-VI-I-0003-1 | 2024-10-18 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | Approved with Comments | 2024-12-23 | YES | Resubmitted |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 46 | AWC | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2014 | 000345 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0003 | 2 | 131242-WST02-VI-I-0003-2 | 2025-02-27 | Vendor Approval of SSN Package (NO2 & NO3 Analyser) | Rev 3: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0003 | NA | "Preliminary Design and Vendor Approval for Public Address System (Pacific Reliance)" && "Vendor Approval of SSN Package (NO2 & NO3 Analyser)" && "Vendor Approval of Waterproofing Vendor – G-Concept Pte. Ltd." && "Vendor Approval-LV, ELV & Earth Cable (Keystone & Polycab)" | 2024-02-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-13 | 68 | AWC | 2025-08-22 | 1 | 000318&&000345&&000854&&001108 | 2024-02-21, 2024-03-06, 2024-05-21, 2024-07-22, 2024-10-04, 2024-10-18, 2024-11-28, 2025-02-27, 2025-03-10, 2025-08-22 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2015 | 000346 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 0 | 131242-WST02-VI-I-0005-0 | 2024-03-07 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-05 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WST02-VI-0005 | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-27 | 70 | AWC | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2016 | 000346 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0005 | 1 | 131242-WST02-VI-I-0005-1 | 2024-12-05 | Vendor Approval of SSN Package (Dissolved Oxygen Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0005 | NA | "Vendor Approval for Thermoplastic Cable Ladder Tray and Accessories (J&J Unex)" && "Vendor Approval of Air Conditioning Mechanical Ventilation (Poh Meng Engineering Pte. Ltd.) " && "Vendor Approval of SSN Package (Dissolved Oxygen Analyzer)" && "Vendor Approval of Siphonic System - Fast Flow System Pte. Ltd." | 2024-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-19 | 152 | AWC | 2025-03-18 | 0 | 000346&&000882&&000950&&001129 | 2024-03-07, 2024-12-05, 2024-12-10, 2025-01-03, 2025-03-18 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2017 | 000347 | 00 | Anuar | HSE | NA | 131242 | WSW41 | MS | C | 0008 | 0 | 131242-WSW41-MS-C-0008-0 | 2024-03-08 | MSRA, SWP for Time Lapse Camera Steel Pole Erection | Approved | 2024-04-08 | 2024-03-20 | Approved |  | YES | NA |  | 131242-WSW41-MS-0008 | NA | "MSRA for LVSG, MCC, MDB, DB & MCP Shifting & Installation Works" && "MSRA, SWP for Time Lapse Camera Steel Pole Erection" && "Method Statement & Risk Assessment for Piping Installation at SWPR" | 2024-03-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-03-28 | 12 | APP | 2025-12-05 | 1 | 000347&&001046&&001337 | 2024-03-08, 2025-02-17, 2025-05-30, 2025-12-05 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
2018 | 000348 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0014 | 0 | 131242-WSW41-CD-IM-0014-0 | 2024-03-08 | Submission Of BIM Coordination VCM Model (Feb-2024) | For Information | 2024-04-08 | 2024-03-20 | For Information |  | YES | NA |  | 131242-WSW41-CD-0014 | NA | "Submission Of BIM Coordination VCM Model (Feb-2024)" | 2024-03-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-28 | 12 | INF | 2024-03-08 | 0 | 000348 | 2024-03-08 | 00 | 1 | For Information | INF | 2024-04-09 | Overdue | 0 | INF | INF
2019 | 000349 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | 0 | 131242-WSD11-CL-EL-7000-0 | 2024-03-08 | THP Lux Calculation and Luminaire Schedule | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-08 | 2024-05-07 | Not Approved | 2024-05-28 | YES | Resubmitted |  | 131242-WSD11-CL-7000 | NA | "THP Lux Calculation and Luminaire Schedule" | 2024-03-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-28 | 60 | NAP | 2024-07-16 | B | 000349 | 2024-03-08, 2024-07-16 | 00, 01 | 2 | For Information | INF |  |  | 0 | NAP | NAP
2020 | 000349 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | CL | EL | 7000 | B | 131242-WSD11-CL-EL-7000-B | 2024-07-16 | THP Lux Calculation and Luminaire Schedule | Rev 1: For Information. | 2024-08-05 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-CL-7000 | NA | "THP Lux Calculation and Luminaire Schedule" | 2024-03-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-30 | 105 | INF | 2024-07-16 | B | 000349 | 2024-03-08, 2024-07-16 | 00, 01 | 2 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
2021 | 000350 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 0 | 131242-WST02-VI-I-0006-0 | 2024-03-11 | Vendor Approval of SSN Package (pH Analyzer) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-04-09 | 2024-05-14 | Approved with Comments | 2024-06-04 | YES | Resubmitted |  | 131242-WST02-VI-0006 | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 64 | AWC | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2022 | 000350 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0006 | 1 | 131242-WST02-VI-I-0006-1 | 2024-12-05 | Vendor Approval of SSN Package (pH Analyzer) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-12-26 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0006 | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-19 | 152 | AWC | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2023 | 000351 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 0 | 131242-WSW41-SP-C-0005-0 | 2024-03-11 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Approved with comment. Please refer to comment sheet for resubmission. | 2024-04-09 | 2024-03-26 | Approved with Comments | 2024-04-17 | YES | Resubmitted |  | 131242-WSW41-SP-0005 | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-31 | 15 | AWC | 2024-06-20 | 1 | 000351 | 2024-03-11, 2024-06-20 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
2024 | 000351 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0005 | 1 | 131242-WSW41-SP-C-0005-1 | 2024-06-20 | Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited) | Rev.1: Approved | 2024-07-10 | 2024-06-28 | Approved |  | YES | NA |  | 131242-WSW41-SP-0005 | NA | "Concrete Design Mix for Raft foundation (Except Water Tank) C32/40 (PanUnited)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-04 | 8 | APP | 2024-06-20 | 1 | 000351 | 2024-03-11, 2024-06-20 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2025 | 000352 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 0 | 131242-WSW41-VI-M-1009-0 | 2024-03-12 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rejected. The proposed vendor is dealer/sales representative and not the manufacturer/brand of pipes and fittings. | 2024-04-11 | 2024-04-17 | Rejected |  | YES | NA |  | 131242-WSW41-VI-1009 | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-01 | 36 | REJ | 2024-05-10 | 1 | 000352 | 2024-03-12, 2024-05-10 | 00, 01 | 2 | Approved | APP |  |  | 0 | REJ | REJ
2026 | 000352 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1009 | 1 | 131242-WSW41-VI-M-1009-1 | 2024-05-10 | Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen) | Rev 0: Approved Please note, that the approval, corresponds to the brand (FROCH and JNDIA) proposed by CES_SDC in this submittal. Approval does not include assessment for TRADER. | 2024-05-31 | 2024-08-06 | Approved |  | YES | NA | R0_Rej | 131242-WSW41-VI-1009 | NA | "Preliminary design and Vendor Approval – Stainless Steel Piping (Shanghai Lauchen)" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-24 | 88 | APP | 2024-05-10 | 1 | 000352 | 2024-03-12, 2024-05-10 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2027 | 000353 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0020 | 0 | 131242-WSW41-MI-P-0020-0 | 2024-03-12 | Process & MEICA Meeting Minutes 0020_20240229 | Rev 0: For Information | 2024-04-11 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-MI-0020 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0020_20250122" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-01 | 70 | INF | 2025-02-18 | 0 | 000353&&000388&&000684&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2028 | 000354 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0004 | 0 | 131242-WSW41-PS-HS-0004-0 | 2024-03-12 | Incentive / Disincentive Audit Scheme for November 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-PS-0004 | NA | "Incentive / Disincentive Audit Scheme for November 2023" && "Monthly Progress Presentation No. 04 (0823)" | 2023-09-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-26 | 6 | INF | 2024-03-12 | 0 | 000106&&000354 | 2023-09-21, 2024-03-12 | 00 | 2 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
2029 | 000355 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0005 | 0 | 131242-WSW41-PS-HS-0005-0 | 2024-03-12 | Incentive / Disincentive Audit Scheme for December 2023 | Rev 0: Scoring confirmed to be at 98/100 | 2024-04-11 | 2024-03-18 | For Information |  | YES | NA |  | 131242-WSW41-PS-0005 | NA | "Incentive / Disincentive Audit Scheme for December 2023" && "Monthly Progress Presentation No. 05 (0923)" | 2023-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-26 | 6 | INF | 2024-03-12 | 0 | 000137&&000355 | 2023-10-25, 2024-03-12 | 00 | 2 | For Information | INF | 2024-04-05 | Overdue | 0 | INF | INF
2030 | 000356 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 0 | 131242-WST02-CL-E-0000-0 | 2024-03-12 | SSN Transformer Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-11 | 2024-05-20 | Not Approved | 2024-06-10 | YES | Resubmitted |  | 131242-WST02-CL-0000 | NA | "SSN Transformer Sizing Calculations" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-01 | 69 | NAP | 2025-05-30 | 2 | 000356 | 2024-03-12, 2024-12-14, 2025-05-30 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2031 | 000356 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 1 | 131242-WST02-CL-E-0000-1 | 2024-12-14 | SSN Transformer Sizing Calculations | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-03 | 2025-02-13 | Approved with Comments | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-CL-0000 | NA | "SSN Transformer Sizing Calculations" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-28 | 61 | AWC | 2025-05-30 | 2 | 000356 | 2024-03-12, 2024-12-14, 2025-05-30 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2032 | 000356 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0000 | 2 | 131242-WST02-CL-E-0000-2 | 2025-05-30 | SSN Transformer Sizing Calculations | Rev 2: Approved with Comments. To revise and resubmit. Please refer to attached file for comments | 2025-06-19 | 2025-07-23 | Approved with Comments | 2025-08-12 | NO | Overdue | Pending Reply from Sunlight. Pending UPS details from Jacobs | 131242-WST02-CL-0000 | NA | "SSN Transformer Sizing Calculations" | 2024-03-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 54 | AWC | 2025-05-30 | 2 | 000356 | 2024-03-12, 2024-12-14, 2025-05-30 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-08-12 | Overdue | 0 | AWC | AWC
2033 | 000357 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0024 | 0 | 131242-WSW41-LT-PM-0024-0 | 2024-03-12 | Notice of Unforeseeable Underground Obstruction Near Chemical Dosing | Refer to S.O. Correspondence No.150. | 2024-04-11 | 2024-05-10 | For Information |  | YES | NA | Refer to S.O. Correspondence No.150. | 131242-WSW41-LT-0024 | NA | "Notice of Unforeseeable Underground Obstruction Near Chemical Dosing" | 2024-03-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-01 | 59 | INF | 2024-03-12 | 0 | 000357 | 2024-03-12 | 00 | 1 | For Information | INF | 2024-05-30 | Overdue | 0 | INF | INF
2034 | 000358 | 00 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 0 | 131242-WST02-BQ-P-0001-0 | 2024-03-12 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-11 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-26 | 72 | AWC | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2035 | 000358 | 01 | Joo kwan | Process | NA | 131242 | WST02 | BQ | P | 0001 | 1 | 131242-WST02-BQ-P-0001-1 | 2024-07-24 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-14 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-07 | 36 | AWC | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2036 | 000358 | 02 | Qili | Process | NA | 131242 | WST02 | BQ | P | 0001 | 2 | 131242-WST02-BQ-P-0001-2 | 2024-11-15 | C4B Sidestream Nitrogen Removal Process Equipment List | Rev 2: For Information | 2024-12-05 | 2025-03-04 | For Information |  | YES | NA |  | 131242-WST02-BQ-0001 | NA | "C4B SSN PLC/ RIO Panel Component Catalogue" && "C4B Sidestream Nitrogen Removal Process Equipment List" && "SSN Cable List" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-29 | 109 | INF | 2025-07-11 | 3 | 000204&&000251&&000358 | 2023-11-22, 2023-12-26, 2024-03-12, 2024-04-08, 2024-06-24, 2024-07-24, 2024-11-15, 2025-04-18, 2025-07-11 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | INF | INF
2037 | 000359 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 0 | 131242-WSD11-VI-I-0001-0 | 2024-03-13 | Vendor Approval of THP Train Instrument | Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-12 | 2024-05-16 | Not Approved | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-27 | 64 | NAP | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2038 | 000359 | 01 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 1 | 131242-WSD11-VI-I-0001-1 | 2024-06-07 | Vendor Approval of THP Train Instrument (Siemens) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-05 | Not Approved | 2024-08-26 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 59 | NAP | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2039 | 000359 | 02 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 2 | 131242-WSD11-VI-I-0001-2 | 2024-08-20 | Vendor Approval of THP Train Instrument (Siemens) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-09-03 | Approved with Comments | 2024-09-23 | YES | Resubmitted |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 14 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2040 | 000359 | 03 | Yean Yee/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0001 | 3 | 131242-WSD11-VI-I-0001-3 | 2025-03-21 | Vendor Approval of THP Train Instrument (Siemens) | Rev 3: Approved with comments (except Electromagnetic flowmeter). To revise and resubmit. Refer attached file for comments. | 2025-04-10 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WSD11-VI-0001 | NA | "Preliminary design and Vendor Approval" && "Preliminary design and Vendor Approval - THP Package" && "Vendor Approval for THP Package" && "Vendor Approval of Steet Structure Fabricator for CA System > 2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of Steet Structure Fabricator for CA System >2M Pipe Support (Cyclect, Super Galvanising Pte Ltd & FRP Products Co Pte Ltd)" && "Vendor Approval of THP Train Instrument" && "Vendor Approval of THP Train Instrument (Siemens)" | 2023-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 46 | AWC | 2025-04-18 | 1 | 000028&&000359&&001187 | 2023-06-14, 2023-07-28, 2023-08-02, 2023-11-10, 2024-03-01, 2024-03-13, 2024-06-07, 2024-08-20, 2025-03-21, 2025-04-03, 2025-04-18 | 00, 01, 02, 03, 04 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2041 | 000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | A | 131242-WST02-DR-P-7001-A | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-28 | 42 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2042 | 000360 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | A | 131242-WST02-DR-P-7002-A | 2024-03-14 | SSN PFD | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-15 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-28 | 42 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2043 | 000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7001 | B | 131242-WST02-DR-P-7001-B | 2024-06-19 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted | R1_AWC | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-03 | 50 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2044 | 000360 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7002 | B | 131242-WST02-DR-P-7002-B | 2024-03-14 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-09 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-03-28 | 147 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2045 | 000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001-C | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 41 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2046 | 000360 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002-C | 2024-08-29 | SSN PFD | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 41 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2047 | 000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001-C | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted | comments received on 14 Feb | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-12 | 79 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2048 | 000360 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002-C | 2024-10-29 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-12 | 79 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2049 | 000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | C | 131242-WST02-DR-P-7001-C | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 | Approved with Comments | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-13 | 14 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2050 | 000360 | 04 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | C | 131242-WST02-DR-P-7002-C | 2025-02-27 | SSN PFD | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-19 | 2025-03-13 | Approved with Comments | 2025-04-02 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-13 | 14 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2051 | 000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7001 | D | 131242-WST02-DR-P-7001-D | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | Approved with Comments |  | YES | NA |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-28 | 65 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2052 | 000360 | 05 | Qili | Process | NA | 131242 | WST02 | DR | P | 7002 | D | 131242-WST02-DR-P-7002-D | 2025-07-14 | SSN PFD | Rev 5: Approved with Comments. There are no active comments on this document. However, the document is approved with comments. This is to accommodate changes if any during the detailing. No resubmission is required at this moment, but resubmission is required if there are any changes to the document during detailing. | 2025-08-01 | 2025-09-17 | Approved with Comments |  | YES | NA |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-28 | 65 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2053 | 000361 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0006 | 0 | 131242-WSW41-PS-HS-0006-0 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Jan 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 | For Information |  | YES | NA |  | 131242-WSW41-PS-0006 | NA | "Incentive / Disincentive Audit Scheme for Jan 2024" && "Monthly Progress Presentation No. 06 (1023)" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-28 | 19 | INF | 2024-03-14 | 0 | 000186&&000361 | 2023-11-15, 2024-03-14 | 00 | 2 | For Information | INF | 2024-04-22 | Overdue | 0 | INF | INF
2054 | 000362 | 00 | Anuar | HSE | NA | 131242 | WSW41 | PS | HS | 0007 | 0 | 131242-WSW41-PS-HS-0007-0 | 2024-03-14 | Incentive / Disincentive Audit Scheme for Feb 2024 | Scoring confirmed to be at 95/100 | 2024-04-15 | 2024-04-02 | For Information |  | YES | NA |  | 131242-WSW41-PS-0007 | NA | "Incentive / Disincentive Audit Scheme for Feb 2024" && "Monthly Progress Presentation No. 07 (1123)" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-03-28 | 19 | INF | 2024-03-14 | 0 | 000285&&000362 | 2024-01-24, 2024-03-14 | 00 | 2 | For Information | INF | 2024-04-22 | Overdue | 0 | INF | INF
2055 | 000363 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0022 | 0 |  | 2024-03-15 | Milestone 1.2 - Underground Services | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0022 | NA | "Milestone 1.2 - Underground Services" && "Milestone 1.2 Underground Services" | 2024-03-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-04 | 67 | REJ | 2024-06-05 | 1 | 000161&&000363 | 2024-03-15, 2024-05-27, 2024-06-05 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
2056 | 000364 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0024 | 0 |  | 2024-03-15 | Milestone 1.2 - SSN Pump Station and Lamella Clarifier | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0024 | NA | "Milestone 1.2 - SSN Pump Station and Lamella Clarifier" && "Milestone 1.2 SSN Lamella Clarifier" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" | 2024-03-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-04 | 67 | REJ | 2025-10-31 | 1 | 000164&&000364 | 2024-03-15, 2024-06-04, 2025-04-22, 2025-10-31 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
2057 | 000365 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0028 | 0 |  | 2024-03-15 | Milestone 1.2 - Sitewide Pipe Rack | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0028 | NA | "Milestone 1.2 - Sitewide Pipe Rack" | 2024-03-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-04 | 67 | REJ | 2024-03-15 | 0 | 000365 | 2024-03-15 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2058 | 000366 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0035 | 0 |  | 2024-03-15 | Milestone 1.2 - SSN Minor Drain | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-16 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0035 | NA | "Milestone 1.2 - SSN Minor Drain" | 2024-03-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-04 | 67 | REJ | 2024-03-15 | 0 | 000366 | 2024-03-15 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2059 | 000367 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0023 | 0 |  | 2024-03-18 | Milestone 1.2 - SSN Water Tank | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0023 | NA | "Milestone 1.2 - SSN Water Tank" && "Milestone 1.2 SSN Water Tank" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-06-03 | 0 | 000163&&000367 | 2024-03-18, 2024-06-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
2060 | 000368 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0025 | 0 |  | 2024-03-18 | Milestone 1.2 - SSN Pump Station and Blower | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0025 | NA | "Milestone 1.2 - SSN Pump Station and Blower " && "Milestone 1.2 - SSN Pump Station and Blower Area" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2025-10-27 | 0 | 000162&&000368 | 2024-03-18, 2024-05-27, 2024-06-05, 2025-04-09, 2025-10-27 | 00, 01, 02, 03, 04 | 5 | Not Approved | NAP |  |  | 0 | REJ | REJ
2061 | 000369 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0026 | 0 |  | 2024-03-18 | Milestone 1.2 - SSN Chemical Dosing Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0026 | NA | "Milestone 1.2 - SSN Chemical Dosing Area " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000369 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2062 | 000370 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0027 | 0 |  | 2024-03-18 | Milestone 1.2 - SSN Electrical Building | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0027 | NA | "Milestone 1.2 - SSN Electrical Building " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000370 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2063 | 000371 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0029 | 0 |  | 2024-03-18 | Milestone 1.2 - THP Air Compress System | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0029 | NA | "Milestone 1.2 - THP Air Compress System " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000371 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2064 | 000372 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0030 | 0 |  | 2024-03-18 | Milestone 1.2 - THP Silo Area | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0030 | NA | "Milestone 1.2 - THP Silo Area " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000372 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2065 | 000373 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0031 | 0 |  | 2024-03-18 | Milestone 1.2 - THP Trains | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0031 | NA | "Milestone 1.2 - THP Trains " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000373 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2066 | 000374 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0032 | 0 |  | 2024-03-18 | Milestone 1.2 - THP Drainage | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0032 | NA | "Milestone 1.2 - THP Drainage " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000374 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2067 | 000375 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0033 | 0 |  | 2024-03-18 | Milestone 1.2 - THP Building Service | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0033 | NA | "Milestone 1.2 - THP Building Service" | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000375 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2068 | 000376 | 00 | Leon | BIM | NA | 131242 | WST02 | CD | IM | 0034 | 0 |  | 2024-03-18 | Milestone 1.2 - THP MCC Room | Rev 0: Rejected. Rejected based on email dt 09 May 24. Submission to include in subsequent MS1.1 submittal revision. | 2024-04-17 | 2024-05-21 | Rejected |  | YES | NA |  | 131242-WST02-CD-0034 | NA | "Milestone 1.2 - THP MCC Room " | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-07 | 64 | REJ | 2024-03-18 | 0 | 000376 | 2024-03-18 | 00 | 1 | Rejected | REJ | 2024-06-10 | Overdue | 0 | REJ | REJ
2069 | 000377 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0010 | 0 | 131242-WSW41-RT-PM-0010-0 | 2024-03-18 | C4B Monthly Progress Report Number No.10 (02 24) | Rev. 0 - Approved with comments - need to re-submit (see attached comment sheet) | 2024-04-17 | 2024-04-01 | Approved with Comments | 2024-04-22 | NO | Overdue |  | 131242-WSW41-RT-0010 | NA | "C4B Monthly Progress Report Number No.10 (02 24)" && "Report of DFS (GUIDE 3) for PIPE RACKS" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-07 | 14 | AWC | 2024-10-28 | 0 | 000377&&000786 | 2024-03-18, 2024-10-28 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2070 | 000378 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 0 | 131242-WSD11-SP-I-0002-0 | 2024-03-19 | Plant Control Narrative | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-18 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted | Pending MP info | 131242-WSD11-SP-0002 | NA | "Plant Control Narrative" | 2024-03-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-08 | 42 | AWC | 2024-10-21 | 1 | 000378 | 2024-03-19, 2024-10-21 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2071 | 000378 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 1 | 131242-WSD11-SP-I-0002-1 | 2024-10-21 | Plant Control Narrative | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-SP-0002 | NA | "Plant Control Narrative" | 2024-03-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2024-10-21 | 1 | 000378 | 2024-03-19, 2024-10-21 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
2072 | 000378 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0002 | 2 | 131242-WSD11-SP-I-0002-2 | 2024-10-21 | Plant Control Narrative | Rev 2: Approved. Please note: if there are any changes in controls, C4B will have to re-issue the document.” | 2024-11-11 | 2025-10-10 | Approved |  | YES | NA |  | 131242-WSD11-SP-0002 | NA | "Plant Control Narrative" | 2024-03-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-04 | 354 | APP | 2024-10-21 | 1 | 000378 | 2024-03-19, 2024-10-21 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-30 | Overdue | 0 | APP | APP
2073 | 000379 | 00 | Boopathi | PMT | NA | 131242 | WSW41 | VI | C | 0014 | 0 | 131242-WSW41-VI-C-0014-0 | 2024-03-19 | Vendor Approval for Waterproof Additive Specialist (CementAID) | Approved. | 2024-04-18 | 2024-03-26 | Approved |  | YES | NA |  | 131242-WSW41-VI-0014 | NA | "Vendor Approval for Waterproof Additive Specialist (CementAID)" | 2024-03-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-08 | 7 | APP | 2024-03-19 | 0 | 000379 | 2024-03-19 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
2074 | 000380 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-C-0007-0 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 | Approved with Comments | 2024-04-17 | YES | Resubmitted |  | 131242-WSW41-SP-0007 | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 6 | AWC | 2024-06-20 | 1 | 000380&&000433 | 2024-03-20, 2024-04-12, 2024-06-20 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2075 | 000380 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 1 | 131242-WSW41-SP-C-0007-1 | 2024-06-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited) | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-06-28 | Approved with Comments | 2024-07-18 | NO | Overdue |  | 131242-WSW41-SP-0007 | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-04 | 8 | AWC | 2024-06-20 | 1 | 000380&&000433 | 2024-03-20, 2024-04-12, 2024-06-20 | 00, 01 | 3 | Approved with Comments | AWC | 2024-07-18 | Overdue | 0 | AWC | AWC
2076 | 000381 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0006 | 0 | 131242-WSW41-SP-C-0006-0 | 2024-03-20 | Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-03-26 | Approved with Comments | 2024-04-17 | NO | Overdue |  | 131242-WSW41-SP-0006 | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (Alliance)" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 6 | AWC | 2024-03-20 | 0 | 000381 | 2024-03-20 | 00 | 1 | Approved with Comments | AWC | 2024-04-15 | Overdue | 0 | AWC | AWC
2077 | 000382 | 00 | Zora | CSA | NA | 131242 | WSW41 | CN | C | 0001 | 0 | 131242-WSW41-CN-C-0001-0 | 2024-03-20 | RFC For SSN Surface Drainage Layout | Approved | 2024-04-19 | 2024-08-29 | Approved |  | YES | NA |  | 131242-WSW41-CN-0001 | NA | "Proposed change of Manufacturer for SSN Discharge Transfer Pumps" && "RFC For HV Routing (from C3B1) to SSN Transformer Room" && "RFC For SSN Surface Drainage Layout" && "RFC for SSN aeration unit blower PLCs and Manufacturer for Motor and VFD" | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-03 | 162 | APP | 2024-04-19 | 1 | 000065&&000117&&000289&&000382 | 2023-08-08, 2023-10-06, 2023-12-12, 2024-01-26, 2024-03-20, 2024-04-19 | 00, 01 | 6 | Rejected | REJ |  |  | 0 | APP | APP
2078 | 000383 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | LT | PM | 0025 | 0 | 131242-WSW41-LT-PM-0025-0 | 2024-03-20 | Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rejected | 2024-04-19 | 2024-06-21 | Rejected | 2024-07-11 | YES | Resubmitted |  | 131242-WSW41-LT-0025 | NA | "Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 93 | REJ | 2024-03-20 | 0 | 000383 | 2024-03-20 | 00 | 1 | Rejected | REJ | 2024-07-11 | Overdue | 0 | REJ | REJ
2079 | 000383 | 01 | Theint Theint | Contracts | NA | 131242 | WSW41 | LT | PM | 0033 | 0 | 131242-WSW41-LT-PM-0033-0 | 2024-06-22 | Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework | Rev 1: Approved | 2024-07-11 | 2024-08-28 | Approved |  | YES | NA |  | 131242-WSW41-LT-0033 | NA | "Revised of Request for Approval to Contractor’s Revised Stage 2 BIM Model Progress Payment Framework" | 2024-06-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-12 | 67 | APP | 2024-06-22 | 0 | 000383 | 2024-06-22 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
2080 | 000384 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 0 | 131242-WST02-CL-P-0003-0 | 2024-03-20 | SSN Process Design Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-19 | 2024-04-25 | Approved with Comments | 2024-05-16 | YES | Resubmitted | Pending MP info | 131242-WST02-CL-0003 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-03 | 36 | AWC | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | Approved | APP |  |  | 0 | AWC | AWC
2081 | 000384 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0003 | 1 | 131242-WST02-CL-P-0003-1 | 2024-08-01 | SSN Process Design Calculation | Rev 1: Approved with Comments. Although there are no active comments the submittal is approved with comments to accommodate changes and resubmittal during the detail engineering. | 2024-08-22 | 2024-09-04 | Approved with Comments | 2024-09-24 | NO | Overdue |  | 131242-WST02-CL-0003 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Engineering Calculation Report For Potable Water Pipe" && "Engineering Calculation Report for Potable Water Pipe" && "SSN Process Design Calculation" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-15 | 34 | AWC | 2025-03-24 | 0 | 000097&&000194&&000384&&001153 | 2023-09-12, 2023-11-17, 2024-03-20, 2024-08-01, 2025-03-24 | 00, 01 | 5 | Approved | APP |  |  | 0 | AWC | AWC
2082 | 000385 | 00 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 0 | 131242-WST02-CH-P-0001-0 | 2024-03-20 | SSN Process Design Basis | R0: Not Approved. Please resubmit | 2024-04-19 | 2024-04-30 | Not Approved | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-CH-0001 | NA | "SSN Process Design Basis" | 2024-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 41 | NAP | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2083 | 000385 | 01 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 1 | 131242-WST02-CH-P-0001-1 | 2024-08-02 | SSN Process Design Basis | R1: Approved with comments. Address the comments and resubmit. | 2024-08-23 | 2024-09-04 | Approved with Comments | 2024-09-24 | YES | Resubmitted |  | 131242-WST02-CH-0001 | NA | "SSN Process Design Basis" | 2024-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-16 | 33 | AWC | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2084 | 000385 | 02 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 2 | 131242-WST02-CH-P-0001-2 | 2024-11-04 | SSN Process Design Basis | R2: Approved with comments. Address the comments and resubmit. | 2024-11-22 | 2025-01-09 | Approved with Comments | 2025-01-29 | YES | Resubmitted | comments received on 14 Feb | 131242-WST02-CH-0001 | NA | "SSN Process Design Basis" | 2024-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-18 | 66 | AWC | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2085 | 000385 | 03 | Qili | Process | NA | 131242 | WST02 | CH | P | 0001 | 3 | 131242-WST02-CH-P-0001-3 | 2025-02-24 | SSN Process Design Basis | R3: Approved with comments. | 2025-03-14 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WST02-CH-0001 | NA | "SSN Process Design Basis" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-10 | 17 | AWC | 2025-02-24 | 3 | 000385 | 2024-03-20, 2024-08-02, 2024-11-04, 2025-02-24 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-04-02 | Overdue | 0 | AWC | AWC
2086 | 000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0001_ST617 | 0 | 131242-WSD11-CL-S-0001_ST617-0 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSD11-CL-0001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | 0 | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2087 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST617 | A | 131242-WSW41-DR-S-1000_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2088 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1001_ST617 | A | 131242-WSW41-DR-S-1001_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2089 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1002_ST617 | A | 131242-WSW41-DR-S-1002_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2090 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 1003_ST617 | A | 131242-WSW41-DR-S-1003_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-1003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2091 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST617 | A | 131242-WSW41-DR-S-2001_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-2001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2092 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2002_ST617 | A | 131242-WSW41-DR-S-2002_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-2002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2093 | 000386 | 00 | Zora | CSA | NA | 131242 | WSW41 | DR | S | 2003_ST617 | A | 131242-WSW41-DR-S-2003_ST617-A | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-DR-2003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | A | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2094 | 000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | NA | THP_PF01 reaction table | 0 | 131242-WSD11-CL--THP_PF01 reaction table-0 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSD11-CL-THP_PF01 reaction table | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | 0 | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2095 | 000386 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | NA | THP_PF02_PR01 reaction table | 0 | 131242-WSD11-CL--THP_PF02_PR01 reaction table-0 | 2024-03-20 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-19 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSD11-CL-THP_PF02_PR01 reaction table | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-03-20 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 43 | NAP | 2024-03-20 | 0 | 000386 | 2024-03-20 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2096 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | A | 131242-WSD11-DR-S-0300_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-0300_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2097 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | A | 131242-WSD11-DR-S-0301_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-0301_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2098 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | A | 131242-WSD11-DR-S-1000_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-1000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2099 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | A | 131242-WSD11-DR-S-1001_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-1001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2100 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | A | 131242-WSD11-DR-S-1002_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-1002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2101 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | A | 131242-WSD11-DR-S-1003_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-1003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2102 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1004_ST617 | A | 131242-WSD11-DR-S-1004_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-1004_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-10-11 | B | 000386 | 2024-07-04, 2024-10-11 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2103 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | A | 131242-WSD11-DR-S-2000_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-2000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2104 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | A | 131242-WSD11-DR-S-2001_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-2001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2105 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | A | 131242-WSD11-DR-S-3000_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-3000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2106 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | A | 131242-WSD11-DR-S-3001_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-3001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2107 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | A | 131242-WSD11-DR-S-3002_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-3002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2108 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | A | 131242-WSD11-DR-S-5000_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2109 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | A | 131242-WSD11-DR-S-5001_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2110 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | A | 131242-WSD11-DR-S-5002_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2111 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | A | 131242-WSD11-DR-S-5003_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2112 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | A | 131242-WSD11-DR-S-5004_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5004_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2113 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | A | 131242-WSD11-DR-S-5005_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5005_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2114 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | A | 131242-WSD11-DR-S-5006_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-5006_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2115 | 000386 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | A | 131242-WSD11-DR-S-8000_ST617-A | 2024-07-04 | ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSD11-DR-8000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 39 | NAP | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2116 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0300_ST617 | B | 131242-WSD11-DR-S-0300_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-0300_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2117 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0301_ST617 | B | 131242-WSD11-DR-S-0301_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-0301_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2118 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000_ST617 | B | 131242-WSD11-DR-S-1000_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-1000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2119 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001_ST617 | B | 131242-WSD11-DR-S-1001_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-1001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2120 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1002_ST617 | B | 131242-WSD11-DR-S-1002_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-1002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2121 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1003_ST617 | B | 131242-WSD11-DR-S-1003_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-1003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2122 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1004_ST617 | B | 131242-WSD11-DR-S-1004_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-1004_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-10-11 | B | 000386 | 2024-07-04, 2024-10-11 | 01, 02 | 2 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
2123 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2000_ST617 | B | 131242-WSD11-DR-S-2000_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-2000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2124 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2001_ST617 | B | 131242-WSD11-DR-S-2001_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-2001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2125 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3000_ST617 | B | 131242-WSD11-DR-S-3000_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-3000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2126 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3001_ST617 | B | 131242-WSD11-DR-S-3001_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-3001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2127 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3002_ST617 | B | 131242-WSD11-DR-S-3002_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-3002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2128 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5000_ST617 | B | 131242-WSD11-DR-S-5000_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2129 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5001_ST617 | B | 131242-WSD11-DR-S-5001_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5001_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2130 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5002_ST617 | B | 131242-WSD11-DR-S-5002_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5002_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2131 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5003_ST617 | B | 131242-WSD11-DR-S-5003_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5003_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2132 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5004_ST617 | B | 131242-WSD11-DR-S-5004_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5004_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2133 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5005_ST617 | B | 131242-WSD11-DR-S-5005_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5005_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2134 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5006_ST617 | B | 131242-WSD11-DR-S-5006_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-5006_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2135 | 000386 | 02 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8000_ST617 | B | 131242-WSD11-DR-S-8000_ST617-B | 2024-10-11 | ST617 - THP-PF-01, 02 & THP-PR-01 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DR-8000_ST617 | NA | "ST617 - THP-PF-01, 02 & THP-PR-01 " && "ST617 - THP-PF-01, 02 & THP-PR-01 Conceptual Design Calculation & Drawings" && "ST617 -THP PLATFORM 01 & 02" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-25 | 18 | AWC | 2024-11-19 | A | 000386&&000824 | 2024-07-04, 2024-10-11, 2024-11-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2136 | 000387 | 00 | Thomas | PCM | NA | 131242 | WSW41 | PS | PM | 0010 | 0 | 131242-WSW41-PS-PM-0010-0 | 2024-03-22 | Monthly Progress Presentation No. 10 (0224) | For Information | 2024-04-23 | 2024-03-26 | For Information |  | YES | NA |  | 131242-WSW41-PS-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Incentive/ Disincentive Audit Scheme for Mar 2024" && "Monthly Progress Presentation No. 10 (0224)" | 2023-10-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-05 | 4 | INF | 2024-08-22 | 0 | 000152&&000387&&000666 | 2023-10-30, 2024-03-22, 2024-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
2137 | 000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0019 | 0 | 131242-WSW41-MI-C-0019-0 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | For Information |  | YES | NA |  | 131242-WSW41-MI-0019 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-05 | 4 | INF | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2138 | 000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0020 | 0 | 131242-WSW41-MI-C-0020-0 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | For Information |  | YES | NA |  | 131242-WSW41-MI-0020 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0020_20250122" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-05 | 4 | INF | 2025-02-18 | 0 | 000353&&000388&&000684&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2139 | 000388 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0021 | 0 | 131242-WSW41-MI-C-0021-0 | 2024-03-22 | CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07 | For Information | 2024-04-23 | 2024-03-26 | For Information |  | YES | NA |  | 131242-WSW41-MI-0021 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0021_20250226" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-11 | 4 | INF | 2025-04-21 | 0 | 000388&&000460&&000684&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2140 | 000389 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0009 | 0 | 131242-WSW41-PC-W-0009-0 | 2024-03-23 | Payment Claim No.9 | Rev(0): Approved. Refer to S.O. correspondence no. 137 dated 27 Mar 2024. | 2024-04-23 | 2024-05-10 | Approved |  | YES | NA |  | 131242-WSW41-PC-0009 | NA | "Payment Claim No.9" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-12 | 48 | APP | 2024-03-23 | 0 | 000389 | 2024-03-23 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
2141 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A | 131242-WSD11-DR-I-1000-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-06 | 87 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | INF | INF
2142 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1001 | A | 131242-WSD11-DR-I-1001-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-06 | 87 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | INF | INF
2143 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1002 | A | 131242-WSD11-DR-I-1002-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-06 | 87 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | INF | INF
2144 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 1003 | A | 131242-WSD11-DR-I-1003-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-06 | 87 | INF | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | INF | INF
2145 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3000 | A | 131242-WSD11-DR-I-3000-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-06 | 87 | INF | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | INF | INF
2146 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3001 | A | 131242-WSD11-DR-I-3001-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 87 | INF | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | INF | INF
2147 | 000390 | 00 | Yaw Feng | EICA | NA | 131242 | WSD11 | DR | I | 3002 | A | 131242-WSD11-DR-I-3002-A | 2024-03-23 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2024-04-23 | 2024-06-18 | For Information | 2024-07-08 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 87 | INF | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | INF | INF
2148 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1000 | A.1 | 131242-WSD11-DR-I-1000-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-16 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | INF | INF
2149 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1001 | A.1 | 131242-WSD11-DR-I-1001-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | INF | INF
2150 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1002 | A.1 | 131242-WSD11-DR-I-1002-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | INF | INF
2151 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 1003 | A.1 | 131242-WSD11-DR-I-1003-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | INF | INF
2152 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3000 | A.1 | 131242-WSD11-DR-I-3000-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | INF | INF
2153 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3001 | A.1 | 131242-WSD11-DR-I-3001-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | INF | INF
2154 | 000390 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 3002 | A.1 | 131242-WSD11-DR-I-3002-A.1 | 2024-08-27 | Biosolid Building Cable Tray Wall Opening Layout & Section Drawings | Rev 1: For Information | 2024-09-24 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 63 | INF | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | INF | INF
2155 | 000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | 0 | 131242-WSD11-DR-M-1170-0 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | For Information | 2024-08-30 | NO | Overdue | Submitted as S000681.1 | 131242-WSD11-DR-1170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 142 | INF | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | INF | INF
2156 | 000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | 0 | 131242-WSD11-DR-M-1171-0 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | For Information | 2024-08-30 | NO | Overdue |  | 131242-WSD11-DR-1171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 142 | INF | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | INF | INF
2157 | 000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | 0 | 131242-WSD11-DR-M-1172-0 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | For Information | 2024-08-30 | NO | Overdue |  | 131242-WSD11-DR-1172 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 142 | INF | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | INF | INF
2158 | 000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | 0 | 131242-WSD11-DR-M-3170-0 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | For Information | 2024-08-30 | NO | Overdue |  | 131242-WSD11-DR-3170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 142 | INF | 2025-02-18 | A.2 | 000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18 | 00, 01 | 3 | Approved | APP |  |  | 0 | INF | INF
2159 | 000391 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | 0 | 131242-WSD11-DR-M-3171-0 | 2024-03-23 | Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout | Rev 0: For Information To revise and resubmit. Refer to attached file for comments. | 2024-04-23 | 2024-08-12 | For Information | 2024-08-30 | NO | Overdue |  | 131242-WSD11-DR-3171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-12 | 142 | INF | 2025-02-18 | A.2 | 000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18 | 00, 01 | 3 | Approved | APP |  |  | 0 | INF | INF
2160 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7308 | A | 131242-WSD11-DR-I-7308-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7308 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2026-01-27 | B | 000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2161 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7309 | A | 131242-WSD11-DR-I-7309-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7309 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2162 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7310 | A | 131242-WSD11-DR-I-7310-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7310 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2026-01-27 | A | 000392&&001987 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2163 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7311 | A | 131242-WSD11-DR-I-7311-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7311 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2164 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7312 | A | 131242-WSD11-DR-I-7312-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7312 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2026-01-27 | A | 000392&&001988 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2165 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7313 | A | 131242-WSD11-DR-I-7313-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7313 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2166 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7314 | A | 131242-WSD11-DR-I-7314-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7314 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2167 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7315 | A | 131242-WSD11-DR-I-7315-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7315 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2168 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7316 | A | 131242-WSD11-DR-I-7316-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7316 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2169 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7317 | A | 131242-WSD11-DR-I-7317-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7317 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2170 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7318 | A | 131242-WSD11-DR-I-7318-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7318 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2171 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7319 | A | 131242-WSD11-DR-I-7319-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7319 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2172 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7320 | A | 131242-WSD11-DR-I-7320-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7320 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2173 | 000392 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | DR | I | 7321 | A | 131242-WSD11-DR-I-7321-A | 2024-03-25 | Compressor Sequencer Panel | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-24 | 2024-05-14 | Not Approved | 2024-06-04 | YES | Resubmitted |  | 131242-WSD11-DR-7321 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 50 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2174 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | B | 131242-WSD11-DR-I-7307-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7307 | NA | "Compressor Sequencer Panel" | 2024-06-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-16 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-06-26, 2025-01-15, 2025-06-16 | 01, 03, 04 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2175 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7308 | B | 131242-WSD11-DR-I-7308-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7308 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2026-01-27 | B | 000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2176 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7309 | B | 131242-WSD11-DR-I-7309-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7309 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2177 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7310 | B | 131242-WSD11-DR-I-7310-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7310 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2026-01-27 | A | 000392&&001987 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2178 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7311 | B | 131242-WSD11-DR-I-7311-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7311 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2179 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7312 | B | 131242-WSD11-DR-I-7312-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7312 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2026-01-27 | A | 000392&&001988 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2180 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7313 | B | 131242-WSD11-DR-I-7313-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7313 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2181 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7314 | B | 131242-WSD11-DR-I-7314-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7314 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2182 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7315 | B | 131242-WSD11-DR-I-7315-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7315 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2183 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7316 | B | 131242-WSD11-DR-I-7316-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7316 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2184 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7317 | B | 131242-WSD11-DR-I-7317-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7317 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2185 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7318 | B | 131242-WSD11-DR-I-7318-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7318 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2186 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7319 | B | 131242-WSD11-DR-I-7319-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7319 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2187 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7320 | B | 131242-WSD11-DR-I-7320-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7320 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2188 | 000392 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7321 | B | 131242-WSD11-DR-I-7321-B | 2024-06-26 | Compressor Sequencer Panel | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-16 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-DR-7321 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 83 | NAP | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2189 | 000392 | 02 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | C | 131242-WSD11-DR-I-7306-C | 2024-11-19 | Compressor Sequencer Panel | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-09 | 2024-12-18 | Not Approved | 2025-01-08 | YES | Resubmitted |  | 131242-WSD11-DR-7306 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-09 | 29 | NAP | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2190 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7306 | D | 131242-WSD11-DR-I-7306-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-DR-7306 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2191 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7307 | D | 131242-WSD11-DR-I-7307-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7307 | NA | "Compressor Sequencer Panel" | 2024-06-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-06-26, 2025-01-15, 2025-06-16 | 01, 03, 04 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2192 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7308 | D | 131242-WSD11-DR-I-7308-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7308 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2026-01-27 | B | 000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2193 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7309 | D | 131242-WSD11-DR-I-7309-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7309 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2194 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7310 | D | 131242-WSD11-DR-I-7310-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7310 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2026-01-27 | A | 000392&&001987 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2195 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7311 | D | 131242-WSD11-DR-I-7311-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7311 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2196 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7312 | D | 131242-WSD11-DR-I-7312-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7312 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2026-01-27 | A | 000392&&001988 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2197 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7313 | D | 131242-WSD11-DR-I-7313-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7313 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2198 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7314 | D | 131242-WSD11-DR-I-7314-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7314 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2199 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7315 | D | 131242-WSD11-DR-I-7315-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7315 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2200 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7316 | D | 131242-WSD11-DR-I-7316-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7316 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2201 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7317 | D | 131242-WSD11-DR-I-7317-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7317 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2202 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7318 | D | 131242-WSD11-DR-I-7318-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7318 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2203 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7319 | D | 131242-WSD11-DR-I-7319-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7319 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2204 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7320 | D | 131242-WSD11-DR-I-7320-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7320 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2205 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7321 | D | 131242-WSD11-DR-I-7321-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7321 | NA | "Compressor Sequencer Panel" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-29 | 69 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2206 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7322 | D | 131242-WSD11-DR-I-7322-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7322 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2207 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7323 | D | 131242-WSD11-DR-I-7323-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7323 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2208 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7324 | D | 131242-WSD11-DR-I-7324-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7324 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2209 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7325 | D | 131242-WSD11-DR-I-7325-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7325 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2210 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7326 | D | 131242-WSD11-DR-I-7326-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7326 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2211 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7327 | D | 131242-WSD11-DR-I-7327-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7327 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2212 | 000392 | 03 | Low | EICA | NA | 131242 | WSD11 | DR | I | 7328 | D | 131242-WSD11-DR-I-7328-D | 2025-01-15 | Compressor Sequencer Panel | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-02-04 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WSD11-DR-7328 | NA | "Compressor Sequencer Panel" | 2025-01-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 69 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2213 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7306 | E | 131242-WSD11-DR-I-7306-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7306 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2214 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7307 | E | 131242-WSD11-DR-I-7307-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7307 | NA | "Compressor Sequencer Panel" | 2024-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-06-26, 2025-01-15, 2025-06-16 | 01, 03, 04 | 3 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2215 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7308 | E | 131242-WSD11-DR-I-7308-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7308 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2026-01-27 | B | 000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2216 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7309 | E | 131242-WSD11-DR-I-7309-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7309 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2217 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7310 | E | 131242-WSD11-DR-I-7310-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7310 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2026-01-27 | A | 000392&&001987 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2218 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7311 | E | 131242-WSD11-DR-I-7311-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7311 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2219 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7312 | E | 131242-WSD11-DR-I-7312-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7312 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2026-01-27 | A | 000392&&001988 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2220 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7313 | E | 131242-WSD11-DR-I-7313-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7313 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2221 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7314 | E | 131242-WSD11-DR-I-7314-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7314 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2222 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7315 | E | 131242-WSD11-DR-I-7315-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7315 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2223 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7316 | E | 131242-WSD11-DR-I-7316-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7316 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2224 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7317 | E | 131242-WSD11-DR-I-7317-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7317 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2225 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7318 | E | 131242-WSD11-DR-I-7318-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7318 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2226 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7319 | E | 131242-WSD11-DR-I-7319-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7319 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2227 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7320 | E | 131242-WSD11-DR-I-7320-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7320 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2228 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7321 | E | 131242-WSD11-DR-I-7321-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7321 | NA | "Compressor Sequencer Panel" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2229 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7322 | E | 131242-WSD11-DR-I-7322-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7322 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2230 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7323 | E | 131242-WSD11-DR-I-7323-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7323 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2231 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7324 | E | 131242-WSD11-DR-I-7324-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7324 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2232 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7325 | E | 131242-WSD11-DR-I-7325-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7325 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2233 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7326 | E | 131242-WSD11-DR-I-7326-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7326 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2234 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7327 | E | 131242-WSD11-DR-I-7327-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7327 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2235 | 000392 | 04 | Karthik | EICA | NA | 131242 | WSD11 | DR | I | 7328 | E | 131242-WSD11-DR-I-7328-E | 2025-06-16 | Compressor Sequencer Panel | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-DR-7328 | NA | "Compressor Sequencer Panel" | 2025-01-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 176 | AWC | 2025-06-16 | E | 000392 | 2025-01-15, 2025-06-16 | 03, 04 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
2236 | 000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-E-7700-A | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7700 | NA | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000393 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2237 | 000393 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7701 | A | 131242-WSD11-DR-E-7701-A | 2024-03-25 | THP Schematic Diagram for Compressed Air System | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7701 | NA | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000393 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2238 | 000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7700 | A | 131242-WSD11-DR-E-7700-A | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue | To check with Yibo and will advise later the submission date. | 131242-WSD11-DR-7700 | NA | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000393 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2239 | 000393 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7701 | A | 131242-WSD11-DR-E-7701-A | 2024-08-13 | THP Schematic Diagram for Compressed Air System | Rev 1: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-09-02 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-DR-7701 | NA | "THP Schematic Diagram for Compressed Air System" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000393 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2240 | 000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-E-7720-A | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7720 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2241 | 000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7721 | A | 131242-WSD11-DR-E-7721-A | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7721 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2242 | 000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7722 | A | 131242-WSD11-DR-E-7722-A | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7722 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2243 | 000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7723 | A | 131242-WSD11-DR-E-7723-A | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7723 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2244 | 000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7724 | A | 131242-WSD11-DR-E-7724-A | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7724 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2245 | 000394 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7725 | A | 131242-WSD11-DR-E-7725-A | 2024-03-25 | THP Schematic Diagram for Compressed Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached file for comments. | 2024-04-24 | 2024-05-17 | Approved with Comments | 2024-06-07 | YES | Resubmitted |  | 131242-WSD11-DR-7725 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 53 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2246 | 000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7720 | A | 131242-WSD11-DR-E-7720-A | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-02 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue | To check with Yibo and will advise later the submission date. | 131242-WSD11-DR-7720 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2247 | 000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7721 | A | 131242-WSD11-DR-E-7721-A | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-DR-7721 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2248 | 000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7722 | A | 131242-WSD11-DR-E-7722-A | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-DR-7722 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2249 | 000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7723 | A | 131242-WSD11-DR-E-7723-A | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-DR-7723 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2250 | 000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7724 | A | 131242-WSD11-DR-E-7724-A | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-DR-7724 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2251 | 000394 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 7725 | A | 131242-WSD11-DR-E-7725-A | 2024-08-13 | THP Schematic Diagram for Compressed Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. | 2024-09-10 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-DR-7725 | NA | "THP Schematic Diagram for Compressed Air Dryer" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 87 | AWC | 2024-08-13 | A | 000394 | 2024-03-25, 2024-08-13 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-28 | Overdue | 0 | AWC | AWC
2252 | 000395 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | A | 131242-WSD11-DR-E-3160-A | 2024-03-25 | Air Compressor Motor Outline Drawing | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached files for comments. | 2024-04-24 | 2024-05-16 | Approved with Comments | 2024-06-06 | YES | Resubmitted |  | 131242-WSD11-DR-3160 | NA | "Air Compressor Motor Outline Drawing " | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 52 | AWC | 2024-08-16 | B | 000395 | 2024-03-25, 2024-08-16 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
2253 | 000395 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | E | 3160 | B | 131242-WSD11-DR-E-3160-B | 2024-08-16 | Air Compressor Motor Outline Drawing | Rev 1: Approved. | 2024-09-05 | 2024-11-04 | Approved |  | YES | NA |  | 131242-WSD11-DR-3160 | NA | "Air Compressor Motor Outline Drawing " | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-30 | 80 | APP | 2024-08-16 | B | 000395 | 2024-03-25, 2024-08-16 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2254 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-A-1000_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2255 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A | 131242-WST02-DR-A-1001_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2256 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A | 131242-WST02-DR-A-1002_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2257 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A | 131242-WST02-DR-A-1003_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2258 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A | 131242-WST02-DR-A-1004_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2259 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A | 131242-WST02-DR-A-1009_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2260 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A | 131242-WST02-DR-A-2001_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2261 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A | 131242-WST02-DR-A-2002_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2262 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A | 131242-WST02-DR-A-2003_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2263 | 000396 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS-A | 2024-03-25 | LTA & Nparks submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2007_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2264 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-A-0001_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-0001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-05 | 21 | NAP | 2024-10-30 | A | 000396 | 2024-05-16, 2024-10-30 | 01, 02 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2265 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A | 131242-WST02-DR-A-1000_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2266 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A | 131242-WST02-DR-A-1001_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2267 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A | 131242-WST02-DR-A-1002_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2268 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A | 131242-WST02-DR-A-1003_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2269 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A | 131242-WST02-DR-A-1004_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2270 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A | 131242-WST02-DR-A-1009_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2271 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A | 131242-WST02-DR-A-2000_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-05 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
2272 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A | 131242-WST02-DR-A-2001_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2273 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A | 131242-WST02-DR-A-2002_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2274 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A | 131242-WST02-DR-A-2003_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2275 | 000396 | 01 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS-A | 2024-05-16 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-06 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-DR-2007_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-30 | 21 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2276 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2277 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.1 | 131242-WST02-DR-A-1001_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2278 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.1 | 131242-WST02-DR-A-1002_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2279 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.1 | 131242-WST02-DR-A-1003_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2280 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2281 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | A.1 | 131242-WST02-DR-A-1006_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1006_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 70 | NAP | 2026-01-09 | A | 000396 | 2024-10-30, 2026-01-09 | 02, 07 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2282 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.1 | 131242-WST02-DR-A-1009_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2283 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.1 | 131242-WST02-DR-A-2000_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
2284 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A.1 | 131242-WST02-DR-A-2001_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-2001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2285 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A.1 | 131242-WST02-DR-A-2002_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-2002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2286 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A.1 | 131242-WST02-DR-A-2003_LTA_NPKS-A.1 | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-2003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2287 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A | 131242-WST02-DR-A-2007_LTA_NPKS-A | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-2007_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
2288 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | A | 131242-WST02-DR-A-3000_LTA_NPKS-A | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-3000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 70 | NAP | 2026-01-09 | A.2 | 000396 | 2024-10-30, 2026-01-09 | 02, 07 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2289 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5004_LTA_NPKS | A | 131242-WST02-DR-A-5004_LTA_NPKS-A | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-5004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 70 | NAP | 2024-10-30 | A | 000396 | 2024-10-30 | 02 | 1 | Not Approved | NAP | 2025-01-28 | Overdue | 0 | NAP | NAP
2290 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 0001_LTA_NPKS | A | 131242-WST02-DR-A-0001_LTA_NPKS-A | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-0001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-13 | 70 | NAP | 2024-10-30 | A | 000396 | 2024-05-16, 2024-10-30 | 01, 02 | 2 | Not Approved | NAP | 2025-01-28 | Overdue | 0 | NAP | NAP
2291 | 000396 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 0002_LTA_NPKS | B | 131242-WST02-DR-A-0002_LTA_NPKS-B | 2024-10-30 | LTA & Nparks submission Set | Rev.2: Not Approved. Please refer to markup comments for resubmission. | 2024-11-20 | 2025-01-08 | Not Approved | 2025-01-28 | YES | Resubmitted |  | 131242-WST02-DR-0002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 70 | NAP | 2024-10-30 | B | 000396 | 2024-10-30 | 02 | 1 | Not Approved | NAP | 2025-01-28 | Overdue | 0 | NAP | NAP
2292 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS-A.1 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted | Rejected as CES requested as drawings need to be included PE endorsement | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2293 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS-A.2 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2294 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.2 | 131242-WST02-DR-A-1002_LTA_NPKS-A.2 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2295 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.2 | 131242-WST02-DR-A-1003_LTA_NPKS-A.2 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2296 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS-A.1 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2297 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.2 | 131242-WST02-DR-A-1009_LTA_NPKS-A.2 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2298 | 000396 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS-A.2 | 2025-03-10 | LTA & Nparks submission Set | Rev 3: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
2299 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS-A.1 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2300 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS-A.2 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2301 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.2 | 131242-WST02-DR-A-1002_LTA_NPKS-A.2 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2302 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.2 | 131242-WST02-DR-A-1003_LTA_NPKS-A.2 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2303 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.1 | 131242-WST02-DR-A-1004_LTA_NPKS-A.1 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2304 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.2 | 131242-WST02-DR-A-1009_LTA_NPKS-A.2 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2305 | 000396 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS-A.2 | 2025-03-21 | LTA & Nparks submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
2306 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS-A.1 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2307 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS-A.2 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2308 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.3 | 131242-WST02-DR-A-1002_LTA_NPKS-A.3 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2309 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.3 | 131242-WST02-DR-A-1003_LTA_NPKS-A.3 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2310 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.3 | 131242-WST02-DR-A-1004_LTA_NPKS-A.3 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2311 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.3 | 131242-WST02-DR-A-1009_LTA_NPKS-A.3 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | NAP | NAP
2312 | 000396 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS-A.2 | 2025-08-12 | LTA & Nparks submission Set | Rev.5: Not Approved. Please refer to markup comments for resubmission. | 2025-09-01 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-26 | 62 | NAP | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ |  |  | 0 | NAP | NAP
2313 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.1 | 131242-WST02-DR-A-1000_LTA_NPKS-A.1 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2314 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.2 | 131242-WST02-DR-A-1001_LTA_NPKS-A.2 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2315 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.3 | 131242-WST02-DR-A-1002_LTA_NPKS-A.3 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2316 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.3 | 131242-WST02-DR-A-1003_LTA_NPKS-A.3 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2317 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.3 | 131242-WST02-DR-A-1004_LTA_NPKS-A.3 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2318 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.3 | 131242-WST02-DR-A-1009_LTA_NPKS-A.3 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ |  |  | 0 | REJ | REJ
2319 | 000396 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.2 | 131242-WST02-DR-A-2000_LTA_NPKS-A.2 | 2025-11-18 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ |  |  | 0 | REJ | REJ
2320 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_LTA_NPKS | A.2 | 131242-WST02-DR-A-1000_LTA_NPKS-A.2 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.2 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2321 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_LTA_NPKS | A.4 | 131242-WST02-DR-A-1001_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2322 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_LTA_NPKS | A.4 | 131242-WST02-DR-A-1002_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2323 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_LTA_NPKS | A.4 | 131242-WST02-DR-A-1003_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2324 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_LTA_NPKS | A.4 | 131242-WST02-DR-A-1004_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2325 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_LTA_NPKS | A | 131242-WST02-DR-A-1005_LTA_NPKS-A | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2026-01-09 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-29 | 87 | PEN | 2026-01-09 | A | 000396 | 2026-01-09 | 07 | 1 | Awaiting S.O.'s response | PEN | 2026-02-26 |  | 0 | PEN | PEN
2326 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_LTA_NPKS | A | 131242-WST02-DR-A-1006_LTA_NPKS-A | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A | 000396 | 2024-10-30, 2026-01-09 | 02, 07 | 2 | Not Approved | NAP | 2026-02-26 |  | 0 | PEN | PEN
2327 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_LTA_NPKS | A.4 | 131242-WST02-DR-A-1009_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 00, 01, 02, 03, 04, 05, 06, 07 | 8 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2328 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_LTA_NPKS | A.4 | 131242-WST02-DR-A-2000_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-05-16 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-05-16, 2024-10-30, 2025-03-10, 2025-03-21, 2025-08-12, 2025-11-18, 2026-01-09 | 01, 02, 03, 04, 05, 06, 07 | 7 | Rejected | REJ | 2026-02-26 |  | 0 | PEN | PEN
2329 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_LTA_NPKS | A.4 | 131242-WST02-DR-A-2001_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2001_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP | 2026-02-26 |  | 0 | PEN | PEN
2330 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_LTA_NPKS | A.4 | 131242-WST02-DR-A-2002_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2002_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP | 2026-02-26 |  | 0 | PEN | PEN
2331 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_LTA_NPKS | A.4 | 131242-WST02-DR-A-2003_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2003_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP | 2026-02-26 |  | 0 | PEN | PEN
2332 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_LTA_NPKS | A.4 | 131242-WST02-DR-A-2007_LTA_NPKS-A.4 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2007_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.4 | 000396 | 2024-03-25, 2024-05-16, 2024-10-30, 2026-01-09 | 00, 01, 02, 07 | 4 | Not Approved | NAP | 2026-02-26 |  | 0 | PEN | PEN
2333 | 000396 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_LTA_NPKS | A.2 | 131242-WST02-DR-A-3000_LTA_NPKS-A.2 | 2026-01-09 | LTA & Nparks submission Set | R6: Contractor requested for rejection as per attached email. | 2026-01-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3000_LTA_NPKS | NA | "LTA & Nparks submission Set" | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-23 | 87 | PEN | 2026-01-09 | A.2 | 000396 | 2024-10-30, 2026-01-09 | 02, 07 | 2 | Not Approved | NAP | 2026-02-26 |  | 0 | PEN | PEN
2334 | 000397 | 00 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 0000_NEA | A | 131242-WST02-DR-A-0000_NEA-A | 2024-03-25 | NEA DC submission Set | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-0000_NEA | NA | "NEA DC submission Set " | 2024-03-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-14 | 38 | NAP | 2024-03-25 | A | 000397 | 2024-03-25 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2335 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2336 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.1 | 131242-WST02-DR-A-1001_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2337 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.1 | 131242-WST02-DR-A-1002_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2338 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.1 | 131242-WST02-DR-A-1003_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2339 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.1 | 131242-WST02-DR-A-1004_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1004_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2340 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_NEA | A.1 | 131242-WST02-DR-A-1006_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1006_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2341 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.1 | 131242-WST02-DR-A-1009_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-1009_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2342 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.1 | 131242-WST02-DR-A-2000_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-11-18, 2026-01-06 | 01, 04, 05 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
2343 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_NEA | A.1 | 131242-WST02-DR-A-2001_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2344 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_NEA | A.1 | 131242-WST02-DR-A-2002_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2345 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_NEA | A.1 | 131242-WST02-DR-A-2003_NEA-A.1 | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2346 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_NEA | A | 131242-WST02-DR-A-2007_NEA-A | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-2007_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2347 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_NEA | A | 131242-WST02-DR-A-3000_NEA-A | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-3000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2348 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 5004_NEA | A | 131242-WST02-DR-A-5004_NEA-A | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-5004_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2024-10-30 | A | 000397 | 2024-10-30 | 01 | 1 | Not Approved | NAP | 2025-02-05 | Overdue | 0 | NAP | NAP
2349 | 000397 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | A | 0002_NEA | B | 131242-WST02-DR-A-0002_NEA-B | 2024-10-30 | NEA DC submission Set | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-20 | 2025-01-16 | Not Approved | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DR-0002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 78 | NAP | 2024-10-30 | B | 000397 | 2024-10-30 | 01 | 1 | Not Approved | NAP | 2025-02-05 | Overdue | 0 | NAP | NAP
2350 | 000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA-A.1 | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted | Rejected as CES requested as drawings need to be included PE endorsement | 131242-WST02-DR-1000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2351 | 000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA-A.2 | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2352 | 000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.2 | 131242-WST02-DR-A-1002_NEA-A.2 | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2353 | 000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.2 | 131242-WST02-DR-A-1003_NEA-A.2 | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2354 | 000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.2 | 131242-WST02-DR-A-1004_NEA-A.2 | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1004_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2355 | 000397 | 02 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.2 | 131242-WST02-DR-A-1009_NEA-A.2 | 2025-03-10 | NEA DC submission Set | Rev 2: Rejected (as requested by contractor via email dated 19 March 2025. | 2025-03-28 | 2025-03-21 | Rejected | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-1009_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-24 | 11 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2356 | 000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA-A.1 | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2357 | 000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA-A.2 | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2358 | 000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.2 | 131242-WST02-DR-A-1002_NEA-A.2 | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2359 | 000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.2 | 131242-WST02-DR-A-1003_NEA-A.2 | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2360 | 000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.2 | 131242-WST02-DR-A-1004_NEA-A.2 | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1004_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2361 | 000397 | 03 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.2 | 131242-WST02-DR-A-1009_NEA-A.2 | 2025-03-21 | NEA DC submission Set | Not Approved - Revise and resubmit | 2025-04-10 | 2025-06-11 | Not Approved | 2025-07-01 | YES | Resubmitted |  | 131242-WST02-DR-1009_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-04 | 82 | NAP | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | NAP | NAP
2362 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.1 | 131242-WST02-DR-A-1000_NEA-A.1 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2363 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.2 | 131242-WST02-DR-A-1001_NEA-A.2 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2364 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.3 | 131242-WST02-DR-A-1002_NEA-A.3 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2365 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.3 | 131242-WST02-DR-A-1003_NEA-A.3 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2366 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.3 | 131242-WST02-DR-A-1004_NEA-A.3 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1004_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2367 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.3 | 131242-WST02-DR-A-1009_NEA-A.3 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-1009_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ |  |  | 0 | REJ | REJ
2368 | 000397 | 04 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.2 | 131242-WST02-DR-A-2000_NEA-A.2 | 2025-11-18 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2025-12-08 | 2025-12-17 | Rejected | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-2000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | REJ | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-11-18, 2026-01-06 | 01, 04, 05 | 3 | Rejected | REJ |  |  | 0 | REJ | REJ
2369 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1000_NEA | A.2 | 131242-WST02-DR-A-1000_NEA-A.2 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2370 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1001_NEA | A.4 | 131242-WST02-DR-A-1001_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2371 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1002_NEA | A.4 | 131242-WST02-DR-A-1002_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2372 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1003_NEA | A.4 | 131242-WST02-DR-A-1003_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2373 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1004_NEA | A.4 | 131242-WST02-DR-A-1004_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2374 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1005_NEA | A | 131242-WST02-DR-A-1005_NEA-A | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005_NEA | NA | "NEA DC submission Set " | 2026-01-06 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-26 | 90 | PEN | 2026-01-06 | A | 000397 | 2026-01-06 | 05 | 1 | Awaiting S.O.'s response | PEN | 2026-02-23 |  | 0 | PEN | PEN
2375 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1006_NEA | A | 131242-WST02-DR-A-1006_NEA-A | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP | 2026-02-23 |  | 0 | PEN | PEN
2376 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 1009_NEA | A.4 | 131242-WST02-DR-A-1009_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-03-10, 2025-03-21, 2025-11-18, 2026-01-06 | 01, 02, 03, 04, 05 | 5 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2377 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2000_NEA | A.4 | 131242-WST02-DR-A-2000_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2025-11-18, 2026-01-06 | 01, 04, 05 | 3 | Rejected | REJ | 2026-02-23 |  | 0 | PEN | PEN
2378 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2001_NEA | A.4 | 131242-WST02-DR-A-2001_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2001_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP | 2026-02-23 |  | 0 | PEN | PEN
2379 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2002_NEA | A.4 | 131242-WST02-DR-A-2002_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2002_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP | 2026-02-23 |  | 0 | PEN | PEN
2380 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2003_NEA | A.4 | 131242-WST02-DR-A-2003_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2003_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP | 2026-02-23 |  | 0 | PEN | PEN
2381 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 2007_NEA | A.4 | 131242-WST02-DR-A-2007_NEA-A.4 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2007_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.4 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP | 2026-02-23 |  | 0 | PEN | PEN
2382 | 000397 | 05 | Zora/HP | CSA | NA | 131242 | WST02 | DR | A | 3000_NEA | A.2 | 131242-WST02-DR-A-3000_NEA-A.2 | 2026-01-06 | NEA DC submission Set | R4: Contractor requested for rejection as per attached email. | 2026-01-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3000_NEA | NA | "NEA DC submission Set " | 2024-10-30 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-20 | 90 | PEN | 2026-01-06 | A.2 | 000397 | 2024-10-30, 2026-01-06 | 01, 05 | 2 | Not Approved | NAP | 2026-02-23 |  | 0 | PEN | PEN
2383 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6000 | A | 131242-WST02-DR-P-6000-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted | Heng Peng to provide DGN dwg | 131242-WST02-DR-6000 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2384 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6001 | A | 131242-WST02-DR-P-6001-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6001 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2385 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6002 | A | 131242-WST02-DR-P-6002-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6002 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2386 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6003 | A | 131242-WST02-DR-P-6003-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6003 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2387 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6004 | A | 131242-WST02-DR-P-6004-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6004 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2388 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6005 | A | 131242-WST02-DR-P-6005-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6005 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2389 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6006 | A | 131242-WST02-DR-P-6006-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6006 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2390 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6007 | A | 131242-WST02-DR-P-6007-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6007 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2391 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6008 | A | 131242-WST02-DR-P-6008-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6008 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2392 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6009 | A | 131242-WST02-DR-P-6009-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6009 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2393 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6010 | A | 131242-WST02-DR-P-6010-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6010 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2394 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6011 | A | 131242-WST02-DR-P-6011-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6011 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2395 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6012 | A | 131242-WST02-DR-P-6012-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6012 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2396 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6013 | A | 131242-WST02-DR-P-6013-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6013 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2397 | 000398 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6014 | A | 131242-WST02-DR-P-6014-A | 2024-03-26 | P&ID for SSN Process | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6014 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2398 | 000398 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#398 CES Reply | A | 131242-WST02--P-S#398 CES Reply- | 2024-10-01 | P&ID for SSN Process | Rev 1: the submittal is closed as per the request of C4B contractor and merged to SRC 731 | 2024-10-21 | 2024-10-24 | Approved with Comments |  | YES | NA |  | 131242-WST02-NA-S#398 CES Reply | NA | "P&ID for SSN Process" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-21 | 23 | AWC | 2024-10-01 | A | 000398 | 2024-10-01 | 01 | 1 | Approved with Comments | AWC | 2024-11-13 | Overdue | 0 | AWC | AWC
2399 | 000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6015 | A | 131242-WST02-DR-P-6015-A | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted | Heng Peng to provide DGN dwg | 131242-WST02-DR-6015 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 35 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2400 | 000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6016 | A | 131242-WST02-DR-P-6016-A | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-6016 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 35 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2401 | 000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6017 | A | 131242-WST02-DR-P-6017-A | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-6017 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 35 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2402 | 000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6018 | A | 131242-WST02-DR-P-6018-A | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-6018 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 35 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2403 | 000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6019 | A | 131242-WST02-DR-P-6019-A | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-6019 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 35 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2404 | 000399 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6020 | A | 131242-WST02-DR-P-6020-A | 2024-03-26 | P&ID for SSN Chemical Dosing Systems | Rev0: Approved with comments, resubmission is required as per the comment sheet. | 2024-04-25 | 2024-04-30 | Approved with Comments | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-6020 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 35 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2405 | 000399 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | NA | NA | S#399 CES Reply | A | 131242-WSD11---S#399 CES Reply- | 2024-10-01 | P&ID for SSN Process | Rev1: The submittal is merged with SRC 731. | 2024-10-21 | 2024-11-07 | Approved with Comments |  | YES | NA |  | 131242-WSD11-NA-S#399 CES Reply | NA | "P&ID for SSN Process" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-21 | 37 | AWC | 2024-10-01 | A | 000399 | 2024-10-01 | 01 | 1 | Approved with Comments | AWC | 2024-11-27 | Overdue | 0 | AWC | AWC
2406 | 000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6200 | A | 131242-WST02-DR-P-6200-A | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted | Heng Peng to provide DGN dwg | 131242-WST02-DR-6200 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2407 | 000400 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6600 | A | 131242-WST02-DR-P-6600-A | 2024-03-26 | P&ID for SSN Plant Water and Instrument Air | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-25 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-DR-6600 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-15 | 58 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2408 | 000400 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | NA | P | S#400 CES Reply | A | 131242-WST02--P-S#400 CES Reply- | 2024-10-01 | P&ID for SSN Plant Water and Instrument Air | Rev 1: The submittal is closed and merged with SRC 731. Resubmission in other submittal. | 2024-10-21 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WST02-NA-S#400 CES Reply | NA | "P&ID for SSN Plant Water and Instrument Air" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Document_Type not in document_type_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-21 | 28 | APP | 2024-10-01 | A | 000400 | 2024-10-01 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
2409 | 000401 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7000 | A | 131242-WST02-DR-I-7000-A | 2024-03-26 | SSN Control System Architecture Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-04-25 | 2024-04-30 | Not Approved | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-09 | 35 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2410 | 000401 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7000 | B | 131242-WST02-DR-I-7000-B | 2024-08-26 | SSN Control System Architecture Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-13 | 2024-10-16 | Approved with Comments | 2024-11-06 | NO | Overdue |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 51 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2411 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2412 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2413 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2414 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2415 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2416 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A | 131242-WST02-DR-A-1009_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2417 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2418 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2419 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A | 131242-WST02-DR-A-2003_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2420 | 000402 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP-A | 2024-03-27 | SSN_FSSD (BP) Submission | Rev.0: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-04-26 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 22 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2421 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-10 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2422 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2423 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2424 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2425 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2426 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A | 131242-WST02-DR-A-1009_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2427 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2428 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2429 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A | 131242-WST02-DR-A-2003_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2430 | 000402 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP-A | 2024-04-19 | SSN_FSSD (BP) Submission | Rev.1: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2024-05-20 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 13 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2431 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A | 131242-WST02-DR-A-1000_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2432 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A | 131242-WST02-DR-A-1001_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2433 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A | 131242-WST02-DR-A-1002_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2434 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A | 131242-WST02-DR-A-1003_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2435 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A | 131242-WST02-DR-A-1004_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2436 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A | 131242-WST02-DR-A-2000_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-02 | 11 | NAP | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2437 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A | 131242-WST02-DR-A-2001_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2438 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A | 131242-WST02-DR-A-2002_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2439 | 000402 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP-A | 2024-05-13 | SSN_FSSD (BP) Submission | Rev.2: Not Approved. Please submit dgn files. | 2024-06-03 | 2024-05-24 | Not Approved | 2024-06-13 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 11 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2440 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2441 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.1 | 131242-WST02-DR-A-1001_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2442 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.1 | 131242-WST02-DR-A-1002_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2443 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.1 | 131242-WST02-DR-A-1003_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2444 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2445 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1006_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 120 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2446 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.1 | 131242-WST02-DR-A-1009_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2447 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.1 | 131242-WST02-DR-A-2000_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2448 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.1 | 131242-WST02-DR-A-2001_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2449 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.1 | 131242-WST02-DR-A-2002_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2450 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.1 | 131242-WST02-DR-A-2003_FSSD_BP-A.1 | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2451 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A | 131242-WST02-DR-A-2007_FSSD_BP-A | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 120 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2452 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A | 131242-WST02-DR-A-3000_FSSD_BP-A | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-3000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 120 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2453 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 5004_FSSD_BP | A | 131242-WST02-DR-A-5004_FSSD_BP-A | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-DR-5004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 120 | NAP | 2024-10-16 | A | 000402 | 2024-10-16 | 03 | 1 | Not Approved | NAP | 2025-03-05 | Overdue | 0 | NAP | NAP
2454 | 000402 | 03 | Aaron | CSA | NA | 131242 | WST02 | CL | A | 0001_FSSD_BP | A | 131242-WST02-CL-A-0001_FSSD_BP-A | 2024-10-16 | SSN_FSSD (BP) Submission | Rev.3: Not Approved. Please refer to comment sheet for resubmission. | 2024-11-06 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-CL-0001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 120 | NAP | 2024-10-16 | A | 000402 | 2024-10-16 | 03 | 1 | Not Approved | NAP | 2025-03-05 | Overdue | 0 | NAP | NAP
2455 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP-A.1 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2456 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2457 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.1 | 131242-WST02-DR-A-1002_FSSD_BP-A.1 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2458 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.2 | 131242-WST02-DR-A-1003_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2459 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP-A.1 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2460 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP-A.1 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1006_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2461 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.2 | 131242-WST02-DR-A-1009_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2462 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.2 | 131242-WST02-DR-A-2000_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2463 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.1 | 131242-WST02-DR-A-2001_FSSD_BP-A.1 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2464 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.2 | 131242-WST02-DR-A-2002_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2465 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.2 | 131242-WST02-DR-A-2003_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2466 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.2 | 131242-WST02-DR-A-2007_FSSD_BP-A.2 | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2467 | 000402 | 04 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A | 131242-WST02-DR-A-3000_FSSD_BP-A | 2025-03-26 | SSN_FSSD (BP) Submission | Not Approved - Revise and resubmit | 2025-04-15 | 2025-05-20 | Not Approved | 2025-06-09 | YES | Resubmitted |  | 131242-WST02-DR-3000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-09 | 55 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2468 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.1 | 131242-WST02-DR-A-1000_FSSD_BP-A.1 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2469 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.3 | 131242-WST02-DR-A-1001_FSSD_BP-A.3 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2470 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.3 | 131242-WST02-DR-A-1002_FSSD_BP-A.3 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2471 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.3 | 131242-WST02-DR-A-1003_FSSD_BP-A.3 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2472 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.1 | 131242-WST02-DR-A-1004_FSSD_BP-A.1 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2473 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.1 | 131242-WST02-DR-A-1006_FSSD_BP-A.1 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1006_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2474 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.2 | 131242-WST02-DR-A-1009_FSSD_BP-A.2 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2475 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.3 | 131242-WST02-DR-A-2000_FSSD_BP-A.3 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2476 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.3 | 131242-WST02-DR-A-2001_FSSD_BP-A.3 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2477 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.2 | 131242-WST02-DR-A-2002_FSSD_BP-A.2 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2478 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.2 | 131242-WST02-DR-A-2003_FSSD_BP-A.2 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2479 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.3 | 131242-WST02-DR-A-2007_FSSD_BP-A.3 | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2480 | 000402 | 05 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | B | 131242-WST02-DR-A-3000_FSSD_BP-B | 2025-08-19 | SSN_FSSD (BP) Submission | Rev.5: Not Approved. Please refer to comments sheet and marked up comments for resubmission. | 2025-09-08 | 2025-10-13 | Not Approved | 2025-10-31 | YES | Resubmitted |  | 131242-WST02-DR-3000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 55 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2481 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.2 | 131242-WST02-DR-A-1000_FSSD_BP-A.2 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2482 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP-A.2 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2483 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP-A.4 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2484 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP-A.4 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2485 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.3 | 131242-WST02-DR-A-1004_FSSD_BP-A.3 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2486 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP-A.2 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1005_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2025-11-07 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-27 | 25 | NAP | 2026-01-07 | A.2 | 000402 | 2025-11-07, 2025-12-03, 2026-01-07 | 06, 07, 08 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2487 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP-A.2 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1006_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2488 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP-A.3 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2489 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.2 | 131242-WST02-DR-A-2000_FSSD_BP-A.2 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2490 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.4 | 131242-WST02-DR-A-2001_FSSD_BP-A.4 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2491 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP-A.4 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2492 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP-A.4 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2493 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP-A.4 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2494 | 000402 | 06 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP-A.2 | 2025-11-07 | SSN_FSSD (BP) Submission | Rev.6: Not Approved. Please refer to comments sheet for resubmission. | 2025-11-27 | 2025-12-02 | Not Approved | 2025-12-22 | YES | Resubmitted |  | 131242-WST02-DR-3000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 25 | NAP | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2495 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-A-1000_FSSD_BP-A.3 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2496 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP-A.2 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2497 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2498 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2499 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.4 | 131242-WST02-DR-A-1004_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2500 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP-A.2 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1005_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2025-11-07 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.2 | 000402 | 2025-11-07, 2025-12-03, 2026-01-07 | 06, 07, 08 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2501 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP-A.2 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1006_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2502 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP-A.3 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2503 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.4 | 131242-WST02-DR-A-2000_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2504 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.5 | 131242-WST02-DR-A-2001_FSSD_BP-A.5 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2505 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2506 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2507 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP-A.4 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2508 | 000402 | 07 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP-A.2 | 2025-12-03 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2025-12-23 | 2026-01-05 | Approved with Comments | 2026-01-23 | YES | Resubmitted |  | 131242-WST02-DR-3000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 33 | AWC | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2509 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1000_FSSD_BP | A.3 | 131242-WST02-DR-A-1000_FSSD_BP-A.3 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2510 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001_FSSD_BP | A.2 | 131242-WST02-DR-A-1001_FSSD_BP-A.2 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.2 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2511 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1002_FSSD_BP | A.4 | 131242-WST02-DR-A-1002_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2512 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1003_FSSD_BP | A.4 | 131242-WST02-DR-A-1003_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2513 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1004_FSSD_BP | A.4 | 131242-WST02-DR-A-1004_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2514 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1005_FSSD_BP | A.2 | 131242-WST02-DR-A-1005_FSSD_BP-A.2 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2025-11-07 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.2 | 000402 | 2025-11-07, 2025-12-03, 2026-01-07 | 06, 07, 08 | 3 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2515 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1006_FSSD_BP | A.2 | 131242-WST02-DR-A-1006_FSSD_BP-A.2 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2516 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1009_FSSD_BP | A.3 | 131242-WST02-DR-A-1009_FSSD_BP-A.3 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.3 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2517 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2000_FSSD_BP | A.4 | 131242-WST02-DR-A-2000_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-05-13 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 02, 03, 04, 05, 06, 07, 08 | 7 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2518 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2001_FSSD_BP | A.5 | 131242-WST02-DR-A-2001_FSSD_BP-A.5 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2001_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.5 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2519 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2002_FSSD_BP | A.4 | 131242-WST02-DR-A-2002_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2002_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2520 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2003_FSSD_BP | A.4 | 131242-WST02-DR-A-2003_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2003_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 03, 04, 05, 06, 07, 08 | 8 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2521 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 2007_FSSD_BP | A.4 | 131242-WST02-DR-A-2007_FSSD_BP-A.4 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2007_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-03-27 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.4 | 000402 | 2024-03-27, 2024-04-19, 2024-05-13, 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 00, 01, 02, 03, 04, 05, 06, 07, 08 | 9 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2522 | 000402 | 08 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 3000_FSSD_BP | A.2 | 131242-WST02-DR-A-3000_FSSD_BP-A.2 | 2026-01-07 | SSN_FSSD (BP) Submission | Rev.7: Approved with comments. Please refer to comments sheet for resubmission. | 2026-01-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3000_FSSD_BP | NA | "SSN_FSSD (BP) Submission " | 2024-10-16 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | A.2 | 000402 | 2024-10-16, 2025-03-26, 2025-08-19, 2025-11-07, 2025-12-03, 2026-01-07 | 03, 04, 05, 06, 07, 08 | 6 | Approved with Comments | AWC | 2026-02-24 |  | 0 | PEN | PEN
2523 | 000403 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | SP | P | 0001 | 0 | 131242-WST02-SP-P-0001-0 | 2024-03-27 | SSN Control Philosophy | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-26 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted | Pending MP resubmission | 131242-WST02-SP-0001 | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 57 | AWC | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2524 | 000403 | 01 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 1 | 131242-WST02-SP-P-0001-1 | 2024-08-12 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-03 | Approved with Comments | 2024-09-23 | YES | Resubmitted |  | 131242-WST02-SP-0001 | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 22 | AWC | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2525 | 000403 | 02 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 2 | 131242-WST02-SP-P-0001-2 | 2024-10-03 | SSN Control Philosophy | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted | Pending MP updates | 131242-WST02-SP-0001 | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 35 | AWC | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2526 | 000403 | 03 | Qili | Process | NA | 131242 | WST02 | SP | P | 0001 | 3 | 131242-WST02-SP-P-0001-3 | 2025-03-14 | SSN Control Philosophy | Approved with Comments | 2025-04-03 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue | Pending MP updates | 131242-WST02-SP-0001 | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 62 | AWC | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2527 | 000404 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0004 | 0 | 131242-WST02-CL-P-0004-0 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-CL-0004 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-11 | 56 | AWC | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2528 | 000404 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 1 | 131242-WST02-CL-P-0004-1 | 2024-07-28 | SSN Chemical Consumption Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-16 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WST02-CL-0004 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 32 | AWC | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2529 | 000404 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0004 | 2 | 131242-WST02-CL-P-0004-2 | 2024-10-16 | SSN Chemical Consumption Calculation | Rev 2: Approved | 2024-11-06 | 2024-11-15 | Approved |  | YES | NA |  | 131242-WST02-CL-0004 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "Heat Load Calculation Report for ACMV" && "SSN Chemical Consumption Calculation" | 2023-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-30 | 30 | APP | 2024-11-11 | 0 | 000244&&000404&&000805 | 2023-12-14, 2024-03-28, 2024-07-28, 2024-10-16, 2024-11-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
2530 | 000405 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0002 | 0 | 131242-WSD11-RT-P-0002-0 | 2024-03-28 | SSN Chemical Consumption Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-04-29 | 2024-05-30 | Approved with Comments | 2024-06-20 | NO | Overdue | After addressing BODR | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 63 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2531 | 000406 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 0 | 131242-WST02-CL-E-0005-0 | 2024-03-28 | SSN 22kV MV Power Cable Sizing Calculations | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-04-29 | 2024-05-23 | Not Approved | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 56 | NAP | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | NAP | NAP
2532 | 000406 | 01 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 1 | 131242-WST02-CL-E-0005-1 | 2024-07-06 | SSN 22kV MV Power Cable Sizing Calculations | Rev 1: Approved with comments. To revise and resubmit. | 2024-07-25 | 2024-07-22 | Approved with Comments | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-20 | 16 | AWC | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
2533 | 000406 | 02 | Freedomer | EICA | NA | 131242 | WST02 | CL | E | 0005 | 2 | 131242-WST02-CL-E-0005-2 | 2025-02-19 | SSN 22kV MV Power Cable Sizing Calculations | Rev 2: Approved. | 2025-03-11 | 2025-05-06 | Approved |  | YES | NA |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-05 | 76 | APP | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | APP | APP
2534 | 000407 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | RT | P | 0001 | 0 | 131242-WST02-RT-P-0001-0 | 2024-03-28 | Basic Design Report of SSN Package | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-05-03 | Not Approved | 2024-05-24 | YES | Resubmitted |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 36 | NAP | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2535 | 000407 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 1 | 131242-WST02-RT-P-0001-1 | 2024-05-23 | Basic Design Report of SSN Package | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-12 | 2024-07-04 | Approved with Comments | 2024-07-24 | YES | Resubmitted | To follow up with MP for resubmission | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-06 | 42 | AWC | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2536 | 000407 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0001 | 2 | 131242-WST02-RT-P-0001-2 | 2024-11-18 | Basic Design Report of SSN Package | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-06 | 2025-01-08 | Approved with Comments | 2025-01-28 | NO | Overdue | comments received on 14 Feb | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-02 | 51 | AWC | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2537 | 000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0015 | 1 | 131242-WST02-DS-M-0015-1 | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DS-0015 | NA | "Datasheet for Dissolved Oxygen Analyser " && "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 32 | NAP | 2025-08-04 | 0 | 000408&&001551 | 2024-03-28, 2024-07-05, 2025-08-04 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2538 | 000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0016 | A | 131242-WST02-DR-M-0016-A | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-0016 | NA | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 32 | NAP | 2024-07-05 | B | 000408 | 2024-03-28, 2024-07-05 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2539 | 000408 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0015 | A | 131242-WST02-DR-M-0015-A | 2024-03-28 | SSN Datasheet & Drawing of Lamella Clarifier | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-29 | Not Approved | 2024-05-20 | YES | Resubmitted |  | 131242-WST02-DR-0015 | NA | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 32 | NAP | 2024-07-05 | B | 000408 | 2024-03-28, 2024-07-05 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2540 | 000408 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0015 | 0 | 131242-WST02-DS-M-0015-0 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue | Pending MP updates | 131242-WST02-DS-0015 | NA | "Datasheet for Dissolved Oxygen Analyser " && "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 55 | AWC | 2025-08-04 | 0 | 000408&&001551 | 2024-03-28, 2024-07-05, 2025-08-04 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2541 | 000408 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0016 | B | 131242-WST02-DR-M-0016-B | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-0016 | NA | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 55 | AWC | 2024-07-05 | B | 000408 | 2024-03-28, 2024-07-05 | 00, 01 | 2 | Approved with Comments | AWC | 2024-09-18 | Overdue | 0 | AWC | AWC
2542 | 000408 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0015 | B | 131242-WST02-DR-M-0015-B | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-0015 | NA | "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 55 | AWC | 2024-07-05 | B | 000408 | 2024-03-28, 2024-07-05 | 00, 01 | 2 | Approved with Comments | AWC | 2024-09-18 | Overdue | 0 | AWC | AWC
2543 | 000408 | 01 | Qili | Process | NA | 131242 | WST02 | CL | M | 0001 | 0 | 131242-WST02-CL-M-0001-0 | 2024-07-05 | SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 55 | AWC | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2544 | 000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0016 | 0 | 131242-WST02-DS-M-0016-0 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | Not Approved | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DS-0016 | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 33 | NAP | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2545 | 000409 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0017 | 0 | 131242-WST02-DR-M-0017-0 | 2024-03-28 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Not approved - Revise and Resubmit | 2024-04-29 | 2024-04-30 | Not Approved | 2024-05-21 | YES | Resubmitted |  | 131242-WST02-DR-0017 | NA | "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 33 | NAP | 2025-03-14 | B | 000409 | 2024-03-28, 2024-07-05, 2025-03-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2546 | 000409 | 01 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 1 | 131242-WST02-DS-M-0016-1 | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted | Pending MP updates | 131242-WST02-DS-0016 | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 55 | AWC | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2547 | 000409 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0017 | B | 131242-WST02-DR-M-0017-B | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WST02-DR-0017 | NA | "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 55 | AWC | 2025-03-14 | B | 000409 | 2024-03-28, 2024-07-05, 2025-03-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2548 | 000409 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0018 | B | 131242-WST02-DR-M-0018-B | 2024-07-05 | SSN Datasheet & Drawing of Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-29 | Approved with Comments | 2024-09-18 | YES | Resubmitted |  | 131242-WST02-DR-0018 | NA | "SSN Datasheet & Drawing of Biomass Separator " | 2024-07-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 55 | AWC | 2025-03-14 | B | 000409 | 2024-07-05, 2025-03-14 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2549 | 000409 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0016 | 2 | 131242-WST02-DS-M-0016-2 | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-DS-0016 | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 122 | AWC | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2550 | 000409 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 0017 | B | 131242-WST02-DR-M-0017-B | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-DR-0017 | NA | "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 122 | AWC | 2025-03-14 | B | 000409 | 2024-03-28, 2024-07-05, 2025-03-14 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
2551 | 000409 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 0018 | B | 131242-WST02-DR-M-0018-B | 2025-03-14 | SSN Datasheet & Drawing of Biomass Separator | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-04-03 | 2025-07-14 | Approved with Comments | 2025-08-01 | NO | Overdue |  | 131242-WST02-DR-0018 | NA | "SSN Datasheet & Drawing of Biomass Separator " | 2024-07-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 122 | AWC | 2025-03-14 | B | 000409 | 2024-07-05, 2025-03-14 | 01, 02 | 2 | Approved with Comments | AWC | 2025-08-01 | Overdue | 0 | AWC | AWC
2552 | 000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A | 131242-WST02-DR-S-1003_ST616-A | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | NO | Overdue | Heng Peng to provide Native DGN sets | 131242-WST02-DR-1003_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 35 | NAP | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
2553 | 000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A | 131242-WST02-DR-S-7001_ST616-A | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | NO | Overdue |  | 131242-WST02-DR-7001_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 35 | NAP | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
2554 | 000410 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A | 131242-WST02-DR-S-8001_ST616-A | 2024-03-28 | ST616_Amendment of ST605 (Main Water Tank Piling Design) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-02 | Not Approved | 2024-05-23 | NO | Overdue |  | 131242-WST02-DR-8001_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 35 | NAP | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
2555 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST609 | A | 131242-WST02-DR-S-1001_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue | Tenwit in Progress | 131242-WST02-DR-1001_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2556 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 2001_ST609 | A | 131242-WST02-DR-S-2001_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue |  | 131242-WST02-DR-2001_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2557 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3001_ST609 | A | 131242-WST02-DR-S-3001_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue |  | 131242-WST02-DR-3001_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2558 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST609 | A | 131242-WST02-DR-S-1002_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue |  | 131242-WST02-DR-1002_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2559 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST609 | A | 131242-WST02-DR-S-1000_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue |  | 131242-WST02-DR-1000_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2560 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 2000_ST609 | A | 131242-WST02-DR-S-2000_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue |  | 131242-WST02-DR-2000_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2561 | 000411 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 3000_ST609 | A | 131242-WST02-DR-S-3000_ST609-A | 2024-03-28 | ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-04-29 | 2024-05-09 | Not Approved | 2024-05-30 | NO | Overdue |  | 131242-WST02-DR-3000_ST609 | NA | "ST609_SSN Pipe Racks Conceptual Design (SSN-PR-01,02,04,05) " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 42 | NAP | 2024-03-28 | A | 000411 | 2024-03-28 | 00 | 1 | Not Approved | NAP | 2024-05-29 | Overdue | 0 | NAP | NAP
2562 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615_BCA | C | 131242-WST02-DR-S-1000_ST615_BCA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue | Heng Peng to provide Native DGN sets and Aaron to address the comments | 131242-WST02-DR-1000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 42 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
2563 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615_BCA | C | 131242-WST02-DR-S-1001_ST615_BCA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-1001_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 42 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
2564 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615_BCA | C | 131242-WST02-DR-S-1002_ST615_BCA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-1002_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 42 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
2565 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615_BCA | C | 131242-WST02-DR-S-5001_ST615_BCA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-5001_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 42 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
2566 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615_BCA | C | 131242-WST02-DR-S-7000_ST615_BCA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-7000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 42 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
2567 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615_BCA | C | 131242-WST02-DR-S-8000_ST615_BCA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-8000_ST615_BCA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " && "ST615 – Amendment of ST604 (BCA Submission for Information) " | 2024-03-05 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 42 | NAP | 2024-04-25 | C | 000340&&000412 | 2024-03-05, 2024-04-02, 2024-04-25 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
2568 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_NOA | C | 131242-WST02-DR-S-A1798-00002-2018-ST615_NOA-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-A1798-00002-2018-ST615_NOA | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 42 | NAP | 2024-04-02 | C | 000412 | 2024-04-02 | 00 | 1 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
2569 | 000412 | 00 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018-ST615_Fdn Advice Letter | C | 131242-WST02-DR-S-A1798-00002-2018-ST615_Fdn Advice Letter-C | 2024-04-02 | ST615 BCA Approved Drawings (Amendment of ST604) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-02 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-A1798-00002-2018-ST615_Fdn Advice Letter | NA | "ST615 BCA Approved Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 42 | NAP | 2024-04-02 | C | 000412 | 2024-04-02 | 00 | 1 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
2570 | 000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-S-1000_ST615-C | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | Not Approved | 2024-05-10 | YES | Resubmitted |  | 131242-WST02-DR-1000_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 17 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2571 | 000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615 | C | 131242-WST02-DR-S-1001_ST615-C | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | Not Approved | 2024-05-10 | YES | Resubmitted |  | 131242-WST02-DR-1001_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 17 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2572 | 000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615 | C | 131242-WST02-DR-S-1002_ST615-C | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | Not Approved | 2024-05-10 | YES | Resubmitted |  | 131242-WST02-DR-1002_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 17 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2573 | 000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615 | C | 131242-WST02-DR-S-5001_ST615-C | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | Not Approved | 2024-05-10 | YES | Resubmitted |  | 131242-WST02-DR-5001_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 17 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2574 | 000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615 | C | 131242-WST02-DR-S-7000_ST615-C | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | Not Approved | 2024-05-10 | YES | Resubmitted |  | 131242-WST02-DR-7000_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 17 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2575 | 000413 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615 | C | 131242-WST02-DR-S-8000_ST615-C | 2024-04-02 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.0: Not Approved. Contractor is requested for resubmission. | 2024-05-02 | 2024-04-19 | Not Approved | 2024-05-10 | YES | Resubmitted |  | 131242-WST02-DR-8000_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 17 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2576 | 000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST615 | C | 131242-WST02-DR-S-1000_ST615-C | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-04 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue | Heng Peng: BIM Pending to clear BIM comments | 131242-WST02-DR-1000_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 20 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2577 | 000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1001_ST615 | C | 131242-WST02-DR-S-1001_ST615-C | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-DR-1001_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 20 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2578 | 000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1002_ST615 | C | 131242-WST02-DR-S-1002_ST615-C | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-DR-1002_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 20 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2579 | 000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST615 | C | 131242-WST02-DR-S-5001_ST615-C | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-DR-5001_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 20 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2580 | 000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST615 | C | 131242-WST02-DR-S-7000_ST615-C | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-DR-7000_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 20 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2581 | 000413 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8000_ST615 | C | 131242-WST02-DR-S-8000_ST615-C | 2024-05-14 | ST615 Issued for Construction Drawings (Amendment of ST604) | Rev.1: Not Approved. Contractor is requested for resubmission. | 2024-06-12 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WST02-DR-8000_ST615 | NA | "ST615 Issued for Construction Drawings (Amendment of ST604) " | 2024-04-02 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-28 | 20 | NAP | 2024-05-14 | C | 000413 | 2024-04-02, 2024-05-14 | 00, 01 | 2 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2582 | 000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1000 | C01 | 131242-WSD11-DR-M-1000-C01 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | Approved with Comments | 2024-06-26 | NO | Overdue | Pending DGN dwg drawing and CAMBI updates and to update Tagging | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 64 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
2583 | 000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1001 | C01 | 131242-WSD11-DR-M-1001-C01 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | Approved with Comments | 2024-06-26 | NO | Overdue |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 64 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | AWC | AWC
2584 | 000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1002 | C01 | 131242-WSD11-DR-M-1002-C01 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | Approved with Comments | 2024-06-26 | NO | Overdue |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 64 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | AWC | AWC
2585 | 000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1003 | C01 | 131242-WSD11-DR-M-1003-C01 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | Approved with Comments | 2024-06-26 | NO | Overdue |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 64 | AWC | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | AWC | AWC
2586 | 000414 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 1004 | C01 | 131242-WSD11-DR-M-1004-C01 | 2024-04-02 | THP GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-02 | 2024-06-05 | Approved with Comments | 2024-06-26 | NO | Overdue |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-16 | 64 | AWC | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | AWC | AWC
2587 | 000415 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0006 | 0 | 131242-WST02-CL-P-0006-0 | 2024-04-03 | SSN Equipment Sizing Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-CL-0006 | NA | "SSN Equipment Sizing Calculation" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-23 | 50 | AWC | 2024-08-12 | 1 | 000415 | 2024-04-03, 2024-08-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2588 | 000415 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0006 | 1 | 131242-WST02-CL-P-0006-1 | 2024-08-12 | SSN Equipment Sizing Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-10-11 | Approved with Comments | 2024-11-01 | YES | Resubmitted |  | 131242-WST02-CL-0006 | NA | "SSN Equipment Sizing Calculation" | 2024-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 60 | AWC | 2024-08-12 | 1 | 000415 | 2024-04-03, 2024-08-12 | 00, 01 | 2 | Approved with Comments | AWC | 2024-10-31 | Overdue | 0 | AWC | AWC
2589 | 000415 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | Comment Reply Sheet 20241118 S415.1 | 1 | 131242-WST02-CL-P-Comment Reply Sheet 20241118 S415.1- | 2024-11-18 | SSN Equipment Sizing Calculation | Rev 2: Approved with Comments. The submittal is requested to be discontinued by CES. | 2024-12-06 | 2025-01-08 | Approved with Comments |  | YES | NA |  | 131242-WST02-CL-Comment Reply Sheet 20241118 S415.1 | NA | "SSN Equipment Sizing Calculation" | 2024-11-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-12-08 | 51 | AWC | 2024-11-18 | 1 | 000415 | 2024-11-18 | 02 | 1 | Approved with Comments | AWC | 2025-01-28 | Overdue | 0 | AWC | AWC
2590 | 000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0005 | 0 | 131242-WST02-CL-P-0005-0 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-17 | 63 | AWC | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
2591 | 000416 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 7010 | 0 | 131242-WST02-DR-P-7010-0 | 2024-04-03 | SSN Process Hydraulic Calculation & Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-03 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-23 | 63 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2592 | 000416 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 1 | 131242-WST02-CL-P-0005-1 | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | Approved with Comments | 2024-11-15 | YES | Resubmitted | Pending MP updates, Need PE endosement | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 65 | AWC | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
2593 | 000416 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 7010 | B | 131242-WST02-DR-P-7010-B | 2024-08-21 | SSN Process Hydraulic Calculation & Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-25 | Approved with Comments | 2024-11-15 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 65 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2594 | 000416 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0005 | 2 | 131242-WST02-CL-P-0005-2 | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-07 | 196 | APP | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP |  |  | 0 | APP | APP
2595 | 000416 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 7010 | C | 131242-WST02-DR-P-7010-C | 2025-03-24 | SSN Process Hydraulic Calculation & Drawing | Rev 2: Approved. Please furnish PE Endorsement. | 2025-04-11 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-07 | 196 | APP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | APP | APP
2596 | 000417 | 00 | Zuo Yu | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 0 | 131242-WSD11-VI-I-0002-0 | 2024-04-04 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-04-18 | Not Approved | 2024-05-09 | YES | Resubmitted |  | 131242-WSD11-VI-0002 | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 14 | NAP | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2597 | 000417 | 01 | Karthik/ Cambi | EICA | NA | 131242 | WSD11 | VI | I | 0002 | 1 | 131242-WSD11-VI-I-0002-1 | 2024-08-15 | Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-04 | 2024-11-08 | Approved with Comments | 2024-11-28 | NO | Overdue |  | 131242-WSD11-VI-0002 | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-29 | 85 | AWC | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2598 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1003 | A | 131242-WST02-DR-B-1003-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 105 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
2599 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1004 | A | 131242-WST02-DR-B-1004-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 105 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
2600 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1005 | A | 131242-WST02-DR-B-1005-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 105 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
2601 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1006 | A | 131242-WST02-DR-B-1006-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 105 | NAP | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | NAP | NAP
2602 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 1007 | A | 131242-WST02-DR-B-1007-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 105 | NAP | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2603 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7001 | A | 131242-WST02-DR-B-7001-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 105 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2604 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7002 | A | 131242-WST02-DR-B-7002-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 105 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2605 | 000418 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | B | 7003 | A | 131242-WST02-DR-B-7003-A | 2024-04-04 | SSN Integrated Security management system and plant CCTV | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-06 | 2024-07-18 | Not Approved | 2024-08-07 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-18 | 105 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2606 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1003 | B | 131242-WST02-DR-B-1003-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | AWC | AWC
2607 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1004 | B | 131242-WST02-DR-B-1004-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
2608 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1005 | B | 131242-WST02-DR-B-1005-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
2609 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1006 | B | 131242-WST02-DR-B-1006-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
2610 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 1007 | B | 131242-WST02-DR-B-1007-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2611 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7001 | B | 131242-WST02-DR-B-7001-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2612 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7002 | B | 131242-WST02-DR-B-7002-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2613 | 000418 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | B | 7003 | B | 131242-WST02-DR-B-7003-B | 2024-10-22 | SSN Integrated Security management system and Plant CCTV | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-12 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 154 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2614 | 000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1011 | A | 131242-WST02-DR-BF-1011-A | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 91 | NAP | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2615 | 000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1012 | A | 131242-WST02-DR-BF-1012-A | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 91 | NAP | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2616 | 000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 1013 | A | 131242-WST02-DR-BF-1013-A | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 91 | NAP | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2617 | 000419 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BF | 7103 | A | 131242-WST02-DR-BF-7103-A | 2024-04-04 | SSN Public Address System | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments | 2024-05-06 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-24 | 91 | NAP | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2618 | 000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1011 | B | 131242-WST02-DR-BF-1011-B | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 11 | AWC | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2619 | 000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1012 | B | 131242-WST02-DR-BF-1012-B | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 11 | AWC | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2620 | 000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 1013 | B | 131242-WST02-DR-BF-1013-B | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 11 | AWC | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2621 | 000419 | 01 | Karthikeyan | EICA | NA | 131242 | WST02 | DR | BF | 7103 | B | 131242-WST02-DR-BF-7103-B | 2024-10-18 | SSN Public Address System | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments | 2024-11-08 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 11 | AWC | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2622 | 000420 | 00 | Suresh | PCM | NA | 131242 | WSW41 | MI | PM | 0010 | 0 | 131242-WSW41-MI-PM-0010-0 | 2024-04-04 | Monthly Progress Meeting Minutes 0010_20240319 | For Information | 2024-05-06 | 2024-04-05 | For Information |  | YES | NA |  | 131242-WSW41-MI-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "CSA Meeting Minutes 0010_20230802" && "Monthly Progress Meeting Minutes 0010_20240319" && "Process & MEICA Meeting Minutes 0010_20230928" | 2023-09-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-18 | 1 | INF | 2024-04-04 | 0 | 000109&&000126&&000152&&000420 | 2023-09-27, 2023-10-12, 2023-10-30, 2024-04-04 | 00 | 4 | For Information | INF | 2024-04-25 | Overdue | 0 | INF | INF
2623 | 000421 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 0 | 131242-WSD11-DS-M-0013-0 | 2024-04-05 | Data Sheet and Drawing of THP Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | Approved with Comments | 2024-07-04 | YES | Resubmitted |  | 131242-WSD11-DS-0013 | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "THP Pump Motor Data Sheet" | 2024-04-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-25 | 69 | AWC | 2026-01-15 | A | 000421&&000634&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
2624 | 000421 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 1 | 131242-WSD11-DS-M-0013-1 | 2024-08-12 | Data Sheet of THP Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WSD11-DS-0013 | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "THP Pump Motor Data Sheet" | 2024-04-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 29 | AWC | 2026-01-15 | A | 000421&&000634&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
2625 | 000421 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0013 | 2 | 131242-WSD11-DS-M-0013-2 | 2025-01-26 | Data Sheet of THP Feed Pump | Rev 2: Approved | 2025-02-13 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DS-0013 | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "THP Pump Motor Data Sheet" | 2024-04-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-09 | 91 | APP | 2026-01-15 | A | 000421&&000634&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
2626 | 000422 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 0 | 131242-WSD11-DS-M-0014-0 | 2024-04-06 | Data Sheet and Drawing of Reactor Feed Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-07 | 2024-06-13 | Approved with Comments | 2024-07-04 | YES | Resubmitted |  | 131242-WSD11-DS-0014 | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-26 | 68 | AWC | 2026-01-20 | 0 | 000422&&000634&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2627 | 000422 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 1 | 131242-WSD11-DS-M-0014-1 | 2024-08-12 | Data Sheet and Drawing of Reactor Feed Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WSD11-DS-0014 | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 29 | AWC | 2026-01-20 | 0 | 000422&&000634&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2628 | 000422 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0014 | 2 | 131242-WSD11-DS-M-0014-2 | 2025-04-10 | Data Sheet and Drawing of Reactor Feed Pump | Rev 2: Approved | 2025-04-30 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0014 | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-24 | 179 | APP | 2026-01-20 | 0 | 000422&&000634&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
2629 | 000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 0001 | A | 131242-WSD11-DR-S-0001-A | 2024-04-06 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSD11-DR-0001 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-26 | 26 | NAP | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | For Information | INF |  |  | 0 | NAP | NAP
2630 | 000423 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0004 | 0 | 131242-WSD11-CL-S-0004-0 | 2024-04-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-07 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSD11-CL-0004 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "THP Feed Pump Pressure Loss Calculation" | 2024-04-05 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-25 | 27 | NAP | 2024-08-15 | 0 | 000423&&000649 | 2024-04-05, 2024-06-05, 2024-08-15 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2631 | 000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301 | A | 131242-WSD11-DR-S-5301-A | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-06-26 | 2024-06-19 | Approved |  | YES | NA |  | 131242-WSD11-DR-5301 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-25 | 14 | APP | 2024-06-26 | B | 000423&&000536 | 2024-06-05, 2024-06-26 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
2632 | 000423 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0004 | 1 | 131242-WSD11-CL-S-0004-1 | 2024-06-05 | Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.1: Approved. Please ensure SS bolt is used. | 2024-07-04 | 2024-06-19 | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-CL-0004 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "THP Feed Pump Pressure Loss Calculation" | 2024-04-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-19 | 14 | PEN | 2024-08-15 | 0 | 000423&&000649 | 2024-04-05, 2024-06-05, 2024-08-15 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
2633 | 000424 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0037 | 0 | 131242-WSW41-CD-IM-0037-0 | 2024-04-08 | Submission Of BIM Coordination VCM Model (Mar-2024) | For Information | 2024-05-08 | 2024-04-19 | For Information |  | YES | NA |  | 131242-WSW41-CD-0037 | NA | "Submission Of BIM Coordination VCM Model (Mar-2024)" | 2024-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-04-28 | 11 | INF | 2024-04-08 | 0 | 000424 | 2024-04-08 | 00 | 1 | For Information | INF | 2024-05-09 | Overdue | 0 | INF | INF
2634 | 000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-S-1003_ST616_BCA-A2 | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Not Approved | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-1003_ST616_BCA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-28 | 9 | NAP | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2635 | 000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | A2 | 131242-WST02-DR-S-7001_ST616_BCA-A2 | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Not Approved | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-7001_ST616_BCA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-28 | 9 | NAP | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2636 | 000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | A2 | 131242-WST02-DR-S-8001_ST616_BCA-A2 | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Not Approved | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-8001_ST616_BCA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-28 | 9 | NAP | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2637 | 000425 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | A.1 |  | 2024-04-08 | ST616_Amendment of ST605 (BCA Approved Drawings) | Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Not Approved | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-A1798-00002-2018_NOA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-28 | 9 | NAP | 2024-04-18 | A.1 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2638 | 000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616_BCA | A2 | 131242-WST02-DR-S-1003_ST616_BCA-A2 | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue | Heng Peng to provide Native DGN sets and Aaron to address the comments | 131242-WST02-DR-1003_ST616_BCA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 26 | NAP | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
2639 | 000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616_BCA | A2 | 131242-WST02-DR-S-7001_ST616_BCA-A2 | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-7001_ST616_BCA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 26 | NAP | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
2640 | 000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616_BCA | A2 | 131242-WST02-DR-S-8001_ST616_BCA-A2 | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-8001_ST616_BCA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 26 | NAP | 2024-04-18 | A2 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
2641 | 000425 | 01 | Aaron/HP | CSA | NA | 131242 | WST02 | DR | S | A1798-00002-2018_NOA | A.1 |  | 2024-04-18 | ST616_Amendment of ST605 (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-17 | 2024-05-14 | Not Approved | 2024-06-04 | NO | Overdue |  | 131242-WST02-DR-A1798-00002-2018_NOA | NA | "ST616_Amendment of ST605 (BCA Approved Drawings) " | 2024-04-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 26 | NAP | 2024-04-18 | A.1 | 000425 | 2024-04-08, 2024-04-18 | 00, 01 | 2 | Not Approved | NAP | 2024-06-03 | Overdue | 0 | NAP | NAP
2642 | 000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A2 | 131242-WST02-DR-S-1003_ST616-A2 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Approved with Comments | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-1003_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 9 | AWC | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF |  |  | 0 | AWC | AWC
2643 | 000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A2 | 131242-WST02-DR-S-7001_ST616-A2 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Approved with Comments | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-7001_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 9 | AWC | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF |  |  | 0 | AWC | AWC
2644 | 000426 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A2 | 131242-WST02-DR-S-8001_ST616-A2 | 2024-04-08 | ST616 _Amendment of ST605 (IFC Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-17 | Approved with Comments | 2024-05-08 | YES | Resubmitted |  | 131242-WST02-DR-8001_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-22 | 9 | AWC | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF |  |  | 0 | AWC | AWC
2645 | 000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST616 | A.2 | 131242-WST02-DR-S-1003_ST616-A.2 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-17 | 2024-05-14 | For Information |  | YES | NA |  | 131242-WST02-DR-1003_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-10 | 18 | INF | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF | 2024-06-03 | Overdue | 0 | INF | INF
2646 | 000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST616 | A.2 | 131242-WST02-DR-S-7001_ST616-A.2 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-28 | 2024-05-14 | For Information |  | YES | NA |  | 131242-WST02-DR-7001_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-10 | 18 | INF | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF | 2024-06-03 | Overdue | 0 | INF | INF
2647 | 000426 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8001_ST616 | A.2 | 131242-WST02-DR-S-8001_ST616-A.2 | 2024-04-26 | ST616 _Amendment of ST605 (IFC Drawings) | For Information | 2024-05-28 | 2024-05-14 | For Information |  | YES | NA |  | 131242-WST02-DR-8001_ST616 | NA | "ST616 _Amendment of ST605 (IFC Drawings) " && "ST616_Amendment of ST605 (Main Water Tank Piling Design)" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-10 | 18 | INF | 2024-04-26 | A.2 | 000410&&000426 | 2024-03-28, 2024-04-08, 2024-04-26 | 00, 01 | 3 | For Information | INF | 2024-06-03 | Overdue | 0 | INF | INF
2648 | 000427 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 0 | 131242-WSW41-CL-S-0004-0 | 2024-04-08 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-08 | 2024-04-22 | Not Approved | 2024-05-13 | YES | Resubmitted |  | 131242-WSW41-CL-0004 | NA | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | 2024-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-28 | 14 | NAP | 2024-04-23 | 1 | 000427 | 2024-04-08, 2024-04-23 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
2649 | 000427 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0004 | 1 | 131242-WSW41-CL-S-0004-1 | 2024-04-23 | Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115) | Rev.1: Approved | 2024-05-14 | 2024-05-02 | Approved |  | YES | NA |  | 131242-WSW41-CL-0004 | NA | "Proposed for WLT for 600mm Dia. WLT1 @Zone 1 (TP115)" | 2024-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-07 | 9 | APP | 2024-04-23 | 1 | 000427 | 2024-04-08, 2024-04-23 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2650 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608 | 0 | 131242-WST02-CL-S-0002_ST608-0 | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-CL-0002_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | 0 | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2651 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1005_ST608 | A | 131242-WST02-DR-S-1005_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1005_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2652 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1001_ST608 | A | 131242-WST02-DR-S-1001_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1001_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2653 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1002_ST608 | A | 131242-WST02-DR-S-1002_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1002_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2654 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2000_ST608 | A | 131242-WST02-DR-S-2000_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2000_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2655 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST608 | A | 131242-WST02-DR-S-3000_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2656 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1003_ST608 | A | 131242-WST02-DR-S-1003_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1003_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2657 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2001_ST608 | A | 131242-WST02-DR-S-2001_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2001_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2658 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3001_ST608 | A | 131242-WST02-DR-S-3001_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-3001_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2659 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1004_ST608 | A | 131242-WST02-DR-S-1004_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-1004_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2660 | 000428 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2002_ST608 | A | 131242-WST02-DR-S-2002_ST608-A | 2024-04-09 | ST608 - SSN-Shelters (Conceptual Design Submission) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-09 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WST02-DR-2002_ST608 | NA | "ST608 - SSN-Shelters (Conceptual Design Submission) " | 2024-04-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 23 | NAP | 2024-04-09 | A | 000428 | 2024-04-09 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2661 | 000428 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608 | B | 131242-WST00-DR-S-8005_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-10 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST00-DR-8005_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2662 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608 | B | 131242-WST02-DR-S-0302_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-0302_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2663 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608 | B | 131242-WST02-DR-S-1200_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-1200_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2664 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608 | B | 131242-WST02-DR-S-1201_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-1201_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2665 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608 | B | 131242-WST02-DR-S-1202_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-1202_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2666 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608 | B | 131242-WST02-DR-S-1203_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-1203_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2667 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608 | B | 131242-WST02-DR-S-1204_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-1204_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2668 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608 | B | 131242-WST02-DR-S-1205_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-1205_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2669 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608 | B | 131242-WST02-DR-S-2200_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-2200_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2670 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608 | B | 131242-WST02-DR-S-2201_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-2201_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2671 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608 | B | 131242-WST02-DR-S-2202_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-2202_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2672 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608 | B | 131242-WST02-DR-S-2203_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-2203_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2673 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608 | B | 131242-WST02-DR-S-3200_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-3200_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2674 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608 | B | 131242-WST02-DR-S-3201_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-3201_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2675 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608 | B | 131242-WST02-DR-S-3202_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-3202_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2676 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608 | B | 131242-WST02-DR-S-5200_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5200_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2677 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608 | B | 131242-WST02-DR-S-5201_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5201_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2678 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608 | B | 131242-WST02-DR-S-5202_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5202_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2679 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608 | B | 131242-WST02-DR-S-5203_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5203_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2680 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608 | B | 131242-WST02-DR-S-5204_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5204_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2681 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608 | B | 131242-WST02-DR-S-5205_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5205_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2682 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608 | B | 131242-WST02-DR-S-5206_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5206_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2683 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608 | B | 131242-WST02-DR-S-5207_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5207_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2684 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608 | B | 131242-WST02-DR-S-5208_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5208_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2685 | 000428 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608 | B | 131242-WST02-DR-S-5209_ST608-B | 2024-09-20 | ST608 – SSN Shelters Details | Rev.1: Not Approved. Please refer to comment sheet for resubmission | 2024-10-18 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WST02-DR-5209_ST608 | NA | "ST608 – SSN Shelters Details" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 13 | NAP | 2024-09-20 | B | 000428 | 2024-09-20 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
2686 | 000428 | 02 | Aaron | CSA | NA | 131242 | WST02 | NA | C | 9999 | CES REPLY SHEET S428 | 131242-WST02--C--CES REPLY SHEET S428 | 2024-10-22 | ST608 – SSN Shelters Details | Rev.2: Not Approved. No updated drawings were submitted. | 2024-11-12 | 2024-12-18 | Not Approved | 2025-01-08 | NO | Overdue |  | 131242-WST02-NA-9999 | NA | "ST608 – SSN Shelters Details" | 2024-10-22 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-11 | 57 | NAP | 2024-10-22 | CES REPLY SHEET S428 | 000428 | 2024-10-22 | 02 | 1 | Not Approved | NAP | 2025-01-07 | Overdue | 0 | NAP | NAP
2687 | 000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A | 131242-WST02-DR-M-1022-A | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 57 | AWC | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2688 | 000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1023 | A | 131242-WST02-DR-M-1023-A | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 57 | AWC | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
2689 | 000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-M-1024-A | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 57 | AWC | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
2690 | 000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1025 | A | 131242-WST02-DR-M-1025-A | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 57 | AWC | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
2691 | 000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1026 | A | 131242-WST02-DR-M-1026-A | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 57 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | AWC | AWC
2692 | 000429 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1027 | A | 131242-WST02-DR-M-1027-A | 2024-04-09 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-09 | 2024-06-05 | Approved with Comments | 2024-06-26 | YES | Resubmitted |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-29 | 57 | AWC | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2693 | 000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1022 | A.1 | 131242-WST02-DR-M-1022-A.1 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue | Shall update and submit under as built drawing | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 50 | AWC | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2694 | 000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5011 | A.1 | 131242-WST02-DR-M-5011-A.1 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-5011 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 50 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2695 | 000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5012 | A.1 | 131242-WST02-DR-M-5012-A.1 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-5012 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 50 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2696 | 000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5013 | A.1 | 131242-WST02-DR-M-5013-A.1 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-5013 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 50 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2697 | 000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5014 | A.1 | 131242-WST02-DR-M-5014-A.1 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-5014 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 50 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2698 | 000429 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5015 | A.1 | 131242-WST02-DR-M-5015-A.1 | 2024-07-10 | Piping General Arrangement-UG & Plant Drain Manholes | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-30 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WST02-DR-5015 | NA | "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 50 | AWC | 2024-10-05 | A.1 | 000161&&000429 | 2024-07-10, 2024-10-05 | 01, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2699 | 000430 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 0 | 131242-WSW41-SH-M-1002-0 | 2024-04-11 | Piping Special Item List | Rev 0: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-05-10 | 2024-06-13 | For Information | 2024-07-04 | YES | Resubmitted |  | 131242-WSW41-SH-1002 | NA | "Piping Special Item List" | 2024-04-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-01 | 63 | INF | 2024-08-01 | 1 | 000430 | 2024-04-11, 2024-08-01 | 00, 01 | 2 | For Information | INF |  |  | 0 | INF | INF
2700 | 000430 | 01 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1002 | 1 | 131242-WSW41-SH-M-1002-1 | 2024-08-01 | Piping Special Item List | Rev 1: For Information. To revise and resubmit. Refer to attached file for comments. | 2024-08-22 | 2024-09-02 | For Information | 2024-09-20 | NO | Overdue | Piping Special Item List is "For Information", will update after design is freezed. | 131242-WSW41-SH-1002 | NA | "Piping Special Item List" | 2024-04-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-15 | 32 | INF | 2024-08-01 | 1 | 000430 | 2024-04-11, 2024-08-01 | 00, 01 | 2 | For Information | INF | 2024-09-20 | Overdue | 0 | INF | INF
2701 | 000431 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0028 | 0 | 131242-WSW41-LT-PM-0028-0 | 2024-04-12 | CV OF TEAM MEMBER (WSHO) | Not Approved. The proposed candidate doesn’t fully meet the requirement of 5 years’ experience as WSHO. Therefore, proposed candidate is disapproved. | 2024-05-13 | 2024-06-06 | Not Approved | 2024-06-27 | NO | Overdue |  | 131242-WSW41-LT-0028 | NA | "CV OF TEAM MEMBER (WSHO)" | 2024-04-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 55 | NAP | 2024-04-12 | 0 | 000431 | 2024-04-12 | 00 | 1 | Not Approved | NAP | 2024-06-26 | Overdue | 0 | NAP | NAP
2702 | 000432 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0002 | 0 | 131242-WSD11-BQ-P-0002-0 | 2024-04-12 | THP Valve List | Rev 0: For Information | 2024-05-13 | 2024-07-26 | For Information |  | YES | NA |  | 131242-WSD11-BQ-0002 | NA | "THP Valve List" | 2024-04-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-05-02 | 105 | INF | 2024-04-12 | 0 | 000432 | 2024-04-12 | 00 | 1 | For Information | INF | 2024-08-15 | Overdue | 0 | INF | INF
2703 | 000433 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0007 | 0 | 131242-WSW41-SP-C-0007-0 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 | Not Approved | 2024-05-23 | NO | Overdue |  | 131242-WSW41-SP-0007 | NA | "Concrete Design Mix for SSN Water Tanks G40 & G45 (PanUnited)" && "Monthly Raw Material Test Reports for Concrete (PanUnited)-Feb 2024" | 2024-03-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-26 | 20 | NAP | 2024-06-20 | 1 | 000380&&000433 | 2024-03-20, 2024-04-12, 2024-06-20 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2704 | 000434 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0008 | 0 | 131242-WSW41-SP-C-0008-0 | 2024-04-12 | Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-13 | 2024-05-02 | Not Approved | 2024-05-23 | NO | Overdue |  | 131242-WSW41-SP-0008 | NA | "Monthly Raw Material Test Reports for Concrete (PanUnited)-Mar 2024" | 2024-04-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 20 | NAP | 2024-04-12 | 0 | 000434 | 2024-04-12 | 00 | 1 | Not Approved | NAP | 2024-05-22 | Overdue | 0 | NAP | NAP
2705 | 000435 | 00 | Chan | PMT | NA | 131242 | WSW41 | LT | PM | 0026 | 0 | 131242-WSW41-LT-PM-0026-0 | 2024-04-13 | Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project) | For Information | 2024-05-13 | 2024-05-10 | For Information |  | YES | NA |  | 131242-WSW41-LT-0026 | NA | "Letter of Undertaking for Application for Soil Dumping at TTP2 (Tuas Three Finger Project)" | 2024-04-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-05-03 | 27 | INF | 2024-04-13 | 0 | 000435 | 2024-04-13 | 00 | 1 | For Information | INF | 2024-05-30 | Overdue | 0 | INF | INF
2706 | 000436 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 0 | 131242-WST02-VI-I-0008-0 | 2024-04-15 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-14 | 2024-05-23 | Approved with Comments | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-VI-0008 | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-05 | 38 | AWC | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2707 | 000436 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0008 | 1 | 131242-WST02-VI-I-0008-1 | 2024-11-28 | Vendor Approval of SSN Package (TSS Analyser - Optical) | Rev 1: Approved with comments. No need resubmission. Refer attached file for comments. | 2024-12-18 | 2025-03-25 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0008 | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-12 | 117 | AWC | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2708 | 000437 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | A.1 | 131242-WSW41-RT-PM-11-A.1 | 2024-04-16 | C4B Monthly Progress Report Number No.11 (03 24) | Rejected as per CES request | 2024-05-15 | 2024-04-17 | Rejected | 2024-05-08 | YES | Resubmitted |  | 131242-WSW41-RT-0011 | NA | "C4B Monthly Progress Report Number No.11 (03 24)" && "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-06 | 1 | REJ | 2024-10-28 | 0 | 000437&&000787 | 2024-04-16, 2024-04-18, 2024-06-11, 2024-10-28 | 00, 01, 02 | 4 | For Information | INF |  |  | 0 | REJ | REJ
2709 | 000437 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | 0 | 131242-WSW41-RT-PM-11-0 | 2024-04-18 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-05-09 | 2024-05-13 | Approved with Comments | 2024-06-03 | YES | Resubmitted |  | 131242-WSW41-RT-0011 | NA | "C4B Monthly Progress Report Number No.11 (03 24)" && "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-02 | 25 | AWC | 2024-10-28 | 0 | 000437&&000787 | 2024-04-16, 2024-04-18, 2024-06-11, 2024-10-28 | 00, 01, 02 | 4 | For Information | INF |  |  | 0 | AWC | AWC
2710 | 000437 | 02 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0011 | 1 | 131242-WSW41-RT-PM-11-1 | 2024-06-11 | C4B Monthly Progress Report Number No.11 (03 24) | Rev. 2 - Approved | 2024-07-02 | 2024-06-18 | Approved |  | YES | NA |  | 131242-WSW41-RT-0011 | NA | "C4B Monthly Progress Report Number No.11 (03 24)" && "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-25 | 7 | APP | 2024-10-28 | 0 | 000437&&000787 | 2024-04-16, 2024-04-18, 2024-06-11, 2024-10-28 | 00, 01, 02 | 4 | For Information | INF |  |  | 0 | APP | APP
2711 | 000438 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 0 | 131242-WST02-VI-I-0007-0 | 2024-04-16 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-05-23 | Not Approved | 2024-06-12 | YES | Resubmitted |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-06 | 37 | NAP | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2712 | 000438 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 1 | 131242-WST02-VI-I-0007-1 | 2024-07-28 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-16 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 52 | NAP | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2713 | 000438 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 2 | 131242-WST02-VI-I-0007-2 | 2024-10-18 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-08 | 2024-12-03 | Approved with Comments | 2024-12-23 | YES | Resubmitted |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 46 | AWC | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2714 | 000438 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0007 | 3 | 131242-WST02-VI-I-0007-3 | 2025-02-27 | Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-03-19 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-13 | 68 | AWC | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2715 | 000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | A | 131242-WST02-DR-E-3150-A | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | Not Approved | 2024-06-10 | YES | Resubmitted |  | 131242-WST02-DR-3150 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-06 | 34 | NAP | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2716 | 000439 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | A | 131242-WST02-DR-E-3151-A | 2024-04-16 | SSN Transformer Outline Drawing | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-05-15 | 2024-05-20 | Not Approved | 2024-06-10 | YES | Resubmitted |  | 131242-WST02-DR-3151 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-06 | 34 | NAP | 2024-12-11 | D | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2717 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | C | 131242-WST02-DR-E-3150-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3150 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 60 | AWC | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2718 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | B | 131242-WST02-DR-E-3151-B | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3151 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 60 | AWC | 2024-12-11 | D | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2719 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3152 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | C | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2720 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | C | 131242-WST02-DR-E-3153-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3153 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2721 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | C | 131242-WST02-DR-E-3154-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3154 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2722 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | C | 131242-WST02-DR-E-3155-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3155 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2723 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | B | 131242-WST02-DR-E-3156-B | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3156 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2724 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3157 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | C | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2725 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | C | 131242-WST02-DR-E-3158-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3158 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2726 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | C | 131242-WST02-DR-E-3159-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-3159 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 60 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2727 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | C | 131242-WST02-DR-E-7010-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 60 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2728 | 000439 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | C | 131242-WST02-DR-E-7011-C | 2024-07-12 | SSN Transformer Outline Drawing | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-01 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 60 | AWC | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2729 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | D | 131242-WST02-DR-E-3150-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3150 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2730 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | D | 131242-WST02-DR-E-3151-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3151 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | D | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2731 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152-C | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3152 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | C | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2732 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | D | 131242-WST02-DR-E-3153-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3153 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2733 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | D | 131242-WST02-DR-E-3154-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3154 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2734 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | D | 131242-WST02-DR-E-3155-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3155 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2735 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | D | 131242-WST02-DR-E-3156-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3156 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2736 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157-C | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3157 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | C | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2737 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | D | 131242-WST02-DR-E-3158-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3158 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2738 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | D | 131242-WST02-DR-E-3159-D | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-3159 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2739 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | E | 131242-WST02-DR-E-7010-E | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2740 | 000439 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | E | 131242-WST02-DR-E-7011-E | 2024-10-16 | SSN Transformer Outline Drawing | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-06 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 22 | AWC | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2741 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3150 | E | 131242-WST02-DR-E-3150-E | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3150 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | E | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2742 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3151 | D | 131242-WST02-DR-E-3151-D | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3151 | NA | "SSN Transformer Outline Drawing" | 2024-04-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | D | 000439 | 2024-04-16, 2024-07-12, 2024-10-16, 2024-12-11 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2743 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3152 | C | 131242-WST02-DR-E-3152-C | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3152 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | C | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2744 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3153 | D | 131242-WST02-DR-E-3153-D | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3153 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2745 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3154 | E | 131242-WST02-DR-E-3154-E | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3154 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2746 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3155 | E | 131242-WST02-DR-E-3155-E | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3155 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2747 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3156 | D | 131242-WST02-DR-E-3156-D | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3156 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2748 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3157 | C | 131242-WST02-DR-E-3157-C | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3157 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | C | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2749 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3158 | D | 131242-WST02-DR-E-3158-D | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3158 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | D | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2750 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 3159 | E | 131242-WST02-DR-E-3159-E | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-3159 | NA | "SSN Transformer Outline Drawing" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2024-12-11 | E | 000439 | 2024-07-12, 2024-10-16, 2024-12-11 | 01, 02, 03 | 3 | Approved with Comments | AWC | 2025-03-05 | Overdue | 0 | AWC | AWC
2751 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | F | 131242-WST02-DR-E-7010-F | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2752 | 000439 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7011 | F | 131242-WST02-DR-E-7011-F | 2024-12-11 | SSN Transformer Outline Drawing | Rev 3: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-01-01 | 2025-02-13 | Approved with Comments | 2025-03-05 | NO | Overdue |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-25 | 64 | AWC | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2753 | 000440 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | E | 7010 | 0 | 131242-WST02-DR-E-7010-0 | 2024-04-16 | SSN Transformer Marshalling Box Schematic Wiring Diagram | Rev 0: Rejected. Not required to resubmit. Please refer to attached comments sheet. | 2024-05-15 | 2024-05-20 | Rejected |  | YES | NA |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-04-30 | 34 | REJ | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
2754 | 000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7005 | A | 131242-WST02-DR-I-7005-A | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-30 | 79 | NAP | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2755 | 000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7006 | A | 131242-WST02-DR-I-7006-A | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-30 | 79 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | NAP | NAP
2756 | 000441 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | DR | I | 7007 | A | 131242-WST02-DR-I-7007-A | 2024-04-16 | SSN sample AC/DC/IO circuit diagram | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-05-15 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-04-30 | 79 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | NAP | NAP
2757 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7007 | B | 131242-WST02-DR-I-7007-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue | Pending from MP | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 58 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | NAP | NAP
2758 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7008 | B | 131242-WST02-DR-I-7008-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 58 | NAP | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | NAP | NAP
2759 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7009 | B | 131242-WST02-DR-I-7009-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue |  | 131242-WST02-DR-7009 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 58 | NAP | 2025-05-04 | D | 000441&&000604&&000605 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
2760 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7010 | B | 131242-WST02-DR-I-7010-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 58 | NAP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2761 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7011 | B | 131242-WST02-DR-I-7011-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 58 | NAP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2762 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7012 | B | 131242-WST02-DR-I-7012-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue |  | 131242-WST02-DR-7012 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 58 | NAP | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2763 | 000441 | 01 | Low | EICA | NA | 131242 | WST02 | DR | I | 7013 | B | 131242-WST02-DR-I-7013-B | 2024-08-20 | SSN IO Sample Schematic Drawing | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-09 | 2024-10-17 | Not Approved | 2024-11-07 | NO | Overdue |  | 131242-WST02-DR-7013 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 58 | NAP | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2764 | 000442 | 00 | Heng Peng/ Muthu | BIM | NA | 131242 | WSW41 | CD | IM | 0038 | 0 | 131242-WSW41-CD-IM-0038-0 | 2024-04-17 | Milestone 1.2 - SSN Overall Changes | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-05-16 | 2024-07-05 | Approved with Comments | 2024-07-25 | NO | Overdue |  | 131242-WSW41-CD-0038 | NA | "Milestone 1.2 - SSN Overall Changes" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-07 | 79 | AWC | 2024-04-17 | 0 | 000442 | 2024-04-17 | 00 | 1 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
2765 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-S-0001_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-0001_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2766 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | A | 131242-WST02-DR-S-0002_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-0002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2767 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | A | 131242-WST02-DR-S-0003_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-0003_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2768 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | A | 131242-WST02-DR-S-1006_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-1006_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2769 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | A | 131242-WST02-DR-S-1007_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-1007_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2770 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | A | 131242-WST02-DR-S-1008_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-1008_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2771 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | A | 131242-WST02-DR-S-3000_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-3000_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2772 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | A | 131242-WST02-DR-S-5001_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-5001_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2773 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | A | 131242-WST02-DR-S-5002_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-5002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2774 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | A | 131242-WST02-DR-S-7000_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-7000_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2775 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | A | 131242-WST02-DR-S-7001_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-7001_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2776 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | A | 131242-WST02-DR-S-7002_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-7002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2777 | 000443 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-S-8002_ST606_BCA-A | 2024-04-17 | ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission) | For Information | 2024-05-16 | 2024-05-13 | For Information |  | YES | NA |  | 131242-WST02-DR-8002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-05-07 | 26 | INF | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
2778 | 000444 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0009 | 0 | 131242-WSW41-SP-C-0009-0 | 2024-04-17 | Reinforcement Bar delivery & Testing Summary -February 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-16 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-SP-0009 | NA | "Reinforcement Bar delivery & Testing Summary -February 2024" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-07 | 15 | AWC | 2024-04-17 | 0 | 000444 | 2024-04-17 | 00 | 1 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
2779 | 000445 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | SH | M | 0001 | 0 | 131242-WSW41-SH-M-0001-0 | 2024-04-17 | Sidewide Piperack Line List | Rev 0: Not approved - Revise and Resubmit | 2024-05-16 | 2024-07-26 | Not Approved | 2024-08-16 | NO | Overdue |  | 131242-WSW41-SH-0001 | NA | "Line List for Hydrotest (Sitewide PipeRack)" && "Sidewide Piperack Line List" | 2024-04-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-07 | 100 | NAP | 2025-10-16 | 0 | 000445&&001749 | 2024-04-17, 2025-10-16 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2780 | 000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1000 | 0 | 131242-WSD11-DR-S-1000-0 | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | Not Approved | 2024-06-03 | YES | Resubmitted |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 24 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | NAP | NAP
2781 | 000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1001 | A | 131242-WSD11-DR-S-1001-A | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | Not Approved | 2024-06-03 | YES | Resubmitted |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-03 | 24 | NAP | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP |  |  | 0 | NAP | NAP
2782 | 000446 | 00 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | A | 131242-WSD11-CL-S-0005-A | 2024-04-19 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-20 | 2024-05-13 | Not Approved | 2024-06-03 | YES | Resubmitted |  | 131242-WSD11-CL-0005 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 24 | NAP | 2024-11-22 | 0 | 000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
2783 | 000446 | 01 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 1 | 131242-WSD11-CL-S-0005-1 | 2024-05-31 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-10 | Not Approved | 2024-07-01 | YES | Resubmitted |  | 131242-WSD11-CL-0005 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-14 | 10 | NAP | 2024-11-22 | 0 | 000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
2784 | 000446 | 02 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 5 | 131242-WSD11-CL-S-0005-5 | 2024-07-16 | THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.2: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-05 | 2024-08-16 | Not Approved | 2024-09-05 | YES | Resubmitted |  | 131242-WSD11-CL-0005 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 31 | NAP | 2024-11-22 | 0 | 000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
2785 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | CL | S | 0005 | 7 | 131242-WSD11-CL-S-0005-7 | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-CL-0005 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "Design Calculation for Overall Load on the Raft Slab and Localized Punching Shear Check" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-04-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 25 | AWC | 2024-11-22 | 0 | 000446&&000837 | 2024-04-19, 2024-05-31, 2024-07-16, 2024-08-28, 2024-11-22 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | AWC | AWC
2786 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1400 | A | 131242-WSD11-DR-S-1400-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-1400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2787 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1401 | A | 131242-WSD11-DR-S-1401-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-1401 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2788 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1402 | A | 131242-WSD11-DR-S-1402-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-1402 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2789 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 1403 | A | 131242-WSD11-DR-S-1403-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-1403 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2790 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2400 | A | 131242-WSD11-DR-S-2400-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-2400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2024-10-07 | B | 000446 | 2024-08-28, 2024-10-07 | 03, 04 | 2 | Approved | APP |  |  | 0 | AWC | AWC
2791 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5400 | A | 131242-WSD11-DR-S-5400-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-5400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2024-10-07 | B | 000446 | 2024-08-28, 2024-10-07 | 03, 04 | 2 | Approved | APP |  |  | 0 | AWC | AWC
2792 | 000446 | 03 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 8003 | A | 131242-WSD11-DR-S-8003-A | 2024-08-28 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-17 | 2024-09-22 | Approved with Comments | 2024-10-10 | YES | Resubmitted |  | 131242-WSD11-DR-8003 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 25 | AWC | 2024-08-28 | A | 000446 | 2024-08-28 | 03 | 1 | Approved with Comments | AWC | 2024-10-10 | Overdue | 0 | AWC | AWC
2793 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1400 | B | 131242-WSD11-DR-S-1400-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSD11-DR-1400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 22 | APP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
2794 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1401 | B | 131242-WSD11-DR-S-1401-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSD11-DR-1401 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 22 | APP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
2795 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1402 | B | 131242-WSD11-DR-S-1402-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSD11-DR-1402 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 22 | APP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
2796 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 1403 | B | 131242-WSD11-DR-S-1403-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSD11-DR-1403 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 22 | APP | 2025-08-13 | B | 000446&&001382 | 2024-08-28, 2024-10-07, 2025-06-16, 2025-08-13 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
2797 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 2400 | B | 131242-WSD11-DR-S-2400-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSD11-DR-2400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 22 | APP | 2024-10-07 | B | 000446 | 2024-08-28, 2024-10-07 | 03, 04 | 2 | Approved | APP |  |  | 0 | APP | APP
2798 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | S | 5400 | B | 131242-WSD11-DR-S-5400-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSD11-DR-5400 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 22 | APP | 2024-10-07 | B | 000446 | 2024-08-28, 2024-10-07 | 03, 04 | 2 | Approved | APP |  |  | 0 | APP | APP
2799 | 000446 | 04 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8003 | B | 131242-WST00-DR-S-8003-B | 2024-10-07 | Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design | Rev.4: Approved. | 2024-10-25 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WST00-DR-8003 | NA | "Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " | 2024-10-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-27 | 22 | APP | 2024-10-07 | B | 000446 | 2024-10-07 | 04 | 1 | Approved | APP |  |  | 0 | APP | APP
2800 | 000447 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0011 | 0 | 131242-WSW41-SP-C-0011-0 | 2024-04-22 | Reinforcement Bar Test Reports -Rebar Size (H10 &H16) | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-05-21 | 2024-05-02 | Approved with Comments | 2024-05-23 | NO | Overdue |  | 131242-WSW41-SP-0011 | NA | "Reinforcement Bar Test Reports -Rebar Size (H10 &H16)" | 2024-04-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-12 | 10 | AWC | 2024-04-22 | 0 | 000447 | 2024-04-22 | 00 | 1 | Approved with Comments | AWC | 2024-05-22 | Overdue | 0 | AWC | AWC
2801 | 000448 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 0 | 131242-WSW41-MS-C-0009-0 | 2024-04-24 | MSRA,SWP for Bored Piling WLT | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-24 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-MS-0009 | NA | "MSRA,SWP for Bored Piling WLT" | 2024-04-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-14 | 8 | NAP | 2024-05-10 | 1 | 000448 | 2024-04-24, 2024-05-10 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
2802 | 000448 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0009 | 1 | 131242-WSW41-MS-C-0009-1 | 2024-05-10 | MSRA,SWP for Bored Piling WLT | Rev.1: Approved | 2024-05-31 | 2024-05-20 | Approved |  | YES | NA |  | 131242-WSW41-MS-0009 | NA | "MSRA,SWP for Bored Piling WLT" | 2024-04-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-24 | 10 | APP | 2024-05-10 | 1 | 000448 | 2024-04-24, 2024-05-10 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2803 | 000449 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | VI | S | 0003 | 0 | 131242-WSW41-VI-S-0003-0 | 2024-04-25 | Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd) | Approved | 2024-05-27 | 2024-05-02 | Approved |  | YES | NA |  | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-09 | 7 | APP | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
2804 | 000450 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0004 | 0 | 131242-WSW41-VI-S-0004-0 | 2024-04-25 | Vendor Approval of ERSS Works (Singlee) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-27 | 2024-05-02 | Not Approved | 2024-05-23 | YES | Resubmitted |  | 131242-WSW41-VI-0004 | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-09 | 7 | NAP | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | Approved | APP |  |  | 0 | NAP | NAP
2805 | 000450 | 01 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | G | 0002 | 0 | 131242-WSW41-VI-G-0002-0 | 2024-07-09 | Vendor Approval of ERSS Works (Singlee) | Rev.1: Not Approved. Submission incomplete, proposed vendor is different in R0 and R1. Please resubmit with comment respond sheet. | 2024-07-29 | 2024-07-17 | Not Approved | 2024-08-06 | NO | Overdue |  | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-23 | 8 | NAP | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP | 2024-08-06 | Overdue | 0 | NAP | NAP
2806 | 000451 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0010 | 0 | 131242-WSW41-PC-W-0010-0 | 2024-04-25 | Payment Claim No.10 | Rev(0): Approved. Please refer to S.O. correspondence no. 15 dated 7 May 2024. | 2024-05-27 | 2024-05-13 | Approved |  | YES | NA |  | 131242-WSW41-PC-0010 | NA | "Payment Claim No.10" | 2024-04-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-15 | 18 | APP | 2024-04-25 | 0 | 000451 | 2024-04-25 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
2807 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 8002_ST606_BCA | A | 131242-WST02-DR-S-8002_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue | Heng Peng to provide latest DGN & PDF drawing | 131242-WST02-DR-8002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2808 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0001_ST606_BCA | A | 131242-WST02-DR-S-0001_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-0001_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2809 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0002_ST606_BCA | A | 131242-WST02-DR-S-0002_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-0002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2810 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 0003_ST606_BCA | A | 131242-WST02-DR-S-0003_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-0003_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2811 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5001_ST606_BCA | A | 131242-WST02-DR-S-5001_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-5001_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2812 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5002_ST606_BCA | A | 131242-WST02-DR-S-5002_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-5002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2813 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606_BCA | A | 131242-WST02-DR-S-1006_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-1006_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2814 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606_BCA | A | 131242-WST02-DR-S-1007_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-1007_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2815 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606_BCA | A | 131242-WST02-DR-S-1008_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-1008_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2816 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606_BCA | A | 131242-WST02-DR-S-7000_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-7000_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2817 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606_BCA | A | 131242-WST02-DR-S-7001_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-7001_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2818 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606_BCA | A | 131242-WST02-DR-S-7002_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-7002_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2819 | 000452 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606_BCA | A | 131242-WST02-DR-S-3000_ST606_BCA-A | 2024-04-26 | ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-05-28 | 2024-05-20 | Approved with Comments | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-3000_ST606_BCA | NA | "ST606 - SSN Main Water Tank Sub Structure Design (BCA Approved Drawings)" && "ST606_SSN Main Water Tanks - Sub Structure Details (BCA Submission)" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-10 | 24 | AWC | 2024-04-26 | A | 000443&&000452 | 2024-04-17, 2024-04-26 | 00 | 2 | Approved with Comments | AWC | 2024-06-07 | Overdue | 0 | AWC | AWC
2820 | 000453 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0011 | 0 | 131242-WSW41-PS-PM-0011-0 | 2024-04-26 | Monthly Progress Presentation No. 11 (0324) | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 | For Information |  | YES | NA |  | 131242-WSW41-PS-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "Incentive/ Disincentive Audit Scheme for Apr 2024" && "Monthly Progress Presentation No. 11 (0324)" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-10 | 13 | INF | 2024-08-22 | 0 | 000176&&000453&&000667 | 2023-11-09, 2024-04-26, 2024-08-22 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
2821 | 000454 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0011 | 0 | 131242-WSW41-MI-PM-0011-0 | 2024-04-26 | Monthly Progress Meeting Minutes 0011_20240423 | Rev. 0 - For Information | 2024-05-28 | 2024-05-09 | For Information |  | YES | NA |  | 131242-WSW41-MI-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0011_20240423" && "Process & MEICA Meeting Minutes 0011_20231012" | 2023-10-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-05-10 | 13 | INF | 2024-04-26 | 0 | 000131&&000153&&000176&&000454 | 2023-10-18, 2023-10-30, 2023-11-09, 2024-04-26 | 00 | 4 | For Information | INF | 2024-05-29 | Overdue | 0 | INF | INF
2822 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | B | 131242-WST02-DR-C-8001_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue | To close after addressing the comments of S#475 & S#128.3. | 131242-WST02-DR-8001_ST610_BCA | NA | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " && "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-05-07 | 0 | 000455&&000466 | 2024-04-30, 2024-05-07 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
2823 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610_BCA | B | 131242-WST02-DR-C-1023_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-1023_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2824 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610_BCA | B | 131242-WST02-DR-C-1024_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-1024_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2825 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610_BCA | B | 131242-WST02-DR-C-3000_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-3000_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2826 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610_BCA | B | 131242-WST02-DR-C-3001_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-3001_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2827 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610_BCA | B | 131242-WST02-DR-C-5004_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-5004_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2828 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610_BCA | B | 131242-WST02-DR-C-5005_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-5005_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2829 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610_BCA | B | 131242-WST02-DR-C-5006_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-5006_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2830 | 000455 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610_BCA | B | 131242-WST02-DR-C-5007_ST610_BCA-B | 2024-04-30 | ST610 – Underground Services (BCA Submission File) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-05-30 | 2024-05-20 | Not Approved | 2024-06-10 | NO | Overdue |  | 131242-WST02-DR-5007_ST610_BCA | NA | "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | NAP | 2024-04-30 | B | 000455 | 2024-04-30 | 00 | 1 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2831 | 000456 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 0 | 131242-WSW41-QA-M-0002-0 | 2024-04-30 | Inspection and test plan for Compressed Air System | Rev 0: Not approved - Revise and Resubmit | 2024-05-30 | 2024-07-15 | Not Approved | 2024-08-02 | YES | Resubmitted |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-14 | 76 | NAP | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2832 | 000456 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0002 | 1 | 131242-WSW41-QA-M-0002-1 | 2024-07-22 | Inspection and test plan for Compressed Air System | Rev 1: Approved | 2024-08-12 | 2024-08-20 | Approved |  | YES | NA |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 29 | APP | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
2833 | 000457 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0008 | 0 | 131242-WSW41-PS-HS-0008-0 | 2024-04-30 | Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024 | For Information | 2024-05-30 | 2024-06-06 | For Information |  | YES | NA |  | 131242-WSW41-PS-0008 | NA | "Monthly Progress Presentation No. 08 (1223)" && "Quarterly Risk Management Workshop 3rd Quarterly RM Workshop – 19 Apr 2024" | 2024-01-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-05-14 | 37 | INF | 2024-04-30 | 0 | 000286&&000457 | 2024-01-24, 2024-04-30 | 00 | 2 | For Information | INF | 2024-06-26 | Overdue | 0 | INF | INF
2834 | 000458 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 0 | 131242-WST02-DS-E-0007-0 | 2024-04-30 | SSN Transformer Data Sheet | Rev 0: Approved with comments. To revise and resubmit.Please refer to attached file for comments. | 2024-05-30 | 2024-05-20 | Approved with Comments | 2024-06-10 | YES | Resubmitted |  | 131242-WST02-DS-0007 | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 20 | AWC | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2835 | 000458 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 1 | 131242-WST02-DS-E-0007-1 | 2024-07-09 | SSN Transformer Data Sheet | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-07-29 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WST02-DS-0007 | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-23 | 63 | AWC | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2836 | 000458 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0007 | 2 | 131242-WST02-DS-E-0007-2 | 2024-10-15 | SSN Transformer Data Sheet | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-05 | 2024-11-04 | Approved with Comments | 2024-11-22 | NO | Overdue |  | 131242-WST02-DS-0007 | NA | "Datasheet for Radar Level Transmitter " && "SSN Transformer Data Sheet" | 2024-04-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 20 | AWC | 2025-07-22 | 1 | 000458&&001231 | 2024-04-30, 2024-07-09, 2024-10-15, 2025-04-16, 2025-07-22 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2837 | 000459 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0009 | 0 | 131242-WST02-VI-I-0009-0 | 2024-05-02 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-05-31 | 2024-07-02 | Approved with Comments | 2024-07-22 | YES | Resubmitted |  | 131242-WST02-VI-0009 | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-22 | 61 | AWC | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
2838 | 000459 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 1 | 131242-WST02-VI-I-0009-1 | 2024-07-30 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-18 | Approved with Comments | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-VI-0009 | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-13 | 50 | AWC | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
2839 | 000459 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0009 | 2 | 131242-WST02-VI-I-0009-2 | 2025-02-27 | Vendor Approval of SSN Package (Radar Level Transmitter) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0009 | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-13 | 43 | AWC | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
2840 | 000460 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0021 | 0 | 131242-WSW41-MI-P-0021-0 | 2024-05-02 | Process & MEICA Meeting Minutes 0021_20240328 | For information | 2024-05-31 | 2024-07-26 | For Information |  | YES | NA |  | 131242-WSW41-MI-0021 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0021_20250226" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-16 | 85 | INF | 2025-04-21 | 0 | 000388&&000460&&000684&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2841 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 1000 | 0 | 131242-WST02-DR-M-1000-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue | 2nd priority | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 81 | AWC | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | AWC | AWC
2842 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4000 | 0 | 131242-WST02-DR-M-4000-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue |  | 131242-WST02-DR-4000 | NA | "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-26 | 81 | AWC | 2025-10-31 | 0 | 000164&&000461 | 2024-05-06, 2025-04-22, 2025-10-31 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2843 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4001 | 0 | 131242-WST02-DR-M-4001-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue |  | 131242-WST02-DR-4001 | NA | "Milestone 2 SSN Water Tank" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-26 | 81 | AWC | 2025-04-28 | A | 000163&&000461 | 2024-05-06, 2025-04-28 | 00, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2844 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4002 | 0 | 131242-WST02-DR-M-4002-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue |  | 131242-WST02-DR-4002 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-26 | 81 | AWC | 2025-10-27 | A | 000162&&000461 | 2024-05-06, 2025-04-09, 2025-10-27 | 00, 03, 04 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
2845 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4003 | 0 | 131242-WST02-DR-M-4003-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue |  | 131242-WST02-DR-4003 | NA | "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-26 | 81 | AWC | 2024-05-06 | 0 | 000461 | 2024-05-06 | 00 | 1 | Approved with Comments | AWC | 2024-08-15 | Overdue | 0 | AWC | AWC
2846 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 4004 | 0 | 131242-WST02-DR-M-4004-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue |  | 131242-WST02-DR-4004 | NA | "Milestone 2 SSN Electrical Building" && "SSN Overall GA & Equipment Layout Drawings" | 2024-05-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-26 | 81 | AWC | 2025-05-15 | 0 | 000191&&000461 | 2024-05-06, 2025-05-15 | 00, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2847 | 000461 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7000 | 0 | 131242-WST02-DR-M-7000-0 | 2024-05-06 | SSN Overall GA & Equipment Layout Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-04 | 2024-07-26 | Approved with Comments | 2024-08-16 | NO | Overdue |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-20 | 81 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2848 | 000462 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 0 | 131242-WST02-VI-I-0010-0 | 2024-05-07 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | Approved with Comments | 2024-07-22 | YES | Resubmitted |  | 131242-WST02-VI-0010 | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 56 | AWC | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2849 | 000462 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 1 | 131242-WST02-VI-I-0010-1 | 2024-08-01 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | Approved with Comments | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-VI-0010 | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-15 | 48 | AWC | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2850 | 000462 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0010 | 2 | 131242-WST02-VI-I-0010-2 | 2025-02-27 | Vendor Approval of SSN Package (Tuning Fork Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-03-19 | 2025-04-11 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0010 | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-13 | 43 | AWC | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2851 | 000463 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 0 | 131242-WST02-VI-I-0011-0 | 2024-05-07 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | Not Approved | 2024-07-22 | YES | Resubmitted |  | 131242-WST02-VI-0011 | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 56 | NAP | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
2852 | 000463 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 1 | 131242-WST02-VI-I-0011-1 | 2024-07-24 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-18 | Approved with Comments | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-VI-0011 | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-07 | 56 | AWC | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2853 | 000463 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0011 | 2 | 131242-WST02-VI-I-0011-2 | 2024-11-09 | Vendor Approval of SSN Package (Electromagnetic Flowmeters) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0011 | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-23 | 15 | AWC | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2854 | 000464 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 0 | 131242-WST02-VI-I-0012-0 | 2024-05-07 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-06-05 | 2024-07-02 | Not Approved | 2024-07-22 | YES | Resubmitted |  | 131242-WST02-VI-0012 | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 56 | NAP | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
2855 | 000464 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 1 | 131242-WST02-VI-I-0012-1 | 2024-08-01 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-22 | 2024-09-18 | Approved with Comments | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-VI-0012 | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-15 | 48 | AWC | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2856 | 000464 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0012 | 2 | 131242-WST02-VI-I-0012-2 | 2024-11-08 | Vendor Approval of SSN Package (Capacitive Level Switches) | Rev 2: Approved with comments. No resubmission required. Refer attached file for comments. | 2024-11-28 | 2024-11-24 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0012 | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-22 | 16 | AWC | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
2857 | 000465 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 0 | 131242-WSW41-MS-C-0010-0 | 2024-05-07 | MSRA,SWP for Bored Piling PDA Test | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-06-12 | Approved with Comments | 2024-07-03 | YES | Resubmitted |  | 131242-WSW41-MS-0010 | NA | "MSRA,SWP for Bored Piling PDA Test" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-27 | 36 | AWC | 2024-06-19 | 1 | 000465 | 2024-05-07, 2024-06-19 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
2858 | 000465 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0010 | 1 | 131242-WSW41-MS-C-0010-1 | 2024-06-19 | MSRA,SWP for Bored Piling PDA Test | Approved | 2024-07-09 | 2024-07-01 | Approved |  | YES | NA |  | 131242-WSW41-MS-0010 | NA | "MSRA,SWP for Bored Piling PDA Test" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-03 | 12 | APP | 2024-06-19 | 1 | 000465 | 2024-05-07, 2024-06-19 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2859 | 000466 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 8001_ST610_BCA | 0 | 131242-WST02-DR-C-8001_ST610_BCA-0 | 2024-05-07 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-05 | 2024-05-20 | Not Approved | 2024-06-10 | YES | Resubmitted |  | 131242-WST02-DR-8001_ST610_BCA | NA | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " && "ST610 – Underground Services (BCA Submission File) " | 2024-04-30 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-21 | 13 | NAP | 2024-05-07 | 0 | 000455&&000466 | 2024-04-30, 2024-05-07 | 00 | 2 | Not Approved | NAP | 2024-06-07 | Overdue | 0 | NAP | NAP
2860 | 000466 | 01 | Aaron | CSA | NA | 131242 | NA | NA | NA | Cmt Sheet Reply 2024 06 12 | 0 | 131242----Cmt Sheet Reply 2024 06 12- | 2024-06-12 | ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-03 | 2024-07-01 | Not Approved | 2024-07-19 | NO | Overdue | To close after addressing the comments of S#475, S#128.3 | 131242-NA-NA-Cmt Sheet Reply 2024 06 12 | NA | "ST610 - Underground Services (PDMH, JMH, EICA Ducts and VC Details) (BCA Approved Drawings) " | 2024-06-12 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-02 | 19 | NAP | 2024-06-12 | 0 | 000466 | 2024-06-12 | 01 | 1 | Not Approved | NAP | 2024-07-19 | Overdue | 0 | NAP | NAP
2861 | 000467 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0039 | 0 | 131242-WSW41-CD-IM-0039-0 | 2024-05-08 | Submission Of BIM Coordination VCM Model (Apr-2024) | For Information | 2024-06-06 | 2024-05-21 | For Information |  | YES | NA |  | 131242-WSW41-CD-0039 | NA | "Submission Of BIM Coordination VCM Model (Apr-2024)" | 2024-05-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-05-28 | 13 | INF | 2024-05-08 | 0 | 000467 | 2024-05-08 | 00 | 1 | For Information | INF | 2024-06-10 | Overdue | 0 | INF | INF
2862 | 000468 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 0 | 131242-WST02-RT-C-0001-0 | 2024-05-09 | Design for Safety Report 2 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-07 | 2024-06-06 | Not Approved | 2024-06-27 | YES | Resubmitted |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-23 | 28 | NAP | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2863 | 000468 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 1 | 131242-WST02-RT-C-0001-1 | 2024-06-07 | Design for Safety Report 2 | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-05 | Not Approved | 2024-07-25 | YES | Resubmitted |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 28 | NAP | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2864 | 000468 | 02 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-C-0001-2 | 2024-08-21 | Design for Safety Report 2 | Rev.2: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-17 | Approved with Comments | 2024-10-07 | YES | Resubmitted |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 27 | AWC | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2865 | 000468 | 03 | Leslie | Project | NA | 131242 | WST02 | RT | C | 0001 | 2 | 131242-WST02-RT-C-0001-2 | 2024-11-03 | Design for Safety Report 2 | Rev.3: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-17 | 34 | AWC | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2866 | 000469 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | C | 0005 | 0 | 131242-WSW41-CL-C-0005-0 | 2024-05-10 | Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47) | Rev.0: Approved | 2024-06-10 | 2024-05-20 | Approved |  | YES | NA |  | 131242-WSW41-CL-0005 | NA | "Proposed for Bored pile WLT for 700mm Dia. WLT2 @Zone 1 (TP47)" | 2024-05-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-30 | 10 | APP | 2024-05-10 | 0 | 000469 | 2024-05-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
2867 | 000470 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0022 | 0 | 131242-WSW41-MI-P-0022-0 | 2024-05-13 | Process & MEICA Meeting Minutes 0022_20240425 | Rev 0: For Information | 2024-06-11 | 2024-08-14 | For Information |  | YES | NA |  | 131242-WSW41-MI-0022 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-02 | 93 | INF | 2025-04-21 | 0 | 000470&&000472&&000684&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2868 | 000471 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | A | 1000 | 0 | 131242-WST02-DR-A-1000-0 | 2024-05-13 | NEA Waiver Submission of SSN Plant | For Information | 2024-06-11 | 2024-05-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-27 | 11 | INF | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | INF | INF
2869 | 000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0022 | 0 | 131242-WSW41-MI-C-0022-0 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 | For Information |  | YES | NA |  | 131242-WSW41-MI-0022 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-05-31 | 17 | INF | 2025-04-21 | 0 | 000470&&000472&&000684&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
2870 | 000472 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0023 | 0 | 131242-WSW41-MI-C-0023-0 | 2024-05-17 | CSA Meeting Minutes 0022 & 00023_20240321 & 0404 | For Information | 2024-06-18 | 2024-06-03 | For Information |  | YES | NA |  | 131242-WSW41-MI-0023 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-06 | 17 | INF | 2024-08-29 | 0 | 000472&&000477&&000684 | 2024-05-17, 2024-05-23, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
2871 | 000473 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 0 | 131242-WSW41-RT-PM-0012-0 | 2024-04-18 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-05-17 | 2024-06-03 | Approved with Comments | 2024-06-24 | YES | Resubmitted |  | 131242-WSW41-RT-0012 | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-05-08 | 46 | AWC | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2872 | 000473 | 01 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0012 | 1 | 131242-WSW41-RT-PM-0012-1 | 2024-06-11 | C4B Monthly Progress Report Number No.12 (04 24) | Rev. 1 - Approved | 2024-07-02 | 2024-06-18 | Approved |  | YES | NA |  | 131242-WSW41-RT-0012 | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-25 | 7 | APP | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
2873 | 000474 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 0 | 131242-WSW41-VI-M-1010-0 | 2024-05-18 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 0: Not approved - Revise and Resubmit | 2024-06-18 | 2024-07-04 | Not Approved | 2024-07-24 | YES | Resubmitted |  | 131242-WSW41-VI-1010 | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-07 | 47 | NAP | 2024-10-17 | 2 | 000474 | 2024-05-18, 2024-09-06, 2024-10-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2874 | 000474 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 1 | 131242-WSW41-VI-M-1010-1 | 2024-09-06 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 1: Not approved - Revise and Resubmit | 2024-09-26 | 2024-09-12 | Not Approved | 2024-10-02 | YES | Resubmitted |  | 131242-WSW41-VI-1010 | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 6 | NAP | 2024-10-17 | 2 | 000474 | 2024-05-18, 2024-09-06, 2024-10-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2875 | 000474 | 02 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1010 | 2 | 131242-WSW41-VI-M-1010-2 | 2024-10-17 | Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG) | Rev 2: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-07 | 2024-11-15 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1010 | NA | "Preliminary design and Vendor Approval – Epoxy Lined Carbon Steel Piping (Hebei Huayang/MUSG)" | 2024-05-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-31 | 29 | AWC | 2024-10-17 | 2 | 000474 | 2024-05-18, 2024-09-06, 2024-10-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-12-05 | Overdue | 0 | AWC | AWC
2876 | 000475 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-C-8001_ST610-C | 2024-05-18 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-01 | 16 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2877 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | C | 131242-WST02-DR-C-1023_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-1023_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2878 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | C | 131242-WST02-DR-C-1024_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-1024_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2879 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | C | 131242-WST02-DR-C-5004_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-5004_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2880 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | C | 131242-WST02-DR-C-5005_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2881 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | C | 131242-WST02-DR-C-5006_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2882 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | C | 131242-WST02-DR-C-3000_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2883 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | C | 131242-WST02-DR-C-3001_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-3001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-12-29 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2884 | 000475 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | C | 131242-WST02-DR-C-5007_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-18 | 2024-06-03 | Not Approved | 2024-06-24 | YES | Resubmitted |  | 131242-WST02-DR-5007_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 |  | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2885 | 000475 | 01 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | C | 131242-WST00-DR-C-8001_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2886 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | C | 131242-WST02-DR-C-1023_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-1023_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2887 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | C | 131242-WST02-DR-C-1024_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-1024_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2888 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | C | 131242-WST02-DR-C-5004_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-5004_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2889 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | C | 131242-WST02-DR-C-5005_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2890 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | C | 131242-WST02-DR-C-5006_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2891 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | C | 131242-WST02-DR-C-3000_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2892 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | C | 131242-WST02-DR-C-3001_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-3001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-12-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2893 | 000475 | 01 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | C | 131242-WST02-DR-C-5007_ST610-C | 2024-06-07 | IFC of ST610 (Underground Services) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-07-01 | Not Approved | 2024-07-19 | YES | Resubmitted |  | 131242-WST02-DR-5007_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 24 | NAP | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2894 | 000475 | 02 | Zora | CSA | NA | 131242 | WST00 | DR | C | 8001_ST610 | D | 131242-WST00-DR-C-8001_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST00-DR-8001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-05-18, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2895 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1023_ST610 | D | 131242-WST02-DR-C-1023_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-1023_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2896 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 1024_ST610 | D | 131242-WST02-DR-C-1024_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-1024_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2897 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5004_ST610 | D | 131242-WST02-DR-C-5004_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-5004_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2898 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5005_ST610 | D | 131242-WST02-DR-C-5005_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-5005_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2899 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5006_ST610 | D | 131242-WST02-DR-C-5006_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-5006_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2900 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3000_ST610 | D | 131242-WST02-DR-C-3000_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-3000_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2901 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 3001_ST610 | D | 131242-WST02-DR-C-3001_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-3001_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-12-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2902 | 000475 | 02 | Zora | CSA | NA | 131242 | WST02 | DR | C | 5007_ST610 | D | 131242-WST02-DR-C-5007_ST610-D | 2024-07-11 | IFC of ST610 (Underground Services) | Rev.2:Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-31 | 2024-08-21 | Approved with Comments | 2024-09-10 | YES | Resubmitted |  | 131242-WST02-DR-5007_ST610 | NA | "IFC of ST610 (Underground Services) " && "ST610 Underground Services (PDMH, JMH, EICA Ducts and VC Details) " | 2023-10-16 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-25 | 41 | AWC | 2024-07-11 | D | 000128&&000475 | 2023-10-16, 2023-12-29, 2024-03-28, 2024-06-07, 2024-07-11 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2024-09-10 | Overdue | 0 | AWC | AWC
2903 | 000475 | 03 | Zora | CSA | NA | 131242 | WST02 | NA | C | Cmt Sheet Reply 2024 10 07 | D | 131242-WST02--C-Cmt Sheet Reply 2024 10 07- | 2024-10-09 | IFC of ST610 (Underground Services) | Rev.3: Approved with comments. | 2024-10-29 | 2024-10-24 | Approved with Comments | 2024-11-14 | NO | Overdue |  | 131242-WST02-NA-Cmt Sheet Reply 2024 10 07 | NA | "IFC of ST610 (Underground Services) " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 15 | AWC | 2024-10-09 | D | 000475 | 2024-10-09 | 03 | 1 | Approved with Comments | AWC | 2024-11-13 | Overdue | 0 | AWC | AWC
2904 | 000476 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 0 | 131242-WST02-VI-I-0016-0 | 2024-05-21 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-20 | 2024-07-02 | Approved with Comments | 2024-07-22 | YES | Resubmitted |  | 131242-WST02-VI-0016 | NA | "Vendor Approval for Active Harmonic Filter (DANFOSS)" && "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-10 | 42 | AWC | 2025-08-05 | 1 | 000476&&001368 | 2024-05-21, 2025-03-17, 2025-06-12, 2025-08-05 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2905 | 000476 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0016 | 1 | 131242-WST02-VI-I-0016-1 | 2025-03-17 | Vendor Approval of SSN Package (Conductive Probe Level Switches) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0016 | NA | "Vendor Approval for Active Harmonic Filter (DANFOSS)" && "Vendor Approval of SSN Package (Conductive Probe Level Switches)" | 2024-05-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 50 | AWC | 2025-08-05 | 1 | 000476&&001368 | 2024-05-21, 2025-03-17, 2025-06-12, 2025-08-05 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2906 | 000477 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0023 | 0 | 131242-WSW41-MI-P-0023-0 | 2024-05-23 | Process & MEICA Meeting Minutes 0023_20240509 | Rev 0: For Information | 2024-06-21 | 2024-08-14 | For Information |  | YES | NA |  | 131242-WSW41-MI-0023 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-06 | 83 | INF | 2024-08-29 | 0 | 000472&&000477&&000684 | 2024-05-17, 2024-05-23, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
2907 | 000478 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CN | S | 0001 | 0 | 131242-WSD11-CN-S-0001-0 | 2024-05-23 | Handrail design loading & Testing of THP Train by CAMBI | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-21 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue | Resubmission on hold and to resubmit after BCA approval of CAMBI Steel Structure | 131242-WSD11-CN-0001 | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-12 | 11 | NAP | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | Rejected | REJ |  |  | 0 | NAP | NAP
2908 | 000479 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0001 | 0 | 131242-WSD11-CN-E-0001-0 | 2024-05-23 | Proposed change of SS316 Cable Tray within THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-18 | Rejected |  | YES | NA |  | 131242-WSD11-CN-0001 | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-12 | 26 | REJ | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | Rejected | REJ |  |  | 0 | REJ | REJ
2909 | 000480 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0002 | 0 | 131242-WSD11-CN-E-0002-0 | 2024-05-23 | Proposed change of Carbon loaded GRP Junction Box within THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | Rejected |  | YES | NA |  | 131242-WSD11-CN-0002 | NA | "Pressure Instrument Mounting in THP Module" && "Proposed change of Carbon loaded GRP Junction Box within THP Module" | 2024-05-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-12 | 42 | REJ | 2024-05-23 | 0 | 000480&&000483 | 2024-05-23 | 00 | 2 | Rejected | REJ | 2024-07-24 | Overdue | 0 | REJ | REJ
2910 | 000481 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0003 | 0 | 131242-WSD11-CN-E-0003-0 | 2024-05-23 | Separate Terminal Box for Motor Space Heater | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 | Rejected |  | YES | NA |  | 131242-WSD11-CN-0003 | NA | "Separate Terminal Box for Motor Space Heater" | 2024-05-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-12 | 20 | REJ | 2024-05-23 | 0 | 000481 | 2024-05-23 | 00 | 1 | Rejected | REJ | 2024-07-02 | Overdue | 0 | REJ | REJ
2911 | 000482 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | E | 0004 | 0 | 131242-WSD11-CN-E-0004-0 | 2024-05-23 | Local Control Station with THP Module | Rev 0: Rejected as the proposal put forth by the contractor is complying with specifications and does not constitute a change. | 2024-06-21 | 2024-06-12 | Rejected |  | YES | NA |  | 131242-WSD11-CN-0004 | NA | "Local Control Station with THP Module" | 2024-05-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-12 | 20 | REJ | 2024-05-23 | 0 | 000482 | 2024-05-23 | 00 | 1 | Rejected | REJ | 2024-07-02 | Overdue | 0 | REJ | REJ
2912 | 000483 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | I | 0002 | 0 | 131242-WSD11-CN-I-0002-0 | 2024-05-23 | Pressure Instrument Mounting in THP Module | Your proposal is acceptable in accordance to P4.2(b)(l), hence, the RFC is rejected. Please follow up as a compliance submission for approval. | 2024-06-21 | 2024-07-04 | Rejected |  | YES | NA |  | 131242-WSD11-CN-0002 | NA | "Pressure Instrument Mounting in THP Module" && "Proposed change of Carbon loaded GRP Junction Box within THP Module" | 2024-05-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-12 | 42 | REJ | 2024-05-23 | 0 | 000480&&000483 | 2024-05-23 | 00 | 2 | Rejected | REJ | 2024-07-24 | Overdue | 0 | REJ | REJ
2913 | 000484 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CN | M | 0001 | 0 | 131242-WSD11-CN-M-0001-0 | 2024-05-23 | Pump Color within THP Module | Rev 0: Rejected Refer to attached file for comments. | 2024-06-21 | 2024-08-08 | Rejected |  | YES | NA |  | 131242-WSD11-CN-0001 | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-12 | 77 | REJ | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | Rejected | REJ |  |  | 0 | REJ | REJ
2914 | 000485 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0020 | 0 | 131242-WSW41-VI-E-0020-0 | 2024-05-23 | Vendor Approval of Electrical Installer (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-06-21 | 2024-07-04 | Approved with Comments | 2024-07-24 | NO | Overdue |  | 131242-WSW41-VI-0020 | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-12 | 42 | AWC | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
2915 | 000486 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | I | 0020 | 0 | 131242-WSW41-VI-I-0020-0 | 2024-05-23 | Vendor Approval of ICA Installer Submission (Cyclect) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-06-21 | 2024-07-02 | Approved with Comments | 2024-07-22 | NO | Overdue |  | 131242-WSW41-VI-0020 | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-12 | 40 | AWC | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
2916 | 000487 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | K | 0001 | 0 | 131242-WSW41-MS-K-0001-0 | 2024-05-27 | MSRA & SWP for Mobilization and Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 | Approved with Comments | 2024-07-01 | NO | Overdue |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-10 | 14 | AWC | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | AWC | AWC
2917 | 000488 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0001 | 0 | 131242-WSW41-MS-G-0001-0 | 2024-05-27 | MSRA & SWP for Sheet Piling Work | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-25 | 2024-06-10 | Not Approved | 2024-07-01 | NO | Overdue |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-10 | 14 | NAP | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | NAP | NAP
2918 | 000489 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0002 | 0 | 131242-WST02-RT-C-0002-0 | 2024-05-28 | Project Safety Review for ERSS | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-18 | Approved with Comments | 2024-07-08 | YES | Resubmitted |  | 131242-WST02-RT-0002 | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 21 | AWC | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
2919 | 000489 | 01 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0002 | 1 | 131242-WST02-RT-C-0002-1 | 2024-07-09 | Project Safety Review for ERSS | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-29 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-RT-0002 | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-23 | 34 | AWC | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
2920 | 000490 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 0 | 131242-WST02-RT-C-0003-0 | 2024-05-28 | Report of DFS (Guide 3) for ERSS | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-26 | 2024-06-13 | Not Approved | 2024-07-04 | YES | Resubmitted |  | 131242-WST02-RT-0003 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 16 | NAP | 2025-07-01 | 0 | 000490&&000752&&001420 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2921 | 000490 | 01 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0003 | 1 | 131242-WST02-RT-C-0003-1 | 2024-06-19 | Report of DFS (Guide 3) for ERSS | Rev.1: Approved | 2024-07-09 | 2024-07-12 | Approved |  | YES | NA |  | 131242-WST02-RT-0003 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-03 | 23 | APP | 2025-07-01 | 0 | 000490&&000752&&001420 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
2922 | 000491 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0030 | 0 | 131242-WSW41-LT-PM-0030-0 | 2024-05-28 | CV of Team member (Planner) | Rev. 0 - Approved with comments. Please refer to attached comment sheet | 2024-06-26 | 2024-06-10 | Approved with Comments | 2024-07-01 | NO | Overdue |  | 131242-WSW41-LT-0030 | NA | "CV of Team member (Planner)" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 13 | AWC | 2024-05-28 | 0 | 000491 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-06-28 | Overdue | 0 | AWC | AWC
2923 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | A | 131242-WST02-DR-M-5000-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-11 | 72 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2924 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | A | 131242-WST02-DR-M-5001-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-11 | 72 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2925 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | A | 131242-WST02-DR-M-5002-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-11 | 72 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2926 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | A | 131242-WST02-DR-M-5003-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2927 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | A | 131242-WST02-DR-M-5004-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5004 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2928 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | A | 131242-WST02-DR-M-5005-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5005 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2929 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | A | 131242-WST02-DR-M-5006-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5006 | NA | "Fire Seal Detail" && "SSN Cast-in Schedule & Details" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2025-02-26 | C.1 | 000492&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2930 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | A | 131242-WST02-DR-M-5007-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5007 | NA | "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2025-02-26 | C.1 | 000492&&000833 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2931 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | A | 131242-WST02-DR-M-5008-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-DR-5008 | NA | "SSN Cast-in Schedule & Details" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2025-02-26 | C.1 | 000492&&000860 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2932 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7001 | A | 131242-WST02-SH-M-7001-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7001 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2933 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7002 | A | 131242-WST02-SH-M-7002-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7002 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2934 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7003 | A | 131242-WST02-SH-M-7003-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7003 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2935 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7004 | A | 131242-WST02-SH-M-7004-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7004 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2936 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7005 | A | 131242-WST02-SH-M-7005-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7005 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2937 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7006 | A | 131242-WST02-SH-M-7006-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7006 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2938 | 000492 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7007 | A | 131242-WST02-SH-M-7007-A | 2024-05-28 | SSN Cast-in Schedule & Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-26 | 2024-08-08 | Approved with Comments | 2024-08-29 | YES | Resubmitted |  | 131242-WST02-SH-7007 | NA | "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-17 | 72 | AWC | 2024-05-28 | A | 000492 | 2024-05-28 | 00 | 1 | Approved with Comments | AWC | 2024-08-28 | Overdue | 0 | AWC | AWC
2939 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | B | 131242-WST02-DR-M-5000-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2940 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | B | 131242-WST02-DR-M-5001-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2941 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | B | 131242-WST02-DR-M-5002-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2942 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | B | 131242-WST02-DR-M-5003-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2943 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | B | 131242-WST02-DR-M-5004-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5004 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2944 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | B | 131242-WST02-DR-M-5005-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5005 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2945 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | B | 131242-WST02-DR-M-5006-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5006 | NA | "Fire Seal Detail" && "SSN Cast-in Schedule & Details" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-02-26 | C.1 | 000492&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2946 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | B | 131242-WST02-DR-M-5007-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5007 | NA | "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-02-26 | C.1 | 000492&&000833 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2947 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | B | 131242-WST02-DR-M-5008-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5008 | NA | "SSN Cast-in Schedule & Details" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-02-26 | C.1 | 000492&&000860 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2948 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7001 | B | 131242-WST02-DR-M-7001-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2949 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7002 | B | 131242-WST02-DR-M-7002-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2950 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7003 | B | 131242-WST02-DR-M-7003-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2951 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7004 | B | 131242-WST02-DR-M-7004-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2952 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7005 | B | 131242-WST02-DR-M-7005-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2953 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7006 | B | 131242-WST02-DR-M-7006-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
2954 | 000492 | 01 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7007 | B | 131242-WST02-DR-M-7007-B | 2024-10-21 | SSN Cast-in Schedule & Details | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-04 | 45 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | AWC | AWC
2955 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5000 | C.1 | 131242-WST02-DR-M-5000-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2956 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5001 | C.1 | 131242-WST02-DR-M-5001-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2957 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5002 | C.1 | 131242-WST02-DR-M-5002-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2958 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5003 | C.1 | 131242-WST02-DR-M-5003-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5003 | NA | "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "SSN Cast-in Schedule & Details" && "SSN_CAT Ladder " | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-09-11 | B | 000188&&000191&&000492&&000831 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-04-04, 2025-05-15, 2025-08-19, 2025-09-11 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2959 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5004 | C.1 | 131242-WST02-DR-M-5004-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5004 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2960 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5005 | C.1 | 131242-WST02-DR-M-5005-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5005 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2961 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5006 | C.1 | 131242-WST02-DR-M-5006-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5006 | NA | "Fire Seal Detail" && "SSN Cast-in Schedule & Details" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-02-26 | C.1 | 000492&&000829 | 2024-05-28, 2024-10-21, 2024-11-21, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-05-16 | Overdue | 0 | AWC | AWC
2962 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5007 | C.1 | 131242-WST02-DR-M-5007-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5007 | NA | "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-02-26 | C.1 | 000492&&000833 | 2024-05-28, 2024-10-21, 2025-02-18, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-05-16 | Overdue | 0 | AWC | AWC
2963 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5008 | C.1 | 131242-WST02-DR-M-5008-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-5008 | NA | "SSN Cast-in Schedule & Details" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-02-26 | C.1 | 000492&&000860 | 2024-05-28, 2024-10-21, 2024-11-30, 2025-02-26 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-05-16 | Overdue | 0 | AWC | AWC
2964 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7001 | C.2 | 131242-WST02-DR-M-7001-C.2 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2965 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7002 | C.1 | 131242-WST02-DR-M-7002-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2966 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7003 | C.1 | 131242-WST02-DR-M-7003-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2967 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7004 | C.1 | 131242-WST02-DR-M-7004-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2968 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7005 | C.1 | 131242-WST02-DR-M-7005-C.1 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2969 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7006 | C.2 | 131242-WST02-DR-M-7006-C.2 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
2970 | 000492 | 02 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 7007 | C.2 | 131242-WST02-DR-M-7007-C.2 | 2025-02-26 | SSN Cast-in Schedule & Details | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-18 | 2025-04-28 | Approved with Comments | 2025-05-16 | NO | Overdue |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-12 | 61 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | AWC | AWC
2971 | 000493 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0015 | 0 | 131242-WSW41-VI-C-0015-0 | 2024-05-29 | Vendor Approval of Testing Laboratory (TUV) | Approved | 2024-06-27 | 2024-06-03 | Approved |  | YES | NA |  | 131242-WSW41-VI-0015 | NA | "Vendor Approval for Distribution Boards (GSM)" && "Vendor Approval of Testing Laboratory (TUV)" | 2024-05-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-18 | 5 | APP | 2025-10-01 | 1 | 000493&&001437 | 2024-05-29, 2025-07-07, 2025-10-01 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
2972 | 000494 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 0 | 131242-WSW41-MS-C-0011-0 | 2024-05-29 | Method Statement for Concrete Temperature Control and Monitoring | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-10 | Not Approved | 2024-07-01 | YES | Resubmitted |  | 131242-WSW41-MS-0011 | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-18 | 12 | NAP | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2973 | 000494 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 1 | 131242-WSW41-MS-C-0011-1 | 2024-06-18 | Method Statement for Concrete Temperature Control and Monitoring | Rev.1:Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-08 | 2024-07-25 | Approved with Comments | 2024-08-15 | YES | Resubmitted |  | 131242-WSW41-MS-0011 | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-02 | 37 | AWC | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2974 | 000494 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0011 | 2 | 131242-WSW41-MS-C-0011-2 | 2024-07-28 | Method Statement for Concrete Temperature Control and Monitoring | Rev.2:Approved with comment. Please refer to comment sheet for resubmission. | 2024-08-16 | 2024-08-13 | Approved with Comments | 2024-09-02 | NO | Overdue |  | 131242-WSW41-MS-0011 | NA | "MSRA for HV Power and Pilot Cable Laying, Testing & Termination" && "Method Statement for Concrete Temperature Control and Monitoring" | 2024-05-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 16 | AWC | 2025-12-08 | 1 | 000494&&001227 | 2024-05-29, 2024-06-18, 2024-07-28, 2025-04-14, 2025-12-08 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2975 | 000495 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SU | K | 0001 | 0 | 131242-WSW41-SU-K-0001-0 | 2024-05-29 | Time Lapse Surveys_Apr 24 | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-06-27 | 2024-06-03 | Not Approved | 2024-06-24 | NO | Overdue |  | 131242-WSW41-SU-0001 | NA | "Time Lapse Surveys_Apr 24" | 2024-05-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-18 | 5 | NAP | 2024-05-29 | 0 | 000495 | 2024-05-29 | 00 | 1 | Not Approved | NAP | 2024-06-21 | Overdue | 0 | NAP | NAP
2976 | 000496 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0029 | 0 | 131242-WSW41-LT-PM-0029-0 | 2024-05-30 | Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24 | Rev(0): Received for S.O.'s assessment. Please refer to S.O. correspondence no. 211 dated 22 Aug 2024. | 2024-06-28 | 2024-08-26 | For Information |  | YES | NA |  | 131242-WSW41-LT-0029 | NA | "Request for Extension of Time Due to Exceptionally Adverse Weather Conditions for the period of May 23 to April 24" | 2024-05-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-19 | 88 | INF | 2024-05-30 | 0 | 000496 | 2024-05-30 | 00 | 1 | For Information | INF | 2024-09-13 | Overdue | 0 | INF | INF
2977 | 000497 | 00 | Low | EICA | NA | 131242 | WSD11 | CN | I | 0001 | 0 | 131242-WSD11-CN-I-0001-0 | 2024-05-30 | General Deviation from ICA G & P Spec | Rev 0: Rejected. To revise and resubmit. Refer attached file for comments. | 2024-06-28 | 2024-08-27 | Rejected | 2024-09-16 | NO | Overdue | (RFC) NO.: 1230207-RFC-0013 | 131242-WSD11-CN-0001 | NA | "General Deviation from ICA G & P Spec" && "Handrail design loading & Testing of THP Train by CAMBI" && "Proposed change of SS316 Cable Tray within THP Module" && "Pump Color within THP Module" | 2024-05-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-13 | 89 | REJ | 2024-05-30 | 0 | 000478&&000479&&000484&&000497 | 2024-05-23, 2024-05-30 | 00 | 4 | Rejected | REJ | 2024-09-16 | Overdue | 0 | REJ | REJ
2978 | 000498 | 00 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0012 | 0 | 131242-WSW41-SP-C-0012-0 | 2024-05-30 | Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-06-28 | 2024-06-12 | Approved with Comments | 2024-07-03 | NO | Overdue |  | 131242-WSW41-SP-0012 | NA | "Test Report for static load test 600mm Dia Bored Pile WLT1 (TP115)" | 2024-05-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-19 | 13 | AWC | 2024-05-30 | 0 | 000498 | 2024-05-30 | 00 | 1 | Approved with Comments | AWC | 2024-07-02 | Overdue | 0 | AWC | AWC
2979 | 000499 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 0 | 131242-WSD11-VI-M-0002-0 | 2024-05-30 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-06-28 | 2024-07-18 | Approved with Comments | 2024-08-07 | YES | Resubmitted |  | 131242-WSD11-VI-0002 | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-13 | 49 | AWC | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2980 | 000499 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | VI | M | 0002 | 1 | 131242-WSD11-VI-M-0002-1 | 2025-03-14 | Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-04-03 | 2025-07-08 | Approved with Comments | 2025-07-28 | NO | Overdue |  | 131242-WSD11-VI-0002 | NA | "Preliminary Design and Vendor Approval for THP System Valve Package (CAMBI Supply)" && "Vendor Approval of THP PLC/ RIO/ HMI Components (Seimens & Lenovo)" | 2024-04-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-28 | 116 | AWC | 2025-03-14 | 1 | 000417&&000499 | 2024-04-04, 2024-05-30, 2024-08-15, 2025-03-14 | 00, 01 | 4 | Approved with Comments | AWC | 2025-07-28 | Overdue | 0 | AWC | AWC
2981 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601_BCA | B | 131242-WST00-DR-G-8000_ST601_BCA-B | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-8000_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | B | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2982 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-0001_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2983 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-0002_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2984 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-1000_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2985 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-1001_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2986 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-1002_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2987 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-1003_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2988 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-1004_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2989 | 000500 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601_BCA | C |  | 2024-05-31 | BCA Approval of ST601 – ERSS < 4m | For Information | 2024-07-01 | 2024-06-10 | For Information |  | YES | NA |  | 131242-WST00-DR-3000_ST601_BCA | NA | "BCA Approval of ST601 – ERSS < 4m " | 2024-05-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-06-20 | 10 | INF | 2024-05-31 | C | 000500 | 2024-05-31 | 00 | 1 | For Information | INF | 2024-06-28 | Overdue | 0 | INF | INF
2990 | 000501 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 0 | 131242-WST02-VI-I-0014-0 | 2024-05-31 | Vendor Approval of SSN Package (Thermal Flow Switches) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | Not Approved | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-VI-0014 | NA | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" && "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-20 | 52 | NAP | 2025-01-08 | 1 | 000501&&000848 | 2024-05-31, 2024-11-28, 2025-01-08 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2991 | 000501 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0014 | 1 | 131242-WST02-VI-I-0014-1 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow Switches) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0014 | NA | "Vendor Approval of SS316 Cable Ladder, Tray and Accessories (HDMANN)" && "Vendor Approval of SSN Package (Thermal Flow Switches)" | 2024-05-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-22 | 118 | AWC | 2025-01-08 | 1 | 000501&&000848 | 2024-05-31, 2024-11-28, 2025-01-08 | 00, 01 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
2992 | 000502 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 0 | 131242-WST02-VI-I-0015-0 | 2024-05-31 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | Approved with Comments | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-VI-0015 | NA | "Vendor Approval of SSN Package (Pressure Gauges)" | 2024-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-20 | 52 | AWC | 2024-08-27 | 1 | 000502 | 2024-05-31, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
2993 | 000502 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0015 | 1 | 131242-WST02-VI-I-0015-1 | 2024-08-27 | Vendor Approval of SSN Package (Pressure Gauges) | Rev 1: Approved. | 2024-09-16 | 2024-11-08 | Approved |  | YES | NA |  | 131242-WST02-VI-0015 | NA | "Vendor Approval of SSN Package (Pressure Gauges)" | 2024-05-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 73 | APP | 2024-08-27 | 1 | 000502 | 2024-05-31, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
2994 | 000503 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 0 | 131242-WST02-VI-I-0013-0 | 2024-06-01 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-01 | 2024-07-22 | Not Approved | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-VI-0013 | NA | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | 2024-06-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 51 | NAP | 2025-01-08 | 1 | 000503 | 2024-06-01, 2025-01-08 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
2995 | 000503 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0013 | 1 | 131242-WST02-VI-I-0013-1 | 2025-01-08 | Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-28 | 2025-03-17 | Approved with Comments | 2025-04-04 | NO | Overdue |  | 131242-WST02-VI-0013 | NA | "Vendor Approval of SSN Package (Thermal Flow/ Mass Flow meter)" | 2024-06-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-22 | 68 | AWC | 2025-01-08 | 1 | 000503 | 2024-06-01, 2025-01-08 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-04 | Overdue | 0 | AWC | AWC
2996 | 000504 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 0 | 131242-WSW41-VI-M-1011-0 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-01 | 2024-07-18 | Approved with Comments | 2024-08-07 | YES | Resubmitted |  | 131242-WSW41-VI-1011 | NA | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | 2024-06-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 47 | AWC | 2024-11-02 | 1 | 000504 | 2024-06-01, 2024-11-02 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
2997 | 000504 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1011 | 1 | 131242-WSW41-VI-M-1011-1 | 2024-11-02 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-21 | 2024-12-05 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1011 | NA | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (JASH)" | 2024-06-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-16 | 33 | AWC | 2024-11-02 | 1 | 000504 | 2024-06-01, 2024-11-02 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
2998 | 000505 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1012 | 0 | 131242-WSW41-VI-M-1012-0 | 2024-06-01 | Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves) | Rev 0: Not approved - Revise and Resubmit | 2024-07-01 | 2024-08-01 | Not Approved | 2024-08-22 | NO | Overdue | This document is no longer valid and should be marked as "Voided." | 131242-WSW41-VI-1012 | NA | "Preliminary Design and Vendor Approval of Metallic Knife Gate Valves (Value Valves)" | 2024-06-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-21 | 61 | NAP | 2024-06-01 | 0 | 000505 | 2024-06-01 | 00 | 1 | Not Approved | NAP | 2024-08-21 | Overdue | 0 | NAP | NAP
2999 | 000506 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0011 | 0 | 131242-WSW41-PC-W-0011-0 | 2024-06-03 | Payment Claim No.11 | For Information | 2024-07-02 | 2024-06-27 | For Information |  | YES | NA |  | 131242-WSW41-PC-0011 | NA | "Payment Claim No.11" | 2024-06-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-23 | 24 | INF | 2024-06-03 | 0 | 000506 | 2024-06-03 | 00 | 1 | For Information | INF | 2024-07-17 | Overdue | 0 | INF | INF
3000 | 000507 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | CL | P | 0010 | 0 | 131242-WST02-CL-P-0010-0 | 2024-06-03 | Blower Pressure Loss Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-07-02 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-CL-0010 | NA | "Blower Pressure Loss Calculation" | 2024-06-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-23 | 58 | NAP | 2025-09-10 | 2 | 000507 | 2024-06-03, 2024-10-22, 2025-09-10 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3001 | 000507 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 1 | 131242-WST02-CL-P-0010-1 | 2024-10-22 | Blower Pressure Loss Calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2024-11-19 | Approved with Comments | 2024-12-09 | YES | Resubmitted |  | 131242-WST02-CL-0010 | NA | "Blower Pressure Loss Calculation" | 2024-06-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 28 | AWC | 2025-09-10 | 2 | 000507 | 2024-06-03, 2024-10-22, 2025-09-10 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3002 | 000507 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0010 | 2 | 131242-WST02-CL-P-0010-2 | 2025-09-10 | Blower Pressure Loss Calculation | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. Provide PE endorsement | 2025-09-30 | 2026-02-23 | Approved with Comments | 2026-03-13 | NO | NA |  | 131242-WST02-CL-0010 | NA | "Blower Pressure Loss Calculation" | 2024-06-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-24 | 166 | AWC | 2025-09-10 | 2 | 000507 | 2024-06-03, 2024-10-22, 2025-09-10 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
3003 | 000508 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0031 | 0 | 131242-WSW41-LT-PM-0031-0 | 2024-06-04 | Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump] | Refer to S.O. Correspondence No.0194. | 2024-07-03 | 2024-08-16 | For Information |  | YES | NA |  | 131242-WSW41-LT-0031 | NA | "Notice of Delay [1. THP Compartmentation Design Changes 2. Design Change for Relocation of Feeder Pump]" | 2024-06-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-24 | 73 | INF | 2024-06-04 | 0 | 000508 | 2024-06-04 | 00 | 1 | For Information | INF | 2024-09-05 | Overdue | 0 | INF | INF
3004 | 000509 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0012 | 0 | 131242-WSW41-MI-PM-0012-0 | 2024-06-04 | Monthly Progress Meeting Minutes 0012_20240521 | For Information | 2024-07-03 | 2024-06-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0012 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "C4B Minutes of Engineering Process & MEICA Meeting No.0012" && "CSA Meeting Minutes 0011 & 0012_20230921 & 20231005" && "Monthly Progress Meeting Minutes 0012_20240521" | 2023-10-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-18 | 0 | INF | 2024-06-04 | 0 | 000131&&000209&&000226&&000509 | 2023-10-18, 2023-11-24, 2023-12-05, 2024-06-04 | 00 | 4 | For Information | INF | 2024-06-24 | Overdue | 0 | INF | INF
3005 | 000510 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0012 | 0 | 131242-WSW41-PS-PM-0012-0 | 2024-06-04 | Monthly Progress Presentation No. 12 (0424) | For Information | 2024-07-03 | 2024-06-04 | For Information |  | YES | NA |  | 131242-WSW41-PS-0012 | NA | "Incentive/ Disincentive Audit Scheme for May 2024" && "Monthly Progress Presentation No. 12 (0424)" | 2024-06-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-24 | 0 | INF | 2024-08-22 | 0 | 000510&&000668 | 2024-06-04, 2024-08-22 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
3006 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3180 | A | 131242-WST02-DR-M-3180-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-3180 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3007 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3181 | A | 131242-WST02-DR-M-3181-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-3181 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3008 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 3182 | A | 131242-WST02-DR-M-3182-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-3182 | NA | "LCS GA and Schematic Drawing" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-10-08 | C | 000511&&001206 | 2024-06-05, 2025-07-08, 2025-10-08 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3009 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5131 | A | 131242-WST02-DR-M-5131-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5131 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2024-06-05 | A | 000511 | 2024-06-05 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3010 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5132 | A | 131242-WST02-DR-M-5132-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5132 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2024-06-05 | A | 000511 | 2024-06-05 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3011 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5133 | A | 131242-WST02-DR-M-5133-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5133 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2024-06-05 | A | 000511 | 2024-06-05 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3012 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5101 | A | 131242-WST02-DR-M-5101-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5101 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2024-06-05 | A | 000511 | 2024-06-05 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3013 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 5102 | A | 131242-WST02-DR-M-5102-A | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5102 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2024-06-05 | A | 000511 | 2024-06-05 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3014 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 0 | 131242-WST02-DS-M-0002-0 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DS-0002 | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-06-26 | 1 | 000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3015 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | E | 0011 | 0 | 131242-WST02-DS-E-0011-0 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DS-0011 | NA | "Data sheet for Autosampler" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-06-16 | 0 | 000511&&001378 | 2024-06-05, 2025-06-16 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3016 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | E | 0017 | 0 | 131242-WST02-DS-E-0017-0 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DS-0017 | NA | "Datasheet for Ammonia Analyser (SSN)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-12-08 | 0 | 000511&&001884 | 2024-06-05, 2025-12-08 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3017 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | I | 0003 | 0 | 131242-WST02-DS-I-0003-0 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DS-0003 | NA | " Data Sheets for Clean Gas System" && "ACMV Material and Catalogue submission (Building Services)- Poh Meng Engineering Pte Ltd" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-06-06 | 2 | 000511&&001234&&001298 | 2024-06-05, 2025-04-17, 2025-05-15, 2025-06-06 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3018 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | OM | I | 0001 | 0 | 131242-WST02-OM-I-0001-0 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-OM-0001 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2024-06-05 | 0 | 000511 | 2024-06-05 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3019 | 000511 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | OM | I | 0002 | 0 | 131242-WST02-OM-I-0002-0 | 2024-06-05 | SSN Blower GA drawings and Data Sheets | Rev 0: Not approved - Revise and Resubmit | 2024-07-04 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-OM-0002 | NA | "O&M Manual for Aeration Blower" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 56 | NAP | 2025-05-26 | 0 | 000511&&001318 | 2024-06-05, 2025-05-26 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
3020 | 000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 0002 | 1 | 131242-WST02-DS-M-0002-1 | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | Approved with Comments | 2024-12-12 | NO | Overdue |  | 131242-WST02-DS-0002 | NA | "Data Sheet for Public Address System (Box speaker, Paging horn speaker, Remote microphone/extension, Voice evacuation frame, Digital power amplifier module, Preamp matrix panel, Power supply manager, Monitor panel, Speaker selector, Line supervisory, Digital announcer, Program timer, EVC Digital Recorder, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for Electromagnetic Flowmeter" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-08 | 30 | AWC | 2025-06-26 | 1 | 000511&&000900&&001297 | 2024-06-05, 2024-10-25, 2024-12-13, 2025-05-15, 2025-06-26 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3021 | 000511 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DR | M | 0101 | B |  | 2024-10-25 | SSN Blower GA drawings and Data Sheets | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-24 | Approved with Comments | 2024-12-12 | NO | Overdue |  | 131242-WST02-DR-0101 | NA | "SSN Blower GA drawings and Data Sheets" | 2024-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-14 | 30 | AWC | 2024-10-25 | B | 000511 | 2024-10-25 | 01 | 1 | Approved with Comments | AWC | 2024-12-12 | Overdue | 0 | AWC | AWC
3022 | 000512 | 00 | Radha | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 0 | 131242-WSW41-MS-C-0012-0 | 2024-06-05 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-04 | 2024-06-27 | Approved with Comments | 2024-07-17 | YES | Resubmitted |  | 131242-WSW41-MS-0012 | NA | "MSRA, SWP for Bored Pile Hacking and Rectification works" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-25 | 22 | AWC | 2024-07-02 | 1 | 000512 | 2024-06-05, 2024-07-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3023 | 000512 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0012 | 1 | 131242-WSW41-MS-C-0012-1 | 2024-07-02 | MSRA, SWP for Bored Pile Hacking and Rectification works | Rev.1: Approved | 2024-07-22 | 2024-07-26 | Approved |  | YES | NA |  | 131242-WSW41-MS-0012 | NA | "MSRA, SWP for Bored Pile Hacking and Rectification works" | 2024-06-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-16 | 24 | APP | 2024-07-02 | 1 | 000512 | 2024-06-05, 2024-07-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3024 | 000513 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 0 | 131242-WST02-VI-I-0017-0 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | Not Approved | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-VI-0017 | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-26 | 46 | NAP | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3025 | 000513 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 1 | 131242-WST02-VI-I-0017-1 | 2024-09-16 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | Approved with Comments | 2024-11-28 | YES | Resubmitted |  | 131242-WST02-VI-0017 | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-30 | 53 | AWC | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3026 | 000513 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 2 | 131242-WST02-VI-I-0017-2 | 2025-01-10 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-30 | 2025-02-12 | Not Approved | 2025-03-04 | YES | Resubmitted |  | 131242-WST02-VI-0017 | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-24 | 33 | NAP | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3027 | 000513 | 03 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0017 | 3 | 131242-WST02-VI-I-0017-3 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0017 | NA | "Vendor Approval of SSN Package (Pressure Transmitters and Differential Pressure Transmitters)" | 2024-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 50 | AWC | 2025-03-17 | 3 | 000513 | 2024-06-06, 2024-09-16, 2025-01-10, 2025-03-17 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
3028 | 000514 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 0 | 131242-WST02-VI-I-0018-0 | 2024-06-06 | Vendor Approval of SSN Package (Pressure Switch) | Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | Approved with Comments | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-VI-0018 | NA | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-26 | 46 | AWC | 2025-05-20 | 2 | 000514 | 2024-06-06, 2025-03-17, 2025-05-20 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3029 | 000514 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 1 | 131242-WST02-VI-I-0018-1 | 2025-03-17 | Vendor Approval of SSN Package (Pressure Switch) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-VI-0018 | NA | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 50 | AWC | 2025-05-20 | 2 | 000514 | 2024-06-06, 2025-03-17, 2025-05-20 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3030 | 000514 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0018 | 2 | 131242-WST02-VI-I-0018-2 | 2025-05-20 | Vendor Approval of SSN Package (Pressure Switch) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-06-09 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-VI-0018 | NA | "Vendor Approval of SSN Package (Pressure Switch)" | 2024-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-03 | 134 | AWC | 2025-05-20 | 2 | 000514 | 2024-06-06, 2025-03-17, 2025-05-20 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
3031 | 000515 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 0 | 131242-WST02-VI-I-0019-0 | 2024-06-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-07-05 | 2024-07-22 | Not Approved | 2024-08-12 | YES | Resubmitted |  | 131242-WST02-VI-0019 | NA | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-26 | 46 | NAP | 2025-03-17 | 2 | 000515 | 2024-06-06, 2024-08-06, 2025-03-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3032 | 000515 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 1 | 131242-WST02-VI-I-0019-1 | 2024-08-06 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-27 | 2024-09-18 | Approved with Comments | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-VI-0019 | NA | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 43 | AWC | 2025-03-17 | 2 | 000515 | 2024-06-06, 2024-08-06, 2025-03-17 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3033 | 000515 | 02 | Yean Yee | EICA | NA | 131242 | WST02 | VI | I | 0019 | 2 | 131242-WST02-VI-I-0019-2 | 2025-03-17 | Vendor Approval of SSN Package (Temperature Transmitters) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-04 | 2025-05-06 | Approved with Comments | 2025-05-26 | NO | Overdue |  | 131242-WST02-VI-0019 | NA | "Vendor Approval of SSN Package (Temperature Transmitters)" | 2024-06-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-31 | 50 | AWC | 2025-03-17 | 2 | 000515 | 2024-06-06, 2024-08-06, 2025-03-17 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-26 | Overdue | 0 | AWC | AWC
3034 | 000516 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0040 | 0 | 131242-WSW41-CD-IM-0040-0 | 2024-06-07 | Submission Of BIM Coordination VCM Model (May-2024) | For Information | 2024-07-08 | 2024-06-22 | For Information |  | YES | NA |  | 131242-WSW41-CD-0040 | NA | "Submission Of BIM Coordination VCM Model (May-2024)" | 2024-06-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-06-27 | 15 | INF | 2024-06-07 | 0 | 000516 | 2024-06-07 | 00 | 1 | For Information | INF | 2024-07-11 | Overdue | 0 | INF | INF
3035 | 000517 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0024 | 0 | 131242-WSW41-MI-P-0024-0 | 2024-06-10 | Process & MEICA Meeting Minutes 0024_20240523 | Minutes of meeting are accepted for information. | 2024-07-09 | 2024-07-02 | For Information |  | YES | NA |  | 131242-WSW41-MI-0024 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-06-30 | 22 | INF | 2024-08-29 | 0 | 000517&&000561&&000684 | 2024-06-10, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3036 | 000518 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 0 | 131242-WSW41-MS-C-0013-0 | 2024-06-10 | MSRA, SWP for Plate Load Test | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-06-27 | Not Approved | 2024-07-17 | YES | Resubmitted |  | 131242-WSW41-MS-0013 | NA | "MSRA, SWP for Plate Load Test" | 2024-06-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 17 | NAP | 2024-07-04 | 1 | 000518 | 2024-06-10, 2024-07-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3037 | 000518 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | MS | C | 0013 | 1 | 131242-WSW41-MS-C-0013-1 | 2024-07-04 | MSRA, SWP for Plate Load Test | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-08-05 | Approved with Comments | 2024-08-26 | NO | Overdue |  | 131242-WSW41-MS-0013 | NA | "MSRA, SWP for Plate Load Test" | 2024-06-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-18 | 32 | AWC | 2024-07-04 | 1 | 000518 | 2024-06-10, 2024-07-04 | 00, 01 | 2 | Approved with Comments | AWC | 2024-08-23 | Overdue | 0 | AWC | AWC
3038 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | S | 8003_ST613_BCA | A | 131242-WST00-DR-S-8003_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue | Heng Peng to provide latest DGN & PDF drawing | 131242-WST00-DR-8003_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3039 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613_BCA | A | 131242-WST02-DR-S-1000_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1000_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3040 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613_BCA | A | 131242-WST02-DR-S-1006_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1006_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3041 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613_BCA | A | 131242-WST02-DR-S-1007_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1007_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3042 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613_BCA | A | 131242-WST02-DR-S-1008_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1008_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3043 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613_BCA | A | 131242-WST02-DR-S-1013_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1013_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3044 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613_BCA | A | 131242-WST02-DR-S-5005_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-5005_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3045 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613_BCA | A | 131242-WST02-DR-S-1014_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1014_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3046 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613_BCA | A | 131242-WST02-DR-S-1015_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1015_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3047 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613_BCA | A | 131242-WST02-DR-S-1016_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1016_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3048 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613_BCA | A | 131242-WST02-DR-S-1017_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1017_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3049 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613_BCA | A | 131242-WST02-DR-S-1018_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1018_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3050 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613_BCA | A | 131242-WST02-DR-S-1019_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1019_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3051 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613_BCA | A | 131242-WST02-DR-S-1020_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1020_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3052 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613_BCA | A | 131242-WST02-DR-S-1021_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1021_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3053 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613_BCA | A | 131242-WST02-DR-S-1022_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-1022_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3054 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613_BCA | A | 131242-WST02-DR-S-3005_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-3005_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3055 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613_BCA | A | 131242-WST02-DR-S-3008_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-3008_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3056 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613_BCA | A | 131242-WST02-DR-S-3009_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-3009_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3057 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613_BCA | A | 131242-WST02-DR-S-7002_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-7002_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3058 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613_BCA | A | 131242-WST02-DR-S-7003_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-7003_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3059 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613_BCA | A | 131242-WST02-DR-S-7004_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-7004_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3060 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613_BCA | A | 131242-WST02-DR-S-7005_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-7005_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3061 | 000519 | 00 | Zora/ HP | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613_BCA | A | 131242-WST02-DR-S-5006_ST613_BCA-A | 2024-06-10 | BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building | Rev.0: Approved with Comments. Please refer to comment sheet for resubmission. | 2024-07-09 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WST02-DR-5006_ST613_BCA | NA | "BCA Approval of ST613 _ Sub Structure of Minor buildings and Super Structure of Elec Building " | 2024-06-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-06-30 | 21 | AWC | 2024-06-10 | A | 000519 | 2024-06-10 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3062 | 000520 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0013 | 0 | 131242-WSW41-RT-PM-0013-0 | 2024-06-12 | C4B Monthly Progress Report Number No.13 (05 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-07-11 | 2024-06-28 | Approved with Comments | 2024-07-18 | NO | Overdue |  | 131242-WSW41-RT-0013 | NA | "C4B Monthly Progress Report Number No.13 (05 24)" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Quarterly Safety Review Follow Up on SSN RC Works" | 2024-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-02 | 16 | AWC | 2025-07-01 | 1 | 000520&&000852&&001420 | 2024-06-12, 2024-11-28, 2025-07-01 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3063 | 000521 | 00 | David | Mech | NA | 131242 | WSW41 | SP | M | 8002 | 0 | 131242-WSW41-SP-M-8002-0 | 2024-06-12 | Datasheet for Thermal Insulation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-11 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue | In Progress | 131242-WSW41-SP-8002 | NA | "Datasheet for Thermal Insulation" | 2024-06-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-02 | 78 | AWC | 2024-06-12 | 0 | 000521 | 2024-06-12 | 00 | 1 | Approved with Comments | AWC | 2024-09-18 | Overdue | 0 | AWC | AWC
3064 | 000522 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 0 | 131242-WSW41-VI-C-0016-0 | 2024-06-13 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-12 | 2024-06-28 | Not Approved | 2024-07-18 | YES | Resubmitted |  | 131242-WSW41-VI-0016 | NA | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-03 | 15 | NAP | 2024-07-22 | 2 | 000522 | 2024-06-13, 2024-07-04, 2024-07-22 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
3065 | 000522 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 1 | 131242-WSW41-VI-C-0016-1 | 2024-07-04 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-17 | Not Approved | 2024-08-06 | YES | Resubmitted |  | 131242-WSW41-VI-0016 | NA | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-18 | 13 | NAP | 2024-07-22 | 2 | 000522 | 2024-06-13, 2024-07-04, 2024-07-22 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
3066 | 000522 | 02 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0016 | 2 | 131242-WSW41-VI-C-0016-2 | 2024-07-22 | Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) | R2: Approved | 2024-08-12 | 2024-08-12 | Approved |  | YES | NA |  | 131242-WSW41-VI-0016 | NA | "Vendor Approval for Precast Chamber Ring (HDPE Lining), Precast Slab, Netting, Manhole Cover & Frame - (CPP) " | 2024-06-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 21 | APP | 2024-07-22 | 2 | 000522 | 2024-06-13, 2024-07-04, 2024-07-22 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
3067 | 000523 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | CL | S | 0006 | 0 | 131242-WSW41-CL-S-0006-0 | 2024-06-14 | Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94 | Rev.0: Approved | 2024-07-15 | 2024-06-28 | Approved |  | YES | NA |  | 131242-WSW41-CL-0006 | NA | "Proposed Drop Height Calculation for PDA test Bored Pile ST615-P156,P118,P135 & ST616-TP12,TP38,TP68,P94" | 2024-06-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-04 | 14 | APP | 2024-06-14 | 0 | 000523 | 2024-06-14 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
3068 | 000524 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0032 | 0 | 131242-WSW41-LT-PM-0032-0 | 2024-06-14 | NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source | Refer to S.O. Correspondence No.000213 dated 23-Aug-2024. | 2024-07-15 | 2024-08-26 | For Information |  | YES | NA |  | 131242-WSW41-LT-0032 | NA | "NOTICE Extension of Time and Cost for C4B/Relocation of the Power Source " | 2024-06-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-07-04 | 73 | INF | 2024-06-14 | 0 | 000524 | 2024-06-14 | 00 | 1 | For Information | INF | 2024-09-13 | Overdue | 0 | INF | INF
3069 | 000525 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0014 | 0 | 131242-WSW41-MS-C-0014-0 | 2024-06-18 | MSRA & SWP of Civil & Structure Work (Substructure) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WSW41-MS-0014 | NA | "MSRA & SWP of Civil & Structure Work (Substructure)" && "MSRA for Protection Relay Replacement Works " | 2024-06-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-08 | 13 | AWC | 2025-05-04 | 0 | 000525&&001266 | 2024-06-18, 2025-05-04 | 00 | 2 | Rejected | REJ |  |  | 0 | AWC | AWC
3070 | 000526 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0015 | 0 | 131242-WSW41-MS-C-0015-0 | 2024-06-18 | MSRA & SWP of Mobilization & Demobilization of Machinery | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-16 | 2024-07-01 | Approved with Comments | 2024-07-19 | NO | Overdue |  | 131242-WSW41-MS-0015 | NA | "MSRA & SWP of Mobilization & Demobilization of Machinery" | 2024-06-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-08 | 13 | AWC | 2024-06-18 | 0 | 000526 | 2024-06-18 | 00 | 1 | Approved with Comments | AWC | 2024-07-19 | Overdue | 0 | AWC | AWC
3071 | 000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A | 131242-WSB01-DR-BH-1000-A | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSB01-DR-1000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-09 | 54 | NAP | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3072 | 000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 3000 | A | 131242-WSB01-DR-BH-3000-A | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSB01-DR-3000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-09 | 54 | NAP | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3073 | 000527 | 00 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 5000 | A | 131242-WSB01-DR-BH-5000-A | 2024-06-19 | THP-Air Compressor's Ducting Layout | Rev 0: Not approved - Revise and Resubmit | 2024-07-17 | 2024-08-12 | Not Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSB01-DR-5000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-09 | 54 | NAP | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3074 | 000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 1000 | A.1 | 131242-WSB01-DR-BH-1000-A.1 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | Approved with Comments |  | YES | NA |  | 131242-WSB01-DR-1000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-28 | 6 | AWC | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
3075 | 000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 3000 | A.1 | 131242-WSB01-DR-BH-3000-A.1 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | Approved with Comments |  | YES | NA |  | 131242-WSB01-DR-3000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-28 | 6 | AWC | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
3076 | 000527 | 01 | Kyaw Myo | BS | NA | 131242 | WSB01 | DR | BH | 5000 | A.1 | 131242-WSB01-DR-BH-5000-A.1 | 2025-01-14 | THP-Air Compressor's Ducting Layout | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-03 | 2025-01-20 | Approved with Comments |  | YES | NA |  | 131242-WSB01-DR-5000 | NA | "Milestone 2 THP Compressed Air System" && "THP-Air Compressor's Ducting Layout" | 2024-06-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-28 | 6 | AWC | 2025-01-14 | A.1 | 000302&&000527 | 2024-06-19, 2024-10-18, 2025-01-14 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
3077 | 000528 | 00 | Balaji | EICA | NA | 131242 | WSW41 | VI | I | 0002 | 0 | 131242-WSW41-VI-I-0002-0 | 2024-06-19 | Vendor Approval of Communication Cable (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-07-17 | 2024-08-05 | Approved with Comments | 2024-08-26 | NO | Overdue |  | 131242-WSW41-VI-0002 | NA | "Preliminary Design and Vendor Approval of Blower (Aerzen)" && "Preliminary Design and Vendor Approval of Blower (Robuschi)" && "Vendor Approval of CONSAAS Audit (ACE EHS)" && "Vendor Approval of Communication Cable (Keystone)" && "Vendor Approval of ERSS Works (Singlee)" && "Vendor Approval of Piling Subcontractorr-Asia Piling Co Pte. Ltd." | 2023-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-03 | 47 | AWC | 2024-07-09 | 0 | 000084&&000135&&000317&&000450&&000528 | 2023-08-28, 2023-10-23, 2023-12-26, 2024-02-20, 2024-06-19, 2024-06-25, 2024-07-09 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3078 | 000529 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0025 | 0 | 131242-WSW41-MI-P-0025-0 | 2024-06-20 | Process & MEICA Meeting Minutes 0025_20240606 | For Information | 2024-07-18 | 2024-08-08 | For Information |  | YES | NA |  | 131242-WSW41-MI-0025 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-10 | 49 | INF | 2024-08-29 | 0 | 000529&&000561&&000684 | 2024-06-20, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3079 | 000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0001_ST606 | C | 131242-WST00-DR-S-0001_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST00-DR-0001_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3080 | 000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0002_ST606 | C | 131242-WST00-DR-S-0002_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST00-DR-0002_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3081 | 000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 0003_ST606 | C | 131242-WST00-DR-S-0003_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST00-DR-0003_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3082 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST606 | C | 131242-WST02-DR-S-1006_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-1006_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3083 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST606 | C | 131242-WST02-DR-S-1007_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-1007_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3084 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST606 | C | 131242-WST02-DR-S-1008_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-1008_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3085 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3000_ST606 | C | 131242-WST02-DR-S-3000_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-3000_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3086 | 000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 5001_ST606 | C | 131242-WST00-DR-S-5001_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST00-DR-5001_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-11 | 52 | AWC | 2024-06-21 | C | 000530 | 2024-06-21 | 00 | 1 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3087 | 000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 5002_ST606 | C | 131242-WST00-DR-S-5002_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST00-DR-5002_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-11 | 52 | AWC | 2024-06-21 | C | 000530 | 2024-06-21 | 00 | 1 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3088 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7000_ST606 | C | 131242-WST02-DR-S-7000_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-7000_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3089 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7001_ST606 | C | 131242-WST02-DR-S-7001_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-7001_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3090 | 000530 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST606 | C | 131242-WST02-DR-S-7002_ST606-C | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST02-DR-7002_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" && "ST606 : SSN Overall Sub-Structure Drawings " | 2023-09-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 52 | AWC | 2024-06-21 | C | 000110&&000530 | 2023-09-29, 2024-06-21 | 00 | 2 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3091 | 000530 | 00 | Zora | CSA | NA | 131242 | WST00 | DR | S | 8002_ST606 | A | 131242-WST00-DR-S-8002_ST606-A | 2024-06-21 | IFC of ST606_SSN Main Water Tanks - Sub Structure Details | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-08-12 | Approved with Comments | 2024-08-30 | NO | Overdue |  | 131242-WST00-DR-8002_ST606 | NA | "IFC of ST606_SSN Main Water Tanks - Sub Structure Details" | 2024-06-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-11 | 52 | AWC | 2024-06-21 | A | 000530 | 2024-06-21 | 00 | 1 | Approved with Comments | AWC | 2024-08-30 | Overdue | 0 | AWC | AWC
3092 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | D | 131242-WST00-DR-G-0001_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-0001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3093 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | D | 131242-WST00-DR-G-0002_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-0002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3094 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | D | 131242-WST00-DR-G-1000_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-1000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3095 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1001_ST601 | D | 131242-WST00-DR-G-1001_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-1001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
3096 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1002_ST601 | D | 131242-WST00-DR-G-1002_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-1002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
3097 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1003_ST601 | D | 131242-WST00-DR-G-1003_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-1003_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-06-21 | D | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
3098 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | D | 131242-WST00-DR-G-1004_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-1004_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3099 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 5100_ST601 | D | 131242-WST00-DR-G-5100_ST601-D | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-5100_ST601 | NA | "IFC of ST601 – ERSS < 4m " | 2024-06-21 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-11 | 14 | AWC | 2024-06-21 | D | 000531 | 2024-06-21 | 00 | 1 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
3100 | 000531 | 00 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | D.1 | 131242-WST00-DR-G-8000_ST601-D.1 | 2024-06-21 | IFC of ST601 – ERSS < 4m | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-07-19 | 2024-07-05 | Approved with Comments | 2024-07-25 | YES | Resubmitted |  | 131242-WST00-DR-8000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-05 | 14 | AWC | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3101 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0001_ST601 | E | 131242-WST00-DR-G-0001_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-12 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-0001_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-05 | 22 | APP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
3102 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 0002_ST601 | E | 131242-WST00-DR-G-0002_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-0002_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-05 | 22 | APP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
3103 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1000_ST601 | E | 131242-WST00-DR-G-1000_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-1000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-05 | 22 | APP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
3104 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 1004_ST601 | E | 131242-WST00-DR-G-1004_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-1004_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-05 | 22 | APP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
3105 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3000_ST601 | E | 131242-WST00-DR-G-3000_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-3000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-05 | 22 | APP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-07-22 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | APP | APP
3106 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3001_ST601 | E | 131242-WST00-DR-G-3001_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-3001_ST601 | NA | "IFC of ST601 – ERSS < 4m " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-11 | 22 | APP | 2024-07-22 | E | 000531 | 2024-07-22 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
3107 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3002_ST601 | E | 131242-WST00-DR-G-3002_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-3002_ST601 | NA | "IFC of ST601 – ERSS < 4m " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-11 | 22 | APP | 2024-07-22 | E | 000531 | 2024-07-22 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
3108 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 3003_ST601 | E | 131242-WST00-DR-G-3003_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-3003_ST601 | NA | "IFC of ST601 – ERSS < 4m " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-11 | 22 | APP | 2024-07-22 | E | 000531 | 2024-07-22 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
3109 | 000531 | 01 | Zora/ HP | CSA | NA | 131242 | WST00 | DR | G | 8000_ST601 | E | 131242-WST00-DR-G-8000_ST601-E | 2024-07-22 | IFC of ST601 – ERSS < 4m | Rev.1: Approved | 2024-08-20 | 2024-08-13 | Approved |  | YES | NA |  | 131242-WST00-DR-8000_ST601 | NA | "IFC of ST601 – ERSS < 4m " && "ST601 – ERSS Design < 4m Depth" | 2023-12-22 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-05 | 22 | APP | 2024-07-22 | E | 000248&&000531 | 2023-12-22, 2024-02-24, 2024-04-15, 2024-06-21, 2024-07-22 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
3110 | 000532 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0009 | 0 | 131242-WSW41-QA-C-0009-0 | 2024-06-25 | Monthly Concrete Cube Records for Structural works (02 24) | For Information | 2024-07-23 | 2024-07-05 | For Information |  | YES | NA |  | 131242-WSW41-QA-0009 | NA | "Inspection and Test Plan for Installation of Fire Hose reel, Fire Hydrant (Pipe Press line, Ductile iron pipe and Equipment Installation)" && "Monthly Concrete Cube Records for Structural works (02 24)" | 2024-06-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-15 | 10 | INF | 2025-06-18 | 0 | 000532&&001387 | 2024-06-25, 2025-06-18 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
3111 | 000533 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 0 | 131242-WSW41-PC-W-0012-0 | 2024-06-25 | Payment Claim No.12 | Rev (0): Rejected due to some PDA test were done in June 2024. | 2024-07-23 | 2024-06-28 | Rejected | 2024-07-18 | YES | Resubmitted |  | 131242-WSW41-PC-0012 | NA | "Payment Claim No.12" | 2024-06-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-15 | 3 | REJ | 2024-06-28 | 1 | 000533 | 2024-06-25, 2024-06-28 | 00, 01 | 2 | Approved | APP |  |  | 0 | REJ | REJ
3112 | 000533 | 01 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0012 | 1 | 131242-WSW41-PC-W-0012-1 | 2024-06-28 | Payment Claim No.12 | Rev (1): Approved, refer to SO Correspondence No. 0181 dated 2 July 2024. | 2024-07-18 | 2024-11-07 | Approved |  | YES | NA |  | 131242-WSW41-PC-0012 | NA | "Payment Claim No.12" | 2024-06-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-12 | 132 | APP | 2024-06-28 | 1 | 000533 | 2024-06-25, 2024-06-28 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3113 | 000534 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | P | 6601 | 0 | 131242-WST02-DR-P-6601-0 | 2024-06-26 | SSN Blower P&ID | Rev 0: Not approved - Revise and Resubmit | 2024-07-24 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-6601 | NA | "SSN Blower P&ID" | 2024-06-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-16 | 35 | NAP | 2024-06-26 | 0 | 000534 | 2024-06-26 | 00 | 1 | Not Approved | NAP | 2024-08-20 | Overdue | 0 | NAP | NAP
3114 | 000534 | 01 | Qili | Process | NA | 131242 | NA | NA | NA | Cmt Sheet Reply S000534 | 0 | 131242----Cmt Sheet Reply S000534- | 2024-08-15 | SSN Blower P&ID | Rev 1: Rejected | 2024-09-04 | 2024-09-06 | Rejected |  | YES | NA |  | 131242-NA-NA-Cmt Sheet Reply S000534 | NA | "SSN Blower P&ID" | 2024-08-15 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-04 | 22 | REJ | 2024-08-15 | 0 | 000534 | 2024-08-15 | 01 | 1 | Rejected | REJ | 2024-09-26 | Overdue | 0 | REJ | REJ
3115 | 000535 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | BQ | P | 0003 | 0 | 131242-WSD11-BQ-P-0003-0 | 2024-06-26 | THP Line List | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-24 | 2024-08-29 | Approved with Comments | 2024-09-18 | NO | Overdue |  | 131242-WSD11-BQ-0003 | NA | "THP Line List" && "THP Listing of Interface Points" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 64 | AWC | 2025-07-21 | 1 | 000321&&000535 | 2024-02-23, 2024-06-26, 2025-07-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3116 | 000536 | 00 | Zora/ HP | CSA | NA | 131242 | WSD11 | DR | S | 5301 | B | 131242-WSD11-DR-S-5301-B | 2024-06-26 | IFC of Compressed Air System - Anchor Bolts Details & Plinth Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-24 | 2024-07-05 | Approved with Comments | 2024-07-25 | NO | Overdue | Zora obtain QP endorsement on the drawing and Heng Peng to provide latest DGN and Tenwit (Kalaban) updating the minor comments | 131242-WSD11-DR-5301 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "IFC of Compressed Air System - Anchor Bolts Details & Plinth Details" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-10 | 9 | AWC | 2024-06-26 | B | 000423&&000536 | 2024-06-05, 2024-06-26 | 00, 01 | 2 | Approved with Comments | AWC | 2024-07-25 | Overdue | 0 | AWC | AWC
3117 | 000537 | 00 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 0 | 131242-WSD11-CL-M-0010-0 | 2024-06-27 | Design Calculation for Instrument Air Receiver | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-07-25 | 2024-08-06 | Approved with Comments | 2024-08-27 | YES | Resubmitted |  | 131242-WSD11-CL-0010 | NA | "Design Calculation for Instrument Air Receiver" && "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-06-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-17 | 40 | AWC | 2024-09-03 | 1 | 000537&&000663 | 2024-06-27, 2024-08-20, 2024-09-03 | 00, 01 | 3 | Approved | APP |  |  | 0 | AWC | AWC
3118 | 000537 | 01 | Yibo | Mech | NA | 131242 | WSD11 | CL | M | 0010 | 1 | 131242-WSD11-CL-M-0010-1 | 2024-09-03 | Design Calculation for Instrument Air Receiver | Rev 1: Approved | 2024-09-23 | 2024-09-05 | Approved |  | YES | NA |  | 131242-WSD11-CL-0010 | NA | "Design Calculation for Instrument Air Receiver" && "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-06-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-17 | 2 | APP | 2024-09-03 | 1 | 000537&&000663 | 2024-06-27, 2024-08-20, 2024-09-03 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
3119 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009_ST607_BCA | A | 131242-WST02-DR-S-1009_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-1009_ST607_BCA | NA | "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-07-01 | A | 000538 | 2024-07-01 | 00 | 1 | Not Approved | NAP | 2024-08-02 | Overdue | 0 | NAP | NAP
3120 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-S-1010_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-1010_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3121 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | A | 131242-WST02-DR-S-1011_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-1011_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3122 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | A | 131242-WST02-DR-S-1012_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-1012_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3123 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | A | 131242-WST02-DR-S-3002_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-3002_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3124 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | A | 131242-WST02-DR-S-7003_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-7003_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3125 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | A | 131242-WST02-DR-S-7004_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-7004_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3126 | 000538 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | A | 131242-WST02-DR-S-8003_ST607_BCA-A | 2024-07-01 | BCA Submission of ST607 – Super Structure of SSN Main Water Tank | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-07-29 | 2024-07-15 | Not Approved | 2024-08-02 | NO | Overdue |  | 131242-WST02-DR-8003_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-21 | 14 | NAP | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF |  |  | 0 | NAP | NAP
3127 | 000539 | 00 | Mohan | QAQC | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-C-0004-0 | 2024-07-02 | Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-07-30 | 2024-07-15 | Approved with Comments | 2024-08-02 | NO | Overdue |  | 131242-WST02-RT-0004 | NA | "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " && "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" | 2024-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-22 | 13 | AWC | 2024-07-15 | 0 | 000539&&000567 | 2024-07-02, 2024-07-15 | 00 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3128 | 000540 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-C-0005-0 | 2024-07-02 | Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616) | For Information | 2024-07-30 | 2024-07-15 | For Information |  | YES | NA |  | 131242-WST02-RT-0005 | NA | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " && "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" | 2024-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-22 | 13 | INF | 2025-07-24 | 0 | 000540&&000568&&001524 | 2024-07-02, 2024-07-15, 2025-07-24 | 00 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
3129 | 000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | A | 131242-WST02-DR-M-5103-A | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5103 | NA | "Blower Encapsulation GA" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-23 | 28 | NAP | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3130 | 000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | A | 131242-WST02-DR-M-5104-A | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5104 | NA | "Blower Encapsulation GA" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-23 | 28 | NAP | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3131 | 000541 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | A | 131242-WST02-DR-M-5105-A | 2024-07-03 | Blower Encapsulation GA | Rev 0: Not approved - Revise and Resubmit | 2024-07-31 | 2024-07-31 | Not Approved | 2024-08-21 | YES | Resubmitted |  | 131242-WST02-DR-5105 | NA | "Blower Encapsulation GA" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-23 | 28 | NAP | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3132 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | B | 131242-WST02-DR-M-5103-B | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-5103 | NA | "Blower Encapsulation GA" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 64 | AWC | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3133 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | B | 131242-WST02-DR-M-5104-B | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-5104 | NA | "Blower Encapsulation GA" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 64 | AWC | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3134 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | B | 131242-WST02-DR-M-5105-B | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-5105 | NA | "Blower Encapsulation GA" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-30 | 64 | AWC | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3135 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5106 | A | 131242-WST02-DR-M-5106-A | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-5106 | NA | "Blower Encapsulation GA" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 64 | AWC | 2025-06-06 | B | 000541 | 2025-01-16, 2025-06-06 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3136 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5107 | A | 131242-WST02-DR-M-5107-A | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-5107 | NA | "Blower Encapsulation GA" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 64 | AWC | 2025-06-06 | B | 000541 | 2025-01-16, 2025-06-06 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3137 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5108 | A | 131242-WST02-DR-M-5108-A | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DR-5108 | NA | "Blower Encapsulation GA" | 2025-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 64 | AWC | 2025-06-06 | B | 000541 | 2025-01-16, 2025-06-06 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3138 | 000541 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 0031 | 0 | 131242-WST02-DS-M-0031-0 | 2025-01-16 | Blower Encapsulation GA | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-05 | 2025-03-21 | Approved with Comments | 2025-04-10 | YES | Resubmitted |  | 131242-WST02-DS-0031 | NA | "Blower Encapsulation GA" | 2025-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-05 | 64 | AWC | 2025-01-16 | 0 | 000541 | 2025-01-16 | 01 | 1 | Approved with Comments | AWC | 2025-04-10 | Overdue | 0 | AWC | AWC
3139 | 000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5103 | D | 131242-WST02-DR-M-5103-D | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-DR-5103 | NA | "Blower Encapsulation GA" | 2024-07-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 41 | AWC | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
3140 | 000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5104 | D | 131242-WST02-DR-M-5104-D | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-DR-5104 | NA | "Blower Encapsulation GA" | 2024-07-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 41 | AWC | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
3141 | 000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5105 | D | 131242-WST02-DR-M-5105-D | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-DR-5105 | NA | "Blower Encapsulation GA" | 2024-07-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 41 | AWC | 2025-06-06 | D | 000541 | 2024-07-03, 2025-01-16, 2025-06-06 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
3142 | 000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5106 | B | 131242-WST02-DR-M-5106-B | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-DR-5106 | NA | "Blower Encapsulation GA" | 2025-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 41 | AWC | 2025-06-06 | B | 000541 | 2025-01-16, 2025-06-06 | 01, 02 | 2 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
3143 | 000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5107 | B | 131242-WST02-DR-M-5107-B | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-DR-5107 | NA | "Blower Encapsulation GA" | 2025-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 41 | AWC | 2025-06-06 | B | 000541 | 2025-01-16, 2025-06-06 | 01, 02 | 2 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
3144 | 000541 | 02 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5108 | B | 131242-WST02-DR-M-5108-B | 2025-06-06 | Blower Encapsulation GA | Rev 2: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-26 | 2025-07-17 | Approved with Comments | 2025-08-06 | NO | Overdue |  | 131242-WST02-DR-5108 | NA | "Blower Encapsulation GA" | 2025-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-20 | 41 | AWC | 2025-06-06 | B | 000541 | 2025-01-16, 2025-06-06 | 01, 02 | 2 | Approved with Comments | AWC | 2025-08-06 | Overdue | 0 | AWC | AWC
3145 | 000542 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0026 | A | 131242-WSW41-MI-P-0026-A | 2024-07-03 | Process & MEICA Meeting Minutes 0026_20240624 | Rev 0: For Information | 2024-07-31 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-MI-0026 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-23 | 57 | INF | 2024-08-29 | 0 | 000542&&000561&&000684 | 2024-07-03, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3146 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7700 | C | 131242-WST02-DR-E-7700-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7700 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3147 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7701 | C | 131242-WST02-DR-E-7701-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7701 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3148 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7702 | C | 131242-WST02-DR-E-7702-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7702 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3149 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7703 | C | 131242-WST02-DR-E-7703-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7703 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3150 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7704 | C | 131242-WST02-DR-E-7704-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7704 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3151 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7705 | C | 131242-WST02-DR-E-7705-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7705 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3152 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7706 | C | 131242-WST02-DR-E-7706-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7706 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3153 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7707 | C | 131242-WST02-DR-E-7707-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7707 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3154 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7708 | C | 131242-WST02-DR-E-7708-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7708 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3155 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7709 | C | 131242-WST02-DR-E-7709-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7709 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3156 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7710 | C | 131242-WST02-DR-E-7710-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7710 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3157 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7711 | C | 131242-WST02-DR-E-7711-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7711 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3158 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7712 | C | 131242-WST02-DR-E-7712-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7712 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3159 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7713 | C | 131242-WST02-DR-E-7713-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7713 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3160 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7714 | C | 131242-WST02-DR-E-7714-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7714 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3161 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7715 | C | 131242-WST02-DR-E-7715-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7715 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3162 | 000543 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DR | E | 7716 | C | 131242-WST02-DR-E-7716-C | 2024-07-04 | Blower Circuit Diagram | Rev 0; Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WST02-DR-7716 | NA | "Blower Circuit Diagram" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 117 | AWC | 2024-07-04 | C | 000543 | 2024-07-04 | 00 | 1 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3163 | 000544 | 00 | Keith | PMT | NA | 131242 | WSW41 | LT | PM | 0034 | 0 | 131242-WSW41-LT-PM-0034-0 | 2024-07-04 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Please refer to comment sheet for resubmission. | 2024-08-01 | 2024-07-16 | For Information | 2024-08-05 | YES | Resubmitted |  | 131242-WSW41-LT-0034 | NA | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | 2024-07-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 12 | INF | 2024-07-04 | 0 | 000544 | 2024-07-04 | 00 | 1 | For Information | INF | 2024-08-05 | Overdue | 0 | INF | INF
3164 | 000544 | 01 | Yuen Fatt | Project | NA | 131242 | NA | LT | PM | 9999 | 0 | 131242--LT-PM-- | 2024-08-03 | Request Owner’s Approval for Use of Linabond Waterproofing Materials | Rev.1: Please refer to comment sheet for resubmission. | 2024-08-23 | 2024-08-19 | Not Approved | 2024-09-06 | NO | Overdue | To change the title : Request Owner’s Approval for Use of Linabond Concrete Corrosion Protection Material | 131242-NA-LT-9999 | NA | "Request Owner’s Approval for Use of Linabond Waterproofing Materials" | 2024-08-03 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-23 | 16 | NAP | 2024-08-03 | 0 | 000544 | 2024-08-03 | 01 | 1 | Not Approved | NAP | 2024-09-06 | Overdue | 0 | NAP | NAP
3165 | 000545 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | RT | C | 0006 | 0 | 131242-WST02-RT-C-0006-0 | 2024-07-04 | Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615) | Approved | 2024-08-01 | 2024-07-17 | Approved |  | YES | NA |  | 131242-WST02-RT-0006 | NA | "SSN Hazardous Area Assessment Report" && "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" && "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-24 | 13 | APP | 2025-11-20 | 0 | 000545&&000772&&001856 | 2024-07-04, 2024-10-23, 2025-11-20 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
3166 | 000546 | 00 | Theint Theint | Project | NA | 131242 | WSW41 | VI | S | 0005 | 0 | 131242-WSW41-VI-S-0005-0 | 2024-07-05 | Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-08-02 | 2024-07-18 | Not Approved | 2024-08-07 | NO | Overdue |  | 131242-WSW41-VI-0005 | NA | "Preliminary Design and Vendor Apporval document for SSN Aeration Blower MCP and THP PLC/RIP Panels (Ener Tech)" && "Preliminary Design and Vendor Approval of Mixer " && "Vendor Approval of Concrete Supplier-Alliance" && "Vendor Approval of Fireseal Contractor (B3 Engineering Pte Ltd)" && "Vendor Approval of Jet Grouting Contractor (Ambuilder Engineering Pte. Ltd.)" | 2023-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-19 | 13 | NAP | 2025-03-25 | 0 | 000059&&000229&&000546&&000816&&001164 | 2023-08-01, 2023-12-05, 2024-07-05, 2024-08-20, 2024-11-16, 2025-03-25 | 00, 01 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3167 | 000547 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0002 | 0 | 131242-WSW41-PO-E-0002-0 | 2024-07-08 | Unpriced PO for Cables (Keystone) | For Information | 2024-08-05 | 2024-08-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0002 | NA | "Unpriced PO for Ball Valve (OVS Engineering)" && "Unpriced PO for Cables (Keystone)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-28 | 28 | INF | 2025-08-22 | 0 | 000547&&001501&&001513 | 2024-07-08, 2025-07-22, 2025-08-22 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3168 | 000548 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0005 | 0 | 131242-WSW41-PO-M-0005-0 | 2024-07-08 | Unpriced PO for Sludge Pump (Netzsch) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-PO-0005 | NA | "Unpriced PO for Cable Raceway (United-U Li) " && "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" && "Unpriced PO for Sludge Pump (Netzsch) " | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-28 | 52 | INF | 2025-08-01 | 0 | 000548&&001070&&001504&&001516 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
3169 | 000549 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0006 | 0 | 131242-WSW41-PO-M-0006-0 | 2024-07-08 | Unpriced PO for cPVC Pipes (George Fischer) | Rev 0: For Information | 2024-08-05 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-PO-0006 | NA | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" && "Unpriced PO for cPVC Pipes (George Fischer)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-28 | 52 | INF | 2025-08-01 | 0 | 000549&&001071&&001505&&001517 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
3170 | 000550 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041-0 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jun-2024) | For Information | 2024-08-05 | 2024-07-23 | For Information | 2024-08-13 | YES | Resubmitted |  | 131242-WSW41-CD-0041 | NA | "Submission Of BIM Coordination VCM Model (Jul-2024)" && "Submission Of BIM Coordination VCM Model (Jun-2024)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-28 | 15 | INF | 2024-08-12 | 0 | 000550&&000631 | 2024-07-08, 2024-08-12 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3171 | 000551 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | G | 0002 | 0 | 131242-WSW41-MS-G-0002-0 | 2024-07-08 | MSRA & SWP for Pre-Augering Work | Rev.0: Approved | 2024-08-05 | 2024-08-08 | Approved |  | YES | NA |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-28 | 31 | APP | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | APP | APP
3172 | 000552 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 0 | 131242-WSW41-RT-PM-0014-0 | 2024-07-09 | C4B Monthly Progress Report Number No.14 (06 24) | Rejected as requested by Contractor | 2024-08-06 | 2024-07-09 | Rejected | 2024-07-29 | YES | Resubmitted |  | 131242-WSW41-RT-0014 | NA | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" && "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 0 | REJ | 2025-01-03 | 0 | 000552&&000948 | 2024-07-09, 2024-07-13, 2025-01-03 | 00, 01 | 3 | For Information | INF |  |  | 0 | REJ | REJ
3173 | 000552 | 01 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0014 | 1 | 131242-WSW41-RT-PM-0014-1 | 2024-07-13 | C4B Monthly Progress Report Number No.14 (06 24) | Rev. 1 - Approved with comments (see attached comment sheet) | 2024-08-01 | 2024-07-30 | Approved with Comments | 2024-08-20 | NO | Overdue |  | 131242-WSW41-RT-0014 | NA | "Bored Piling Pile Eccentricity Reports (ECC 19 & 20)" && "C4B Monthly Progress Report Number No.14 (06 24)" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-27 | 17 | AWC | 2025-01-03 | 0 | 000552&&000948 | 2024-07-09, 2024-07-13, 2025-01-03 | 00, 01 | 3 | For Information | INF |  |  | 0 | AWC | AWC
3174 | 000553 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 0 | 131242-WST02-CL-P-0007-0 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | Approved with Comments | 2024-09-02 | YES | Resubmitted |  | 131242-WST02-CL-0007 | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 35 | AWC | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3175 | 000553 | 00 | Qili | Process | NA | 131242 | WST02 | DS | I | 0004 | 0 | 131242-WST02-DS-I-0004-0 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | Approved with Comments | 2024-09-02 | YES | Resubmitted |  | 131242-WST02-DS-0004 | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 35 | AWC | 2025-04-25 | 0 | 000553&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
3176 | 000553 | 00 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018-0 | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | Approved with Comments | 2024-09-02 | YES | Resubmitted |  | 131242-WST02-DS-0018 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Pressure Gauge" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 35 | AWC | 2025-08-22 | 0 | 000553&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3177 | 000553 | 00 | Qili | Process | NA | 131242 | WST02 | DR | I | 5020 | A | 131242-WST02-DR-I-5020-A | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | Approved with Comments | 2024-09-02 | YES | Resubmitted |  | 131242-WST02-DR-5020 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 35 | AWC | 2024-11-02 | A | 000553 | 2024-07-09, 2024-11-02 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3178 | 000553 | 00 | Qili | Process | NA | 131242 | WST02 | DR | M | 5021 | A | 131242-WST02-DR-M-5021-A | 2024-07-09 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-08-06 | 2024-08-13 | Approved with Comments | 2024-09-02 | YES | Resubmitted |  | 131242-WST02-DR-5021 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 35 | AWC | 2025-03-06 | A | 000553 | 2024-07-09, 2024-11-02, 2025-03-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3179 | 000553 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 1 | 131242-WST02-CL-P-0007-1 | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-21 | 2024-11-19 | Approved with Comments | 2024-12-09 | YES | Resubmitted |  | 131242-WST02-CL-0007 | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-16 | 17 | AWC | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3180 | 000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0025 | A | 131242-WST02-DR-M-0025-A | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | Approved with Comments | 2024-12-09 | YES | Resubmitted |  | 131242-WST02-DR-0025 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 17 | AWC | 2024-11-02 | A | 000553 | 2024-11-02 | 01 | 1 | Approved with Comments | AWC | 2024-12-09 | Overdue | 0 | AWC | AWC
3181 | 000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | M | 0026 | A | 131242-WST02-DR-M-0026-A | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | Approved with Comments | 2024-12-09 | YES | Resubmitted |  | 131242-WST02-DR-0026 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-11-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 17 | AWC | 2024-11-02 | A | 000553 | 2024-11-02 | 01 | 1 | Approved with Comments | AWC | 2024-12-09 | Overdue | 0 | AWC | AWC
3182 | 000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | I | 5020 | A | 131242-WST02-DR-I-5020-A | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | Approved with Comments | 2024-12-09 | YES | Resubmitted |  | 131242-WST02-DR-5020 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-16 | 17 | AWC | 2024-11-02 | A | 000553 | 2024-07-09, 2024-11-02 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-09 | Overdue | 0 | AWC | AWC
3183 | 000553 | 01 | Qili | Process | NA | 131242 | WST02 | DR | I | 5021 | A | 131242-WST02-DR-I-5021-A | 2024-11-02 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev0: The submittal is approved with comments, please address the comments and resubmit. | 2024-11-29 | 2024-11-19 | Approved with Comments | 2024-12-09 | YES | Resubmitted |  | 131242-WST02-DR-5021 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-16 | 17 | AWC | 2025-03-06 | A | 000553 | 2024-07-09, 2024-11-02, 2025-03-06 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3184 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-P-0007-2 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-CL-0007 | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 48 | AWC | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3185 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | P | 0008 | 0 | 131242-WST02-CL-P-0008-0 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-CL-0008 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3186 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | M | 5020 | 0 | 131242-WST02-CL-M-5020-0 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-CL-5020 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3187 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | CL | M | 5021 | 0 | 131242-WST02-CL-M-5021-0 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-CL-5021 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3188 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018-0 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DS-0018 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Pressure Gauge" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 48 | AWC | 2025-08-22 | 0 | 000553&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3189 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 0019 | 0 | 131242-WST02-DS-M-0019-0 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DS-0019 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Rotameter" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-09-10 | 0 | 000553&&001672 | 2025-03-06, 2025-08-22, 2025-09-10 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3190 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DS | M | 5741 | 0 | 131242-WST02-DS-M-5741-0 | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DS-5741 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3191 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 5021 | A | 131242-WST02-DR-M-5021-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-5021 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 48 | AWC | 2025-03-06 | A | 000553 | 2024-07-09, 2024-11-02, 2025-03-06 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3192 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 5022 | A | 131242-WST02-DR-M-5022-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-5022 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3193 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1200 | A | 131242-WST02-DR-M-1200-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1200 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3194 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1201 | B | 131242-WST02-DR-M-1201-B | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1201 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3195 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1202 | B | 131242-WST02-DR-M-1202-B | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1202 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3196 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1203 | A | 131242-WST02-DR-M-1203-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1203 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3197 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1204 | A | 131242-WST02-DR-M-1204-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1204 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" && "ST608 drawings Connection Details" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147&&001285 | 2025-03-06, 2025-03-21, 2025-05-13, 2025-07-29 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3198 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1205 | A | 131242-WST02-DR-M-1205-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1205 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3199 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1206 | A | 131242-WST02-DR-M-1206-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1206 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3200 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1207 | A | 131242-WST02-DR-M-1207-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1207 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3201 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1208 | A | 131242-WST02-DR-M-1208-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1208 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3202 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1209 | A | 131242-WST02-DR-M-1209-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1209 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3203 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 1210 | A | 131242-WST02-DR-M-1210-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-1210 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-07-29 | C | 000553&&001147 | 2025-03-06, 2025-03-21, 2025-07-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3204 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3203 | A | 131242-WST02-DR-M-3203-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3203 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | 2025-02-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 48 | AWC | 2025-03-06 | A | 000553&&001052 | 2025-02-18, 2025-03-06 | 00, 02 | 2 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3205 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3204 | A | 131242-WST02-DR-M-3204-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3204 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "PC Pump Dry Run Protection Switch Box Outline drawing and Schematic Wiring Diagram " | 2025-02-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 48 | AWC | 2025-03-06 | A | 000553&&001052 | 2025-02-18, 2025-03-06 | 00, 02 | 2 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3206 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3205 | A | 131242-WST02-DR-M-3205-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3205 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3207 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3206 | A | 131242-WST02-DR-M-3206-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3206 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3208 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3207 | A | 131242-WST02-DR-M-3207-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3207 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3209 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3208 | A | 131242-WST02-DR-M-3208-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3208 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3210 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3209 | A | 131242-WST02-DR-M-3209-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3209 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3211 | 000553 | 02 | Qili | Process | NA | 131242 | WST02 | DR | M | 3210 | A | 131242-WST02-DR-M-3210-A | 2025-03-06 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev2: The submittal is approved with comments, please address the comments and resubmit. | 2025-03-26 | 2025-04-23 | Approved with Comments | 2025-05-13 | YES | Resubmitted |  | 131242-WST02-DR-3210 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 48 | AWC | 2025-03-06 | A | 000553 | 2025-03-06 | 02 | 1 | Approved with Comments | AWC | 2025-05-13 | Overdue | 0 | AWC | AWC
3212 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0007 | 2 | 131242-WST02-CL-P-0007-2 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-CL-0007 | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
3213 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | P | 0008 | 0 | 131242-WST02-CL-P-0008-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-CL-0008 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
3214 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | M | 5020 | 0 | 131242-WST02-CL-M-5020-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-CL-5020 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
3215 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | CL | M | 5021 | 0 | 131242-WST02-CL-M-5021-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-CL-5021 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
3216 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0018 | 0 | 131242-WST02-DS-M-0018-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DS-0018 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Pressure Gauge" | 2024-07-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-08-22 | 0 | 000553&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00, 02, 03 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
3217 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0019 | 0 | 131242-WST02-DS-M-0019-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DS-0019 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Rotameter" | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-09-10 | 0 | 000553&&001672 | 2025-03-06, 2025-08-22, 2025-09-10 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3218 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 0020 | 0 | 131242-WST02-DS-M-0020-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DS-0020 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Conductive Level Switch" | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-11 | 45 | AWC | 2025-09-10 | 0 | 000553&&001673 | 2025-08-22, 2025-09-10 | 00, 03 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3219 | 000553 | 03 | Qili | Process | NA | 131242 | WST02 | DS | M | 5741 | 0 | 131242-WST02-DS-M-5741-0 | 2025-08-22 | Data Sheet, Drawing and Calculation of SSN Diffuser | Rev3: The submittal is approved with comments, please address the comments and resubmit. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DS-5741 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-05 | 45 | AWC | 2025-08-22 | 0 | 000553 | 2025-03-06, 2025-08-22 | 02, 03 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
3220 | 000554 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5000 | A | 131242-WST02-DR-I-5000-A | 2024-07-10 | SSN UPS and Battery Room Layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | Not Approved | 2024-09-20 | NO | Overdue |  | 131242-WST02-DR-5000 | NA | "Building Services ACMV" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Plumbing and Sanitary " && "SSN Preliminary Lightning Protection System" && "SSN UPS and Battery Room Layout" && "Typical Installation Details for Lighting" && "Typical Installation Details for Power" && "Typical Installation drawing For PA & Fire Alarm" && "Typical installation drawing for PA & Fire Alarm System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 54 | NAP | 2025-10-29 | A.4 | 000161&&000189&&000191&&000205&&000219&&000307&&000310&&000492&&000554&&001299&&001306 | 2023-11-22, 2024-02-13, 2024-05-28, 2024-07-06, 2024-07-10, 2024-10-05, 2024-10-21, 2024-12-24, 2025-02-13, 2025-02-20, 2025-02-24, 2025-02-26, 2025-03-25, 2025-05-15, 2025-05-18, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 21 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3221 | 000555 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 5001 | A | 131242-WST02-DR-I-5001-A | 2024-07-10 | SSN Process Non-Process room layout | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-07 | 2024-09-02 | Not Approved | 2024-09-20 | NO | Overdue |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-24 | 54 | NAP | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3222 | 000556 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 0 | 131242-WSD11-RT-EK-0000-0 | 2024-07-10 | THP LPS Risk Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | Approved with Comments | 2024-10-14 | YES | Resubmitted |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 76 | AWC | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3223 | 000556 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 1 | 131242-WSD11-RT-EK-0000-1 | 2024-10-28 | THP LPS Risk Assessment Report | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-12-08 | Approved with Comments | 2024-12-27 | YES | Resubmitted |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-11 | 41 | AWC | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3224 | 000556 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EK | 0000 | 2 | 131242-WSD11-RT-EK-0000-2 | 2025-07-07 | THP LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 57 | AWC | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3225 | 000557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 0 | 131242-WST02-RT-EK-0000-0 | 2024-07-10 | SSN LPS Risk Assessment Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-07 | 2024-09-24 | Not Approved | 2024-10-14 | YES | Resubmitted |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-30 | 76 | NAP | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3226 | 000557 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 1 | 131242-WST02-RT-EK-0000-1 | 2024-10-24 | SSN LPS Risk Assessment Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-11-14 | 2024-12-08 | Not Approved | 2024-12-27 | YES | Resubmitted |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-07 | 45 | NAP | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3227 | 000557 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EK | 0000 | 2 | 131242-WST02-RT-EK-0000-2 | 2025-07-07 | SSN LPS Risk Assessment Report | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-25 | 2025-09-02 | Approved with Comments | 2025-09-22 | NO | Overdue |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-21 | 57 | AWC | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3228 | 000558 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0028 | 0 | 131242-WSW41-MI-IM-0028-0 | 2024-07-10 | BIM Bi-Weekly Meeting Minutes 0028_20240626 | For Information | 2024-08-07 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WSW41-MI-0028 | NA | "BIM Bi-Weekly Meeting Minutes 0028_20240626" && "CSA Meeting Minutes 0027,0028_June" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-30 | 51 | INF | 2024-08-06 | 0 | 000558&&000562&&000622 | 2024-07-10, 2024-07-12, 2024-08-06 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3229 | 000559 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0018 | 0 | 131242-WSW41-VI-M-0018-0 | 2024-07-12 | Preliminary Design and Vendor Approval for Parabolic Screen | Rev 0: Approved | 2024-08-12 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-VI-0018 | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-26 | 52 | APP | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | Approved | APP |  |  | 0 | APP | APP
3230 | 000560 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 0 | 131242-WSW41-VI-M-0020-0 | 2024-07-12 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WSW41-VI-0020 | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 42 | AWC | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
3231 | 000560 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0020 | 1 | 131242-WSW41-VI-M-0020-1 | 2024-09-16 | Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch) | Rev 1: Approved | 2024-10-04 | 2024-09-24 | Approved |  | YES | NA |  | 131242-WSW41-VI-0020 | NA | "Preliminary Design and Vendor Approval for Top Manway (Aluminium Hatch)" && "Vendor Approval of Electrical Installer (Cyclect)" && "Vendor Approval of ICA Installer Submission (Cyclect)" | 2024-05-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-30 | 8 | APP | 2024-09-16 | 1 | 000485&&000486&&000560 | 2024-05-23, 2024-07-12, 2024-09-16 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
3232 | 000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0024 | 0 | 131242-WSW41-MI-C-0024-0 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-MI-0024 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-26 | 31 | INF | 2024-08-29 | 0 | 000517&&000561&&000684 | 2024-06-10, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3233 | 000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0025 | 0 | 131242-WSW41-MI-C-0025-0 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-MI-0025 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-26 | 31 | INF | 2024-08-29 | 0 | 000529&&000561&&000684 | 2024-06-20, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3234 | 000561 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0026 | 0 | 131242-WSW41-MI-C-0026-0 | 2024-07-12 | CSA Meeting Minutes 0024,0025,0026_May | For Information | 2024-08-12 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-MI-0026 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-26 | 31 | INF | 2024-08-29 | 0 | 000542&&000561&&000684 | 2024-07-03, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3235 | 000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0027 | 0 | 131242-WSW41-MI-C-0027-0 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 | For Information |  | YES | NA |  | 131242-WSW41-MI-0027 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0027,0028_June" && "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-01 | 18 | INF | 2024-08-29 | 0 | 000562&&000584&&000684 | 2024-07-12, 2024-07-24, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3236 | 000562 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0028 | 0 | 131242-WSW41-MI-C-0028-0 | 2024-07-12 | CSA Meeting Minutes 0027,0028_June | For Information | 2024-08-12 | 2024-07-30 | For Information |  | YES | NA |  | 131242-WSW41-MI-0028 | NA | "BIM Bi-Weekly Meeting Minutes 0028_20240626" && "CSA Meeting Minutes 0027,0028_June" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-26 | 18 | INF | 2024-08-06 | 0 | 000558&&000562&&000622 | 2024-07-10, 2024-07-12, 2024-08-06 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3237 | 000563 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0010 | 0 | 131242-WSW41-QA-C-0010-0 | 2024-07-12 | Monthly Concrete Cube Records for Structural works (03 24) | Rev.0: Not Approved. Please refer to comment sheet for resubmission | 2024-08-12 | 2024-08-12 | Not Approved | 2024-08-30 | NO | Overdue |  | 131242-WSW41-QA-0010 | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-01 | 31 | NAP | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3238 | 000564 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | E | 0002 | 0 | 131242-WSW41-MS-E-0002-0 | 2024-07-12 | MSRA, SWP for Electrical Work | Rev 0: Not approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-12 | 2024-09-24 | Not Approved | 2024-10-14 | NO | Overdue |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-26 | 74 | NAP | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3239 | 000565 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 0 | 131242-WSW41-MS-M-0001-0 | 2024-07-13 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-12 | 2024-08-23 | Approved with Comments | 2024-09-12 | YES | Resubmitted |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-27 | 41 | AWC | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | AWC | AWC
3240 | 000565 | 01 | Bryan | HSE | NA | 131242 | WSW41 | MS | M | 0001 | 1 | 131242-WSW41-MS-M-0001-1 | 2024-09-05 | MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work | Rev 1: Approved | 2024-09-25 | 2024-10-03 | Approved |  | YES | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-19 | 28 | APP | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | APP | APP
3241 | 000566 | 00 | Zuo Yu | EICA | NA | 131242 | WST02 | VI | I | 0020 | 0 | 131242-WST02-VI-I-0020-0 | 2024-07-13 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-08-12 | 2024-08-06 | Approved with Comments | 2024-08-27 | YES | Resubmitted |  | 131242-WST02-VI-0020 | NA | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | 2024-07-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-02 | 24 | AWC | 2024-08-16 | 1 | 000566 | 2024-07-13, 2024-08-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3242 | 000566 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | VI | I | 0020 | 1 | 131242-WST02-VI-I-0020-1 | 2024-08-16 | Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-05 | 2024-10-10 | Approved with Comments | 2024-10-30 | NO | Overdue | Vendor Changed to Fox | 131242-WST02-VI-0020 | NA | "Preliminary Design and Vendor Approval of SSN Aeration Blower Package (Logical Path)" | 2024-07-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-30 | 55 | AWC | 2024-08-16 | 1 | 000566 | 2024-07-13, 2024-08-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-10-30 | Overdue | 0 | AWC | AWC
3243 | 000567 | 00 | Krishanthy | PCM | NA | 131242 | WST02 | RT | C | 0004 | 0 | 131242-WST02-RT-C-0004-0 | 2024-07-15 | Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area | Approved | 2024-08-13 | 2024-08-12 | Approved |  | YES | NA |  | 131242-WST02-RT-0004 | NA | "Report of DFS (Guide 3) for Substructure & Superstructure work at SSN & THP area " && "Test Report for Static Load Test Dia 700mm Bored Pile WLT 2 TP47) Zone 1 ST616" | 2024-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-29 | 28 | APP | 2024-07-15 | 0 | 000539&&000567 | 2024-07-02, 2024-07-15 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
3244 | 000568 | 00 | Leslie | PCM | NA | 131242 | WST02 | RT | C | 0005 | 0 | 131242-WST02-RT-C-0005-0 | 2024-07-15 | Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-13 | 2024-08-22 | Approved with Comments | 2024-09-11 | NO | Overdue |  | 131242-WST02-RT-0005 | NA | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " && "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" | 2024-07-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-07-29 | 38 | AWC | 2025-07-24 | 0 | 000540&&000568&&001524 | 2024-07-02, 2024-07-15, 2025-07-24 | 00 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3245 | 000569 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 0 | 131242-WSD11-CD-I-0002-0 | 2024-07-16 | THP Instrument Lists | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-14 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WSD11-CD-0002 | NA | "THP Instrument Lists" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 63 | NAP | 2024-12-13 | 1 | 000569 | 2024-07-16, 2024-12-13 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
3246 | 000569 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WSD11 | CD | I | 0002 | 1 | 131242-WSD11-CD-I-0002-1 | 2024-12-13 | THP Instrument Lists | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-01-03 | 2025-02-13 | Not Approved | 2025-03-05 | NO | Overdue |  | 131242-WSD11-CD-0002 | NA | "THP Instrument Lists" | 2024-07-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-27 | 62 | NAP | 2024-12-13 | 1 | 000569 | 2024-07-16, 2024-12-13 | 00, 01 | 2 | Not Approved | NAP | 2025-03-05 | Overdue | 0 | NAP | NAP
3247 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | A | 131242-WSD11-DR-EP-7100-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7100 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3248 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | A | 131242-WSD11-DR-EP-7101-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7101 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3249 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | A | 131242-WSD11-DR-EP-7102-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7102 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3250 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | A | 131242-WSD11-DR-EP-7103-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7103 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3251 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | A | 131242-WSD11-DR-EP-7104-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7104 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3252 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | A | 131242-WSD11-DR-EP-7105-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7105 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3253 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | A | 131242-WSD11-DR-EP-7106-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7106 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3254 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | A | 131242-WSD11-DR-EP-7107-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7107 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3255 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7108 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3256 | 000570 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109-A | 2024-07-16 | THP SLD | Rev 0: Not Approved. To revise and resubmit. Please refer to attached file for comments. | 2024-08-14 | 2024-08-21 | Not Approved | 2024-09-10 | YES | Resubmitted |  | 131242-WSD11-DR-7109 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-05 | 36 | NAP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | NAP | NAP
3257 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-EI-7000-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-21 | 2024-10-03 | Not Approved | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | NAP | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | NAP | NAP
3258 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | B | 131242-WSD11-DR-EI-7001-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | REJ | REJ
3259 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | B | 131242-WSD11-DR-EI-7002-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | REJ | REJ
3260 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | B | 131242-WSD11-DR-EI-7003-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7003 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3261 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | B | 131242-WSD11-DR-EI-7004-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7004 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3262 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | B | 131242-WSD11-DR-EI-7005-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7005 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3263 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | B | 131242-WSD11-DR-EI-7006-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7006 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3264 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | B | 131242-WSD11-DR-EI-7007-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7007 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3265 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | B | 131242-WSD11-DR-EI-7008-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7008 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3266 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | B | 131242-WSD11-DR-EI-7009-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7009 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | REJ | REJ
3267 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | B | 131242-WSD11-DR-EI-7010-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3268 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | B | 131242-WSD11-DR-EI-7020-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3269 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | B | 131242-WSD11-DR-EI-7021-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3270 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | B | 131242-WSD11-DR-EI-7022-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3271 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | B | 131242-WSD11-DR-EI-7023-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3272 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | B | 131242-WSD11-DR-EI-7024-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7024 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3273 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | B | 131242-WSD11-DR-EI-7025-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3274 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | B | 131242-WSD11-DR-EI-7026-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3275 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | B | 131242-WSD11-DR-EI-7027-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3276 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | B | 131242-WSD11-DR-EI-7028-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7028 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2026-02-03 | A | 000570&&002001 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3277 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | B | 131242-WSD11-DR-EI-7029-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7029 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | REJ | REJ
3278 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | B | 131242-WSD11-DR-EI-7030-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7030 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | REJ | REJ
3279 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | B | 131242-WSD11-DR-EP-3000-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | REJ | REJ
3280 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | B | 131242-WSD11-DR-EP-3001-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3281 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | B | 131242-WSD11-DR-EP-3002-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3282 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | B | 131242-WSD11-DR-EP-3003-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3283 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | B | 131242-WSD11-DR-EP-3004-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3284 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | B | 131242-WSD11-DR-EP-3005-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3285 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | B | 131242-WSD11-DR-EP-3006-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3286 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | B | 131242-WSD11-DR-EP-3007-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3287 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | B | 131242-WSD11-DR-EP-3008-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3288 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | B | 131242-WSD11-DR-EP-3009-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3289 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | B | 131242-WSD11-DR-EP-3010-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3290 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | B | 131242-WSD11-DR-EP-3011-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3291 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | B | 131242-WSD11-DR-EP-3012-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3292 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | B | 131242-WSD11-DR-EP-3013-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-21 | 2 | REJ | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3293 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | B | 131242-WSD11-DR-EP-7100-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7100 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3294 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | B | 131242-WSD11-DR-EP-7101-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7101 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3295 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | B | 131242-WSD11-DR-EP-7102-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7102 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3296 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | B | 131242-WSD11-DR-EP-7103-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7103 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3297 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | B | 131242-WSD11-DR-EP-7104-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7104 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3298 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | B | 131242-WSD11-DR-EP-7105-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7105 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3299 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | B | 131242-WSD11-DR-EP-7106-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7106 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3300 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | B | 131242-WSD11-DR-EP-7107-B | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7107 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3301 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108-A | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7108 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3302 | 000570 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109-A | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to reject the submission. | 2024-10-29 | 2024-10-03 | Rejected | 2024-10-23 | YES | Resubmitted |  | 131242-WSD11-DR-7109 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-15 | 2 | REJ | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3303 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | B | 131242-WSD11-DR-EI-7000-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-10-23 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
3304 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | B | 131242-WSD11-DR-EI-7001-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | AWC | AWC
3305 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | B | 131242-WSD11-DR-EI-7002-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | AWC | AWC
3306 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | B | 131242-WSD11-DR-EI-7003-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7003 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3307 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | B | 131242-WSD11-DR-EI-7004-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7004 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3308 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | B | 131242-WSD11-DR-EI-7005-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7005 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3309 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | B | 131242-WSD11-DR-EI-7006-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7006 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3310 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | B | 131242-WSD11-DR-EI-7007-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7007 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3311 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | B | 131242-WSD11-DR-EI-7008-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7008 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3312 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | B | 131242-WSD11-DR-EI-7009-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7009 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3313 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | B | 131242-WSD11-DR-EI-7010-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3314 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | B | 131242-WSD11-DR-EI-7020-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3315 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | B | 131242-WSD11-DR-EI-7021-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3316 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | B | 131242-WSD11-DR-EI-7022-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3317 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | B | 131242-WSD11-DR-EI-7023-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3318 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | B | 131242-WSD11-DR-EI-7024-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7024 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3319 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | B | 131242-WSD11-DR-EI-7025-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3320 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | B | 131242-WSD11-DR-EI-7026-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3321 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | B | 131242-WSD11-DR-EI-7027-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3322 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | B | 131242-WSD11-DR-EI-7028-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7028 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000570&&002001 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3323 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | B | 131242-WSD11-DR-EI-7029-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7029 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3324 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | B | 131242-WSD11-DR-EI-7030-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7030 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3325 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | B | 131242-WSD11-DR-EP-3000-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
3326 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | B | 131242-WSD11-DR-EP-3001-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3327 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | B | 131242-WSD11-DR-EP-3002-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3328 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | B | 131242-WSD11-DR-EP-3003-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3329 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | B | 131242-WSD11-DR-EP-3004-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3330 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | B | 131242-WSD11-DR-EP-3005-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3331 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | B | 131242-WSD11-DR-EP-3006-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3332 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | B | 131242-WSD11-DR-EP-3007-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3333 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | B | 131242-WSD11-DR-EP-3008-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3334 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | B | 131242-WSD11-DR-EP-3009-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3335 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | B | 131242-WSD11-DR-EP-3010-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3336 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | B | 131242-WSD11-DR-EP-3011-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3337 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | B | 131242-WSD11-DR-EP-3012-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3338 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | B | 131242-WSD11-DR-EP-3013-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3339 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | B | 131242-WSD11-DR-EP-7100-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7100 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3340 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | B | 131242-WSD11-DR-EP-7101-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7101 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3341 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | B | 131242-WSD11-DR-EP-7102-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7102 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3342 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | B | 131242-WSD11-DR-EP-7103-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7103 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3343 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | B | 131242-WSD11-DR-EP-7104-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7104 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3344 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | B | 131242-WSD11-DR-EP-7105-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7105 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3345 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | B | 131242-WSD11-DR-EP-7106-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7106 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3346 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | B | 131242-WSD11-DR-EP-7107-B | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7107 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3347 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | A | 131242-WSD11-DR-EP-7108-A | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7108 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3348 | 000570 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | A | 131242-WSD11-DR-EP-7109-A | 2024-10-03 | THP SLD | Rev 2: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-11-01 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSD11-DR-7109 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-17 | 26 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3349 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | C | 131242-WSD11-DR-EI-7000-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
3350 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | C | 131242-WSD11-DR-EI-7001-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | AWC | AWC
3351 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | C | 131242-WSD11-DR-EI-7002-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | AWC | AWC
3352 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | C | 131242-WSD11-DR-EI-7003-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7003 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3353 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | C | 131242-WSD11-DR-EI-7004-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7004 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3354 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | C | 131242-WSD11-DR-EI-7005-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7005 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3355 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | C | 131242-WSD11-DR-EI-7006-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7006 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3356 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | C | 131242-WSD11-DR-EI-7007-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7007 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3357 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | C | 131242-WSD11-DR-EI-7008-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7008 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3358 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | C | 131242-WSD11-DR-EI-7009-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7009 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3359 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | C | 131242-WSD11-DR-EI-7010-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3360 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | C | 131242-WSD11-DR-EI-7020-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3361 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | C | 131242-WSD11-DR-EI-7021-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3362 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | C | 131242-WSD11-DR-EI-7022-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3363 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | C | 131242-WSD11-DR-EI-7023-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3364 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | C | 131242-WSD11-DR-EI-7024-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7024 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3365 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | C | 131242-WSD11-DR-EI-7025-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3366 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | C | 131242-WSD11-DR-EI-7026-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3367 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | C | 131242-WSD11-DR-EI-7027-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3368 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | C | 131242-WSD11-DR-EI-7028-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7028 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000570&&002001 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3369 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | C | 131242-WSD11-DR-EI-7029-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7029 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3370 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | C | 131242-WSD11-DR-EI-7030-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7030 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3371 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | C | 131242-WSD11-DR-EI-7031-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7031 | NA | "THP SLD" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-11-21, 2025-03-07, 2025-10-23 | 03, 04, 05 | 3 | Approved | APP |  |  | 0 | AWC | AWC
3372 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | C | 131242-WSD11-DR-EP-3000-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
3373 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | C | 131242-WSD11-DR-EP-3001-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3374 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | C | 131242-WSD11-DR-EP-3002-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3375 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | C | 131242-WSD11-DR-EP-3003-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3376 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | C | 131242-WSD11-DR-EP-3004-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3377 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | C | 131242-WSD11-DR-EP-3005-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3378 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | C | 131242-WSD11-DR-EP-3006-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3379 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | C | 131242-WSD11-DR-EP-3007-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3380 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | C | 131242-WSD11-DR-EP-3008-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3381 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | C | 131242-WSD11-DR-EP-3009-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3382 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | C | 131242-WSD11-DR-EP-3010-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3383 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | C | 131242-WSD11-DR-EP-3011-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3384 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | C | 131242-WSD11-DR-EP-3012-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3385 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | C | 131242-WSD11-DR-EP-3013-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3386 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | C | 131242-WSD11-DR-EP-7100-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7100 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3387 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | C | 131242-WSD11-DR-EP-7101-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7101 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3388 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | C | 131242-WSD11-DR-EP-7102-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7102 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3389 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | C | 131242-WSD11-DR-EP-7103-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7103 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3390 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | C | 131242-WSD11-DR-EP-7104-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7104 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3391 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | C | 131242-WSD11-DR-EP-7105-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7105 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3392 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | C | 131242-WSD11-DR-EP-7106-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7106 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3393 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | C | 131242-WSD11-DR-EP-7107-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7107 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3394 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | C | 131242-WSD11-DR-EP-7108-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7108 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3395 | 000570 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | C | 131242-WSD11-DR-EP-7109-C | 2024-11-21 | THP SLD | Rev 3: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2024-12-19 | 2024-12-30 | Approved with Comments | 2025-01-17 | YES | Resubmitted |  | 131242-WSD11-DR-7109 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3396 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | D | 131242-WSD11-DR-EI-7000-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
3397 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | D | 131242-WSD11-DR-EI-7001-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | AWC | AWC
3398 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | D | 131242-WSD11-DR-EI-7002-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | AWC | AWC
3399 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | D | 131242-WSD11-DR-EI-7003-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7003 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3400 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | D | 131242-WSD11-DR-EI-7004-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7004 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3401 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | D | 131242-WSD11-DR-EI-7005-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7005 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3402 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | D | 131242-WSD11-DR-EI-7006-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7006 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3403 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | D | 131242-WSD11-DR-EI-7007-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7007 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3404 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | D | 131242-WSD11-DR-EI-7008-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7008 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3405 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | D | 131242-WSD11-DR-EI-7009-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7009 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3406 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | D | 131242-WSD11-DR-EI-7010-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3407 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7011 | D | 131242-WSD11-DR-EI-7011-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7011 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-27 | 60 | AWC | 2026-02-03 | B | 000570&&001757 | 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 04, 05 | 4 | Approved | APP |  |  | 0 | AWC | AWC
3408 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | D | 131242-WSD11-DR-EI-7020-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3409 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | D | 131242-WSD11-DR-EI-7021-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3410 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | D | 131242-WSD11-DR-EI-7022-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3411 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | D | 131242-WSD11-DR-EI-7023-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3412 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | D | 131242-WSD11-DR-EI-7024-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7024 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3413 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | D | 131242-WSD11-DR-EI-7025-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3414 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | D | 131242-WSD11-DR-EI-7026-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3415 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | D | 131242-WSD11-DR-EI-7027-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3416 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | D | 131242-WSD11-DR-EI-7028-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7028 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000570&&002001 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3417 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | D | 131242-WSD11-DR-EI-7029-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7029 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3418 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | D | 131242-WSD11-DR-EI-7030-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7030 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3419 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | D | 131242-WSD11-DR-EI-7031-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7031 | NA | "THP SLD" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-11-21, 2025-03-07, 2025-10-23 | 03, 04, 05 | 3 | Approved | APP |  |  | 0 | AWC | AWC
3420 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | D | 131242-WSD11-DR-EP-3000-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | AWC | AWC
3421 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | D | 131242-WSD11-DR-EP-3001-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3422 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | D | 131242-WSD11-DR-EP-3002-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3423 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | D | 131242-WSD11-DR-EP-3003-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3424 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | D | 131242-WSD11-DR-EP-3004-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3425 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | D | 131242-WSD11-DR-EP-3005-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3426 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | D | 131242-WSD11-DR-EP-3006-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3427 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | D | 131242-WSD11-DR-EP-3007-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3428 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | D | 131242-WSD11-DR-EP-3008-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3429 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | D | 131242-WSD11-DR-EP-3009-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3430 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | D | 131242-WSD11-DR-EP-3010-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3431 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | D | 131242-WSD11-DR-EP-3011-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3432 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | D | 131242-WSD11-DR-EP-3012-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3433 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | D | 131242-WSD11-DR-EP-3013-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3434 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | D | 131242-WSD11-DR-EP-7100-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7100 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3435 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | D | 131242-WSD11-DR-EP-7101-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7101 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3436 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | D | 131242-WSD11-DR-EP-7102-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7102 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3437 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | D | 131242-WSD11-DR-EP-7103-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7103 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3438 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | D | 131242-WSD11-DR-EP-7104-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7104 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3439 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | D | 131242-WSD11-DR-EP-7105-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7105 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3440 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | D | 131242-WSD11-DR-EP-7106-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7106 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3441 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | D | 131242-WSD11-DR-EP-7107-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7107 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3442 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | D | 131242-WSD11-DR-EP-7108-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7108 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3443 | 000570 | 04 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | D | 131242-WSD11-DR-EP-7109-D | 2025-03-07 | THP SLD | Rev 4: Approved with comment. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-05-06 | Approved with Comments | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-DR-7109 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 60 | AWC | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3444 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | E | 131242-WSD11-DR-EI-7000-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | APP | APP
3445 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | E | 131242-WSD11-DR-EI-7001-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | APP | APP
3446 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | E | 131242-WSD11-DR-EI-7002-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | APP | APP
3447 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | E | 131242-WSD11-DR-EI-7003-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7003 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3448 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | E | 131242-WSD11-DR-EI-7004-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7004 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3449 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | E | 131242-WSD11-DR-EI-7005-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7005 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3450 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | E | 131242-WSD11-DR-EI-7006-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7006 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3451 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | E | 131242-WSD11-DR-EI-7007-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7007 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3452 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | E | 131242-WSD11-DR-EI-7008-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7008 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3453 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7009 | E | 131242-WSD11-DR-EI-7009-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7009 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | APP | APP
3454 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7010 | E | 131242-WSD11-DR-EI-7010-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3455 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7011 | E | 131242-WSD11-DR-EI-7011-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7011 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | B | 000570&&001757 | 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 04, 05 | 4 | Approved | APP |  |  | 0 | APP | APP
3456 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | E | 131242-WSD11-DR-EI-7020-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3457 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | E | 131242-WSD11-DR-EI-7021-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3458 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | E | 131242-WSD11-DR-EI-7022-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3459 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | E | 131242-WSD11-DR-EI-7023-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3460 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | E | 131242-WSD11-DR-EI-7024-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7024 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3461 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | E | 131242-WSD11-DR-EI-7025-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3462 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | E | 131242-WSD11-DR-EI-7026-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3463 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | E | 131242-WSD11-DR-EI-7027-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | APP | APP
3464 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7028 | E | 131242-WSD11-DR-EI-7028-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7028 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000570&&002001 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3465 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7029 | E | 131242-WSD11-DR-EI-7029-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7029 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | APP | APP
3466 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7030 | E | 131242-WSD11-DR-EI-7030-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7030 | NA | "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 01, 02, 03, 04, 05 | 5 | Approved | APP |  |  | 0 | APP | APP
3467 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7031 | E | 131242-WSD11-DR-EI-7031-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7031 | NA | "THP SLD" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-11-21, 2025-03-07, 2025-10-23 | 03, 04, 05 | 3 | Approved | APP |  |  | 0 | APP | APP
3468 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | E | 131242-WSD11-DR-EP-3000-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | APP | APP
3469 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | E | 131242-WSD11-DR-EP-3001-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | APP | APP
3470 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | E | 131242-WSD11-DR-EP-3002-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3471 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | E | 131242-WSD11-DR-EP-3003-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
3472 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | E | 131242-WSD11-DR-EP-3004-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
3473 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | E | 131242-WSD11-DR-EP-3005-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3474 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | E | 131242-WSD11-DR-EP-3006-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | APP | APP
3475 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | E | 131242-WSD11-DR-EP-3007-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
3476 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | E | 131242-WSD11-DR-EP-3008-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3477 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | E | 131242-WSD11-DR-EP-3009-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3478 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3010 | E | 131242-WSD11-DR-EP-3010-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | APP | APP
3479 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3011 | E | 131242-WSD11-DR-EP-3011-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC |  |  | 0 | APP | APP
3480 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3012 | E | 131242-WSD11-DR-EP-3012-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3012 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-11 | B | 000291&&000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3481 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3013 | E | 131242-WSD11-DR-EP-3013-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-3013 | NA | "THP ICA GA & Wiring drawings" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-11-11 | B | 000570&&001230&&001328 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
3482 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7100 | E | 131242-WSD11-DR-EP-7100-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7100 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3483 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7101 | E | 131242-WSD11-DR-EP-7101-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7101 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3484 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7102 | E | 131242-WSD11-DR-EP-7102-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7102 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3485 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7103 | E | 131242-WSD11-DR-EP-7103-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7103 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3486 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7104 | E | 131242-WSD11-DR-EP-7104-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7104 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3487 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7105 | E | 131242-WSD11-DR-EP-7105-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7105 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3488 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7106 | E | 131242-WSD11-DR-EP-7106-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7106 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3489 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7107 | E | 131242-WSD11-DR-EP-7107-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7107 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3490 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7108 | E | 131242-WSD11-DR-EP-7108-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7108 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3491 | 000570 | 05 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7109 | E | 131242-WSD11-DR-EP-7109-E | 2025-10-23 | THP SLD | Rev 5: Approved | 2025-11-12 | 2026-02-02 | Approved |  | YES | NA |  | 131242-WSD11-DR-7109 | NA | "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-06 | 102 | APP | 2025-10-23 | E | 000570 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | APP | APP
3492 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7000 | A | 131242-WSD11-DR-EI-7000-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-30 | 38 | REJ | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | REJ | REJ
3493 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7001 | A | 131242-WSD11-DR-EI-7001-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-30 | 38 | REJ | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | REJ | REJ
3494 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7002 | A | 131242-WSD11-DR-EI-7002-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-30 | 38 | REJ | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | REJ | REJ
3495 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7003 | A | 131242-WSD11-DR-EI-7003-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7003 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3496 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7004 | A | 131242-WSD11-DR-EI-7004-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7004 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3497 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7005 | A | 131242-WSD11-DR-EI-7005-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7005 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3498 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7006 | A | 131242-WSD11-DR-EI-7006-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7006 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3499 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7007 | A | 131242-WSD11-DR-EI-7007-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7007 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3500 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7008 | A | 131242-WSD11-DR-EI-7008-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7008 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3501 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7020 | A | 131242-WSD11-DR-EI-7020-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3502 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7021 | A | 131242-WSD11-DR-EI-7021-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3503 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7022 | A | 131242-WSD11-DR-EI-7022-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3504 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7023 | A | 131242-WSD11-DR-EI-7023-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3505 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7024 | A | 131242-WSD11-DR-EI-7024-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7024 | NA | "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2025-10-23 | E | 000570&&000571 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | REJ | REJ
3506 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7025 | A | 131242-WSD11-DR-EI-7025-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3507 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7026 | A | 131242-WSD11-DR-EI-7026-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3508 | 000571 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7027 | A | 131242-WSD11-DR-EI-7027-A | 2024-07-16 | THP MCC Schematic Diagram | Rev 0: Rejected.Please refer to attached file for comments. To consolidate submittals 570, 571 and 575 into one shop drawing set in submittal 570. | 2024-08-14 | 2024-08-23 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-05 | 38 | REJ | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3509 | 000571 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#571 Cmt Reply Sht | A | 131242-WSD11---S#571 Cmt Reply Sht- | 2024-10-01 | THP SLD | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 | Not Approved |  | YES | NA |  | 131242-WSD11-NA-S#571 Cmt Reply Sht | NA | "THP SLD" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-21 | 2 | NAP | 2024-10-01 | A | 000571 | 2024-10-01 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
3510 | 000572 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302 | A | 131242-WSD11-DR-S-5302-A | 2024-07-17 | IFC of BSB Silo Area Pump Plinth Details | For Information | 2024-08-15 | 2024-08-28 | For Information |  | YES | NA |  | 131242-WSD11-DR-5302 | NA | "IFC of BSB Silo Area Pump Plinth Details " | 2024-07-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 42 | INF | 2024-07-17 | A | 000572 | 2024-07-17 | 00 | 1 | For Information | INF | 2024-09-17 | Overdue | 0 | INF | INF
3511 | 000573 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5501 | A | 131242-WST02-DR-S-5501-A | 2024-07-17 | IFC of SSN Electrical Building Transformer Plinth Details | Rev.0: Approved with comments. Revise and resubmit. | 2024-08-15 | 2024-09-14 | Approved with Comments | 2024-10-03 | NO | Overdue |  | 131242-WST02-DR-5501 | NA | "GA Drawing for Dosing Pump" && "Hookup Drawing for Magnetic Level Gauge" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-06 | 59 | AWC | 2026-01-20 | 0 | 000573&&000917&&001969 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3512 | 000574 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0006 | 0 | 131242-WSW41-VI-S-0006-0 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 | Approved |  | YES | NA |  | 131242-WSW41-VI-0006 | NA | "Preliminary Design and Vendor Aapproval Document for SSN Aeration Blower MCP & THP PLC/RIO Panels (FOX)" && "Preliminary Design and Vendor Approval For Progressive Cavity Pump (NETZSCH)" && "Vendor Approval of Concrete Supplier-Pan United" && "Vendor Approval of Scaffolding Contractor (H.K.L scaffolding and Formwork Pte Ltd.) " | 2023-08-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-31 | 26 | APP | 2024-12-11 | 0 | 000064&&000107&&000574&&000886 | 2023-08-08, 2023-09-22, 2023-09-25, 2024-07-17, 2024-07-31, 2024-12-11 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
3513 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3000 | A | 131242-WSD11-DR-EP-3000-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-31 | 29 | REJ | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | REJ | REJ
3514 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3001 | A | 131242-WSD11-DR-EP-3001-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-31 | 29 | REJ | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3515 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3002 | A | 131242-WSD11-DR-EP-3002-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-31 | 29 | REJ | 2025-11-11 | B | 000390&&000570&&000575&&001230&&001328 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3516 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3003 | A | 131242-WSD11-DR-EP-3003-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3003 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3517 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3004 | A | 131242-WSD11-DR-EP-3004-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3004 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3518 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3005 | A | 131242-WSD11-DR-EP-3005-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3519 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3006 | A | 131242-WSD11-DR-EP-3006-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3520 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3007 | A | 131242-WSD11-DR-EP-3007-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3007 | NA | "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2025-11-11 | B | 000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11 | 00, 01, 02, 03, 04, 05 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3521 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3008 | A | 131242-WSD11-DR-EP-3008-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3008 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3522 | 000575 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3009 | A | 131242-WSD11-DR-EP-3009-A | 2024-07-17 | THP MCC Outline Drawing | Rev 0: Rejected. Please refer to attached file for comments. | 2024-08-15 | 2024-08-15 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3009 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-06 | 29 | REJ | 2025-11-28 | A | 000292&&000570&&000575&&001230&&001328 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-11-11, 2025-11-28 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3523 | 000575 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | NA | NA | S#575 Cmt Reply Sht | A | 131242-WSD11---S#575 Cmt Reply Sht- | 2024-10-01 | THP MCC Outline Drawing | Rev.1: As per Contractor's request to withdraw the submission. | 2024-10-21 | 2024-10-03 | Not Approved |  | YES | NA |  | 131242-WSD11-NA-S#575 Cmt Reply Sht | NA | "THP MCC Outline Drawing" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-21 | 2 | NAP | 2024-10-01 | A | 000575 | 2024-10-01 | 01 | 1 | Not Approved | NAP | 2024-10-23 | Overdue | 0 | NAP | NAP
3524 | 000576 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | VI | S | 0007 | 0 | 131242-WSW41-VI-S-0007-0 | 2024-07-17 | Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) | Approved | 2024-08-15 | 2024-08-12 | Approved |  | YES | NA |  | 131242-WSW41-VI-0007 | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-31 | 26 | APP | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
3525 | 000577 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | VI | C | 0017 | 0 | 131242-WSW41-VI-C-0017-0 | 2024-07-17 | Vendor Approval for PVC Lining System - (Linabond) | Approved | 2024-08-15 | 2024-08-12 | Approved |  | YES | NA |  | 131242-WSW41-VI-0017 | NA | "Preliminary Design and Vendor Approval of Manway" && "Preliminary Design and Vendor Approval of Manway (SYNCHONG HOE)" && "Vendor Approval for PVC Lining System - (Linabond)" | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-31 | 26 | APP | 2024-07-31 | 1 | 000295&&000577 | 2024-02-01, 2024-07-17, 2024-07-31 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
3526 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1000_ST613 | C | 131242-WST02-DR-S-1000_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1000_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3527 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1006_ST613 | C | 131242-WST02-DR-S-1006_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1006_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3528 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1007_ST613 | C | 131242-WST02-DR-S-1007_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1007_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3529 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1008_ST613 | C | 131242-WST02-DR-S-1008_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1008_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3530 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1013_ST613 | C | 131242-WST02-DR-S-1013_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1013_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3531 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1014_ST613 | B | 131242-WST02-DR-S-1014_ST613-B | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1014_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | B | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3532 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1015_ST613 | C | 131242-WST02-DR-S-1015_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1015_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3533 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1016_ST613 | C | 131242-WST02-DR-S-1016_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1016_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3534 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1017_ST613 | C | 131242-WST02-DR-S-1017_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1017_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3535 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1018_ST613 | C | 131242-WST02-DR-S-1018_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1018_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3536 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1019_ST613 | C | 131242-WST02-DR-S-1019_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1019_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3537 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1020_ST613 | C | 131242-WST02-DR-S-1020_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1020_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3538 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1021_ST613 | C | 131242-WST02-DR-S-1021_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1021_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3539 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 1022_ST613 | C | 131242-WST02-DR-S-1022_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-1022_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3540 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3005_ST613 | C | 131242-WST02-DR-S-3005_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-3005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3541 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3008_ST613 | C | 131242-WST02-DR-S-3008_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-3008_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3542 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 3009_ST613 | C | 131242-WST02-DR-S-3009_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-3009_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3543 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5005_ST613 | C | 131242-WST02-DR-S-5005_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-5005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3544 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5006_ST613 | C | 131242-WST02-DR-S-5006_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-5006_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3545 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7002_ST613 | C | 131242-WST02-DR-S-7002_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-7002_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3546 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7003_ST613 | C | 131242-WST02-DR-S-7003_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-7003_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3547 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7004_ST613 | C | 131242-WST02-DR-S-7004_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-7004_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3548 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 7005_ST613 | C | 131242-WST02-DR-S-7005_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-7005_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3549 | 000578 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8003_ST613 | C | 131242-WST02-DR-S-8003_ST613-C | 2024-07-20 | IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building | For Information | 2024-08-19 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-DR-8003_ST613 | NA | "IFC ofST613_Sub Structure of Minor buildings and Super Structure of Elec Building " && "ST613 _Raft Foundations of Minor Structures and Super Structure of Electrical Building " | 2024-01-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-08-03 | 32 | INF | 2024-07-20 | C | 000275&&000578 | 2024-01-13, 2024-04-04, 2024-07-20 | 00, 01 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3550 | 000579 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WST02 | CD | I | 0001 | 0 | 131242-WST02-CD-I-0001-0 | 2024-07-22 | SSN PLC I/O List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-20 | 2024-09-17 | Not Approved | 2024-10-07 | YES | Resubmitted |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 57 | NAP | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3551 | 000579 | 01 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 1 | 131242-WST02-CD-I-0001-1 | 2024-11-06 | SSN RIO 0201 I/O List | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-26 | 2024-12-18 | Not Approved | 2025-01-08 | YES | Resubmitted |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-20 | 42 | NAP | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3552 | 000579 | 02 | Low | EICA | NA | 131242 | WST02 | CD | I | 0001 | 2 | 131242-WST02-CD-I-0001-2 | 2025-03-06 | SSN RIO 0201 I/O List | Rev 2: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-03-26 | 2025-05-07 | Not Approved | 2025-05-27 | YES | Resubmitted |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-20 | 62 | NAP | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3553 | 000579 | 03 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 3 | 131242-WST02-CD-I-0001-3 | 2025-06-16 | SSN RIO 0201 I/O List | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-04 | 2025-07-10 | Approved with Comments | 2025-07-30 | YES | Resubmitted |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 24 | AWC | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3554 | 000579 | 04 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0001 | 4 | 131242-WST02-CD-I-0001-4 | 2025-08-19 | SSN RIO 0201 I/O List | Rev 4: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-08 | 2025-09-15 | Approved with Comments | 2025-10-03 | NO | Overdue |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 27 | AWC | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3555 | 000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1191 | A | 131242-WSD11-DR-M-1191-A | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | Approved with Comments | 2024-10-24 | NO | Overdue | To check with relevent area discipline (Target 28 Feb 2025) | 131242-WSD11-DR-1191 | NA | "THP Cast in Layout Inside Bio-solid Building" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-07-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-12 | 73 | AWC | 2025-08-13 | B | 000580&&001382 | 2024-07-23, 2025-06-16, 2025-08-13 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3556 | 000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3190 | A | 131242-WSD11-DR-M-3190-A | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | Approved with Comments | 2024-10-24 | NO | Overdue |  | 131242-WSD11-DR-3190 | NA | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-12 | 73 | AWC | 2024-07-23 | A | 000580 | 2024-07-23 | 00 | 1 | Approved with Comments | AWC | 2024-10-24 | Overdue | 0 | AWC | AWC
3557 | 000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4000 | A | 131242-WSD11-DR-M-4000-A | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | Approved with Comments | 2024-10-24 | NO | Overdue |  | 131242-WSD11-DR-4000 | NA | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-12 | 73 | AWC | 2024-07-23 | A | 000580 | 2024-07-23 | 00 | 1 | Approved with Comments | AWC | 2024-10-24 | Overdue | 0 | AWC | AWC
3558 | 000580 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9000 | A | 131242-WSD11-DR-M-9000-A | 2024-07-23 | THP Cast in Layout Inside Bio-solid Building | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-21 | 2024-10-04 | Approved with Comments | 2024-10-24 | NO | Overdue |  | 131242-WSD11-DR-9000 | NA | "THP Cast in Layout Inside Bio-solid Building" | 2024-07-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-12 | 73 | AWC | 2024-07-23 | A | 000580 | 2024-07-23 | 00 | 1 | Approved with Comments | AWC | 2024-10-24 | Overdue | 0 | AWC | AWC
3559 | 000581 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 3100 | A.1 | 131242-WSW41-SD-S-3100-A.1 | 2024-07-23 | Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details | For Information | 2024-08-21 | 2024-08-14 | For Information |  | YES | NA |  | 131242-WSW41-SD-3100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" | 2024-07-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-12 | 22 | INF | 2025-12-17 | X | 000581&&001085&&001906 | 2024-07-23, 2025-03-04, 2025-12-17 | 00 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
3560 | 000582 | 00 | Sithu | Const; | NA | 131242 | WSW41 | SD | S | 1150 | A.1 | 131242-WSW41-SD-S-1150-A.1 | 2024-07-23 | Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details | For Information | 2024-08-21 | 2024-08-13 | For Information |  | YES | NA |  | 131242-WSW41-SD-1150 | NA | "Compressor System Plinths at Biosolids Building(+22.6m SHD)GL H-J/5-6 Setting Out Plan and Details" | 2024-07-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-12 | 21 | INF | 2024-07-23 | A.1 | 000582 | 2024-07-23 | 00 | 1 | For Information | INF | 2024-09-02 | Overdue | 0 | INF | INF
3561 | 000583 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 0 | 131242-WSW41-VI-I-0003-0 | 2024-07-24 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2024-08-22 | 2024-09-02 | Not Approved | 2024-09-20 | YES | Resubmitted |  | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-07 | 40 | NAP | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3562 | 000583 | 01 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 1 | 131242-WSW41-VI-I-0003-1 | 2024-11-29 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-12-19 | 2025-02-25 | Not Approved | 2025-03-17 | YES | Resubmitted |  | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-13 | 88 | NAP | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3563 | 000583 | 02 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 2 | 131242-WSW41-VI-I-0003-2 | 2025-03-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-04-08 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-02 | 6 | AWC | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3564 | 000583 | 03 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0003 | 3 | 131242-WSW41-VI-I-0003-3 | 2025-06-19 | Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND) | Rev 3: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-07-09 | 2025-07-10 | Approved with Comments | 2025-07-30 | NO | Overdue |  | 131242-WSW41-VI-0003 | NA | "Preliminary Design and Vendor Approval of Air Compressor System (ICA) (INGERSOLL-RAND)" && "Preliminary Design and Vendor Approval of Diffuser (Xylem)" && "Vendor Approval of C&S Contractor (DingXin Construction Pte Ltd)" | 2023-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-03 | 21 | AWC | 2025-06-19 | 3 | 000139&&000449&&000583 | 2023-10-25, 2024-04-25, 2024-07-24, 2024-11-06, 2024-11-29, 2025-03-19, 2025-06-19 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2025-07-30 | Overdue | 0 | AWC | AWC
3565 | 000584 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0027 | 0 | 131242-WSW41-MI-P-0027-0 | 2024-07-24 | Process & MEICA Meeting Minutes 0027_20240704 | Rev 0: For Information | 2024-08-22 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-MI-0027 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0027,0028_June" && "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-07 | 36 | INF | 2024-08-29 | 0 | 000562&&000584&&000684 | 2024-07-12, 2024-07-24, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3566 | 000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0013 | 0 | 131242-WSW41-SP-C-0013-0 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-SP-0013 | NA | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | 2024-07-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 18 | INF | 2024-07-25 | 0 | 000585 | 2024-07-25 | 00 | 1 | For Information | INF | 2024-08-30 | Overdue | 0 | INF | INF
3567 | 000585 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0014 | 0 | 131242-WSW41-SP-C-0014-0 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 | For Information | 2024-08-23 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-SP-0014 | NA | "Monthly Raw Material Test Reports for Concrete (Alliance)-Feb & Mar 2024 " | 2024-07-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 18 | INF | 2024-07-25 | 0 | 000585 | 2024-07-25 | 00 | 1 | For Information | INF | 2024-08-30 | Overdue | 0 | INF | INF
3568 | 000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0016 | 0 | 131242-WSW41-SP-C-0016-0 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-SP-0016 | NA | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 18 | INF | 2024-07-25 | 0 | 000586 | 2024-07-25 | 00 | 1 | For Information | INF | 2024-08-30 | Overdue | 0 | INF | INF
3569 | 000586 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0017 | 0 | 131242-WSW41-SP-C-0017-0 | 2024-07-25 | Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024 | For Information | 2024-08-23 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-SP-0017 | NA | "Monthly Raw Material Test Reports for Concrete (PanUnited)-April & May 2024" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 18 | INF | 2024-07-25 | 0 | 000586 | 2024-07-25 | 00 | 1 | For Information | INF | 2024-08-30 | Overdue | 0 | INF | INF
3570 | 000587 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0008 | 0 | 131242-WSW41-VI-S-0008-0 | 2024-07-25 | Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd. | Approved | 2024-08-23 | 2024-08-12 | Approved | 2024-08-30 | YES | Resubmitted |  | 131242-WSW41-VI-0008 | NA | "Preliminary Design and Vendor Approval For Lifting Equipment - Electric Hoist & Davit/Jib Crane (Helmsion)" && "Vendor Approval of Rebar Supplier-Lian Bee Metal Pte Ltd" && "Vendor Approval of Steel Structure Fabricator and Installer – Sanhe Construction Pte. Ltd." | 2023-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-08 | 18 | APP | 2025-06-16 | 2 | 000074&&000587&&000802 | 2023-08-16, 2024-07-25, 2024-11-06, 2025-01-26, 2025-06-16 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
3571 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-0001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3572 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-0002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3573 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-0003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3574 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-1000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3575 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-1001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3576 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-1002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3577 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-1003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3578 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-1004_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3579 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-2000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3580 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-3000_URA | NA | "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2024-10-09 | A | 000588 | 2024-07-25, 2024-08-24, 2024-10-09 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3581 | 000588 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA-A | 2024-07-25 | THP URA Submission | Not Approved | 2024-08-23 | 2024-08-02 | Not Approved | 2024-08-23 | YES | Resubmitted |  | 131242-WSD11-DR-9000_URA | NA | "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 8 | NAP | 2024-10-09 | A | 000588 | 2024-07-25, 2024-08-24, 2024-10-09 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3582 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-12 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-0001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3583 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-0002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3584 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-0003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3585 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-1000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3586 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-1001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3587 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-1002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3588 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-1003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3589 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-1004_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3590 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-2000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
3591 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-3000_URA | NA | "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2024-10-09 | A | 000588 | 2024-07-25, 2024-08-24, 2024-10-09 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3592 | 000588 | 01 | Zora | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA-A | 2024-08-24 | THP URA Submission | Rev.1: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-20 | 2024-09-13 | Not Approved | 2024-10-03 | YES | Resubmitted |  | 131242-WSD11-DR-9000_URA | NA | "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-07 | 20 | NAP | 2024-10-09 | A | 000588 | 2024-07-25, 2024-08-24, 2024-10-09 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3593 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0001_URA | A | 131242-WSD11-DR-A-0001_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-10-29 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3594 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0002_URA | A | 131242-WSD11-DR-A-0002_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3595 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 0003_URA | A | 131242-WSD11-DR-A-0003_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-0003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3596 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1000_URA | A | 131242-WSD11-DR-A-1000_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3597 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1001_URA | A | 131242-WSD11-DR-A-1001_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1001_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3598 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1002_URA | A | 131242-WSD11-DR-A-1002_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1002_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3599 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1003_URA | A | 131242-WSD11-DR-A-1003_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1003_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3600 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 1004_URA | A | 131242-WSD11-DR-A-1004_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-1004_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3601 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 2000_URA | A | 131242-WSD11-DR-A-2000_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-2000_URA | NA | "ST617 Revised THP-PF-01 and THP-PF-02 Archi Drawing for URA resubmission" && "THP URA Submission" | 2024-07-25 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2025-06-23 | A | 000588&&001394 | 2024-07-25, 2024-08-24, 2024-10-09, 2025-06-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
3602 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 3000_URA | A | 131242-WSD11-DR-A-3000_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-3000_URA | NA | "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2024-10-09 | A | 000588 | 2024-07-25, 2024-08-24, 2024-10-09 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3603 | 000588 | 02 | Thet Myo | CSA | NA | 131242 | WSD11 | DR | A | 9000_URA | A | 131242-WSD11-DR-A-9000_URA-A | 2024-10-09 | THP URA Submission | Rev 2: Approved with comments. Attached comment file for information. Resubmission is not needed. | 2024-11-07 | 2024-10-29 | Approved with Comments |  | YES | NA |  | 131242-WSD11-DR-9000_URA | NA | "THP URA Submission" | 2024-07-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-23 | 20 | AWC | 2024-10-09 | A | 000588 | 2024-07-25, 2024-08-24, 2024-10-09 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2024-11-18 | Overdue | 0 | AWC | AWC
3604 | 000589 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 0 | 131242-WST02-VI-E-0007-0 | 2024-07-26 | Vendor Approval of Earthing System & LPS Material | Rev 0: Approved with Comments. To revise and resubmit. Please refer to attached sheet for comments | 2024-08-26 | 2024-08-05 | Approved with Comments | 2024-08-26 | YES | Resubmitted |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-09 | 10 | AWC | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3605 | 000589 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0007 | 1 | 131242-WST02-VI-E-0007-1 | 2024-09-02 | Vendor Approval of Earthing System & LPS Material (Heng) | Rev 1: Approved. | 2024-09-20 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-16 | 57 | APP | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
3606 | 000590 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 0 | 131242-WST02-DS-E-0004-0 | 2024-07-27 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 0: Rejected. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 | Rejected | 2024-09-04 | YES | Resubmitted |  | 131242-WST02-DS-0004 | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-10 | 19 | REJ | 2025-04-25 | 0 | 000553&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | REJ | REJ
3607 | 000590 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 1 | 131242-WST02-DS-E-0004-1 | 2024-12-02 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 1: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-12-20 | 2025-01-16 | Approved with Comments | 2025-02-05 | YES | Resubmitted |  | 131242-WST02-DS-0004 | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-16 | 45 | AWC | 2025-04-25 | 0 | 000553&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
3608 | 000590 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0004 | 2 | 131242-WST02-DS-E-0004-2 | 2025-04-09 | SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB | Rev 2: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2025-04-29 | 2025-05-08 | Approved with Comments | 2025-05-28 | NO | Overdue | Pending reply from Sunlight. Will follow-up with Sunlight. | 131242-WST02-DS-0004 | NA | "Data Sheet for Clean Gas devices, Public devices, Fire alarm field devices (Building Services)- Pacific Reliance " && "Data Sheet, Drawing and Calculation of SSN Diffuser" && "SSN and THP Data Sheet for LV Switchgear, MCC Panel and MDB" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-23 | 29 | AWC | 2025-04-25 | 0 | 000553&&000590&&001252 | 2024-07-09, 2024-07-27, 2024-12-02, 2025-04-09, 2025-04-25 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
3609 | 000591 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 0 | 131242-WSD11-CL-P-0003-0 | 2024-07-28 | PLant Drain Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-08-26 | 2024-09-02 | Not Approved | 2024-09-20 | YES | Resubmitted |  | 131242-WSD11-CL-0003 | NA | "PLant Drain Hydraulic Calculation" | 2024-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-17 | 36 | NAP | 2024-10-21 | 1 | 000591 | 2024-07-28, 2024-10-21 | 00, 01 | 2 | Approved | APP |  |  | 0 | NAP | NAP
3610 | 000591 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0003 | 1 | 131242-WSD11-CL-P-0003-1 | 2024-10-21 | PLant Drain Hydraulic Calculation | Rev 1: Approved | 2024-11-11 | 2024-11-15 | Approved |  | YES | NA |  | 131242-WSD11-CL-0003 | NA | "PLant Drain Hydraulic Calculation" | 2024-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-04 | 25 | APP | 2024-10-21 | 1 | 000591 | 2024-07-28, 2024-10-21 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3611 | 000592 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0006 | 0 | 131242-WST02-VI-E-0006-0 | 2024-07-28 | Vendor Approval of SS Cable Ladder, Trays and Accessories | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-08-26 | 2024-08-15 | Approved with Comments | 2024-09-04 | NO | Overdue | To follow-up with UNITED ULI. | 131242-WST02-VI-0006 | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-11 | 18 | AWC | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3612 | 000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5351 | 0 | 131242-WST02-DS-M-5351-0 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-DS-5351 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-17 | 73 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3613 | 000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5361 | 0 | 131242-WST02-DS-M-5361-0 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-DS-5361 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-17 | 73 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3614 | 000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5371 | 0 | 131242-WST02-DS-M-5371-0 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-DS-5371 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-17 | 73 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3615 | 000593 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5381 | 0 | 131242-WST02-DS-M-5381-0 | 2024-07-28 | Progressive Cavity Pump Data Sheet | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-26 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-DS-5381 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-17 | 73 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3616 | 000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5351 | 1 | 131242-WST02-DS-M-5351-1 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5351 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-06 | 103 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-24 | Overdue | 0 | AWC | AWC
3617 | 000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5361 | 1 | 131242-WST02-DS-M-5361-1 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | Approved with Comments | 2025-04-24 | NO | Overdue |  | 131242-WST02-DS-5361 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 103 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-24 | Overdue | 0 | AWC | AWC
3618 | 000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5371 | 1 | 131242-WST02-DS-M-5371-1 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | Approved with Comments | 2025-04-24 | NO | Overdue |  | 131242-WST02-DS-5371 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 103 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-24 | Overdue | 0 | AWC | AWC
3619 | 000593 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5381 | 1 | 131242-WST02-DS-M-5381-1 | 2024-12-23 | Progressive Cavity Pump Data Sheet | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-13 | 2025-04-05 | Approved with Comments | 2025-04-24 | NO | Overdue |  | 131242-WST02-DS-5381 | NA | "Progressive Cavity Pump Data Sheet" | 2024-07-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 103 | AWC | 2024-12-23 | 1 | 000593 | 2024-07-28, 2024-12-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-04-24 | Overdue | 0 | AWC | AWC
3620 | 000594 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | E | 0003 | 0 | 131242-WSW41-PO-E-0003-0 | 2024-07-29 | Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight) | Rev 0: For Information. | 2024-08-27 | 2024-08-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0003 | NA | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" && "Unpriced PO for Non-return Check Valve (Breen International)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-07-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-18 | 7 | INF | 2025-08-01 | 0 | 000594&&001502&&001514 | 2024-07-29, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3621 | 000595 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0007 | 0 | 131242-WSW41-PO-M-0007-0 | 2024-07-30 | Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen) | For Information | 2024-08-28 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-PO-0007 | NA | "Unpriced PO for Cable Support System (Jiangsu HDMann) " && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | 2024-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-19 | 30 | INF | 2025-08-01 | 0 | 000595&&001115&&001506 | 2024-07-30, 2025-03-11, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3622 | 000596 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0035 | 0 | 131242-WSW41-LT-PM-0035-0 | 2024-07-30 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024 | Please refer to S.O. Correspondence No.229. | 2024-08-28 | 2024-10-07 | Approved |  | YES | NA |  | 131242-WSW41-LT-0035 | NA | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From S.O. on 15 January 2024" | 2024-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-19 | 69 | APP | 2024-07-30 | 0 | 000596 | 2024-07-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
3623 | 000597 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 0 | 131242-WSD11-CL-P-0006-0 | 2024-07-30 | Air Compressor Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-04 | Approved with Comments | 2024-09-24 | YES | Resubmitted |  | 131242-WSD11-CL-0006 | NA | "Air Compressor Pressure Loss Calculation" && "Support design for compressed Air system <2m" | 2024-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 36 | AWC | 2025-01-10 | A | 000597&&000959 | 2024-07-30, 2024-09-30, 2025-01-10 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3624 | 000597 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0006 | 1 | 131242-WSD11-CL-P-0006-1 | 2024-09-30 | Air Compressor Pressure Loss Calculation | Rev 1: Approved with Comments. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | Approved with Comments | 2024-11-25 | NO | Overdue |  | 131242-WSD11-CL-0006 | NA | "Air Compressor Pressure Loss Calculation" && "Support design for compressed Air system <2m" | 2024-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-14 | 36 | AWC | 2025-01-10 | A | 000597&&000959 | 2024-07-30, 2024-09-30, 2025-01-10 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3625 | 000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5009 | A | 131242-WST02-DR-M-5009-A | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | Approved with Comments | 2024-09-20 | NO | Overdue | Shall update and submit under as built drawing | 131242-WST02-DR-5009 | NA | "Underground Cast In Schedule and Details" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 34 | AWC | 2024-07-30 | A | 000598 | 2024-07-30 | 00 | 1 | Approved with Comments | AWC | 2024-09-20 | Overdue | 0 | AWC | AWC
3626 | 000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | DR | M | 5010 | A | 131242-WST02-DR-M-5010-A | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | Approved with Comments | 2024-09-20 | NO | Overdue |  | 131242-WST02-DR-5010 | NA | "Underground Cast In Schedule and Details" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 34 | AWC | 2024-07-30 | A | 000598 | 2024-07-30 | 00 | 1 | Approved with Comments | AWC | 2024-09-20 | Overdue | 0 | AWC | AWC
3627 | 000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7008 | A | 131242-WST02-SH-M-7008-A | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | Approved with Comments | 2024-09-20 | NO | Overdue |  | 131242-WST02-SH-7008 | NA | "Underground Cast In Schedule and Details" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 34 | AWC | 2024-07-30 | A | 000598 | 2024-07-30 | 00 | 1 | Approved with Comments | AWC | 2024-09-20 | Overdue | 0 | AWC | AWC
3628 | 000598 | 00 | Kyaw Myo | Piping | NA | 131242 | WST02 | SH | M | 7009 | A | 131242-WST02-SH-M-7009-A | 2024-07-30 | Underground Cast In Schedule and Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-28 | 2024-09-02 | Approved with Comments | 2024-09-20 | NO | Overdue |  | 131242-WST02-SH-7009 | NA | "Underground Cast In Schedule and Details" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 34 | AWC | 2024-07-30 | A | 000598 | 2024-07-30 | 00 | 1 | Approved with Comments | AWC | 2024-09-20 | Overdue | 0 | AWC | AWC
3629 | 000599 | 00 | Balaji/ Karthik | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 0 | 131242-WSW41-VI-I-0004-0 | 2024-07-30 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-28 | 2024-10-10 | Not Approved | 2024-10-30 | YES | Resubmitted |  | 131242-WSW41-VI-0004 | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-13 | 72 | NAP | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | Approved | APP |  |  | 0 | NAP | NAP
3630 | 000599 | 01 | Low | EICA | NA | 131242 | WSW41 | VI | I | 0004 | 1 | 131242-WSW41-VI-I-0004-1 | 2024-11-02 | Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland) | Rev 1: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-21 | 2024-12-18 | Not Approved | 2025-01-08 | NO | Overdue |  | 131242-WSW41-VI-0004 | NA | "Preliminary Design and Vendor Approval of ATEX/IECex Hazardous Risk Assessor (TUV Rheinland)" && "Vendor Approval of Centrifugal Pump (KSB Singapore (Asia Pacific) Pte Ltd)" && "Vendor Approval of ERSS Works (Singlee)" | 2023-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-16 | 46 | NAP | 2025-05-30 | 1 | 000103&&000450&&000599 | 2023-09-18, 2024-04-25, 2024-07-30, 2024-11-02, 2025-05-30 | 00, 01 | 5 | Approved | APP |  |  | 0 | NAP | NAP
3631 | 000600 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0004 | 0 | 131242-WSW41-QA-M-0004-0 | 2024-07-31 | Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings | Rev 0: Approved | 2024-08-29 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-14 | 33 | APP | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | APP | APP
3632 | 000601 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 0 | 131242-WSD11-SP-I-0001-0 | 2024-07-31 | THP Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-08-29 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-SP-0001 | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-14 | 70 | AWC | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3633 | 000601 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 1 | 131242-WSD11-SP-I-0001-1 | 2025-05-19 | THP Functional Design Specification | Rev.1: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-06-06 | 2025-07-04 | Approved with Comments |  | YES | NA |  | 131242-WSD11-SP-0001 | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-02 | 46 | AWC | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3634 | 000601 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0001 | 2 | 131242-WSD11-SP-I-0001-2 | 2025-08-12 | THP Functional Design Specification | Rev.2: Approved with comments. Now no resubmittal is required. Resubmittal is required if any changes during the detailing. | 2025-09-01 | 2025-10-08 | Approved with Comments |  | YES | NA |  | 131242-WSD11-SP-0001 | NA | "THP Functional Design Specification" && "THP System Control Philosophy" | 2023-12-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-26 | 57 | AWC | 2025-08-12 | 2 | 000224&&000601 | 2023-12-01, 2024-03-01, 2024-07-31, 2025-05-19, 2025-08-12 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-28 | Overdue | 0 | AWC | AWC
3635 | 000602 | 00 | Low | EICA | NA | 131242 | WSD11 | SP | I | 0003 | 0 | 131242-WSD11-SP-I-0003-0 | 2024-07-31 | THP Alarm List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-08-29 | 2024-11-08 | Not Approved | 2024-11-28 | NO | Overdue |  | 131242-WSD11-SP-0003 | NA | "THP Alarm List" | 2024-07-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 100 | NAP | 2024-07-31 | 0 | 000602 | 2024-07-31 | 00 | 1 | Not Approved | NAP | 2024-11-28 | Overdue | 0 | NAP | NAP
3636 | 000603 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 1000 | 0 | 131242-WST02-CL-M-1000-0 | 2024-07-31 | SSN Underground Piping Stress Calculation Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-08-29 | 2024-09-02 | Approved with Comments | 2024-09-20 | NO | Overdue | The Only comment is to get PE endorsement (Mech Piping PE) | 131242-WST02-CL-1000 | NA | "C4B SSN Drain Hydraulic Calculation" && "SSN Underground Piping Stress Calculation Report" | 2024-07-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 33 | AWC | 2026-02-24 | 0 | 000603&&002018 | 2024-07-31, 2026-02-24 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3637 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | A | 131242-WST02-DR-EI-7000-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3638 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | A | 131242-WST02-DR-EI-7001-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3639 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | A | 131242-WST02-DR-EI-7002-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3640 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | A | 131242-WST02-DR-EI-7003-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3641 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | A | 131242-WST02-DR-EI-7004-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3642 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | A | 131242-WST02-DR-EI-7005-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3643 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | A | 131242-WST02-DR-EI-7006-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | REJ | REJ
3644 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | A | 131242-WST02-DR-EI-7007-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | REJ | REJ
3645 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | A | 131242-WST02-DR-EI-7008-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | REJ | REJ
3646 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | A | 131242-WST02-DR-EI-7009-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7009 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2025-05-04 | D | 000441&&000604&&000605 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | REJ | REJ
3647 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | A | 131242-WST02-DR-EI-7010-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3648 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7011 | A | 131242-WST02-DR-EI-7011-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-15 | 48 | REJ | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3649 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | A | 131242-WST02-DR-EI-7020-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3650 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | A | 131242-WST02-DR-EI-7021-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3651 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | A | 131242-WST02-DR-EI-7022-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3652 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | A | 131242-WST02-DR-EI-7023-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3653 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | A | 131242-WST02-DR-EI-7024-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7024 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2025-05-04 | D | 000604&&000605&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | REJ | REJ
3654 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | A | 131242-WST02-DR-EI-7025-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3655 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | A | 131242-WST02-DR-EI-7026-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7026 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3656 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | A | 131242-WST02-DR-EI-7027-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7027 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3657 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | A | 131242-WST02-DR-EI-7028-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7028 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3658 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | A | 131242-WST02-DR-EI-7029-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7029 | NA | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2025-05-04 | D | 000604&&000605 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | REJ | REJ
3659 | 000604 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7030 | A | 131242-WST02-DR-EI-7030-A | 2024-08-01 | LVSG Schematic Diagram | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-7030 | NA | "LVSG Schematic Diagram" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | B | 000604&&000605&&001809 | 2024-08-01, 2024-11-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3660 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | A | 131242-WST02-DR-EP-7100-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3661 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | A | 131242-WST02-DR-EP-7101-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3662 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | A | 131242-WST02-DR-EP-7102-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3663 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | A | 131242-WST02-DR-EP-7103-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-15 | 48 | NAP | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3664 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | A | 131242-WST02-DR-EP-7104-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3665 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | A | 131242-WST02-DR-EP-7105-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3666 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | A | 131242-WST02-DR-EP-7106-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3667 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | A | 131242-WST02-DR-EP-7107-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3668 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | A | 131242-WST02-DR-EP-7108-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3669 | 000605 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | A | 131242-WST02-DR-EP-7109-A | 2024-08-01 | SSN LVSG 0101AB Single Line Diagram | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-21 | 48 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3670 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | B | 131242-WST02-DR-EI-7000-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3671 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | B | 131242-WST02-DR-EI-7001-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3672 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | B | 131242-WST02-DR-EI-7002-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3673 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | B | 131242-WST02-DR-EI-7003-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3674 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | B | 131242-WST02-DR-EI-7004-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3675 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | B | 131242-WST02-DR-EI-7005-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3676 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | B | 131242-WST02-DR-EI-7006-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | NAP | NAP
3677 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | B | 131242-WST02-DR-EI-7007-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | NAP | NAP
3678 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | B | 131242-WST02-DR-EI-7008-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | NAP | NAP
3679 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | B | 131242-WST02-DR-EI-7009-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7009 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-04 | D | 000441&&000604&&000605 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
3680 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | B | 131242-WST02-DR-EI-7010-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3681 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7011 | B | 131242-WST02-DR-EI-7011-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3682 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | B | 131242-WST02-DR-EI-7020-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3683 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | B | 131242-WST02-DR-EI-7021-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3684 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | B | 131242-WST02-DR-EI-7022-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3685 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | B | 131242-WST02-DR-EI-7023-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3686 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | B | 131242-WST02-DR-EI-7024-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7024 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-04 | D | 000604&&000605&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
3687 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | B | 131242-WST02-DR-EI-7025-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3688 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | B | 131242-WST02-DR-EI-7026-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7026 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3689 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | B | 131242-WST02-DR-EI-7027-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7027 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3690 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | B | 131242-WST02-DR-EI-7028-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7028 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3691 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | B | 131242-WST02-DR-EI-7029-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7029 | NA | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-05-04 | D | 000604&&000605 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | NAP | NAP
3692 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7030 | B | 131242-WST02-DR-EI-7030-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7030 | NA | "LVSG Schematic Diagram" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001809 | 2024-08-01, 2024-11-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3693 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | B | 131242-WST02-DR-EP-3000-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | NAP | NAP
3694 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | B | 131242-WST02-DR-EP-3001-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3695 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | B | 131242-WST02-DR-EP-3002-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3696 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | B | 131242-WST02-DR-EP-3003-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3697 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | B | 131242-WST02-DR-EP-3004-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3698 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | B | 131242-WST02-DR-EP-3005-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3699 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | B | 131242-WST02-DR-EP-3006-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3700 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | B | 131242-WST02-DR-EP-3007-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3701 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | B | 131242-WST02-DR-EP-3008-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 39 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
3702 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | B | 131242-WST02-DR-EP-3009-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 39 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
3703 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | B | 131242-WST02-DR-EP-3010-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 39 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3704 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | B | 131242-WST02-DR-EP-3011-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 39 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3705 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | B | 131242-WST02-DR-EP-7100-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3706 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | B | 131242-WST02-DR-EP-7101-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3707 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | B | 131242-WST02-DR-EP-7102-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3708 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | B | 131242-WST02-DR-EP-7103-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3709 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | B | 131242-WST02-DR-EP-7104-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3710 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | B | 131242-WST02-DR-EP-7105-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3711 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | B | 131242-WST02-DR-EP-7106-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3712 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | B | 131242-WST02-DR-EP-7107-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3713 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | B | 131242-WST02-DR-EP-7108-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3714 | 000605 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | B | 131242-WST02-DR-EP-7109-B | 2024-11-21 | SSN LVSG 0101AB Single Line Diagram | Rev 1: Not approved. To revise and resubmit. | 2024-12-11 | 2024-12-30 | Not Approved | 2025-01-17 | YES | Resubmitted |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 39 | NAP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3715 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | C | 131242-WST02-DR-EI-7000-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3716 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | C | 131242-WST02-DR-EI-7001-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3717 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | C | 131242-WST02-DR-EI-7002-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3718 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | C | 131242-WST02-DR-EI-7003-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3719 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | C | 131242-WST02-DR-EI-7004-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3720 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | C | 131242-WST02-DR-EI-7005-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3721 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | C | 131242-WST02-DR-EI-7006-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
3722 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | C | 131242-WST02-DR-EI-7007-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | AWC | AWC
3723 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | C | 131242-WST02-DR-EI-7008-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | AWC | AWC
3724 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | C | 131242-WST02-DR-EI-7009-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7009 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-04 | D | 000441&&000604&&000605 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3725 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | C | 131242-WST02-DR-EI-7010-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3726 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | C | 131242-WST02-DR-EI-7020-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3727 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | C | 131242-WST02-DR-EI-7021-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3728 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | C | 131242-WST02-DR-EI-7022-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3729 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | C | 131242-WST02-DR-EI-7023-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3730 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | C | 131242-WST02-DR-EI-7024-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7024 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-04 | D | 000604&&000605&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3731 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | C | 131242-WST02-DR-EI-7025-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3732 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | C | 131242-WST02-DR-EI-7026-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7026 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3733 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | C | 131242-WST02-DR-EI-7027-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7027 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3734 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | C | 131242-WST02-DR-EI-7028-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7028 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3735 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | C | 131242-WST02-DR-EI-7029-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7029 | NA | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-05-04 | D | 000604&&000605 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | AWC | AWC
3736 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | C | 131242-WST02-DR-EP-3000-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | AWC | AWC
3737 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | C | 131242-WST02-DR-EP-3001-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3738 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | C | 131242-WST02-DR-EP-3002-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3739 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | C | 131242-WST02-DR-EP-3003-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3740 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | C | 131242-WST02-DR-EP-3004-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3741 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | C | 131242-WST02-DR-EP-3005-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3742 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | C | 131242-WST02-DR-EP-3006-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3743 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | C | 131242-WST02-DR-EP-3007-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
3744 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | C | 131242-WST02-DR-EP-3008-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
3745 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | C | 131242-WST02-DR-EP-3009-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | AWC | AWC
3746 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | C | 131242-WST02-DR-EP-3010-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3747 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | C | 131242-WST02-DR-EP-3011-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3748 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | C | 131242-WST02-DR-EP-7100-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3749 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | C | 131242-WST02-DR-EP-7101-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3750 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | C | 131242-WST02-DR-EP-7102-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3751 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | C | 131242-WST02-DR-EP-7103-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3752 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | C | 131242-WST02-DR-EP-7104-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3753 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | C | 131242-WST02-DR-EP-7105-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3754 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | C | 131242-WST02-DR-EP-7106-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3755 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | C | 131242-WST02-DR-EP-7107-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3756 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | C | 131242-WST02-DR-EP-7108-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3757 | 000605 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | C | 131242-WST02-DR-EP-7109-C | 2025-01-21 | SSN LVSG 0101AB Single Line Diagram | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-10 | 2025-02-07 | Approved with Comments | 2025-02-27 | YES | Resubmitted |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-04 | 17 | AWC | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3758 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7000 | D | 131242-WST02-DR-EI-7000-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "Plumbing and Sanitary (SSN Area)" && "SSN Control System Architecture Drawing" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Overall Single Line Diagram" && "SSN Plumbing and Sanitary " | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-10-29 | A.4 | 000188&&000189&&000201&&000219&&000220&&000225&&000401&&000461&&000604&&000605 | 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2024-03-26, 2024-05-06, 2024-08-01, 2024-08-26, 2024-09-26, 2024-09-28, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-24, 2025-04-03, 2025-05-04, 2025-07-15, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 24 | Approved with Comments | AWC |  |  | 0 | APP | APP
3759 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7001 | D | 131242-WST02-DR-EI-7001-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | APP | APP
3760 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7002 | D | 131242-WST02-DR-EI-7002-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | APP | APP
3761 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7003 | D | 131242-WST02-DR-EI-7003-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | APP | APP
3762 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7004 | D | 131242-WST02-DR-EI-7004-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7004 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-18 | A | 000220&&000308&&000492&&000604&&000605&&001284&&001305 | 2023-11-30, 2024-02-13, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-13, 2025-05-18 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | APP | APP
3763 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7005 | D | 131242-WST02-DR-EI-7005-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7005 | NA | "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-18 | A | 000220&&000308&&000441&&000492&&000604&&000605&&001305 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-05-18 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3764 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7006 | D | 131242-WST02-DR-EI-7006-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7006 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | APP | APP
3765 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7007 | D | 131242-WST02-DR-EI-7007-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7007 | NA | "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" && "SSN sample AC/DC/IO circuit diagram" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-04 | D | 000220&&000308&&000441&&000492&&000604&&000605 | 2023-11-30, 2024-04-16, 2024-07-06, 2024-08-01, 2024-08-20, 2024-10-21, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04 | 00, 01, 02, 03 | 12 | Approved | APP |  |  | 0 | APP | APP
3766 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7008 | D | 131242-WST02-DR-EI-7008-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7008 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2024-07-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-04 | D | 000308&&000441&&000604&&000605 | 2024-07-06, 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-03-27, 2025-05-04 | 00, 01, 02, 03 | 7 | Approved | APP |  |  | 0 | APP | APP
3767 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7009 | D | 131242-WST02-DR-EI-7009-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7009 | NA | "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-04 | D | 000441&&000604&&000605 | 2024-08-01, 2024-08-20, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | APP | APP
3768 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7010 | D | 131242-WST02-DR-EI-7010-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | APP | APP
3769 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7020 | D | 131242-WST02-DR-EI-7020-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
3770 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7021 | D | 131242-WST02-DR-EI-7021-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
3771 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7022 | D | 131242-WST02-DR-EI-7022-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
3772 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7023 | D | 131242-WST02-DR-EI-7023-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
3773 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7024 | D | 131242-WST02-DR-EI-7024-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7024 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-04 | D | 000604&&000605&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | APP | APP
3774 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7025 | D | 131242-WST02-DR-EI-7025-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3775 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7026 | D | 131242-WST02-DR-EI-7026-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7026 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
3776 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7027 | D | 131242-WST02-DR-EI-7027-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7027 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
3777 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7028 | D | 131242-WST02-DR-EI-7028-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7028 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
3778 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7029 | D | 131242-WST02-DR-EI-7029-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7029 | NA | "LVSG Schematic Diagram" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-05-04 | D | 000604&&000605 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 4 | Approved | APP |  |  | 0 | APP | APP
3779 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | D | 131242-WST02-DR-EP-3000-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | APP | APP
3780 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | D | 131242-WST02-DR-EP-3001-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | APP | APP
3781 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | D | 131242-WST02-DR-EP-3002-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3782 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | D | 131242-WST02-DR-EP-3003-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | APP | APP
3783 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | D | 131242-WST02-DR-EP-3004-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
3784 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | D | 131242-WST02-DR-EP-3005-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3785 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | D | 131242-WST02-DR-EP-3006-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
3786 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | D | 131242-WST02-DR-EP-3007-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | APP | APP
3787 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3008 | D | 131242-WST02-DR-EP-3008-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | APP | APP
3788 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3009 | D | 131242-WST02-DR-EP-3009-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | APP | APP
3789 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3010 | D | 131242-WST02-DR-EP-3010-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3790 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3011 | D | 131242-WST02-DR-EP-3011-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | APP | APP
3791 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7100 | D | 131242-WST02-DR-EP-7100-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7100 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3792 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7101 | D | 131242-WST02-DR-EP-7101-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7101 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3793 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7102 | D | 131242-WST02-DR-EP-7102-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7102 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3794 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7103 | D | 131242-WST02-DR-EP-7103-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7103 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000419&&000605&&000870 | 2024-04-04, 2024-08-01, 2024-10-18, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
3795 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7104 | D | 131242-WST02-DR-EP-7104-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7104 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Panel GA & Wiring drawing for BS Systems" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870&&001305 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-05-18, 2025-07-24 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
3796 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7105 | D | 131242-WST02-DR-EP-7105-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7105 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3797 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7106 | D | 131242-WST02-DR-EP-7106-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7106 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3798 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7107 | D | 131242-WST02-DR-EP-7107-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7107 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3799 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7108 | D | 131242-WST02-DR-EP-7108-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7108 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3800 | 000605 | 03 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7109 | D | 131242-WST02-DR-EP-7109-D | 2025-05-04 | SSN LVSG 0101AB Single Line Diagram | Approved | 2025-05-22 | 2025-05-25 | Approved |  | YES | NA |  | 131242-WST02-DR-7109 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-18 | 21 | APP | 2025-07-24 | C | 000605&&000870 | 2024-08-01, 2024-11-21, 2024-12-03, 2025-01-21, 2025-04-08, 2025-05-04, 2025-07-24 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | APP | APP
3801 | 000606 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 0 | 131242-WST02-VI-E-0008-0 | 2024-08-01 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-08-30 | 2024-09-24 | Approved with Comments | 2024-10-14 | YES | Resubmitted |  | 131242-WST02-VI-0008 | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-15 | 54 | AWC | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3802 | 000606 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0008 | 1 | 131242-WST02-VI-E-0008-1 | 2024-10-28 | Vendor Approval of Multi Cable Transit (MCT) (HILTI ) | Rev 1: Approved with comments. Resubmission not required. Refer to attached file for comments to note. | 2024-11-18 | 2024-11-24 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0008 | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-11 | 27 | AWC | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3803 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3000 | A | 131242-WST02-DR-EP-3000-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA | Combined with Prolog 000605 - GA, Schematic Diagram and SLD for WST02-LVSG-0101 A/B | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | REJ | REJ
3804 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3001 | A | 131242-WST02-DR-EP-3001-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3805 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3002 | A | 131242-WST02-DR-EP-3002-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3806 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3003 | A | 131242-WST02-DR-EP-3003-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3807 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3004 | A | 131242-WST02-DR-EP-3004-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3808 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3005 | A | 131242-WST02-DR-EP-3005-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3809 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3006 | A | 131242-WST02-DR-EP-3006-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3810 | 000607 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3007 | A | 131242-WST02-DR-EP-3007-A | 2024-08-01 | SSN LVSG 0101AB Outline GA Drawing | Rev 0: Rejected. Refer to attached file for comments. | 2024-08-30 | 2024-09-18 | Rejected |  | YES | NA |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 48 | REJ | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | REJ | REJ
3811 | 000608 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0008 | 0 | 131242-WSW41-PO-M-0008-0 | 2024-08-01 | Unpriced PO for Centrifugal Pump (KSB) | For Information | 2024-08-30 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-PO-0008 | NA | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" && "Unpriced PO for Centrifugal Pump (KSB)" && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 28 | INF | 2025-08-01 | 0 | 000608&&001163&&001507 | 2024-08-01, 2025-03-25, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3812 | 000609 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0009 | 0 | 131242-WSW41-PO-M-0009-0 | 2024-08-01 | Unpriced PO for FRP Tank (Jizhou Zhongyi) | For Information | 2024-08-30 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-PO-0009 | NA | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" && "Unpriced PO for FRP Tank (Jizhou Zhongyi)" && "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 28 | INF | 2025-08-01 | 0 | 000609&&001286&&001508 | 2024-08-01, 2025-05-13, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3813 | 000610 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | K | 2001 | 0 | 131242-WST02-VI-K-2001-0 | 2024-08-01 | LPS Sample Materials – U-Clamp Connector | Rev 0: Approved. Please refer to attached sheet for comments | 2024-08-30 | 2024-08-05 | Approved |  | YES | NA |  | 131242-WST02-VI-2001 | NA | "LPS Sample Materials – U-Clamp Connector" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 4 | APP | 2024-08-01 | 0 | 000610 | 2024-08-01 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
3814 | 000611 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 0 | 131242-WSW41-SP-C-0019-0 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-02 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WSW41-SP-0019 | NA | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | 2024-08-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-22 | 17 | AWC | 2024-08-02 | 0 | 000611 | 2024-08-02 | 00, 01 | 2 | Approved with Comments | AWC | 2024-09-06 | Overdue | 0 | AWC | AWC
3815 | 000611 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0019 | 1 | 131242-WSW41-SP-C-0019-1 | 2024-08-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance) | Approved | 2024-08-23 | 2024-09-17 | Approved |  | YES | NA |  | 131242-WSW41-SP-0019 | NA | "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump, Bio Solid Building Inside Plinth C35/45 (Alliance)" | 2024-08-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-22 | 46 | APP | 2024-08-02 | 0 | 000611 | 2024-08-02 | 00, 01 | 2 | Approved with Comments | AWC | 2024-10-07 | Overdue | 0 | APP | APP
3816 | 000612 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0005 | 0 | 131242-WSW41-QA-M-0005-0 | 2024-08-02 | Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings | Rev 0: Approved | 2024-09-02 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0005 | NA | "FAT report for Power cable, Control Cable, Instrument Cable (Witness) " && "Inspection Test Plan for Formwork" && "Vendor Manufacturing Inspection Test Plan for cPVC Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-16 | 31 | APP | 2025-01-13 | 0 | 000148&&000612&&000969 | 2023-10-27, 2023-12-21, 2024-08-02, 2025-01-13 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
3817 | 000613 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0013 | 0 | 131242-WSW41-PC-W-0013-0 | 2024-08-02 | Payment Claim No.13 | Rev(0): Approved. Please refer to S.O. correspondence no. 0196 dated 5 August 2024. | 2024-09-02 | 2024-08-16 | Approved |  | YES | NA |  | 131242-WSW41-PC-0013 | NA | "Payment Claim No.13" | 2024-08-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-22 | 14 | APP | 2024-08-02 | 0 | 000613 | 2024-08-02 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
3818 | 000614 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0036 | 0 | 131242-WSW41-LT-PM-0036-0 | 2024-08-02 | NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions | Please refer to S.O. Correspondence No.229. | 2024-09-02 | 2024-10-07 | Approved |  | YES | NA |  | 131242-WSW41-LT-0036 | NA | "NOTICE for Potential Extension of Time and Cost in Lieu of New Clarification/ Instructions" | 2024-08-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-22 | 66 | APP | 2024-08-02 | 0 | 000614 | 2024-08-02 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
3819 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-S-1100-A.2 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-1100 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2024-08-27 | A.2 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3820 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1104 | A.3 | 131242-WST02-SD-S-1104-A.3 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-1104 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3821 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5100 | A.3 | 131242-WST02-SD-S-5100-A.3 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-5100 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2025-04-08 | A | 000615&&001209 | 2024-08-05, 2024-08-27, 2025-04-08 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3822 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5101 | A.3 | 131242-WST02-SD-S-5101-A.3 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-5101 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2025-04-08 | A | 000615&&001209 | 2024-08-05, 2024-08-27, 2025-04-08 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3823 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5102 | A.3 | 131242-WST02-SD-S-5102-A.3 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-5102 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3824 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5103 | A.3 | 131242-WST02-SD-S-5103-A.3 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-5103 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3825 | 000615 | 00 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5104 | A.3 | 131242-WST02-SD-S-5104-A.3 | 2024-08-05 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WST02-SD-5104 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 14 | AWC | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3826 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1100 | A.2 | 131242-WST02-SD-S-1100-A.2 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-16 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-1100 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2024-08-27 | A.2 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3827 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 1104 | A.3 | 131242-WST02-SD-S-1104-A.3 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-1104 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3828 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5100 | A.3 | 131242-WST02-SD-S-5100-A.3 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-5100 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2025-04-08 | A | 000615&&001209 | 2024-08-05, 2024-08-27, 2025-04-08 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | APP | APP
3829 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5101 | A.3 | 131242-WST02-SD-S-5101-A.3 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-5101 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" && "Steel Shop Drawings For SSN PR-001 (ST609)" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2025-04-08 | A | 000615&&001209 | 2024-08-05, 2024-08-27, 2025-04-08 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | APP | APP
3830 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5102 | A.3 | 131242-WST02-SD-S-5102-A.3 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-5102 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3831 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5103 | A.3 | 131242-WST02-SD-S-5103-A.3 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-5103 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3832 | 000615 | 01 | Sithu | Const; | NA | 131242 | WST02 | SD | S | 5104 | A.3 | 131242-WST02-SD-S-5104-A.3 | 2024-08-27 | Shop Drawing of Plant Drain Manholes Setting out plan and Details | Rev 1: Approved | 2024-09-24 | 2024-09-10 | Approved |  | YES | NA |  | 131242-WST02-SD-5104 | NA | "Shop Drawing of Plant Drain Manholes Setting out plan and Details" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-10 | 14 | APP | 2024-08-27 | A.3 | 000615 | 2024-08-05, 2024-08-27 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3833 | 000616 | 00 | Qili | Process | NA | 131242 | WST02 | CL | M | 0002 | 0 | 131242-WST02-CL-M-0002-0 | 2024-08-05 | Strength Calculation for Biomass Separator | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-02 | Approved with Comments | 2024-09-20 | NO | Overdue | Pending MP updates | 131242-WST02-CL-0002 | NA | "Engineering Calculation Report For Fire Hydrant Pipe" && "Engineering Calculation Report for Fire Hydrant Pipe" && "Preliminary Sizing Calculation for SSN Future OCF System" && "Siphonic System Schematic and Calculation" && "Strength Calculation for Biomass Separator" | 2023-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 28 | AWC | 2025-05-28 | 0 | 000096&&000193&&000206&&000616&&001326 | 2023-09-12, 2023-11-17, 2023-11-22, 2024-08-05, 2025-03-04, 2025-05-28 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3834 | 000617 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0009 | 0 | 131242-WSW41-PS-HS-0009-0 | 2024-08-05 | Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024 | For Information | 2024-09-03 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WSW41-PS-0009 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Monthly Progress Presentation No. 09 (0124)" && "Quarterly Risk Management Workshop 4th Quarterly RM Workshop – 22 Jul 2024" | 2023-10-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-19 | 16 | INF | 2024-08-05 | 0 | 000152&&000319&&000617 | 2023-10-30, 2024-02-21, 2024-08-05 | 00 | 3 | For Information | INF | 2024-09-10 | Overdue | 0 | INF | INF
3835 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | A | 131242-WSD11-DR-M-5051-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5051 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3836 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | A | 131242-WSD11-DR-M-5052-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5052 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3837 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | A | 131242-WSD11-DR-M-5053-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5053 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3838 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | A | 131242-WSD11-DR-M-5054-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5054 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3839 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | A | 131242-WSD11-DR-M-5071-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5071 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3840 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | A | 131242-WSD11-DR-M-5072-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5072 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3841 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | A | 131242-WSD11-DR-M-5073-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5073 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3842 | 000618 | 00 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | A | 131242-WSD11-DR-M-5081-A | 2024-08-05 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-03 | 2024-09-05 | Approved with Comments | 2024-09-25 | YES | Resubmitted |  | 131242-WSD11-DR-5081 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-25 | 31 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3843 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | B | 131242-WSD11-DR-M-5051-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-12 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted | All comments on 2D Drawing (Mech/Elec.) was closed, minor cmt on 3D, need QA/QC checklist, Drafting team will follow up..-> in 1 to 2 weeks | 131242-WSD11-DR-5051 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3844 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | B | 131242-WSD11-DR-M-5052-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5052 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3845 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | B | 131242-WSD11-DR-M-5053-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5053 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3846 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | B | 131242-WSD11-DR-M-5054-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5054 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3847 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | B | 131242-WSD11-DR-M-5071-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5071 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3848 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | B | 131242-WSD11-DR-M-5072-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5072 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3849 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | B | 131242-WSD11-DR-M-5073-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5073 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3850 | 000618 | 01 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | B | 131242-WSD11-DR-M-5081-B | 2024-10-22 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-20 | 2025-01-13 | Approved with Comments | 2025-01-31 | YES | Resubmitted |  | 131242-WSD11-DR-5081 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 83 | AWC | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3851 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5051 | C | 131242-WSD11-DR-M-5051-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5051 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3852 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5052 | C | 131242-WSD11-DR-M-5052-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5052 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3853 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5053 | C | 131242-WSD11-DR-M-5053-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5053 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3854 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5054 | C | 131242-WSD11-DR-M-5054-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5054 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3855 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5071 | C | 131242-WSD11-DR-M-5071-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5071 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3856 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5072 | C | 131242-WSD11-DR-M-5072-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5072 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3857 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5073 | C | 131242-WSD11-DR-M-5073-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5073 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3858 | 000618 | 02 | Yibo | Mech | NA | 131242 | WSD11 | DR | M | 5081 | C | 131242-WSD11-DR-M-5081-C | 2025-05-13 | GA for Compressor Air, Instrument Air Receiver & Air Dryer | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-06-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5081 | NA | "GA for Compressor Air, Instrument Air Receiver & Air Dryer" | 2024-08-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-05-27 | 328 | PEN | 2025-05-13 | C | 000618 | 2024-08-05, 2024-10-22, 2025-05-13 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-06-30 |  | 0 | PEN | PEN
3859 | 000619 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0006 | 0 | 131242-WSW41-RT-C-0006-0 | 2024-08-05 | Bored Piling Pile Eccentricity Reports (ECC 01 to 07) | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-09-03 | 2024-08-19 | Not Approved | 2024-09-06 | NO | Overdue |  | 131242-WSW41-RT-0006 | NA | "Bored Piling Pile Eccentricity Reports (ECC 01 to 07)" && "C4B Monthly Progress Report Number No.06 (10/23)" | 2023-11-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-19 | 14 | NAP | 2024-08-05 | 0 | 000174&&000619 | 2023-11-08, 2024-08-05 | 00 | 2 | Not Approved | NAP | 2024-09-06 | Overdue | 0 | NAP | NAP
3860 | 000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0015 | 0 | 131242-WSW41-SP-C-0015-0 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 | For Information |  | YES | NA |  | 131242-WSW41-SP-0015 | NA | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | 2024-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-25 | 14 | INF | 2024-08-05 | 0 | 000620 | 2024-08-05 | 00 | 1 | For Information | INF | 2024-09-06 | Overdue | 0 | INF | INF
3861 | 000620 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | SP | C | 0018 | 0 | 131242-WSW41-SP-C-0018-0 | 2024-08-05 | Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 | For Information | 2024-09-03 | 2024-08-19 | For Information |  | YES | NA |  | 131242-WSW41-SP-0018 | NA | "Monthly Raw Material Test Reports for Concrete (Alliance)-Apr & May 2024 " | 2024-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-25 | 14 | INF | 2024-08-05 | 0 | 000620 | 2024-08-05 | 00 | 1 | For Information | INF | 2024-09-06 | Overdue | 0 | INF | INF
3862 | 000621 | 00 | Qili | Process | NA | 131242 | WST02 | MM | P | 0001 | 0 | 131242-WST02-MM-P-0001-0 | 2024-08-05 | SSN Reactor Floor flat Design Memo | For Information | 2024-09-03 | 2024-08-21 | For Information |  | YES | NA |  | 131242-WST02-MM-0001 | NA | "Memo-Deed of Warranty for SSN 22kV DistrubutionTransformer " && "SSN Reactor Floor flat Design Memo" | 2024-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-25 | 16 | INF | 2025-07-22 | 1 | 000621&&001188 | 2024-08-05, 2025-04-03, 2025-07-22 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
3863 | 000622 | 00 | Qili | Process | NA | 131242 | WSW41 | MI | P | 0028 | 0 | 131242-WSW41-MI-P-0028-0 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0028 | NA | "BIM Bi-Weekly Meeting Minutes 0028_20240626" && "CSA Meeting Minutes 0027,0028_June" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-20 | 9 | INF | 2024-08-06 | 0 | 000558&&000562&&000622 | 2024-07-10, 2024-07-12, 2024-08-06 | 00 | 3 | For Information | INF | 2024-09-04 | Overdue | 0 | INF | INF
3864 | 000622 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0029 | 0 | 131242-WSW41-MI-P-0029-0 | 2024-08-06 | Process & MEICA Meeting Minutes 0028 & 0029_20240709 | For information | 2024-09-04 | 2024-08-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0029 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-08-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-26 | 9 | INF | 2024-08-29 | 0 | 000622&&000683&&000684 | 2024-08-06, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3865 | 000623 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 0 | 131242-WSW41-QA-E-0001-0 | 2024-08-06 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 84 | AWC | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | AWC | AWC
3866 | 000623 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 1 | 131242-WSW41-QA-E-0001-1 | 2024-11-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-11 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-05 | 23 | AWC | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | AWC | AWC
3867 | 000623 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 2 | 131242-WSW41-QA-E-0001-2 | 2025-01-16 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-30 | 33 | APP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | APP | APP
3868 | 000623 | 03 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 3 | 131242-WSW41-QA-E-0001-3 | 2025-02-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 3: Approved. | 2025-03-13 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-07 | 65 | APP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | APP | APP
3869 | 000623 | 04 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 4 | 131242-WSW41-QA-E-0001-4 | 2025-07-03 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 4: Approved with comments. To revise and resubmit. | 2025-07-23 | 2025-09-15 | Approved with Comments | 2025-10-03 | YES | Resubmitted |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-17 | 74 | AWC | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | AWC | AWC
3870 | 000623 | 05 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0001 | 5 | 131242-WSW41-QA-E-0001-5 | 2025-10-08 | Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR | Rev 5: Approved | 2025-10-28 | 2026-02-20 | Approved |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 135 | APP | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | APP | APP
3871 | 000624 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 0 | 131242-WSW41-QA-M-0003-0 | 2024-08-06 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 0: Not approved - Revise and Resubmit | 2024-09-04 | 2024-09-06 | Not Approved | 2024-09-26 | YES | Resubmitted |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 31 | NAP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | NAP | NAP
3872 | 000624 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 1 | 131242-WSW41-QA-M-0003-1 | 2024-10-09 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 1: Not approved - Revise and Resubmit | 2024-10-29 | 2024-10-25 | Not Approved | 2024-11-15 | YES | Resubmitted |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-23 | 16 | NAP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | NAP | NAP
3873 | 000624 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0003 | 2 | 131242-WSW41-QA-M-0003-2 | 2024-11-21 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower | Rev 2: Approved | 2024-12-11 | 2024-12-05 | Approved |  | YES | NA |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-05 | 14 | APP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | APP | APP
3874 | 000625 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0007 | 0 | 131242-WSW41-QA-M-0007-0 | 2024-08-06 | FAT Procedure for Air Receiver and Air Dryer (Compressor air system) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-04 | 2024-09-04 | Approved with Comments | 2024-09-24 | NO | Overdue |  | 131242-WSW41-QA-0007 | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-20 | 29 | AWC | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
3875 | 000626 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 0 | 131242-WST02-DS-E-0000-0 | 2024-08-07 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-05 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DS-0000 | NA | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 83 | AWC | 2024-12-19 | 1 | 000626 | 2024-08-07, 2024-12-19 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3876 | 000626 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0000 | 1 | 131242-WST02-DS-E-0000-1 | 2024-12-19 | SSN MV Cable and Pilot Cable Data Sheet and Specification | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-01-16 | Approved with Comments | 2025-02-05 | NO | Overdue |  | 131242-WST02-DS-0000 | NA | "SSN MV Cable and Pilot Cable Data Sheet and Specification" | 2024-08-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 28 | AWC | 2024-12-19 | 1 | 000626 | 2024-08-07, 2024-12-19 | 00, 01 | 2 | Approved with Comments | AWC | 2025-02-05 | Overdue | 0 | AWC | AWC
3877 | 000627 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0011 | 0 | 131242-WSW41-QA-C-0011-0 | 2024-08-07 | Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024 | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 | Approved with Comments | 2024-09-06 | NO | Overdue |  | 131242-WSW41-QA-0011 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 12 | AWC | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3878 | 000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0013 | 0 | 131242-WSW41-MI-PM-0013-0 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-MI-0013 | NA | "BIM Bi-Weekly Meeting Minutes 0012 & 0013_20231115 & 1129" && "CSA Meeting Minutes 0013_20231019" && "Monthly Progress Meeting Minutes 0013_20240618" && "Process & MEICA Meeting Minutes 0013_20231123" | 2023-11-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 5 | INF | 2024-08-07 | 0 | 000184&&000226&&000253&&000628 | 2023-11-14, 2023-12-05, 2023-12-27, 2024-08-07 | 00 | 4 | For Information | INF | 2024-08-30 | Overdue | 0 | INF | INF
3879 | 000628 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0013 | 0 | 131242-WSW41-PS-PM-0013-0 | 2024-08-07 | Monthly Progress Meeting Minutes 0013_20240618 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-PS-0013 | NA | "Incentive/ Disincentive Audit Scheme for Jun 2024" && "Monthly Progress Meeting Minutes 0013_20240618" | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-27 | 5 | INF | 2024-08-22 | 0 | 000628&&000669 | 2024-08-07, 2024-08-22 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
3880 | 000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0014 | 0 | 131242-WSW41-MI-PM-0014-0 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-MI-0014 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "C4B Minutes of CSA Progress Meeting No.0014" && "Monthly Progress Meeting Minutes 0014_20240723" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-21 | 5 | INF | 2024-08-07 | 0 | 000213&&000259&&000268&&000629 | 2023-11-27, 2024-01-03, 2024-01-09, 2024-08-07 | 00 | 4 | For Information | INF | 2024-08-30 | Overdue | 0 | INF | INF
3881 | 000629 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0014 | 0 | 131242-WSW41-PS-PM-0014-0 | 2024-08-07 | Monthly Progress Meeting Minutes 0014_20240723 | Rev. 0 - For Information | 2024-09-05 | 2024-08-12 | For Information |  | YES | NA |  | 131242-WSW41-PS-0014 | NA | "Incentive/ Disincentive Audit Scheme for Jul 2024" && "Monthly Progress Meeting Minutes 0014_20240723" | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-27 | 5 | INF | 2024-10-14 | 0 | 000629&&000760 | 2024-08-07, 2024-10-14 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
3882 | 000630 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 0 | 131242-WSW41-SP-C-0020-0 | 2024-08-07 | Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-05 | 2024-08-19 | Approved with Comments | 2024-09-06 | YES | Resubmitted |  | 131242-WSW41-SP-0020 | NA | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 12 | AWC | 2024-10-02 | 1 | 000630 | 2024-08-07, 2024-10-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
3883 | 000630 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0020 | 1 | 131242-WSW41-SP-C-0020-1 | 2024-10-02 | Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United) | Rev.1: Approved | 2024-10-22 | 2024-10-14 | Approved |  | YES | NA |  | 131242-WSW41-SP-0020 | NA | "Concrete Design Mix for Electrical Building Super structure ,PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" && "Concrete Design Mix for Electrical Building Super structure, PDMH, Pipe Rack Stump ,Plinth C35/45 (Pan United)" | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-16 | 12 | APP | 2024-10-02 | 1 | 000630 | 2024-08-07, 2024-10-02 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
3884 | 000631 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041-0 | 2024-07-08 | Submission Of BIM Coordination VCM Model (Jul-2024) | Resubmit: Considering the VCM submitted only contains link, Contractor to provide full list of contents (from the link) per folder/zip file with file size and timestamp (Transmittal Cover). Also, Contractor to ensure that the link provided should be Contractor's OneDrive link or link to Contractor's CDE. | 2024-08-05 | 2024-08-08 | For Information |  | YES | NA |  | 131242-WSW41-CD-0041 | NA | "Submission Of BIM Coordination VCM Model (Jul-2024)" && "Submission Of BIM Coordination VCM Model (Jun-2024)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-28 | 31 | INF | 2024-08-12 | 0 | 000550&&000631 | 2024-07-08, 2024-08-12 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3885 | 000631 | 01 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0041 | 0 | 131242-WSW41-CD-IM-0041-0 | 2024-08-12 | Submission Of BIM Coordination VCM Model (Jul-2024) | For Information | 2024-08-30 | 2024-08-26 | For Information |  | YES | NA |  | 131242-WSW41-CD-0041 | NA | "Submission Of BIM Coordination VCM Model (Jul-2024)" && "Submission Of BIM Coordination VCM Model (Jun-2024)" | 2024-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-08-26 | 14 | INF | 2024-08-12 | 0 | 000550&&000631 | 2024-07-08, 2024-08-12 | 00, 01 | 3 | For Information | INF | 2024-09-13 | Overdue | 0 | INF | INF
3886 | 000632 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0016 | 0 | 131242-WSW41-MS-C-0016-0 | 2024-08-12 | MSRA, SWP for Erection, Dismantling and Use of Scaffold | Approved | 2024-09-09 | 2024-08-30 | Approved |  | YES | NA |  | 131242-WSW41-MS-0016 | NA | "MSRA for MCCB Replacement Works" && "MSRA, SWP for Erection, Dismantling and Use of Scaffold " && "MSRA, SWP for FRP Tanks Defect Repair Lamination Works " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-01 | 18 | APP | 2025-10-28 | 0 | 000632&&001797&&001798 | 2024-08-12, 2025-10-28 | 00 | 3 | For Information | INF |  |  | 0 | APP | APP
3887 | 000633 | 00 | Bryan | QAQC | NA | 131242 | WSW41 | MS | C | 0017 | 0 | 131242-WSW41-MS-C-0017-0 | 2024-08-12 | MSRA, SWP for Jet Grouting | Approved | 2024-09-09 | 2024-09-02 | Approved |  | YES | NA |  | 131242-WSW41-MS-0017 | NA | "MSRA & Safe Work Procedure For NDT Activities" && "MSRA, SWP for Jet Grouting" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-01 | 21 | APP | 2025-10-31 | 0 | 000633&&001811 | 2024-08-12, 2025-10-31 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | APP | APP
3888 | 000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0010 | 0 | 131242-WSD11-DS-E-0010-0 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0010 | NA | "Datasheet for Pressure Switch" && "Progressive Cavity Pumps" && "THP Pump Motor Data Sheet" | 2023-12-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 78 | AWC | 2026-01-30 | 2 | 000222&&000634&&001181 | 2023-12-01, 2024-08-12, 2025-04-01, 2025-09-10, 2026-01-30 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
3889 | 000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0012 | 0 | 131242-WSD11-DS-E-0012-0 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0012 | NA | "Data Sheet of Desuperheater " && "Datasheet for Thermal Flow Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-01 | 78 | AWC | 2026-01-15 | 0 | 000634&&000648&&001956 | 2024-08-12, 2026-01-15 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3890 | 000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0013 | 0 | 131242-WSD11-DS-E-0013-0 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0013 | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "THP Pump Motor Data Sheet" | 2024-04-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 78 | AWC | 2026-01-15 | A | 000421&&000634&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
3891 | 000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0014 | 0 | 131242-WSD11-DS-E-0014-0 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0014 | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-26 | 78 | AWC | 2026-01-20 | 0 | 000422&&000634&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3892 | 000634 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | E | 0015 | 0 | 131242-WSD11-DS-E-0015-0 | 2024-08-12 | THP Pump Motor Data Sheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSD11-DS-0015 | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-01 | 78 | AWC | 2026-01-29 | 0 | 000634&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
3893 | 000635 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 0 | 131242-WSD11-DS-M-0015-0 | 2024-08-12 | Data Sheet of Flash Tank Discharge Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DS-0015 | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-01 | 58 | AWC | 2026-01-29 | 0 | 000634&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
3894 | 000635 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0015 | 1 | 131242-WSD11-DS-M-0015-1 | 2024-11-13 | Data Sheet of Flash Tank Discharge Pump | Rev 1: Approved | 2024-12-03 | 2024-12-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0015 | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-27 | 23 | APP | 2026-01-29 | 0 | 000634&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
3895 | 000636 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 0 | 131242-WSD11-DS-M-0016-0 | 2024-08-12 | Data Sheet of Precooler S2 CIRC Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DS-0016 | NA | "Data Sheet of Precooler S2 CIRC Pump" && "Datasheet for Pressure Transmitter (THP-BOP) " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-01 | 58 | AWC | 2026-01-30 | 0 | 000636&&001999 | 2024-08-12, 2024-11-13, 2026-01-30 | 00, 01 | 3 | Approved | APP |  |  | 0 | AWC | AWC
3896 | 000636 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0016 | 1 | 131242-WSD11-DS-M-0016-1 | 2024-11-13 | Data Sheet of Precooler S2 CIRC Pump | Rev 1: Approved | 2024-12-03 | 2024-06-12 | Approved |  | YES | NA |  | 131242-WSD11-DS-0016 | NA | "Data Sheet of Precooler S2 CIRC Pump" && "Datasheet for Pressure Transmitter (THP-BOP) " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-27 |  | APP | 2026-01-30 | 0 | 000636&&001999 | 2024-08-12, 2024-11-13, 2026-01-30 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
3897 | 000637 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 0 | 131242-WSD11-DS-M-0017-0 | 2024-08-12 | Data Sheet of Digester Feed Pump | Rev 0: Not approved - Revise and Resubmit | 2024-09-09 | 2024-10-09 | Not Approved | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DS-0017 | NA | "Data Sheet of Digester Feed Pump" && "Datasheet for Temperature Sensor (THP-BOP) " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-01 | 58 | NAP | 2026-03-02 | 0 | 000637&&002020 | 2024-08-12, 2025-03-04, 2026-03-02 | 00, 01 | 3 | Approved | APP |  |  | 0 | NAP | NAP
3898 | 000637 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0017 | 1 | 131242-WSD11-DS-M-0017-1 | 2025-03-04 | Data Sheet of Digester Feed Pump | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-DS-0017 | NA | "Data Sheet of Digester Feed Pump" && "Datasheet for Temperature Sensor (THP-BOP) " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | APP | 2026-03-02 | 0 | 000637&&002020 | 2024-08-12, 2025-03-04, 2026-03-02 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
3899 | 000638 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0018 | 0 | 131242-WSW41-VI-C-0018-0 | 2024-08-13 | Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings) | Rev 0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-08-19 | Approved with Comments | 2024-09-06 | NO | Overdue |  | 131242-WSW41-VI-0018 | NA | "Preliminary Design and Vendor Approval for Parabolic Screen" && "Vendor Approval for Distribution Boards (ZPA)" && "Vendor Approval of Mechanical Installer - JD Waters Pte Ltd" && "Vendor Approval of uPVC Pipe and Fittings (Vicplas Holdings)" | 2024-02-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 6 | AWC | 2025-08-21 | 1 | 000332&&000559&&000638&&001432 | 2024-02-29, 2024-03-04, 2024-07-12, 2024-08-13, 2025-07-04, 2025-08-21 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3900 | 000639 | 00 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 0 | 131242-WST02-SP-I-0002-0 | 2024-08-13 | SSN Functional Design Specification | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-SP-0002 | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 57 | AWC | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3901 | 000639 | 01 | Balaji | EICA | NA | 131242 | WST02 | SP | I | 0002 | 1 | 131242-WST02-SP-I-0002-1 | 2025-02-21 | SSN Functional Design Specification | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-03-13 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WST02-SP-0002 | NA | "SSN Aeration Blower Control Philosophy" && "SSN Functional Design Specification" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-07 | 20 | AWC | 2025-06-04 | 1 | 000639&&001032 | 2024-08-13, 2025-02-07, 2025-02-21, 2025-06-04 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3902 | 000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1165 | A | 131242-WSD11-DR-M-1165-A | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | Approved with Comments | 2024-10-29 | NO | Overdue | 2nd priority (Shall update and submit under as built drawing) | 131242-WSD11-DR-1165 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 57 | AWC | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3903 | 000640 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1166 | A | 131242-WSD11-DR-M-1166-A | 2024-08-13 | Piping General Arrangement of Air Compressor system | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-10-09 | Approved with Comments | 2024-10-29 | NO | Overdue |  | 131242-WSD11-DR-1166 | NA | "Milestone 2 THP Compressed Air System" && "Piping General Arrangement of Air Compressor system" && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 57 | AWC | 2025-08-13 | B | 000302&&000640&&001382 | 2024-08-13, 2024-10-18, 2025-06-16, 2025-08-13 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3904 | 000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5600_ST612_BCA | F | 131242-WST02-DR-S-5600_ST612_BCA-F | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WST02-DR-5600_ST612_BCA | NA | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-02 | 17 | INF | 2024-08-13 | F | 000641 | 2024-08-13 | 00 | 1 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3905 | 000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5601_ST612_BCA | F | 131242-WST02-DR-S-5601_ST612_BCA-F | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WST02-DR-5601_ST612_BCA | NA | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-02 | 17 | INF | 2024-08-13 | F | 000641 | 2024-08-13 | 00 | 1 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3906 | 000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 5602_ST612_BCA | F | 131242-WST02-DR-S-5602_ST612_BCA-F | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WST02-DR-5602_ST612_BCA | NA | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-02 | 17 | INF | 2024-08-13 | F | 000641 | 2024-08-13 | 00 | 1 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3907 | 000641 | 00 | Zora | CSA | NA | 131242 | WST02 | DR | S | 8600_ST612_BCA | F | 131242-WST02-DR-S-8600_ST612_BCA-F | 2024-08-13 | BCA Approval of ST612 – Typical Railing | For Information | 2024-09-10 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WST02-DR-8600_ST612_BCA | NA | "BCA Approval of ST612 – Typical Railing " | 2024-08-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-02 | 17 | INF | 2024-08-13 | F | 000641 | 2024-08-13 | 00 | 1 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3908 | 000642 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 0 | 131242-WSW41-QA-M-0008-0 | 2024-08-13 | Inspection Test Plan for HDPE Pipe Installation | As requested to reject this submittal. | 2024-09-10 | 2024-09-24 | Rejected | 2024-10-14 | YES | Resubmitted |  | 131242-WSW41-QA-0008 | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 42 | REJ | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3909 | 000642 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0008 | 1 | 131242-WSW41-QA-M-0008-1 | 2024-10-01 | Inspection Test Plan for HDPE Pipe Installation | Rev 1: Approved | 2024-10-21 | 2024-10-25 | Approved |  | YES | NA |  | 131242-WSW41-QA-0008 | NA | "FAT report for SSN Oil Filled HV/LV Transformer (Hitachi Energy)" && "Inspection Test Plan for HDPE Pipe Installation" && "Material Submission for HDG Thread Rod, Flat Washer & Hex Nut" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-15 | 24 | APP | 2024-11-30 | 0 | 000216&&000642&&000858 | 2023-11-30, 2023-12-12, 2024-08-13, 2024-10-01, 2024-11-30 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
3910 | 000643 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 0 | 131242-WSW41-QA-M-0006-0 | 2024-08-13 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-10 | 2024-10-16 | Not Approved | 2024-11-06 | YES | Resubmitted |  | 131242-WSW41-QA-0006 | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 64 | NAP | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | NAP | NAP
3911 | 000643 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-M-0006-1 | 2024-12-12 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 1: Approved | 2025-01-02 | 2025-01-20 | Approved |  | YES | NA |  | 131242-WSW41-QA-0006 | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-26 | 39 | APP | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | APP | APP
3912 | 000643 | 02 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0006 | 1 | 131242-WSW41-QA-M-0006-1 | 2025-09-25 | Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM) | Rev 2: Approved | 2025-10-15 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSW41-QA-0006 | NA | "Inspection Test Plan for Waterproofing Concrete and Application Work" && "Vendor Manufacturing Inspection Test Plan for Fine bubble air diffuser system (XYLEM)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-09 | 11 | APP | 2025-09-25 | 1 | 000149&&000643 | 2023-10-27, 2024-08-13, 2024-12-12, 2025-09-25 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | APP | APP
3913 | 000644 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 0 | 131242-WSD11-RT-EL-0000-0 | 2024-08-13 | THP Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | Not Approved | 2024-10-16 | YES | Resubmitted |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 44 | NAP | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3914 | 000644 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 1 | 131242-WSD11-RT-EL-0000-1 | 2025-04-22 | THP Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-05-12 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-05-06 | 14 | NAP | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3915 | 000644 | 02 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-EL-0000-2 | 2025-06-20 | THP Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-07-10 | 2025-08-04 | Not Approved | 2025-08-22 | YES | Resubmitted |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-04 | 45 | NAP | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
3916 | 000644 | 03 | Freedomer | EICA | NA | 131242 | WSD11 | RT | EL | 0000 | 2 | 131242-WSD11-RT-EL-0000-2 | 2025-12-15 | THP Lux Simulation Report | Rev 3: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-01-02 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WSD11-RT-0000 | NA | "THP LPS Risk Assessment Report" && "THP Lux Simulation Report" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 49 | NAP | 2025-12-15 | 2 | 000556&&000644 | 2024-07-10, 2024-08-13, 2024-10-28, 2025-04-22, 2025-06-20, 2025-07-07, 2025-12-15 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2026-02-20 | Overdue | 0 | NAP | NAP
3917 | 000645 | 00 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 0 | 131242-WST02-RT-EL-0000-0 | 2024-08-13 | SSN Lux Simulation Report | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-10 | 2024-09-26 | Not Approved | 2024-10-16 | YES | Resubmitted |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 44 | NAP | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3918 | 000645 | 01 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 1 | 131242-WST02-RT-EL-0000-1 | 2025-03-12 | SSN Lux Simulation Report | Rev 1: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-04-01 | 2025-05-06 | Not Approved | 2025-05-26 | YES | Resubmitted |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-26 | 55 | NAP | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3919 | 000645 | 02 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 2 | 131242-WST02-RT-EL-0000-2 | 2025-06-20 | SSN Lux Simulation Report | Rev 2: Not approved. To revise and resubmit. | 2025-07-10 | 2025-08-04 | Not Approved | 2025-08-22 | YES | Resubmitted |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-04 | 45 | NAP | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3920 | 000645 | 03 | Freedomer | EICA | NA | 131242 | WST02 | RT | EL | 0000 | 3 | 131242-WST02-RT-EL-0000-3 | 2025-11-20 | SSN Lux Simulation Report | Rev 3: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-10 | 2025-12-17 | Approved with Comments | 2026-01-06 | NO | Overdue |  | 131242-WST02-RT-0000 | NA | "SSN LPS Risk Assessment Report" && "SSN Lux Simulation Report" | 2024-07-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-04 | 27 | AWC | 2025-11-20 | 3 | 000557&&000645 | 2024-07-10, 2024-08-13, 2024-10-24, 2025-03-12, 2025-06-20, 2025-07-07, 2025-11-20 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-01-06 | Overdue | 0 | AWC | AWC
3921 | 000646 | 00 | Low/ Fox | EICA | NA | 131242 | WST02 | DR | I | 7002 | A | 131242-WST02-DR-I-7002-A | 2024-08-13 | Aeration Blower System Architecture Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-09-10 | 2024-08-27 | Approved with Comments | 2024-09-16 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-27 | 14 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3922 | 000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 1900 | A | 131242-WST02-DR-S-1900-A | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | Approved with Comments | 2024-10-01 | NO | Overdue |  | 131242-WST02-DR-1900 | NA | "SSN RIO - 0401 GA & Wiring Diagram" && "Waterproofing Concrete Demarcation of SSN Main Water Tank " | 2024-08-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 29 | AWC | 2025-07-29 | B | 000647&&001536 | 2024-08-13, 2025-07-29 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3923 | 000647 | 00 | Sithu | Const; | NA | 131242 | WST02 | DR | S | 3900 | A | 131242-WST02-DR-S-3900-A | 2024-08-13 | Waterproofing Concrete Demarcation of SSN Main Water Tank | Rev.0: Approved with comment. Please refer to comment sheet for resubmission. | 2024-09-10 | 2024-09-11 | Approved with Comments | 2024-10-01 | NO | Overdue |  | 131242-WST02-DR-3900 | NA | "Waterproofing Concrete Demarcation of SSN Main Water Tank " | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 29 | AWC | 2024-08-13 | A | 000647 | 2024-08-13 | 00 | 1 | Approved with Comments | AWC | 2024-10-01 | Overdue | 0 | AWC | AWC
3924 | 000648 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0012 | 0 | 131242-WSD11-DS-M-0012-0 | 2024-08-12 | Data Sheet of Desuperheater | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-09 | 2024-09-03 | Approved with Comments | 2024-09-23 | NO | Overdue |  | 131242-WSD11-DS-0012 | NA | "Data Sheet of Desuperheater " && "Datasheet for Thermal Flow Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-01 | 22 | AWC | 2026-01-15 | 0 | 000634&&000648&&001956 | 2024-08-12, 2026-01-15 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3925 | 000649 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0004 | 0 | 131242-WSD11-CL-P-0004-0 | 2024-08-15 | THP Feed Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-08 | Approved with Comments | 2024-10-28 | NO | Overdue |  | 131242-WSD11-CL-0004 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "THP Feed Pump Pressure Loss Calculation" | 2024-04-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-29 | 54 | AWC | 2024-08-15 | 0 | 000423&&000649 | 2024-04-05, 2024-06-05, 2024-08-15 | 00, 01 | 3 | Approved with Comments | AWC | 2024-10-28 | Overdue | 0 | AWC | AWC
3926 | 000650 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0008 | 0 | 131242-WSD11-CL-P-0008-0 | 2024-08-15 | Desuperheater Calculation | Rev 0: Approved with Comments. To revise and resubmit. Please include PE Endorsement. | 2024-09-12 | 2024-08-23 | Approved with Comments | 2024-09-12 | NO | Overdue |  | 131242-WSD11-CL-0008 | NA | "Desuperheater Calculation" | 2024-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 8 | AWC | 2024-08-15 | 0 | 000650 | 2024-08-15 | 00 | 1 | Approved with Comments | AWC | 2024-09-12 | Overdue | 0 | AWC | AWC
3927 | 000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | A | 131242-WSD11-DR-M-5100-A | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DR-5100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP PC Pump GA Drawings" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 55 | AWC | 2026-01-12 | C | 000651&&001944 | 2024-08-15, 2025-06-12, 2026-01-12 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
3928 | 000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | A | 131242-WSD11-DR-M-5110-A | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DR-5110 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 55 | AWC | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3929 | 000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | A | 131242-WSD11-DR-M-5120-A | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DR-5120 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 55 | AWC | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3930 | 000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | A | 131242-WSD11-DR-M-5130-A | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DR-5130 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 55 | AWC | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3931 | 000651 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | A | 131242-WSD11-DR-M-5140-A | 2024-08-15 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-DR-5140 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-04 | 55 | AWC | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3932 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5100 | B | 131242-WSD11-DR-M-5100-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP PC Pump GA Drawings" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2026-01-12 | C | 000651&&001944 | 2024-08-15, 2025-06-12, 2026-01-12 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | PEN | PEN
3933 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5110 | B | 131242-WSD11-DR-M-5110-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5110 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-30 |  | 0 | PEN | PEN
3934 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5120 | B | 131242-WSD11-DR-M-5120-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5120 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-30 |  | 0 | PEN | PEN
3935 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5121 | B | 131242-WSD11-DR-M-5121-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5121 | NA | "THP PC Pump GA Drawings" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | B | 000651 | 2025-06-12 | 01 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
3936 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5130 | B | 131242-WSD11-DR-M-5130-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5130 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-30 |  | 0 | PEN | PEN
3937 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5131 | B | 131242-WSD11-DR-M-5131-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5131 | NA | "THP PC Pump GA Drawings" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | B | 000651 | 2025-06-12 | 01 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
3938 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5132 | B | 131242-WSD11-DR-M-5132-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5132 | NA | "THP PC Pump GA Drawings" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | B | 000651 | 2025-06-12 | 01 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
3939 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5140 | B | 131242-WSD11-DR-M-5140-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5140 | NA | "THP PC Pump GA Drawings" | 2024-08-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2025-06-12 | B | 000651 | 2024-08-15, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-30 |  | 0 | PEN | PEN
3940 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5141 | B | 131242-WSD11-DR-M-5141-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5141 | NA | "THP PC Pump GA Drawings" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | B | 000651 | 2025-06-12 | 01 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
3941 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5142 | B | 131242-WSD11-DR-M-5142-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5142 | NA | "THP PC Pump GA Drawings" | 2025-06-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-07-02 | 298 | PEN | 2025-06-12 | B | 000651 | 2025-06-12 | 01 | 1 | Awaiting S.O.'s response | PEN | 2025-07-30 |  | 0 | PEN | PEN
3942 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | B | 131242-WSD11-DR-M-5150-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5150 | NA | "Ring Circulation Pump Drawing" && "THP PC Pump GA Drawings" | 2024-10-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2025-06-12 | B | 000651&&000784 | 2024-10-28, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-30 |  | 0 | PEN | PEN
3943 | 000651 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | B | 131242-WSD11-DR-M-5160-B | 2025-06-12 | THP PC Pump GA Drawings | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-07-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5160 | NA | "Ring Circulation Pump Drawing" && "THP PC Pump GA Drawings" | 2024-10-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-06-26 | 298 | PEN | 2025-06-12 | B | 000651&&000784 | 2024-10-28, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC | 2025-07-30 |  | 0 | PEN | PEN
3944 | 000652 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0030 | 0 | 131242-WSW41-MI-P-0030-0 | 2024-08-06 | Process & MEICA Meeting Minutes 0030_20240801 | Rev 0: For Information | 2024-09-04 | 2024-09-03 | For Information |  | YES | NA |  | 131242-WSW41-MI-0030 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-08-26 | 28 | INF | 2024-08-29 | 0 | 000652&&000683&&000684 | 2024-08-06, 2024-08-29 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
3945 | 000653 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0010 | 0 | 131242-WSW41-PO-M-0010-0 | 2024-07-08 | Unpriced PO for Hyperbolix Mixer (Entec International) | For Information | 2024-08-05 | 2024-08-29 | For Information |  | YES | NA |  | 131242-WSW41-PO-0010 | NA | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Hyperbolix Mixer (Entec International)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-07-28 | 52 | INF | 2025-08-01 | 0 | 000653&&001500&&001509 | 2024-07-08, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
3946 | 000654 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0011 | 0 | 131242-WSW41-PO-M-0011-0 | 2024-08-15 | Unpriced PO for Dosing Pump (ProMinent) | Rev 0: For Information | 2024-09-12 | 2024-08-29 | Approved |  | YES | NA |  | 131242-WSW41-PO-0011 | NA | "Unpriced PO for Dosing Pump (ProMinent)" && "Unpriced PO for Pressure Transmitter (Emerson)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-04 | 14 | APP | 2025-08-01 | 0 | 000654&&001501&&001510 | 2024-08-15, 2025-07-22, 2025-08-01 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | APP | APP
3947 | 000655 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0010 | 0 | 131242-WSW41-QA-M-0010-0 | 2024-08-15 | Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-12 | 2024-09-03 | Approved with Comments | 2024-09-23 | NO | Overdue |  | 131242-WSW41-QA-0010 | NA | "Materials submission and Vendor Approval of Top Manway Cover – Maccanvas" && "Monthly Concrete Cube Records for Structural works (03 24)" && "Procedure for Non-Pressure Hydrotest of underground HDPE line-Reg" | 2024-07-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-08-29 | 19 | AWC | 2024-12-18 | 1 | 000563&&000655&&000885 | 2024-07-12, 2024-08-15, 2024-12-11, 2024-12-18 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3948 | 000656 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 0 | 131242-WSD11-DS-M-0011-0 | 2024-08-16 | Data Sheet for Steam Sparger Package | Rev 0: Not approved - Revise and Resubmit | 2024-09-13 | 2024-09-10 | Not Approved | 2024-09-30 | YES | Resubmitted |  | 131242-WSD11-DS-0011 | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-05 | 25 | NAP | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
3949 | 000656 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0011 | 1 | 131242-WSD11-DS-M-0011-1 | 2025-02-18 | Data Sheet for Steam Sparger Package | Rev 1: Approved | 2025-03-10 | 2025-03-10 | Approved |  | YES | NA |  | 131242-WSD11-DS-0011 | NA | "Data Sheet for Steam Sparger Package" && "Datasheet for Temperature Transmitter " | 2024-08-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 20 | APP | 2026-01-21 | 1 | 000656&&001173 | 2024-08-16, 2025-02-18, 2025-03-27, 2025-10-27, 2026-01-21 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | APP | APP
3950 | 000657 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0011 | 0 | 131242-WSW41-QA-M-0011-0 | 2024-08-19 | Procedure for Welding of Underground HDPE Pipe | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-16 | 2024-09-10 | Approved with Comments | 2024-09-30 | NO | Overdue |  | 131242-WSW41-QA-0011 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 22 | AWC | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3951 | 000658 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0015 | 0 | 131242-WSW41-RT-PM-0015-0 | 2024-08-19 | C4B Monthly Progress Report Number No.15 (07 24) | Rev. 0 - Approved with comments (see attached comment sheet) | 2024-09-16 | 2024-09-06 | Approved with Comments | 2024-09-26 | NO | Overdue |  | 131242-WSW41-RT-0015 | NA | "Bored Piling Pile Eccentricity Reports (ECC 21 & 22) and Final ECC Report " && "C4B Monthly Progress Report Number No.15 (07 24)" | 2024-08-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-08 | 18 | AWC | 2025-06-27 | 0 | 000658&&001416 | 2024-08-19, 2025-06-27 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
3952 | 000659 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1382 | 0 | 131242-WST02-DS-E-1382-0 | 2024-08-19 | Sample Board Submission for uPVC Pipe 6” & 4” | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-09-16 | 2024-09-26 | Approved |  | YES | NA |  | 131242-WST02-DS-1382 | NA | "Sample Board Submission for uPVC Pipe 6” & 4” " | 2024-08-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-08 | 38 | APP | 2024-08-19 | 0 | 000659 | 2024-08-19 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
3953 | 000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7020 | A | 131242-WST02-DR-I-7020-A | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | Not Approved | 2024-09-26 | NO | Overdue |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 18 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3954 | 000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7021 | A | 131242-WST02-DR-I-7021-A | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | Not Approved | 2024-09-26 | NO | Overdue |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 18 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3955 | 000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7022 | A | 131242-WST02-DR-I-7022-A | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | Not Approved | 2024-09-26 | NO | Overdue |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 18 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3956 | 000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7023 | A | 131242-WST02-DR-I-7023-A | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | Not Approved | 2024-09-26 | NO | Overdue |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 18 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3957 | 000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7024 | A | 131242-WST02-DR-I-7024-A | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | Not Approved | 2024-09-26 | NO | Overdue |  | 131242-WST02-DR-7024 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 18 | NAP | 2025-05-04 | D | 000604&&000605&&000660 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | NAP | NAP
3958 | 000660 | 00 | Low | EICA | NA | 131242 | WST02 | DR | I | 7025 | A | 131242-WST02-DR-I-7025-A | 2024-08-19 | SSN Control Network Connection Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-09-16 | 2024-09-06 | Not Approved | 2024-09-26 | NO | Overdue |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-02 | 18 | NAP | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3959 | 000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A | 131242-WST02-DR-BF-7002-A | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | Not Approved | 2024-10-11 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 34 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3960 | 000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1005 | A | 131242-WST02-DR-BF-1005-A | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | Not Approved | 2024-10-11 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 34 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
3961 | 000661 | 00 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5001 | A | 131242-WST02-DR-BF-5001-A | 2024-08-20 | SSN External Fire Hydrant Layout & Details | Rev 0: Not approved - Revise and Resubmit | 2024-09-17 | 2024-09-23 | Not Approved | 2024-10-11 | YES | Resubmitted |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 34 | NAP | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
3962 | 000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 7002 | A.1 | 131242-WST02-DR-BF-7002-A.1 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-03 | 104 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3963 | 000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 1005 | A.1 | 131242-WST02-DR-BF-1005-A.1 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-03 | 104 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
3964 | 000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5001 | A.1 | 131242-WST02-DR-BF-5001-A.1 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-5001 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" && "SSN Process Non-Process room layout" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-03 | 104 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000555&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-07-10, 2024-08-20, 2024-10-05, 2024-10-21, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3965 | 000661 | 01 | Kyaw Myo | BS | NA | 131242 | WST02 | DR | BF | 5002 | A.1 | 131242-WST02-DR-BF-5002-A.1 | 2025-06-19 | SSN External Fire Hydrant Layout & Details | Rev 1: Approved with comments- Revise and Resubmit | 2025-07-09 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DR-5002 | NA | "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN Cast-in Schedule & Details" && "SSN Door Window Schedule" && "SSN External Fire Hydrant Layout & Details " && "SSN Preliminary Lightning Protection System" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-07-03 | 104 | AWC | 2025-11-21 | A.2 | 000161&&000191&&000205&&000492&&000661&&000833 | 2023-11-22, 2024-05-28, 2024-07-06, 2024-10-05, 2024-10-21, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-26, 2025-05-15, 2025-06-19, 2025-08-19, 2025-11-21 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3966 | 000662 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0009 | 0 | 131242-WSD11-CL-P-0009-0 | 2024-08-20 | Flash Tank Discharge Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-09 | Approved with Comments | 2024-10-29 | NO | Overdue |  | 131242-WSD11-CL-0009 | NA | "Flash Tank Discharge Pump Pressure Loss Calculation" | 2024-08-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 50 | AWC | 2024-08-20 | 0 | 000662 | 2024-08-20 | 00 | 1 | Approved with Comments | AWC | 2024-10-29 | Overdue | 0 | AWC | AWC
3967 | 000663 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0010 | 0 | 131242-WSD11-CL-P-0010-0 | 2024-08-20 | Precooler S2 Circ Pump Pressure Loss Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-10-08 | Approved with Comments | 2024-10-28 | NO | Overdue |  | 131242-WSD11-CL-0010 | NA | "Design Calculation for Instrument Air Receiver" && "Precooler S2 Circ Pump Pressure Loss Calculation" | 2024-06-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-03 | 49 | AWC | 2024-09-03 | 1 | 000537&&000663 | 2024-06-27, 2024-08-20, 2024-09-03 | 00, 01 | 3 | Approved | APP |  |  | 0 | AWC | AWC
3968 | 000664 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 0 | 131242-WSD11-CL-P-0007-0 | 2024-08-20 | Steam Sparger Calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-17 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted |  | 131242-WSD11-CL-0007 | NA | "G2D Pipe Support_Report from QPD" && "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 21 | AWC | 2026-01-12 | 1 | 000664&&000960&&001945 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3969 | 000664 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0007 | 1 | 131242-WSD11-CL-P-0007-1 | 2025-04-10 | Steam Sparger Calculation | Rev 1: Approved. Please furnish PE Endorsement. | 2025-04-30 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-CL-0007 | NA | "G2D Pipe Support_Report from QPD" && "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-24 | 179 | APP | 2026-01-12 | 1 | 000664&&000960&&001945 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
3970 | 000665 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 0 | 131242-WST02-QA-E-0002-0 | 2024-08-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-18 | 2024-09-24 | Not Approved | 2024-10-14 | YES | Resubmitted |  | 131242-WST02-QA-0002 | NA | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " && "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-10 | 34 | NAP | 2025-08-19 | 0 | 000665&&001603 | 2024-08-21, 2024-10-25, 2025-08-19 | 00, 01 | 3 | For Information | INF |  |  | 0 | NAP | NAP
3971 | 000665 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0002 | 1 | 131242-WST02-QA-E-0002-1 | 2024-10-25 | Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-15 | 2024-11-04 | Approved with Comments | 2024-11-22 | NO | Overdue |  | 131242-WST02-QA-0002 | NA | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " && "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-08-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-08 | 10 | AWC | 2025-08-19 | 0 | 000665&&001603 | 2024-08-21, 2024-10-25, 2025-08-19 | 00, 01 | 3 | For Information | INF |  |  | 0 | AWC | AWC
3972 | 000666 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0010 | 0 | 131242-WSW41-PS-HS-0010-0 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Mar 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WSW41-PS-0010 | NA | "BIM Bi-Weekly Meeting Minutes 0009 & 0010_20231004 & 1018" && "Incentive/ Disincentive Audit Scheme for Mar 2024" && "Monthly Progress Presentation No. 10 (0224)" | 2023-10-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-05 | 8 | INF | 2024-08-22 | 0 | 000152&&000387&&000666 | 2023-10-30, 2024-03-22, 2024-08-22 | 00 | 3 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3973 | 000667 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0011 | 0 | 131242-WSW41-PS-HS-0011-0 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Apr 2024 | Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WSW41-PS-0011 | NA | "BIM Bi-Weekly Meeting Minutes 0011_20231101" && "Incentive/ Disincentive Audit Scheme for Apr 2024" && "Monthly Progress Presentation No. 11 (0324)" | 2023-11-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-05 | 8 | INF | 2024-08-22 | 0 | 000176&&000453&&000667 | 2023-11-09, 2024-04-26, 2024-08-22 | 00 | 3 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3974 | 000668 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0012 | 0 | 131242-WSW41-PS-HS-0012-0 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for May 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-09-19 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WSW41-PS-0012 | NA | "Incentive/ Disincentive Audit Scheme for May 2024" && "Monthly Progress Presentation No. 12 (0424)" | 2024-06-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-05 | 8 | INF | 2024-08-22 | 0 | 000510&&000668 | 2024-06-04, 2024-08-22 | 00 | 2 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3975 | 000669 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0013 | 0 | 131242-WSW41-PS-HS-0013-0 | 2024-08-22 | Incentive/ Disincentive Audit Scheme for Jun 2024 | Rev 0: Scoring confirmed to be at 93/100 | 2024-09-19 | 2024-08-30 | For Information |  | YES | NA |  | 131242-WSW41-PS-0013 | NA | "Incentive/ Disincentive Audit Scheme for Jun 2024" && "Monthly Progress Meeting Minutes 0013_20240618" | 2024-08-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-05 | 8 | INF | 2024-08-22 | 0 | 000628&&000669 | 2024-08-07, 2024-08-22 | 00 | 2 | For Information | INF | 2024-09-19 | Overdue | 0 | INF | INF
3976 | 000670 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | - | 131242-WSW41-QA-C-0013-- | 2024-08-22 | Monthly Concrete Cube Records for Structural works for Apr 2024 | Rejected as requested by Contractor | 2024-09-19 | 2024-08-30 | Rejected | 2024-09-19 | YES | Resubmitted | Request for Reject | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 8 | REJ | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3977 | 000670 | 01 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0013 | 0 | 131242-WSW41-QA-C-0013-0 | 2024-08-27 | Monthly Concrete Cube Records for Structural works for May 2024 | Rejected as requested by Contractor | 2024-09-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365) | 2024-09-10 | 587 | PEN | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
3978 | 000671 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 0 | 131242-WSW41-VI-E-0010-0 | 2024-08-23 | Vendor Approval of Surge Diverter | Rev 0: Approved with comments. Refer to attached file for comments. | 2024-09-20 | 2024-09-26 | Approved with Comments | 2024-10-16 | YES | Resubmitted |  | 131242-WSW41-VI-0010 | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-06 | 34 | AWC | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3979 | 000671 | 01 | Freedomer | EICA | NA | 131242 | WSW41 | VI | E | 0010 | 1 | 131242-WSW41-VI-E-0010-1 | 2024-10-04 | Vendor Approval of Surge Diverter | Rev 1: Approved. | 2024-10-24 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSW41-VI-0010 | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-18 | 25 | APP | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
3980 | 000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1200 | A | 131242-WSD11-DR-M-1200-A | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue | Submission unsuccessful on 11 Jul 2024. | 131242-WSD11-DR-1200 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 55 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3981 | 000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1201 | A | 131242-WSD11-DR-M-1201-A | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue |  | 131242-WSD11-DR-1201 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 55 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3982 | 000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1202 | A | 131242-WSD11-DR-M-1202-A | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue |  | 131242-WSD11-DR-1202 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 55 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3983 | 000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1203 | A | 131242-WSD11-DR-M-1203-A | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue |  | 131242-WSD11-DR-1203 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 55 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3984 | 000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1204 | A | 131242-WSD11-DR-M-1204-A | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue |  | 131242-WSD11-DR-1204 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 55 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3985 | 000672 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 8000 | A | 131242-WSD11-DR-M-8000-A | 2024-08-23 | THP Equipment layout | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue |  | 131242-WSD11-DR-8000 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP Equipment layout" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 55 | AWC | 2025-11-28 | A.1 | 000292&&000672 | 2024-08-23, 2025-05-09, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3986 | 000673 | 00 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-Z-0001-0 | 2024-08-23 | SSN 30 Percent ALMOP Report | Rev 0: Not approved - Revise and Resubmit | 2024-09-20 | 2024-09-06 | Rejected | 2024-09-26 | YES | Resubmitted |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-06 | 14 | REJ | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
3987 | 000673 | 01 | Qili | Process | NA | 131242 | WST02 | RT | Z | 0001 | 0 | 131242-WST02-RT-Z-0001-0 | 2024-09-06 | SSN 30 Percent ALMOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted |  | 131242-WST02-RT-0001 | NA | "Basic Design Report of SSN Package" && "Design for Safety Report 2" && "SSN 30 Percent ALMOP Report" && "Safety Review Report for SSN Structures" | 2024-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 38 | AWC | 2024-12-18 | 0 | 000407&&000468&&000673&&000912 | 2024-03-28, 2024-05-09, 2024-05-23, 2024-06-07, 2024-08-21, 2024-08-23, 2024-09-06, 2024-11-03, 2024-11-18, 2024-12-18 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3988 | 000673 | 02 | Qili | Process | NA | 131242 | WST02 | RT | Z | Comment Reply Sheet 20240716 S673.2 | 0 | 131242-WST02-RT-Z-Comment Reply Sheet 20240716 S673.2-0 | 2024-10-29 | SSN 30 Percent ALMOP Report | Rev 2: Approved | 2024-11-19 | 2024-11-27 | Approved |  | YES | NA |  | 131242-WST02-RT-Comment Reply Sheet 20240716 S673.2 | NA | "SSN 30 Percent ALMOP Report" | 2024-10-29 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-18 | 29 | APP | 2024-10-29 | 0 | 000673 | 2024-10-29 | 02 | 1 | Approved | APP |  |  | 0 | APP | APP
3989 | 000674 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0037 | 0 | 131242-WSW41-LT-PM-0037-0 | 2024-08-23 | NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements | Received for information. Please refer to S.O. Correspondence no. 241 dated 23 Oct 2024. | 2024-09-20 | 2025-11-20 | For Information |  | YES | NA |  | 131242-WSW41-LT-0037 | NA | "NOTICE Extension of Time and Cost for Additional C4B/ Aluminium Handrails QAQC Requirements " | 2024-08-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365) | 2024-09-12 | 454 | INF | 2024-08-23 | 0 | 000674 | 2024-08-23 | 00 | 1 | For Information | INF | 2025-12-10 | Overdue | 0 | INF | INF
3990 | 000675 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 0 | 131242-WSW41-VI-M-0021-0 | 2024-08-23 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-20 | 2024-09-10 | Approved with Comments | 2024-09-30 | YES | Resubmitted | In Progress | 131242-WSW41-VI-0021 | NA | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" && "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 18 | AWC | 2025-07-02 | 1 | 000675&&000679 | 2024-08-23, 2024-08-26, 2025-07-02 | 00, 01 | 3 | Approved | APP |  |  | 0 | AWC | AWC
3991 | 000675 | 01 | David | Mech | NA | 131242 | WSW41 | VI | M | 0021 | 1 | 131242-WSW41-VI-M-0021-1 | 2025-07-02 | Preliminary Design and Vendor Approval of Aachor Bolt (Hilti) | Rev 1: Approved | 2025-07-22 | 2025-11-24 | Approved |  | YES | NA | In Progress | 131242-WSW41-VI-0021 | NA | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" && "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-16 | 145 | APP | 2025-07-02 | 1 | 000675&&000679 | 2024-08-23, 2024-08-26, 2025-07-02 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
3992 | 000676 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 0 | 131242-WST02-QA-E-0003-0 | 2024-08-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-29 | Not Approved | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-QA-0003 | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-15 | 64 | NAP | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | For Information | INF |  |  | 0 | NAP | NAP
3993 | 000676 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 1 | 131242-WST02-QA-E-0003-1 | 2024-12-26 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-15 | 2025-02-03 | Approved with Comments | 2025-02-21 | YES | Resubmitted |  | 131242-WST02-QA-0003 | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-09 | 39 | AWC | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | For Information | INF |  |  | 0 | AWC | AWC
3994 | 000676 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0003 | 2 | 131242-WST02-QA-E-0003-2 | 2025-02-07 | Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-02-27 | 2025-02-18 | Approved with Comments | 2025-03-10 | NO | Overdue |  | 131242-WST02-QA-0003 | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-21 | 11 | AWC | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | For Information | INF |  |  | 0 | AWC | AWC
3995 | 000677 | 00 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 0 | 131242-WST02-SP-I-0001-0 | 2024-08-26 | SSN Control Narrative | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-09-23 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WST02-SP-0001 | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-09 | 44 | AWC | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
3996 | 000677 | 01 | Qili | Process | NA | 131242 | WST02 | SP | I | 0001 | 1 | 131242-WST02-SP-I-0001-1 | 2025-03-24 | SSN Control Narrative | Approved with Comments | 2025-04-11 | 2025-05-15 | Approved with Comments | 2025-06-04 | NO | Overdue |  | 131242-WST02-SP-0001 | NA | "SSN Control Narrative" && "SSN Control Philosophy" | 2024-03-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-04-07 | 52 | AWC | 2025-03-24 | 1 | 000403&&000677 | 2024-03-27, 2024-08-12, 2024-08-26, 2024-10-03, 2025-03-14, 2025-03-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2025-06-04 | Overdue | 0 | AWC | AWC
3997 | 000678 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 0 | 131242-WSD11-RT-P-0003-0 | 2024-08-26 | THP HAZOP Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-23 | 2024-10-09 | Approved with Comments | 2024-10-29 | YES | Resubmitted |  | 131242-WSD11-RT-0003 | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-15 | 44 | AWC | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3998 | 000678 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | P | 0003 | 1 | 131242-WSD11-RT-P-0003-1 | 2024-10-28 | THP HAZOP Report | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2025-04-08 | Approved with Comments | 2025-04-28 | NO | Overdue |  | 131242-WSD11-RT-0003 | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-11 | 162 | AWC | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
3999 | 000679 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | E | 0021 | 0 | 131242-WSW41-VI-E-0021-0 | 2024-08-26 | Vendor Approval of Electrical Consultant – YHW LLP | Approved | 2024-09-23 | 2024-09-26 | Approved |  | YES | NA |  | 131242-WSW41-VI-0021 | NA | "Preliminary Design and Vendor Approval of Aachor Bolt (Hilti)" && "Vendor Approval of Electrical Consultant – YHW LLP" | 2024-08-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-09 | 31 | APP | 2025-07-02 | 1 | 000675&&000679 | 2024-08-23, 2024-08-26, 2025-07-02 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
4000 | 000680 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | QA | C | 0014 | 0 | 131242-WST02-QA-C-0014-0 | 2024-08-27 | Laboratory Test Report on Soil Samples | For Information | 2024-09-24 | 2024-09-17 | For Information |  | YES | NA |  | 131242-WST02-QA-0014 | NA | "Factory Acceptance Test Report for Clean Gas System Panel" && "Laboratory Test Report on Soil Samples" | 2024-08-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-16 | 21 | INF | 2025-07-30 | 0 | 000680&&001539 | 2024-08-27, 2025-07-30 | 00 | 2 | Approved | APP |  |  | 0 | INF | INF
4001 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.1 | 131242-WSD11-DR-M-1170-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-1170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 49 | AWC | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4002 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | A.1 | 131242-WSD11-DR-M-1171-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-1171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 49 | AWC | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4003 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | A.1 | 131242-WSD11-DR-M-1172-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-1172 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 49 | AWC | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4004 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1173 | A.1 | 131242-WSD11-DR-M-1173-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-1173 | NA | "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 49 | AWC | 2025-08-13 | B | 000681&&001382 | 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4005 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | A.1 | 131242-WSD11-DR-M-3170-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-3170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 49 | AWC | 2025-02-18 | A.2 | 000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18 | 00, 01 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4006 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | A.1 | 131242-WSD11-DR-M-3171-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-3171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-11 | 49 | AWC | 2025-02-18 | A.2 | 000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18 | 00, 01 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4007 | 000681 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4100 | A.1 | 131242-WSD11-DR-M-4100-A.1 | 2024-08-28 | Biosolid Building Piping Opening | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-25 | 2024-10-16 | Approved with Comments | 2024-11-06 | YES | Resubmitted |  | 131242-WSD11-DR-4100 | NA | "Biosolid Building Piping Opening " | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-17 | 49 | AWC | 2025-02-18 | A.2 | 000681 | 2024-08-28, 2025-02-18 | 00, 01 | 2 | Approved | APP |  |  | 0 | AWC | AWC
4008 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1170 | A.2 | 131242-WSD11-DR-M-1170-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-10 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-1170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
4009 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1171 | A.2 | 131242-WSD11-DR-M-1171-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-1171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
4010 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1172 | A.2 | 131242-WSD11-DR-M-1172-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-1172 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-08-13 | B | 000391&&000681&&001382 | 2024-03-23, 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
4011 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1173 | A.2 | 131242-WSD11-DR-M-1173-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-1173 | NA | "Biosolid Building Piping Opening " && "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-08-13 | B | 000681&&001382 | 2024-08-28, 2025-02-18, 2025-06-16, 2025-08-13 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
4012 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3170 | A.2 | 131242-WSD11-DR-M-3170-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-3170 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-02-18 | A.2 | 000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
4013 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 3171 | A.2 | 131242-WSD11-DR-M-3171-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-3171 | NA | "Biosolid Building Pipe, Ducting Wall Opening & Plinth Layout" && "Biosolid Building Piping Opening " | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-02-18 | A.2 | 000391&&000681 | 2024-03-23, 2024-08-28, 2025-02-18 | 00, 01 | 3 | Approved | APP |  |  | 0 | APP | APP
4014 | 000681 | 01 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 4100 | A.2 | 131242-WSD11-DR-M-4100-A.2 | 2025-02-18 | Biosolid Building Piping Opening | Rev 1: Approved | 2025-03-18 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DR-4100 | NA | "Biosolid Building Piping Opening " | 2024-08-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-04 | 68 | APP | 2025-02-18 | A.2 | 000681 | 2024-08-28, 2025-02-18 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
4015 | 000682 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 0 | 131242-WSW41-QA-C-0015-0 | 2024-08-29 | Plate Load test report | Rev.0:Not Approved. Please refer to attached comment sheet for resubmission. | 2024-09-26 | 2024-09-18 | Not Approved | 2024-10-08 | YES | Resubmitted |  | 131242-WSW41-QA-0015 | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Plate Load test report " && "T&C Check List " && "Testing Check List (Process)" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-18 | 20 | NAP | 2026-01-28 | 0 | 000682&&000694&&001636&&001712 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4016 | 000682 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | C | 0015 | 1 | 131242-WSW41-QA-C-0015-1 | 2024-10-30 | Plate Load test report | Approved | 2024-11-20 | 2024-11-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0015 | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Plate Load test report " && "T&C Check List " && "Testing Check List (Process)" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-13 | 9 | APP | 2026-01-28 | 0 | 000682&&000694&&001636&&001712 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
4017 | 000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0029 | 0 | 131242-WSW41-MI-C-0029-0 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0029 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-08-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000622&&000683&&000684 | 2024-08-06, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4018 | 000683 | 00 | Zora | CSA | NA | 131242 | WSW41 | MI | C | 0030 | 0 | 131242-WSW41-MI-C-0030-0 | 2024-08-29 | CSA Meeting Minutes 0029,0030_1207 & 0808 2024 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0030 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000652&&000683&&000684 | 2024-08-06, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4019 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0019 | 0 | 131242-WSW41-MI-IM-0019-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0019 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0019_20241217" && "Process & MEICA Meeting Minutes 0019_20240215" | 2024-02-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2025-01-16 | 0 | 000323&&000388&&000684&&000980 | 2024-02-23, 2024-03-22, 2024-08-29, 2025-01-16 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
4020 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0020 | 0 | 131242-WSW41-MI-IM-0020-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0020 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0020_20250122" && "Process & MEICA Meeting Minutes 0020_20240229" | 2024-03-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2025-02-18 | 0 | 000353&&000388&&000684&&001049 | 2024-03-12, 2024-03-22, 2024-08-29, 2025-02-18 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
4021 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0021 | 0 | 131242-WSW41-MI-IM-0021-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0021 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0019, 0020, 0021_2024 01 25, 02 22, 03 07" && "Monthly Progress Meeting Minutes 0021_20250226" && "Process & MEICA Meeting Minutes 0021_20240328" | 2024-03-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2025-04-21 | 0 | 000388&&000460&&000684&&001243 | 2024-03-22, 2024-05-02, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
4022 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0022 | 0 | 131242-WSW41-MI-IM-0022-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0022 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Monthly Progress Meeting Minutes 0022_20250324" && "Process & MEICA Meeting Minutes 0022_20240425" | 2024-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2025-04-21 | 0 | 000470&&000472&&000684&&001245 | 2024-05-13, 2024-05-17, 2024-08-29, 2025-04-21 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
4023 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0023 | 0 | 131242-WSW41-MI-IM-0023-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0023 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0022 & 00023_20240321 & 0404" && "Process & MEICA Meeting Minutes 0023_20240509" | 2024-05-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000472&&000477&&000684 | 2024-05-17, 2024-05-23, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4024 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0024 | 0 | 131242-WSW41-MI-IM-0024-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0024 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0024_20240523" | 2024-06-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000517&&000561&&000684 | 2024-06-10, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4025 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0025 | 0 | 131242-WSW41-MI-IM-0025-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0025 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0025_20240606" | 2024-06-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000529&&000561&&000684 | 2024-06-20, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4026 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0026 | 0 | 131242-WSW41-MI-IM-0026-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0026 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0024,0025,0026_May" && "Process & MEICA Meeting Minutes 0026_20240624" | 2024-07-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000542&&000561&&000684 | 2024-07-03, 2024-07-12, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4027 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0027 | 0 | 131242-WSW41-MI-IM-0027-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0027 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0027,0028_June" && "Process & MEICA Meeting Minutes 0027_20240704" | 2024-07-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000562&&000584&&000684 | 2024-07-12, 2024-07-24, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4028 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0029 | 0 | 131242-WSW41-MI-IM-0029-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0029 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Process & MEICA Meeting Minutes 0028 & 0029_20240709 " | 2024-08-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000622&&000683&&000684 | 2024-08-06, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4029 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0030 | 0 | 131242-WSW41-MI-IM-0030-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0030 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0029,0030_1207 & 0808 2024" && "Process & MEICA Meeting Minutes 0030_20240801" | 2024-08-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-12 | 12 | INF | 2024-08-29 | 0 | 000652&&000683&&000684 | 2024-08-06, 2024-08-29 | 00 | 3 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4030 | 000684 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | MI | IM | 0031 | 0 | 131242-WSW41-MI-IM-0031-0 | 2024-08-29 | BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031 | For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0031 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-18 | 12 | INF | 2024-10-14 | 0 | 000684&&000685&&000762 | 2024-08-29, 2024-10-14 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
4031 | 000685 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0031 | 0 | 131242-WSW41-MI-P-0031-0 | 2024-08-29 | Process & MEICA Meeting Minutes 0031_20240815 | Rev. 0 - For Information | 2024-09-26 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0031 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-18 | 12 | INF | 2024-10-14 | 0 | 000684&&000685&&000762 | 2024-08-29, 2024-10-14 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
4032 | 000686 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 0 | 131242-WSD11-DS-M-0021-0 | 2024-08-29 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 0: Not approved - Revise and Resubmit | 2024-09-26 | 2024-10-17 | Not Approved | 2024-11-07 | YES | Resubmitted |  | 131242-WSD11-DS-0021 | NA | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-18 | 49 | NAP | 2025-01-20 | 2 | 000686 | 2024-08-29, 2024-11-07, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
4033 | 000686 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 1 | 131242-WSD11-DS-M-0021-1 | 2024-11-07 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-27 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DS-0021 | NA | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-21 | 28 | AWC | 2025-01-20 | 2 | 000686 | 2024-08-29, 2024-11-07, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4034 | 000686 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0021 | 2 | 131242-WSD11-DS-M-0021-2 | 2025-01-20 | Data Sheet of Pressure Relief Valve at Air Receiver | Rev 2: Approved | 2025-02-07 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DS-0021 | NA | "Data Sheet of Pressure Relief Valve at Air Receiver" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-03 | 97 | APP | 2025-01-20 | 2 | 000686 | 2024-08-29, 2024-11-07, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4035 | 000687 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | Z | 0001 | 0 | 131242-WSD11-RT-Z-0001-0 | 2024-08-29 | THP 30 Percent ALMOP Study Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-26 | 2024-10-17 | Approved with Comments | 2024-11-07 | NO | Overdue |  | 131242-WSD11-RT-0001 | NA | "Report of DFS (GUIDE 3) for THP Trains Installation" && "THP - Basis of Design Report" && "THP 30 Percent ALMOP Study Report" && "THP Atex Hazardous Area Assessment Report" && "THP Protected Corridor Lux Simulation Report" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-12 | 49 | AWC | 2025-06-20 | 0 | 000208&&000278&&000687&&001134&&001393 | 2023-11-22, 2024-01-17, 2024-08-29, 2024-09-11, 2025-03-18, 2025-06-20 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4036 | 000688 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 0 | 131242-WSD11-QA-M-0012-0 | 2024-08-30 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-11-05 | Approved with Comments | 2024-11-25 | YES | Resubmitted |  | 131242-WSD11-QA-0012 | NA | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | 2024-08-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-19 | 67 | AWC | 2025-04-21 | 1 | 000688 | 2024-08-30, 2025-04-21 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4037 | 000688 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0012 | 1 | 131242-WSD11-QA-M-0012-1 | 2025-04-21 | Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-09 | 2025-09-08 | Approved with Comments |  | YES | NA |  | 131242-WSD11-QA-0012 | NA | "Vendor Manufacturing Inspection and test plan and FAT procedure for THP, Process Gas Skid, Sludge cooler" | 2024-08-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-05-05 | 140 | AWC | 2025-04-21 | 1 | 000688 | 2024-08-30, 2025-04-21 | 00, 01 | 2 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
4038 | 000689 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 0 | 131242-WSW41-QA-E-0004-0 | 2024-08-30 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 0: Rejected. Refer to the attached file for comments. | 2024-09-27 | 2024-11-25 | Rejected | 2024-12-13 | YES | Resubmitted |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-13 | 87 | REJ | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
4039 | 000689 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 1 | 131242-WSW41-QA-E-0004-1 | 2025-02-07 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 1: Approved with comments. Refer to the attached file for comments. | 2025-02-27 | 2025-03-13 | Approved with Comments | 2025-04-02 | YES | Resubmitted |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-21 | 34 | AWC | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4040 | 000689 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0004 | 2 | 131242-WSW41-QA-E-0004-2 | 2025-03-14 | Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd) | Rev 2: Approved. | 2025-04-03 | 2025-05-07 | Approved |  | YES | NA |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-28 | 54 | APP | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | APP | APP
4041 | 000690 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | CL | P | 0011 | 0 | 131242-WSD11-CL-P-0011-0 | 2024-08-30 | THP Plant Process Water Hydraulic Calculation | Rev 0: Not approved - Revise and Resubmit | 2024-09-27 | 2024-10-29 | Not Approved | 2024-11-19 | NO | Overdue |  | 131242-WSD11-CL-0011 | NA | "THP Plant Process Water Hydraulic Calculation" | 2024-08-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-19 | 60 | NAP | 2024-08-30 | 0 | 000690 | 2024-08-30 | 00 | 1 | Not Approved | NAP | 2024-11-18 | Overdue | 0 | NAP | NAP
4042 | 000691 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 0 | 131242-WSW41-QA-M-0013-0 | 2024-08-31 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-09-27 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-14 | 44 | AWC | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4043 | 000691 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0013 | 1 | 131242-WSW41-QA-M-0013-1 | 2025-04-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) | Approved | 2025-05-07 | 2025-05-19 | Approved |  | YES | NA |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-01 | 32 | APP | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
4044 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010_ST607_BCA | A | 131242-WST02-DR-S-1010_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-1010_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4045 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011_ST607_BCA | A | 131242-WST02-DR-S-1011_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-1011_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4046 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1012_ST607_BCA | A | 131242-WST02-DR-S-1012_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-1012_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4047 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3000_ST607_BCA | A | 131242-WST02-DR-S-3000_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-3000_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " | 2024-08-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-20 | 11 | INF | 2024-08-31 | A | 000692 | 2024-08-31 | 00 | 1 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4048 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002_ST607_BCA | A | 131242-WST02-DR-S-3002_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-3002_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4049 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7003_ST607_BCA | A | 131242-WST02-DR-S-7003_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-7003_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4050 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 7004_ST607_BCA | A | 131242-WST02-DR-S-7004_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-7004_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4051 | 000692 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8003_ST607_BCA | A | 131242-WST02-DR-S-8003_ST607_BCA-A | 2024-08-31 | BCA Approval of ST607 – Super Structure of SSN Main Water Tank | NA | 2024-09-27 | 2024-09-11 | For Information |  | YES | NA |  | 131242-WST02-DR-8003_ST607_BCA | NA | "BCA Approval of ST607 – Super Structure of SSN Main Water Tank " && "BCA Submission of ST607 – Super Structure of SSN Main Water Tank " | 2024-07-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-09-14 | 11 | INF | 2024-08-31 | A | 000538&&000692 | 2024-07-01, 2024-08-31 | 00 | 2 | For Information | INF | 2024-10-01 | Overdue | 0 | INF | INF
4052 | 000693 | 00 | Boopathi | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-C-0016-0 | 2024-08-31 | Monthly Concrete Cube Records for Structural works for July 2024 | For Information | 2024-09-27 | 2024-09-18 | For Information |  | YES | NA |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-20 | 18 | INF | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | INF | INF
4053 | 000694 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 0 | 131242-WSW41-QA-M-0015-0 | 2024-09-02 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Rev 0: Not approved - Revise and Resubmit | 2024-09-30 | 2024-10-13 | Not Approved | 2024-11-01 | YES | Resubmitted |  | 131242-WSW41-QA-0015 | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Plate Load test report " && "T&C Check List " && "Testing Check List (Process)" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-16 | 41 | NAP | 2026-01-28 | 0 | 000682&&000694&&001636&&001712 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4054 | 000694 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0015 | 1 | 131242-WSW41-QA-M-0015-1 | 2025-03-27 | FAT Procedure for Fine Bubble Air Diffuser system (XYLEM) | Approved | 2025-04-16 | 2025-05-19 | Approved |  | YES | NA |  | 131242-WSW41-QA-0015 | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Plate Load test report " && "T&C Check List " && "Testing Check List (Process)" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-10 | 53 | APP | 2026-01-28 | 0 | 000682&&000694&&001636&&001712 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | APP | APP
4055 | 000695 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0038 | 0 | 131242-WSW41-LT-PM-0038-0 | 2024-09-03 | Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions | Rev(0): Rejected. Please refer to S.O. Correspondence No. 246 dated 7 Nov 2024. | 2024-10-01 | 2025-11-20 | Rejected | 2025-12-10 | NO | Overdue |  | 131242-WSW41-LT-0038 | NA | "Notice for Extension of Time and Cost for Delays in Sidewide Pipe Rack Approvals for ST 603 submissions" | 2024-09-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-23 | 443 | REJ | 2024-09-03 | 0 | 000695 | 2024-09-03 | 00 | 1 | Rejected | REJ | 2025-12-10 | Overdue | 0 | REJ | REJ
4056 | 000696 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0014 | 0 | 131242-WSW41-PC-W-0014-0 | 2024-09-03 | Payment Claim No.14 | Rev(0): Approved. See S.O. correspondence no. 219 dated 6 Sep 2024. | 2024-10-01 | 2024-10-09 | Approved |  | YES | NA |  | 131242-WSW41-PC-0014 | NA | "Payment Claim No.14" | 2024-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-23 | 36 | APP | 2024-09-03 | 0 | 000696 | 2024-09-03 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4057 | 000697 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 0 | 131242-WSD11-DS-M-0018-0 | 2024-09-03 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted |  | 131242-WSD11-DS-0018 | NA | "Data Sheet for Pre Cooler Cooling Water Control Valve" && "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | 2024-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-23 | 41 | AWC | 2026-03-02 | 0 | 000697&&002021 | 2024-09-03, 2025-05-05, 2026-03-02 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4058 | 000697 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0018 | 1 | 131242-WSD11-DS-M-0018-1 | 2025-05-05 | Data Sheet for Pre Cooler Cooling Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0018 | NA | "Data Sheet for Pre Cooler Cooling Water Control Valve" && "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | 2024-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-19 | 336 | PEN | 2026-03-02 | 0 | 000697&&002021 | 2024-09-03, 2025-05-05, 2026-03-02 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
4059 | 000698 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 0 | 131242-WSD11-DS-M-0019-0 | 2024-09-03 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-01 | 2024-10-13 | Approved with Comments | 2024-11-01 | YES | Resubmitted |  | 131242-WSD11-DS-0019 | NA | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-23 | 40 | AWC | 2025-01-20 | 2 | 000698 | 2024-09-03, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4060 | 000698 | 01 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 1 | 131242-WSD11-DS-M-0019-1 | 2024-11-13 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DS-0019 | NA | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 22 | AWC | 2025-01-20 | 2 | 000698 | 2024-09-03, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4061 | 000698 | 02 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0019 | 2 | 131242-WSD11-DS-M-0019-2 | 2025-01-20 | Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DS-0019 | NA | "Data Sheet for Flash Tank Discharge Pump Dilution Water Control Valve" | 2024-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-03 | 97 | APP | 2025-01-20 | 2 | 000698 | 2024-09-03, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4062 | 000699 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0039 | 0 | 131242-WSW41-LT-PM-0039-0 | 2024-09-04 | Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024) | Rejected. Please refer to S.O. Correspondence no. 257 dated 2 Dec 2024. | 2024-10-02 | 2025-02-24 | Rejected |  | YES | NA | SO Corres 000258. Sent to Vincent on 03 Dec 2025 | 131242-WSW41-LT-0039 | NA | "Notice of Delay Of THP Courtyard Compartmentation Design Changes and Design Change for Relocation of Feeder Pump (C4B –003_JUN_2024)" | 2024-09-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-24 | 173 | REJ | 2024-09-04 | 0 | 000699 | 2024-09-04 | 00 | 1 | Rejected | REJ | 2025-03-14 | Overdue | 0 | REJ | REJ
4063 | 000700 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0015 | 0 | 131242-WSW41-MI-PM-0015-0 | 2024-09-04 | Monthly Progress Meeting Minutes 0015_20240827 | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0015 | NA | "BIM Bi-Weekly Meeting Minutes 0014 & 0015_20231213 & 1227" && "CSA Meeting Minutes 0015_20231116" && "Monthly Progress Meeting Minutes 0015_20240827" && "Process & MEICA Meeting Minutes 0014&0015_20231207 & 1221" | 2023-12-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-18 | 6 | INF | 2024-09-04 | 0 | 000240&&000259&&000268&&000700 | 2023-12-14, 2024-01-03, 2024-01-09, 2024-09-04 | 00 | 4 | For Information | INF | 2024-09-30 | Overdue | 0 | INF | INF
4064 | 000701 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0015 | 0 | 131242-WSW41-PS-PM-0015-0 | 2024-09-04 | Monthly Progress Presentation No. 15 (0824) | Rev. 0 - For Information | 2024-10-02 | 2024-09-10 | For Information |  | YES | NA |  | 131242-WSW41-PS-0015 | NA | "Incentive/ Disincentive Audit Scheme for Aug 2024" && "Monthly Progress Presentation No. 15 (0824)" | 2024-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-24 | 6 | INF | 2024-10-14 | 0 | 000701&&000761 | 2024-09-04, 2024-10-14 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4065 | 000702 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PO | M | 0012 | 0 | 131242-WSW41-PO-M-0012-0 | 2024-09-05 | Unpriced LOA for Structural Steel Works (Sanhe) | Rev 0: For Information | 2024-10-03 | 2024-10-13 | For Information |  | YES | NA |  | 131242-WSW41-PO-0012 | NA | "Unpriced LOA for Structural Steel Works (Sanhe) " && "Unpriced PO for Temperature Transmitter (Endress & Hauser)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-25 | 38 | INF | 2025-08-01 | 1 | 000702&&001502&&001511 | 2024-09-05, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
4066 | 000703 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | C | 0018 | 0 | 131242-WSW41-MS-C-0018-0 | 2024-09-05 | MSRA for RC Super-Structural Work | Rev.0: Approved. Please refer to comment sheet. | 2024-10-03 | 2024-09-26 | Approved |  | YES | NA |  | 131242-WSW41-MS-0018 | NA | "MSRA for RC Super-Structural Work" | 2024-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-25 | 21 | APP | 2024-09-05 | 0 | 000703 | 2024-09-05 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4067 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD | A | 131242-WSD11-DR-A-1000_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-1000_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 26 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-01-04, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4068 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD | A | 131242-WSD11-DR-A-1001_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-1001_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 26 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4069 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD | A | 131242-WSD11-DR-A-1002_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-1002_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 26 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4070 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD | A | 131242-WSD11-DR-A-1003_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-1003_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 26 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4071 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD | A | 131242-WSD11-DR-A-1004_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-1004_FSSD | NA | "Draft Waiver Application of THP Layout (THP-FSSD-WA 01)" && "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " && "WSD11- Waiver Application of THP Layout (THP-FSSD-WA 01)" | 2023-11-10 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 26 | NAP | 2024-09-06 | A | 000182&&000704 | 2023-11-10, 2024-09-06 | 00, 01 | 3 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4072 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_FSSD | A | 131242-WSD11-DR-A-2000_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-2000_FSSD | NA | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-26 | 26 | NAP | 2024-09-06 | A | 000704 | 2024-09-06 | 00 | 1 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4073 | 000704 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_FSSD | A | 131242-WSD11-DR-A-3000_FSSD-A | 2024-09-06 | FSSD Amendment of Approved Biosolid Building with new fire compartmentation | Not Approved | 2024-10-04 | 2024-10-02 | Not Approved | 2024-10-22 | NO | Overdue |  | 131242-WSD11-DR-3000_FSSD | NA | "FSSD Amendment of Approved Biosolid Building with new fire compartmentation " | 2024-09-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-26 | 26 | NAP | 2024-09-06 | A | 000704 | 2024-09-06 | 00 | 1 | Not Approved | NAP | 2024-10-22 | Overdue | 0 | NAP | NAP
4074 | 000705 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | C | 0019 | 0 | 131242-WSW41-VI-C-0019-0 | 2024-09-06 | Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-04 | 2024-09-26 | Approved with Comments | 2024-10-16 | NO | Overdue |  | 131242-WSW41-VI-0019 | NA | "Vendor Approval of Mechanical Installer – Cyclect Electrical Engineering Pte. Ltd." && "Vendor Approval of Protective Lining Installer - SQO Dynamics Pte. Ltd." | 2024-02-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 20 | AWC | 2024-09-06 | 0 | 000333&&000705 | 2024-02-29, 2024-09-06 | 00 | 2 | Approved with Comments | AWC | 2024-10-16 | Overdue | 0 | AWC | AWC
4075 | 000706 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 0 | 131242-WST02-QA-E-0005-0 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-26 | 53 | AWC | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | AWC | AWC
4076 | 000706 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 1 | 131242-WST02-QA-E-0005-1 | 2024-11-20 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-10 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-04 | 24 | AWC | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | AWC | AWC
4077 | 000706 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 2 | 131242-WST02-QA-E-0005-2 | 2025-01-16 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 2: Approved. | 2025-02-05 | 2025-02-18 | Approved |  | YES | NA |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-30 | 33 | APP | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | APP | APP
4078 | 000706 | 03 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 3 | 131242-WST02-QA-E-0005-3 | 2025-02-26 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-03-18 | 2025-05-06 | Approved |  | YES | NA |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-12 | 69 | APP | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | APP | APP
4079 | 000706 | 04 | Dhanapal.S | QAQC | NA | 131242 | WST02 | QA | E | 0005 | 4 | 131242-WST02-QA-E-0005-4 | 2025-07-03 | Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone) | Rev 3: Approved. | 2025-07-23 | 2025-10-01 | Approved |  | YES | NA |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-07-17 | 90 | APP | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF |  |  | 0 | APP | APP
4080 | 000707 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 0 | 131242-WST02-QA-E-0006-0 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-QA-0006 | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-26 | 53 | AWC | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
4081 | 000707 | 01 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 1 | 131242-WST02-QA-E-0006-1 | 2024-12-20 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-10 | 2025-02-20 | Approved with Comments | 2025-03-12 | YES | Resubmitted |  | 131242-WST02-QA-0006 | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-03 | 62 | AWC | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
4082 | 000707 | 02 | Radha | QAQC | NA | 131242 | WST02 | QA | E | 0006 | 2 | 131242-WST02-QA-E-0006-2 | 2025-10-08 | Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) | Rev 2: Approved | 2025-10-28 | 2026-02-20 | Approved |  | YES | NA |  | 131242-WST02-QA-0006 | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-22 | 135 | APP | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | APP | APP
4083 | 000708 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0001 | 0 | 131242-WSW41-QA-I-0001-0 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0001 | NA | "Inspection Test Plan for Architectural work " && "Inspection Test Plan for Earthwork" && "Inspection Test Plan for Structural Steel Work" && "ST620, Air compressor duct support – materials, fit-up, welding, NDT, Galvanise and painting reports submission" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LV, ELV, EARTH CABLES, BARE CONDUCTOR " && "Vendor Manufacturing Inspection test plan and FAT procedure for Communication Cables (ICA) (Keystone)" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-20 | 63 | AWC | 2025-10-08 | 5 | 000144&&000166&&000316&&000623&&000708&&001413 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-02-20, 2024-08-06, 2024-09-06, 2024-11-21, 2024-12-05, 2025-01-16, 2025-02-21, 2025-06-27, 2025-07-03, 2025-10-08 | 00, 01, 02, 03, 04, 05 | 13 | Approved | APP |  |  | 0 | AWC | AWC
4084 | 000709 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 0 | 131242-WSW41-QA-I-0002-0 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | Approved with Comments | 2024-11-28 | YES | Resubmitted |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 63 | AWC | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4085 | 000709 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 1 | 131242-WSW41-QA-I-0002-1 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | Approved with Comments | 2025-03-14 | YES | Resubmitted |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 63 | AWC | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4086 | 000709 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0002 | 2 | 131242-WSW41-QA-I-0002-2 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0002 | NA | "Inspection Test Plan for Bored piling work" && "Inspection Test Plan for Plastering and Painting Work" && "Inspection and test plan for Compressed Air System" && "Vendor Manufacturing Inspection test plan and FAT procedure for Instrument Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-10-23 | 179 | PEN | 2025-10-09 | 2 | 000145&&000167&&000456&&000709 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-04-30, 2024-07-22, 2024-09-06, 2024-12-13, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved with Comments | AWC | 2025-11-26 |  | 0 | PEN | PEN
4087 | 000710 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 0 | 131242-WSW41-QA-I-0003-0 | 2024-09-06 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-10-04 | 2024-11-08 | Approved with Comments | 2024-11-28 | YES | Resubmitted |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 63 | AWC | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | AWC | AWC
4088 | 000710 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 1 | 131242-WSW41-QA-I-0003-1 | 2024-12-23 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-01-13 | 2025-02-24 | Approved with Comments | 2025-03-14 | YES | Resubmitted |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-06 | 63 | AWC | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | AWC | AWC
4089 | 000710 | 02 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0003 | 2 | 131242-WSW41-QA-I-0003-2 | 2025-10-09 | Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) | Rev 2: Approved | 2025-10-29 | 2026-02-20 | Approved | 2026-03-12 |  | Overdue |  | 131242-WSW41-QA-0003 | NA | "Inspection Test Plan for Installation of Raised Access Floor System Work" && "Inspection Test Plan for Reinforcement work" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Air Blower" && "Vendor Manufacturing Inspection test plan and FAT procedure for Control Cables (ICA & Electrical) (Keystone) " | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-23 | 134 | APP | 2025-10-09 | 2 | 000146&&000168&&000624&&000710 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-08-06, 2024-09-06, 2024-10-09, 2024-11-21, 2024-12-23, 2025-10-09 | 00, 01, 02 | 10 | Approved | APP |  |  | 0 | APP | APP
4090 | 000711 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0011 | 0 | 131242-WST02-VI-E-0011-0 | 2024-09-06 | Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-04 | 2024-10-09 | Approved with Comments | 2024-10-29 | NO | Overdue | To follow-up with VICPLAS. | 131242-WST02-VI-0011 | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 33 | AWC | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
4091 | 000712 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-E-0007-0 | 2024-09-06 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev.0: Rejected as per Contractor's request. | 2024-10-04 | 2024-09-09 | Rejected | 2024-09-27 | YES | Resubmitted |  | 131242-WSW41-QA-0007 | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 3 | REJ | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | Approved | APP |  |  | 0 | REJ | REJ
4092 | 000712 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | E | 0007 | 0 | 131242-WSW41-QA-E-0007-0 | 2024-09-09 | FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone) | Rev 1: Approved. Please refer to attached file and note our comments. | 2024-09-27 | 2024-10-29 | Approved |  | YES | NA |  | 131242-WSW41-QA-0007 | NA | "FAT Procedure for Air Receiver and Air Dryer (Compressor air system)" && "FAT report for CU/LSZH (AT, UV) Single core earth cable (1C x 240mm2 and Bare copper conductor (1C x 240 mm2) (Keystone)" && "Inspection Test Plan for Roadwork" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-23 | 50 | APP | 2024-09-09 | 0 | 000150&&000625&&000712 | 2023-10-27, 2024-08-06, 2024-09-06, 2024-09-09 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
4093 | 000713 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | RT | C | 0007 | 0 | 131242-WSW41-RT-C-0007-0 | 2024-09-06 | Bored Piling Pile Eccentricity Reports (ECC 08 to 12) | Not Approved | 2024-10-04 | 2024-09-13 | Not Approved | 2024-10-03 | NO | Overdue |  | 131242-WSW41-RT-0007 | NA | "Bored Piling Pile Eccentricity Reports (ECC 08 to 12)" && "C4B Monthly Progress Report Number No.07 (11/23)" | 2023-12-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-20 | 7 | NAP | 2024-09-06 | 0 | 000234&&000713 | 2023-12-11, 2024-09-06 | 00 | 2 | Not Approved | NAP | 2024-10-03 | Overdue | 0 | NAP | NAP
4094 | 000714 | 00 | Boopathi | QAQC | NA | 131242 | WST02 | DS | C | 1384 | 0 | 131242-WST02-DS-C-1384-0 | 2024-09-09 | Sample Board Submission for PVC lining System (Linabond) | For Information | 2024-10-07 | 2024-09-13 | For Information |  | YES | NA |  | 131242-WST02-DS-1384 | NA | "Sample Board Submission for PVC lining System (Linabond)" | 2024-09-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-29 | 4 | INF | 2024-09-09 | 0 | 000714 | 2024-09-09 | 00 | 1 | For Information | INF | 2024-10-03 | Overdue | 0 | INF | INF
4095 | 000715 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | SP | C | 0021 | 0 | 131242-WSW41-SP-C-0021-0 | 2024-09-09 | Datat Sheet for Steel Structure and Painting | Rev.0: Not Approved. Please refer to comment sheet for resubmission. | 2024-10-07 | 2024-10-09 | Not Approved | 2024-10-29 | YES | Resubmitted |  | 131242-WSW41-SP-0021 | NA | "Datat Sheet for Steel Structure and Painting" | 2024-09-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-29 | 30 | NAP | 2024-11-16 | 1 | 000715 | 2024-09-09, 2024-11-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4096 | 000715 | 01 | Radha | QAQC | NA | 131242 | WSW41 | SP | C | 0021 | 1 | 131242-WSW41-SP-C-0021-1 | 2024-11-16 | Datat Sheet for Steel Structure and Painting | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-05 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSW41-SP-0021 | NA | "Datat Sheet for Steel Structure and Painting" | 2024-09-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-30 | 22 | AWC | 2024-11-16 | 1 | 000715 | 2024-09-09, 2024-11-16 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4097 | 000716 | 00 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 0 | 131242-WSD11-DS-M-0023-0 | 2024-09-09 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-07 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted |  | 131242-WSD11-DS-0023 | NA | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-29 | 35 | AWC | 2025-01-20 | 2 | 000716 | 2024-09-09, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4098 | 000716 | 01 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 1 | 131242-WSD11-DS-M-0023-1 | 2024-11-13 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-03 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WSD11-DS-0023 | NA | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-27 | 22 | AWC | 2025-01-20 | 2 | 000716 | 2024-09-09, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4099 | 000716 | 02 | Jovonne | Process | NA | 131242 | WSD11 | DS | M | 0023 | 2 | 131242-WSD11-DS-M-0023-2 | 2025-01-20 | Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve | Rev 2: Approved | 2025-02-07 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSD11-DS-0023 | NA | "Data Sheet for Precooler Stage 1 & 2 Sludge Return Control Valve " | 2024-09-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-02-03 | 97 | APP | 2025-01-20 | 2 | 000716 | 2024-09-09, 2024-11-13, 2025-01-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4100 | 000717 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0045 | 0 | 131242-WST02-CD-IM-0045-0 | 2024-09-09 | Submission Of BIM Coordination VCM Model (Aug-2024) | For Information. | 2024-10-07 | 2024-09-24 | For Information |  | YES | NA |  | 131242-WST02-CD-0045 | NA | "Submission Of BIM Coordination VCM Model (Aug-2024)" | 2024-09-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-29 | 15 | INF | 2024-09-09 | 0 | 000717 | 2024-09-09 | 00 | 1 | For Information | INF | 2024-10-14 | Overdue | 0 | INF | INF
4101 | 000718 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 0 | 131242-WST02-DS-E-0010-0 | 2024-09-10 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-10-29 | Approved with Comments | 2024-11-19 | YES | Resubmitted |  | 131242-WST02-DS-0010 | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-30 | 49 | AWC | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4102 | 000718 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 1 | 131242-WST02-DS-E-0010-1 | 2024-12-19 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-09 | 2025-02-18 | Approved with Comments | 2025-03-10 | YES | Resubmitted |  | 131242-WST02-DS-0010 | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 61 | AWC | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4103 | 000718 | 02 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0010 | 2 | 131242-WST02-DS-E-0010-2 | 2025-03-07 | SSN & THP LV, ELV and Earth Cable Data Sheet and Specification | Rev 2: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-03-27 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DS-0010 | NA | "Datasheet for Temperature Transmitter" && "SSN & THP LV, ELV and Earth Cable Data Sheet and Specification" | 2024-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-03-21 | 51 | AWC | 2025-06-25 | 0 | 000718&&001406 | 2024-09-10, 2024-12-19, 2025-03-07, 2025-06-25 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4104 | 000719 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1383 | 0 | 131242-WST02-DS-E-1383-0 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0003) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 | Approved |  | YES | NA |  | 131242-WST02-DS-1383 | NA | "Sample Board Submission for Lightning and Earthing System (MTF 0003)" | 2024-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-30 | 16 | APP | 2024-09-10 | 0 | 000719 | 2024-09-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4105 | 000720 | 00 | Mohan | QAQC | NA | 131242 | WST02 | DS | E | 1385 | 0 | 131242-WST02-DS-E-1385-0 | 2024-09-10 | Sample Board Submission for Lightning and Earthing System (MTF 0005) | Rev 0: Approved. Refer to attached file for comments as noted. | 2024-10-08 | 2024-09-26 | Approved |  | YES | NA |  | 131242-WST02-DS-1385 | NA | "Sample Board Submission for Lightning and Earthing System (MTF 0005)" | 2024-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-30 | 16 | APP | 2024-09-10 | 0 | 000720 | 2024-09-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4106 | 000721 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5451 | 0 | 131242-WST02-DS-M-5451-0 | 2024-09-10 | Data Sheet for Side Manway | Rev 0: Rejected | 2024-10-08 | 2024-10-11 | Rejected |  | YES | NA |  | 131242-WST02-DS-5451 | NA | "Data Sheet for Side Manway" | 2024-09-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-09-30 | 31 | REJ | 2024-09-10 | 0 | 000721 | 2024-09-10 | 00 | 1 | Rejected | REJ | 2024-10-31 | Overdue | 0 | REJ | REJ
4107 | 000722 | 00 | Bryan | HSE | NA | 131242 | WSW41 | MS | Z | 0001 | 0 | 131242-WSW41-MS-Z-0001-0 | 2024-09-11 | MSRA SWP for Operating Forklift | Approved | 2024-10-09 | 2024-10-10 | Approved |  | YES | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-25 | 29 | APP | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | APP | APP
4108 | 000723 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0002 | 0 | 131242-WST02-RT-P-0002-0 | 2024-09-12 | Detailed Design Report – SSN PACKAGE | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-10 | 2024-11-07 | Approved with Comments | 2024-11-27 | NO | Overdue | comments received on 14 Feb | 131242-WST02-RT-0002 | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-09-26 | 56 | AWC | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | Approved | APP |  |  | 0 | AWC | AWC
4109 | 000724 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0016 | 0 | 131242-WSW41-QA-C-0016-0 | 2024-09-16 | Mock-up Temperature Monitoring Test Reports (Alliance) | For Information | 2024-10-14 | 2024-09-26 | For Information |  | YES | NA |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-09-30 | 10 | INF | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | INF | INF
4110 | 000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5351 | 0 | 131242-WST02-CL-P-5351-0 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | Approved with Comments | 2024-10-24 | YES | Resubmitted |  | 131242-WST02-CL-5351 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-06 | 18 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4111 | 000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5361 | 0 | 131242-WST02-CL-P-5361-0 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | Approved with Comments | 2024-10-24 | YES | Resubmitted |  | 131242-WST02-CL-5361 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-06 | 18 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4112 | 000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5371 | 0 | 131242-WST02-CL-P-5371-0 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | Approved with Comments | 2024-10-24 | YES | Resubmitted |  | 131242-WST02-CL-5371 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-06 | 18 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4113 | 000725 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5381 | 0 | 131242-WST02-CL-P-5381-0 | 2024-09-16 | SSN PC pump sizing calculation | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-14 | 2024-10-04 | Approved with Comments | 2024-10-24 | YES | Resubmitted |  | 131242-WST02-CL-5381 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-06 | 18 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4114 | 000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5351 | 1 | 131242-WST02-CL-P-5351-1 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-17 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-CL-5351 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 11 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4115 | 000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5361 | 1 | 131242-WST02-CL-P-5361-1 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-CL-5361 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 11 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4116 | 000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5371 | 1 | 131242-WST02-CL-P-5371-1 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-CL-5371 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 11 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4117 | 000725 | 01 | Prachi | Process | NA | 131242 | WST02 | CL | P | 5381 | 1 | 131242-WST02-CL-P-5381-1 | 2024-11-27 | SSN PC pump sizing calculation | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-26 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WST02-CL-5381 | NA | "SSN PC pump sizing calculation " | 2024-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-11 | 11 | AWC | 2024-11-27 | 1 | 000725 | 2024-09-16, 2024-11-27 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4118 | 000726 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0016 | 0 | 131242-WSW41-RT-PM-0016-0 | 2024-09-16 | C4B Monthly Progress Report Number No.16 (08 24) | Rev. 0 - Approved with comments (need to re-submit; see attached comment sheet) | 2024-10-14 | 2024-10-01 | Approved with Comments | 2024-10-21 | NO | Overdue |  | 131242-WSW41-RT-0016 | NA | "C4B Monthly Progress Report Number No.16 (08 24) " | 2024-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-06 | 15 | AWC | 2024-09-16 | 0 | 000726 | 2024-09-16 | 00 | 1 | Approved with Comments | AWC | 2024-10-21 | Overdue | 0 | AWC | AWC
4119 | 000727 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0040 | 0 | 131242-WSW41-LT-PM-0040-0 | 2024-09-16 | NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA | Rejected. Please refer to S.O. Correspondence no. 258 dated 2 Dec 2024. | 2024-10-14 | 2025-02-24 | Rejected |  | YES | NA | SO Corres 000257. Sent to Vincent on 03 Dec 2025 | 131242-WSW41-LT-0040 | NA | "NOTICE for Extension of Time and Cost for Augering and Sheet Piling surrounding PDMH- C1A - 0102 AREA" | 2024-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-06 | 161 | REJ | 2024-09-16 | 0 | 000727 | 2024-09-16 | 00 | 1 | Rejected | REJ | 2025-03-14 | Overdue | 0 | REJ | REJ
4120 | 000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 0 | 131242-WST02-DS-M-5301-0 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 | Not Approved | 2024-11-04 | YES | Resubmitted |  | 131242-WST02-DS-5301 | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-08 | 26 | NAP | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
4121 | 000728 | 00 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 0 | 131242-WST02-DS-M-5311-0 | 2024-09-18 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Not approved - Revise and Resubmit | 2024-10-16 | 2024-10-14 | Not Approved | 2024-11-04 | YES | Resubmitted |  | 131242-WST02-DS-5311 | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-08 | 26 | NAP | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
4122 | 000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 1 | 131242-WST02-DS-M-5301-1 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2024-12-31 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DS-5301 | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 4 | NAP | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
4123 | 000728 | 01 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 1 | 131242-WST02-DS-M-5311-1 | 2024-12-10 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Not approved - Revise and Resubmit [SRC Comment reply Sheet not provided] | 2025-01-08 | 2024-12-14 | Not Approved | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-DS-5311 | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 4 | NAP | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | NAP | NAP
4124 | 000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5301 | 2 | 131242-WST02-DS-M-5301-2 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-10 | 2025-01-09 | Approved |  | YES | NA |  | 131242-WST02-DS-5301 | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-03 | 20 | APP | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4125 | 000728 | 02 | David | Mech | NA | 131242 | WST02 | DS | M | 5311 | 2 | 131242-WST02-DS-M-5311-2 | 2024-12-20 | Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 2: Approved | 2025-01-20 | 2025-01-09 | Approved |  | YES | NA |  | 131242-WST02-DS-5311 | NA | "Data Sheet for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-03 | 20 | APP | 2024-12-20 | 2 | 000728 | 2024-09-18, 2024-12-10, 2024-12-20 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4126 | 000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5301 | 0 | 131242-WST02-CL-P-5301-0 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 | Approved with Comments | 2024-11-04 | YES | Resubmitted |  | 131242-WST02-CL-5301 | NA | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-08 | 26 | AWC | 2024-09-18 | 1 | 000729 | 2024-09-18 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-01 | Overdue | 0 | AWC | AWC
4127 | 000729 | 00 | David | Mech | NA | 131242 | WST02 | CL | P | 5311 | 0 | 131242-WST02-CL-P-5311-0 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-14 | Approved with Comments | 2024-11-04 | NO | Overdue |  | 131242-WST02-CL-5311 | NA | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-08 | 26 | AWC | 2024-09-18 | 0 | 000729 | 2024-09-18 | 00, 01 | 2 | Approved with Comments | AWC | 2024-11-01 | Overdue | 0 | AWC | AWC
4128 | 000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5301 | 1 | 131242-WST02-CL-P-5301-1 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-08 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-CL-5301 | NA | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-08 | 78 | AWC | 2024-09-18 | 1 | 000729 | 2024-09-18 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
4129 | 000729 | 01 | Qili | Process | NA | 131242 | WST02 | CL | P | 5311 | 1 | 131242-WST02-CL-P-5311-1 | 2024-09-18 | Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-CL-5311 | NA | "Sizing Calculation for EQ Tank Transfer Pump and Discharge Transfer Pump" | 2024-09-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-08 | 78 | AWC | 2024-09-18 | 0 | 000729 | 2024-09-18 | 00, 01 | 2 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
4130 | 000730 | 00 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 0 | 131242-WST02-VI-E-0009-0 | 2024-09-18 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 0: Rejected. To revise and resubmit. Refer to attached file for comments. | 2024-10-16 | 2024-10-10 | Rejected | 2024-10-30 | YES | Resubmitted |  | 131242-WST02-VI-0009 | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-02 | 22 | REJ | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | REJ | REJ
4131 | 000730 | 01 | Freedomer | EICA | NA | 131242 | WST02 | VI | E | 0009 | 1 | 131242-WST02-VI-E-0009-1 | 2024-10-14 | Vendor Approval of LPS Materials (Skypro_DEHN) | Rev 1: Approved with comments. Refer to attached file for comments. | 2024-11-04 | 2024-11-07 | Approved with Comments | 2024-11-27 | NO | Overdue | To follow-up with SKYPRO. | 131242-WST02-VI-0009 | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-28 | 24 | AWC | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | AWC | AWC
4132 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | B | 131242-WST02-DR-P-6000-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6000 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4133 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | B | 131242-WST02-DR-P-6001-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6001 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4134 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | B | 131242-WST02-DR-P-6002-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6002 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4135 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | B | 131242-WST02-DR-P-6003-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6003 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4136 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | B | 131242-WST02-DR-P-6004-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6004 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4137 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | B | 131242-WST02-DR-P-6005-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6005 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4138 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | B | 131242-WST02-DR-P-6006-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6006 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4139 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | B | 131242-WST02-DR-P-6007-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6007 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4140 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | B | 131242-WST02-DR-P-6008-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6008 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4141 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | B | 131242-WST02-DR-P-6009-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6009 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4142 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | B | 131242-WST02-DR-P-6010-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6010 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4143 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | B | 131242-WST02-DR-P-6011-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6011 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4144 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | B | 131242-WST02-DR-P-6012-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6012 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4145 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | B | 131242-WST02-DR-P-6013-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6013 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4146 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | B | 131242-WST02-DR-P-6014-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6014 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4147 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | B | 131242-WST02-DR-P-6015-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6015 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4148 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | B | 131242-WST02-DR-P-6016-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6016 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4149 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | B | 131242-WST02-DR-P-6017-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6017 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4150 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | B | 131242-WST02-DR-P-6018-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6018 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4151 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | B | 131242-WST02-DR-P-6019-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6019 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4152 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | B | 131242-WST02-DR-P-6020-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6020 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4153 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | B | 131242-WST02-DR-P-6200-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6200 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4154 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | C | 131242-WST02-DR-P-6300-C | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6300 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4155 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | C | 131242-WST02-DR-P-6301-C | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6301 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4156 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | C | 131242-WST02-DR-P-6500-C | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6500 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4157 | 000731 | 00 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | B | 131242-WST02-DR-P-6600-B | 2024-09-19 | P&ID for SSN | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-17 | 2024-11-07 | Approved with Comments | 2024-11-27 | YES | Resubmitted |  | 131242-WST02-DR-6600 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-03 | 49 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4158 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | C | 131242-WST02-DR-P-6000-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6000 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4159 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | C | 131242-WST02-DR-P-6001-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6001 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4160 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | C | 131242-WST02-DR-P-6002-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6002 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4161 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | C | 131242-WST02-DR-P-6003-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6003 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4162 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | C | 131242-WST02-DR-P-6004-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6004 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4163 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | C | 131242-WST02-DR-P-6005-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6005 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4164 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | C | 131242-WST02-DR-P-6006-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6006 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4165 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | C | 131242-WST02-DR-P-6007-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6007 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4166 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | C | 131242-WST02-DR-P-6008-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6008 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4167 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | C | 131242-WST02-DR-P-6009-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6009 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4168 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | C | 131242-WST02-DR-P-6010-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6010 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4169 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | C | 131242-WST02-DR-P-6011-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6011 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4170 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | C | 131242-WST02-DR-P-6012-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6012 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4171 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | C | 131242-WST02-DR-P-6013-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6013 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4172 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | C | 131242-WST02-DR-P-6014-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6014 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4173 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | C | 131242-WST02-DR-P-6015-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6015 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4174 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | C | 131242-WST02-DR-P-6016-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6016 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4175 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | C | 131242-WST02-DR-P-6017-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6017 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4176 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | C | 131242-WST02-DR-P-6018-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6018 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4177 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | C | 131242-WST02-DR-P-6019-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6019 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4178 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | C | 131242-WST02-DR-P-6020-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6020 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4179 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | C | 131242-WST02-DR-P-6200-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6200 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4180 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300-D | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6300 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4181 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301-D | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6301 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4182 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500-D | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6500 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4183 | 000731 | 01 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | C | 131242-WST02-DR-P-6600-C | 2025-01-03 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-01-23 | 2025-03-06 | Approved with Comments | 2025-03-26 | YES | Resubmitted |  | 131242-WST02-DR-6600 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-17 | 62 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4184 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-P-6000-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6000 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4185 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | D | 131242-WST02-DR-P-6001-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6001 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4186 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | D | 131242-WST02-DR-P-6002-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6002 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4187 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | D | 131242-WST02-DR-P-6003-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6003 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4188 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | D | 131242-WST02-DR-P-6004-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6004 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4189 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | D | 131242-WST02-DR-P-6005-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6005 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4190 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | D | 131242-WST02-DR-P-6006-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6006 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4191 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | D | 131242-WST02-DR-P-6007-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6007 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4192 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | D | 131242-WST02-DR-P-6008-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6008 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4193 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | D | 131242-WST02-DR-P-6009-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6009 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4194 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | D | 131242-WST02-DR-P-6010-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6010 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4195 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | D | 131242-WST02-DR-P-6011-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6011 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4196 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | D | 131242-WST02-DR-P-6012-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6012 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4197 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | D | 131242-WST02-DR-P-6013-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6013 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4198 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | D | 131242-WST02-DR-P-6014-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6014 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4199 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | D | 131242-WST02-DR-P-6015-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6015 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4200 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | D | 131242-WST02-DR-P-6016-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6016 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4201 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | D | 131242-WST02-DR-P-6017-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6017 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4202 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | D | 131242-WST02-DR-P-6018-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6018 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4203 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | D | 131242-WST02-DR-P-6019-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6019 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4204 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | D | 131242-WST02-DR-P-6020-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6020 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4205 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | D | 131242-WST02-DR-P-6200-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6200 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4206 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6300 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4207 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6301 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4208 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6500 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4209 | 000731 | 02 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | D | 131242-WST02-DR-P-6600-D | 2025-06-16 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-07-04 | 2025-08-28 | Approved with Comments | 2025-09-17 | YES | Resubmitted |  | 131242-WST02-DR-6600 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-30 | 73 | AWC | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4210 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6000 | D | 131242-WST02-DR-P-6000-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6000 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4211 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6001 | D | 131242-WST02-DR-P-6001-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6001 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4212 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6002 | D | 131242-WST02-DR-P-6002-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6002 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4213 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6003 | D | 131242-WST02-DR-P-6003-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6003 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4214 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6004 | D | 131242-WST02-DR-P-6004-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6004 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4215 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6005 | D | 131242-WST02-DR-P-6005-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6005 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4216 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6006 | D | 131242-WST02-DR-P-6006-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6006 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4217 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6007 | D | 131242-WST02-DR-P-6007-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6007 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4218 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6008 | D | 131242-WST02-DR-P-6008-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6008 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4219 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6009 | D | 131242-WST02-DR-P-6009-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6009 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4220 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6010 | D | 131242-WST02-DR-P-6010-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6010 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4221 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6011 | D | 131242-WST02-DR-P-6011-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6011 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4222 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6012 | D | 131242-WST02-DR-P-6012-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6012 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4223 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6013 | D | 131242-WST02-DR-P-6013-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6013 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4224 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6014 | D | 131242-WST02-DR-P-6014-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6014 | NA | "P&ID for SSN" && "P&ID for SSN Process" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000398&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4225 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6015 | D | 131242-WST02-DR-P-6015-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6015 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4226 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6016 | D | 131242-WST02-DR-P-6016-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6016 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4227 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6017 | D | 131242-WST02-DR-P-6017-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6017 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4228 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6018 | D | 131242-WST02-DR-P-6018-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6018 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4229 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6019 | D | 131242-WST02-DR-P-6019-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6019 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4230 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6020 | D | 131242-WST02-DR-P-6020-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6020 | NA | "P&ID for SSN" && "P&ID for SSN Chemical Dosing Systems" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000399&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4231 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6200 | D | 131242-WST02-DR-P-6200-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6200 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4232 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6300 | D | 131242-WST02-DR-P-6300-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6300 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4233 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6301 | D | 131242-WST02-DR-P-6301-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6301 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4234 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6500 | D | 131242-WST02-DR-P-6500-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6500 | NA | "P&ID for SSN" && "Plant Drain and Safety Shower P&ID" | 2023-11-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000187&&000731 | 2023-11-15, 2024-04-25, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4235 | 000731 | 03 | Qili | Process | NA | 131242 | WST02 | DR | P | 6600 | D | 131242-WST02-DR-P-6600-D | 2026-02-24 | P&ID for SSN | Rev.1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-6600 | NA | "P&ID for SSN" && "P&ID for SSN Plant Water and Instrument Air" | 2024-03-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | D | 000400&&000731 | 2024-03-26, 2024-09-19, 2025-01-03, 2025-06-16, 2026-02-24 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
4236 | 000732 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0041 | 0 | 131242-WSW41-LT-PM-0041-0 | 2024-09-20 | CV of Team member (Construction Manager) | Rev 0: Approved | 2024-10-18 | 2024-10-14 | Approved |  | YES | NA |  | 131242-WSW41-LT-0041 | NA | "CV of Team member (Construction Manager)" | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-10 | 24 | APP | 2024-09-20 | 0 | 000732 | 2024-09-20 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4237 | 000733 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 0 | 131242-WSW41-QA-M-0017-0 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | Approved with Comments | 2024-11-25 | YES | Resubmitted |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 46 | AWC | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4238 | 000733 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0017 | 1 | 131242-WSW41-QA-M-0017-1 | 2025-03-06 | Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-03-26 | 2025-03-21 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-03-20 | 15 | AWC | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4239 | 000734 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0016 | 0 | 131242-WSW41-QA-M-0016-0 | 2024-09-20 | Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-18 | 2024-11-05 | Approved with Comments | 2024-11-25 | NO | Overdue |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-04 | 46 | AWC | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4240 | 000735 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0042 | 0 | 131242-WSW41-LT-PM-0042-0 | 2024-09-20 | Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area | Rev (0): Rejected. Please refer to S.O. correspondence no. 268 16 Dec 2024. | 2024-10-18 | 2025-11-20 | Rejected | 2025-12-10 | NO | Overdue |  | 131242-WSW41-LT-0042 | NA | "Extension of Time and Cost for Unforeseeable Underground Obstruction Near Chemical Dosing Area" | 2024-09-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-10 | 426 | REJ | 2024-09-20 | 0 | 000735 | 2024-09-20 | 00 | 1 | Rejected | REJ | 2025-12-10 | Overdue | 0 | REJ | REJ
4241 | 000736 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | MI | P | 0032 | 0 | 131242-WSW41-MI-P-0032-0 | 2024-09-27 | Process & MEICA Meeting Minutes 0032_20240829 | For Information | 2024-10-25 | 2024-10-10 | For Information |  | YES | NA |  | 131242-WSW41-MI-0032 | NA | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Process & MEICA Meeting Minutes 0032_20240829" | 2024-09-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-17 | 13 | INF | 2024-10-14 | 0 | 000736&&000762 | 2024-09-27, 2024-10-14 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4242 | 000737 | 00 | Krishanthy | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-C-0008-0 | 2024-09-27 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-10-25 | 2024-10-24 | Approved with Comments | 2024-11-14 | YES | Resubmitted |  | 131242-WSW41-RT-0008 | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-11 | 27 | AWC | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | AWC | AWC
4243 | 000737 | 01 | Max | HSE | NA | 131242 | WSW41 | RT | C | 0008 | 1 | 131242-WSW41-RT-C-0008-1 | 2024-11-07 | Safety Review for Earth Retaining or Stabilizing Structures (ERSS) | Rev.1: Approved | 2024-11-27 | 2024-11-28 | Approved |  | YES | NA |  | 131242-WSW41-RT-0008 | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-21 | 21 | APP | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
4244 | 000738 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0019 | 0 | 131242-WSW41-QA-M-0019-0 | 2024-09-28 | Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd) | Rev 0: Approved with comments. Refer to attached comment sheet for resubmission. | 2024-10-25 | 2024-10-29 | Approved with Comments | 2024-11-19 | NO | Overdue |  | 131242-WSW41-QA-0019 | NA | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" && "Monthly Concrete Cube Records for Structural works for August 2024" && "T&C Check List " && "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-18 | 31 | AWC | 2025-09-30 | 0 | 000738&&000814&&001343&&001712 | 2024-09-28, 2024-11-14, 2025-06-04, 2025-09-30 | 00 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4245 | 000739 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | MI | PM | 0016 | 0 | 131242-WSW41-MI-PM-0016-0 | 2024-10-01 | Monthly Progress Meeting Minutes 0016_20240924 | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 | For Information |  | YES | NA |  | 131242-WSW41-MI-0016 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0016_20231130" && "Monthly Progress Meeting Minutes 0016_20240924" && "Process & MEICA Meeting Minutes 0016_20240104" | 2024-01-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-15 | 2 | INF | 2024-10-01 | 0 | 000267&&000279&&000339&&000739 | 2024-01-09, 2024-01-18, 2024-03-05, 2024-10-01 | 00 | 4 | For Information | INF | 2024-10-23 | Overdue | 0 | INF | INF
4246 | 000740 | 00 | Krishanthy | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-PM-0016-0 | 2024-10-01 | Monthly Progress Presentation No. 16 (0924) | Rev. 0 - For Information | 2024-10-29 | 2024-10-03 | For Information |  | YES | NA |  | 131242-WSW41-PS-0016 | NA | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" && "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-21 | 2 | INF | 2024-10-31 | 0 | 000740&&000785&&000793 | 2024-10-01, 2024-10-28, 2024-10-31 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
4247 | 000741 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 0 | 131242-WSW41-QA-M-0014-0 | 2024-10-02 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-10-30 | 2024-11-05 | Approved with Comments | 2024-11-25 | YES | Resubmitted |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-22 | 34 | AWC | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4248 | 000741 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0014 | 1 | 131242-WSW41-QA-M-0014-1 | 2025-03-18 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL) | Rev 1: Approved | 2025-04-07 | 2025-04-27 | Approved |  | YES | NA |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-01 | 40 | APP | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | APP | APP
4249 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | S | 8005_ST608_BCA | C | 131242-WST00-DR-S-8005_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST00-DR-8005_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4250 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 0302_ST608_BCA | C | 131242-WST02-DR-S-0302_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-0302_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4251 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1200_ST608_BCA | C | 131242-WST02-DR-S-1200_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4252 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1201_ST608_BCA | C | 131242-WST02-DR-S-1201_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4253 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1202_ST608_BCA | C | 131242-WST02-DR-S-1202_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4254 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1203_ST608_BCA | C | 131242-WST02-DR-S-1203_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1203_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4255 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1204_ST608_BCA | C | 131242-WST02-DR-S-1204_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1204_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4256 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1205_ST608_BCA | C | 131242-WST02-DR-S-1205_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-1205_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4257 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2200_ST608_BCA | C | 131242-WST02-DR-S-2200_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-2200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4258 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2201_ST608_BCA | C | 131242-WST02-DR-S-2201_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-2201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4259 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2202_ST608_BCA | C | 131242-WST02-DR-S-2202_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-2202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4260 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 2203_ST608_BCA | C | 131242-WST02-DR-S-2203_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-2203_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4261 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3200_ST608_BCA | C | 131242-WST02-DR-S-3200_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-3200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4262 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3201_ST608_BCA | C | 131242-WST02-DR-S-3201_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-3201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4263 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 3202_ST608_BCA | C | 131242-WST02-DR-S-3202_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-3202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4264 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5200_ST608_BCA | C | 131242-WST02-DR-S-5200_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5200_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4265 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5201_ST608_BCA | C | 131242-WST02-DR-S-5201_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5201_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4266 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5202_ST608_BCA | C | 131242-WST02-DR-S-5202_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5202_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4267 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5203_ST608_BCA | C | 131242-WST02-DR-S-5203_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5203_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4268 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5204_ST608_BCA | C | 131242-WST02-DR-S-5204_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5204_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4269 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5205_ST608_BCA | C | 131242-WST02-DR-S-5205_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5205_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4270 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5206_ST608_BCA | C | 131242-WST02-DR-S-5206_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5206_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4271 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5207_ST608_BCA | C | 131242-WST02-DR-S-5207_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5207_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4272 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5208_ST608_BCA | C | 131242-WST02-DR-S-5208_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5208_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4273 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5209_ST608_BCA | C | 131242-WST02-DR-S-5209_ST608_BCA-C | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-DR-5209_ST608_BCA | NA | "BCA approval of ST608 - SSN Shelter" && "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-12-05 | E | 000742&&000875 | 2024-10-04, 2024-12-05 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4274 | 000742 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | CL | S | 0002_ST608_BCA | 0 | 131242-WST02-CL-S-0002_ST608_BCA-0 | 2024-10-04 | BCA submission of ST608 – SSN Shelters (for Information) | For Information | 2024-11-04 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WST02-CL-0002_ST608_BCA | NA | "BCA submission of ST608 – SSN Shelters (for Information) " | 2024-10-04 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-24 | 20 | INF | 2024-10-04 | 0 | 000742 | 2024-10-04 | 00 | 1 | For Information | INF | 2024-11-13 | Overdue | 0 | INF | INF
4275 | 000743 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0015 | 0 | 131242-WSW41-PC-W-0015-0 | 2024-10-04 | Payment Claim No.15 | Rev(0): Approved. Please refer to S.O. correspondence no. 230 dated 4 Oct 2024 | 2024-11-04 | 2024-10-09 | Approved |  | YES | NA |  | 131242-WSW41-PC-0015 | NA | "Payment Claim No.15" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-24 | 5 | APP | 2024-10-04 | 0 | 000743 | 2024-10-04 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4276 | 000744 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 0 | 131242-WSW41-QA-M-0018-0 | 2024-10-04 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-04 | 2024-10-11 | Approved with Comments | 2024-11-01 | YES | Resubmitted |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-24 | 7 | AWC | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4277 | 000744 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0018 | 1 | 131242-WSW41-QA-M-0018-1 | 2024-10-30 | Vendor Manufacturing Inspection test plan for Side Manway | Rev 1: Approved | 2024-11-20 | 2024-12-05 | Approved |  | YES | NA |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-13 | 36 | APP | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | APP | APP
4278 | 000745 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0043 | 0 | 131242-WSW41-LT-PM-0043-0 | 2024-10-07 | Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 269 dated 17 Dec 2024. | 2024-11-05 | 2025-02-24 | Rejected |  | YES | NA | SO Corres 000269. Sent to Vincent on 17 Dec 2025 | 131242-WSW41-LT-0043 | NA | "Notice for Extension of Time and Cost for Not To Proceed Relocation of Power Source After Design (NOC REF: C4B-004 _JUN_2024)" | 2024-10-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-27 | 140 | REJ | 2024-10-07 | 0 | 000745 | 2024-10-07 | 00 | 1 | Rejected | REJ | 2025-03-14 | Overdue | 0 | REJ | REJ
4279 | 000746 | 00 | Dharmen | PMT | NA | 131242 | WSW41 | LT | PM | 0044 | 0 | 131242-WSW41-LT-PM-0044-0 | 2024-10-07 | CV of Team member (WSHO) | Approved | 2024-11-05 | 2024-11-15 | Approved |  | YES | NA |  | 131242-WSW41-LT-0044 | NA | "CV of Team member (WSHO)" | 2024-10-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-27 | 39 | APP | 2024-10-07 | 0 | 000746 | 2024-10-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4280 | 000747 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0017 | 0 | 131242-WSW41-QA-C-0017-0 | 2024-10-08 | Mock-up Temperature Monitoring Test Reports - G40 (Pan U) | For Information | 2024-11-06 | 2024-10-14 | For Information |  | YES | NA |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-22 | 6 | INF | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | INF | INF
4281 | 000748 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0046 | 0 | 131242-WSW41-CD-IM-0046-0 | 2024-10-08 | Submission Of BIM Coordination VCM Model (Sept-2024) | For Information. | 2024-11-06 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WSW41-CD-0046 | NA | "Submission Of BIM Coordination VCM Model (Sept-2024)" | 2024-10-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-28 | 21 | INF | 2024-10-08 | 0 | 000748 | 2024-10-08 | 00 | 1 | For Information | INF | 2024-11-18 | Overdue | 0 | INF | INF
4282 | 000749 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | C | 0007 | 0 | 131242-WST02-CL-C-0007-0 | 2024-10-09 | Bar chair Design for SSN Water Tanks Raft Slabs | For Information | 2024-11-07 | 2024-10-14 | Approved |  | YES | NA |  | 131242-WST02-CL-0007 | NA | "Bar chair Design for SSN Water Tanks Raft Slabs " && "Data Sheet, Drawing and Calculation of SSN Diffuser" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-23 | 5 | APP | 2025-08-22 | 2 | 000553&&000749 | 2024-07-09, 2024-10-09, 2024-11-02, 2025-03-06, 2025-08-22 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | APP | APP
4283 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0100_ST602_BCA | E | 131242-WST00-DR-G-0100_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-0100_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4284 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 0101_ST602_BCA | E | 131242-WST00-DR-G-0101_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-0101_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4285 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 1100_ST602_BCA | E | 131242-WST00-DR-G-1100_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-1100_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4286 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 1101_ST602_BCA | E | 131242-WST00-DR-G-1101_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-1101_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4287 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 3100_ST602_BCA | E | 131242-WST00-DR-G-3100_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-3100_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4288 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 3101_ST602_BCA | E | 131242-WST00-DR-G-3101_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-3101_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4289 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 5101_ST602_BCA | E | 131242-WST00-DR-G-5101_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-5101_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4290 | 000750 | 00 | Thet Myo | CSA | NA | 131242 | WST00 | DR | G | 8001_ST602_BCA | E | 131242-WST00-DR-G-8001_ST602_BCA-E | 2024-10-09 | BCA approval of ST602 - ERSS Design < 6m | For Information | 2024-11-07 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WST00-DR-8001_ST602_BCA | NA | "BCA approval of ST602 - ERSS Design < 6m " | 2024-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-10-29 | 30 | INF | 2024-10-09 | E | 000750 | 2024-10-09 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4291 | 000751 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451-0 | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | Approved with Comments | 2024-11-01 | YES | Resubmitted |  | 131242-WST02-CL-5451 | NA | "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 2 | AWC | 2024-12-17 | 0 | 000751 | 2024-10-09, 2024-11-08, 2024-12-17 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4292 | 000751 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A | 131242-WST02-DR-M-5451-A | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | Approved with Comments | 2024-11-01 | YES | Resubmitted |  | 131242-WST02-DR-5451 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 2 | AWC | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
4293 | 000751 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A | 131242-WST02-DR-M-5452-A | 2024-10-09 | Side Manway Calculation and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-07 | 2024-10-11 | Approved with Comments | 2024-11-01 | YES | Resubmitted |  | 131242-WST02-DR-5452 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 2 | AWC | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
4294 | 000751 | 01 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451-0 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-CL-5451 | NA | "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 27 | AWC | 2024-12-17 | 0 | 000751 | 2024-10-09, 2024-11-08, 2024-12-17 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4295 | 000751 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A.1 | 131242-WST02-DR-M-5451-A.1 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5451 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 27 | AWC | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
4296 | 000751 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A.1 | 131242-WST02-DR-M-5452-A.1 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted |  | 131242-WST02-DR-5452 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 27 | AWC | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
4297 | 000751 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5451 | 0 | 131242-WST02-CL-M-5451-0 | 2024-12-17 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | Approved |  | YES | NA |  | 131242-WST02-CL-5451 | NA | "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema | 2024-12-31 | 34 | APP | 2024-12-17 | 0 | 000751 | 2024-10-09, 2024-11-08, 2024-12-17 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4298 | 000751 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5451 | A.1 | 131242-WST02-DR-M-5451-A.1 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | Approved |  | YES | NA |  | 131242-WST02-DR-5451 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema | 2024-11-22 | 73 | APP | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
4299 | 000751 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5452 | A.1 | 131242-WST02-DR-M-5452-A.1 | 2024-11-08 | Side Manway Calculation and GA Drawing | Rev 2: Approved | 2025-01-07 | 2025-01-20 | Approved |  | YES | NA |  | 131242-WST02-DR-5452 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema | 2024-11-22 | 73 | APP | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP |  |  | 0 | APP | APP
4300 | 000752 | 00 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 0 | 131242-WST02-RT-P-0003-0 | 2024-10-09 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-07 | 2024-11-15 | Approved with Comments | 2024-12-05 | YES | Resubmitted |  | 131242-WST02-RT-0003 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-23 | 37 | AWC | 2025-07-01 | 0 | 000490&&000752&&001420 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4301 | 000752 | 01 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 1 | 131242-WST02-RT-P-0003-1 | 2024-12-10 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-12-31 | 2024-12-14 | Approved with Comments | 2025-01-03 | YES | Resubmitted |  | 131242-WST02-RT-0003 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-24 | 4 | AWC | 2025-07-01 | 0 | 000490&&000752&&001420 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4302 | 000752 | 02 | Qili | Process | NA | 131242 | WST02 | RT | P | 0003 | 2 | 131242-WST02-RT-P-0003-2 | 2025-01-20 | SSN HAZOP Report | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-02-07 | 2025-03-13 | Approved with Comments | 2025-04-02 | NO | Overdue |  | 131242-WST02-RT-0003 | NA | "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " && "Report of DFS (Guide 3) for ERSS" && "SSN HAZOP Report" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-02-03 | 52 | AWC | 2025-07-01 | 0 | 000490&&000752&&001420 | 2024-05-28, 2024-06-19, 2024-10-09, 2024-12-10, 2025-01-20, 2025-07-01 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4303 | 000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 1400 | 0 | 131242-WST02-DR-S-1400-0 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-DR-1400 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-30 | 19 | INF | 2025-12-18 | H | 000753&&000836&&001148&&001730&&001914 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 6 | Not Approved | NAP |  |  | 0 | INF | INF
4304 | 000753 | 00 | Thet Myo | CSA | NA | 131242 | WST02 | DR | S | 5400 | 0 | 131242-WST02-DR-S-5400-0 | 2024-10-10 | SSN- Biomass separator footing detail | For Information | 2024-11-08 | 2024-10-29 | For Information |  | YES | NA |  | 131242-WST02-DR-5400 | NA | "Hookup Drawing -TSS Analyser" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-30 | 19 | INF | 2025-12-18 | F | 000753&&000836&&001730&&001788&&001914 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00 | 5 | Not Approved | NAP |  |  | 0 | INF | INF
4305 | 000754 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0045 | 0 | 131242-WSW41-LT-PM-0045-0 | 2024-10-10 | NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024) | Rev (0): Rejected. Please refer to S.O. correspondence no. 308 dated 12 March 2025 | 2024-11-08 | 2025-11-20 | Rejected | 2025-12-10 | NO | Overdue |  | 131242-WSW41-LT-0045 | NA | "NOTICE Extension of Time and Cost for Change In Particulars Specifications From SO on 15 January 2024 (C4B-005_JUL_2024)" | 2024-10-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365); Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-30 | 406 | REJ | 2024-10-10 | 0 | 000754 | 2024-10-10 | 00 | 1 | Rejected | REJ | 2025-12-10 | Overdue | 0 | REJ | REJ
4306 | 000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 0 | 131242-WST02-DS-M-5501-0 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted | In progress. Process (Qili) will provide updated Datasheet (some change as Pump Calculation, we just received SO cmt sheet on Pump Calc last week) -> in 2 weeks | 131242-WST02-DS-5501 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 47 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4307 | 000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5511 | 0 | 131242-WST02-DS-M-5511-0 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted |  | 131242-WST02-DS-5511 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 47 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4308 | 000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5521 | 0 | 131242-WST02-DS-M-5521-0 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted |  | 131242-WST02-DS-5521 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 47 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4309 | 000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5531 | 0 | 131242-WST02-DS-M-5531-0 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted |  | 131242-WST02-DS-5531 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 47 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4310 | 000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5541 | 0 | 131242-WST02-DS-M-5541-0 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted |  | 131242-WST02-DS-5541 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 47 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4311 | 000755 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5551 | 0 | 131242-WST02-DS-M-5551-0 | 2024-10-11 | Data Sheets for Dosing Pumps | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted |  | 131242-WST02-DS-5551 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-31 | 47 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4312 | 000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5501 | 1 | 131242-WST02-DS-M-5501-1 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5501 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4313 | 000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5511 | 1 | 131242-WST02-DS-M-5511-1 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5511 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4314 | 000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5521 | 1 | 131242-WST02-DS-M-5521-1 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5521 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4315 | 000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5531 | 1 | 131242-WST02-DS-M-5531-1 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5531 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4316 | 000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5541 | 1 | 131242-WST02-DS-M-5541-1 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5541 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4317 | 000755 | 01 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5551 | 1 | 131242-WST02-DS-M-5551-1 | 2025-03-04 | Data Sheets for Dosing Pumps | Rev 1: Approved | 2025-03-24 | 2025-10-06 | Approved with Comments |  | YES | NA |  | 131242-WST02-DS-5551 | NA | "Data Sheets for Dosing Pumps" | 2024-10-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-03-18 | 216 | AWC | 2025-03-04 | 1 | 000755 | 2024-10-11, 2025-03-04 | 00, 01 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
4318 | 000756 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0020 | 0 | 131242-WSW41-QA-M-0020-0 | 2024-10-11 | Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2024-11-11 | 2024-11-19 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0020 | NA | "Monthly Concrete Cube Records for Structural works for September 2024" && "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" && "T&C Check List " | 2024-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-31 | 39 | AWC | 2025-09-30 | 0 | 000756&&000830&&001712 | 2024-10-11, 2024-11-21, 2025-09-30 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4319 | 000757 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | C | 0018 | 0 | 131242-WSW41-QA-C-0018-0 | 2024-10-11 | Mock-up Temperature Monitoring Test Reports – G45 (Pan U) | For information. | 2024-11-11 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-10-25 | 13 | INF | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC |  |  | 0 | INF | INF
4320 | 000758 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 0 | 131242-WSW41-VI-M-1006-0 | 2024-10-12 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-11 | 2024-11-24 | Approved with Comments | 2024-12-12 | YES | Resubmitted |  | 131242-WSW41-VI-1006 | NA | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | 2024-10-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-01 | 43 | AWC | 2025-01-16 | 1 | 000758 | 2024-10-12, 2025-01-16 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4321 | 000758 | 01 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1006 | 1 | 131242-WSW41-VI-M-1006-1 | 2025-01-16 | Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton) | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-02-05 | 2025-01-20 | Approved with Comments |  | YES | NA | As per SO response, Resubmission is not required. | 131242-WSW41-VI-1006 | NA | "Preliminary Design and Vendor Approval – Metallic Ball Valves (OVS_Heaton)" | 2024-10-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-01-30 | 4 | AWC | 2025-01-16 | 1 | 000758 | 2024-10-12, 2025-01-16 | 00, 01 | 2 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4322 | 000759 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0_NIL | 131242-WSW41-MS-M-0002-0_NIL | 2024-10-14 | Delivery and Storage of Compressor Package at Biosolids Building | Rev.0: As requested by Contractor to reject the submittal. | 2024-11-12 | 2024-10-14 | Rejected | 2024-11-04 | YES | Resubmitted |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-28 | 0 | REJ | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | REJ | REJ
4323 | 000759 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 0 | 131242-WSW41-MS-M-0002-0 | 2024-10-15 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 0: Approved with comments - Revise and Resubmit | 2024-11-05 | 2024-10-24 | Approved with Comments | 2024-11-14 | YES | Resubmitted |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 9 | AWC | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | AWC | AWC
4324 | 000759 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | M | 0002 | 1 | 131242-WSW41-MS-M-0002-1 | 2024-10-30 | Delivery and Storage of Compressor Package at Biosolids Building | Rev 2: Approved | 2024-11-20 | 2024-12-03 | Approved |  | YES | NA |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-13 | 34 | APP | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | APP | APP
4325 | 000760 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0014 | 0 | 131242-WSW41-PS-HS-0014-0 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Jul 2024 | Rev 0: Scoring confirmed to be at 98/100 | 2024-11-12 | 2024-11-15 | For Information |  | YES | NA |  | 131242-WSW41-PS-0014 | NA | "Incentive/ Disincentive Audit Scheme for Jul 2024" && "Monthly Progress Meeting Minutes 0014_20240723" | 2024-08-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-28 | 32 | INF | 2024-10-14 | 0 | 000629&&000760 | 2024-08-07, 2024-10-14 | 00 | 2 | For Information | INF | 2024-12-05 | Overdue | 0 | INF | INF
4326 | 000761 | 00 | Samy | HSE | NA | 131242 | WSW41 | PS | HS | 0015 | 0 | 131242-WSW41-PS-HS-0015-0 | 2024-10-14 | Incentive/ Disincentive Audit Scheme for Aug 2024 | Rev 0: Scoring confirmed to be at 95/100 | 2024-11-12 | 2024-11-15 | For Information |  | YES | NA |  | 131242-WSW41-PS-0015 | NA | "Incentive/ Disincentive Audit Scheme for Aug 2024" && "Monthly Progress Presentation No. 15 (0824)" | 2024-09-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-28 | 32 | INF | 2024-10-14 | 0 | 000701&&000761 | 2024-09-04, 2024-10-14 | 00 | 2 | For Information | INF | 2024-12-05 | Overdue | 0 | INF | INF
4327 | 000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0031 | 0 | 131242-WSW41-MI-C-0031-0 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0031 | NA | "BIM Bi-Weekly Meeting Minutes 0019~0027, 0029~0031" && "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Process & MEICA Meeting Minutes 0031_20240815" | 2024-08-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-28 | 10 | INF | 2024-10-14 | 0 | 000684&&000685&&000762 | 2024-08-29, 2024-10-14 | 00 | 3 | For Information | INF | 2024-11-13 | Overdue | 0 | INF | INF
4328 | 000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0032 | 0 | 131242-WSW41-MI-C-0032-0 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0032 | NA | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" && "Process & MEICA Meeting Minutes 0032_20240829" | 2024-09-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-10-28 | 10 | INF | 2024-10-14 | 0 | 000736&&000762 | 2024-09-27, 2024-10-14 | 00 | 2 | For Information | INF | 2024-11-13 | Overdue | 0 | INF | INF
4329 | 000762 | 00 | Krishanthy | CSA | NA | 131242 | WSW41 | MI | C | 0033 | 0 | 131242-WSW41-MI-C-0033-0 | 2024-10-14 | CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024 | For information. | 2024-11-12 | 2024-10-24 | For Information |  | YES | NA |  | 131242-WSW41-MI-0033 | NA | "CSA Meeting Minutes 0031,0032,0033_2208, 0509 & 1909 2024" | 2024-10-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-03 | 10 | INF | 2024-10-14 | 0 | 000762 | 2024-10-14 | 00 | 1 | For Information | INF | 2024-11-13 | Overdue | 0 | INF | INF
4330 | 000763 | 00 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 0 | 131242-WST02-CD-I-0005-0 | 2024-10-15 | SSN Instrument List | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2024-11-13 | 2025-02-13 | Not Approved | 2025-03-05 | YES | Resubmitted |  | 131242-WST02-CD-0005 | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-10-29 | 121 | NAP | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
4331 | 000763 | 01 | Yean Yee/ Low | EICA | NA | 131242 | WST02 | CD | I | 0005 | 1 | 131242-WST02-CD-I-0005-1 | 2025-10-27 | SSN Instrument List | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-11-14 | 2026-01-26 | Approved with Comments | 2026-02-13 | NO | Overdue |  | 131242-WST02-CD-0005 | NA | "SSN Instrument List " && "Submission of Milestone 1.1 Astrea Separator Model" && "Submission of Milestone 1.1 Pump Stataion and Blower Area" | 2023-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 91 | AWC | 2025-10-27 | 1 | 000162&&000164&&000763 | 2023-11-06, 2024-10-15, 2025-10-27 | 00, 01 | 4 | Approved with Comments | AWC | 2026-02-13 | Overdue | 0 | AWC | AWC
4332 | 000764 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 0 | 131242-WSD11-QA-I-0004-0 | 2024-10-17 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2024-11-15 | 2025-03-25 | Approved with Comments | 2025-04-14 | YES | Resubmitted |  | 131242-WSD11-QA-0004 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-06 | 159 | AWC | 2026-01-28 | 0 | 000764&&000993 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4333 | 000764 | 01 | Radha | QAQC | NA | 131242 | WSD11 | QA | I | 0004 | 1 | 131242-WSD11-QA-I-0004-1 | 2025-05-30 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel | Approved with comments. Please refer to comment sheet for resubmission. | 2025-06-19 | 2025-06-04 | Approved with Comments | 2025-06-24 | NO | Overdue |  | 131242-WSD11-QA-0004 | NA | "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Compressor Master Control Panel " | 2024-10-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-06-13 | 5 | AWC | 2026-01-28 | 0 | 000764&&000993 | 2024-10-17, 2025-01-20, 2025-04-08, 2025-05-30, 2026-01-28 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4334 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614 | A | 131242-WSW41-DR-S-0310_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0310_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4335 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614 | A | 131242-WSW41-DR-S-0311_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0311_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4336 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614 | A | 131242-WSW41-DR-S-0312_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0312_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4337 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614 | A | 131242-WSW41-DR-S-0313_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0313_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4338 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614 | A | 131242-WSW41-DR-S-0314_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0314_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4339 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614 | A | 131242-WSW41-DR-S-0315_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0315_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4340 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0316_ST614 | A | 131242-WSW41-DR-S-0316_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0316_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4341 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0317_ST614 | A | 131242-WSW41-DR-S-0317_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-0317_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4342 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614 | A | 131242-WSW41-DR-S-1100_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-1100_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4343 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614 | A | 131242-WSW41-DR-S-1101_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-1101_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4344 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614 | A | 131242-WSW41-DR-S-1102_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-1102_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4345 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614 | A | 131242-WSW41-DR-S-1103_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-1103_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4346 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614 | A | 131242-WSW41-DR-S-1104_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-1104_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4347 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614 | A | 131242-WSW41-DR-S-2100_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-2100_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4348 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614 | A | 131242-WSW41-DR-S-2101_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-2101_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4349 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614 | A | 131242-WSW41-DR-S-3100_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-3100_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4350 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614 | A | 131242-WSW41-DR-S-5100_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-5100_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4351 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614 | A | 131242-WSW41-DR-S-5101_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-5101_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4352 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614 | A | 131242-WSW41-DR-S-5102_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-5102_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4353 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614 | A | 131242-WSW41-DR-S-5103_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-5103_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4354 | 000765 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614 | A | 131242-WSW41-DR-S-8002_ST614-A | 2024-10-17 | ST614 - SiteWide Pipe Rack 003 | For information. | 2024-11-15 | 2024-11-08 | For Information |  | YES | NA |  | 131242-WSW41-DR-8002_ST614 | NA | "ST614 - SiteWide Pipe Rack 003" | 2024-10-17 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-06 | 22 | INF | 2024-10-17 | A | 000765 | 2024-10-17 | 00 | 1 | For Information | INF | 2024-11-28 | Overdue | 0 | INF | INF
4355 | 000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | CL | M | 5461 | 0 | 131242-WST02-CL-M-5461-0 | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | Approved with Comments | 2024-12-05 | YES | Resubmitted |  | 131242-WST02-CL-5461 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-07 | 28 | AWC | 2025-04-04 | 2 | 000766 | 2024-10-18, 2025-04-04 | 00, 02 | 2 | Approved | APP |  |  | 0 | AWC | AWC
4356 | 000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | DR | M | 5461 | A | 131242-WST02-DR-M-5461-A | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | Approved with Comments | 2024-12-05 | YES | Resubmitted |  | 131242-WST02-DR-5461 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Hookup Drawing - Rotameter" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-07 | 28 | AWC | 2025-10-23 | A | 000766&&001783 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4357 | 000766 | 00 | David | Piping/ BS | NA | 131242 | WST02 | DR | M | 5463 | A | 131242-WST02-DR-M-5463-A | 2024-10-18 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-18 | 2024-11-15 | Approved with Comments | 2024-12-05 | YES | Resubmitted |  | 131242-WST02-DR-5463 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-07 | 28 | AWC | 2025-04-04 | C | 000766 | 2024-10-18, 2024-12-06, 2025-04-04 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4358 | 000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | A.1 | 131242-WST02-DR-M-5461-A.1 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-27 | 2024-12-12 | Approved with Comments | 2025-01-02 | YES | Resubmitted | The Only comment is to get PE endorsement (Mech PE) | 131242-WST02-DR-5461 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Hookup Drawing - Rotameter" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 6 | AWC | 2025-10-23 | A | 000766&&001783 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4359 | 000766 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5463 | A.1 | 131242-WST02-DR-M-5463-A.1 | 2024-12-06 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-01-06 | 2024-12-12 | Approved with Comments | 2025-01-02 | YES | Resubmitted |  | 131242-WST02-DR-5463 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-20 | 6 | AWC | 2025-04-04 | C | 000766 | 2024-10-18, 2024-12-06, 2025-04-04 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | AWC | AWC
4360 | 000766 | 02 | David | Mech | NA | 131242 | WST02 | CL | M | 5461 | 2 | 131242-WST02-CL-M-5461-2 | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-CL-5461 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-18 | 185 | APP | 2025-04-04 | 2 | 000766 | 2024-10-18, 2025-04-04 | 00, 02 | 2 | Approved | APP |  |  | 0 | APP | APP
4361 | 000766 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5461 | C | 131242-WST02-DR-M-5461-C | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5461 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Hookup Drawing - Rotameter" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-18 | 185 | APP | 2025-10-23 | A | 000766&&001783 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | APP | APP
4362 | 000766 | 02 | David | Mech | NA | 131242 | WST02 | DR | M | 5463 | C | 131242-WST02-DR-M-5463-C | 2025-04-04 | GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway) | Rev 2: Approved | 2025-04-24 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WST02-DR-5463 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" | 2024-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-04-18 | 185 | APP | 2025-04-04 | C | 000766 | 2024-10-18, 2024-12-06, 2025-04-04 | 00, 01, 02 | 3 | Approved | APP |  |  | 0 | APP | APP
4363 | 000767 | 00 | Leslie | PCM | NA | 131242 | WSW41 | RT | PM | 0017 | 0 | 131242-WSW41-RT-PM-0017-0 | 2024-10-19 | C4B Monthly Progress Report Number No.17 (09 24) | Rev. 0 - Approved with comments, need to re-submit (see attached comment sheet) | 2024-11-18 | 2024-10-25 | Approved with Comments | 2024-11-15 | NO | Overdue |  | 131242-WSW41-RT-0017 | NA | "C4B Monthly Progress Report Number No.17 (09 24) " | 2024-10-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-08 | 6 | AWC | 2024-10-19 | 0 | 000767 | 2024-10-19 | 00 | 1 | Approved with Comments | AWC | 2024-11-14 | Overdue | 0 | AWC | AWC
4364 | 000768 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0046 | 0 | 131242-WSW41-LT-PM-0046-0 | 2024-10-21 | Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings | Rev (0): Received for information. lease refer to S.O. correspondence no. 289 dated 21 Jan 2025. | 2024-11-19 | 2025-11-20 | For Information |  | YES | NA |  | 131242-WSW41-LT-0046 | NA | "Notice for Extension of Time and Cost for Other Contractors Work Delays to the Electrical and Transformer Buildings" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Duration_of_Review too high (>365) | 2024-11-10 | 395 | INF | 2024-10-21 | 0 | 000768 | 2024-10-21 | 00 | 1 | For Information | INF | 2025-12-10 | Overdue | 0 | INF | INF
4365 | 000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5501 | 0 | 131242-WST02-CL-P-5501-0 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue | Pending model update, need PE endorsement | 131242-WST02-CL-5501 | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-10 | 91 | AWC | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4366 | 000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5511 | 0 | 131242-WST02-CL-P-5511-0 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WST02-CL-5511 | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-10 | 91 | AWC | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4367 | 000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5521 | 0 | 131242-WST02-CL-P-5521-0 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WST02-CL-5521 | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-10 | 91 | AWC | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4368 | 000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5531 | 0 | 131242-WST02-CL-P-5531-0 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WST02-CL-5531 | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-10 | 91 | AWC | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4369 | 000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5541 | 0 | 131242-WST02-CL-P-5541-0 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WST02-CL-5541 | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-10 | 91 | AWC | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4370 | 000769 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 5551 | 0 | 131242-WST02-CL-P-5551-0 | 2024-10-21 | SSN Dosing Pump Sizing Calculations | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-19 | 2025-01-20 | Approved with Comments | 2025-02-07 | NO | Overdue |  | 131242-WST02-CL-5551 | NA | "SSN Dosing Pump Sizing Calculations" | 2024-10-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-10 | 91 | AWC | 2024-10-21 | 0 | 000769 | 2024-10-21 | 00 | 1 | Approved with Comments | AWC | 2025-02-07 | Overdue | 0 | AWC | AWC
4371 | 000770 | 00 | Sithu | Const; | NA | 131242 | WST02 | CL | K | 0001 | 0 | 131242-WST02-CL-K-0001-0 | 2024-10-22 | SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs | Rev 0: Approved with comments. Please refer to comment sheet. | 2024-11-20 | 2024-11-21 | Approved with Comments | 2024-12-11 | NO | Overdue |  | 131242-WST02-CL-0001 | NA | "SSN Cable Sizing Calculations" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" && "SSN Water Tank Formwork and False Work Design of Walls, Beams and Slabs" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-05 | 30 | AWC | 2025-05-30 | 2 | 000173&&000199&&000408&&000770 | 2023-11-08, 2023-11-22, 2024-05-06, 2024-06-24, 2024-07-05, 2024-08-07, 2024-10-22, 2025-05-30 | 00, 01, 02 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4372 | 000771 | 00 | Radha | QAQC | NA | 131242 | WSW41 | RT | C | 0008 | 0 | 131242-WSW41-RT-C-0008-0 | 2024-10-22 | Bored Piling Pile Eccentricity Reports (ECC 13 to 18) | For Information. Please find attached comment sheet. | 2024-11-20 | 2024-11-04 | For Information |  | YES | NA |  | 131242-WSW41-RT-0008 | NA | "Bored Piling Pile Eccentricity Reports (ECC 13 to 18)" && "C4B Monthly Progress Report Number No.08 (12/23)" && "Safety Review for Earth Retaining or Stabilizing Structures (ERSS)" | 2024-01-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-05 | 13 | INF | 2024-11-07 | 1 | 000276&&000737&&000771 | 2024-01-16, 2024-09-27, 2024-10-22, 2024-11-07 | 00, 01 | 4 | Approved | APP |  |  | 0 | INF | INF
4373 | 000772 | 00 | Qili | Process | NA | 131242 | WST02 | RT | E | 0006 | 0 | 131242-WST02-RT-E-0006-0 | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-RT-0006 | NA | "SSN Hazardous Area Assessment Report" && "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" && "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | 2024-07-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-06 | 153 | AWC | 2025-11-20 | 0 | 000545&&000772&&001856 | 2024-07-04, 2024-10-23, 2025-11-20 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4374 | 000772 | 00 | Qili | Process | NA | 131242 | WST02 | DR | E | 8001 | A | 131242-WST02-DR-E-8001-A | 2024-10-23 | SSN Hazardous Area Assessment Report | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-21 | 2025-03-25 | Approved with Comments | 2025-04-14 | NO | Overdue |  | 131242-WST02-DR-8001 | NA | "SSN Hazardous Area Assessment Report" | 2024-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-12 | 153 | AWC | 2024-10-23 | A | 000772 | 2024-10-23 | 00 | 1 | Approved with Comments | AWC | 2025-04-14 | Overdue | 0 | AWC | AWC
4375 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0310_ST614_BCA | A | 131242-WSW41-DR-S-0310_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0310_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4376 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0311_ST614_BCA | A | 131242-WSW41-DR-S-0311_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0311_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4377 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0312_ST614_BCA | A | 131242-WSW41-DR-S-0312_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0312_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4378 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0313_ST614_BCA | A | 131242-WSW41-DR-S-0313_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0313_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4379 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0314_ST614_BCA | A | 131242-WSW41-DR-S-0314_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0314_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4380 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0315_ST614_BCA | A | 131242-WSW41-DR-S-0315_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0315_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | C | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4381 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0316_ST614_BCA | A | 131242-WSW41-DR-S-0316_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0316_ST614_BCA | NA | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2024-10-23 | A | 000773 | 2024-10-23 | 00 | 1 | For Information | INF | 2025-01-02 | Overdue | 0 | INF | INF
4382 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 0317_ST614_BCA | A | 131242-WSW41-DR-S-0317_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-0317_ST614_BCA | NA | "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2024-10-23 | A | 000773 | 2024-10-23 | 00 | 1 | For Information | INF | 2025-01-02 | Overdue | 0 | INF | INF
4383 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1100_ST614_BCA | A | 131242-WSW41-DR-S-1100_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-1100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4384 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1101_ST614_BCA | A | 131242-WSW41-DR-S-1101_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-1101_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4385 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1102_ST614_BCA | A | 131242-WSW41-DR-S-1102_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-1102_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4386 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1103_ST614_BCA | A | 131242-WSW41-DR-S-1103_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-1103_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4387 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 1104_ST614_BCA | A | 131242-WSW41-DR-S-1104_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-1104_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4388 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2100_ST614_BCA | A | 131242-WSW41-DR-S-2100_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-2100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4389 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 2101_ST614_BCA | A | 131242-WSW41-DR-S-2101_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-2101_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4390 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 3100_ST614_BCA | A | 131242-WSW41-DR-S-3100_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-3100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4391 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5100_ST614_BCA | A | 131242-WSW41-DR-S-5100_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-5100_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4392 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5101_ST614_BCA | A | 131242-WSW41-DR-S-5101_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-5101_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4393 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5102_ST614_BCA | A | 131242-WSW41-DR-S-5102_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-5102_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4394 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 5103_ST614_BCA | A | 131242-WSW41-DR-S-5103_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-5103_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4395 | 000773 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | DR | S | 8002_ST614_BCA | A | 131242-WSW41-DR-S-8002_ST614_BCA-A | 2024-10-23 | BCA submission of ST614 – Site Wide Piperack 03 (for Information) | For information | 2024-11-21 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSW41-DR-8002_ST614_BCA | NA | "BCA Approval of ST614 (Side Wide Pipe Rack WSW41-PR-03) " && "BCA submission of ST614 – Site Wide Piperack 03 (for Information) " | 2024-10-23 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2024-11-12 | 52 | INF | 2025-01-03 | D | 000773&&000947 | 2024-10-23, 2025-01-03 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
4396 | 000774 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 0 | 131242-WSW41-DS-E-1386-0 | 2024-10-23 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 0: Approved with comments. To revise and resubmit. Please refer to attached file for comments. | 2024-11-21 | 2024-11-21 | Approved with Comments | 2024-12-11 | YES | Resubmitted |  | 131242-WSW41-DS-1386 | NA | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | 2024-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-12 | 29 | AWC | 2024-12-20 | 1 | 000774 | 2024-10-23, 2024-12-20 | 00, 01 | 2 | Rejected | REJ |  |  | 0 | AWC | AWC
4397 | 000774 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | DS | E | 1386 | 1 | 131242-WSW41-DS-E-1386-1 | 2024-12-20 | Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh | Rev 1: Rejected. Wrong comment reply sheet has been attached. | 2025-01-10 | 2025-02-18 | Rejected | 2025-03-10 | NO | Overdue |  | 131242-WSW41-DS-1386 | NA | "Sample Board Submission for Pre-fabricated 6 mm Solid Copper Round Rod Grid size 200mmX200mm Wire mesh" | 2024-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-03 | 60 | REJ | 2024-12-20 | 1 | 000774 | 2024-10-23, 2024-12-20 | 00, 01 | 2 | Rejected | REJ | 2025-03-10 | Overdue | 0 | REJ | REJ
4398 | 000775 | 00 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 0 | 131242-WSW41-MS-C-0019-0 | 2024-10-23 | MSRA for RC Wall | Rev.0: Approved with comments. Please refer to comment sheet for resubmission. | 2024-11-21 | 2024-11-15 | Approved with Comments | 2024-12-05 | YES | Resubmitted |  | 131242-WSW41-MS-0019 | NA | "MSRA for RC Wall" | 2024-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-12 | 23 | AWC | 2024-12-19 | 1 | 000775 | 2024-10-23, 2024-11-26, 2024-12-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4399 | 000775 | 01 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-C-0019-1 | 2024-11-26 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2024-12-16 | 2024-12-18 | Approved with Comments | 2025-01-08 | YES | Resubmitted |  | 131242-WSW41-MS-0019 | NA | "MSRA for RC Wall" | 2024-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-12-10 | 22 | AWC | 2024-12-19 | 1 | 000775 | 2024-10-23, 2024-11-26, 2024-12-19 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4400 | 000775 | 02 | Charles | Const; | NA | 131242 | WSW41 | MS | C | 0019 | 1 | 131242-WSW41-MS-C-0019-1 | 2024-12-19 | MSRA for RC Wall | Rev.1: Approved with comments. Please refer to comment sheet. | 2025-01-09 | 2025-01-08 | Approved with Comments | 2025-01-28 | NO | Overdue |  | 131242-WSW41-MS-0019 | NA | "MSRA for RC Wall" | 2024-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-01-02 | 20 | AWC | 2024-12-19 | 1 | 000775 | 2024-10-23, 2024-11-26, 2024-12-19 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2025-01-28 | Overdue | 0 | AWC | AWC
4401 | 000776 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0047 | 0 | 131242-WSW41-LT-PM-0047-0 | 2024-10-25 | Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works | Rejected. Please refer to S.O. correspondence no. 276 dated 7 January 2025. | 2024-11-25 | 2025-08-25 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0047 | NA | "Cost for 1st Extension of Time for Completion of Phase I of the Works and Whole of the Works " | 2024-10-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-14 | 304 | REJ | 2024-10-25 | 0 | 000776 | 2024-10-25 | 00 | 1 | Rejected | REJ | 2025-09-12 | Overdue | 0 | REJ | REJ
4402 | 000777 | 00 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 0 | 131242-WSW41-VI-M-0010-0 | 2024-10-25 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments | 2024-11-25 | 2024-11-27 | Approved with Comments | 2024-12-17 | YES | Resubmitted |  | 131242-WSW41-VI-0010 | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-08 | 33 | AWC | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4403 | 000777 | 01 | Qili | Process | NA | 131242 | WSW41 | VI | M | 0010 | 1 | 131242-WSW41-VI-M-0010-1 | 2025-01-11 | Preliminary Design and Vendor Approval for Spray Nozzles | Rev 1: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-01-30 | 2025-02-12 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0010 | NA | "Preliminary Design and Vendor Approval for Spray Nozzles " && "Vendor Approval of Steel Structure Painter and Fireproofing Painter – Brandschutz Fire Technology Pte. Ltd." && "Vendor Approval of Surge Diverter " && "Vendor Approval of site infrastructure contractor – Seong Construction Pte. Ltd." | 2023-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-01-25 | 32 | AWC | 2025-02-03 | 0 | 000072&&000671&&000777&&001015 | 2023-08-15, 2024-08-23, 2024-10-04, 2024-10-25, 2025-01-11, 2025-02-03 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4404 | 000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1024 | A | 131242-WST02-DR-M-1024-A | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-09 | 183 | AWC | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | AWC | AWC
4405 | 000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 1025 | A | 131242-WST02-DR-M-1025-A | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-09 | 183 | AWC | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | AWC | AWC
4406 | 000778 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 2000 | A | 131242-WST02-DR-M-2000-A | 2024-10-26 | SSN Piping Support Plan Layout (Cast-In Supports) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-25 | 2025-04-27 | Approved with Comments | 2025-05-15 | NO | Overdue |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-09 | 183 | AWC | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | AWC | AWC
4407 | 000779 | 00 | Charisse | Piping/ BS | NA | 131242 | WST02 | DR | M | 0001 | A | 131242-WST02-DR-M-0001-A | 2024-10-26 | SSN Piping Drawing Index | Rev 0: For Information | 2024-11-25 | 2024-11-27 | For Information |  | YES | NA |  | 131242-WST02-DR-0001 | NA | "Drawing Index (Building and Services Mech.)" && "SSN Drawing Index (Cable Tray Layout)" && "SSN Drawing Index (Instrument Layout)" && "SSN Piping Drawing Index" | 2024-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-15 | 32 | INF | 2025-02-21 | A | 000779&&001002&&001063&&001064 | 2024-10-26, 2025-01-26, 2025-02-21 | 00 | 4 | Rejected | REJ |  |  | 0 | INF | INF
4408 | 000780 | 00 | Yuen Fatt | Project | NA | 131242 | WSW41 | VI | S | 0009 | 0 | 131242-WSW41-VI-S-0009-0 | 2024-10-26 | Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-20 | Approved with Comments | 2024-12-10 | NO | Overdue |  | 131242-WSW41-VI-0009 | NA | "Vendor Approval of Steel Structure Painter and Fireproofing Painter – OS Builders Pte. Ltd. " && "Vendor Approval of site office building contractor – Cape Engineering Construction Pte. Ltd." | 2023-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-09 | 25 | AWC | 2024-10-26 | 0 | 000071&&000780 | 2023-08-15, 2024-10-26 | 00 | 2 | Approved with Comments | AWC | 2024-12-10 | Overdue | 0 | AWC | AWC
4409 | 000781 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0002 | 0 | 131242-WST02-VI-A-0002-0 | 2024-10-26 | Vendor Approval of Raised Floor – Hemsco Pte. Ltd. | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-25 | 2024-11-15 | Approved with Comments | 2024-12-05 | NO | Overdue |  | 131242-WST02-VI-0002 | NA | "Preliminary Design and Vendor Approval for Fire Protection System (Pacific Reliance)" && "Vendor Approval for Stainless Steel Pipes & Fittings - Ann Aik" && "Vendor Approval of MV Cable (Jiangsu_Keystone and Polycab)" && "Vendor Approval of MV Cable (Keystone & Polycab)" && "Vendor Approval of Raised Floor – Hemsco Pte. Ltd. " && "Vendor Approval of Raised Floor – Momentum Construction Pte. Ltd. " && "Vendor Approval of SSN Package (ORP Analyser)" && "Vendor Approval of Stainless Steel Pipes and Fittings - Ann Aik" | 2024-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-09 | 20 | AWC | 2025-07-03 | 0 | 000299&&000329&&000781&&001109&&001325&&001428&&001431 | 2024-02-03, 2024-02-28, 2024-03-25, 2024-06-07, 2024-10-16, 2024-10-26, 2025-03-10, 2025-04-18, 2025-05-28, 2025-07-02, 2025-07-03 | 00, 01, 02, 03 | 11 | Approved | APP |  |  | 0 | AWC | AWC
4410 | 000782 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 0 | 131242-WSW41-QA-M-0021-0 | 2024-10-28 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 0: Not approved - Revise and Resubmit | 2024-11-26 | 2024-11-27 | Not Approved | 2024-12-17 | YES | Resubmitted |  | 131242-WSW41-QA-0021 | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-17 | 30 | NAP | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
4411 | 000782 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0021 | 1 | 131242-WSW41-QA-M-0021-1 | 2024-12-14 | FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd) | Rev 1: Approved | 2025-01-03 | 2025-01-20 | Approved |  | YES | NA |  | 131242-WSW41-QA-0021 | NA | "Alternative materials submission for roof waterproofing, Nippon Proof seal 2301(1k polyurethane coating), Unifoam, Geonic 105, BRC 3315, Zota M150 (G-Concept Construction Pte Ltd)" && "FAT report for stainless steel pipes, fittings, flange, plate (Froch enterprise Co. Ltd & Zhejiang Jndia pipeline industry co ltd)" && "Issue for Information-Monthly Concrete Cube Records for Structural Works for October 2024" && "Temperature Monitoring of SSN Water Tank Over All Raft Slab_PUC Thickness: 700mm" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-12-28 | 37 | APP | 2025-04-03 | 0 | 000782&&000825&&000952&&001196 | 2024-10-28, 2024-11-20, 2024-12-14, 2025-01-04, 2025-04-03 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | APP | APP
4412 | 000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0001 | A | 131242-WSD11-DR-M-0001-A | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSD11-DR-0001 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-11 | 47 | INF | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | For Information | INF |  |  | 0 | INF | INF
4413 | 000783 | 00 | Geno | Piping/ BS | NA | 131242 | WSD11 | DR | M | 0002 | A | 131242-WSD11-DR-M-0002-A | 2024-10-28 | THP Drawing Index | Rev 0: For Information | 2024-11-26 | 2024-12-14 | For Information |  | YES | NA |  | 131242-WSD11-DR-0002 | NA | "THP BCA BP Submission" && "THP Drawing Index" && "THP URA Amendment submissions" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-17 | 47 | INF | 2026-01-05 | A | 000783&&001893&&001931 | 2024-10-28, 2025-12-14, 2026-01-05 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
4414 | 000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5150 | A | 131242-WSD11-DR-M-5150-A | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | Approved with Comments | 2024-12-17 | NO | Overdue |  | 131242-WSD11-DR-5150 | NA | "Ring Circulation Pump Drawing" && "THP PC Pump GA Drawings" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-17 | 30 | AWC | 2025-06-12 | B | 000651&&000784 | 2024-10-28, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4415 | 000784 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5160 | A | 131242-WSD11-DR-M-5160-A | 2024-10-28 | Ring Circulation Pump Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-26 | 2024-11-27 | Approved with Comments | 2024-12-17 | NO | Overdue |  | 131242-WSD11-DR-5160 | NA | "Ring Circulation Pump Drawing" && "THP PC Pump GA Drawings" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-17 | 30 | AWC | 2025-06-12 | B | 000651&&000784 | 2024-10-28, 2025-06-12 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4416 | 000785 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0016 | 0 | 131242-WSW41-PS-HS-0016-0 | 2024-10-28 | Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024 | For Information | 2024-11-26 | 2024-11-15 | For Information |  | YES | NA |  | 131242-WSW41-PS-0016 | NA | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" && "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-11 | 18 | INF | 2024-10-31 | 0 | 000740&&000785&&000793 | 2024-10-01, 2024-10-28, 2024-10-31 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
4417 | 000786 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0010 | 0 | 131242-WSW41-RT-C-0010-0 | 2024-10-28 | Report of DFS (GUIDE 3) for PIPE RACKS | Rev.0: Approved with comments. Revise and resubmit. | 2024-11-26 | 2024-12-08 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSW41-RT-0010 | NA | "C4B Monthly Progress Report Number No.10 (02 24)" && "Report of DFS (GUIDE 3) for PIPE RACKS" | 2024-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-11 | 41 | AWC | 2024-10-28 | 0 | 000377&&000786 | 2024-03-18, 2024-10-28 | 00 | 2 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4418 | 000787 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0011 | 0 | 131242-WSW41-RT-C-0011-0 | 2024-10-28 | Report of PROJECT SAFETY REVIEW for PIPE RACKS | For Information | 2024-11-26 | 2024-12-18 | For Information |  | YES | NA |  | 131242-WSW41-RT-0011 | NA | "C4B Monthly Progress Report Number No.11 (03 24)" && "Report of PROJECT SAFETY REVIEW for PIPE RACKS" | 2024-04-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-11 | 51 | INF | 2024-10-28 | 0 | 000437&&000787 | 2024-04-16, 2024-04-18, 2024-06-11, 2024-10-28 | 00, 01, 02 | 4 | For Information | INF | 2025-01-07 | Overdue | 0 | INF | INF
4419 | 000788 | 00 | Theint Theint | Contracts | NA | 131242 | WSW41 | PC | W | 0016 | 0 | 131242-WSW41-PC-W-0016-0 | 2024-10-29 | Payment Claim No.16 | Rev(0): Approved. Please refer to S.O. Correspondence no. 244 dated 1 Nov 2024. | 2024-11-27 | 2024-11-07 | Approved |  | YES | NA |  | 131242-WSW41-PC-0016 | NA | "Payment Claim No.16" | 2024-10-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-18 | 9 | APP | 2024-10-29 | 0 | 000788 | 2024-10-29 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4420 | 000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 9100 | A | 131242-WSD11-DR-M-9100-A | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue | 2nd priority (Shall update and submit under as built drawing) | 131242-WSD11-DR-9100 | NA | "THP Underground Piping and Cast in Details" | 2024-10-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 36 | AWC | 2024-10-30 | A | 000789 | 2024-10-30 | 00 | 1 | Approved with Comments | AWC | 2024-12-25 | Overdue | 0 | AWC | AWC
4421 | 000789 | 00 | Geno | Piping | NA | 131242 | WSD11 | DR | M | 1190 | A | 131242-WSD11-DR-M-1190-A | 2024-10-30 | THP Underground Piping and Cast in Details | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-28 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WSD11-DR-1190 | NA | "THP RIO Panel GA & Wiring drawings (RIO 3,4,5,6)" && "THP Underground Piping and Cast in Details" | 2024-10-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-19 | 36 | AWC | 2025-08-13 | B | 000789&&001382 | 2024-10-30, 2025-06-16, 2025-08-13 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4422 | 000790 | 00 | Max | PMT | NA | 131242 | WSW41 | RT | C | 0012 | 0 | 131242-WSW41-RT-C-0012-0 | 2024-10-30 | Quarterly Safety Review Follow Up on ERSS | For Information | 2024-11-28 | 2024-11-15 | For Information |  | YES | NA |  | 131242-WSW41-RT-0012 | NA | "C4B Monthly Progress Report Number No.12 (04 24)" && "Quarterly Safety Review Follow Up on ERSS" && "Quarterly Safety Review Follow Up on ERSS, SSN Structure, SWPR and THP area " | 2024-04-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-13 | 16 | INF | 2025-07-01 | 1 | 000473&&000790&&001420 | 2024-04-18, 2024-06-11, 2024-10-30, 2025-07-01 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | INF | INF
4423 | 000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0034 | 0 | 131242-WSW41-MI-C-0034-0 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0034 | NA | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | 2024-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-20 | 15 | INF | 2024-10-31 | 0 | 000791 | 2024-10-31 | 00 | 1 | For Information | INF | 2024-12-05 | Overdue | 0 | INF | INF
4424 | 000791 | 00 | Thet Myo | CSA | NA | 131242 | WSW41 | MI | C | 0035 | 0 | 131242-WSW41-MI-C-0035-0 | 2024-10-31 | CSA Meeting Minutes 0034,0035_0310 & 1710 2024 | Rev 0: For information. | 2024-11-28 | 2024-11-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0035 | NA | "CSA Meeting Minutes 0034,0035_0310 & 1710 2024" | 2024-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-20 | 15 | INF | 2024-10-31 | 0 | 000791 | 2024-10-31 | 00 | 1 | For Information | INF | 2024-12-05 | Overdue | 0 | INF | INF
4425 | 000792 | 00 | PCM | PCM | NA | 131242 | WSW41 | MI | PM | 0017 | 0 | 131242-WSW41-MI-PM-0017-0 | 2024-10-31 | Monthly Progress Meeting Minutes 0017_20241023 | Rev. 0 - For Information | 2024-11-28 | 2024-11-07 | For Information |  | YES | NA |  | 131242-WSW41-MI-0017 | NA | "BIM Bi-Weekly Meeting Minutes 0016, 0017 & 0018_20240110, 0124 & 0207" && "CSA Meeting Minutes 0017 & 0018_20231228 20240111" && "Monthly Progress Meeting Minutes 0017_20241023" && "Process & MEICA Meeting Minutes 0017_20240118" | 2024-02-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-14 | 7 | INF | 2024-10-31 | 0 | 000298&&000320&&000339&&000792 | 2024-02-02, 2024-02-22, 2024-03-05, 2024-10-31 | 00 | 4 | For Information | INF | 2024-11-27 | Overdue | 0 | INF | INF
4426 | 000793 | 00 | PCM | PCM | NA | 131242 | WSW41 | PS | PM | 0016 | 0 | 131242-WSW41-PS-PM-0016-0 | 2024-10-31 | Monthly Progress Presentation No. 17 (1024) | For Information | 2024-11-28 | 2024-11-07 | For Information |  | YES | NA |  | 131242-WSW41-PS-0016 | NA | "Monthly Progress Presentation No. 16 (0924)" && "Monthly Progress Presentation No. 17 (1024)" && "Quarterly Risk Management Workshop 5th Quarterly RM Workshop – 23 Oct 2024" | 2024-10-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2024-11-14 | 7 | INF | 2024-10-31 | 0 | 000740&&000785&&000793 | 2024-10-01, 2024-10-28, 2024-10-31 | 00 | 3 | For Information | INF | 2024-11-27 | Overdue | 0 | INF | INF
4427 | 000794 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0001 | 0 | 131242-WST02-VI-A-0001-0 | 2024-10-31 | Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd) | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-11-28 | 2024-11-25 | Approved with Comments | 2024-12-13 | NO | Overdue |  | 131242-WST02-VI-0001 | NA | "Preliminary design and Vendor Approval for SSN Package" && "Preliminary design and Vendor Approval – SSN Package (ICA)" && "Vendor Approval of Door and Louvre Window (Hang Hong Contractor Pte Ltd)" && "Vendor Approval of LV Switchgear, MCC, MDB and LCS (GSM)" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Emergency Eye Wash and Shower, Sanitary Wares c/w fitting accessories, Ductile Iron Pipes c/w fittings – PLUMBING & SANITARY" && "Vendor Approval of Stainless-Steel Pipes, Fittings, Fire Hydrant, Fire Hose reel, Ductile Iron Pipes c/w fittings – FIRE PROTECTION SYSTEM (Snow)" | 2023-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-14 | 25 | AWC | 2026-02-05 | 2 | 000088&&000237&&000241&&000794&&001113&&001154 | 2023-09-05, 2023-10-05, 2023-10-31, 2023-12-12, 2023-12-14, 2024-02-03, 2024-05-02, 2024-10-31, 2025-03-10, 2025-03-24, 2025-06-04, 2025-08-12, 2026-02-05 | 00, 01, 02, 03 | 14 | Approved | APP |  |  | 0 | AWC | AWC
4428 | 000795 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | M | 0022 | 0 | 131242-WSW41-QA-M-0022-0 | 2024-11-01 | FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver) | Rev 0: Approved | 2024-11-29 | 2024-12-05 | Approved |  | YES | NA |  | 131242-WSW41-QA-0022 | NA | "FAT Report for Compressed Air System (Air Compressor, Air Dryer, Air Receiver)" && "Inspection Test Plan for Protective Linings for Concrete (Tank Internal) (Linabond)" && "Inspection and test plan for Cable Laying, Installation, Testing and Termination (Cyclect Electrical engineering pte Ltd)" | 2024-11-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-21 | 34 | APP | 2025-02-18 | 0 | 000795&&000982&&001055 | 2024-11-01, 2025-01-16, 2025-02-18 | 00 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
4429 | 000796 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0023 | 0 | 131242-WSW41-VI-E-0023-0 | 2024-11-02 | Vendor Approval of EICA Material and Accessories (Cable Gland) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments | 2024-11-29 | 2024-11-24 | Approved with Comments | 2024-12-12 | NO | Overdue |  | 131242-WSW41-VI-0023 | NA | "Vendor Approval of EICA Material and Accessories (Cable Gland)" | 2024-11-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 22 | AWC | 2024-11-02 | 0 | 000796 | 2024-11-02 | 00 | 1 | Approved with Comments | AWC | 2024-12-12 | Overdue | 0 | AWC | AWC
4430 | 000797 | 00 | Karthikeyan | EICA | NA | 131242 | WSW41 | VI | E | 0022 | 0 | 131242-WSW41-VI-E-0022-0 | 2024-11-02 | Preliminary Design and Vendor Approval of Unistrut Support | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2024-11-29 | 2024-11-24 | Approved with Comments | 2024-12-12 | NO | Overdue |  | 131242-WSW41-VI-0022 | NA | "Preliminary Design and Vendor Approval of Unistrut Support" | 2024-11-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-22 | 22 | AWC | 2024-11-02 | 0 | 000797 | 2024-11-02 | 00 | 1 | Approved with Comments | AWC | 2024-12-12 | Overdue | 0 | AWC | AWC
4431 | 000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | A | 131242-WST02-DR-M-5311-A | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | Approved with Comments | 2024-12-26 | YES | Resubmitted | In Progress | 131242-WST02-DR-5311 | NA | "GA Drawing for Centrifugal Pump" && "Hookup Drawing for Pressure Transmitter" | 2024-11-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-24 | 31 | AWC | 2025-09-24 | A | 000798&&001693 | 2024-11-04, 2025-04-17, 2025-09-24 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
4432 | 000798 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5301 | A | 131242-WST02-DR-M-5301-A | 2024-11-04 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2024-12-02 | 2024-12-05 | Approved with Comments | 2024-12-26 | NO | Overdue |  | 131242-WST02-DR-5301 | NA | "GA Drawing for Centrifugal Pump" && "Shop Drawing for Louvre Door and Window" | 2024-11-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-24 | 31 | AWC | 2025-11-12 | 0 | 000798&&001604 | 2024-11-04, 2025-04-17, 2025-11-12 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
4433 | 000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5311 | B | 131242-WST02-DR-M-5311-B | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5311 | NA | "GA Drawing for Centrifugal Pump" && "Hookup Drawing for Pressure Transmitter" | 2024-11-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-01 | 354 | PEN | 2025-09-24 | A | 000798&&001693 | 2024-11-04, 2025-04-17, 2025-09-24 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
4434 | 000798 | 01 | David | Mech | NA | 131242 | WST02 | DR | M | 5301 | B | 131242-WST02-DR-M-5301-B | 2025-04-17 | GA Drawing for Centrifugal Pump | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-05-07 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5301 | NA | "GA Drawing for Centrifugal Pump" && "Shop Drawing for Louvre Door and Window" | 2024-11-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-05-01 | 354 | PEN | 2025-11-12 | 0 | 000798&&001604 | 2024-11-04, 2025-04-17, 2025-11-12 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | PEN | PEN
4435 | 000799 | 00 | Prachi | Process | NA | 131242 | WSW41 | VI | M | 2001 | 0 | 131242-WSW41-VI-M-2001-0 | 2024-11-05 | Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package | Rev 0: Approved | 2024-12-03 | 2024-12-05 | Approved |  | YES | NA |  | 131242-WSW41-VI-2001 | NA | "Preliminary Design and Vendor Approval of Air Release Valves (AVK) - SSN Package" | 2024-11-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2024-11-25 | 30 | APP | 2024-11-05 | 0 | 000799 | 2024-11-05 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
4436 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618 | A | 131242-WSD11-DR-S-2300_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-2300_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4437 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618 | A | 131242-WSD11-DR-S-3300_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-3300_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4438 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 3301_ST618 | A | 131242-WSD11-DR-S-3301_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-3301_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4439 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618 | A | 131242-WSD11-DR-S-5300_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5300_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4440 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618 | A | 131242-WSD11-DR-S-5301_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5301_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4441 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618 | A | 131242-WSD11-DR-S-5302_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5302_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4442 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618 | A | 131242-WSD11-DR-S-5303_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5303_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC
4443 | 000800 | 00 | Zora | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618 | A | 131242-WSD11-DR-S-5304_ST618-A | 2024-11-06 | ST618- THP Train 1 & 2 Conceptual | Rev.0: Approved with comments. Please refer to comment sheet. | 2024-12-04 | 2024-12-07 | Approved with Comments | 2024-12-27 | NO | Overdue |  | 131242-WSD11-DR-5304_ST618 | NA | "ST618- THP Train 1 & 2 Conceptual" | 2024-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2024-11-26 | 31 | AWC | 2024-11-06 | A | 000800 | 2024-11-06 | 00 | 1 | Approved with Comments | AWC | 2024-12-26 | Overdue | 0 | AWC | AWC