9347 | 001477 | 00 | Vincent | PMT | NA | 131242 | WSW41 | LT | PM | 0062 | 0 | 131242-WSW41-LT-PM-0062-0 | 2025-07-15 | Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New Biosolids Building | Rev (0): Rejected. Please refer to S.O. correspondence no. 386 dated 13 Aug 2025. | 2025-08-12 | 2025-08-22 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0062 | NA | "Notice of Delay and Cost of Delivery and Installation of Air Compressor System At New Biosolids Building" | 2025-07-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-04 | 38 | REJ | 2025-07-15 | 0 | 001477 | 2025-07-15 | 00 | 1 | Rejected | REJ | 2025-09-11 | Overdue | 0 | REJ | REJ
9348 | 001478 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0035 | 0 | 131242-WST02-QA-I-0035-0 | 2025-07-16 | Factory Acceptance Test Report for Capacitive Level Switch/Leak Detector | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-QA-0035 | NA | " Factory Acceptance Test Report for Capacitive Level Switch/Leak Detector" | 2025-07-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 147 | AWC | 2025-07-16 | 0 | 001478 | 2025-07-16 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9349 | 001479 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0036 | 0 | 131242-WST02-QA-I-0036-0 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-10-24 | Approved with Comments | 2025-11-13 | NO | Overdue |  | 131242-WST02-QA-0036 | NA | " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && "Inspection Test Plan for Transformer" && "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | 2025-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 100 | AWC | 2025-07-21 | 0 | 001479&&001480&&001492 | 2025-07-16, 2025-07-21 | 00 | 3 | Approved | APP |  |  | 0 | AWC | AWC
9350 | 001480 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0036 | 0 | 131242-WST02-QA-I-0036-0 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN) | Rev 0: Rejected. No resubmission required. | 2025-08-13 | 2025-12-09 | Rejected |  | YES | NA |  | 131242-WST02-QA-0036 | NA | " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && "Inspection Test Plan for Transformer" && "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | 2025-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 146 | REJ | 2025-07-21 | 0 | 001479&&001480&&001492 | 2025-07-16, 2025-07-21 | 00 | 3 | Approved | APP |  |  | 0 | REJ | REJ
9351 | 001481 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0032 | 0 | 131242-WST02-QA-I-0032-0 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-11-05 | Approved with Comments | 2025-11-25 | NO | Overdue |  | 131242-WST02-QA-0032 | NA | "SAT Procedure for LVSG Panels (Sunlight)" && "Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" | 2025-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 112 | AWC | 2026-01-12 | 0 | 001481&&001554&&001949 | 2025-07-16, 2025-08-04, 2026-01-12 | 00 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
9352 | 001482 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5130 | C | 131242-WSD11-SD-S-5130-C | 2025-07-16 | Shop Drawing for Cat Ladder Details ST617 THP-PF-01 _ QPD design drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-13 | 2025-08-12 | Not Approved | 2025-09-01 | NO | Overdue | QPD design drawing | 131242-WSD11-SD-5130 | NA | "Shop Drawing for Cat Ladder Details ST617 THP-PF-01 _ QPD design drawing" | 2025-07-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 27 | NAP | 2025-07-16 | C | 001482 | 2025-07-16 | 00 | 1 | Not Approved | NAP | 2025-09-01 | Overdue | 0 | NAP | NAP
9353 | 001483 | 00 | Aaron | CSA | NA | Mock up Drawing | NA | NA | NA | 9999 | C | Mock up Drawing----- | 2025-07-16 | Aluminum Railing (Mock-up) Drawing | Rev 0: Approved with comments. Please refer comment sheet for resubmission. | 2025-08-13 | 2025-08-14 | Approved with Comments | 2025-09-03 | NO | Overdue |  | Mock up Drawing-NA-NA-9999 | NA | "Aluminum Railing (Mock-up) Drawing" | 2025-07-16 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 29 | AWC | 2025-07-16 | C | 001483 | 2025-07-16 | 00 | 1 | Approved with Comments | AWC | 2025-09-03 | Overdue | 0 | AWC | AWC
9354 | 001484 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0039 | 0 | 131242-WST02-QA-I-0039-0 | 2025-07-16 | Vendor Manufacturing Inspection Test Plan for Pressure Transmitters (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-13 | 2025-10-23 | Approved with Comments | 2025-11-12 | NO | Overdue |  | 131242-WST02-QA-0039 | NA | "Vendor Manufacturing Inspection Test Plan for Pressure Transmitters (SSN)" | 2025-07-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 99 | AWC | 2025-07-16 | 0 | 001484 | 2025-07-16 | 00 | 1 | Approved with Comments | AWC | 2025-11-12 | Overdue | 0 | AWC | AWC
9355 | 001485 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0024 | 0 | 131242-WSW41-PS-HS-0024-0 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for Mar 2025 | NA | 2025-08-14 | 2025-09-11 | Approved |  | YES | NA |  | 131242-WSW41-PS-0024 | NA | "Incentive/ Disincentive Audit Scheme for Mar 2025" | 2025-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-06 | 56 | APP | 2025-07-17 | 0 | 001485 | 2025-07-17 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9356 | 001486 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0025 | 0 | 131242-WSW41-PS-HS-0025-0 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for Apr 2025 | NA | 2025-08-14 | 2025-09-11 | Approved |  | YES | NA |  | 131242-WSW41-PS-0025 | NA | "Incentive/ Disincentive Audit Scheme for Apr 2025" | 2025-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-06 | 56 | APP | 2025-07-17 | 0 | 001486 | 2025-07-17 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9357 | 001487 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0026 | 0 | 131242-WSW41-PS-HS-0026-0 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for May 2025 | NA | 2025-08-14 | 2025-09-11 | Approved |  | YES | NA |  | 131242-WSW41-PS-0026 | NA | "Incentive/ Disincentive Audit Scheme for May 2025" | 2025-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-06 | 56 | APP | 2025-07-17 | 0 | 001487 | 2025-07-17 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9358 | 001488 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0027 | 0 | 131242-WSW41-PS-HS-0027-0 | 2025-07-17 | Incentive/ Disincentive Audit Scheme for Jun 2025 | NA | 2025-08-14 | 2025-09-11 | Approved |  | YES | NA |  | 131242-WSW41-PS-0027 | NA | "Incentive/ Disincentive Audit Scheme for Jun 2025" | 2025-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-06 | 56 | APP | 2025-07-17 | 0 | 001488 | 2025-07-17 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9359 | 001489 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0037 | 0 | 131242-WST02-QA-I-0037-0 | 2025-07-21 | Factory Acceptance Test Report for Auto Sampler | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-18 | 2025-10-24 | Approved with Comments | 2025-11-13 | NO | Overdue |  | 131242-WST02-QA-0037 | NA | "Factory Acceptance Test Report for Auto Sampler" && "Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) " | 2025-07-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-10 | 95 | AWC | 2025-07-21 | 0 | 001489&&001494 | 2025-07-21 | 00 | 2 | Approved with Comments | AWC | 2025-11-13 | Overdue | 0 | AWC | AWC
9360 | 001490 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0038 | 0 | 131242-WST02-QA-I-0038-0 | 2025-07-21 | Factory Acceptance Test Report for TSS Analyser - Optical | NA | 2025-08-18 | 2025-08-26 | Approved with Comments | 2025-09-15 | NO | Overdue |  | 131242-WST02-QA-0038 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" && "Factory Acceptance Test Report for TSS Analyser - Optical" && "Inspection Test Plan for Low Voltage Switchgear" | 2025-01-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-04 | 36 | AWC | 2025-07-22 | 0 | 000958&&001490&&001521 | 2025-01-09, 2025-07-21, 2025-07-22 | 00 | 3 | Approved | APP |  |  | 0 | AWC | AWC
9361 | 001491 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0040 | 0 | 131242-WSW41-QA-I-0040-0 | 2025-07-21 | Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand | Rev 0: Accepted for Information. No resubmission required. | 2025-08-18 | 2025-12-09 | For Information |  | YES | NA |  | 131242-WSW41-QA-0040 | NA | "Inspection Test Plan - Aluminium Handrail & Cat Ladder Fabrication (SanHe - Jiangsu HDmann Electric Group Co., Ltd.) " && "Inspection Test Plan for PVC Cable Support System (XLV & Control Room) - Manufacturer Legrand" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Metallic Knife Gate valves (JASH) " | 2025-01-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-04 | 141 | INF | 2025-08-18 | 1 | 000974&&001454&&001491 | 2025-01-14, 2025-07-09, 2025-07-21, 2025-08-18 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | INF | INF
9362 | 001492 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0036 | 0 | 131242-WST02-QA-E-0036-0 | 2025-07-21 | Inspection Test Plan for Transformer | Approved | 2025-08-18 | 2025-08-01 | Approved |  | YES | NA |  | 131242-WST02-QA-0036 | NA | " Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" && "Inspection Test Plan for Transformer" && "Vendor Manufacturing Inspection Test Plan for Auto Sampler (SSN)" | 2025-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-04 | 11 | APP | 2025-07-21 | 0 | 001479&&001480&&001492 | 2025-07-16, 2025-07-21 | 00 | 3 | Approved | APP |  |  | 0 | APP | APP
9363 | 001493 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0101 | 0 | 131242-WSD11-QA-M-0101-0 | 2025-07-21 | FAT Report for Desuperheater (Cambi) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-08-18 | 2025-11-23 | Approved with Comments |  | YES | NA |  | 131242-WSD11-QA-0101 | NA | "FAT Report for Desuperheater (Cambi)" | 2025-07-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-10 | 125 | AWC | 2025-07-21 | 0 | 001493 | 2025-07-21 | 00 | 1 | Approved with Comments | AWC | 2025-12-11 | Overdue | 0 | AWC | AWC
9364 | 001494 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0037 | 0 | 131242-WST02-QA-E-0037-0 | 2025-07-21 | Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) | Approved | 2025-08-18 | 2025-08-01 | Approved |  | YES | NA |  | 131242-WST02-QA-0037 | NA | "Factory Acceptance Test Report for Auto Sampler" && "Inspection Test Plan for Low Voltage Motor Control Centre (MCCs) " | 2025-07-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-10 | 11 | APP | 2025-07-21 | 0 | 001489&&001494 | 2025-07-21 | 00 | 2 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | APP | APP
9365 | 001495 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0102 | 0 | 131242-WSD11-QA-M-0102-0 | 2025-07-21 | Hydro Test Pack and Golden Weld Joint Procedure for Steam High Pressure Line | NA | 2025-08-18 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSD11-QA-0102 | NA | "Hydro Test Pack and Golden Weld Joint Procedure for Steam High Pressure Line" | 2025-07-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-10 | 49 | AWC | 2025-07-21 | 0 | 001495 | 2025-07-21 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
9366 | 001496 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0014 | 0 | 131242-WST02-DS-I-0014-0 | 2025-07-22 | Datasheet for Conductivity Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-19 | 2025-08-15 | Approved with Comments | 2025-09-04 | NO | Overdue |  | 131242-WST02-DS-0014 | NA | "Datasheet for Conductivity Analyser" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 24 | AWC | 2025-07-22 | 0 | 001496 | 2025-07-22 | 00 | 1 | Approved with Comments | AWC | 2025-09-04 | Overdue | 0 | AWC | AWC
9367 | 001497 | 00 | Liying | Mech | NA | 131242 | WSW41 | VI | M | 1018 | 0 | 131242-WSW41-VI-M-1018-0 | 2025-07-22 | Preliminary design and Vendor Approval - Strainer (Asahi, Agru) | Rev 0: Approved with Comments, no re-submission required. Refer to attached file for comments. | 2025-08-19 | 2025-08-01 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-1018 | NA | "Preliminary design and Vendor Approval - Strainer (Asahi, Agru)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-11 | 10 | AWC | 2025-07-22 | 0 | 001497 | 2025-07-22 | 00 | 1 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
9368 | 001498 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5003 | B | 131242-WST02-SD-S-5003-B | 2025-07-22 | ST617 THP-PF-02 Shop Drawing Submission | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-12-10 | Not Approved | 2025-12-30 | NO | Overdue |  | 131242-WST02-SD-5003 | NA | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 141 | NAP | 2026-02-09 | A.5 | 001498&&001698&&001803 | 2025-07-22, 2025-09-26, 2026-02-09 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9369 | 001499 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | A | 0008 | 0 | 131242-WST02-MS-A-0008-0 | 2025-07-22 | MSRA, SWP for Waterproofing Works (Electrical Building Roof) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-19 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WST02-MS-0008 | NA | "MSRA, SWP for Waterproofing Works (Electrical Building Roof)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 10 | AWC | 2025-07-22 | 0 | 001499 | 2025-07-22 | 00 | 1 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
9370 | 001500 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0010 | 0 | 131242-WSW41-PO-E-0010-0 | 2025-07-22 | Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0010 | NA | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Hyperbolix Mixer (Entec International)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2024-07-08 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-01 | 0 | 000653&&001500&&001509 | 2024-07-08, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9371 | 001500 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0001 | 0 | 131242-WSW41-PO-I-0001-0 | 2025-08-01 | Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser) | For Information | 2025-08-29 | 2025-08-11 | For Information |  | YES | Resubmitted |  | 131242-WSW41-PO-0001 | NA | "Unpriced PO for Building Management System (Willowglen)" && "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Knife Gate Valve (Jash Engineering)" | 2025-07-22 | YES | NO | Submission_Session group inconsistency on Submission_Date; Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-15 | 10 | INF | 2025-08-27 | 0 | 001500&&001512&&001630 | 2025-07-22, 2025-08-01, 2025-08-27 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
9372 | 001501 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0011 | 0 | 131242-WSW41-PO-E-0011-0 | 2025-07-22 | Unpriced PO for Radar Level Transmitter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Disciplin | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0011 | NA | "Unpriced PO for Dosing Pump (ProMinent)" && "Unpriced PO for Pressure Transmitter (Emerson)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-01 | 0 | 000654&&001501&&001510 | 2024-08-15, 2025-07-22, 2025-08-01 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
9373 | 001501 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0002 | 0 | 131242-WSW41-PO-I-0002-0 | 2025-08-22 | Unpriced PO for Radar Level Transmitter (Endress & Hauser) | Accepted for information | 2025-09-11 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0002 | NA | "Unpriced PO for Ball Valve (OVS Engineering)" && "Unpriced PO for Cables (Keystone)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 105 | INF | 2025-08-22 | 0 | 000547&&001501&&001513 | 2024-07-08, 2025-07-22, 2025-08-22 | 00, 01 | 3 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9374 | 001502 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0012 | 0 | 131242-WSW41-PO-E-0012-0 | 2025-07-22 | Unpriced PO for Tuning Fork Level Switch (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0012 | NA | "Unpriced LOA for Structural Steel Works (Sanhe) " && "Unpriced PO for Temperature Transmitter (Endress & Hauser)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-09-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-01 | 1 | 000702&&001502&&001511 | 2024-09-05, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9375 | 001502 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0003 | 0 | 131242-WSW41-PO-I-0003-0 | 2025-08-01 | Unpriced PO for Tuning Fork Level Switch (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0003 | NA | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" && "Unpriced PO for Non-return Check Valve (Breen International)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 000594&&001502&&001514 | 2024-07-29, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9376 | 001503 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0013 | 0 | 131242-WSW41-PO-E-0013-0 | 2025-07-22 | Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0013 | NA | "Unpriced PO for CSEL Pipes (MUSG)" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) " | 2025-02-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-22 | 0 | 001069&&001503&&001611 | 2025-02-24, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9377 | 001503 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0004 | 0 | 131242-WSW41-PO-I-0004-0 | 2025-08-01 | Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0004 | NA | "Unppriced PO for YHW" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for Metallic Butterfly Valve (OVS Engineering)" | 2025-02-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 001038&&001503&&001515 | 2025-02-11, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9378 | 001504 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0014 | 0 | 131242-WSW41-PO-E-0014-0 | 2025-07-22 | Unpriced PO for Capacitive Level Switch (IFM) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0014 | NA | "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for HDPE Pipes (AGRU) " && "Unpriced PO for Thermal Flow Switch (Endress & Hauser) " | 2025-03-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-22 | 0 | 001098&&001504&&001612 | 2025-03-06, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9379 | 001504 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0005 | 0 | 131242-WSW41-PO-I-0005-0 | 2025-08-01 | Unpriced PO for Capacitive Level Switch (IFM) | Rev 0: Accepted for Information. | 2025-08-21 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0005 | NA | "Unpriced PO for Cable Raceway (United-U Li) " && "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" && "Unpriced PO for Sludge Pump (Netzsch) " | 2024-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 126 | INF | 2025-08-01 | 0 | 000548&&001070&&001504&&001516 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9380 | 001505 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0015 | 0 | 131242-WSW41-PO-E-0015-0 | 2025-07-22 | Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0015 | NA | "Unpriced LOA for MEICA installer (Cyclect Engineering)" && "Unpriced PO for Pressure Switch (IFM) " && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | 2025-04-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-22 | 0 | 001211&&001505&&001613 | 2025-04-08, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9381 | 001505 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0006 | 0 | 131242-WSW41-PO-I-0006-0 | 2025-08-01 | Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0006 | NA | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" && "Unpriced PO for cPVC Pipes (George Fischer)" | 2024-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 000549&&001071&&001505&&001517 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9382 | 001506 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0016 | 0 | 131242-WSW41-PO-E-0016-0 | 2025-07-22 | Unpriced PO for Pressure Gauge (Baumer) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0016 | NA | "Unpriced LOA for Fire Protection System" && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Rotameter (Krohne) " | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-08-22 | 0 | 001214&&001506&&001614 | 2025-04-09, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9383 | 001506 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0007 | 0 | 131242-WSW41-PO-I-0007-0 | 2025-08-01 | Unpriced PO for Pressure Gauge (Baumer) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0007 | NA | "Unpriced PO for Cable Support System (Jiangsu HDMann) " && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Stainless Steel Pipe (Shanghai Lauchen)" | 2024-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 000595&&001115&&001506 | 2024-07-30, 2025-03-11, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9384 | 001507 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0017 | 0 | 131242-WSW41-PO-E-0017-0 | 2025-07-22 | Unpriced PO for Conductive Level Switch (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0017 | NA | "Unpriced LOA for Electric Hoist (Helmsion Engineering) " && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " && "Unpriced PO for Raised Floor (Momentum Construction)" | 2025-05-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-05 | 9 | REJ | 2025-09-09 | 0 | 001287&&001507&&001663 | 2025-05-13, 2025-07-22, 2025-09-09 | 00 | 3 | For Information | INF |  |  | 0 | REJ | REJ
9385 | 001507 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0008 | 0 | 131242-WSW41-PO-I-0008-0 | 2025-08-01 | Unpriced PO for Conductive Level Switch (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0008 | NA | "Unpriced PO for Cable Raceway (Jiangsu HDMann)" && "Unpriced PO for Centrifugal Pump (KSB)" && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 000608&&001163&&001507 | 2024-08-01, 2025-03-25, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9386 | 001508 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0018_Superceded | 0 | 131242-WSW41-PO-E-0018_Superceded-0 | 2025-07-22 | Unpriced PO for Pressure Transmitter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0018_Superceded | NA | "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2025-07-22 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 9 | REJ | 2025-07-22 | 0 | 001508 | 2025-07-22 | 00 | 1 | Rejected | REJ | 2025-08-20 | Overdue | 0 | REJ | REJ
9387 | 001508 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0009 | 0 | 131242-WSW41-PO-I-0009-0 | 2025-08-01 | Unpriced PO for Pressure Transmitter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0009 | NA | "Unpriced PO for Accessories for Lighting Protection (SkyPRO)" && "Unpriced PO for FRP Tank (Jizhou Zhongyi)" && "Unpriced PO for Pressure Transmitter (Endress & Hauser) " | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 000609&&001286&&001508 | 2024-08-01, 2025-05-13, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9388 | 001509 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0019 | 0 | 131242-WSW41-PO-E-0019-0 | 2025-07-22 | Unpriced PO for Pressure Transmitter (Emerson) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0019 | NA | "Unpriced PO for Control Panels (Fox Singapore)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 9 | REJ | 2025-09-09 | 0 | 001509&&001665 | 2025-07-22, 2025-09-09 | 00 | 2 | For Information | INF |  |  | 0 | REJ | REJ
9389 | 001509 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0010 | 0 | 131242-WSW41-PO-I-0010-0 | 2025-08-01 | Unpriced PO for Pressure Transmitter (Emerson) | For Information | 2025-08-21 | 2025-08-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0010 | NA | "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Hyperbolix Mixer (Entec International)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2024-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 10 | INF | 2025-08-01 | 0 | 000653&&001500&&001509 | 2024-07-08, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-29 | Overdue | 0 | INF | INF
9390 | 001510 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0020 | 0 | 131242-WSW41-PO-E-0020-0 | 2025-07-22 | Unpriced PO for Pressure Transmitter (Emerson) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0020 | NA | "Unpriced PO for PMS Panel (Vector Infotech)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 9 | REJ | 2025-09-09 | 0 | 001510&&001666 | 2025-07-22, 2025-09-09 | 00 | 2 | For Information | INF |  |  | 0 | REJ | REJ
9391 | 001510 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0011 | 0 | 131242-WSW41-PO-I-0011-0 | 2025-08-01 | Unpriced PO for Pressure Transmitter (Emerson) | Rev 1: Not Approved. Wrong PO reference. To revise and resubmit. | 2025-08-21 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WSW41-PO-0011 | NA | "Unpriced PO for Dosing Pump (ProMinent)" && "Unpriced PO for Pressure Transmitter (Emerson)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-15 | 136 | NAP | 2025-08-01 | 0 | 000654&&001501&&001510 | 2024-08-15, 2025-07-22, 2025-08-01 | 00, 01 | 3 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
9392 | 001511 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | E | 0021 | 0 | 131242-WSW41-PO-E-0021-0 | 2025-07-22 | Unpriced PO for Temperature Transmitter (Endress & Hauser) | Rev 0: Rejected. To resubmit under correct Discipline | 2025-08-19 | 2025-07-31 | Rejected | 2025-08-20 | YES | Resubmitted |  | 131242-WSW41-PO-0021 | NA | "Unpriced PO for PDB & LCP (GSM) " && "Unpriced PO for Temperature Transmitter (Endress & Hauser)" | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 9 | REJ | 2025-09-30 | 0 | 001511&&001709 | 2025-07-22, 2025-09-30 | 00 | 2 | For Information | INF |  |  | 0 | REJ | REJ
9393 | 001511 | 01 | Caeden | Contracts | NA | 131242 | WSW41 | PO | I | 0012 | 1 | 131242-WSW41-PO-I-0012-1 | 2025-08-01 | Unpriced PO for Temperature Transmitter (Endress & Hauser) | For Information | 2025-08-21 | 2025-08-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0012 | NA | "Unpriced LOA for Structural Steel Works (Sanhe) " && "Unpriced PO for Temperature Transmitter (Endress & Hauser)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-09-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-15 | 4 | INF | 2025-08-01 | 1 | 000702&&001502&&001511 | 2024-09-05, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF | 2025-08-25 | Overdue | 0 | INF | INF
9394 | 001512 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0001 | 0 | 131242-WSW41-PO-M-0001-0 | 2025-07-22 | Unpriced PO for Knife Gate Valve (Jash Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0001 | NA | "Unpriced PO for Building Management System (Willowglen)" && "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Knife Gate Valve (Jash Engineering)" | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-11 | 125 | INF | 2025-08-27 | 0 | 001500&&001512&&001630 | 2025-07-22, 2025-08-01, 2025-08-27 | 00 | 3 | For Information | INF |  |  | 0 | INF | INF
9395 | 001513 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0002 | 0 | 131242-WSW41-PO-M-0002-0 | 2025-07-22 | Unpriced PO for Ball Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-04 | For Information |  | YES | NA |  | 131242-WSW41-PO-0002 | NA | "Unpriced PO for Ball Valve (OVS Engineering)" && "Unpriced PO for Cables (Keystone)" && "Unpriced PO for Radar Level Transmitter (Endress & Hauser)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 105 | INF | 2025-08-22 | 0 | 000547&&001501&&001513 | 2024-07-08, 2025-07-22, 2025-08-22 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
9396 | 001514 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0003 | 0 | 131242-WSW41-PO-M-0003-0 | 2025-07-22 | Unpriced PO for Non-return Check Valve (Breen International) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0003 | NA | "Unpriced PO for LV Switch Gear, MDB & MCC Panel (Sunlight)" && "Unpriced PO for Non-return Check Valve (Breen International)" && "Unpriced PO for Tuning Fork Level Switch (Endress & Hauser)" | 2024-07-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 125 | INF | 2025-08-01 | 0 | 000594&&001502&&001514 | 2024-07-29, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
9397 | 001515 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0004 | 0 | 131242-WSW41-PO-M-0004-0 | 2025-07-22 | Unpriced PO for Metallic Butterfly Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0004 | NA | "Unppriced PO for YHW" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for Metallic Butterfly Valve (OVS Engineering)" | 2025-02-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 125 | INF | 2025-08-01 | 0 | 001038&&001503&&001515 | 2025-02-11, 2025-07-22, 2025-08-01 | 00, 01 | 3 | For Information | INF |  |  | 0 | INF | INF
9398 | 001516 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0005 | 0 | 131242-WSW41-PO-M-0005-0 | 2025-07-22 | Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0005 | NA | "Unpriced PO for Cable Raceway (United-U Li) " && "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for SCF RFP Wastewater Combination Air Valve (AVK Singapore)" && "Unpriced PO for Sludge Pump (Netzsch) " | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 125 | INF | 2025-08-01 | 0 | 000548&&001070&&001504&&001516 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
9399 | 001517 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0006 | 0 | 131242-WSW41-PO-M-0006-0 | 2025-07-22 | Unpriced PO for SS Auto Ball Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0006 | NA | "Unpriced PO for Cable Raceway (Jebsen & Jessen)" && "Unpriced PO for SS Auto Ball Valve (OVS Engineering)" && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" && "Unpriced PO for cPVC Pipes (George Fischer)" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 125 | INF | 2025-08-01 | 0 | 000549&&001071&&001505&&001517 | 2024-07-08, 2025-02-24, 2025-07-22, 2025-08-01 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
9400 | 001518 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | M | 0025 | 0 | 131242-WSW41-PO-M-0025-0 | 2025-07-22 | Unpriced PO for Manual Ball Valve (OVS Engineering) | Rev 0: For Information Only. | 2025-08-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0025 | NA | "Unpriced PO for Manual Ball Valve (OVS Engineering) " | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-11 | 125 | INF | 2025-07-22 | 0 | 001518 | 2025-07-22 | 00 | 1 | For Information | INF | 2025-12-12 | Overdue | 0 | INF | INF
9401 | 001519 | 00 | Liying | Mech | NA | 131242 | WSW41 | SH | M | 1005 | 0 | 131242-WSW41-SH-M-1005-0 | 2025-07-22 | Piping Valve List & Datasheet – Plastic Valve (GF) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-19 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WSW41-SH-1005 | NA | "Piping Valve List & Datasheet – Plastic Valve (GF)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 44 | AWC | 2025-07-22 | 0 | 001519 | 2025-07-22 | 00 | 1 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
9402 | 001520 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0041 | 0 | 131242-WST02-QA-I-0041-0 | 2025-07-22 | Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-19 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WST02-QA-0041 | NA | "Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi)" && "Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN)" | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-11 | 140 | AWC | 2025-08-05 | 0 | 001520&&001561 | 2025-07-22, 2025-08-05 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
9403 | 001521 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0038 | 0 | 131242-WST02-QA-E-0038-0 | 2025-07-22 | Inspection Test Plan for Low Voltage Switchgear | Rev 0: Approved | 2025-08-19 | 2025-08-01 | Approved |  | YES | NA |  | 131242-WST02-QA-0038 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-1st Batch)" && "Factory Acceptance Test Report for TSS Analyser - Optical" && "Inspection Test Plan for Low Voltage Switchgear" | 2025-01-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-05 | 10 | APP | 2025-07-22 | 0 | 000958&&001490&&001521 | 2025-01-09, 2025-07-21, 2025-07-22 | 00 | 3 | Approved | APP |  |  | 0 | APP | APP
9404 | 001522 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0095 | 0 | 131242-WSW41-QA-M-0095-0 | 2025-07-23 | Inspection Test Plan for CSEL Pipe Installation | NA | 2025-08-20 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSW41-QA-0095 | NA | "Inspection Test Plan for CSEL Pipe Installation" | 2025-07-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 47 | AWC | 2025-07-23 | 0 | 001522 | 2025-07-23 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
9405 | 001523 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1401 | 0 | 131242-WST02-DS-E-1401-0 | 2025-07-23 | Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118 | Rev 0: Approved with comments. To revise and resubmit. | 2025-08-20 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WST02-DS-1401 | NA | "Sample Board Submission for SS Cable Cleats ,Single, Cleats, Cable Range 94-118" && "Sample board Submission for PA Conduit ,Saddle,Junction box" | 2025-07-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-06 | 9 | AWC | 2025-07-23 | 0 | 001426&&001523 | 2025-07-02, 2025-07-23 | 00 | 2 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
9406 | 001524 | 00 | Htet Nu | Project | NA | 131242 | WST02 | RT | S | 0005 | 0 | 131242-WST02-RT-S-0005-0 | 2025-07-24 | DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-21 | 2025-08-01 | Not Approved | 2025-08-21 | NO | Overdue |  | 131242-WST02-RT-0005 | NA | "DFS Guide 3 for SSN Steel Structure and MEICA Equipment Installation" && "Report of Project Safety Review for Substructure & Superstructure work at SSN & THP area " && "Test Report for PDA Test 700mm Dia Bored Pile TP12,TP38,TP68 &TP94 (ST 616)" | 2024-07-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 8 | NAP | 2025-07-24 | 0 | 000540&&000568&&001524 | 2024-07-02, 2024-07-15, 2025-07-24 | 00 | 3 | Not Approved | NAP | 2025-08-21 | Overdue | 0 | NAP | NAP
9407 | 001525 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1153 | A | 131242-WST02-DR-S-1153-A | 2025-07-24 | SSN Electrical building L2, Column C2A PE Endorsement | For Information | 2025-08-21 | 2025-08-12 | For Information |  | YES | NA |  | 131242-WST02-DR-1153 | NA | "SSN Electrical building L2, Column C2A PE Endorsement" && "SSN RIO 0201 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-07 | 19 | INF | 2025-07-29 | C | 001147&&001525 | 2025-03-21, 2025-07-24, 2025-07-29 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | INF | INF
9408 | 001526 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7000 | A | 131242-WSD11-DR-BE-7000-A | 2025-07-24 | THP 1&2 Building Services DB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-21 | 2025-09-15 | Approved with Comments | 2025-10-03 | NO | Overdue |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 53 | AWC | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | AWC | AWC
9409 | 001526 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7002 | A | 131242-WSD11-DR-BE-7002-A | 2025-07-24 | THP 1&2 Building Services DB SLD | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-08-21 | 2025-09-15 | Approved with Comments | 2025-10-03 | NO | Overdue |  | 131242-WSD11-DR-7002 | NA | "THP 1&2 Building Services DB SLD" && "THP MCC Schematic Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2024-03-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 53 | AWC | 2025-10-23 | E | 000143&&000570&&000571&&001526 | 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-07-24, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 9 | Approved | APP |  |  | 0 | AWC | AWC
9410 | 001527 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0025 | 0 | 131242-WST02-QA-A-0025-0 | 2025-07-24 | Material Submission – ARDEX 320 – Liquid Concrete Hardener and Dustproofer (Raised Floor Installations, Momentum Construction) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-21 | 2025-08-01 | Approved with Comments | 2025-08-21 | NO | Overdue |  | 131242-WST02-QA-0025 | NA | "Material Submission – ARDEX 320 – Liquid Concrete Hardener and Dustproofer (Raised Floor Installations, Momentum Construction)" | 2025-07-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 8 | AWC | 2025-07-24 | 0 | 001527 | 2025-07-24 | 00 | 1 | Approved with Comments | AWC | 2025-08-21 | Overdue | 0 | AWC | AWC
9411 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8601 | A | 131242-WST02-DR-S-8601-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-8601 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 62 | NAP | 2026-02-09 | A.6 | 001528 | 2025-07-24, 2025-11-07, 2026-02-09 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9412 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1004 | A | 131242-WST02-DR-S-1004-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
9413 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1005 | A | 131242-WST02-DR-S-1005-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
9414 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1006 | A | 131242-WST02-DR-S-1006-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | NAP | NAP
9415 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1007 | A | 131242-WST02-DR-S-1007-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9416 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1008 | A | 131242-WST02-DR-S-1008-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9417 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A | 131242-WST02-DR-S-1009-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | NAP | NAP
9418 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010 | A | 131242-WST02-DR-S-1010-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9419 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002 | A | 131242-WST02-DR-S-3002-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9420 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601 | A | 131242-WST02-DR-S-5601-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-5601 | NA | "Data Sheet for Parabolic Screen" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Screen General Arrangement Drawing" | 2024-12-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2025-07-24 | A | 000931&&001051&&001528 | 2024-12-27, 2025-04-01, 2025-05-26, 2025-07-24 | 00, 01 | 4 | Not Approved | NAP | 2025-10-14 | Overdue | 0 | NAP | NAP
9421 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5602 | A | 131242-WST02-DR-S-5602-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-5602 | NA | "GA Drawing for Static Screen - Plinth Opening & Seal plate" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-06-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2025-07-24 | A | 001374&&001528 | 2025-06-16, 2025-07-24 | 00 | 2 | Not Approved | NAP | 2025-10-14 | Overdue | 0 | NAP | NAP
9422 | 001528 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5603 | A | 131242-WST02-DR-S-5603-A | 2025-07-24 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | NA | 2025-08-21 | 2025-09-24 | Not Approved | 2025-10-14 | YES | Resubmitted |  | 131242-WST02-DR-5603 | NA | "Design Calculation and Drawings for Hyperbolic Mixer Anchor" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-03-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 62 | NAP | 2025-07-24 | A | 001153&&001528 | 2025-03-24, 2025-07-24 | 00 | 2 | Not Approved | NAP | 2025-10-14 | Overdue | 0 | NAP | NAP
9423 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1004 | A.5 | 131242-WST02-DR-S-1004-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | AWC | AWC
9424 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1005 | A.5 | 131242-WST02-DR-S-1005-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | AWC | AWC
9425 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1006 | A.5 | 131242-WST02-DR-S-1006-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | AWC | AWC
9426 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1007 | A.5 | 131242-WST02-DR-S-1007-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9427 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1008 | A.5 | 131242-WST02-DR-S-1008-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9428 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A.5 | 131242-WST02-DR-S-1009-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | AWC | AWC
9429 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010 | A.5 | 131242-WST02-DR-S-1010-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9430 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002 | A.5 | 131242-WST02-DR-S-3002-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9431 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3003 | A.5 | 131242-WST02-DR-S-3003-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9432 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3004 | A.5 | 131242-WST02-DR-S-3004-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9433 | 001528 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8601 | A.5 | 131242-WST02-DR-S-8601-A.5 | 2025-11-07 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-27 | 2025-11-24 | Approved with Comments | 2025-12-12 | YES | Resubmitted |  | 131242-WST02-DR-8601 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-21 | 17 | AWC | 2026-02-09 | A.6 | 001528 | 2025-07-24, 2025-11-07, 2026-02-09 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9434 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1004 | A.6 | 131242-WST02-DR-S-1004-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP | 2026-03-27 |  | 0 | PEN | PEN
9435 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1005 | A.6 | 131242-WST02-DR-S-1005-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP | 2026-03-27 |  | 0 | PEN | PEN
9436 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1006 | A.6 | 131242-WST02-DR-S-1006-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP | 2026-03-27 |  | 0 | PEN | PEN
9437 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1007 | A.6 | 131242-WST02-DR-S-1007-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9438 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1008 | A.6 | 131242-WST02-DR-S-1008-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9439 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A.6 | 131242-WST02-DR-S-1009-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP | 2026-03-27 |  | 0 | PEN | PEN
9440 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1010 | A.6 | 131242-WST02-DR-S-1010-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9441 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3002 | A.6 | 131242-WST02-DR-S-3002-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9442 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3003 | A.6 | 131242-WST02-DR-S-3003-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9443 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3004 | A.6 | 131242-WST02-DR-S-3004-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9444 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 3005 | A.6 | 131242-WST02-DR-S-3005-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9445 | 001528 | 02 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8601 | A.6 | 131242-WST02-DR-S-8601-A.6 | 2026-02-09 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-8601 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-07-24 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.6 | 001528 | 2025-07-24, 2025-11-07, 2026-02-09 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
9446 | 001529 | 00 | Aaron | CSA | NA | Fabrication Drawing | NA | NA | NA | 9999 | A.6 | Fabrication Drawing----- | 2025-07-24 | ST603_SWPR01&02 fabrication drawing | R0: Not approved. (Same fabrication drawings with PE endorsement submitted in prolog #1531) Please clarify. | 2025-08-21 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | Fabrication Drawing-NA-NA-9999 | NA | "ST603_SWPR01&02 fabrication drawing" && "ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed)" | 2025-07-24 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 162 | NAP | 2025-07-24 | A.6 | 001529&&001531 | 2025-07-24 | 00 | 2 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
9447 | 001530 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | A | 3017 | A | 131242-WST02-SD-A-3017-A | 2025-07-24 | Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-21 | 2025-08-25 | Not Approved | 2025-09-12 | NO | Overdue |  | 131242-WST02-SD-3017 | NA | "Aluminum Chequered Plate for all Floor Openings and Fire Stop at SSN Electrical Room" && "Waterproofing Shop Drawing Submission " | 2025-06-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-07 | 32 | NAP | 2025-08-27 | C | 001356&&001530 | 2025-06-12, 2025-07-24, 2025-07-30, 2025-08-27 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9448 | 001531 | 00 | Aaron | CSA | NA | Fabrication Drawing | NA | NA | NA | 9999 | A | Fabrication Drawing----- | 2025-07-24 | ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed) | NA | 2025-08-21 | 2025-09-15 | For Information |  | YES | NA |  | Fabrication Drawing-NA-NA-9999 | NA | "ST603_SWPR01&02 fabrication drawing" && "ST621 SWPR 01&02 Fabrication Drawing (PE Endorsed)" | 2025-07-24 | NO | YES | Project_Code pattern mismatch (^[A-Z0-9-]*$); Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID pattern mismatch (^[A-Z0-9-]+$); Document_ID does not start with valid code from project_schema; Department not in department_schema | 2025-08-13 | 53 | INF | 2025-07-24 | A.6 | 001529&&001531 | 2025-07-24 | 00 | 2 | Not Approved | NAP | 2025-10-03 | Overdue | 0 | INF | INF
9449 | 001532 | 00 | Bryan | Project | NA | 131242 | WSW41 | MS | Z | 0002 | 0 | 131242-WSW41-MS-Z-0002-0 | 2025-07-28 | MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works | NA | 2025-08-25 | 2025-09-15 | Approved |  | YES | NA |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-11 | 49 | APP | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP |  |  | 0 | APP | APP
9450 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CL | S | 0002_ST618_BCA | 0 | 131242-WSD11-CL-S-0002_ST618_BCA-0 | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-CL-0002_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-18 | 157 | INF | 2025-07-29 | 0 | 001533 | 2025-07-29 | 00 | 1 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9451 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0302_ST618_BCA | C | 131242-WSD11-DR-S-0302_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-0302_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9452 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1300_ST618_BCA | C | 131242-WSD11-DR-S-1300_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9453 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1301_ST618_BCA | C | 131242-WSD11-DR-S-1301_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1301_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9454 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1302_ST618_BCA | C | 131242-WSD11-DR-S-1302_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1302_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9455 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1303_ST618_BCA | C | 131242-WSD11-DR-S-1303_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1303_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9456 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1304_ST618_BCA | C | 131242-WSD11-DR-S-1304_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1304_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9457 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1305_ST618_BCA | C | 131242-WSD11-DR-S-1305_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1305_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9458 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1306_ST618_BCA | C | 131242-WSD11-DR-S-1306_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-1306_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9459 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2300_ST618_BCA | C | 131242-WSD11-DR-S-2300_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-2300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9460 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3300_ST618_BCA | C | 131242-WSD11-DR-S-3300_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-3300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9461 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5300_ST618_BCA | C | 131242-WSD11-DR-S-5300_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5300_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9462 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5301_ST618_BCA | C | 131242-WSD11-DR-S-5301_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5301_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9463 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5302_ST618_BCA | C | 131242-WSD11-DR-S-5302_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5302_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9464 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5303_ST618_BCA | C | 131242-WSD11-DR-S-5303_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5303_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9465 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5304_ST618_BCA | C | 131242-WSD11-DR-S-5304_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5304_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9466 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5305_ST618_BCA | C | 131242-WSD11-DR-S-5305_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5305_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9467 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5306_ST618_BCA | C | 131242-WSD11-DR-S-5306_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5306_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9468 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5307_ST618_BCA | C | 131242-WSD11-DR-S-5307_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5307_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9469 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5308_ST618_BCA | C | 131242-WSD11-DR-S-5308_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5308_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9470 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5309_ST618_BCA | C | 131242-WSD11-DR-S-5309_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5309_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9471 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5310_ST618_BCA | C | 131242-WSD11-DR-S-5310_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5310_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9472 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5311_ST618_BCA | C | 131242-WSD11-DR-S-5311_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5311_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9473 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5312_ST618_BCA | C | 131242-WSD11-DR-S-5312_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5312_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9474 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5313_ST618_BCA | C | 131242-WSD11-DR-S-5313_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5313_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9475 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5314_ST618_BCA | C | 131242-WSD11-DR-S-5314_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5314_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9476 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5315_ST618_BCA | C | 131242-WSD11-DR-S-5315_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5315_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9477 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5316_ST618_BCA | C | 131242-WSD11-DR-S-5316_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-5316_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" && "ST618 WD Response For THP Train Cambi Structures" | 2025-04-25 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-12 | 157 | INF | 2025-07-29 | C | 001255&&001533 | 2025-04-25, 2025-07-29 | 00 | 2 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9478 | 001533 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 8001_ST618_BCA | C | 131242-WSD11-DR-S-8001_ST618_BCA-C | 2025-07-29 | BCA Approval of ST618 (THP Train_Cambi Structures) | For information | 2025-08-26 | 2026-01-02 | For Information |  | YES | NA |  | 131242-WSD11-DR-8001_ST618_BCA | NA | "BCA Approval of ST618 (THP Train_Cambi Structures)" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-08-18 | 157 | INF | 2025-07-29 | C | 001533 | 2025-07-29 | 00 | 1 | For Information | INF | 2026-01-22 | Overdue | 0 | INF | INF
9479 | 001534 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | E | 0039 | 0 | 131242-WSW41-QA-E-0039-0 | 2025-07-29 | Material Submission for HV Plug and Transformer Termination Kit | Rev 0: Approved with comments. To revise and resubmit. | 2025-08-26 | 2025-09-03 | Approved with Comments | 2025-09-23 | NO | Overdue |  | 131242-WSW41-QA-0039 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Apr 2025" && "Material Submission for HV Plug and Transformer Termination Kit " | 2025-07-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 36 | AWC | 2025-07-29 | 0 | 001429&&001534 | 2025-07-02, 2025-07-29 | 00 | 2 | Approved with Comments | AWC | 2025-09-23 | Overdue | 0 | AWC | AWC
9480 | 001535 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0013 | 0 | 131242-WST02-DS-I-0013-0 | 2025-07-29 | Datasheet for TSS Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-08-15 | Approved with Comments | 2025-09-04 | NO | Overdue |  | 131242-WST02-DS-0013 | NA | "Datasheet for TSS Analyser" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 17 | AWC | 2025-07-29 | 0 | 001535 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-09-04 | Overdue | 0 | AWC | AWC
9481 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1751 | B | 131242-WST02-DR-IP-1751-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1751 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9482 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1752 | B | 131242-WST02-DR-IP-1752-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1752 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9483 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1753 | B | 131242-WST02-DR-IP-1753-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1753 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9484 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1754 | B | 131242-WST02-DR-IP-1754-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1754 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9485 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1755 | B | 131242-WST02-DR-IP-1755-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1755 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9486 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1756 | B | 131242-WST02-DR-IP-1756-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1756 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9487 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1757 | B | 131242-WST02-DR-IP-1757-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1757 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9488 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1758 | B | 131242-WST02-DR-IP-1758-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1758 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9489 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1759 | B | 131242-WST02-DR-IP-1759-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1759 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9490 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1760 | B | 131242-WST02-DR-IP-1760-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1760 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9491 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1761 | B | 131242-WST02-DR-IP-1761-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1761 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9492 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1762 | B | 131242-WST02-DR-IP-1762-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1762 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9493 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1763 | B | 131242-WST02-DR-IP-1763-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1763 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9494 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1764 | B | 131242-WST02-DR-IP-1764-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1764 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9495 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1765 | B | 131242-WST02-DR-IP-1765-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1765 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9496 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1766 | B | 131242-WST02-DR-IP-1766-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1766 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9497 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1767 | B | 131242-WST02-DR-IP-1767-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1767 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9498 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1768 | B | 131242-WST02-DR-IP-1768-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1768 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9499 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1769 | B | 131242-WST02-DR-IP-1769-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1769 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9500 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1770 | B | 131242-WST02-DR-IP-1770-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1770 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9501 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1771 | B | 131242-WST02-DR-IP-1771-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1771 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9502 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1772 | B | 131242-WST02-DR-IP-1772-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1772 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9503 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1773 | B | 131242-WST02-DR-IP-1773-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1773 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9504 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1774 | B | 131242-WST02-DR-IP-1774-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1774 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9505 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1775 | B | 131242-WST02-DR-IP-1775-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1775 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9506 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1776 | B | 131242-WST02-DR-IP-1776-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1776 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9507 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1777 | B | 131242-WST02-DR-IP-1777-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1777 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9508 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1778 | B | 131242-WST02-DR-IP-1778-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1778 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9509 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1779 | B | 131242-WST02-DR-IP-1779-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1779 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9510 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1780 | B | 131242-WST02-DR-IP-1780-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1780 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9511 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1781 | B | 131242-WST02-DR-IP-1781-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1781 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9512 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1782 | B | 131242-WST02-DR-IP-1782-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1782 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9513 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1783 | B | 131242-WST02-DR-IP-1783-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1783 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9514 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1784 | B | 131242-WST02-DR-IP-1784-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1784 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9515 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1785 | B | 131242-WST02-DR-IP-1785-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1785 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9516 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1786 | B | 131242-WST02-DR-IP-1786-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1786 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9517 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1787 | B | 131242-WST02-DR-IP-1787-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1787 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9518 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1788 | B | 131242-WST02-DR-IP-1788-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1788 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9519 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1789 | B | 131242-WST02-DR-IP-1789-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1789 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9520 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1790 | B | 131242-WST02-DR-IP-1790-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1790 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9521 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1791 | B | 131242-WST02-DR-IP-1791-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1791 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9522 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1792 | B | 131242-WST02-DR-IP-1792-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1792 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9523 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1793 | B | 131242-WST02-DR-IP-1793-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1793 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9524 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1794 | B | 131242-WST02-DR-IP-1794-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1794 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9525 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1795 | B | 131242-WST02-DR-IP-1795-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1795 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9526 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1796 | B | 131242-WST02-DR-IP-1796-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1796 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9527 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1797 | B | 131242-WST02-DR-IP-1797-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1797 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9528 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1798 | B | 131242-WST02-DR-IP-1798-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1798 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9529 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1799 | B | 131242-WST02-DR-IP-1799-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1799 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9530 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1800 | B | 131242-WST02-DR-IP-1800-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1800 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9531 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1801 | B | 131242-WST02-DR-IP-1801-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1801 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9532 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1802 | B | 131242-WST02-DR-IP-1802-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1802 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9533 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1803 | B | 131242-WST02-DR-IP-1803-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1803 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9534 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1804 | B | 131242-WST02-DR-IP-1804-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1804 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9535 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1805 | B | 131242-WST02-DR-IP-1805-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1805 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9536 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1806 | B | 131242-WST02-DR-IP-1806-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1806 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9537 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1807 | B | 131242-WST02-DR-IP-1807-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1807 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9538 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1808 | B | 131242-WST02-DR-IP-1808-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1808 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9539 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1809 | B | 131242-WST02-DR-IP-1809-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1809 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9540 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1810 | B | 131242-WST02-DR-IP-1810-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1810 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9541 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1811 | B | 131242-WST02-DR-IP-1811-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1811 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9542 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1812 | B | 131242-WST02-DR-IP-1812-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1812 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9543 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1813 | B | 131242-WST02-DR-IP-1813-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1813 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9544 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1814 | B | 131242-WST02-DR-IP-1814-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1814 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9545 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1815 | B | 131242-WST02-DR-IP-1815-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1815 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9546 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1816 | B | 131242-WST02-DR-IP-1816-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1816 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9547 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1817 | B | 131242-WST02-DR-IP-1817-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1817 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9548 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1818 | B | 131242-WST02-DR-IP-1818-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1818 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9549 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1819 | B | 131242-WST02-DR-IP-1819-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1819 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9550 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1820 | B | 131242-WST02-DR-IP-1820-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1820 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9551 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1821 | B | 131242-WST02-DR-IP-1821-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1821 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9552 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1822 | B | 131242-WST02-DR-IP-1822-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1822 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9553 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1823 | B | 131242-WST02-DR-IP-1823-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1823 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9554 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1824 | B | 131242-WST02-DR-IP-1824-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1824 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9555 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1825 | B | 131242-WST02-DR-IP-1825-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1825 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9556 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1826 | B | 131242-WST02-DR-IP-1826-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1826 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9557 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1827 | B | 131242-WST02-DR-IP-1827-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1827 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9558 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1828 | B | 131242-WST02-DR-IP-1828-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1828 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9559 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1829 | B | 131242-WST02-DR-IP-1829-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1829 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9560 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1830 | B | 131242-WST02-DR-IP-1830-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1830 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9561 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1831 | B | 131242-WST02-DR-IP-1831-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1831 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9562 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1832 | B | 131242-WST02-DR-IP-1832-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1832 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9563 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1833 | B | 131242-WST02-DR-IP-1833-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1833 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9564 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1834 | B | 131242-WST02-DR-IP-1834-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1834 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9565 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1835 | B | 131242-WST02-DR-IP-1835-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1835 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9566 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1836 | B | 131242-WST02-DR-IP-1836-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1836 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9567 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1837 | B | 131242-WST02-DR-IP-1837-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1837 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9568 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1838 | B | 131242-WST02-DR-IP-1838-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1838 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9569 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1839 | B | 131242-WST02-DR-IP-1839-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1839 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9570 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1840 | B | 131242-WST02-DR-IP-1840-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1840 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9571 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1841 | B | 131242-WST02-DR-IP-1841-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1841 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9572 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1842 | B | 131242-WST02-DR-IP-1842-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1842 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9573 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1843 | B | 131242-WST02-DR-IP-1843-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1843 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9574 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1844 | B | 131242-WST02-DR-IP-1844-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1844 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9575 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1845 | B | 131242-WST02-DR-IP-1845-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1845 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9576 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1846 | B | 131242-WST02-DR-IP-1846-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1846 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9577 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1847 | B | 131242-WST02-DR-IP-1847-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1847 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9578 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1848 | B | 131242-WST02-DR-IP-1848-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1848 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9579 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1849 | B | 131242-WST02-DR-IP-1849-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1849 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9580 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1850 | B | 131242-WST02-DR-IP-1850-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1850 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9581 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1851 | B | 131242-WST02-DR-IP-1851-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1851 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9582 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1852 | B | 131242-WST02-DR-IP-1852-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1852 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9583 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1853 | B | 131242-WST02-DR-IP-1853-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1853 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9584 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1854 | B | 131242-WST02-DR-IP-1854-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1854 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9585 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1855 | B | 131242-WST02-DR-IP-1855-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1855 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9586 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1856 | B | 131242-WST02-DR-IP-1856-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1856 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9587 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1857 | B | 131242-WST02-DR-IP-1857-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1857 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9588 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1858 | B | 131242-WST02-DR-IP-1858-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1858 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9589 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1859 | B | 131242-WST02-DR-IP-1859-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1859 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9590 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1860 | B | 131242-WST02-DR-IP-1860-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1860 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9591 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1861 | B | 131242-WST02-DR-IP-1861-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1861 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9592 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1862 | B | 131242-WST02-DR-IP-1862-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1862 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9593 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1863 | B | 131242-WST02-DR-IP-1863-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1863 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9594 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1864 | B | 131242-WST02-DR-IP-1864-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1864 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9595 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1865 | B | 131242-WST02-DR-IP-1865-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1865 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9596 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1866 | B | 131242-WST02-DR-IP-1866-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1866 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9597 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1867 | B | 131242-WST02-DR-IP-1867-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1867 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9598 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1868 | B | 131242-WST02-DR-IP-1868-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1868 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9599 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1869 | B | 131242-WST02-DR-IP-1869-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1869 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9600 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1870 | B | 131242-WST02-DR-IP-1870-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1870 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9601 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1871 | B | 131242-WST02-DR-IP-1871-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1871 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9602 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1872 | B | 131242-WST02-DR-IP-1872-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1872 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9603 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1873 | B | 131242-WST02-DR-IP-1873-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1873 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9604 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1874 | B | 131242-WST02-DR-IP-1874-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1874 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9605 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1875 | B | 131242-WST02-DR-IP-1875-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1875 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9606 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1876 | B | 131242-WST02-DR-IP-1876-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1876 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9607 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1877 | B | 131242-WST02-DR-IP-1877-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1877 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9608 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1878 | B | 131242-WST02-DR-IP-1878-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1878 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9609 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1879 | B | 131242-WST02-DR-IP-1879-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1879 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9610 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1880 | B | 131242-WST02-DR-IP-1880-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1880 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9611 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1881 | B | 131242-WST02-DR-IP-1881-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1881 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9612 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1882 | B | 131242-WST02-DR-IP-1882-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1882 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9613 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1883 | B | 131242-WST02-DR-IP-1883-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1883 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9614 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1884 | B | 131242-WST02-DR-IP-1884-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1884 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9615 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1885 | B | 131242-WST02-DR-IP-1885-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1885 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9616 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1886 | B | 131242-WST02-DR-IP-1886-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1886 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9617 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1887 | B | 131242-WST02-DR-IP-1887-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1887 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9618 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1888 | B | 131242-WST02-DR-IP-1888-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1888 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9619 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1889 | B | 131242-WST02-DR-IP-1889-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1889 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9620 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1890 | B | 131242-WST02-DR-IP-1890-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1890 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9621 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1891 | B | 131242-WST02-DR-IP-1891-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1891 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9622 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1892 | B | 131242-WST02-DR-IP-1892-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1892 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9623 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1893 | B | 131242-WST02-DR-IP-1893-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1893 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9624 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1894 | B | 131242-WST02-DR-IP-1894-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1894 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9625 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1895 | B | 131242-WST02-DR-IP-1895-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1895 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9626 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1896 | B | 131242-WST02-DR-IP-1896-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1896 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9627 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1897 | B | 131242-WST02-DR-IP-1897-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1897 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9628 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1898 | B | 131242-WST02-DR-IP-1898-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1898 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9629 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1899 | B | 131242-WST02-DR-IP-1899-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1899 | NA | "SSN RIO - 0401 GA & Wiring Diagram" | 2025-07-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 107 | AWC | 2025-07-29 | B | 001536 | 2025-07-29 | 00 | 1 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9630 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1900 | B | 131242-WST02-DR-IP-1900-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1900 | NA | "SSN RIO - 0401 GA & Wiring Diagram" && "Waterproofing Concrete Demarcation of SSN Main Water Tank " | 2024-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-07-29 | B | 000647&&001536 | 2024-08-13, 2025-07-29 | 00 | 2 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9631 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1901 | B | 131242-WST02-DR-IP-1901-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1901 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9632 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1902 | B | 131242-WST02-DR-IP-1902-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1902 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9633 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1903 | B | 131242-WST02-DR-IP-1903-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1903 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9634 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1904 | B | 131242-WST02-DR-IP-1904-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1904 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9635 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1905 | B | 131242-WST02-DR-IP-1905-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1905 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9636 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1906 | B | 131242-WST02-DR-IP-1906-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1906 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9637 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1907 | B | 131242-WST02-DR-IP-1907-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1907 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9638 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1908 | B | 131242-WST02-DR-IP-1908-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1908 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9639 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1909 | B | 131242-WST02-DR-IP-1909-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1909 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9640 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1910 | B | 131242-WST02-DR-IP-1910-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1910 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9641 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1911 | B | 131242-WST02-DR-IP-1911-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1911 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9642 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1912 | B | 131242-WST02-DR-IP-1912-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1912 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9643 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1913 | B | 131242-WST02-DR-IP-1913-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1913 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9644 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1914 | B | 131242-WST02-DR-IP-1914-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1914 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9645 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1915 | B | 131242-WST02-DR-IP-1915-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1915 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9646 | 001536 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IP | 1916 | B | 131242-WST02-DR-IP-1916-B | 2025-07-29 | SSN RIO - 0401 GA & Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-26 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DR-1916 | NA | "SSN Panel (FBTB-0101) - GA & Schematic Drawings" && "SSN Panel RIO-204 - GA & Schematic Drawings" && "SSN RIO - 0401 GA & Wiring Diagram" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-12 | 107 | AWC | 2025-11-17 | B | 001177&&001536 | 2025-03-28, 2025-07-10, 2025-07-29, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9647 | 001537 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0013 | 0 | 131242-WST02-QA-BS-0013-0 | 2025-07-30 | Factory Acceptance Test Report for Public Address System | NA | 2025-08-27 | 2025-09-23 | Approved |  | YES | NA |  | 131242-WST02-QA-0013 | NA | "Factory Acceptance Test Report for Public Address System" | 2025-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-19 | 55 | APP | 2025-07-30 | 0 | 001537 | 2025-07-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9648 | 001538 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0042 | 0 | 131242-WST02-QA-I-0042-0 | 2025-07-30 | Factory Acceptance Test Report for Pressure Transmitters (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-10-23 | Approved with Comments | 2025-11-12 | NO | Overdue |  | 131242-WST02-QA-0042 | NA | "Certificate of Proper Installation for LVSG Panels (Sunlight)" && "Factory Acceptance Test Report for Pressure Transmitters (SSN)" | 2025-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 85 | AWC | 2025-08-05 | 0 | 001538&&001562 | 2025-07-30, 2025-08-05 | 00 | 2 | For Information | INF |  |  | 0 | AWC | AWC
9649 | 001539 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0014 | 0 | 131242-WST02-QA-BS-0014-0 | 2025-07-30 | Factory Acceptance Test Report for Clean Gas System Panel | Approved | 2025-08-27 | 2025-10-27 | Approved |  | YES | NA |  | 131242-WST02-QA-0014 | NA | "Factory Acceptance Test Report for Clean Gas System Panel" && "Laboratory Test Report on Soil Samples" | 2024-08-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-13 | 89 | APP | 2025-07-30 | 0 | 000680&&001539 | 2024-08-27, 2025-07-30 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
9650 | 001540 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0043 | 0 | 131242-WST02-QA-I-0043-0 | 2025-07-30 | Factory Acceptance Test Report for PH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WST02-QA-0043 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-2nd Batch)" && "Factory Acceptance Test Report for PH Analyser" | 2025-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-13 | 132 | AWC | 2025-07-30 | 0 | 000978&&001540 | 2025-01-16, 2025-07-30 | 00 | 2 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
9651 | 001541 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0103 | 0 | 131242-WST02-QA-M-0103-0 | 2025-07-30 | FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect-6th Batch) | NA | 2025-08-27 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WST02-QA-0103 | NA | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect-6th Batch) " | 2025-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 40 | AWC | 2025-07-30 | 0 | 001541 | 2025-07-30 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
9652 | 001542 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0044 | 0 | 131242-WST02-QA-I-0044-0 | 2025-07-30 | Factory Acceptance Test Report for Dissolved Oxygen Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-08-27 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WST02-QA-0044 | NA | " Inspection Test Plan for Distribution Panels (MDBs)" && "Factory Acceptance Test Report for Dissolved Oxygen Analyser" | 2025-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 132 | AWC | 2025-08-22 | 0 | 001542&&001607 | 2025-07-30, 2025-08-22 | 00 | 2 | Approved | APP |  |  | 0 | AWC | AWC
9653 | 001543 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 1402 | 0 | 131242-WST02-QA-BS-1402-0 | 2025-07-30 | Sample Board Submission for 50x50 SS316 Trunking | NA | 2025-08-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-1402 | NA | "Sample Board Submission for 50x50 SS316 Trunking" | 2025-07-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-08-19 | 250 | PEN | 2025-07-30 | 0 | 001543 | 2025-07-30 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-09-16 |  | 0 | PEN | PEN
9654 | 001544 | 00 | Bryan | CSA | NA | 131242 | WST02 | MS | C | 0034 | 0 | 131242-WST02-MS-C-0034-0 | 2025-07-30 | MSRA and SWP for SSN Tanks Openings Top Shelter Canvas Cover Installation | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-08-27 | 2025-08-25 | Approved with Comments | 2025-09-12 | NO | Overdue |  | 131242-WST02-MS-0034 | NA | "MSRA and SWP for SSN Tanks Openings Top Shelter Canvas Cover Installation" | 2025-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 26 | AWC | 2025-07-30 | 0 | 001544 | 2025-07-30 | 00 | 1 | Approved with Comments | AWC | 2025-09-12 | Overdue | 0 | AWC | AWC
9655 | 001545 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | IP | 0045 | 0 | 131242-WSW41-QA-IP-0045-0 | 2025-07-31 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSW41-QA-0045 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" && "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | 2025-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-14 | 131 | NAP | 2026-01-15 | 1 | 001019&&001545&&001830 | 2025-02-03, 2025-07-31, 2025-11-07, 2026-01-15 | 00, 01 | 4 | For Information | INF |  |  | 0 | NAP | NAP
9656 | 001545 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | IP | 0045 | 1 | 131242-WSW41-QA-IP-0045-1 | 2026-01-15 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-04 |  | Awaiting S.O.'s response |  | NO | NA |  | 131242-WSW41-QA-0045 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" && "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | 2025-02-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-29 | 81 | PEN | 2026-01-15 | 1 | 001019&&001545&&001830 | 2025-02-03, 2025-07-31, 2025-11-07, 2026-01-15 | 00, 01 | 4 | For Information | INF | 2026-03-04 |  | 0 | PEN | PEN
9657 | 001546 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0063 | 0 | 131242-WSW41-LT-PM-0063-0 | 2025-08-01 | CV of Team Member (QA/QC Manager) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-08-29 | 2026-01-16 | Not Approved | 2026-02-05 | NO | Overdue |  | 131242-WSW41-LT-0063 | NA | "CV of Team Member (QA/QC Manager)" | 2025-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 168 | NAP | 2025-08-01 | 0 | 001546 | 2025-08-01 | 00 | 1 | Not Approved | NAP | 2026-02-05 | Overdue | 0 | NAP | NAP
9658 | 001547 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7001 | A | 131242-WST02-DR-I-7001-A | 2025-08-01 | THP Overall Network Diagrams | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-29 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-15 | 53 | NAP | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9659 | 001547 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7002 | A | 131242-WST02-DR-I-7002-A | 2025-08-01 | THP Overall Network Diagrams | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-29 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-15 | 53 | NAP | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9660 | 001547 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7003 | A | 131242-WST02-DR-I-7003-A | 2025-08-01 | THP Overall Network Diagrams | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-08-29 | 2025-09-23 | Not Approved | 2025-10-13 | YES | Resubmitted |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-15 | 53 | NAP | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9661 | 001547 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7001 | A | 131242-WST02-DR-I-7001-A | 2025-10-28 | THP Overall Network Diagrams | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DR-7001 | NA | " THP Overall Network Diagrams" && "Building Services ACMV" && "Hose Reel (SSN Area)" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Overall Single Line Diagram" && "SSN PFD" | 2023-11-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | AWC | 2025-10-29 | A.4 | 000190&&000201&&000219&&000220&&000225&&000360&&000418&&000492&&000604&&000605&&001305&&001333&&001547 | 2023-11-15, 2023-11-23, 2023-11-30, 2023-12-04, 2024-03-14, 2024-04-04, 2024-06-19, 2024-08-01, 2024-08-29, 2024-09-26, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2024-12-24, 2025-01-21, 2025-02-13, 2025-02-14, 2025-02-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-05-30, 2025-07-14, 2025-07-15, 2025-08-01, 2025-08-25, 2025-10-27, 2025-10-28, 2025-10-29 | 00, 01, 02, 03, 04, 05 | 33 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9662 | 001547 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7002 | B | 131242-WST02-DR-I-7002-B | 2025-10-28 | THP Overall Network Diagrams | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DR-7002 | NA | " THP Overall Network Diagrams" && "Aeration Blower System Architecture Drawing" && "LVSG Schematic Diagram" && "Panel GA & Wiring drawing for BS Systems" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN PFD" && "SSN Single Line Diagram for MOV DB" | 2023-11-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | AWC | 2025-10-28 | B | 000220&&000308&&000360&&000418&&000492&&000604&&000605&&000646&&000661&&001305&&001547 | 2023-11-30, 2024-02-13, 2024-03-14, 2024-04-04, 2024-08-01, 2024-08-13, 2024-08-20, 2024-08-29, 2024-10-21, 2024-10-22, 2024-10-29, 2024-11-21, 2025-01-21, 2025-02-26, 2025-02-27, 2025-04-03, 2025-05-04, 2025-05-18, 2025-06-19, 2025-07-14, 2025-08-01, 2025-10-28 | 00, 01, 02, 03, 04, 05 | 23 | Approved with Comments | AWC | 2025-12-16 | Overdue | 0 | AWC | AWC
9663 | 001547 | 01 | Balaji | EICA | NA | 131242 | WST02 | DR | I | 7003 | B | 131242-WST02-DR-I-7003-B | 2025-10-28 | THP Overall Network Diagrams | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-17 | 2025-11-26 | Approved with Comments | 2025-12-16 | NO | Overdue |  | 131242-WST02-DR-7003 | NA | " THP Overall Network Diagrams" && "Fire Alarm-Gas Suppression" && "LVSG Schematic Diagram" && "SSN Cast-in Schedule & Details" && "SSN Distribution Board Single Line Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Single Line Diagram for MOV DB" | 2023-11-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | AWC | 2025-10-28 | B | 000188&&000220&&000308&&000418&&000492&&000604&&000605&&001547 | 2023-11-15, 2023-11-30, 2024-02-13, 2024-04-04, 2024-07-06, 2024-08-01, 2024-09-28, 2024-10-21, 2024-10-22, 2024-11-21, 2025-01-21, 2025-02-26, 2025-03-27, 2025-04-03, 2025-05-04, 2025-08-01, 2025-09-11, 2025-10-28 | 00, 01, 02, 03 | 18 | Approved with Comments | AWC | 2025-12-16 | Overdue | 0 | AWC | AWC
9664 | 001548 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | SSN | 0 | 131242-WST02-SD-S-SSN-0 | 2025-08-01 | Shop Drawing for ST608 (SH001,002,003, CR001, PR003)_PE Endorsed | For Information. Please refer to comment sheet. | 2025-08-29 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WST02-SD-SSN | NA | "Shop Drawing for ST608 (SH001,002,003, CR001, PR003)_PE Endorsed" | 2025-08-01 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema | 2025-08-21 | 87 | INF | 2025-08-01 | 0 | 001548 | 2025-08-01 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9665 | 001549 | 00 | Mr Low | EICA | NA | 131242 | WST02 | VI | I | 0026 | 0 | 131242-WST02-VI-I-0026-0 | 2025-08-04 | Vendor Approval of Building Management System (BMS) (Willowglen) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-09-01 | 2025-09-11 | Not Approved | 2025-10-01 | YES | Resubmitted |  | 131242-WST02-VI-0026 | NA | "Vendor Approval of Building Management System (BMS) (Willowglen)" | 2025-08-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-24 | 38 | NAP | 2025-12-04 | 2 | 001549 | 2025-08-04, 2025-09-29, 2025-12-04 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9666 | 001549 | 01 | Mr Low | EICA | NA | 131242 | WST02 | VI | I | 0026 | 1 | 131242-WST02-VI-I-0026-1 | 2025-09-29 | Vendor Approval of Building Management System (BMS) (Willowglen) | Rev 1: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-17 | 2025-11-14 | Approved with Comments | 2025-12-04 | YES | Resubmitted |  | 131242-WST02-VI-0026 | NA | "Vendor Approval of Building Management System (BMS) (Willowglen)" | 2025-08-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 46 | AWC | 2025-12-04 | 2 | 001549 | 2025-08-04, 2025-09-29, 2025-12-04 | 00, 01, 02 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9667 | 001549 | 02 | Balaji | EICA | NA | 131242 | WST02 | VI | I | 0026 | 2 | 131242-WST02-VI-I-0026-2 | 2025-12-04 | Vendor Approval of Building Management System (BMS) (Willowglen) | Rev 2: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-24 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WST02-VI-0026 | NA | "Vendor Approval of Building Management System (BMS) (Willowglen)" | 2025-08-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-18 | 67 | AWC | 2025-12-04 | 2 | 001549 | 2025-08-04, 2025-09-29, 2025-12-04 | 00, 01, 02 | 3 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
9668 | 001550 | 00 | Mr Low | EICA | NA | 131242 | WSW41 | VI | I | 0007 | 0 | 131242-WSW41-VI-I-0007-0 | 2025-08-04 | Vendor Approval of PMS Network Interface Panel (Vector InfoTech) | Rev 0: Approved with comments. No resubmission required. Refer attached file for comments. | 2025-09-01 | 2025-08-14 | Approved with Comments |  | YES | NA |  | 131242-WSW41-VI-0007 | NA | "Preliminary Design and Vendor Approval For Chemical Dosing Pumps" && "Vendor Approval of PMS Network Interface Panel (Vector InfoTech)" && "Vendor Approval of Rebar Supplier-BRC ASIA LIMITED" && "Vendor Approval of Scaffolding Contractor (A&B Scaffold Engineering Pte Ltd.) " | 2023-08-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-18 | 10 | AWC | 2025-08-04 | 0 | 000067&&000232&&000576&&001550 | 2023-08-11, 2023-12-08, 2024-07-17, 2024-07-29, 2025-02-28, 2025-08-04 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2025-09-03 | Overdue | 0 | AWC | AWC
9669 | 001551 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0015 | 0 | 131242-WST02-DS-I-0015-0 | 2025-08-04 | Datasheet for Dissolved Oxygen Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-01 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-DS-0015 | NA | "Datasheet for Dissolved Oxygen Analyser " && "SSN Datasheet & Drawing of Lamella Clarifier" && "SSN Datasheet, Calculation & GA Drawing of Lamella Clarifier" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 58 | AWC | 2025-08-04 | 0 | 000408&&001551 | 2024-03-28, 2024-07-05, 2025-08-04 | 00, 01 | 3 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
9670 | 001552 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0018 | 0 | 131242-WST02-DS-I-0018-0 | 2025-08-04 | Datasheet for Pressure Gauge | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments | 2025-09-01 | 2025-11-05 | Approved with Comments | 2025-11-25 | NO | Overdue |  | 131242-WST02-DS-0018 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Pressure Gauge" | 2024-07-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 93 | AWC | 2025-08-22 | 0 | 000553&&001552 | 2024-07-09, 2025-03-06, 2025-08-04, 2025-08-22 | 00, 02, 03 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9671 | 001553 | 00 | Radha | QAQC | NA | 131242 | WSD11 | QA | M | 0105 | 0 | 131242-WSD11-QA-M-0105-0 | 2025-08-04 | FAT Report for SS Pipe in THP-HS Line (Cyclect) | NA | 2025-09-01 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSD11-QA-0105 | NA | "FAT Report for SS Pipe in THP-HS Line (Cyclect)" | 2025-08-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-24 | 35 | APP | 2025-08-04 | 0 | 001553 | 2025-08-04 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9672 | 001554 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0032 | 0 | 131242-WST02-QA-I-0032-0 | 2025-08-04 | SAT Procedure for LVSG Panels (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. | 2025-09-01 | 2025-08-26 | Approved with Comments | 2025-09-15 | NO | Overdue |  | 131242-WST02-QA-0032 | NA | "SAT Procedure for LVSG Panels (Sunlight)" && "Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" | 2025-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-18 | 22 | AWC | 2026-01-12 | 0 | 001481&&001554&&001949 | 2025-07-16, 2025-08-04, 2026-01-12 | 00 | 3 | Not Approved | NAP |  |  | 0 | AWC | AWC
9673 | 001555 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0106 | 0 | 131242-WSD11-QA-M-0106-0 | 2025-08-05 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for G1 Booster Pumps (KSB) | NA | 2025-09-02 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSD11-QA-0106 | NA | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for G1 Booster Pumps (KSB)" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 34 | AWC | 2025-08-05 | 0 | 001555 | 2025-08-05 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
9674 | 001556 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0107 | 0 | 131242-WSD11-QA-M-0107-0 | 2025-08-05 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for G2D Booster Pumps (KSB) | NA | 2025-09-02 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-WSD11-QA-0107 | NA | "Vendor Manufacturing Inspection Test Plan and FAT Procedure for G2D Booster Pumps (KSB)" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 34 | AWC | 2025-08-05 | 0 | 001556 | 2025-08-05 | 00 | 1 | Approved with Comments | AWC | 2025-09-26 | Overdue | 0 | AWC | AWC
9675 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3004 | A_To withdraw | 131242-WST02-DR-BE-3004-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3004 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-09 | A.6 | 000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9676 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | A_To withdraw | 131242-WST02-DR-BE-7010-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9677 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | A_To withdraw | 131242-WST02-DR-BE-3005-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9678 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | A_To withdraw | 131242-WST02-DR-BE-7011-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9679 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | A_To withdraw | 131242-WST02-DR-BE-7012-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7012 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9680 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | A_To withdraw | 131242-WST02-DR-BE-7013-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7013 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9681 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3000 | A_To withdraw | 131242-WST02-DR-BE-3000-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | NAP | NAP
9682 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | A_To withdraw | 131242-WST02-DR-BE-3001-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9683 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3002 | A_To withdraw | 131242-WST02-DR-BE-3002-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9684 | 001557 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3003 | A_To withdraw | 131242-WST02-DR-BE-3003-A_To withdraw | 2025-08-05 | LDB-0001 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3003 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Chemical Dosing Area" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-09 | A.6 | 000192&&000605&&000607&&001165&&001528&&001557 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-05-15, 2025-08-05, 2025-08-22, 2025-11-07, 2026-02-09 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9685 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3010 | A_To withdraw | 131242-WST02-DR-BE-3010-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9686 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3011 | A_To withdraw | 131242-WST02-DR-BE-3011-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9687 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7016 | A_To withdraw | 131242-WST02-DR-BE-7016-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7016 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | NAP | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9688 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7015 | A_To withdraw | 131242-WST02-DR-BE-7015-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7015 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | NAP | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9689 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7017 | A_To withdraw | 131242-WST02-DR-BE-7017-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7017 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | NAP | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9690 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7018 | A_To withdraw | 131242-WST02-DR-BE-7018-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7018 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | NAP | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9691 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3006 | A_To withdraw | 131242-WST02-DR-BE-3006-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9692 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3007 | A_To withdraw | 131242-WST02-DR-BE-3007-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3007 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000605&&000607&&001165&&001558 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9693 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3008 | A_To withdraw | 131242-WST02-DR-BE-3008-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3008 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
9694 | 001558 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3009 | A_To withdraw | 131242-WST02-DR-BE-3009-A_To withdraw | 2025-08-05 | LDB-0002 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3009 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000605&&000866&&001165&&001558 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
9695 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3015 | A_To withdraw | 131242-WST02-DR-BE-3015-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9696 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3017 | A_To withdraw | 131242-WST02-DR-BE-3017-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3017 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9697 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3016 | A_To withdraw | 131242-WST02-DR-BE-3016-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9698 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7020 | A_To withdraw | 131242-WST02-DR-BE-7020-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9699 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3018 | A_To withdraw | 131242-WST02-DR-BE-3018-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3018 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-10-31 | A | 000164&&000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9700 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7021 | A_To withdraw | 131242-WST02-DR-BE-7021-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9701 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7023 | A_To withdraw | 131242-WST02-DR-BE-7023-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9702 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 7022 | A_To withdraw | 131242-WST02-DR-BE-7022-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9703 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3012 | A_To withdraw | 131242-WST02-DR-BE-3012-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3012 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9704 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3013 | A_To withdraw | 131242-WST02-DR-BE-3013-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3013 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9705 | 001559 | 00 | Freedomer | BS | NA | 131242 | WST02 | DR | BE | 3014 | A_To withdraw | 131242-WST02-DR-BE-3014-A_To withdraw | 2025-08-05 | SDB-0003 SLD, Schematic and GA Drawing | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Not Approved | 2025-09-09 | NO | Overdue |  | 131242-WST02-DR-3014 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 15 | NAP | 2025-08-22 | B | 000866&&001165&&001559 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
9706 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3141 | A | 131242-WST02-DR-EP-3141-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-3141 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9707 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3142 | A | 131242-WST02-DR-EP-3142-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-3142 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9708 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3143 | A | 131242-WST02-DR-EP-3143-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-3143 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9709 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7240 | A | 131242-WST02-DR-EP-7240-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-7240 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9710 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7242 | A | 131242-WST02-DR-EP-7242-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-7242 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9711 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7241 | A | 131242-WST02-DR-EP-7241-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-7241 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9712 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7340 | A | 131242-WST02-DR-EP-7340-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-7340 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9713 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7342 | A | 131242-WST02-DR-EP-7342-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-7342 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9714 | 001560 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3140 | A | 131242-WST02-DR-EP-3140-A | 2025-08-05 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-08-20 | Approved with Comments | 2025-09-09 | YES | Resubmitted |  | 131242-WST02-DR-3140 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 15 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9715 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3141 | B | 131242-WST02-DR-EP-3141-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-3141 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9716 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3142 | B | 131242-WST02-DR-EP-3142-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-3142 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9717 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3143 | B | 131242-WST02-DR-EP-3143-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-3143 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9718 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7240 | B | 131242-WST02-DR-EP-7240-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-7240 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9719 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7242 | B | 131242-WST02-DR-EP-7242-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-7242 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9720 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7241 | B | 131242-WST02-DR-EP-7241-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-7241 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9721 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7340 | B | 131242-WST02-DR-EP-7340-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-7340 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9722 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7342 | B | 131242-WST02-DR-EP-7342-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-7342 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9723 | 001560 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3140 | B | 131242-WST02-DR-EP-3140-B | 2025-10-01 | Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2026-02-20 | Approved with Comments | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-3140 | NA | "Active Harmonic Filter B 0101~0501 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 142 | AWC | 2025-10-01 | B | 001560 | 2025-08-05, 2025-10-01 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-12 | Overdue | 0 | AWC | AWC
9724 | 001561 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0041 | 0 | 131242-WST02-QA-E-0041-0 | 2025-08-05 | Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi) | NA | 2025-09-02 | 2025-09-02 | For Information |  | YES | NA |  | 131242-WST02-QA-0041 | NA | "Certificate of Proper Installation for Hermetically Sealed Oil Filled HV/LV Transformers (Hitachi)" && "Vendor Manufacturing Inspection Test Plan for Pressure Switch (SSN)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-19 | 28 | INF | 2025-08-05 | 0 | 001520&&001561 | 2025-07-22, 2025-08-05 | 00 | 2 | For Information | INF | 2025-09-22 | Overdue | 0 | INF | INF
9725 | 001562 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0042 | 0 | 131242-WST02-QA-E-0042-0 | 2025-08-05 | Certificate of Proper Installation for LVSG Panels (Sunlight) | NA | 2025-09-02 | 2025-09-02 | For Information |  | YES | NA |  | 131242-WST02-QA-0042 | NA | "Certificate of Proper Installation for LVSG Panels (Sunlight)" && "Factory Acceptance Test Report for Pressure Transmitters (SSN)" | 2025-07-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-19 | 28 | INF | 2025-08-05 | 0 | 001538&&001562 | 2025-07-30, 2025-08-05 | 00 | 2 | For Information | INF | 2025-09-22 | Overdue | 0 | INF | INF
9726 | 001563 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | E | 0043 | 0 | 131242-WSD11-QA-E-0043-0 | 2025-08-05 | Certificate of Proper Installation for WSD11-MCC-0101A&B (Sunlight) | NA | 2025-09-02 | 2025-09-02 | For Information |  | YES | NA |  | 131242-WSD11-QA-0043 | NA | "Certificate of Proper Installation for WSD11-MCC-0101A&B (Sunlight) " | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-25 | 28 | INF | 2025-08-05 | 0 | 001563 | 2025-08-05 | 00 | 1 | For Information | INF | 2025-09-22 | Overdue | 0 | INF | INF
9727 | 001564 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0015 | 0 | 131242-WST02-QA-BS-0015-0 | 2025-08-05 | Factory Acceptance Test Report for Fire Alarm System | R0: Approved with comments. Revise and resubmit. | 2025-09-02 | 2025-10-22 | Approved with Comments | 2025-11-11 | YES | Resubmitted |  | 131242-WST02-QA-0015 | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-19 | 78 | AWC | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9728 | 001564 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | BS | 0015 | 1 | 131242-WST02-QA-BS-0015-1 | 2025-11-27 | Factory Acceptance Test Report for Fire Alarm System | R0: Approved with comments. Revise and resubmit. | 2025-12-17 |  | Awaiting S.O.'s response |  | NO | NA |  | 131242-WST02-QA-0015 | NA | "FAT report for SS Cable Ladder, Accessories 2nd batch (HDMANN)" && "Factory Acceptance Test Report for Fire Alarm System " && "Sample Board Submission for Roof Waterproofing (G-Concept)" && "Vendor Manufacturing Inspection & Test Plan & FAT Procedure for RIO Panel (Fox)" | 2025-01-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-11 | 130 | PEN | 2025-11-27 | 1 | 000972&&001025&&001338&&001564 | 2025-01-13, 2025-02-07, 2025-06-03, 2025-08-05, 2025-08-21, 2025-11-27 | 00, 01 | 6 | Approved with Comments | AWC | 2026-01-14 |  | 0 | PEN | PEN
9729 | 001565 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0040 | 0 | 131242-WST02-QA-E-0040-0 | 2025-08-05 | SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-02 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-WST02-QA-0040 | NA | "SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi)" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-25 | 57 | AWC | 2026-01-02 | 1 | 001565 | 2025-08-05, 2026-01-02 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9730 | 001565 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0040 | 1 | 131242-WST02-QA-E-0040-1 | 2026-01-02 | SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi) | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-22 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-QA-0040 | NA | "SAT Report for Hermetically Sealed Oil-Filled HV/LV Transformers (Hitachi)" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-16 | 31 | AWC | 2026-01-02 | 1 | 001565 | 2025-08-05, 2026-01-02 | 00, 01 | 2 | Approved with Comments | AWC | 2026-02-20 | Overdue | 0 | AWC | AWC
9731 | 001566 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0064 | 0 | 131242-WSW41-LT-PM-0064-0 | 2025-08-06 | Notice for Extension of Time and Cost for Interface Work at C4A THP Courtyard Reinforced Concrete Ground Slab - (THP Train 1 and Train 2) | Rev (0): Rejected. Please refer to S.O. correspondence no. 400 dated 10 Sep 2025. | 2025-09-03 | 2025-09-23 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0064 | NA | "Notice for Extension of Time and Cost for Interface Work at C4A THP Courtyard Reinforced Concrete Ground Slab - (THP Train 1 and Train 2)" | 2025-08-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-26 | 48 | REJ | 2025-08-06 | 0 | 001566 | 2025-08-06 | 00 | 1 | Rejected | REJ | 2025-10-13 | Overdue | 0 | REJ | REJ
9732 | 001567 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | VI | A | 0008 | 0 | 131242-WST02-VI-A-0008-0 | 2025-08-06 | Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd | R0: Approved with comments. Please refer to comment sheet. | 2025-09-03 | 2025-08-26 | Approved with Comments |  | YES | NA |  | 131242-WST02-VI-0008 | NA | "Vendor Approval of Multi Cable Transit (MCT) (HILTI )" && "Vendor Approval of Painting Vendor – ISO TEAM C&P Pte. Ltd" && "Vendor Approval of SSN Package (TSS Analyser - Optical)" | 2024-04-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-20 | 20 | AWC | 2025-08-06 | 0 | 000436&&000606&&001567 | 2024-04-15, 2024-08-01, 2024-10-28, 2024-11-28, 2025-08-06 | 00, 01 | 5 | Approved with Comments | AWC | 2025-09-15 | Overdue | 0 | AWC | AWC
9733 | 001568 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0026 | 0 | 131242-WST02-QA-A-0026-0 | 2025-08-06 | Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636 | R0: Approved with comments. Please refer to comment sheet. Resubmission is not required | 2025-09-03 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-QA-0026 | NA | " Factory Acceptance Test Report for Conductivity Analyser" && "FAT Procedure for LVSG Panels (Sunlight)" && "Material Submission – HILTI Elastomeric Silicone Sealant CP601s & HILTI Firestop Mortar CP636" | 2025-03-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-20 | 61 | AWC | 2025-08-06 | 0 | 001132&&001466&&001568 | 2025-03-18, 2025-05-23, 2025-07-11, 2025-08-06 | 00, 01 | 4 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9734 | 001569 | 00 | YiHao | Contracts | NA | 131242 | WSW41 | PC | W | 0025 | 0 | 131242-WSW41-PC-W-0025-0 | 2025-08-07 | Payment Claim No.25 | Rev (0): Approved. Please refer to S.O. correspondence no. 381 dated 17 Aug 2025. | 2025-09-04 | 2025-08-22 | Approved |  | YES | NA |  | 131242-WSW41-PC-0025 | NA | "Payment Claim No.25" | 2025-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-27 | 15 | APP | 2025-08-07 | 0 | 001569 | 2025-08-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9735 | 001570 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0108 | 0 | 131242-WSW41-QA-M-0108-0 | 2025-08-07 | FAT Report for Manual Knife Gate Valves - Batch 1 (Jash) | NA | 2025-09-04 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WSW41-QA-0108 | NA | "FAT Report for Manual Knife Gate Valves - Batch 1 (Jash)" | 2025-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-27 | 26 | APP | 2025-08-07 | 0 | 001570 | 2025-08-07 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9736 | 001571 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0109 | 0 | 131242-WSW41-QA-M-0109-0 | 2025-08-07 | Test Report 2.2 for Manual Plastic Valves | NA | 2025-09-04 | 2025-09-08 | Not Approved | 2025-09-26 | NO | Overdue |  | 131242-WSW41-QA-0109 | NA | "FAT Report for CSEL Piping (3rd Batch) " && "Test Report 2.2 for Manual Plastic Valves " | 2025-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 32 | NAP | 2025-08-12 | 0 | 001571&&001579 | 2025-08-07, 2025-08-12 | 00 | 2 | Approved | APP |  |  | 0 | NAP | NAP
9737 | 001572 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200-A | 2025-08-07 | THP Courtyard Sump Design (Updates) | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-04 | 2025-08-25 | Not Approved | 2025-09-12 | YES | Resubmitted |  | 131242-WSD11-DR-5200 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 18 | NAP | 2025-12-14 | A | 000861&&001226&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | NAP | NAP
9738 | 001572 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210-A | 2025-08-07 | THP Courtyard Sump Design (Updates) | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-04 | 2025-08-25 | Not Approved | 2025-09-12 | YES | Resubmitted |  | 131242-WSD11-DR-1210 | NA | "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-21 | 18 | NAP | 2025-12-14 | A | 000861&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | NAP | NAP
9739 | 001572 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200-A | 2025-09-15 | THP Courtyard Sump Design (Updates) | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-24 | Approved with Comments | 2025-10-14 | YES | Resubmitted |  | 131242-WSD11-DR-5200 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-29 | 9 | AWC | 2025-12-14 | A | 000861&&001226&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | AWC | AWC
9740 | 001572 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210-A | 2025-09-15 | THP Courtyard Sump Design (Updates) | Rev 1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-03 | 2025-09-24 | Approved with Comments | 2025-10-14 | YES | Resubmitted |  | 131242-WSD11-DR-1210 | NA | "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-29 | 9 | AWC | 2025-12-14 | A | 000861&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | AWC | AWC
9741 | 001572 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5200 | A | 131242-WSD11-DR-S-5200-A | 2025-12-14 | THP Courtyard Sump Design (Updates) | Rev2: Approved | 2026-01-01 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSD11-DR-5200 | NA | "THP Courtyard - Valve Pit, Sump and Kerb Detail " && "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 25 | APP | 2025-12-14 | A | 000861&&001226&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | APP | APP
9742 | 001572 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1210 | A | 131242-WSD11-DR-S-1210-A | 2025-12-14 | THP Courtyard Sump Design (Updates) | Rev2: Approved | 2026-01-01 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSD11-DR-1210 | NA | "THP Courtyard Sump Design (Updates)" && "THP- Valve Pit, Sump and Kerb Detail" | 2024-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 25 | APP | 2025-12-14 | A | 000861&&001572 | 2024-11-30, 2025-08-07, 2025-09-15, 2025-12-14 | 00, 01, 02 | 4 | Approved | APP |  |  | 0 | APP | APP
9743 | 001573 | 00 | Bryan | EICA | NA | 131242 | WST02 | MS | M | 0009 | 0 | 131242-WST02-MS-M-0009-0 | 2025-08-09 | MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-05 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-MS-0009 | NA | "MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) " && "MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground)" | 2025-08-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-29 | 142 | AWC | 2025-08-13 | 0 | 001573&&001585 | 2025-08-09, 2025-08-13 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9744 | 001574 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 0062 | 0 | 131242-WSW41-CD-IM-0062-0 | 2025-08-11 | VCM Submission for 2025-07 | NA | 2025-09-08 | 2025-08-27 | For Information |  | YES | NA |  | 131242-WSW41-CD-0062 | NA | "VCM Submission for 2025-07" | 2025-08-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-31 | 16 | INF | 2025-08-11 | 0 | 001574 | 2025-08-11 | 00 | 1 | For Information | INF | 2025-09-16 | Overdue | 0 | INF | INF
9745 | 001575 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0065 | 0 | 131242-WSW41-LT-PM-0065-0 | 2025-08-11 | Notice for Extension of Time and Cost for Additional Aluminium Handrails QAQC requirements (NOC REF: C4B-006_AUG_2024) | Rev (0): Received for information. Please refer to S.O. correspondence no. 398 dated 10 Sep 25. | 2025-09-08 | 2025-09-23 | For Information |  | YES | NA |  | 131242-WSW41-LT-0065 | NA | "Notice for Extension of Time and Cost for Additional Aluminium Handrails QAQC requirements (NOC REF: C4B-006_AUG_2024)" | 2025-08-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-08-31 | 43 | INF | 2025-08-11 | 0 | 001575 | 2025-08-11 | 00 | 1 | For Information | INF | 2025-10-13 | Overdue | 0 | INF | INF
9746 | 001576 | 00 | Jun | EICA | NA | 131242 | WSD11 | VI | M | 1018 | 0 | 131242-WSD11-VI-M-1018-0 | 2025-08-12 | Vendor Approval for Insulation Material & Cladding Sheet – STHP & HS | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-09-09 | 2025-11-24 | Approved with Comments |  | YES | NA |  | 131242-WSD11-VI-1018 | NA | "Vendor Approval for Insulation Material & Cladding Sheet – STHP & HS" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-01 | 104 | AWC | 2025-08-12 | 0 | 001576 | 2025-08-12 | 00 | 1 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
9747 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0305_ST621_BCA | A | 131242-WSW41-DR-S-0305_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0305_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9748 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0306_ST621_BCA | A | 131242-WSW41-DR-S-0306_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0306_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9749 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0307_ST621_BCA | A | 131242-WSW41-DR-S-0307_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0307_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9750 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0308_ST621_BCA | A | 131242-WSW41-DR-S-0308_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0308_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9751 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0309_ST621_BCA | A | 131242-WSW41-DR-S-0309_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0309_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9752 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1000_ST621_BCA | A | 131242-WSW41-DR-S-1000_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-1000_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9753 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1001_ST621_BCA | A | 131242-WSW41-DR-S-1001_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-1001_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9754 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1002_ST621_BCA | A | 131242-WSW41-DR-S-1002_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-1002_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9755 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1003_ST621_BCA | A | 131242-WSW41-DR-S-1003_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-1003_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9756 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1004_ST621_BCA | A | 131242-WSW41-DR-S-1004_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-1004_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9757 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2000_ST621_BCA | A | 131242-WSW41-DR-S-2000_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-2000_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9758 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3000_ST621_BCA | A | 131242-WSW41-DR-S-3000_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-3000_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9759 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2001_ST621_BCA | A | 131242-WSW41-DR-S-2001_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-2001_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9760 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5000_ST621_BCA | A | 131242-WSW41-DR-S-5000_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-5000_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9761 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5001_ST621_BCA | A | 131242-WSW41-DR-S-5001_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-5001_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9762 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5003_ST621_BCA | A | 131242-WSW41-DR-S-5003_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-5003_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9763 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5002_ST621_BCA | A | 131242-WSW41-DR-S-5002_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-5002_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9764 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8001_ST621_BCA | A | 131242-WSW41-DR-S-8001_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-8001_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9765 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0300_ST621_BCA | A | 131242-WSW41-DR-S-0300_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0300_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9766 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0301_ST621_BCA | A | 131242-WSW41-DR-S-0301_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0301_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9767 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0303_ST621_BCA | A | 131242-WSW41-DR-S-0303_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0303_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9768 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0302_ST621_BCA | A | 131242-WSW41-DR-S-0302_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0302_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9769 | 001577 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0304_ST621_BCA | A | 131242-WSW41-DR-S-0304_ST621_BCA-A | 2025-08-12 | BCA Approval of ST621 (Site Wide Pipe Rack) | NA | 2025-09-09 | 2025-09-25 | For Information |  | YES | NA |  | 131242-WSW41-DR-0304_ST621_BCA | NA | "BCA Approval of ST621 (Site Wide Pipe Rack)" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-09-01 | 44 | INF | 2025-08-12 | A | 001577 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-10-15 | Overdue | 0 | INF | INF
9770 | 001578 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5761 | 0 | 131242-WST02-DS-M-5761-0 | 2025-08-12 | SSN Aeration Line Automatic Condensate Drain Valve | NA | 2025-09-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5761 | NA | "SSN Aeration Line Automatic Condensate Drain Valve" | 2025-08-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-01 | 237 | PEN | 2025-08-12 | 0 | 001578 | 2025-08-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-09-29 |  | 0 | PEN | PEN
9771 | 001579 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0109 | 0 | 131242-WSW41-QA-M-0109-0 | 2025-08-12 | FAT Report for CSEL Piping (3rd Batch) | NA | 2025-09-09 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0109 | NA | "FAT Report for CSEL Piping (3rd Batch) " && "Test Report 2.2 for Manual Plastic Valves " | 2025-08-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-26 | 27 | APP | 2025-08-12 | 0 | 001571&&001579 | 2025-08-07, 2025-08-12 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
9772 | 001580 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0104 | 0 | 131242-WSD11-QA-M-0104-0 | 2025-08-12 | FAT Report for IA Line from THP to SWPR (SS Spools) | NA | 2025-09-09 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSD11-QA-0104 | NA | "FAT Report for IA Line from THP to SWPR (SS Spools)" | 2025-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-01 | 27 | APP | 2025-08-12 | 0 | 001580 | 2025-08-12 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9773 | 001581 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1403 | 0 | 131242-WST02-DS-E-1403-0 | 2025-08-12 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | Rev 0: Not approved. To revise and resubmit. | 2025-09-09 | 2025-09-26 | Not Approved | 2025-10-16 | YES | Resubmitted |  | 131242-WST02-DS-1403 | NA | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | 2025-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-01 | 45 | NAP | 2025-10-06 | 2 | 001581 | 2025-08-12, 2025-09-30, 2025-10-06 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9774 | 001581 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1403 | 0 | 131242-WST02-DS-E-1403-0 | 2025-09-30 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | Rev 1: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-10-20 | 2025-10-02 | Rejected | 2025-10-22 | YES | Resubmitted |  | 131242-WST02-DS-1403 | NA | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | 2025-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 2 | REJ | 2025-10-06 | 2 | 001581 | 2025-08-12, 2025-09-30, 2025-10-06 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
9775 | 001581 | 02 | Dhanapal | QAQC | NA | 131242 | WST02 | DS | E | 1403 | 2 | 131242-WST02-DS-E-1403-2 | 2025-10-06 | Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch | Rev 2: Not approved - Revise and Resubmit Refer to attached file for comments. | 2025-10-24 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WST02-DS-1403 | NA | "Sample Board Submission for - TEX300s, TEL33,3G Switch, 2G Switch " | 2025-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-20 | 119 | NAP | 2025-10-06 | 2 | 001581 | 2025-08-12, 2025-09-30, 2025-10-06 | 00, 01, 02 | 3 | Not Approved | NAP | 2026-02-20 | Overdue | 0 | NAP | NAP
9776 | 001582 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0049 | 0 | 131242-WSW41-MI-C-0049-0 | 2025-08-12 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | For Information | 2025-09-09 | 2025-08-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0049 | NA | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-01 | 3 | INF | 2025-08-12 | 0 | 001582 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-09-04 | Overdue | 0 | INF | INF
9777 | 001582 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0050 | 0 | 131242-WSW41-MI-C-0050-0 | 2025-08-12 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | For Information | 2025-09-09 | 2025-08-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0050 | NA | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-01 | 3 | INF | 2025-08-12 | 0 | 001582 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-09-04 | Overdue | 0 | INF | INF
9778 | 001582 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0051 | 0 | 131242-WSW41-MI-C-0051-0 | 2025-08-12 | CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025 | For Information | 2025-09-09 | 2025-08-15 | For Information |  | YES | NA |  | 131242-WSW41-MI-0051 | NA | "CSA Meeting Minutes 0049, 0050 & 0051_10062025, 26062025 & 10072025" | 2025-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-01 | 3 | INF | 2025-08-12 | 0 | 001582 | 2025-08-12 | 00 | 1 | For Information | INF | 2025-09-04 | Overdue | 0 | INF | INF
9779 | 001583 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0110 | 0 | 131242-WSW41-QA-M-0110-0 | 2025-08-12 | FAT Report for SWPR Pipe's Guide Supports | NA | 2025-09-09 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0110 | NA | "FAT Report for SWPR Pipe's Guide Supports " | 2025-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-01 | 27 | APP | 2025-08-12 | 0 | 001583 | 2025-08-12 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9780 | 001584 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0066 | 0 | 131242-WSW41-LT-PM-0066-0 | 2025-08-13 | Notice For Extension of Time And Cost For Delay Of Vessel Stratford 138 IMO 9305491 Due To Force Majeure And Fire | Rev (0): Rejected. Please refer to S.O. correspondence no. 408 dated 3 Oct 2025. | 2025-09-10 | 2025-10-15 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0066 | NA | "Notice For Extension of Time And Cost For Delay Of Vessel Stratford 138 IMO 9305491 Due To Force Majeure And Fire" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 63 | REJ | 2025-08-13 | 0 | 001584 | 2025-08-13 | 00 | 1 | Rejected | REJ | 2025-11-04 | Overdue | 0 | REJ | REJ
9781 | 001585 | 00 | Bryan | BS | NA | 131242 | WST02 | MS | M | 0009 | 0 | 131242-WST02-MS-M-0009-0 | 2025-08-13 | MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-10 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WST02-MS-0009 | NA | "MSRA and SWP for Installation of Fire Hydrant, Fire Hose Reel and Plumbing Sanitary Piping Work (Underground & Above Ground) " && "MSRA and SWP for Installation of Fire Hydrant, Potable, sprinkler, and Sanitary Piping Work (Underground & Above ground)" | 2025-08-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 138 | AWC | 2025-08-13 | 0 | 001573&&001585 | 2025-08-09, 2025-08-13 | 00 | 2 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
9782 | 001586 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5200 | E | 131242-WSW41-DR-S-5200-E | 2025-08-13 | SWPR _Platform A and B- Cat ladders | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WSW41-DR-5200 | NA | "SWPR _Platform A and B- Cat ladders" && "THP Courtyard - Valve Pit, Sump and Kerb Detail " | 2025-04-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 62 | NAP | 2025-08-13 | E | 001226&&001586 | 2025-04-14, 2025-08-13 | 00 | 2 | Not Approved | NAP | 2025-11-03 | Overdue | 0 | NAP | NAP
9783 | 001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8600 | A.3 | 131242-WSW41-DR-S-8600-A.3 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSW41-DR-8600 | NA | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-26 | 63 | APP | 2025-11-06 | A.3 | 001586 | 2025-11-06 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
9784 | 001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5604 | A.3 | 131242-WSW41-DR-S-5604-A.3 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSW41-DR-5604 | NA | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-26 | 63 | APP | 2025-11-06 | A.3 | 001586 | 2025-11-06 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
9785 | 001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1011 | A.3 | 131242-WSW41-DR-S-1011-A.3 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSW41-DR-1011 | NA | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-26 | 63 | APP | 2025-11-06 | A.3 | 001586 | 2025-11-06 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
9786 | 001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1010 | A.3 | 131242-WSW41-DR-S-1010-A.3 | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSW41-DR-1010 | NA | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-26 | 63 | APP | 2025-11-06 | A.3 | 001586 | 2025-11-06 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
9787 | 001586 | 01 | Aaron | CSA | NA | 131242 | WSW41 | CL | S | 5200 | B | 131242-WSW41-CL-S-5200-B | 2025-11-06 | SWPR _Platform A and B- Cat ladders | Rev1: Approved | 2025-11-26 | 2026-01-08 | Approved |  | YES | NA |  | 131242-WSW41-CL-5200 | NA | "SWPR _Platform A and B- Cat ladders" | 2025-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-26 | 63 | APP | 2025-11-06 | B | 001586 | 2025-11-06 | 01 | 1 | Approved | APP |  |  | 0 | APP | APP
9788 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 1101 | A.3 | 131242-WSD11-SD-S-1101-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-1101 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9789 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 1102 | A.3 | 131242-WSD11-SD-S-1102-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-1102 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9790 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 1103 | A.3 | 131242-WSD11-SD-S-1103-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-1103 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9791 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 2100 | A.3 | 131242-WSD11-SD-S-2100-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-2100 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9792 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 3100 | A.3 | 131242-WSD11-SD-S-3100-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-3100 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9793 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5100 | A.3 | 131242-WSD11-SD-S-5100-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-5100 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9794 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5101 | A.3 | 131242-WSD11-SD-S-5101-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-5101 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9795 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 5102 | A.3 | 131242-WSD11-SD-S-5102-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-5102 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9796 | 001587 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | 8002 | A.3 | 131242-WSD11-SD-S-8002-A.3 | 2025-08-13 | ST619 THP-PR01 (PE endorsed drawing) | R0: For Information. Please refer to comment sheet. | 2025-09-10 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSD11-SD-8002 | NA | "ST619 THP-PR01 (PE endorsed drawing)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 75 | INF | 2025-08-13 | A.3 | 001587 | 2025-08-13 | 00 | 1 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9797 | 001588 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | SSN_PLINTH REBAR DETAILS | A | 131242-WST02-DR-S-SSN_PLINTH REBAR DETAILS-A | 2025-08-13 | SSN Equipment Loading and Equipment Plinth Layout | Rev 0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-DR-SSN_PLINTH REBAR DETAILS | NA | "SSN Equipment Loading and Equipment Plinth Layout" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 54 | AWC | 2025-08-13 | A | 001588 | 2025-08-13 | 00 | 1 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9798 | 001589 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5600 | A | 131242-WST02-SD-S-5600-A | 2025-08-13 | Shop Drawing for Typical Railing Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-SD-5600 | NA | "Shop Drawing for Typical Railing Details" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 41 | AWC | 2025-08-13 | A | 001589 | 2025-08-13 | 00 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
9799 | 001589 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5601 | A | 131242-WST02-SD-S-5601-A | 2025-08-13 | Shop Drawing for Typical Railing Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-SD-5601 | NA | "Shop Drawing for Typical Railing Details" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 41 | AWC | 2025-08-13 | A | 001589 | 2025-08-13 | 00 | 1 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
9800 | 001589 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5602 | A | 131242-WST02-SD-S-5602-A | 2025-08-13 | Shop Drawing for Typical Railing Details | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-10 | 2025-09-23 | Approved with Comments | 2025-10-13 | NO | Overdue |  | 131242-WST02-SD-5602 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Typical Railing Details" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-27 | 41 | AWC | 2025-08-13 | A | 001458&&001589 | 2025-07-11, 2025-08-13 | 00 | 2 | Approved with Comments | AWC | 2025-10-13 | Overdue | 0 | AWC | AWC
9801 | 001590 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0111 | 0 | 131242-WSW41-QA-M-0111-0 | 2025-08-13 | Material Test Report EN 10204-3.1 for Manual Ball Valves (OVS-Heaton) | NA | 2025-09-10 | 2025-09-08 | Not Approved | 2025-09-26 | NO | Overdue |  | 131242-WSW41-QA-0111 | NA | "Material Test Report EN 10204-3.1 for Manual Ball Valves (OVS-Heaton)" | 2025-08-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 26 | NAP | 2025-08-13 | 0 | 001590 | 2025-08-13 | 00 | 1 | Not Approved | NAP | 2025-09-26 | Overdue | 0 | NAP | NAP
9802 | 001591 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | RT | Z | 0003 | 0 | 131242-WSD11-RT-Z-0003-0 | 2025-08-14 | 80% THP ALMOP Report | NA | 2025-09-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-RT-0003 | NA | "80% THP ALMOP Report" && "Project Safety Review Report for THP Installation" && "THP HAZOP Report" && "THP Short Circuit Study Report" | 2024-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-08-28 | 235 | PEN | 2025-08-14 | 0 | 000678&&000827&&001388&&001591 | 2024-08-26, 2024-10-28, 2024-11-20, 2025-03-25, 2025-06-18, 2025-08-14 | 00, 01 | 6 | Approved | APP |  |  | 0 | PEN | PEN
9803 | 001592 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0046 | 0 | 131242-WST02-QA-I-0046-0 | 2025-08-14 | Factory Acceptance Test Report for Temperature Transmitters | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-QA-0046 | NA | "Factory Acceptance Test Report for Temperature Transmitters" | 2025-08-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-03 | 53 | AWC | 2025-08-14 | 0 | 001592 | 2025-08-14 | 00 | 1 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9804 | 001593 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0047 | 0 | 131242-WST02-QA-I-0047-0 | 2025-08-14 | Factory Acceptance Test Report for Tuning Fork Level Switches | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-11 | 2025-11-05 | Approved with Comments | 2025-11-25 | NO | Overdue |  | 131242-WST02-QA-0047 | NA | "Factory Acceptance Test Report for Tuning Fork Level Switches " && "SAT Report for WST02-MCC-1001A & WST02-MCC-1001B" | 2025-08-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-03 | 83 | AWC | 2025-09-01 | 0 | 001593&&001643 | 2025-08-14, 2025-09-01 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9805 | 001594 | 00 | Htet Nu | PCM | NA | 131242 | WSW41 | RT | PM | 0027 | 0 | 131242-WSW41-RT-PM-0027-0 | 2025-08-15 | C4B Monthly Progress Report Number No.27 (07 25) | NA | 2025-09-12 | 2025-08-30 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0027 | NA | "C4B Monthly Progress Report Number No.27 (07 25)" | 2025-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-04 | 15 | AWC | 2025-08-15 | 0 | 001594 | 2025-08-15 | 00 | 1 | Approved with Comments | AWC | 2025-09-18 | Overdue | 0 | AWC | AWC
9806 | 001595 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0112 | 0 | 131242-WSW41-QA-M-0112-0 | 2025-08-15 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) (3rd Batch) | NA | 2025-09-12 | 2025-09-08 | Approved |  | YES | NA |  | 131242-WSW41-QA-0112 | NA | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) (3rd Batch)" | 2025-08-15 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-04 | 24 | APP | 2025-08-15 | 0 | 001595 | 2025-08-15 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9807 | 001596 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0042 | 0 | 131242-WSW41-QA-C-0042-0 | 2025-08-15 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Jun 2025 | NA | 2025-09-12 | 2025-08-26 | For Information |  | YES | NA |  | 131242-WSW41-QA-0042 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Jun 2025" | 2025-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-04 | 11 | INF | 2025-08-15 | 0 | 001596 | 2025-08-15 | 00 | 1 | For Information | INF | 2025-09-15 | Overdue | 0 | INF | INF
9808 | 001597 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0067 | 0 | 131242-WSW41-LT-PM-0067-0 | 2025-08-15 | Notice for Extension of Time and Cost for Delay Due To Relay Modification of SSN 22KV Incoming Feeder From C3B1 HVSG | Rev (0): Rejected. Please refer to S.O. correspondence no. 409 dated 3 Oct 2025. | 2025-09-12 | 2025-10-15 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0067 | NA | "Notice for Extension of Time and Cost for Delay Due To Relay Modification of SSN 22KV Incoming Feeder From C3B1 HVSG" | 2025-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-04 | 61 | REJ | 2025-08-15 | 0 | 001597 | 2025-08-15 | 00 | 1 | Rejected | REJ | 2025-11-04 | Overdue | 0 | REJ | REJ
9809 | 001598 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0048 | 0 | 131242-WST02-QA-I-0048-0 | 2025-08-17 | Factory Acceptance Test Report for Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-23 | Approved with Comments | 2025-11-12 | NO | Overdue |  | 131242-WST02-QA-0048 | NA | "FAT Report for Air Blowers (Aerzen)" && "Factory Acceptance Test Report for Thermal Flow Switch" | 2025-02-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-08-31 | 67 | AWC | 2025-08-17 | 0 | 001021&&001598 | 2025-02-05, 2025-08-17 | 00 | 2 | Approved with Comments | AWC | 2025-11-12 | Overdue | 0 | AWC | AWC
9810 | 001599 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0049 | 0 | 131242-WST02-QA-I-0049-0 | 2025-08-17 | Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-12 | 2025-10-23 | Approved with Comments | 2025-11-12 | NO | Overdue |  | 131242-WST02-QA-0049 | NA | "FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight)" && "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) " | 2025-08-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-06 | 67 | AWC | 2025-09-10 | 0 | 001599&&001671 | 2025-08-17, 2025-09-10 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9811 | 001600 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0016 | 0 | 131242-WST02-QA-BS-0016-0 | 2025-08-19 | QA/QC Report for Air Conditioning System | Rev0: Not Approved. Resubmission required. | 2025-09-16 | 2025-10-10 | Not Approved | 2025-10-30 | YES | Resubmitted |  | 131242-WST02-QA-0016 | NA | "QA/QC Report for Air Conditioning System" | 2025-08-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 52 | NAP | 2025-10-13 | 1 | 001600 | 2025-08-19, 2025-10-13 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
9812 | 001600 | 01 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0016 | 1 | 131242-WST02-QA-BS-0016-1 | 2025-10-13 | QA/QC Report for Air Conditioning System | Rev0: Not Approved. Resubmission required. | 2025-10-31 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0016 | NA | "QA/QC Report for Air Conditioning System" | 2025-08-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-10-27 | 175 | PEN | 2025-10-13 | 1 | 001600 | 2025-08-19, 2025-10-13 | 00, 01 | 2 | Not Approved | NAP | 2025-11-28 |  | 0 | PEN | PEN
9813 | 001601 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0017 | 0 | 131242-WST02-QA-BS-0017-0 | 2025-08-19 | QA/QC Report for Mechanical Ventilation Fan | Rev0: Not Approved. Resubmission required. | 2025-09-16 | 2025-10-10 | Not Approved | 2025-10-30 | YES | Resubmitted |  | 131242-WST02-QA-0017 | NA | "QA/QC Report for Mechanical Ventilation Fan" && "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | 2025-02-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 52 | NAP | 2025-10-13 | 1 | 001036&&001601 | 2025-02-11, 2025-08-19, 2025-10-13 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9814 | 001601 | 01 | Mohan | QAQC | NA | 131242 | WST02 | QA | BS | 0017 | 1 | 131242-WST02-QA-BS-0017-1 | 2025-10-13 | QA/QC Report for Mechanical Ventilation Fan | Rev0: Not Approved. Resubmission required. | 2025-10-31 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0017 | NA | "QA/QC Report for Mechanical Ventilation Fan" && "Samples Board Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" | 2025-02-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-10-27 | 175 | PEN | 2025-10-13 | 1 | 001036&&001601 | 2025-02-11, 2025-08-19, 2025-10-13 | 00, 01 | 3 | Not Approved | NAP | 2025-11-28 |  | 0 | PEN | PEN
9815 | 001602 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0113 | 0 | 131242-WST02-QA-M-0113-0 | 2025-08-19 | FAT Report for Manual Knife Gate Valves Batch 2 (Jash) | NA | 2025-09-16 | 2025-09-02 | Approved |  | YES | NA |  | 131242-WST02-QA-0113 | NA | "FAT Report for Manual Knife Gate Valves Batch 2 (Jash)" | 2025-08-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-08 | 14 | APP | 2025-08-19 | 0 | 001602 | 2025-08-19 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9816 | 001603 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0002 | 0 | 131242-WST02-QA-S-0002-0 | 2025-08-19 | ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-09-16 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WST02-QA-0002 | NA | "ST614, Batch 1, GL M-V, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission " && "Vendor Manufacturing Inspection and test plan and FAT procedure for Hermetically Sealed Oil-Filled HV/LV Transformers" | 2024-08-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 69 | INF | 2025-08-19 | 0 | 000665&&001603 | 2024-08-21, 2024-10-25, 2025-08-19 | 00, 01 | 3 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9817 | 001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 2008 | A | 131242-WST02-SD-A-2008-A | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | Not Approved | 2025-09-24 | YES | Resubmitted |  | 131242-WST02-SD-2008 | NA | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 16 | NAP | 2025-08-19 | A | 001604 | 2025-08-19 | 00 | 1 | Not Approved | NAP | 2025-09-24 | Overdue | 0 | NAP | NAP
9818 | 001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5300 | A | 131242-WST02-SD-A-5300-A | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | Not Approved | 2025-09-24 | YES | Resubmitted |  | 131242-WST02-SD-5300 | NA | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 16 | NAP | 2025-08-19 | A | 001604 | 2025-08-19 | 00 | 1 | Not Approved | NAP | 2025-09-24 | Overdue | 0 | NAP | NAP
9819 | 001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5301 | A | 131242-WST02-SD-A-5301-A | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | Not Approved | 2025-09-24 | YES | Resubmitted |  | 131242-WST02-SD-5301 | NA | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 16 | NAP | 2025-08-19 | A | 001604 | 2025-08-19 | 00 | 1 | Not Approved | NAP | 2025-09-24 | Overdue | 0 | NAP | NAP
9820 | 001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5302 | A | 131242-WST02-SD-A-5302-A | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | Not Approved | 2025-09-24 | YES | Resubmitted |  | 131242-WST02-SD-5302 | NA | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 16 | NAP | 2025-08-19 | A | 001604 | 2025-08-19 | 00 | 1 | Not Approved | NAP | 2025-09-24 | Overdue | 0 | NAP | NAP
9821 | 001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5303 | A | 131242-WST02-SD-A-5303-A | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | Not Approved | 2025-09-24 | YES | Resubmitted |  | 131242-WST02-SD-5303 | NA | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 16 | NAP | 2025-08-19 | A | 001604 | 2025-08-19 | 00 | 1 | Not Approved | NAP | 2025-09-24 | Overdue | 0 | NAP | NAP
9822 | 001604 | 00 | Yuen Fatt | CSA | NA | 131242 | WST02 | SD | A | 5340 | A | 131242-WST02-SD-A-5340-A | 2025-08-19 | Shop Drawing for Louvre Door and Window | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-16 | 2025-09-04 | Not Approved | 2025-09-24 | YES | Resubmitted |  | 131242-WST02-SD-5340 | NA | "Shop Drawing for Louvre Door and Window" | 2025-08-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 16 | NAP | 2025-08-19 | A | 001604 | 2025-08-19 | 00 | 1 | Not Approved | NAP | 2025-09-24 | Overdue | 0 | NAP | NAP
9823 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 1000 | 0 | 131242-WST02-DR-A-1000-0 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 22 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
9824 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 2000 | 0 | 131242-WST02-DR-A-2000-0 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 22 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | NAP | NAP
9825 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 2008 | 1 | 131242-WST02-DR-A-2008-1 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-2008 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "Shop Drawing for Louvre Door and Window" | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 22 | NAP | 2025-11-17 | B | 001194&&001604 | 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17 | 00, 01, 02 | 4 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9826 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5300 | 1 | 131242-WST02-DR-A-5300-1 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5300 | NA | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 22 | NAP | 2025-11-12 | 1 | 001604 | 2025-11-12 | 01 | 1 | Not Approved | NAP | 2025-12-24 | Overdue | 0 | NAP | NAP
9827 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5301 | 0 | 131242-WST02-DR-A-5301-0 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5301 | NA | "GA Drawing for Centrifugal Pump" && "Shop Drawing for Louvre Door and Window" | 2024-11-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 22 | NAP | 2025-11-12 | 0 | 000798&&001604 | 2024-11-04, 2025-04-17, 2025-11-12 | 00, 01 | 3 | Not Approved | NAP | 2025-12-24 | Overdue | 0 | NAP | NAP
9828 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5302 | 0 | 131242-WST02-DR-A-5302-0 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5302 | NA | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 22 | NAP | 2025-11-12 | 0 | 001604 | 2025-11-12 | 01 | 1 | Not Approved | NAP | 2025-12-24 | Overdue | 0 | NAP | NAP
9829 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5303 | 1 | 131242-WST02-DR-A-5303-1 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5303 | NA | "Shop Drawing for Louvre Door and Window" | 2025-11-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 22 | NAP | 2025-11-12 | 1 | 001604 | 2025-11-12 | 01 | 1 | Not Approved | NAP | 2025-12-24 | Overdue | 0 | NAP | NAP
9830 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | DR | A | 5340 | 0 | 131242-WST02-DR-A-5340-0 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-DR-5340 | NA | "SSN Instrument Hookup Drawing for Radar Level Transmitter" && "Shop Drawing for Louvre Door and Window" | 2025-09-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 22 | NAP | 2025-11-12 | 0 | 001604&&001675 | 2025-09-10, 2025-11-12 | 00, 01 | 2 | Not Approved | NAP | 2025-12-24 | Overdue | 0 | NAP | NAP
9831 | 001604 | 01 | Yuen Fatt | CSA | NA | 131242 | WST02 | CL | A | 0005 | 0 | 131242-WST02-CL-A-0005-0 | 2025-11-12 | Shop Drawing for Louvre Door and Window | Rev 1: Not Approved. Please refer to comment sheet for resubmission | 2025-12-02 | 2025-12-04 | Not Approved | 2025-12-24 | NO | Overdue |  | 131242-WST02-CL-0005 | NA | "Anchor bolt Details for pipe supports for post drill and Cast-in type" && "SSN 22kV MV Power Cable Sizing Calculations" && "SSN Process Hydraulic Calculation & Drawing" && "Shop Drawing for Louvre Door and Window" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 22 | NAP | 2025-11-12 | 0 | 000406&&000416&&000805&&001604 | 2024-03-28, 2024-04-03, 2024-07-06, 2024-08-21, 2024-11-11, 2025-02-19, 2025-03-24, 2025-11-12 | 00, 01, 02 | 8 | Not Approved | NAP | 2025-12-24 | Overdue | 0 | NAP | NAP
9832 | 001605 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0003 | 0 | 131242-WST02-QA-S-0003-0 | 2025-08-19 | ST609 Inspection Reports | For information | 2025-09-16 | 2025-10-13 | For Information |  | YES | NA |  | 131242-WST02-QA-0003 | NA | "2Hrs Fire rated AAC Blocks" && "ST609 Inspection Reports" && "Vendor Manufacturing Inspection and test plan and FAT procedure for LVSG/MCC/MDB SWITCH BOARD (SUNLIGHT) " | 2024-08-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-02 | 55 | INF | 2025-08-19 | 0 | 000676&&000856&&001605 | 2024-08-26, 2024-11-29, 2024-12-20, 2024-12-26, 2025-02-07, 2025-08-19 | 00, 01, 02 | 6 | For Information | INF | 2025-10-31 | Overdue | 0 | INF | INF
9833 | 001606 | 00 | Radha | QAQC | NA | 131242 | WSW41 | QA | S | 0004 | 0 | 131242-WSW41-QA-S-0004-0 | 2025-08-19 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | NA | 2025-09-16 | 2025-09-24 | Approved with Comments | 2025-10-14 | YES | Resubmitted |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-02 | 36 | AWC | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9834 | 001606 | 01 | Radha | QAQC | NA | 131242 | WSW41 | QA | S | 0004 | 1 | 131242-WSW41-QA-S-0004-1 | 2025-12-10 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2025-12-30 | 2025-12-17 | Approved with Comments | 2026-01-06 | YES | Resubmitted |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-24 | 7 | AWC | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9835 | 001606 | 02 | Radha | QAQC | NA | 131242 | WSW41 | QA | S | 0004 | 2 | 131242-WSW41-QA-S-0004-2 | 2026-01-07 | Test Procedure for Pull & Push Load Test - Aluminium Handrail | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-27 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WSW41-QA-0004 | NA | "Inspection Test Plan for Concreting Work" && "Inspection Test Plan for Installation of Door and Window Work" && "Inspection and test plan for earthing and lightning installation (Cyclect Electrical engineering Pte Ltd)" && "Test Procedure for Pull & Push Load Test - Aluminium Handrail" && "Vendor Manufacturing Inspection Test Plan for HDPE Pipe and Fittings" | 2023-10-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-21 | 5 | AWC | 2026-01-07 | 2 | 000147&&000169&&000600&&000689&&001606 | 2023-10-27, 2023-11-06, 2023-12-21, 2024-01-29, 2024-07-31, 2024-08-30, 2025-02-07, 2025-03-14, 2025-08-19, 2025-12-10, 2026-01-07 | 00, 01, 02 | 11 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
9836 | 001607 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0044 | 0 | 131242-WST02-QA-E-0044-0 | 2025-08-22 | Inspection Test Plan for Distribution Panels (MDBs) | NA | 2025-09-19 | 2025-09-15 | Approved |  | YES | NA |  | 131242-WST02-QA-0044 | NA | " Inspection Test Plan for Distribution Panels (MDBs)" && "Factory Acceptance Test Report for Dissolved Oxygen Analyser" | 2025-07-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 24 | APP | 2025-08-22 | 0 | 001542&&001607 | 2025-07-30, 2025-08-22 | 00 | 2 | Approved | APP |  |  | 0 | APP | APP
9837 | 001608 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0005 | 0 | 131242-WST02-QA-S-0005-0 | 2025-08-20 | ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For informaiton | 2025-09-17 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WST02-QA-0005 | NA | "Inspection and test Plan for fire protection system " && "ST614, Batch 2, GL J-L & GL V-AB, SWPR-03 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for LV Power Cables (Keystone)" | 2024-09-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-03 | 68 | INF | 2025-08-20 | 0 | 000706&&001260&&001608 | 2024-09-06, 2024-11-20, 2025-01-16, 2025-02-26, 2025-04-30, 2025-07-03, 2025-07-04, 2025-08-20 | 00, 01, 02, 03, 04 | 8 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9838 | 001609 | 00 | Karthik | EICA | NA | 131242 | WSD11 | DR | BF | 7001 | A | 131242-WSD11-DR-BF-7001-A | 2025-08-22 | THP Fire alarm devices interface with C4A Fire Alarm panel | R0: Approved. | 2025-09-19 | 2025-10-22 | Approved |  | YES | NA |  | 131242-WSD11-DR-7001 | NA | " THP Fire alarm devices interface with C4A Fire Alarm panel" && "THP Compartmentalization Lighting and Ventilation Fan" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Process Flow Diagram" && "THP SLD" | 2023-10-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 61 | APP | 2025-10-23 | E | 000143&&000198&&000570&&000571&&001012&&001609 | 2023-10-26, 2023-11-21, 2024-03-18, 2024-07-16, 2024-08-26, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-26, 2025-03-07, 2025-08-22, 2025-10-23 | 00, 01, 02, 03, 04, 05 | 12 | Approved | APP |  |  | 0 | APP | APP
9839 | 001610 | 00 | Qili | Process | NA | 131242 | WST02 | CL | P | 0012 | 0 | 131242-WST02-CL-P-0012-0 | 2025-08-22 | G2D Water Hydraulic Pressure Loss Calculation | NA | 2025-09-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CL-0012 | NA | "G2D Water Hydraulic Pressure Loss Calculation" | 2025-08-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 227 | PEN | 2025-08-22 | 0 | 001610 | 2025-08-22 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-09 |  | 0 | PEN | PEN
9840 | 001611 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0013 | 0 | 131242-WSW41-PO-I-0013-0 | 2025-08-22 | Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0013 | NA | "Unpriced PO for CSEL Pipes (MUSG)" && "Unpriced PO for Electromagnetic Flowmeter (Endress & Hauser)" && "Unpriced PO for NO2, NO3, NH4 Analyser (Ansac) " | 2025-02-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 105 | INF | 2025-08-22 | 0 | 001069&&001503&&001611 | 2025-02-24, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9841 | 001612 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0014 | 0 | 131242-WSW41-PO-I-0014-0 | 2025-08-22 | Unpriced PO for Thermal Flow Switch (Endress & Hauser) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0014 | NA | "Unpriced PO for Capacitive Level Switch (IFM)" && "Unpriced PO for HDPE Pipes (AGRU) " && "Unpriced PO for Thermal Flow Switch (Endress & Hauser) " | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 105 | INF | 2025-08-22 | 0 | 001098&&001504&&001612 | 2025-03-06, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9842 | 001613 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0015 | 0 | 131242-WSW41-PO-I-0015-0 | 2025-08-22 | Unpriced PO for Pressure Switch (IFM) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0015 | NA | "Unpriced LOA for MEICA installer (Cyclect Engineering)" && "Unpriced PO for Pressure Switch (IFM) " && "Unpriced PO for Thermal Mass Flowmeter (Endress & Hauser)" | 2025-04-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 105 | INF | 2025-08-22 | 0 | 001211&&001505&&001613 | 2025-04-08, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9843 | 001614 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0016 | 0 | 131242-WSW41-PO-I-0016-0 | 2025-08-22 | Unpriced PO for Rotameter (Krohne) | Rev 0: Accepted for Information | 2025-09-19 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0016 | NA | "Unpriced LOA for Fire Protection System" && "Unpriced PO for Pressure Gauge (Baumer) " && "Unpriced PO for Rotameter (Krohne) " | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-05 | 105 | INF | 2025-08-22 | 0 | 001214&&001506&&001614 | 2025-04-09, 2025-07-22, 2025-08-22 | 00 | 3 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9844 | 001615 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | M | 0026 | 0 | 131242-WSW41-PO-M-0026-0 | 2025-08-22 | Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng) | Rev 0: For Information Only. | 2025-09-19 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0026 | NA | "Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng)" && "Unpriced PO for Valve for Condensate System (Spirax Sarco)" | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-11 | 94 | INF | 2025-10-31 | 0 | 001615&&001800 | 2025-08-22, 2025-10-31 | 00 | 2 | For Information | INF |  |  | 0 | INF | INF
9845 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1004 | A.1 | 131242-WST02-SD-S-1004-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1004 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9846 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1005 | A.1 | 131242-WST02-SD-S-1005-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1005 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9847 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1006 | A.1 | 131242-WST02-SD-S-1006-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1006 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9848 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1007 | A.1 | 131242-WST02-SD-S-1007-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1007 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2026-02-09 | A.5 | 001616&&001698&&001803 | 2025-08-22, 2025-09-26, 2026-02-09 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | VOID | VOID
9849 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1008 | A.1 | 131242-WST02-SD-S-1008-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1008 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9850 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1009 | A.1 | 131242-WST02-SD-S-1009-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1009 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-09-29 | A | 001616&&001700 | 2025-08-22, 2025-09-29 | 00 | 2 | Rejected | REJ |  |  | 0 | VOID | VOID
9851 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1010 | A.1 | 131242-WST02-SD-S-1010-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-1010 | NA | "Lintel and Stiffener Shop Drawings" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-05 | 40 | VOID | 2025-08-22 | A.1 | 001008&&001042&&001616 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-08-22 | 00, 01, 02 | 5 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9852 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3002 | A.1 | 131242-WST02-SD-S-3002-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-3002 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9853 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3003 | A.1 | 131242-WST02-SD-S-3003-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-3003 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9854 | 001616 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8601 | A.1 | 131242-WST02-SD-S-8601-A.1 | 2025-08-22 | Railing Shop Drawing- SSN Tanks and Chemical Dosing area | Contractor requests to VOID this submission due to duplication with #1528 | 2025-09-19 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WST02-SD-8601 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Review_Status not in approval_code_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-11 | 40 | VOID | 2025-08-22 | A.1 | 001616 | 2025-08-22 | 00 | 1 | (VOID NOT IN USE) | VOID |  |  | 0 | VOID | VOID
9855 | 001617 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5361 | 0 | 131242-WSW41-DR-M-5361-0 | 2025-08-25 | Piping Special Item - Metallic Strainer (Spirax Sarco) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments | 2025-09-22 | 2025-10-22 | Not Approved | 2025-11-11 | NO | Overdue |  | 131242-WSW41-DR-5361 | NA | "Piping Special Item - Metallic Strainer (Spirax Sarco)" | 2025-08-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 58 | NAP | 2025-08-25 | 0 | 001617 | 2025-08-25 | 00 | 1 | Not Approved | NAP | 2025-11-11 | Overdue | 0 | NAP | NAP
9856 | 001618 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5371 | 0 | 131242-WSW41-DR-M-5371-0 | 2025-08-25 | Piping Special Item - Plastic Strainer (Asahi/ Argu) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-10-22 | Not Approved | 2025-11-11 | NO | Overdue |  | 131242-WSW41-DR-5371 | NA | "Piping Special Item - Plastic Strainer (Asahi/ Argu)" | 2025-08-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 58 | NAP | 2025-08-25 | 0 | 001618 | 2025-08-25 | 00 | 1 | Not Approved | NAP | 2025-11-11 | Overdue | 0 | NAP | NAP
9857 | 001619 | 00 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5465 | A | 131242-WST02-DR-M-5465-A | 2025-08-25 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-5465 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 77 | AWC | 2026-01-22 | C | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9858 | 001619 | 00 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5466 | A | 131242-WST02-DR-M-5466-A | 2025-08-25 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-5466 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 77 | AWC | 2026-01-22 | C | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9859 | 001619 | 00 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5467 | A | 131242-WST02-DR-M-5467-A | 2025-08-25 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-11-10 | Approved with Comments | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-5467 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 77 | AWC | 2026-01-22 | D | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9860 | 001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5465 | B | 131242-WST02-DR-M-5465-B | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5465 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-01 | 170 | PEN | 2026-01-22 | C | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
9861 | 001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5466 | B | 131242-WST02-DR-M-5466-B | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5466 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-01 | 170 | PEN | 2026-01-22 | C | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
9862 | 001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5467 | B | 131242-WST02-DR-M-5467-B | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5467 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-01 | 170 | PEN | 2026-01-22 | D | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
9863 | 001619 | 01 | David Li | Mech | NA | 131242 | WST02 | DR | M | 5468 | B | 131242-WST02-DR-M-5468-B | 2025-10-18 | GA drawing for Splitter Box | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5468 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-07 | 170 | PEN | 2026-01-22 | D | 001619&&001974 | 2025-10-18, 2026-01-22 | 00, 01 | 2 | Awaiting S.O.'s response | PEN |  |  | 0 | PEN | PEN
9864 | 001620 | 00 | Htet Nu | EICA | NA | 131242 | WSW41 | LC | E | 0001 | 0 | 131242-WSW41-LC-E-0001-0 | 2025-08-25 | C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026) | Rev 0: For Information. | 2025-09-22 | 2025-10-01 | For Information |  | YES | NA |  | 131242-WSW41-LC-0001 | NA | "C4B Electrical Installation Licence_EMA (13/08/2025 to 12/08/2026)" && "Contractor’s Site Office, Workers’ Rest Area and Car Park Shelter" | 2024-01-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-08 | 37 | INF | 2025-08-25 | 0 | 000277&&001620 | 2024-01-16, 2024-02-02, 2025-08-25 | 00, 01 | 3 | For Information | INF | 2025-10-21 | Overdue | 0 | INF | INF
9865 | 001621 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1403 | 0 | 131242-WST02-QA-E-1403-0 | 2025-08-25 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-09-22 | 2025-09-26 | Not Approved | 2025-10-16 | YES | Resubmitted |  | 131242-WST02-QA-1403 | NA | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 32 | NAP | 2025-10-29 | 0 | 001621 | 2025-08-25, 2025-10-01, 2025-10-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9866 | 001621 | 01 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1403 | 0 | 131242-WST02-QA-E-1403-0 | 2025-10-01 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | Rev 1: Rejected. To revise and resubmit. Refer to attached file for comments. | 2025-10-21 | 2025-10-06 | Rejected | 2025-10-24 | YES | Resubmitted |  | 131242-WST02-QA-1403 | NA | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 5 | REJ | 2025-10-29 | 0 | 001621 | 2025-08-25, 2025-10-01, 2025-10-29 | 00, 01, 02 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
9867 | 001621 | 02 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1403 | 0 | 131242-WST02-QA-E-1403-0 | 2025-10-29 | Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A | Rev 2: Not approved - Revise and Resubmit Refer to attached file for comments. | 2025-11-18 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WST02-QA-1403 | NA | "Sample Board Submission for Light Fitting and 1 Way 1G Explosion Proof Switch Surface Mounting Sockets 32A" | 2025-08-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-12 | 118 | NAP | 2025-10-29 | 0 | 001621 | 2025-08-25, 2025-10-01, 2025-10-29 | 00, 01, 02 | 3 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
9868 | 001622 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0006 | 0 | 131242-WST02-QA-S-0006-0 | 2025-08-25 | ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-09-22 | 2025-10-24 | For Information |  | YES | NA |  | 131242-WST02-QA-0006 | NA | "Inspection and test Plan and Factory Acceptance Test for Public Address System" && "ST608 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection test plan and FAT procedure for MV Cables (Keystone) " | 2024-09-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-08 | 60 | INF | 2025-10-08 | 2 | 000707&&001262&&001622 | 2024-09-06, 2024-12-20, 2025-05-02, 2025-07-05, 2025-08-25, 2025-10-08 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | INF | INF
9869 | 001623 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1602 | A | 131242-WST02-DR-S-1602-A | 2025-08-25 | SSN Chemical Dosing Platform Design | R0: Approved with comments. Please refer to comment sheet for resubmsision. | 2025-09-22 | 2025-12-02 | Approved with Comments | 2025-12-22 | NO | Overdue |  | 131242-WST02-DR-1602 | NA | "SSN Chemical Dosing Platform Design" && "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 99 | AWC | 2025-08-25 | A | 001453&&001623 | 2025-07-08, 2025-08-25 | 00 | 2 | Approved with Comments | AWC | 2025-12-22 | Overdue | 0 | AWC | AWC
9870 | 001623 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1603 | A | 131242-WST02-DR-S-1603-A | 2025-08-25 | SSN Chemical Dosing Platform Design | R0: Approved with comments. Please refer to comment sheet for resubmsision. | 2025-09-22 | 2025-12-02 | Approved with Comments | 2025-12-22 | NO | Overdue |  | 131242-WST02-DR-1603 | NA | "SSN Chemical Dosing Platform Design" && "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-08 | 99 | AWC | 2025-08-25 | A | 001453&&001623 | 2025-07-08, 2025-08-25 | 00 | 2 | Approved with Comments | AWC | 2025-12-22 | Overdue | 0 | AWC | AWC
9871 | 001623 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5604 | A | 131242-WST02-DR-S-5604-A | 2025-08-25 | SSN Chemical Dosing Platform Design | R0: Approved with comments. Please refer to comment sheet for resubmsision. | 2025-09-22 | 2025-12-02 | Approved with Comments | 2025-12-22 | NO | Overdue |  | 131242-WST02-DR-5604 | NA | "SSN Chemical Dosing Platform Design" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-08-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-14 | 99 | AWC | 2025-09-08 | A.1 | 001623&&001656 | 2025-08-25, 2025-09-08 | 00 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
9872 | 001624 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0018 | 0 | 131242-WST02-OM-M-0018-0 | 2025-08-25 | Operation and Maintenance Manual for Parabolic Screen | NA | 2025-09-22 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0018 | NA | "Operation and Maintenance Manual for Parabolic Screen" | 2025-08-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-14 | 224 | PEN | 2025-08-25 | 0 | 001624 | 2025-08-25 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-10 |  | 0 | PEN | PEN
9873 | 001625 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001-A | 2025-08-26 | SSN Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-09 | 76 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
9874 | 001625 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001-A | 2025-08-26 | SSN Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-09 | 76 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
9875 | 001625 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | A | 1001 | A | 131242-WST02-DR-A-1001-A | 2025-08-26 | SSN Rain Water Drainage Layout and Detail Design | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-23 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-09 | 76 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
9876 | 001626 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0027 | 0 | 131242-WSW41-QA-A-0027-0 | 2025-08-26 | Material Submission for Waterproofing (Pro-Werkze Pte Ltd) | R0: Approved | 2025-09-23 | 2025-09-17 | Approved |  | YES | NA |  | 131242-WSW41-QA-0027 | NA | "Material Submission for Waterproofing (Pro-Werkze Pte Ltd)" && "Test Report submission for HDG Thread rod, Flat washer & Hex Nut (Sidewide piperack stumps)" && "Vendor Manufacturing Inspection test plan and test procedures for Metallic ball valves (Heaton)" | 2024-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-09 | 22 | APP | 2025-08-26 | 0 | 000889&&001240&&001626 | 2024-12-12, 2025-04-21, 2025-08-26 | 00, 01 | 4 | Approved | APP |  |  | 0 | APP | APP
9877 | 001627 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0068 | 0 | 131242-WSW41-LT-PM-0068-0 | 2025-08-26 | CV of Team Member (WSHO) | NA | 2025-09-23 | 2025-09-11 | Approved |  | YES | NA |  | 131242-WSW41-LT-0068 | NA | "CV of Team Member (WSHO)" | 2025-08-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-15 | 16 | APP | 2025-08-26 | 0 | 001627 | 2025-08-26 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9878 | 001628 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0045 | 0 | 131242-WST02-QA-EI-0045-0 | 2025-08-27 | SAT Report for WST02-LVSG-0101A & WST02-LVSG-0101B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-24 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-QA-0045 | NA | "SAT Report for WST02-LVSG-0101A & WST02-LVSG-0101B" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-16 | 35 | AWC | 2025-08-27 | 0 | 001628 | 2025-08-27 | 00 | 1 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
9879 | 001629 | 00 | Radha | QAQC | NA | 131242 | WST02 | QA | S | 0007 | 0 | 131242-WST02-QA-S-0007-0 | 2025-08-27 | ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-09-24 | 2025-10-29 | For Information |  | YES | NA |  | 131242-WST02-QA-0007 | NA | "Inspection and test Plan and Factory Acceptance Test for Fire Alarm System " && "Material Submission of E400ST Epoxy Adhesive (Wet trade – Huaya Construction Pte ltd) " && "ST621 - IRN, Materials Inspection, Testing, Fit-up, Welding, NDT, Galvanize and Painting Report Submission" | 2024-12-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-10 | 63 | INF | 2025-08-27 | 0 | 000884&&001263&&001629 | 2024-12-11, 2025-05-02, 2025-07-07, 2025-08-27 | 00, 01 | 4 | For Information | INF | 2025-11-18 | Overdue | 0 | INF | INF
9880 | 001630 | 00 | Caeden | Contracts | NA | 131242 | WSW41 | PO | B | 0001 | 0 | 131242-WSW41-PO-B-0001-0 | 2025-08-27 | Unpriced PO for Building Management System (Willowglen) | NA | 2025-09-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-PO-0001 | NA | "Unpriced PO for Building Management System (Willowglen)" && "Unpriced PO for Conductivity Analyser, Dissolved Oxygen Analyser, TSS Analyser, and pH Analyser(Endress & Hauser)" && "Unpriced PO for Knife Gate Valve (Jash Engineering)" | 2025-07-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-09-10 | 222 | PEN | 2025-08-27 | 0 | 001500&&001512&&001630 | 2025-07-22, 2025-08-01, 2025-08-27 | 00 | 3 | For Information | INF | 2025-10-14 |  | 0 | PEN | PEN
9881 | 001631 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | VI | I | 0006 | 0 | 131242-WSD11-VI-I-0006-0 | 2025-08-27 | Vendor Information of BD Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-10-30 | Approved with Comments | 2025-11-19 | NO | Overdue |  | 131242-WSD11-VI-0006 | NA | "Vendor Information of BD Flowmeter " | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-16 | 64 | AWC | 2025-08-27 | 0 | 001631 | 2025-08-27 | 00 | 1 | Approved with Comments | AWC | 2025-11-19 | Overdue | 0 | AWC | AWC
9882 | 001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5390 | A | 131242-WST02-DR-I-5390-A | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5390 | NA | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-16 | 105 | AWC | 2025-08-27 | A | 001632 | 2025-08-27 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9883 | 001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5391 | A | 131242-WST02-DR-I-5391-A | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5391 | NA | "Datasheet & GA drawing for sampling pump" && "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-10 | 105 | AWC | 2025-10-18 | B | 001172&&001632 | 2025-03-27, 2025-08-27, 2025-10-18 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9884 | 001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5392 | A | 131242-WST02-DR-I-5392-A | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5392 | NA | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-16 | 105 | AWC | 2025-08-27 | A | 001632 | 2025-08-27 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9885 | 001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5393 | A | 131242-WST02-DR-I-5393-A | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5393 | NA | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-16 | 105 | AWC | 2025-08-27 | A | 001632 | 2025-08-27 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9886 | 001632 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5394 | A | 131242-WST02-DR-I-5394-A | 2025-08-27 | SSN Instrument Hookup Drawing for Electromagnetic FIT | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-24 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5394 | NA | "SSN Instrument Hookup Drawing for Electromagnetic FIT" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-16 | 105 | AWC | 2025-08-27 | A | 001632 | 2025-08-27 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9887 | 001633 | 00 | Karthik | EICA | NA | 131242 | WSD11 | BQ | I | 0010 | 0 | 131242-WSD11-BQ-I-0010-0 | 2025-08-27 | Cable List for RIO-0101 | Rev 0: Rejected. No resubmission required. | 2025-09-24 | 2025-12-10 | Rejected |  | YES | NA |  | 131242-WSD11-BQ-0010 | NA | "Cable List for RIO-0101" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-16 | 105 | REJ | 2025-08-27 | 0 | 001633 | 2025-08-27 | 00 | 1 | Rejected | REJ | 2025-12-30 | Overdue | 0 | REJ | REJ
9888 | 001634 | 00 | Karthik | EICA | NA | 131242 | WSD11 | BQ | I | 0011 | 0 | 131242-WSD11-BQ-I-0011-0 | 2025-08-27 | Cable List for RIO-002A | Rev 0: Rejected. No resubmission required. | 2025-09-24 | 2025-12-10 | Rejected |  | YES | NA |  | 131242-WSD11-BQ-0011 | NA | "Cable List for RIO-002A" | 2025-08-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-16 | 105 | REJ | 2025-08-27 | 0 | 001634 | 2025-08-27 | 00 | 1 | Rejected | REJ | 2025-12-30 | Overdue | 0 | REJ | REJ
9889 | 001635 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0046 | 0 | 131242-WSW41-QA-E-0046-0 | 2025-08-28 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel | Rev 0: Not approved. To revise and resubmit. Refer to attache file for comments. | 2025-09-25 | 2025-10-01 | Not Approved | 2025-10-21 | YES | Resubmitted |  | 131242-WSW41-QA-0046 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-11 | 34 | NAP | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | For Information | INF |  |  | 0 | NAP | NAP
9890 | 001635 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0046 | 1 | 131242-WSW41-QA-E-0046-1 | 2025-10-02 | Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel | Rev 1: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-22 | 2025-10-10 | Approved with Comments | 2025-10-30 | NO | Overdue |  | 131242-WSW41-QA-0046 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-16 | 8 | AWC | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | For Information | INF |  |  | 0 | AWC | AWC
9891 | 001636 | 00 | Joo Kwan | Process | NA | 131242 | NA | NA | NA | 9999 | 1 | 131242----- | 2025-08-29 | Testing Check List (Process) | Approved with comments. | 2025-09-26 | 2025-10-01 | Approved with Comments | 2025-10-21 | YES | Resubmitted |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-12 | 33 | AWC | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | AWC | AWC
9892 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0011 | 0 | 131242-WSW41-QA-N-0011-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0011 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9893 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0012 | 0 | 131242-WSW41-QA-N-0012-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0012 | NA | "FAT Report for Power Cable, Control Cable, MV Cable" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | 2024-12-31 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000936&&001304&&001636&&001712 | 2024-12-31, 2025-05-18, 2025-09-30, 2026-01-28 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9894 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0013 | 0 | 131242-WSW41-QA-N-0013-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9895 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0014 | 0 | 131242-WSW41-QA-N-0014-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9896 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0015 | 0 | 131242-WSW41-QA-N-0015-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0015 | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Plate Load test report " && "T&C Check List " && "Testing Check List (Process)" | 2024-08-29 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000682&&000694&&001636&&001712 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9897 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0016 | 0 | 131242-WSW41-QA-N-0016-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9898 | 001636 | 01 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0017 | 0 | 131242-WSW41-QA-N-0017-0 | 2026-01-28 | Testing Check List (Process) | Approved with comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | NO | PEN | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
9899 | 001637 | 00 | Joo Kwan | Process | NA | 131242 | NA | NA | NA | 9999 | 0 | 131242----- | 2025-08-29 | Commissioning Plan for EQ Tank and Lamella Clarifier | NA | 2025-09-26 | 2025-09-08 | Approved with Comments | 2025-09-26 | NO | Overdue |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-12 | 10 | AWC | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | AWC | AWC
9900 | 001638 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0200 | 0 | 131242-WSD11-QA-N-0200-0 | 2025-08-29 | Commissioning Plan for THP Train | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-09-26 | 2025-09-04 | Approved with Comments | 2025-09-24 | NO | Overdue |  | 131242-WSD11-QA-0200 | NA | "Commissioning Plan for THP Train" | 2025-08-29 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-18 | 6 | AWC | 2025-08-29 | 0 | 001638 | 2025-08-29 | 00 | 1 | Approved with Comments | AWC | 2025-09-24 | Overdue | 0 | AWC | AWC
9901 | 001639 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0050 | 0 | 131242-WST02-QA-I-0050-0 | 2025-08-29 | Factory Acceptance Test Report for Conductive Probe Level Switches | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-09-26 | 2025-11-14 | Approved with Comments | 2025-12-04 | NO | Overdue |  | 131242-WST02-QA-0050 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-3rd Batch)" && "Factory Acceptance Test Report for Conductive Probe Level Switches" | 2025-02-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-12 | 77 | AWC | 2025-08-29 | 0 | 001059&&001639 | 2025-02-19, 2025-08-29 | 00 | 2 | Approved with Comments | AWC | 2025-12-04 | Overdue | 0 | AWC | AWC
9902 | 001640 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0301 | C | 131242-WSD11-DR-S-0301-C | 2025-08-29 | HDG Grating Clamp Details | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-09-26 | 2025-10-23 | Not Approved | 2025-11-12 | YES | Resubmitted |  | 131242-WSD11-DR-0301 | NA | "HDG Grating Clamp Details" | 2025-08-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-18 | 55 | NAP | 2025-08-29 | C | 001640 | 2025-08-29 | 00 | 1 | Not Approved | NAP | 2025-11-12 | Overdue | 0 | NAP | NAP
9903 | 001640 | 01 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment sheet | C | 131242-WSD11-DR-S-comment sheet- | 2025-11-05 | HDG Grating Clamp Details | Rev 1: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-25 | 2025-11-13 | Not Approved | 2025-12-03 | YES | Resubmitted |  | 131242-WSD11-DR-comment sheet | NA | "HDG Grating Clamp Details" | 2025-11-05 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 8 | NAP | 2025-11-05 | C | 001640 | 2025-11-05 | 01 | 1 | Not Approved | NAP | 2025-12-03 | Overdue | 0 | NAP | NAP
9904 | 001640 | 02 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | comment sheet.R1 | C | 131242-WSD11-DR-S-comment sheet.R1- | 2025-11-24 | HDG Grating Clamp Details | Rev 2: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-12 | 2025-12-29 | Not Approved | 2026-01-16 | NO | Overdue |  | 131242-WSD11-DR-comment sheet.R1 | NA | "HDG Grating Clamp Details" | 2025-11-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-14 | 35 | NAP | 2025-11-24 | C | 001640 | 2025-11-24 | 02 | 1 | Not Approved | NAP | 2026-01-16 | Overdue | 0 | NAP | NAP
9905 | 001641 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1604 | F | 131242-WSD11-DR-S-1604-F | 2025-08-29 | THP Silo Crossover Platform Pipe Support | NA | 2025-09-26 | 2025-09-17 | Not Approved | 2025-10-07 | NO | Overdue |  | 131242-WSD11-DR-1604 | NA | "THP Silo Crossover Platform Pipe Support" | 2025-08-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-18 | 19 | NAP | 2025-08-29 | F | 001641 | 2025-08-29 | 00 | 1 | Not Approved | NAP | 2025-10-07 | Overdue | 0 | NAP | NAP
9906 | 001641 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5603 | E | 131242-WSD11-DR-S-5603-E | 2025-08-29 | THP Silo Crossover Platform Pipe Support | NA | 2025-09-26 | 2025-09-17 | Not Approved | 2025-10-07 | NO | Overdue |  | 131242-WSD11-DR-5603 | NA | "THP Silo Crossover Platform Pipe Support" | 2025-08-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-18 | 19 | NAP | 2025-08-29 | E | 001641 | 2025-08-29 | 00 | 1 | Not Approved | NAP | 2025-10-07 | Overdue | 0 | NAP | NAP
9907 | 001641 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5604 | F | 131242-WSD11-DR-S-5604-F | 2025-08-29 | THP Silo Crossover Platform Pipe Support | NA | 2025-09-26 | 2025-09-17 | Not Approved | 2025-10-07 | NO | Overdue |  | 131242-WSD11-DR-5604 | NA | "THP Silo Crossover Platform Pipe Support" | 2025-08-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-18 | 19 | NAP | 2025-08-29 | F | 001641 | 2025-08-29 | 00 | 1 | Not Approved | NAP | 2025-10-07 | Overdue | 0 | NAP | NAP
9908 | 001642 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5471 | A | 131242-WST02-DR-M-5471-A | 2025-09-01 | GA drawing for Sampling Sink | NA | 2025-09-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5471 | NA | "GA drawing for Sampling Sink" && "Hookup Drawing for Conductive Probe Level Switch" | 2025-09-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-21 | 217 | PEN | 2026-01-20 | 0 | 001642&&001970 | 2025-09-01, 2026-01-20 | 00 | 2 | Awaiting S.O.'s response | PEN |  |  | 0 | PEN | PEN
9909 | 001643 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0047 | 0 | 131242-WST02-QA-EI-0047-0 | 2025-09-01 | SAT Report for WST02-MCC-1001A & WST02-MCC-1001B | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-09-29 | 2025-10-01 | Approved with Comments | 2025-10-21 | NO | Overdue |  | 131242-WST02-QA-0047 | NA | "Factory Acceptance Test Report for Tuning Fork Level Switches " && "SAT Report for WST02-MCC-1001A & WST02-MCC-1001B" | 2025-08-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-15 | 30 | AWC | 2025-09-01 | 0 | 001593&&001643 | 2025-08-14, 2025-09-01 | 00 | 2 | Approved with Comments | AWC | 2025-10-21 | Overdue | 0 | AWC | AWC
9910 | 001644 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | M | 0116 | 0 | 131242-WSW41-QA-M-0116-0 | 2025-09-01 | Load Test Reports for Top Manway (Aluminium Hatch) | NA | 2025-09-29 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0116 | NA | "Load Test Reports for Top Manway (Aluminium Hatch)" | 2025-09-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-21 | 217 | PEN | 2025-09-01 | 0 | 001644 | 2025-09-01 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-17 |  | 0 | PEN | PEN
9911 | 001645 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0069 | 0 | 131242-WSW41-LT-PM-0069-0 | 2025-09-02 | Part 2 Further Notice For Extension Of Time and Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | Rev (0): Rejected. Please refer to S.O. correspondence no. 409 dated 3 Oct 2025. | 2025-09-30 | 2025-10-15 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0069 | NA | "Part 2 Further Notice For Extension Of Time and Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG" | 2025-09-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-22 | 43 | REJ | 2025-09-02 | 0 | 001645 | 2025-09-02 | 00 | 1 | Rejected | REJ | 2025-11-04 | Overdue | 0 | REJ | REJ
9912 | 001646 | 00 | Freedomer | EICA | NA | 131242 | WST02 | CN | E | 0002 | 0 | 131242-WST02-CN-E-0002-0 | 2025-09-03 | RFC for LVSG and MCC Panel to Directly Sit on the Floor Instead of Concrete Base | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-10-01 | 2025-10-06 | Not Approved | 2025-10-24 | NO | Overdue |  | 131242-WST02-CN-0002 | NA | "RFC for LVSG and MCC Panel to Directly Sit on the Floor Instead of Concrete Base" | 2025-09-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-23 | 33 | NAP | 2025-09-03 | 0 | 001646 | 2025-09-03 | 00 | 1 | Not Approved | NAP | 2025-10-24 | Overdue | 0 | NAP | NAP
9913 | 001647 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0026 | 0 | 131242-WSW41-PC-W-0026-0 | 2025-09-03 | Payment Claim No.26 | Rev (0): Approved. Please refer S.O. correspondence no. 396 dated 9 Sep 25. | 2025-10-01 | 2025-09-23 | Approved |  | YES | NA |  | 131242-WSW41-PC-0026 | NA | "Payment Claim No.26" | 2025-09-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-23 | 20 | APP | 2025-09-03 | 0 | 001647 | 2025-09-03 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9914 | 001648 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0046 | 0 | 131242-WSD11-DS-M-0046-0 | 2025-09-04 | THP G2D Pressure Reducing Valve Data Sheet | Rev 0: Approved | 2025-10-02 | 2025-10-22 | Approved |  | YES | NA |  | 131242-WSD11-DS-0046 | NA | "THP G2D Pressure Reducing Valve Data Sheet" | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-24 | 48 | APP | 2025-09-04 | 0 | 001648 | 2025-09-04 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9915 | 001649 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5560 | 0 | 131242-WST02-DS-M-5560-0 | 2025-09-04 | Solenoid Valve Data Sheet | Rev 0: Approved | 2025-10-02 | 2025-10-22 | Approved |  | YES | NA |  | 131242-WST02-DS-5560 | NA | "Solenoid Valve Data Sheet" | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-24 | 48 | APP | 2026-12-29 | 1 | 001649 | 2025-09-04, 2026-12-29 | 00, 01 | 2 | Approved | APP |  |  | 0 | APP | APP
9916 | 001649 | 01 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5560 | 1 | 131242-WST02-DS-M-5560-1 | 2026-12-29 | Solenoid Valve Data Sheet | Rev 0: Approved | 2027-01-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5560 | NA | "Solenoid Valve Data Sheet" | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2027-01-12 |  | PEN | 2026-12-29 | 1 | 001649 | 2025-09-04, 2026-12-29 | 00, 01 | 2 | Approved | APP |  |  | 0 | PEN | PEN
9917 | 001650 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0054 | 0 | 131242-WST02-QA-I-0054-0 | 2025-09-04 | Vendor Manufacturing Inspection Test Plan for Rotameter | Rev 0: Approved with comments. No resubmission required. | 2025-10-02 | 2025-12-10 | Approved with Comments |  | YES | NA |  | 131242-WST02-QA-0054 | NA | "FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight)" && "Vendor Manufacturing Inspection Test Plan for Rotameter " | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-24 | 97 | AWC | 2025-10-01 | 0 | 001650&&001717 | 2025-09-04, 2025-10-01 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9918 | 001651 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0051 | 0 | 131242-WST02-QA-I-0051-0 | 2025-09-04 | FAT Report for RIO Mock Up Panel | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-10-02 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-QA-0051 | NA | "FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight)" && "FAT Report for RIO Mock Up Panel " | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 97 | AWC | 2025-09-18 | 0 | 001651&&001683 | 2025-09-04, 2025-09-18 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9919 | 001652 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0052 | 0 | 131242-WST02-QA-I-0052-0 | 2025-09-04 | FAT Report for PLC Mock Up Panel | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-10-02 | 2025-12-09 | For Information | 2025-12-29 | NO | Overdue |  | 131242-WST02-QA-0052 | NA | " Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss)" && "FAT Report for PLC Mock Up Panel " | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 96 | INF | 2025-09-29 | 0 | 001652&&001704 | 2025-09-04, 2025-09-29 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | INF | INF
9920 | 001653 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0053 | 0 | 131242-WST02-QA-I-0053-0 | 2025-09-04 | FAT Report for FFOTP Mock Up Panel | Rev 0: Accepted for Information. To revise and resubmit. Refer attached file for comments. | 2025-10-02 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WST02-QA-0053 | NA | "FAT Report for FFOTP Mock Up Panel" && "SAT Procedure for MDB Panels (Sunlight)" | 2025-09-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 96 | AWC | 2025-10-01 | 0 | 001653&&001718 | 2025-09-04, 2025-10-01 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9921 | 001654 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0008 | 0 | 131242-WST02-QA-S-0008-0 | 2025-09-04 | ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission | For information | 2025-10-02 | 2025-10-29 | For Information |  | YES | NA |  | 131242-WST02-QA-0008 | NA | "Inspection and test Plan and Factory Acceptance Test for Clean Gas System" && "Material Submission PVC Groove Joint (Wet trade – Huaya Construction Pte ltd) " && "ST617, PF-01 IRN, Materials testing, Fit-up, welding, NDT, Galvanize and painting report submission" | 2024-12-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-18 | 55 | INF | 2025-09-04 | 0 | 000883&&001268&&001654 | 2024-12-10, 2025-05-04, 2025-07-05, 2025-09-04 | 00, 01 | 4 | For Information | INF | 2025-11-18 | Overdue | 0 | INF | INF
9922 | 001655 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | RT | Z | 0002 | 0 | 131242-WSD11-RT-Z-0002-0 | 2025-09-08 | FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-06 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WSD11-RT-0002 | NA | "FAT Report for MCC Panels WST02-MCC-0102 A & B (Sunlight)" && "Report of Project Safety Review for THP Trains Installation" && "SSN Chemical Consumption Calculation" && "THP Load Flow Study Report" | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-22 | 28 | AWC | 2025-09-08 | 0 | 000405&&000826&&001150&&001655 | 2024-03-28, 2024-11-20, 2025-03-24, 2025-03-25, 2025-06-18, 2025-09-03, 2025-09-08 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9923 | 001656 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8600 | A.1 | 131242-WST02-DR-S-8600-A.1 | 2025-09-08 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-06 | 2025-10-23 | Not Approved | 2025-11-12 | NO | Overdue |  | 131242-WST02-DR-8600 | NA | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-28 | 45 | NAP | 2025-11-06 | A.3 | 001656&&001733 | 2025-09-08, 2025-10-09, 2025-11-06 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9924 | 001656 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1011 | A.1 | 131242-WST02-DR-S-1011-A.1 | 2025-09-08 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-06 | 2025-10-23 | Not Approved | 2025-11-12 | NO | Overdue |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-22 | 45 | NAP | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9925 | 001656 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5604 | A.1 | 131242-WST02-DR-S-5604-A.1 | 2025-09-08 | Shop Drawing for SWPR-03 Platform A&B Cat ladder | Rev 0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-06 | 2025-10-23 | Not Approved | 2025-11-12 | NO | Overdue |  | 131242-WST02-DR-5604 | NA | "SSN Chemical Dosing Platform Design" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-08-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-22 | 45 | NAP | 2025-09-08 | A.1 | 001623&&001656 | 2025-08-25, 2025-09-08 | 00 | 2 | Not Approved | NAP | 2025-11-12 | Overdue | 0 | NAP | NAP
9926 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5016 | A | 131242-WST02-DR-M-5016-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5016 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9927 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5017 | A | 131242-WST02-DR-M-5017-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5017 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9928 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5018 | A | 131242-WST02-DR-M-5018-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5018 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9929 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5019 | A | 131242-WST02-DR-M-5019-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5019 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9930 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5050 | A | 131242-WST02-DR-M-5050-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5050 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9931 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5051 | A | 131242-WST02-DR-M-5051-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5051 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9932 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5052 | A | 131242-WST02-DR-M-5052-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5052 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9933 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5053 | A | 131242-WST02-DR-M-5053-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5053 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9934 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5054 | A | 131242-WST02-DR-M-5054-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5054 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9935 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5055 | A | 131242-WST02-DR-M-5055-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5055 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9936 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5056 | A | 131242-WST02-DR-M-5056-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5056 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9937 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5057 | A | 131242-WST02-DR-M-5057-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5057 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9938 | 001657 | 00 | David | Mech | NA | 131242 | WST02 | DR | M | 5060 | A | 131242-WST02-DR-M-5060-A | 2025-09-08 | Chemical Cabinet - GA drawing | NA | 2025-10-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5060 | NA | "Chemical Cabinet - GA drawing" | 2025-09-08 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-09-28 | 210 | PEN | 2025-09-08 | A | 001657 | 2025-09-08 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-10-24 |  | 0 | PEN | PEN
9939 | 001658 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0114 | 0 | 131242-WSW41-QA-M-0114-0 | 2025-09-08 | Vendor Manufacturing Inspection Test Plan & FAT Procedure for Flange Adaptors (Synchong Hoe) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-10-06 | 2025-12-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0114 | NA | "Vendor Manufacturing Inspection Test Plan & FAT Procedure for Flange Adaptors (Synchong Hoe)" | 2025-09-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-28 | 106 | AWC | 2025-09-08 | 0 | 001658 | 2025-09-08 | 00 | 1 | Approved with Comments | AWC | 2026-01-12 | Overdue | 0 | AWC | AWC
9940 | 001659 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0063 | 0 | 131242-WST02-CD-IM-0063-0 | 2025-09-08 | VCM Submission for 2025-08 | For Information | 2025-10-06 | 2025-10-01 | For Information |  | YES | NA |  | 131242-WST02-CD-0063 | NA | "VCM Submission for 2025-08" | 2025-09-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-28 | 23 | INF | 2025-09-08 | 0 | 001659 | 2025-09-08 | 00 | 1 | For Information | INF | 2025-10-21 | Overdue | 0 | INF | INF
9941 | 001660 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | SP | C | 0032 | 0 | 131242-WSW41-SP-C-0032-0 | 2025-09-09 | Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe) | R0: Not Approved Please refer to comment sheet for resubmission. | 2025-10-07 | 2025-10-24 | Not Approved | 2025-11-13 | NO | Overdue |  | 131242-WSW41-SP-0032 | NA | "Monorail Steel Beam, Painting System Specification Submission for Approval (SanHe)" && "Repair Procedures for Intumescent Coating System (Interchar 212) (OS Builders - SanHe)" | 2025-07-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-23 | 45 | NAP | 2025-09-09 | 0 | 001436&&001660 | 2025-07-05, 2025-09-09 | 00 | 2 | Not Approved | NAP | 2025-11-13 | Overdue | 0 | NAP | NAP
9942 | 001661 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0043 | 0 | 131242-WSW41-QA-C-0043-0 | 2025-09-09 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Jul 2025 | For information | 2025-10-07 | 2025-10-10 | For Information |  | YES | NA |  | 131242-WSW41-QA-0043 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural Works for Jul 2025" | 2025-09-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-29 | 31 | INF | 2025-09-09 | 0 | 001661 | 2025-09-09 | 00 | 1 | For Information | INF | 2025-10-30 | Overdue | 0 | INF | INF
9943 | 001662 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0055 | 0 | 131242-WST02-QA-I-0055-0 | 2025-09-09 | Factory Acceptance Test Report for Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-07 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-QA-0055 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-4th Batch)" && "Factory Acceptance Test Report for Rotameter" | 2025-03-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-23 | 92 | AWC | 2025-09-09 | 0 | 001086&&001662 | 2025-03-04, 2025-09-09 | 00 | 2 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9944 | 001663 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0017 | 0 | 131242-WSW41-PO-I-0017-0 | 2025-09-09 | Unpriced PO for Raised Floor (Momentum Construction) | Rev 0: Accepted for Information | 2025-10-07 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0017 | NA | "Unpriced LOA for Electric Hoist (Helmsion Engineering) " && "Unpriced PO for Conductive Level Switch (Endress & Hauser) " && "Unpriced PO for Raised Floor (Momentum Construction)" | 2025-05-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-23 | 87 | INF | 2025-09-09 | 0 | 001287&&001507&&001663 | 2025-05-13, 2025-07-22, 2025-09-09 | 00 | 3 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9945 | 001664 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0018 | 0 | 131242-WSW41-PO-I-0018-0 | 2025-09-09 | Unpriced PO for Automatic Waste Water Sampler (Endress & Hauser) | Rev 0: Accepted for Information | 2025-10-07 | 2025-12-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0018 | NA | "Unpriced PO for Automatic Waste Water Sampler (Endress & Hauser)" | 2025-09-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-29 | 87 | INF | 2025-09-09 | 0 | 001664 | 2025-09-09 | 00 | 1 | For Information | INF | 2025-12-25 | Overdue | 0 | INF | INF
9946 | 001665 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0019 | 0 | 131242-WSW41-PO-I-0019-0 | 2025-09-09 | Unpriced PO for Control Panels (Fox Singapore) | Rev 0: Accepted for Information. No resubmission required. Refer attached file for comments. | 2025-10-07 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSW41-PO-0019 | NA | "Unpriced PO for Control Panels (Fox Singapore)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-23 | 48 | INF | 2025-09-09 | 0 | 001509&&001665 | 2025-07-22, 2025-09-09 | 00 | 2 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9947 | 001666 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0020 | 0 | 131242-WSW41-PO-I-0020-0 | 2025-09-09 | Unpriced PO for PMS Panel (Vector Infotech) | Rev 0: Accepted for Information. No resubmission required. Refer attached file for comments. | 2025-10-07 | 2025-10-27 | For Information |  | YES | NA |  | 131242-WSW41-PO-0020 | NA | "Unpriced PO for PMS Panel (Vector Infotech)" && "Unpriced PO for Pressure Transmitter (Emerson)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-23 | 48 | INF | 2025-09-09 | 0 | 001510&&001666 | 2025-07-22, 2025-09-09 | 00 | 2 | For Information | INF | 2025-11-14 | Overdue | 0 | INF | INF
9948 | 001667 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0117 | 0 | 131242-WSW41-QA-M-0117-0 | 2025-09-10 | FAT Report for THP Area Pipe Supports | Rev 0: Approved | 2025-10-08 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0117 | NA | "FAT Report for THP Area Pipe Supports" | 2025-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-30 | 104 | APP | 2025-09-10 | 0 | 001667 | 2025-09-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9949 | 001668 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | SP | I | 0005 | 0 | 131242-WSD11-SP-I-0005-0 | 2025-09-10 | Master Control for THP | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WSD11-SP-0005 | NA | "Master Control for THP" | 2025-09-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-30 | 96 | NAP | 2025-09-10 | 0 | 001668 | 2025-09-10 | 00 | 1 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
9950 | 001669 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0118 | 0 | 131242-WSW41-QA-M-0118-0 | 2025-09-10 | FAT Report for SWPR Pipe Guide Supports | Rev 0: Approved | 2025-10-08 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0118 | NA | "FAT Report for SWPR Pipe Guide Supports" | 2025-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-30 | 104 | APP | 2025-09-10 | 0 | 001669 | 2025-09-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9951 | 001670 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0119 | 0 | 131242-WSW41-QA-M-0119-0 | 2025-09-10 | FAT Report for SWPR SS 316L Pipes | Rev 0: Approved | 2025-10-08 | 2025-12-23 | Approved |  | YES | NA |  | 131242-WSW41-QA-0119 | NA | "FAT Report for SWPR SS 316L Pipes" | 2025-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-30 | 104 | APP | 2025-09-10 | 0 | 001670 | 2025-09-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9952 | 001671 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0049 | 0 | 131242-WST02-QA-EI-0049-0 | 2025-09-10 | FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-08 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WST02-QA-0049 | NA | "FAT Report for MCC Panels WST02-MCC-0101 A & B (Sunlight)" && "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (SSN) " | 2025-08-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 145 | AWC | 2025-09-10 | 0 | 001599&&001671 | 2025-08-17, 2025-09-10 | 00 | 2 | Approved with Comments | AWC | 2026-02-20 | Overdue | 0 | AWC | AWC
9953 | 001672 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0019 | 0 | 131242-WST02-DS-I-0019-0 | 2025-09-10 | Datasheet for Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-11-05 | Approved with Comments | 2025-11-25 | NO | Overdue |  | 131242-WST02-DS-0019 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Rotameter" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 56 | AWC | 2025-09-10 | 0 | 000553&&001672 | 2025-03-06, 2025-08-22, 2025-09-10 | 00, 02, 03 | 3 | Approved with Comments | AWC | 2025-11-25 | Overdue | 0 | AWC | AWC
9954 | 001673 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0020 | 0 | 131242-WST02-DS-I-0020-0 | 2025-09-10 | Datasheet for Conductive Level Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-11-13 | Approved with Comments | 2025-12-03 | NO | Overdue |  | 131242-WST02-DS-0020 | NA | "Data Sheet, Drawing and Calculation of SSN Diffuser" && "Datasheet for Conductive Level Switch" | 2025-08-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 64 | AWC | 2025-09-10 | 0 | 000553&&001673 | 2025-08-22, 2025-09-10 | 00, 03 | 2 | Approved with Comments | AWC | 2025-12-03 | Overdue | 0 | AWC | AWC
9955 | 001674 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5371 | A | 131242-WST02-DR-I-5371-A | 2025-09-10 | SSN Instrument Hookup Drawing for Temperature Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5371 | NA | "PC Pump GA Drawing " && "SSN Instrument Hookup Drawing for Temperature Transmitter" | 2024-12-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-24 | 91 | AWC | 2025-09-10 | A | 000925&&001674 | 2024-12-23, 2025-09-10 | 00 | 2 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9956 | 001675 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5340 | A | 131242-WST02-DR-I-5340-A | 2025-09-10 | SSN Instrument Hookup Drawing for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5340 | NA | "SSN Instrument Hookup Drawing for Radar Level Transmitter" && "Shop Drawing for Louvre Door and Window" | 2025-09-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-30 | 91 | AWC | 2025-11-12 | 0 | 001604&&001675 | 2025-09-10, 2025-11-12 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | AWC | AWC
9957 | 001675 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5341 | A | 131242-WST02-DR-I-5341-A | 2025-09-10 | SSN Instrument Hookup Drawing for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5341 | NA | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | 2025-09-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-30 | 91 | AWC | 2025-09-10 | A | 001675 | 2025-09-10 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9958 | 001675 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5342 | A | 131242-WST02-DR-I-5342-A | 2025-09-10 | SSN Instrument Hookup Drawing for Radar Level Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-08 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5342 | NA | "SSN Instrument Hookup Drawing for Radar Level Transmitter" | 2025-09-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-09-30 | 91 | AWC | 2025-09-10 | A | 001675 | 2025-09-10 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9959 | 001676 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | RT | Z | 0002 | 0 | 131242-WST02-RT-Z-0002-0 | 2025-09-11 | 80% SSN ALMOP Report | NA | 2025-10-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-RT-0002 | NA | "80% SSN ALMOP Report" && "Detailed Design Report – SSN PACKAGE" && "Project Safety Review for ERSS" && "Safety Review Report for Sitewide Pipe Rack" | 2024-05-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-09-25 | 207 | PEN | 2025-09-11 | 0 | 000489&&000723&&001131&&001676 | 2024-05-28, 2024-07-09, 2024-09-12, 2025-03-18, 2025-06-18, 2025-09-11 | 00, 01 | 6 | Approved | APP |  |  | 0 | PEN | PEN
9960 | 001677 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 1404 | 0 | 131242-WST02-QA-E-1404-0 | 2025-09-12 | Sample Board Submission for 40W Floodling Lighting | NA | 2025-10-10 | 2025-09-26 | Not Approved | 2025-10-16 | NO | Overdue |  | 131242-WST02-QA-1404 | NA | "Sample Board Submission for 40W Floodling Lighting" | 2025-09-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-02 | 14 | NAP | 2025-09-12 | 0 | 001677 | 2025-09-12 | 00 | 1 | Not Approved | NAP | 2025-10-16 | Overdue | 0 | NAP | NAP
9961 | 001678 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0120 | 0 | 131242-WSW41-QA-M-0120-0 | 2025-09-12 | FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH) | Rev 0: Approved | 2025-10-10 | 2025-12-15 | Approved |  | YES | NA |  | 131242-WSW41-QA-0120 | NA | "FAT Report for Diffuser System (Xylem)" && "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" | 2025-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-02 | 94 | APP | 2025-10-21 | 1 | 001678&&001684 | 2025-09-12, 2025-09-22, 2025-10-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | APP | APP
9962 | 001679 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0009 | 0 | 131242-WST02-QA-S-0009-0 | 2025-09-15 | ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-10-13 | 2025-10-29 | For Information |  | YES | NA |  | 131242-WST02-QA-0009 | NA | "FAT report for LV Power cable, Earth cable (Witnessed) CU/LSZH (AT,UV) SINGLE CORE EARTH CABLE (1C x 50mm2) CU/XLPE/LSZH/AWA/LSZH (AT,UV) (1C x 240mm2) CU/XLPE/LSZH/SWA/LSZH(AT,UV) POWER CABLE (3G x 4mm2) CU/XLPE/LSZH/CTS/LSZH (AT,UV) VSD CABLE (3C x 25mm2+3E x 10mm2) " && "ST619, PR-01 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Samples Submission for AAC Blocks & Sample Board Submission for Galvanized frame tie, PVC Corner bead, PVC Groove line, Galvanised U-Lintel, Corrugated Lintel, Self adhesive fiber mesh, Galvanised. Brick/Plaster mesh" | 2024-12-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-09-29 | 44 | INF | 2025-09-15 | 0 | 000873&&000901&&001679 | 2024-12-04, 2024-12-13, 2025-09-15 | 00 | 3 | For Information | INF | 2025-11-18 | Overdue | 0 | INF | INF
9963 | 001680 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | E | 0050 | 0 | 131242-WSD11-QA-E-0050-0 | 2025-09-16 | SAT Procedure for MCC Panels WSD11-MCC-0101A&B | Rev 0: Approved. | 2025-10-14 | 2025-10-06 | Approved |  | YES | NA |  | 131242-WSD11-QA-0050 | NA | "SAT Procedure for MCC Panels WSD11-MCC-0101A&B" | 2025-09-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-06 | 20 | APP | 2025-09-16 | 0 | 001680 | 2025-09-16 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
9964 | 001681 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0028 | 0 | 131242-WSW41-RT-PM-0028-0 | 2025-09-16 | C4B Monthly Progress Report Number No.28 (08 25) | NA | 2025-10-14 | 2025-09-26 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0028 | NA | "C4B Monthly Progress Report Number No.28 (08 25)" | 2025-09-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-06 | 10 | AWC | 2025-09-16 | 0 | 001681 | 2025-09-16 | 00 | 1 | Approved with Comments | AWC | 2025-10-16 | Overdue | 0 | AWC | AWC
9965 | 001682 | 00 | Aaron | CSA | NA | 131242 | NA | NA | NA | BCA_INST_ANNEX_E | 0 | 131242----BCA_INST_ANNEX_E- | 2025-09-17 | Annex E - ST601 & ST602 ERSS | For information | 2025-10-15 | 2025-10-06 | For Information |  | YES | NA |  | 131242-NA-NA-BCA_INST_ANNEX_E | NA | "Annex E - ST601 & ST602 ERSS" | 2025-09-17 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-10-07 | 19 | INF | 2025-09-17 | 0 | 001682 | 2025-09-17 | 00 | 1 | For Information | INF | 2025-10-24 | Overdue | 0 | INF | INF
9966 | 001683 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0051 | 0 | 131242-WST02-QA-E-0051-0 | 2025-09-18 | FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight) | Rev 0: Approved with comments. To revise and resubmit. | 2025-10-16 | 2025-10-06 | Approved with Comments | 2025-10-24 | NO | Overdue |  | 131242-WST02-QA-0051 | NA | "FAT Report for MDB Panels WST02-MDB-0001 A & B (Sunlight)" && "FAT Report for RIO Mock Up Panel " | 2025-09-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-02 | 18 | AWC | 2025-09-18 | 0 | 001651&&001683 | 2025-09-04, 2025-09-18 | 00 | 2 | Approved with Comments | AWC | 2025-10-24 | Overdue | 0 | AWC | AWC
9967 | 001684 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0120 | 0 | 131242-WSW41-QA-M-0120-0 | 2025-09-22 | FAT Report for Diffuser System (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-20 | 2025-10-06 | Approved with Comments | 2025-10-24 | YES | Resubmitted |  | 131242-WSW41-QA-0120 | NA | "FAT Report for Diffuser System (Xylem)" && "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" | 2025-09-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-06 | 14 | AWC | 2025-10-21 | 1 | 001678&&001684 | 2025-09-12, 2025-09-22, 2025-10-21 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9968 | 001684 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0120 | 1 | 131242-WSW41-QA-M-0120-1 | 2025-10-21 | FAT Report for Diffuser System (Xylem) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0120 | NA | "FAT Report for Diffuser System (Xylem)" && "FAT Report for Sampling Pump (Progressive Cavity Type) - (NETZSCH)" | 2025-09-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-11-04 | 167 | PEN | 2025-10-21 | 1 | 001678&&001684 | 2025-09-12, 2025-09-22, 2025-10-21 | 00, 01 | 3 | Approved with Comments | AWC | 2025-12-08 |  | 0 | PEN | PEN
9969 | 001685 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0022 | 0 | 131242-WST02-DS-I-0022-0 | 2025-09-23 | Datasheet for Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-10-23 | Approved with Comments | 2025-11-12 | YES | Resubmitted |  | 131242-WST02-DS-0022 | NA | "Datasheet for Thermal Flow Switch" | 2025-09-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 30 | AWC | 2026-01-15 | 1 | 001685 | 2025-09-23, 2026-01-15 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
9970 | 001685 | 01 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0022 | 1 | 131242-WST02-DS-I-0022-1 | 2026-01-15 | Datasheet for Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-0022 | NA | "Datasheet for Thermal Flow Switch" | 2025-09-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-29 | 81 | PEN | 2026-01-15 | 1 | 001685 | 2025-09-23, 2026-01-15 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-04 |  | 0 | PEN | PEN
9971 | 001686 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0071 | 0 | 131242-WSW41-LT-PM-0071-0 | 2025-09-23 | Request for Deferment of Liquidated Damages – Contract Milestone 4 (CM4: Pre-Commissioning Test for Digestion Pre-treatment Facility, Sidestream Nitrogen Removal Facility and Pipe Rack) (5 Oct 2025) | Rev (0): Received for information. Please refer to S.O. correspondence no. 407 dated 3 Oct 25. | 2025-10-21 | 2025-10-15 | For Information |  | YES | NA |  | 131242-WSW41-LT-0071 | NA | "Request for Deferment of Liquidated Damages – Contract Milestone 4 (CM4: Pre-Commissioning Test for Digestion Pre-treatment Facility, Sidestream Nitrogen Removal Facility and Pipe Rack) (5 Oct 2025) " | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 22 | INF | 2025-09-23 | 0 | 001686 | 2025-09-23 | 00 | 1 | For Information | INF | 2025-11-04 | Overdue | 0 | INF | INF
9972 | 001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5490 | A | 131242-WST02-DR-I-5490-A | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5490 | NA | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 78 | AWC | 2025-09-23 | A | 001687 | 2025-09-23 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9973 | 001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5491 | A | 131242-WST02-DR-I-5491-A | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5491 | NA | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 78 | AWC | 2025-09-23 | A | 001687 | 2025-09-23 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9974 | 001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5492 | A | 131242-WST02-DR-I-5492-A | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5492 | NA | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 78 | AWC | 2025-09-23 | A | 001687 | 2025-09-23 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9975 | 001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5493 | A | 131242-WST02-DR-I-5493-A | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5493 | NA | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 78 | AWC | 2025-09-23 | A | 001687 | 2025-09-23 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9976 | 001687 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5494 | A | 131242-WST02-DR-I-5494-A | 2025-09-23 | Hookup Drawing -Thermal Flow Switch | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-21 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5494 | NA | "Hookup Drawing -Thermal Flow Switch" | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 78 | AWC | 2025-09-23 | A | 001687 | 2025-09-23 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9977 | 001688 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0070 | 0 | 131242-WSW41-LT-PM-0070-0 | 2025-09-23 | Notice for Extension of Time and Cost for Delays in Site Wide Pipe Rack Approvals for ST 603-621 Submissions Amongst Other Delays | Rev (0): Rejected. Please refer to S.O. correspondence no. 435 dated 13 Feb 2026. | 2025-10-21 | 2026-02-24 | Rejected |  | YES | NA |  | 131242-WSW41-LT-0070 | NA | "Notice for Extension of Time and Cost for Delays in Site Wide Pipe Rack Approvals for ST 603-621 Submissions Amongst Other Delays" | 2025-09-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 154 | REJ | 2025-09-23 | 0 | 001688 | 2025-09-23 | 00 | 1 | Rejected | REJ | 2026-03-16 | Overdue | 0 | REJ | REJ
9978 | 001689 | 00 | Danny | QAQC | NA | 131242 | WSW41 | QA | M | 0115 | 0 | 131242-WSW41-QA-M-0115-0 | 2025-09-24 | FAT Report for Manual Knife Gate Valves - Batch 3 (JASH) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-10-22 | 2026-01-30 | Approved with Comments |  | YES | NA |  | 131242-WSW41-QA-0115 | NA | "FAT Report for Manual Knife Gate Valves - Batch 3 (JASH)" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-14 | 128 | AWC | 2025-09-24 | 0 | 001689 | 2025-09-24 | 00 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
9979 | 001690 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0009 | 0 | 131242-WST02-VI-A-0009-0 | 2025-09-24 | Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd. | Approved | 2025-10-22 | 2025-10-13 | Approved |  | YES | NA |  | 131242-WST02-VI-0009 | NA | "Vendor Approval of Chequered Plate and Grating – Wan Sern Metal Industries Pte. Ltd." && "Vendor Approval of LPS Materials (Skypro_DEHN)" && "Vendor Approval of SSN Package (Radar Level Transmitter)" | 2024-05-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-08 | 19 | APP | 2025-09-24 | 0 | 000459&&000730&&001690 | 2024-05-02, 2024-07-30, 2024-09-18, 2024-10-14, 2025-02-27, 2025-09-24 | 00, 01, 02 | 6 | Approved | APP |  |  | 0 | APP | APP
9980 | 001691 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5480 | A | 131242-WST02-DR-I-5480-A | 2025-09-24 | Hookup Drawing - Hydrostatic Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-5480 | NA | "Hookup Drawing - Hydrostatic Level Switch" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 78 | NAP | 2025-09-24 | A | 001691 | 2025-09-24 | 00 | 1 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
9981 | 001691 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5481 | A | 131242-WST02-DR-I-5481-A | 2025-09-24 | Hookup Drawing - Hydrostatic Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-5481 | NA | "Hookup Drawing - Hydrostatic Level Switch" && "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-08 | 78 | NAP | 2025-09-24 | A | 001123&&001691 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, 01 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
9982 | 001691 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5482 | A | 131242-WST02-DR-I-5482-A | 2025-09-24 | Hookup Drawing - Hydrostatic Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-5482 | NA | "Hookup Drawing - Hydrostatic Level Switch" && "Hyperbolic Mixer GA, rain cover, exploded view and nameplate Drawings" | 2025-03-13 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-08 | 78 | NAP | 2025-09-24 | A | 001123&&001691 | 2025-03-13, 2025-07-07, 2025-09-24 | 00, 01 | 3 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
9983 | 001692 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0012 | 0 | 131242-WST02-DS-I-0012-0 | 2025-09-24 | Datasheet for Pressure Transmitter (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-10-23 | Approved with Comments | 2025-11-12 | NO | Overdue |  | 131242-WST02-DS-0012 | NA | "Datasheet for Pressure Transmitter (SSN)" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 29 | AWC | 2025-09-24 | 0 | 001692 | 2025-09-24 | 00 | 1 | Approved with Comments | AWC | 2025-11-12 | Overdue | 0 | AWC | AWC
9984 | 001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5310 | A | 131242-WST02-DR-I-5310-A | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5310 | NA | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 77 | AWC | 2025-09-24 | A | 001693 | 2025-09-24 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9985 | 001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5311 | A | 131242-WST02-DR-I-5311-A | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5311 | NA | "GA Drawing for Centrifugal Pump" && "Hookup Drawing for Pressure Transmitter" | 2024-11-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-08 | 77 | AWC | 2025-09-24 | A | 000798&&001693 | 2024-11-04, 2025-04-17, 2025-09-24 | 00, 01 | 3 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9986 | 001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5312 | A | 131242-WST02-DR-I-5312-A | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5312 | NA | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 77 | AWC | 2025-09-24 | A | 001693 | 2025-09-24 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9987 | 001693 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5313 | A | 131242-WST02-DR-I-5313-A | 2025-09-24 | Hookup Drawing for Pressure Transmitter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WST02-DR-5313 | NA | "Hookup Drawing for Pressure Transmitter" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 77 | AWC | 2025-09-24 | A | 001693 | 2025-09-24 | 00 | 1 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
9988 | 001694 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0021 | 0 | 131242-WST02-DS-I-0021-0 | 2025-09-24 | Datasheet for Pressure Switch (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-22 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DS-0021 | NA | "Datasheet for Pressure Switch (SSN)" | 2025-09-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 82 | AWC | 2025-09-24 | 0 | 001694 | 2025-09-24 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
9989 | 001695 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0121 | 0 | 131242-WSW41-QA-M-0121-0 | 2025-09-25 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-10-23 | 2026-01-07 | Not Approved | 2026-01-27 | YES | Resubmitted |  | 131242-WSW41-QA-0121 | NA | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | 2025-09-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 104 | NAP | 2026-01-27 | 1 | 001695&&001696 | 2025-09-25, 2026-01-27 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9990 | 001695 | 01 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0121 | 1 | 131242-WSW41-QA-M-0121-1 | 2026-01-27 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0121 | NA | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | 2025-09-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | 1 | 001695&&001696 | 2025-09-25, 2026-01-27 | 00, 01 | 3 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
9991 | 001696 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0121 | 0_Withdraw | 131242-WSW41-QA-M-0121-0_Withdraw | 2025-09-25 | FAT Report for Actuated Butterfly Valves (OVS/Rotork) | Contractor request to VOID due to duplication of submission | 2025-10-23 | 2025-10-01 | (VOID / NOT IN USE) |  | YES | NA |  | 131242-WSW41-QA-0121 | NA | "FAT Report for Actuated Butterfly Valves (OVS/Rotork) " | 2025-09-25 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Review_Status not in approval_code_schema | 2025-10-15 | 6 | VOID | 2026-01-27 | 1 | 001695&&001696 | 2025-09-25, 2026-01-27 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | VOID | VOID
9992 | 001697 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0122 | 0 | 131242-WSW41-QA-M-0122-0 | 2025-09-25 | FAT Report for Actuated Ball Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-10-23 | 2026-01-07 | Not Approved | 2026-01-27 | YES | Resubmitted |  | 131242-WSW41-QA-0122 | NA | "FAT Report for Actuated Ball Valves (OVS/Rotork)" | 2025-09-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 104 | NAP | 2026-01-27 | 1 | 001697 | 2025-09-25, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
9993 | 001697 | 01 | Soe Myat | QAQC | NA | 131242 | WSW41 | QA | M | 0122 | 1 | 131242-WSW41-QA-M-0122-1 | 2026-01-27 | FAT Report for Actuated Ball Valves (OVS/Rotork) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0122 | NA | "FAT Report for Actuated Ball Valves (OVS/Rotork)" | 2025-09-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | 1 | 001697 | 2025-09-25, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
9994 | 001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.1 | 131242-WST02-SD-S-8600-A.1 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-10 | 45 | NAP | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
9995 | 001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1007 | A.1 | 131242-WST02-SD-S-1007-A.1 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-SD-1007 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " | 2025-08-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-10 | 45 | NAP | 2026-02-09 | A.5 | 001616&&001698&&001803 | 2025-08-22, 2025-09-26, 2026-02-09 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9996 | 001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5003 | A.1 | 131242-WST02-SD-S-5003-A.1 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-SD-5003 | NA | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " | 2025-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-10 | 45 | NAP | 2026-02-09 | A.5 | 001498&&001698&&001803 | 2025-07-22, 2025-09-26, 2026-02-09 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
9997 | 001698 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5004 | A.1 | 131242-WST02-SD-S-5004-A.1 | 2025-09-26 | Shop drawing for Cat ladders at SSN Area and Electrical Building | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-24 | 2025-11-10 | Not Approved | 2025-11-28 | NO | Overdue |  | 131242-WST02-SD-5004 | NA | "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-09-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-16 | 45 | NAP | 2026-02-09 | A.5 | 001698&&001700&&001803 | 2025-09-26, 2025-09-29, 2026-02-09 | 00, 01 | 3 | Rejected | REJ |  |  | 0 | NAP | NAP
9998 | 001699 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | S | 0010 | 0 | 131242-WST02-QA-S-0010-0 | 2025-09-26 | ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission | For information | 2025-10-24 | 2025-10-13 | For Information |  | YES | NA |  | 131242-WST02-QA-0010 | NA | "FAT report for Earth cable, LV Power cable (Unwitnessed)" && "Material Submission PC Vent Block with Netting (Wet Cast) (Wet Trade - Huayu Construction Pte Ltd)" && "ST617, PF-02 IRN, Materials Testing, Fit-Up, Welding, NDT, Galvanize and Painting Report Submission" && "Vendor Manufacturing Inspection Test Plan for ACMV Installation Works (Building Services)" | 2024-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-10 | 17 | INF | 2025-09-26 | 0 | 000913&&000935&&001424&&001699 | 2024-12-18, 2024-12-31, 2025-07-02, 2025-09-26 | 00 | 4 | For Information | INF | 2025-10-31 | Overdue | 0 | INF | INF
9999 | 001700 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1009 | A | 131242-WST02-SD-S-1009-A | 2025-09-29 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | Rejected as per CES's request. | 2025-10-27 | 2025-10-14 | Rejected |  | YES | NA |  | 131242-WST02-SD-1009 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-08-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 15 | REJ | 2025-09-29 | A | 001616&&001700 | 2025-08-22, 2025-09-29 | 00 | 2 | Rejected | REJ | 2025-11-03 | Overdue | 0 | REJ | REJ
10000 | 001700 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5004 | A | 131242-WST02-SD-S-5004-A | 2025-09-29 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | Rejected as per CES's request. | 2025-10-27 | 2025-10-14 | Rejected |  | YES | NA |  | 131242-WST02-SD-5004 | NA | "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-09-26 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 15 | REJ | 2026-02-09 | A.5 | 001698&&001700&&001803 | 2025-09-26, 2025-09-29, 2026-02-09 | 00, 01 | 3 | Rejected | REJ |  |  | 0 | REJ | REJ
10001 | 001700 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A | 131242-WST02-SD-S-8600-A | 2025-09-29 | Shop drawing for Retractable Cat Ladders for JMH 001 & 002 | Rejected as per CES's request. | 2025-10-27 | 2025-10-14 | Rejected |  | YES | NA |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-13 | 15 | REJ | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10002 | 001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3030 | A | 131242-WSD11-DR-IC-3030-A | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-DR-3030 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10003 | 001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3031 | A | 131242-WSD11-DR-IC-3031-A | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-DR-3031 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10004 | 001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3032 | A | 131242-WSD11-DR-IC-3032-A | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-DR-3032 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10005 | 001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3033 | A | 131242-WSD11-DR-IC-3033-A | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-DR-3033 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10006 | 001701 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IC | 3034 | A | 131242-WSD11-DR-IC-3034-A | 2025-09-29 | THP PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WSD11-DR-3034 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP PMS Panel GA and Wiring Diagram" | 2025-05-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-11-28 | A | 000292&&001701 | 2025-05-09, 2025-09-29, 2025-11-28 | 00, 02, 03 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10007 | 001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3030 | A | 131242-WST02-DR-IC-3030-A | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10008 | 001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3031 | A | 131242-WST02-DR-IC-3031-A | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10009 | 001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3032 | A | 131242-WST02-DR-IC-3032-A | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WST02-DR-3032 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-10-27 | Overdue | 0 | AWC | AWC
10010 | 001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3033 | A | 131242-WST02-DR-IC-3033-A | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WST02-DR-3033 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-09-29 | A | 000163&&000870&&001702 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2025-10-27 | Overdue | 0 | AWC | AWC
10011 | 001702 | 00 | Balaji | EICA | NA | 131242 | WST02 | DR | IC | 3034 | A | 131242-WST02-DR-IC-3034-A | 2025-09-29 | SSN PMS Panel GA and Wiring Diagram | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-10-27 | 2025-10-07 | Approved with Comments | 2025-10-27 | NO | Overdue |  | 131242-WST02-DR-3034 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 8 | AWC | 2025-09-29 | A | 000870&&001702 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-09-29 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2025-10-27 | Overdue | 0 | AWC | AWC
10012 | 001703 | 00 | Liying | Mech | NA | 131242 | WSW41 | DR | M | 5351 | 0 | 131242-WSW41-DR-M-5351-0 | 2025-09-29 | SP Item - Flange Adaptor (Synchong Hoe) | NA | 2025-10-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-5351 | NA | "SP Item - Flange Adaptor (Synchong Hoe)" | 2025-09-29 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-10-19 | 189 | PEN | 2025-09-29 | 0 | 001703 | 2025-09-29 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-11-14 |  | 0 | PEN | PEN
10013 | 001704 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0052 | 0 | 131242-WST02-QA-E-0052-0 | 2025-09-29 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss) | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-27 | 2025-10-15 | Approved with Comments | 2025-11-04 | NO | Overdue |  | 131242-WST02-QA-0052 | NA | " Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Aeration Blower A,B,C,D,E Harmonic Filter Panel (Danfoss)" && "FAT Report for PLC Mock Up Panel " | 2025-09-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-13 | 16 | AWC | 2025-09-29 | 0 | 001652&&001704 | 2025-09-04, 2025-09-29 | 00 | 2 | Approved with Comments | AWC | 2025-11-04 | Overdue | 0 | AWC | AWC
10014 | 001705 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0056 | 0 | 131242-WST02-QA-I-0056-0 | 2025-09-30 | Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-10-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-QA-0056 | NA | " Vendor Manufacturing Inspection Test Plan for NH4 Analyser / N02 Analyser / N03 Analyser (SSN)" && "FAT procedure for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-03-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 72 | NAP | 2025-09-30 | 0 | 001096&&001705 | 2025-03-06, 2025-09-30 | 00 | 2 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
10015 | 001706 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0123 | 0 | 131242-WSW41-QA-M-0123-0 | 2025-09-30 | FAT Report for Clamp Shoe Support, Stopper Support In Site Wide Pipe Rack | Rev 0: Approved | 2025-10-28 | 2026-01-30 | Approved |  | YES | NA |  | 131242-WSW41-QA-0123 | NA | "FAT Report for Clamp Shoe Support, Stopper Support In Site Wide Pipe Rack" | 2025-09-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-20 | 122 | APP | 2025-09-30 | 0 | 001706 | 2025-09-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10016 | 001707 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0124 | 0 | 131242-WSW41-QA-M-0124-0 | 2025-09-30 | FAT Report for Clamp Shoe Support in Site Wide Pipe Rack | Rev 0: Approved | 2025-10-28 | 2026-01-30 | Approved |  | YES | NA |  | 131242-WSW41-QA-0124 | NA | "FAT Report for Clamp Shoe Support in Site Wide Pipe Rack" | 2025-09-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-20 | 122 | APP | 2025-09-30 | 0 | 001707 | 2025-09-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10017 | 001708 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0044 | 0 | 131242-WSW41-QA-C-0044-0 | 2025-09-30 | Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025 | For information | 2025-10-28 | 2025-10-13 | For Information |  | YES | NA |  | 131242-WSW41-QA-0044 | NA | " Issue for Information-Monthly Concrete Cube Records for Structural Works for Aug 2025" && "Inspection and Test Plan for Pipe Support fabrication and Installation (CS Channel, SS Unistrut) - Cyclect Engineering Pte Ltd " | 2025-01-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-14 | 13 | INF | 2025-09-30 | 0 | 000985&&001708 | 2025-01-17, 2025-09-30 | 00 | 2 | For Information | INF | 2025-10-31 | Overdue | 0 | INF | INF
10018 | 001709 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | I | 0021 | 0 | 131242-WSW41-PO-I-0021-0 | 2025-09-30 | Unpriced PO for PDB & LCP (GSM) | Rev 0: For Information | 2025-10-28 | 2025-12-11 | For Information |  | YES | NA |  | 131242-WSW41-PO-0021 | NA | "Unpriced PO for PDB & LCP (GSM) " && "Unpriced PO for Temperature Transmitter (Endress & Hauser)" | 2025-07-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-14 | 72 | INF | 2025-09-30 | 0 | 001511&&001709 | 2025-07-22, 2025-09-30 | 00 | 2 | For Information | INF | 2025-12-31 | Overdue | 0 | INF | INF
10019 | 001710 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | E | 0029 | 0 | 131242-WSW41-PO-E-0029-0 | 2025-09-30 | Unpriced PO for Earthing Material (Heng Hardware) | For Information | 2025-10-28 | 2025-11-05 | For Information |  | YES | NA |  | 131242-WSW41-PO-0029 | NA | "Unpriced PO for Earthing Material (Heng Hardware) " | 2025-09-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-20 | 36 | INF | 2025-09-30 | 0 | 001710 | 2025-09-30 | 00 | 1 | For Information | INF | 2025-11-25 | Overdue | 0 | INF | INF
10020 | 001711 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | E | 0028 | 0 | 131242-WSW41-PO-E-0028-0 | 2025-09-30 | Unpriced PO for Power and Lighting Material (Hong An Engineering) | For information | 2025-10-28 | 2025-11-10 | For Information |  | YES | NA |  | 131242-WSW41-PO-0028 | NA | "Unpriced PO for Power and Lighting Material (Hong An Engineering)" | 2025-09-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-20 | 41 | INF | 2025-09-30 | 0 | 001711 | 2025-09-30 | 00 | 1 | For Information | INF | 2025-11-28 | Overdue | 0 | INF | INF
10021 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0011 | 0 | 131242-WSW41-QA-N-0011-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0011 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for April 2024" && "Procedure for Welding of Underground HDPE Pipe" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for Lan Cables (Keystone) " | 2024-08-07 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000627&&000657&&001264&&001636&&001712 | 2024-08-07, 2024-08-19, 2025-05-02, 2025-09-30, 2026-01-28 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10022 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0012 | 0 | 131242-WSW41-QA-N-0012-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0012 | NA | "FAT Report for Power Cable, Control Cable, MV Cable" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection test plan and FAT procedure for F/FTP CAT.6 ARMOUR Lan Cables (Keystone)" | 2024-12-31 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000936&&001304&&001636&&001712 | 2024-12-31, 2025-05-18, 2025-09-30, 2026-01-28 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10023 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0013 | 0 | 131242-WSW41-QA-N-0013-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0013 | NA | "FAT report for SS Unistrut Support, Accessories (HDMANN) " && "Materials Submission – Lite.Mix ALC joint Adhesive ECO for AAC blocks (Wet trade – Huayu Construction Pte ltd)" && "Monthly Concrete Cube Records for Structural works for Apr 2024 " && "Monthly Concrete Cube Records for Structural works for May 2024 " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Progressive Cavity Pump (NETZSCH) " && "Vendor Manufacturing Inspection Test Plan for Radar Level Transmitter" | 2024-08-22 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000670&&000691&&000970&&000999&&001313&&001636&&001712 | 2024-08-22, 2024-08-27, 2024-08-31, 2025-01-13, 2025-01-24, 2025-04-17, 2025-05-20, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10024 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0014 | 0 | 131242-WSW41-QA-N-0014-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0014 | NA | "FAT Report for Radar Level Transmitter 1st Batch " && "FAT report for SS Cable Ladder, Cable Tray, Accessories 2nd batch (United ULI)" && "Materials Submission for roof waterproofing, Nippon Proof seal 1102, Unifoam, Geonic 105, BRC 3315, Zota M150 & World brand 200 Adhesive (G-Concept Construction Pte Ltd) " && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan and FAT procedure for Hyperbolic Mixer (ENTEC INTERNATIONAL)" | 2024-10-02 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000741&&000971&&000998&&001336&&001636&&001712 | 2024-10-02, 2025-01-13, 2025-01-22, 2025-03-10, 2025-03-18, 2025-05-30, 2025-07-22, 2025-09-30, 2026-01-28 | 00, 01 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10025 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0015 | 0 | 131242-WSW41-QA-N-0015-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0015 | NA | "FAT Procedure for Fine Bubble Air Diffuser system (XYLEM)" && "Plate Load test report " && "T&C Check List " && "Testing Check List (Process)" | 2024-08-29 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000682&&000694&&001636&&001712 | 2024-08-29, 2024-09-02, 2024-10-30, 2025-03-27, 2025-09-30, 2026-01-28 | 00, 01 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10026 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0016 | 0 | 131242-WSW41-QA-N-0016-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0016 | NA | "ITP for Lightning Protection System Installation" && "Materials Catalogue Submission for Siphonic System (Fast Flow Singapore Pte Ltd)" && "Mock-up Temperature Monitoring Test Reports (Alliance)" && "Monthly Concrete Cube Records for Structural works for July 2024" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for Stainless Steel Welded pipe, Seamless pipe & fittings, Flange & Forged fittings and Plate " && "Vendor Manufacturing Inspection test plan and FAT procedure for Aeration Blower MCP and PLC panel (Fox)" | 2024-08-31 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000693&&000724&&000734&&001014&&001022&&001340&&001636&&001712 | 2024-08-31, 2024-09-16, 2024-09-20, 2025-01-26, 2025-02-06, 2025-03-14, 2025-06-03, 2025-08-25, 2025-09-30, 2026-01-28 | 00, 01 | 10 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10027 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0017 | 0 | 131242-WSW41-QA-N-0017-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0017 | NA | "FAT Report for ELV Control Cable, ELV Signal Cable, LAN Cable, FO Cable" && "Inspection and test plan for Indoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Mock-up Temperature Monitoring Test Reports - G40 (Pan U)" && "T&C Check List " && "Testing Check List (Process)" && "Vendor Manufacturing Inspection Test Plan for SSN Package (Lamella Clarifier, Biomass Separator) (Matten Plant) " | 2024-09-20 | YES | NO | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2026-01-28 | 0 | 000733&&000747&&001056&&001342&&001636&&001712 | 2024-09-20, 2024-10-08, 2025-02-18, 2025-03-06, 2025-06-03, 2025-09-30, 2026-01-28 | 00, 01 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10028 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0018 | 0 | 131242-WSW41-QA-N-0018-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0018 | NA | " Vendor Manufacturing Inspection test plan for Side Manway " && "Inspection and test plan for Outdoor Cable Support System Installation (Cyclect Electrical engineering pte Ltd)" && "Materials Submission - Floor self levelling for SSN Electrical buildings & Grout materials for Patching works" && "Mock-up Temperature Monitoring Test Reports – G45 (Pan U)" && "T&C Check List " && "Vendor Manufacturing Inspection test plan for Electromagnetic Flow Transmitter" | 2024-10-04 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2025-09-30 | 0 | 000744&&000757&&001054&&001057&&001339&&001357&&001712 | 2024-10-04, 2024-10-11, 2024-10-30, 2025-02-18, 2025-06-03, 2025-06-12, 2025-09-30 | 00, 01 | 8 | Approved with Comments | AWC | 2026-01-13 | Overdue | 0 | AWC | AWC
10029 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0019 | 0 | 131242-WSW41-QA-N-0019-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0019 | NA | "Factory Acceptance Test Report for Electromagnetic Flowmeter Transmitter" && "Monthly Concrete Cube Records for Structural works for August 2024" && "T&C Check List " && "Vendor Manufacturing Inspection Test Plan for Structural Steel works fabrication and installation (Sanhe Construction Pte Ltd)" | 2024-09-28 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2025-09-30 | 0 | 000738&&000814&&001343&&001712 | 2024-09-28, 2024-11-14, 2025-06-04, 2025-09-30 | 00 | 4 | Approved with Comments | AWC | 2026-01-13 | Overdue | 0 | AWC | AWC
10030 | 001712 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | QA | N | 0020 | 0 | 131242-WSW41-QA-N-0020-0 | 2025-09-30 | T&C Check List | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-10-28 | 2025-12-24 | Approved with Comments | 2026-01-13 |  | Overdue |  | 131242-WSW41-QA-0020 | NA | "Monthly Concrete Cube Records for Structural works for September 2024" && "Side Manway manufacturer’s WPS/PQR, Test procedures, ITA, Welder qualification records, WQT" && "T&C Check List " | 2024-10-11 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-14 | 85 | AWC | 2025-09-30 | 0 | 000756&&000830&&001712 | 2024-10-11, 2024-11-21, 2025-09-30 | 00 | 3 | Approved with Comments | AWC | 2026-01-13 | Overdue | 0 | AWC | AWC
10031 | 001713 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5753 | 0 | 131242-WST02-DS-M-5753-0 | 2025-09-30 | Data Sheet for SSN Sludge Comparment Mixing Nozzle | NA | 2025-10-28 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5753 | NA | "Data Sheet for SSN Sludge Comparment Mixing Nozzle" | 2025-09-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-10-20 | 188 | PEN | 2025-09-30 | 0 | 001713 | 2025-09-30 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-11-17 |  | 0 | PEN | PEN
10032 | 001714 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | QA | N | 0300 | 0 | 131242-WSD11-QA-N-0300-0 | 2025-09-30 | Commissioning Plan for Steam Line | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-10-28 | 2026-01-06 | Not Approved | 2026-01-26 | YES | Resubmitted |  | 131242-WSD11-QA-0300 | NA | "Commissioning Plan for Steam Line" | 2025-09-30 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-20 | 98 | NAP | 2025-09-30 | 0 | 001714 | 2025-09-30 | 00 | 1 | Not Approved | NAP | 2026-01-26 | Overdue | 0 | NAP | NAP
10033 | 001715 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DS | M | 0047 | 0 | 131242-WSD11-DS-M-0047-0 | 2025-09-30 | Data Sheet for THP IA Pressure Reducing Valve | Rev 0: Approved | 2025-10-28 | 2025-10-21 | Approved |  | YES | NA |  | 131242-WSD11-DS-0047 | NA | "Data Sheet for THP IA Pressure Reducing Valve " | 2025-09-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-20 | 21 | APP | 2025-09-30 | 0 | 001715 | 2025-09-30 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10034 | 001716 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0072 | 0 | 131242-WSW41-LT-PM-0072-0 | 2025-09-30 | Extension of Time – CM4 Milestone | NA | 2025-10-28 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0072 | NA | "Extension of Time – CM4 Milestone " | 2025-09-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-10-20 | 188 | PEN | 2025-09-30 | 0 | 001716 | 2025-09-30 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-11-17 |  | 0 | PEN | PEN
10035 | 001717 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0054 | 0 | 131242-WST02-QA-I-0054-0 | 2025-10-01 | FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-29 | 2026-02-16 | Approved with Comments | 2026-03-06 | NO | Overdue |  | 131242-WST02-QA-0054 | NA | "FAT Report for MDB Panels WST02-MDB-1001 A & B (Sunlight)" && "Vendor Manufacturing Inspection Test Plan for Rotameter " | 2025-09-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 138 | AWC | 2025-10-01 | 0 | 001650&&001717 | 2025-09-04, 2025-10-01 | 00 | 2 | Approved with Comments | AWC | 2026-03-06 | Overdue | 0 | AWC | AWC
10036 | 001718 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | EI | 0053 | 0 | 131242-WST02-QA-EI-0053-0 | 2025-10-01 | SAT Procedure for MDB Panels (Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-29 | 2025-11-25 | Approved with Comments | 2025-12-15 | NO | Overdue |  | 131242-WST02-QA-0053 | NA | "FAT Report for FFOTP Mock Up Panel" && "SAT Procedure for MDB Panels (Sunlight)" | 2025-09-04 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 55 | AWC | 2025-10-01 | 0 | 001653&&001718 | 2025-09-04, 2025-10-01 | 00 | 2 | Approved with Comments | AWC | 2025-12-15 | Overdue | 0 | AWC | AWC
10037 | 001719 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0010 | 0 | 131242-WST02-VI-A-0010-0 | 2025-10-01 | Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-29 | 2025-10-08 | Not Approved | 2025-10-28 | NO | Overdue |  | 131242-WST02-VI-0010 | NA | "Vendor Approval of Aluminium Handrail and Cat Ladder Fabricator and Installer – Sanhe Construction Pte. Ltd." && "Vendor Approval of Metal Roofing and Cladding – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Tuning Fork Level Switches)" | 2024-05-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 7 | NAP | 2025-10-01 | 0 | 000462&&001082&&001719 | 2024-05-07, 2024-08-01, 2025-02-27, 2025-03-03, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP | 2025-10-28 | Overdue | 0 | NAP | NAP
10038 | 001720 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0011 | 0 | 131242-WST02-VI-A-0011-0 | 2025-10-01 | Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-10-29 | 2025-10-08 | Not Approved | 2025-10-28 | NO | Overdue |  | 131242-WST02-VI-0011 | NA | "Vendor Approval - 2" UPVC Pipe and Fittings (VicPlas)" && "Vendor Approval of Metal Coping and Flashing – CM Metal Pte. Ltd." && "Vendor Approval of SSN Package (Electromagnetic Flowmeters)" | 2024-05-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-15 | 7 | NAP | 2025-10-01 | 0 | 000463&&000711&&001720 | 2024-05-07, 2024-07-24, 2024-09-06, 2024-11-09, 2025-10-01 | 00, 01, 02 | 5 | Not Approved | NAP | 2025-10-28 | Overdue | 0 | NAP | NAP
10039 | 001721 | 00 | NA | Mech | NA | 131242 | WSD11 | CL | M | 1087 | 0 | 131242-WSD11-CL-M-1087-0 | 2025-10-03 | G2D Line Surge Load Calculation Report | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-10-31 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSD11-CL-1087 | NA | "G2D Line Surge Load Calculation Report " | 2025-10-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-23 | 119 | AWC | 2025-10-03 | 0 | 001721 | 2025-10-03 | 00 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
10040 | 001722 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0126 | 0 | 131242-WSW41-QA-M-0126-0 | 2025-10-06 | FAT Report for & Operating Instructions for Air Flow Control Valve (Effektiv/Emile Egger & Cie SA) | Rev 0: Approved | 2025-11-03 | 2025-10-22 | Approved |  | YES | NA |  | 131242-WSW41-QA-0126 | NA | "FAT Report for & Operating Instructions for Air Flow Control Valve (Effektiv/Emile Egger & Cie SA)" | 2025-10-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-26 | 16 | APP | 2025-10-06 | 0 | 001722 | 2025-10-06 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10041 | 001723 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0028 | 0 | 131242-WSW41-QA-A-0028-0 | 2025-10-06 | SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team) | Rev 0: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-03 | 2025-10-13 | Approved with Comments | 2025-10-31 | NO | Overdue |  | 131242-WSW41-QA-0028 | NA | "FAT report for SS Cable Ladder Cover, Cable Tray Cover 5th batch (United ULI)" && "SSN Electrical Building & SSN Watertank (External & Internal) Painting System Material Submission(ISO-Team)" && "Test Report submission for SS Anchor rod, Washer & Nut (THP feed pumps, Ring circulation pumps & Air compressor pipe supports)" | 2025-03-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-20 | 7 | AWC | 2025-10-06 | 0 | 001138&&001239&&001723 | 2025-03-20, 2025-04-21, 2025-10-06 | 00 | 3 | Approved with Comments | AWC | 2025-10-31 | Overdue | 0 | AWC | AWC
10042 | 001724 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | EI | 0055 | 0 | 131242-WSD11-QA-EI-0055-0 | 2025-10-06 | FAT Report for MCC Panels WSD11-MCC-0001 A & B (Sunlight) | Rev 0: Not approved - Revise and Resubmit | 2025-11-03 | 2026-02-09 | Not Approved | 2026-02-27 | NO | Overdue |  | 131242-WSD11-QA-0055 | NA | "FAT Report for MCC Panels WSD11-MCC-0001 A & B (Sunlight)" | 2025-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-26 | 126 | NAP | 2025-10-06 | 0 | 001724 | 2025-10-06 | 00 | 1 | Not Approved | NAP | 2026-02-27 | Overdue | 0 | NAP | NAP
10043 | 001725 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | I | 0058 | 0 | 131242-WSD11-QA-I-0058-0 | 2025-10-06 | Factory Acceptance Test Report for Electromagnetic Flow Transmitter (THP) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-03 | 2025-12-10 | Not Approved | 2025-12-30 | NO | Overdue |  | 131242-WSD11-QA-0058 | NA | "Factory Acceptance Test Report for Electromagnetic Flow Transmitter (THP)" | 2025-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-26 | 65 | NAP | 2025-10-06 | 0 | 001725 | 2025-10-06 | 00 | 1 | Not Approved | NAP | 2025-12-30 | Overdue | 0 | NAP | NAP
10044 | 001726 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | I | 0057 | 0 | 131242-WSD11-QA-I-0057-0 | 2025-10-06 | Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-03 | 2025-12-10 | Approved with Comments | 2025-12-30 | NO | Overdue |  | 131242-WSD11-QA-0057 | NA | "FAT procedure for SSN ARS/Lamella Clarifier (Matten Plant) " && "Vendor Manufacturing Inspection Test Plan for Electromagnetic Flow Transmitter (THP)" | 2025-03-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-20 | 65 | AWC | 2025-10-06 | 0 | 001116&&001726 | 2025-03-12, 2025-10-06 | 00 | 2 | Approved with Comments | AWC | 2025-12-30 | Overdue | 0 | AWC | AWC
10045 | 001727 | 00 | Dhanapal | QAQC | NA | 131242 | WSD11 | QA | E | 0056 | 0 | 131242-WSD11-QA-E-0056-0 | 2025-10-06 | SAT Report for WSD11-MCC-0101A & WSD11-MCC-0101B | Rev 0: Rejected. Refer to attached file for comments. | 2025-11-03 | 2026-02-09 | Rejected | 2026-02-27 | NO | Overdue |  | 131242-WSD11-QA-0056 | NA | "SAT Report for WSD11-MCC-0101A & WSD11-MCC-0101B" | 2025-10-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-26 | 126 | REJ | 2025-10-06 | 0 | 001727 | 2025-10-06 | 00 | 1 | Rejected | REJ | 2026-02-27 | Overdue | 0 | REJ | REJ
10046 | 001728 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | ST617 THP-PF-02 Fab | 0 | 131242-WSD11-DR-S-ST617 THP-PF-02 Fab- | 2025-10-08 | ST617 THP-PF-02 Fabrication Drawing (PE Endorsed) | For Information | 2025-11-05 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSD11-DR-ST617 THP-PF-02 Fab | NA | "ST617 THP-PF-02 Fabrication Drawing (PE Endorsed)" | 2025-10-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-10-28 | 47 | INF | 2025-10-08 | 0 | 001728 | 2025-10-08 | 00 | 1 | For Information | INF | 2025-12-12 | Overdue | 0 | INF | INF
10047 | 001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1600_ST611 | A | 131242-WST02-DR-S-1600_ST611-A | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-1600_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10048 | 001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1601_ST611 | A | 131242-WST02-DR-S-1601_ST611-A | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-1601_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10049 | 001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1607_ST611 | A | 131242-WST02-DR-S-1607_ST611-A | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-1607_ST611 | NA | "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-28 | 86 | NAP | 2025-10-08 | A | 001729 | 2025-10-08 | 00 | 1 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10050 | 001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5600_ST611 | A | 131242-WST02-DR-S-5600_ST611-A | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-5600_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10051 | 001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5601_ST611 | A | 131242-WST02-DR-S-5601_ST611-A | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-5601_ST611 | NA | "ST611 Pipe Supports Redesign" && "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-07-11 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-10-08 | A | 001460&&001729 | 2025-07-11, 2025-10-08 | 00 | 2 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10052 | 001729 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5406_ST611 | A | 131242-WST02-DR-S-5406_ST611-A | 2025-10-08 | ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-5406_ST611 | NA | "ST611_SSN water tank Pipe Support (above and internal area) (PE Endorsed Drawing)" | 2025-10-08 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-28 | 86 | NAP | 2025-10-08 | A | 001729 | 2025-10-08 | 00 | 1 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10053 | 001730 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1400 | A | 131242-WST02-DR-S-1400-A | 2025-10-08 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmision. | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-1400 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-12-18 | H | 000753&&000836&&001148&&001730&&001914 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
10054 | 001730 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1401 | A | 131242-WST02-DR-S-1401-A | 2025-10-08 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmision. | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-1401 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-12-18 | H | 001148&&001730&&001914 | 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
10055 | 001730 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5400 | A | 131242-WST02-DR-S-5400-A | 2025-10-08 | SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing) | R0: Not Approved. Please refer to comment sheet for resubmision. | 2025-11-05 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-DR-5400 | NA | "Hookup Drawing -TSS Analyser" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-22 | 86 | NAP | 2025-12-18 | F | 000753&&000836&&001730&&001788&&001914 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
10056 | 001731 | 00 | Heng Peng | BIM | NA | 131242 | WST02 | CD | IM | 0064 | 0 | 131242-WST02-CD-IM-0064-0 | 2025-10-08 | VCM Submission for 2025-09 | For Information | 2025-11-05 | 2025-10-29 | For Information |  | YES | NA |  | 131242-WST02-CD-0064 | NA | "VCM Submission for 2025-09" | 2025-10-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-28 | 21 | INF | 2025-10-08 | 0 | 001731 | 2025-10-08 | 00 | 1 | For Information | INF | 2025-11-18 | Overdue | 0 | INF | INF
10057 | 001732 | 00 | Freedomer | EICA | NA | 131242 | WST00 | DS | E | 0001 | 0 | 131242-WST00-DS-E-0001-0 | 2025-10-08 | SSN and THP Local Control Station (LCS) Components Datasheet | Rev 0: Approved with comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-05 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST00-DS-0001 | NA | "SSN and THP Local Control Station (LCS) Components Datasheet" | 2025-10-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-28 | 139 | AWC | 2025-10-08 | 0 | 001732 | 2025-10-08 | 00 | 1 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10058 | 001733 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8600 | A | 131242-WST02-DR-S-8600-A | 2025-10-09 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:0: Not Approved. Please refer to comment sheet for resubmission | 2025-11-06 | 2025-10-14 | Not Approved | 2025-11-03 | YES | Resubmitted |  | 131242-WST02-DR-8600 | NA | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-09-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-23 | 5 | NAP | 2025-11-06 | A.3 | 001656&&001733 | 2025-09-08, 2025-10-09, 2025-11-06 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10059 | 001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 8600 | A.3 | 131242-WST02-DR-S-8600-A.3 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-DR-8600 | NA | "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2025-09-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 67 | AWC | 2025-11-06 | A.3 | 001656&&001733 | 2025-09-08, 2025-10-09, 2025-11-06 | 00, 01 | 3 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10060 | 001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1009 | A.3 | 131242-WST02-DR-S-1009-A.3 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 67 | AWC | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | AWC | AWC
10061 | 001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5004 | A.3 | 131242-WST02-DR-S-5004-A.3 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-DR-5004 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 67 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10062 | 001733 | 01 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5005 | A.3 | 131242-WST02-DR-S-5005-A.3 | 2025-11-06 | Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing) | Rev:1: Approved with comments. Please refer to comment sheet for resubmission | 2025-11-26 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-DR-5005 | NA | "Milestone 2 SSN Electrical Building" && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN Cast-in Schedule & Details" && "SSN Electrical Building Archi Drawing" | 2024-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 67 | AWC | 2025-11-06 | A.3 | 000191&&000492&&000832&&001733 | 2024-05-28, 2024-10-21, 2024-11-22, 2025-02-26, 2025-05-15, 2025-11-06 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10063 | 001734 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | Fabrication Drawing | A.3 | 131242-WSD11-DR-S-Fabrication Drawing- | 2025-10-09 | THP-PF01 Grating Fabrication Drawing | For information | 2025-11-06 | 2025-11-13 | For Information |  | YES | NA |  | 131242-WSD11-DR-Fabrication Drawing | NA | "THP-PF01 Grating Fabrication Drawing" | 2025-10-09 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-10-29 | 35 | INF | 2025-10-09 | A.3 | 001734 | 2025-10-09 | 00 | 1 | For Information | INF | 2025-12-03 | Overdue | 0 | INF | INF
10064 | 001735 | 00 | David | Mech | NA | 131242 | WSW41 | VI | M | 1019 | 0 | 131242-WSW41-VI-M-1019-0 | 2025-10-10 | Preliminary Design and Vendor Approval – Hose Point | Rev 0: Approved | 2025-11-07 | 2025-11-24 | Approved |  | YES | NA |  | 131242-WSW41-VI-1019 | NA | "Preliminary Design and Vendor Approval – Hose Point" | 2025-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-10-30 | 45 | APP | 2025-10-10 | 0 | 001735 | 2025-10-10 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10065 | 001736 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0001 | 0 | 131242-WSD11-SH-M-0001-0 | 2025-10-10 | Line List for Hydrotest (CA system) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-07 | 2025-11-24 | Approved with Comments |  | YES | NA |  | 131242-WSD11-SH-0001 | NA | "Line List for Hydrotest (CA system)" | 2025-10-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-30 | 45 | AWC | 2025-10-10 | 0 | 001736 | 2025-10-10 | 00 | 1 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
10066 | 001737 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0029 | 0 | 131242-WSW41-RT-PM-0029-0 | 2025-10-11 | C4B Monthly Progress Report Number No. 29 (09 25) | Approved with comments which will be addressed in the next MPR. | 2025-11-07 | 2025-11-27 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0029 | NA | "C4B Monthly Progress Report Number No. 29 (09 25)" | 2025-10-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$) | 2025-10-31 | 47 | AWC | 2025-10-13 | 0_VOID | 001737&&001746 | 2025-10-11, 2025-10-13 | 00 | 2 | Rejected | REJ |  |  | 0 | AWC | AWC
10067 | 001738 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 1247 | 0 | 131242-WSW41-QA-M-01247-0 | 2025-10-13 | FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) | NA | 2025-11-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-1247 | NA | "FAT Report for Manual Knife Gate Valves- Batch 4 (JASH) " | 2025-10-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-02 | 175 | PEN | 2025-10-13 | 0 | 001738 | 2025-10-13 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-11-28 |  | 0 | PEN | PEN
10068 | 001739 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0128 | 0 | 131242-WSD11-QA-M-0128-0 | 2025-10-13 | FAT report for Steam Jet Heater (Steam Sparger) | NA | 2025-11-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0128 | NA | "FAT report for Steam Jet Heater (Steam Sparger) " | 2025-10-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-02 | 175 | PEN | 2025-10-13 | 0 | 001739 | 2025-10-13 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-11-28 |  | 0 | PEN | PEN
10069 | 001740 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | DS | BH | 0001 | 0 | 131242-WST02-DS-BH-0001-0 | 2025-10-13 | Datasheet for ACMV Equipment | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-10 | 2025-10-22 | Not Approved | 2025-11-11 | NO | Overdue |  | 131242-WST02-DS-0001 | NA | "Data Sheet for Fire Alarm System (Fire alarm panel, Intelligent smoke detector, Intelligent break glass call point, Horn and LED strobe light, Fire alarm bell, BMS communications bridges, control relay modules, Input modules, Fire resistant cable, Conduits, trunking and accessories)" && "Datasheet for ACMV Equipment" && "Epoxy Coating System" && "FRP TANK DATA SHEET" | 2023-05-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-27 | 9 | NAP | 2025-10-13 | 0 | 000016&&001236&&001296&&001740 | 2023-05-26, 2025-04-18, 2025-05-15, 2025-10-13 | 00 | 4 | Not Approved | NAP | 2025-11-11 | Overdue | 0 | NAP | NAP
10070 | 001741 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0129 | 0 | 131242-WST02-QA-M-0129-0 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-1) | Rev0: Approved | 2025-11-10 | 2025-10-30 | Approved |  | YES | NA |  | 131242-WST02-QA-0129 | NA | "FAT Report for Lamella Clarifier Biomass Separator (ARS-1)" | 2025-10-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-02 | 17 | APP | 2025-10-13 | 0 | 001741 | 2025-10-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10071 | 001742 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0130 | 0 | 131242-WST02-QA-M-0130-0 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-2) | Rev0: Approved | 2025-11-10 | 2025-10-30 | Approved |  | YES | NA |  | 131242-WST02-QA-0130 | NA | "FAT Report for Lamella Clarifier Biomass Separator (ARS-2)" | 2025-10-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-02 | 17 | APP | 2025-10-13 | 0 | 001742 | 2025-10-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10072 | 001743 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0131 | 0 | 131242-WST02-QA-M-0131-0 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-3) | Rev0: Approved | 2025-11-10 | 2025-10-30 | Approved |  | YES | NA |  | 131242-WST02-QA-0131 | NA | "FAT Report for Lamella Clarifier Biomass Separator (ARS-3)" | 2025-10-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-02 | 17 | APP | 2025-10-13 | 0 | 001743 | 2025-10-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10073 | 001744 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0132 | 0 | 131242-WST02-QA-M-0132-0 | 2025-10-13 | FAT Report for Lamella Clarifier Biomass Separator (ARS-4) | Rev0: Approved | 2025-11-10 | 2025-10-30 | Approved |  | YES | NA |  | 131242-WST02-QA-0132 | NA | "FAT Report for Lamella Clarifier Biomass Separator (ARS-4) " | 2025-10-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-02 | 17 | APP | 2025-10-13 | 0 | 001744 | 2025-10-13 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10074 | 001745 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0029 | 0 | 131242-WSW41-QA-A-0029-0 | 2025-10-13 | Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-10 | 2025-10-23 | Not Approved | 2025-11-12 | NO | Overdue |  | 131242-WSW41-QA-0029 | NA | "FAT report for SS Cable Ladder, Tray and Accessories (HDMANN) 4th batch" && "Metal Roofing & Cladding, Fire rated cladding - material submission for approval (CM Metal)" && "Test Report submission for Sidewide piperack – 03, (GL V-M) steel structure material testing" && "Vendor Manufacturing Inspection Test Plan for CSEL Pipes FBE Coating and Liquid Epoxy Coating" | 2025-01-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-10-27 | 10 | NAP | 2025-10-13 | 0 | 000940&&001217&&001238&&001745 | 2025-01-02, 2025-04-10, 2025-04-21, 2025-10-13 | 00 | 4 | Not Approved | NAP | 2025-11-12 | Overdue | 0 | NAP | NAP
10075 | 001746 | 00 | Jeline | PMT | NA | 131242 | WSW41 | RT | PM | 0029 | 0_VOID | 131242-WSW41-RT-PM-0029-0_VOID | 2025-10-13 | C4B Monthly Progress Report Number No. 29 (09 25) | Contractor submit duplication from #1737 | 2025-11-10 | 2025-10-17 | Rejected |  |  | NA |  | 131242-WSW41-RT-0029 | NA | "C4B Monthly Progress Report Number No. 29 (09 25)" | 2025-10-11 | NO | YES | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema; Latest_Revision pattern mismatch (^[A-Z0-9.]+$) | 2025-10-27 | 4 | REJ | 2025-10-13 | 0_VOID | 001737&&001746 | 2025-10-11, 2025-10-13 | 00 | 2 | Rejected | REJ | 2025-11-06 | Overdue | 0 | REJ | REJ
10076 | 001747 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0057 | 0 | 131242-WSW41-QA-E-0057-0 | 2025-10-14 | FAT Report for LCS panels WST02-401-LCS-P-0101,W SD11-111-LCS-P-0101,W ST02-201-LCS-P-0101, WSR02-204-LC-P-0102-(Sunlight) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-11 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WSW41-QA-0057 | NA | "FAT Report for LCS panels WST02-401-LCS-P-0101,W SD11-111-LCS-P-0101,W ST02-201-LCS-P-0101, WSR02-204-LC-P-0102-(Sunlight)" | 2025-10-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-03 | 44 | AWC | 2025-10-14 | 0 | 001747 | 2025-10-14 | 00 | 1 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10077 | 001748 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0027 | 0 | 131242-WSW41-PC-W-0027-0 | 2025-10-16 | Payment Claim No. 27 | Rev (0): Approved. Please refer to S.O. correspondence no. 411 dated 13 Oct 2025. | 2025-11-13 | 2025-11-13 | Approved |  | YES | NA |  | 131242-WSW41-PC-0027 | NA | "Payment Claim No. 27" | 2025-10-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-05 | 28 | APP | 2025-10-16 | 0 | 001748 | 2025-10-16 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10078 | 001749 | 00 | K Balaji | Mech | NA | 131242 | WSW41 | SH | M | 0001 | 0 | 131242-WSW41-SH-M-0001-0 | 2025-10-16 | Line List for Hydrotest (Sitewide PipeRack) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | Approved with Comments |  | YES | NA |  | 131242-WSW41-SH-0001 | NA | "Line List for Hydrotest (Sitewide PipeRack)" && "Sidewide Piperack Line List" | 2024-04-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-10-30 | 39 | AWC | 2025-10-16 | 0 | 000445&&001749 | 2024-04-17, 2025-10-16 | 00 | 2 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
10079 | 001750 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0003 | 0 | 131242-WSD11-SH-M-0003-0 | 2025-10-16 | Line List for Hydrotest (Biosolid Building) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | Approved with Comments | 2025-12-12 | NO | Overdue |  | 131242-WSD11-SH-0003 | NA | "Line List for Hydrotest (Biosolid Building)" | 2025-10-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 39 | AWC | 2025-10-16 | 0 | 001750 | 2025-10-16 | 00 | 1 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
10080 | 001751 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0004 | 0 | 131242-WSD11-SH-M-0004-0 | 2025-10-16 | Line List for Hydrotest (THP Courtyard - Interconnecting Pipe Rack) | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | Approved with Comments |  | YES | NA |  | 131242-WSD11-SH-0004 | NA | "Line List for Hydrotest (THP Courtyard - Interconnecting Pipe Rack)" | 2025-10-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-05 | 39 | AWC | 2025-10-16 | 0 | 001751 | 2025-10-16 | 00 | 1 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
10081 | 001752 | 00 | K Balaji | Mech | NA | 131242 | WSD11 | SH | M | 0005 | 0 | 131242-WSD11-SH-M-0005-0 | 2025-10-16 | Line List for Hydrotest (THP Courtyard - Cooler Platforms) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-13 | 2025-11-24 | Approved with Comments | 2025-12-12 | NO | Overdue |  | 131242-WSD11-SH-0005 | NA | "Line List for Hydrotest (THP Courtyard - Cooler Platforms)" | 2025-10-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 39 | AWC | 2025-10-16 | 0 | 001752 | 2025-10-16 | 00 | 1 | Approved with Comments | AWC | 2025-12-12 | Overdue | 0 | AWC | AWC
10082 | 001753 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0073 | 0 | 131242-WSW41-LT-PM-0073-0 | 2025-10-16 | Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG | NA | 2025-11-13 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0073 | NA | "Part 2 Further Notice For Extension Of Time And Cost For Delay Due To Relay Modification Of SSN 22kV Incoming Feeder From C3B1 HVSG" | 2025-10-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-05 | 172 | PEN | 2025-10-16 | 0 | 001753 | 2025-10-16 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-03 |  | 0 | PEN | PEN
10083 | 001754 | 00 | David | Mech | NA | 131242 | WST02 | CL | M | 1001 | 0 | 131242-WST02-CL-M-1001-0 | 2025-10-18 | Blower Aeration Air Piping Stress Calculation Report | NA | 2025-11-14 |  | Awaiting S.O.'s response |  |  | NA | Submitted Docs is 131242-WSD11-CL-M-1001. Typo in Area code | 131242-WST02-CL-1001 | NA | "Blower Aeration Air Piping Stress Calculation Report" | 2025-10-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-07 | 170 | PEN | 2025-10-18 | 0 | 001754 | 2025-10-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-04 |  | 0 | PEN | PEN
10084 | 001755 | 00 | Yibo | Mech | NA | 131242 | WST02 | OM | M | 0004 | 0 | 131242-WST02-OM-M-0004-0 | 2025-10-18 | O&M Manual for Hyperbolic Mixer | NA | 2025-11-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0004 | NA | "O&M Manual for Hyperbolic Mixer" | 2025-10-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-07 | 170 | PEN | 2025-10-18 | 0 | 001755 | 2025-10-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-04 |  | 0 | PEN | PEN
10085 | 001756 | 00 | Yibo | Mech | NA | 131242 | WSW41 | VI | M | 0027 | 0 | 131242-WSW41-VI-M-0027-0 | 2025-10-18 | Preliminary Design And Vendor Approval For Chute | Rev 0: Approved | 2025-11-14 | 2025-11-24 | Approved |  | YES | NA |  | 131242-WSW41-VI-0027 | NA | "Preliminary Design And Vendor Approval For Chute" | 2025-10-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-07 | 37 | APP | 2025-10-18 | 0 | 001756 | 2025-10-18 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10086 | 001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3001 | A | 131242-WSD11-DR-BE-3001-A | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 29 | NAP | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10087 | 001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3005 | A | 131242-WSD11-DR-BE-3005-A | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 29 | NAP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10088 | 001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7010 | A | 131242-WSD11-DR-BE-7010-A | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 29 | NAP | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | NAP | NAP
10089 | 001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7011 | A | 131242-WSD11-DR-BE-7011-A | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WSD11-DR-7011 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 29 | NAP | 2026-02-03 | B | 000570&&001757 | 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 04, 05 | 4 | Approved | APP |  |  | 0 | NAP | NAP
10090 | 001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7012 | A | 131242-WSD11-DR-BE-7012-A | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WSD11-DR-7012 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001757 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10091 | 001757 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7013 | A | 131242-WSD11-DR-BE-7013-A | 2025-10-22 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WSD11-DR-7013 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001757 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10092 | 001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3001 | B | 131242-WSD11-DR-BE-3001-B | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Compressed Air System" && "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-03-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 000302&&000390&&000570&&000575&&001039&&001230&&001328&&001757 | 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-21, 2025-02-12, 2025-03-07, 2025-04-16, 2025-05-28, 2025-06-04, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10093 | 001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3005 | B | 131242-WSD11-DR-BE-3005-B | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3005 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001757 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 12 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10094 | 001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7010 | B | 131242-WSD11-DR-BE-7010-B | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7010 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 000570&&001757 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
10095 | 001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7011 | B | 131242-WSD11-DR-BE-7011-B | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7011 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" && "THP SLD" | 2025-03-07 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 000570&&001757 | 2025-03-07, 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01, 04, 05 | 4 | Approved | APP |  |  | 0 | PEN | PEN
10096 | 001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7012 | B | 131242-WSD11-DR-BE-7012-B | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7012 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001757 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10097 | 001757 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7013 | B | 131242-WSD11-DR-BE-7013-B | 2026-02-03 | THP LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7013 | NA | "THP LDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001757 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10098 | 001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7300 | A | 131242-WSD11-DR-EI-7300-A | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WSD11-DR-7300 | NA | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001758 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10099 | 001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3100 | A | 131242-WSD11-DR-EP-3100-A | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WSD11-DR-3100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001758&&001944 | 2025-10-22, 2026-01-12, 2026-01-27 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10100 | 001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3101 | A | 131242-WSD11-DR-EP-3101-A | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WSD11-DR-3101 | NA | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001758 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10101 | 001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7200 | A | 131242-WSD11-DR-EP-7200-A | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WSD11-DR-7200 | NA | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001758 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10102 | 001758 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7201 | A | 131242-WSD11-DR-EP-7201-A | 2025-10-22 | THP UPSDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WSD11-DR-7201 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 19 | AWC | 2026-01-27 | B | 001160&&001758 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10103 | 001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7300 | B | 131242-WSD11-DR-EI-7300-B | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7300 | NA | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001758 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10104 | 001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3100 | B | 131242-WSD11-DR-EP-3100-B | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001758&&001944 | 2025-10-22, 2026-01-12, 2026-01-27 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10105 | 001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3101 | B | 131242-WSD11-DR-EP-3101-B | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3101 | NA | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001758 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10106 | 001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7200 | B | 131242-WSD11-DR-EP-7200-B | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7200 | NA | "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001758 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10107 | 001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7201 | B | 131242-WSD11-DR-EP-7201-B | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7201 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001160&&001758 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10108 | 001758 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7202 | B | 131242-WSD11-DR-EP-7202-B | 2026-01-27 | THP UPSDB-0001A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7202 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001160&&001758 | 2025-03-25, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10109 | 001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7302 | A | 131242-WSD11-DR-EI-7302-A | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-7302 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10110 | 001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3102 | A | 131242-WSD11-DR-EP-3102-A | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-3102 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10111 | 001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3103 | A | 131242-WSD11-DR-EP-3103-A | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-3103 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10112 | 001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7205 | A | 131242-WSD11-DR-EP-7205-A | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-7205 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 29 | NAP | 2026-01-27 | B | 001160&&001759 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10113 | 001759 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7206 | A | 131242-WSD11-DR-EP-7206-A | 2025-10-22 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-7206 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10114 | 001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7302 | B | 131242-WSD11-DR-EI-7302-B | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7302 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10115 | 001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3102 | B | 131242-WSD11-DR-EP-3102-B | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3102 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10116 | 001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3103 | B | 131242-WSD11-DR-EP-3103-B | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3103 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10117 | 001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7205 | B | 131242-WSD11-DR-EP-7205-B | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7205 | NA | "THP UPS DB SLD Drawing " && "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001160&&001759 | 2025-03-25, 2025-10-22, 2026-01-27 | 00, 01 | 3 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10118 | 001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7206 | B | 131242-WSD11-DR-EP-7206-B | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7206 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001759 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10119 | 001759 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7207 | B | 131242-WSD11-DR-EP-7207-B | 2026-01-27 | THP UPSDB-0001B SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7207 | NA | "THP UPSDB-0001B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | B | 001759 | 2026-01-27 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10120 | 001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7304 | A | 131242-WSD11-DR-EI-7304-A | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-7304 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10121 | 001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3104 | A | 131242-WSD11-DR-EP-3104-A | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-3104 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10122 | 001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3105 | A | 131242-WSD11-DR-EP-3105-A | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-3105 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10123 | 001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7210 | A | 131242-WSD11-DR-EP-7210-A | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-7210 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10124 | 001760 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7211 | A | 131242-WSD11-DR-EP-7211-A | 2025-10-22 | THP UPSDB-0105A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WSD11-DR-7211 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10125 | 001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7304 | B | 131242-WSD11-DR-EI-7304-B | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7304 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10126 | 001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3104 | B | 131242-WSD11-DR-EP-3104-B | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3104 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10127 | 001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3105 | B | 131242-WSD11-DR-EP-3105-B | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3105 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10128 | 001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7210 | B | 131242-WSD11-DR-EP-7210-B | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7210 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10129 | 001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7211 | B | 131242-WSD11-DR-EP-7211-B | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7211 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001760 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10130 | 001760 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7212 | B | 131242-WSD11-DR-EP-7212-B | 2026-01-27 | THP UPSDB-0105A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7212 | NA | "THP UPSDB-0105A SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | B | 001760 | 2026-01-27 | 01 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10131 | 001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7308 | A | 131242-WST02-DR-EI-7308-A | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7308 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-02-03 | B | 001761 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10132 | 001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3108 | A | 131242-WST02-DR-EP-3108-A | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3108 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-02-03 | B | 001761 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10133 | 001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3109 | A | 131242-WST02-DR-EP-3109-A | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3109 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-02-03 | B | 001761 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10134 | 001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7220 | A | 131242-WST02-DR-EP-7220-A | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7220 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 19 | AWC | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10135 | 001761 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7221 | A | 131242-WST02-DR-EP-7221-A | 2025-10-22 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7221 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 19 | AWC | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10136 | 001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7308 | B | 131242-WST02-DR-EI-7308-B | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7308 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001761 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10137 | 001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3108 | B | 131242-WST02-DR-EP-3108-B | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3108 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001761 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10138 | 001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3109 | B | 131242-WST02-DR-EP-3109-B | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3109 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001761 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10139 | 001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7220 | B | 131242-WST02-DR-EP-7220-B | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7220 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10140 | 001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7221 | B | 131242-WST02-DR-EP-7221-B | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7221 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10141 | 001761 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7222 | B | 131242-WST02-DR-EP-7222-B | 2026-02-03 | SSN 201-VDB-0001 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7222 | NA | "SSN 201-VDB-0001 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001761 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10142 | 001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7312 | A | 131242-WST02-DR-EI-7312-A | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-7312 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" && "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001762&&001992 | 2025-10-22, 2026-01-28, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10143 | 001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3112 | A | 131242-WST02-DR-EP-3112-A | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-3112 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10144 | 001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3113 | A | 131242-WST02-DR-EP-3113-A | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-3113 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10145 | 001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7230 | A | 131242-WST02-DR-EP-7230-A | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-7230 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10146 | 001762 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7231 | A | 131242-WST02-DR-EP-7231-A | 2025-10-22 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-7231 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10147 | 001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7312 | B | 131242-WST02-DR-EI-7312-B | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7312 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" && "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001762&&001992 | 2025-10-22, 2026-01-28, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10148 | 001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3112 | B | 131242-WST02-DR-EP-3112-B | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3112 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10149 | 001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3113 | B | 131242-WST02-DR-EP-3113-B | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3113 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10150 | 001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7230 | B | 131242-WST02-DR-EP-7230-B | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7230 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10151 | 001762 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7231 | B | 131242-WST02-DR-EP-7231-B | 2026-02-03 | SSN 201-VDB-0001A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7231 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001762 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10152 | 001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7324 | A | 131242-WST02-DR-EI-7324-A | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7324 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10153 | 001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3124 | A | 131242-WST02-DR-EP-3124-A | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3124 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10154 | 001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3125 | A | 131242-WST02-DR-EP-3125-A | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3125 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10155 | 001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7265 | A | 131242-WST02-DR-EP-7265-A | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7265 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10156 | 001763 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7266 | A | 131242-WST02-DR-EP-7266-A | 2025-10-22 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7266 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 19 | AWC | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10157 | 001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7324 | B | 131242-WST02-DR-EI-7324-B | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7324 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10158 | 001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3124 | B | 131242-WST02-DR-EP-3124-B | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3124 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10159 | 001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3125 | B | 131242-WST02-DR-EP-3125-B | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3125 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10160 | 001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7265 | B | 131242-WST02-DR-EP-7265-B | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7265 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10161 | 001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7266 | B | 131242-WST02-DR-EP-7266-B | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7266 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001763 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10162 | 001763 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7267 | B | 131242-WST02-DR-EP-7267-B | 2026-01-27 | SSN UPSDB-0004 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7267 | NA | "SSN UPSDB-0004 SLD, Schematic and GA Drawing" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | B | 001763 | 2026-01-27 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10163 | 001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7326 | A | 131242-WST02-DR-EI-7326-A | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-7326 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10164 | 001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3126 | A | 131242-WST02-DR-EP-3126-A | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-3126 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10165 | 001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3127 | A | 131242-WST02-DR-EP-3127-A | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-3127 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10166 | 001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7270 | A | 131242-WST02-DR-EP-7270-A | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-7270 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10167 | 001764 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7271 | A | 131242-WST02-DR-EP-7271-A | 2025-10-22 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | YES | Resubmitted |  | 131242-WST02-DR-7271 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10168 | 001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7326 | B | 131242-WST02-DR-EI-7326-B | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7326 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10169 | 001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3126 | B | 131242-WST02-DR-EP-3126-B | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3126 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10170 | 001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3127 | B | 131242-WST02-DR-EP-3127-B | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3127 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10171 | 001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7270 | B | 131242-WST02-DR-EP-7270-B | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7270 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10172 | 001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7271 | B | 131242-WST02-DR-EP-7271-B | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7271 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001764 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10173 | 001764 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7272 | B | 131242-WST02-DR-EP-7272-B | 2026-01-27 | SSN UPSDB-0005 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7272 | NA | "SSN UPSDB-0005 SLD, Schematic and GA Drawing" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | B | 001764 | 2026-01-27 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10174 | 001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7316 | A | 131242-WST02-DR-EI-7316-A | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7316 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10175 | 001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3116 | A | 131242-WST02-DR-EP-3116-A | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-3116 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10176 | 001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3117 | A | 131242-WST02-DR-EP-3117-A | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-3117 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10177 | 001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7245 | A | 131242-WST02-DR-EP-7245-A | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7245 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10178 | 001765 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7246 | A | 131242-WST02-DR-EP-7246-A | 2025-10-22 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-19 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7246 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 29 | NAP | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10179 | 001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7316 | B | 131242-WST02-DR-EI-7316-B | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7316 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10180 | 001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3116 | B | 131242-WST02-DR-EP-3116-B | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3116 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10181 | 001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3117 | B | 131242-WST02-DR-EP-3117-B | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3117 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10182 | 001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7245 | B | 131242-WST02-DR-EP-7245-B | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7245 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10183 | 001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7246 | B | 131242-WST02-DR-EP-7246-B | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7246 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001765 | 2025-10-22, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10184 | 001765 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7247 | B | 131242-WST02-DR-EP-7247-B | 2026-01-28 | SSN UPSDB-0101A SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7247 | NA | "SSN UPSDB-0101A SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | B | 001765 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10185 | 001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3006 | A_VOID | 131242-WSD11-DR-BE-3006-A_VOID | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-05 | 2 | REJ | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10186 | 001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3010 | A_VOID | 131242-WSD11-DR-BE-3010-A_VOID | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-05 | 2 | REJ | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10187 | 001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7015 | A_VOID | 131242-WSD11-DR-BE-7015-A_VOID | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7015 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-11 | 2 | REJ | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
10188 | 001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7016 | A_VOID | 131242-WSD11-DR-BE-7016-A_VOID | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7016 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-11 | 2 | REJ | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
10189 | 001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7017 | A_VOID | 131242-WSD11-DR-BE-7017-A_VOID | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7017 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-11 | 2 | REJ | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
10190 | 001766 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7018 | A_VOID | 131242-WSD11-DR-BE-7018-A_VOID | 2025-10-22 | THP UPSDB-0101A SLD, Schematic and GA Drawing | 1) description/subject is incorrect 2) drawings uploaded in Submittal #001773 | 2025-11-19 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WSD11-DR-7018 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-11 | 2 | REJ | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | REJ | REJ
10191 | 001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7306 | A | 131242-WSD11-DR-EI-7306-A | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-7306 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 50 | NAP | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10192 | 001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3106 | A | 131242-WSD11-DR-EP-3106-A | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-3106 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | NAP | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10193 | 001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3107 | A | 131242-WSD11-DR-EP-3107-A | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-3107 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | NAP | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10194 | 001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7215 | A | 131242-WSD11-DR-EP-7215-A | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-7215 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | NAP | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10195 | 001767 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7216 | A | 131242-WSD11-DR-EP-7216-A | 2025-10-22 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Not approved - Revise and Resubmit | 2025-11-19 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-7216 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | NAP | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10196 | 001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7306 | B | 131242-WSD11-DR-EI-7306-B | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7306 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2024-11-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 000392&&001767 | 2024-11-19, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 02, 03, 04 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10197 | 001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3106 | B | 131242-WSD11-DR-EP-3106-B | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3106 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10198 | 001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3107 | B | 131242-WSD11-DR-EP-3107-B | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3107 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10199 | 001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7215 | B | 131242-WSD11-DR-EP-7215-B | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7215 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10200 | 001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7216 | B | 131242-WSD11-DR-EP-7216-B | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7216 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" && "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | B | 001767 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10201 | 001767 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7217 | B | 131242-WSD11-DR-EP-7217-B | 2026-01-27 | THP UPSDB-0106A SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7217 | NA | "THP UPSDB-0106A SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | B | 001767 | 2026-01-27 | 01 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10202 | 001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7308 | A | 131242-WSD11-DR-EI-7308-A | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-7308 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 50 | AWC | 2026-01-27 | B | 000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 03, 04 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10203 | 001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3108 | A | 131242-WSD11-DR-EP-3108-A | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-3108 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | AWC | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10204 | 001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3109 | A | 131242-WSD11-DR-EP-3109-A | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-3109 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | AWC | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10205 | 001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7220 | A | 131242-WSD11-DR-EP-7220-A | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-7220 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | AWC | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10206 | 001768 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7221 | A | 131242-WSD11-DR-EP-7221-A | 2025-10-22 | THP UPSDB-0106 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WSD11-DR-7221 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 50 | AWC | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10207 | 001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7308 | B | 131242-WSD11-DR-EI-7308-B | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7308 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2024-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 000392&&001768 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2025-10-22, 2026-01-27 | 00, 01, 03, 04 | 6 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10208 | 001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3108 | B | 131242-WSD11-DR-EP-3108-B | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3108 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10209 | 001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3109 | B | 131242-WSD11-DR-EP-3109-B | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3109 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10210 | 001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7220 | B | 131242-WSD11-DR-EP-7220-B | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7220 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10211 | 001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7221 | B | 131242-WSD11-DR-EP-7221-B | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7221 | NA | "THP UPSDB-0106 SLD, Schematic and GA Drawing" && "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001768 | 2025-10-22, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10212 | 001768 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7222 | B | 131242-WSD11-DR-EP-7222-B | 2026-01-27 | THP UPSDB-0107 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7222 | NA | "THP UPSDB-0107 SLD, Schematic and GA Drawing" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | B | 001768 | 2026-01-27 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10213 | 001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7310 | A | 131242-WST02-DR-EI-7310-A | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7310 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 36 | AWC | 2026-02-03 | B | 001769&&001992 | 2025-10-22, 2026-01-28, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10214 | 001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3110 | A | 131242-WST02-DR-EP-3110-A | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3110 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 36 | AWC | 2026-02-03 | B | 001769 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10215 | 001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3111 | A | 131242-WST02-DR-EP-3111-A | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3111 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 36 | AWC | 2026-02-03 | B | 001769 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10216 | 001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7225 | A | 131242-WST02-DR-EP-7225-A | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7225 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 36 | AWC | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10217 | 001769 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7226 | A | 131242-WST02-DR-EP-7226-A | 2025-10-22 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-19 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7226 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-05 | 36 | AWC | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10218 | 001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7310 | B | 131242-WST02-DR-EI-7310-B | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7310 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001769&&001992 | 2025-10-22, 2026-01-28, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10219 | 001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3110 | B | 131242-WST02-DR-EP-3110-B | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3110 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001769 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10220 | 001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3111 | B | 131242-WST02-DR-EP-3111-B | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3111 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001769 | 2025-10-22, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10221 | 001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7225 | B | 131242-WST02-DR-EP-7225-B | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7225 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10222 | 001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7226 | B | 131242-WST02-DR-EP-7226-B | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7226 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2025-10-22, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10223 | 001769 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7227 | B | 131242-WST02-DR-EP-7227-B | 2026-02-03 | SSN 201-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7227 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001769 | 2025-03-25, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10224 | 001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7314 | A | 131242-WST02-DR-EI-7314-A | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7314 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10225 | 001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3114 | A | 131242-WST02-DR-EP-3114-A | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3114 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10226 | 001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3115 | A | 131242-WST02-DR-EP-3115-A | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3115 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10227 | 001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7235 | A | 131242-WST02-DR-EP-7235-A | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7235 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10228 | 001770 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7236 | A | 131242-WST02-DR-EP-7236-A | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7236 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10229 | 001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7314 | B | 131242-WST02-DR-EI-7314-B | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-12 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7314 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10230 | 001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3114 | B | 131242-WST02-DR-EP-3114-B | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3114 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10231 | 001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3115 | B | 131242-WST02-DR-EP-3115-B | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3115 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10232 | 001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7235 | B | 131242-WST02-DR-EP-7235-B | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7235 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10233 | 001770 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7236 | B | 131242-WST02-DR-EP-7236-B | 2025-10-23 | SSN 201-VDB-0002A SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7236 | NA | "SSN 201-VDB-0002A SLD, Schematic and GA Drawing" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2025-10-23 | A | 001770 | 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2025-12-17 | Overdue | 0 | AWC | AWC
10234 | 001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7304 | A | 131242-WST02-DR-EI-7304-A | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-7304 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001771 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10235 | 001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3104 | A | 131242-WST02-DR-EP-3104-A | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-3104 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001771 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10236 | 001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3105 | A | 131242-WST02-DR-EP-3105-A | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-3105 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001771 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10237 | 001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7210 | A | 131242-WST02-DR-EP-7210-A | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-7210 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 35 | AWC | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10238 | 001771 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7211 | A | 131242-WST02-DR-EP-7211-A | 2025-10-23 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-7211 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 35 | AWC | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10239 | 001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7304 | B | 131242-WST02-DR-EI-7304-B | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7304 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001771 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10240 | 001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3104 | B | 131242-WST02-DR-EP-3104-B | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3104 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001771 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10241 | 001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3105 | B | 131242-WST02-DR-EP-3105-B | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3105 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001771 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10242 | 001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7210 | B | 131242-WST02-DR-EP-7210-B | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7210 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10243 | 001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7211 | B | 131242-WST02-DR-EP-7211-B | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7211 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10244 | 001771 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7212 | B | 131242-WST02-DR-EP-7212-B | 2026-02-03 | SSN 203-VDB-0001 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7212 | NA | "SSN 203-VDB-0001 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001468&&001771 | 2025-07-11, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10245 | 001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7306 | A | 131242-WST02-DR-EI-7306-A | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7306 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" && "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001772&&001984 | 2025-10-23, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10246 | 001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3106 | A | 131242-WST02-DR-EP-3106-A | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3106 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001772 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10247 | 001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3107 | A | 131242-WST02-DR-EP-3107-A | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-3107 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001772 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10248 | 001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7215 | A | 131242-WST02-DR-EP-7215-A | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7215 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 35 | AWC | 2026-02-03 | B | 001468&&001772 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10249 | 001772 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7216 | A | 131242-WST02-DR-EP-7216-A | 2025-10-23 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-20 | 2025-11-27 | Approved with Comments | 2025-12-17 | NO | Overdue |  | 131242-WST02-DR-7216 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 35 | AWC | 2026-02-03 | B | 001772 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10250 | 001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7306 | B | 131242-WST02-DR-EI-7306-B | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7306 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" && "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001772&&001984 | 2025-10-23, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10251 | 001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3106 | B | 131242-WST02-DR-EP-3106-B | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3106 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001772 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10252 | 001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3107 | B | 131242-WST02-DR-EP-3107-B | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3107 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001772 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10253 | 001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7215 | B | 131242-WST02-DR-EP-7215-B | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7215 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" && "SSN-Chemical Unloading LCP - GA and Wiring Drawing" | 2025-07-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001468&&001772 | 2025-07-11, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10254 | 001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7216 | B | 131242-WST02-DR-EP-7216-B | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7216 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001772 | 2025-10-23, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10255 | 001772 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7217 | B | 131242-WST02-DR-EP-7217-B | 2026-02-03 | SSN 203-VDB-0002 SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7217 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" | 2026-02-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-23 | 62 | PEN | 2026-02-03 | B | 001772 | 2026-02-03 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-23 |  | 0 | PEN | PEN
10256 | 001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3006 | A | 131242-WSD11-DR-BE-3006-A | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 47 | NAP | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10257 | 001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3010 | A | 131242-WSD11-DR-BE-3010-A | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 47 | NAP | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10258 | 001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7015 | A | 131242-WSD11-DR-BE-7015-A | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DR-7015 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 47 | NAP | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10259 | 001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7016 | A | 131242-WSD11-DR-BE-7016-A | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DR-7016 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 47 | NAP | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10260 | 001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7017 | A | 131242-WSD11-DR-BE-7017-A | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DR-7017 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 47 | NAP | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10261 | 001773 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7018 | A | 131242-WSD11-DR-BE-7018-A | 2025-10-23 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-20 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WSD11-DR-7018 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 47 | NAP | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10262 | 001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3006 | B | 131242-WSD11-DR-BE-3006-B | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3006 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP MCC Outline Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-07-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 000570&&000575&&001230&&001328&&001766&&001773 | 2024-07-17, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-04-16, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-11-11, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 13 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10263 | 001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 3010 | B | 131242-WSD11-DR-BE-3010-B | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3010 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP SLD" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 000291&&000292&&000570&&001230&&001328&&001766&&001773 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 17 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10264 | 001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7015 | B | 131242-WSD11-DR-BE-7015-B | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7015 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10265 | 001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7016 | B | 131242-WSD11-DR-BE-7016-B | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7016 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10266 | 001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7017 | B | 131242-WSD11-DR-BE-7017-B | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7017 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10267 | 001773 | 01 | Freedomer | EICA | NA | 131242 | WSD11 | DR | BE | 7018 | B | 131242-WSD11-DR-BE-7018-B | 2026-02-03 | THP LDB-0002 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7018 | NA | "THP LDB-0002 SLD, Schematic and GA Drawing" && "THP UPSDB-0101A SLD, Schematic and GA Drawing" | 2025-10-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001766&&001773 | 2025-10-22, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10268 | 001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | A | 131242-WST02-DR-BE-3001-A | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 28 | NAP | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10269 | 001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | A | 131242-WST02-DR-BE-3005-A | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 28 | NAP | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10270 | 001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | A | 131242-WST02-DR-BE-7010-A | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 28 | NAP | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10271 | 001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | A | 131242-WST02-DR-BE-7011-A | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 28 | NAP | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10272 | 001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | A | 131242-WST02-DR-BE-7012-A | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7012 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 28 | NAP | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10273 | 001774 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | A | 131242-WST02-DR-BE-7013-A | 2025-10-23 | SSN LDB-0001 SLD, Schematic and GA Drawing | R0: Not Approved. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-20 | Not Approved | 2025-12-10 | NO | Overdue |  | 131242-WST02-DR-7013 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 28 | NAP | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10274 | 001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | B | 131242-WST02-DR-BE-3001-B | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10275 | 001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | B | 131242-WST02-DR-BE-3005-B | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10276 | 001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | B | 131242-WST02-DR-BE-7010-B | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10277 | 001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | B | 131242-WST02-DR-BE-7011-B | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10278 | 001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | B | 131242-WST02-DR-BE-7012-B | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7012 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10279 | 001774 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | B | 131242-WST02-DR-BE-7013-B | 2026-02-03 | SSN LDB-0001 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7013 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10280 | 001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3001 | A_VOID | 131242-WST02-DR-BE-3001-A_VOID | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WST02-DR-3001 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-06 | 1 | REJ | 2026-02-03 | B | 000163&&000605&&000607&&001165&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10281 | 001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3005 | A_VOID | 131242-WST02-DR-BE-3005-A_VOID | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WST02-DR-3005 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-06 | 1 | REJ | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001774&&001775 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10282 | 001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7010 | A_VOID | 131242-WST02-DR-BE-7010-A_VOID | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WST02-DR-7010 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Process Hydraulic Calculation & Drawing" && "SSN Transformer Marshalling Box Schematic Wiring Diagram" && "SSN Transformer Outline Drawing" | 2024-04-03 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-06 | 1 | REJ | 2026-02-03 | B | 000416&&000439&&000440&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2024-04-03, 2024-04-16, 2024-07-12, 2024-08-01, 2024-08-20, 2024-08-21, 2024-10-16, 2024-11-21, 2024-12-11, 2025-01-21, 2025-03-24, 2025-05-04, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 19 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10283 | 001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7011 | A_VOID | 131242-WST02-DR-BE-7011-A_VOID | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WST02-DR-7011 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "LVSG Schematic Diagram" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Over All Network Archtecture Drawings" && "SSN Transformer Outline Drawing" && "SSN: Plant Drain Hydraulic Profile and calculation " | 2023-11-08 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-06 | 1 | REJ | 2026-02-03 | B | 000173&&000439&&000441&&000604&&000605&&001333&&001557&&001774&&001775 | 2023-11-08, 2024-05-06, 2024-07-12, 2024-08-01, 2024-08-07, 2024-08-20, 2024-10-16, 2024-11-21, 2024-12-11, 2025-05-30, 2025-08-05, 2025-08-25, 2025-10-23, 2025-10-27, 2026-02-03 | 00, 01, 02, 03 | 16 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10284 | 001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7012 | A_VOID | 131242-WST02-DR-BE-7012-A_VOID | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WST02-DR-7012 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-06 | 1 | REJ | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10285 | 001775 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7013 | A_VOID | 131242-WST02-DR-BE-7013-A_VOID | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | 1) drawings incorrect 2) drawings uploaded in Submittal #0017776 | 2025-11-20 | 2025-10-24 | Rejected |  | YES | NA |  | 131242-WST02-DR-7013 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "SSN IO Sample Schematic Drawing" && "SSN LDB-0001 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2024-08-20 | YES | NO | Project_Code not in project_schema; Document_Revision pattern mismatch (^[A-Z0-9.]*$); Department not in department_schema | 2025-11-06 | 1 | REJ | 2026-02-03 | B | 000441&&001557&&001774&&001775 | 2024-08-20, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | REJ | REJ
10286 | 001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3006 | A | 131242-WST02-DR-BE-3006-A | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10287 | 001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3010 | A | 131242-WST02-DR-BE-3010-A | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10288 | 001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7015 | A | 131242-WST02-DR-BE-7015-A | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7015 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10289 | 001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7016 | A | 131242-WST02-DR-BE-7016-A | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7016 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10290 | 001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7017 | A | 131242-WST02-DR-BE-7017-A | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7017 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10291 | 001776 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7018 | A | 131242-WST02-DR-BE-7018-A | 2025-10-23 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7018 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10292 | 001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3006 | A | 131242-WST02-DR-BE-3006-A | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3006 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000605&&000607&&001165&&001558&&001776 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-05-04, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10293 | 001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3010 | A | 131242-WST02-DR-BE-3010-A | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3010 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-11-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001776 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10294 | 001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7015 | A | 131242-WST02-DR-BE-7015-A | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7015 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10295 | 001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7016 | A | 131242-WST02-DR-BE-7016-A | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7016 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10296 | 001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7017 | A | 131242-WST02-DR-BE-7017-A | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7017 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10297 | 001776 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7018 | A | 131242-WST02-DR-BE-7018-A | 2026-02-03 | SSN LDB-0002 SLD, Schematic and GA Drawing | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7018 | NA | "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LDB-0002 SLD, Schematic and GA Drawing" | 2025-08-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 001558&&001776 | 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10298 | 001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3011 | A | 131242-WST02-DR-BE-3011-A | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10299 | 001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3015 | A | 131242-WST02-DR-BE-3015-A | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10300 | 001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7020 | A | 131242-WST02-DR-BE-7020-A | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10301 | 001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7021 | A | 131242-WST02-DR-BE-7021-A | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10302 | 001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7022 | A | 131242-WST02-DR-BE-7022-A | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10303 | 001777 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7023 | A | 131242-WST02-DR-BE-7023-A | 2025-10-23 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-20 | 2025-11-10 | Approved with Comments | 2025-11-28 | YES | Resubmitted |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 18 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10304 | 001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3011 | A | 131242-WST02-DR-BE-3011-A | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3011 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "LDB-0002 SLD, Schematic and GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-11-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000605&&000866&&001165&&001558&&001777 | 2024-11-21, 2024-12-02, 2025-01-21, 2025-03-07, 2025-03-25, 2025-03-28, 2025-05-04, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10305 | 001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3015 | A | 131242-WST02-DR-BE-3015-A | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Approved with Comments |  |  | NA |  | 131242-WST02-DR-3015 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | AWC | 2026-02-03 | A | 000866&&001165&&001559&&001777 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-23 |  | 0 | AWC | AWC
10306 | 001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7020 | A | 131242-WST02-DR-BE-7020-A | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Approved with Comments |  |  | NA |  | 131242-WST02-DR-7020 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-23 |  | 0 | AWC | AWC
10307 | 001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7021 | A | 131242-WST02-DR-BE-7021-A | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Approved with Comments |  |  | NA |  | 131242-WST02-DR-7021 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-23 |  | 0 | AWC | AWC
10308 | 001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7022 | A | 131242-WST02-DR-BE-7022-A | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Approved with Comments |  |  | NA |  | 131242-WST02-DR-7022 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-23 |  | 0 | AWC | AWC
10309 | 001777 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7023 | A | 131242-WST02-DR-BE-7023-A | 2026-02-03 | SSN SDB-0003 SLD, Schematic and GA Drawing | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2026-02-23 |  | Approved with Comments |  |  | NA |  | 131242-WST02-DR-7023 | NA | "LVSG Schematic Diagram" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN Control Network Connection Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN SDB-0003 SLD, Schematic and GA Drawing" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | AWC | 2026-02-03 | A | 000604&&000605&&000660&&001559&&001777 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-08-05, 2025-10-23, 2026-02-03 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-23 |  | 0 | AWC | AWC
10310 | 001778 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | PS | P | 0001 | 0 | 131242-WST02-PS-P-0001-0 | 2025-10-23 | SSN Functional Design Specification Workshop | Rev0: The document is submitted for information. However, please see the comments in the comment sheet. | 2025-11-20 | 2026-01-12 | For Information |  | YES | NA |  | 131242-WST02-PS-0001 | NA | "SSN Functional Design Specification Workshop" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-12 | 81 | INF | 2025-10-23 | 0 | 001778 | 2025-10-23 | 00 | 1 | For Information | INF | 2026-01-30 | Overdue | 0 | INF | INF
10311 | 001779 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5204 | 0 | 131242-WSD11-DR-M-5204-0 | 2025-10-23 | GA for Steam Strainer | NA | 2025-11-20 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5204 | NA | "GA for Steam Strainer" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-12 | 165 | PEN | 2025-10-23 | 0 | 001779 | 2025-10-23 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-10 |  | 0 | PEN | PEN
10312 | 001780 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | DR | M | 5203 | 0 | 131242-WSD11-DR-M-5203-0 | 2025-10-23 | GA for Steam Relief Valve | NA | 2025-11-20 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5203 | NA | "GA for Steam Relief Valve" | 2025-10-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-12 | 165 | PEN | 2025-10-23 | 0 | 001780 | 2025-10-23 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-10 |  | 0 | PEN | PEN
10313 | 001781 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | ST617 THP-PF-01 TOS 15.875 Grating Fab | 0 | 131242-WSD11-DR-S-ST617 THP-PF-01 TOS 15.875 Grating Fab- | 2025-10-23 | ST617 THP-PF-01 TOS 15.875 Grating Fabrication Drawing (PE endorsement) | For Information. Drawings shall be submitted individual sheet. | 2025-11-20 | 2025-12-17 | For Information |  | YES | NA |  | 131242-WSD11-DR-ST617 THP-PF-01 TOS 15.875 Grating Fab | NA | "ST617 THP-PF-01 TOS 15.875 Grating Fabrication Drawing (PE endorsement)" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2025-11-12 | 55 | INF | 2025-10-23 | 0 | 001781 | 2025-10-23 | 00 | 1 | For Information | INF | 2026-01-06 | Overdue | 0 | INF | INF
10314 | 001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5450 | A | 131242-WST02-DR-I-5450-A | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5450 | NA | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | NAP | 2025-10-23 | A | 001782 | 2025-10-23 | 00 | 1 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10315 | 001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5451 | A | 131242-WST02-DR-I-5451-A | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5451 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | NAP | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10316 | 001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5452 | A | 131242-WST02-DR-I-5452-A | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5452 | NA | "Hookup Drawing - Pressure Gauge" && "Side Manway Calculation and GA Drawing" | 2024-10-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | NAP | 2025-10-23 | A | 000751&&001782 | 2024-10-09, 2024-11-08, 2025-10-23 | 00, 01, 02 | 4 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10317 | 001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5453 | A | 131242-WST02-DR-I-5453-A | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5453 | NA | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | NAP | 2025-10-23 | A | 001782 | 2025-10-23 | 00 | 1 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10318 | 001782 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5454 | A | 131242-WST02-DR-I-5454-A | 2025-10-23 | Hookup Drawing - Pressure Gauge | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5454 | NA | "Hookup Drawing - Pressure Gauge" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | NAP | 2025-10-23 | A | 001782 | 2025-10-23 | 00 | 1 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10319 | 001783 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5460 | A | 131242-WST02-DR-I-5460-A | 2025-10-23 | Hookup Drawing - Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5460 | NA | "Hookup Drawing - Rotameter" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | AWC | 2025-10-23 | A | 001783 | 2025-10-23 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10320 | 001783 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5461 | A | 131242-WST02-DR-I-5461-A | 2025-10-23 | Hookup Drawing - Rotameter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5461 | NA | "GA drawing and calculation for ALUMINIUM ACCESS COVER (Top Manway)" && "Hookup Drawing - Rotameter" | 2024-10-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | AWC | 2025-10-23 | A | 000766&&001783 | 2024-10-18, 2024-12-06, 2025-04-04, 2025-10-23 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10321 | 001784 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5350 | A | 131242-WST02-DR-I-5350-A | 2025-10-23 | Hookup Drawing - Capacitive Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5350 | NA | "Hookup Drawing - Capacitive Level Switch" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | NAP | 2025-10-23 | A | 001784 | 2025-10-23 | 00 | 1 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10322 | 001784 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5351 | A | 131242-WST02-DR-I-5351-A | 2025-10-23 | Hookup Drawing - Capacitive Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5351 | NA | "Hookup Drawing - Capacitive Level Switch" && "PC Pump GA Drawing " | 2024-12-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | NAP | 2025-10-23 | A | 000925&&001784 | 2024-12-23, 2025-10-23 | 00 | 2 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10323 | 001784 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5352 | A | 131242-WST02-DR-I-5352-A | 2025-10-23 | Hookup Drawing - Capacitive Level Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Not Approved | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5352 | NA | "Hookup Drawing - Capacitive Level Switch" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | NAP | 2025-10-23 | A | 001784 | 2025-10-23 | 00 | 1 | Not Approved | NAP | 2026-01-02 | Overdue | 0 | NAP | NAP
10324 | 001785 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5410 | A | 131242-WST02-DR-I-5410-A | 2025-10-23 | Hookup Drawing - Conductivity Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5410 | NA | "Hookup Drawing - Conductivity Analyser" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | AWC | 2025-10-23 | A | 001785 | 2025-10-23 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10325 | 001785 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5411 | A | 131242-WST02-DR-I-5411-A | 2025-10-23 | Hookup Drawing - Conductivity Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5411 | NA | "Hookup Drawing - Conductivity Analyser" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | AWC | 2025-10-23 | A | 001785 | 2025-10-23 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10326 | 001786 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5420 | A | 131242-WST02-DR-I-5420-A | 2025-10-23 | Hookup Drawing - DO Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5420 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing - DO Analyser" | 2024-12-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | AWC | 2025-10-23 | A | 000911&&001786 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10327 | 001786 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5421 | A | 131242-WST02-DR-I-5421-A | 2025-10-23 | Hookup Drawing - DO Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5421 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing - DO Analyser" | 2025-04-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | AWC | 2025-10-23 | A | 000911&&001786 | 2025-04-01, 2025-10-23 | 00, 01 | 2 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10328 | 001787 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5320 | A | 131242-WST02-DR-I-5320-A | 2025-10-23 | Hookup Drawing - pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5320 | NA | "Hookup Drawing - pH Analyser" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | AWC | 2025-10-23 | A | 001787 | 2025-10-23 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10329 | 001787 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5321 | A | 131242-WST02-DR-I-5321-A | 2025-10-23 | Hookup Drawing - pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5321 | NA | "Hookup Drawing - pH Analyser" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | AWC | 2025-10-23 | A | 001787 | 2025-10-23 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10330 | 001787 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5322 | A | 131242-WST02-DR-I-5322-A | 2025-10-23 | Hookup Drawing - pH Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5322 | NA | "Hookup Drawing - pH Analyser" | 2025-10-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 53 | AWC | 2025-10-23 | A | 001787 | 2025-10-23 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10331 | 001788 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5400 | A | 131242-WST02-DR-I-5400-A | 2025-10-23 | Hookup Drawing -TSS Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5400 | NA | "Hookup Drawing -TSS Analyser" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | AWC | 2025-12-18 | F | 000753&&000836&&001730&&001788&&001914 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00 | 5 | Not Approved | NAP |  |  | 0 | AWC | AWC
10332 | 001788 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5401 | A | 131242-WST02-DR-I-5401-A | 2025-10-23 | Hookup Drawing -TSS Analyser | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-20 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5401 | NA | "GA Drawing for FRP Tank" && "Hookup Drawing -TSS Analyser" | 2024-12-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-06 | 53 | AWC | 2025-10-23 | A | 000911&&001788 | 2024-12-17, 2025-04-01, 2025-10-23 | 00, 01 | 3 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10333 | 001789 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | ST617 THP-PF-01 | A | 131242-WSD11-SD-S-ST617 THP-PF-01 -A | 2025-10-24 | ST617 THP-PF-01 Shop Drawing - Additional Grating Support Beams At TOS 15.875 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-21 | 2025-12-19 | Approved with Comments | 2026-01-08 | NO | Overdue |  | 131242-WSD11-SD-ST617 THP-PF-01 | NA | "ST617 THP-PF-01 Shop Drawing - Additional Grating Support Beams At TOS 15.875" | 2025-10-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-13 | 56 | AWC | 2025-10-24 | A | 001789 | 2025-10-24 | 00 | 1 | Approved with Comments | AWC | 2026-01-08 | Overdue | 0 | AWC | AWC
10334 | 001790 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | ST617 THP-PF-01 Platform & Railing | A | 131242-WSD11-SD-S-ST617 THP-PF-01 Platform & Railing-A | 2025-10-24 | ST617 THP-PF-01 Platform & Railing Fab Drawings (PE Endrosed) | Rev-0 Approved with Comments. Please refer to the comment sheet for the comments. | 2025-11-21 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WSD11-SD-ST617 THP-PF-01 Platform & Railing | NA | "ST617 THP-PF-01 Platform & Railing Fab Drawings (PE Endrosed)" | 2025-10-24 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-13 | 46 | AWC | 2025-10-24 | A | 001790 | 2025-10-24 | 00 | 1 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
10335 | 001791 | 00 | Yibo | Mech | NA | 131242 | WST11 | DR | M | 5475 | A | 131242-WST11-DR-M-5475-A | 2025-10-27 | Rectangular Bellow Drawing | Rev 0: Approved | 2025-11-24 | 2025-11-24 | Approved |  | YES | NA |  | 131242-WST11-DR-5475 | NA | "Rectangular Bellow Drawing" | 2025-10-27 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Department not in department_schema | 2025-11-16 | 28 | APP | 2025-10-27 | A | 001791 | 2025-10-27 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10336 | 001792 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | B | 0006 | 0 | 131242-WST02-VI-B-0006-0 | 2025-10-27 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-24 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-VI-0006 | NA | "Vendor Approval of Epoxy Coating - ISO Team C&P Pte. ltd." && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Drager)" && "Vendor Approval of SS Cable Ladder, Trays and Accessories" && "Vendor Approval of SSN Package (pH Analyzer)" | 2024-03-11 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-10 | 45 | AWC | 2025-10-27 | 0 | 000350&&000592&&001168&&001792 | 2024-03-11, 2024-07-28, 2024-12-05, 2025-03-26, 2025-10-27 | 00, 01 | 5 | Approved with Comments | AWC | 2025-12-31 | Overdue | 0 | AWC | AWC
10337 | 001793 | 00 | Karthik | EICA | NA | 131242 | WST02 | IP | BM | 1071 | A | 131242-WST02-IP-BM-1071-A | 2025-10-27 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-24 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-IP-1071 | NA | "BMS Panel GA & Wiring Drawing " | 2025-10-27 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-16 | 45 | NAP | 2025-10-27 | A | 001793 | 2025-10-27 | 00 | 1 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
10338 | 001793 | 00 | Karthik | EICA | NA | 131242 | WST02 | IP | BM | 1001 | A | 131242-WST02-IP-BM-1001-A | 2025-10-27 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-24 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-IP-1001 | NA | "BMS Panel GA & Wiring Drawing " | 2025-10-27 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-16 | 45 | NAP | 2025-10-27 | A | 001793 | 2025-10-27 | 00 | 1 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
10339 | 001793 | 00 | Karthik | EICA | NA | 131242 | WST02 | IP | BM | 1031 | A | 131242-WST02-IP-BM-1031-A | 2025-10-27 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-11-24 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-IP-1031 | NA | "BMS Panel GA & Wiring Drawing " | 2025-10-27 | NO | YES | Project_Code not in project_schema; Document_Type not in document_type_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-16 | 45 | NAP | 2025-10-27 | A | 001793 | 2025-10-27 | 00 | 1 | Not Approved | NAP | 2025-12-31 | Overdue | 0 | NAP | NAP
10340 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1001 | A | 131242-WST02-DR-BM-1001-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | PEN | PEN
10341 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1002 | A | 131242-WST02-DR-BM-1002-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | PEN | PEN
10342 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1003 | A | 131242-WST02-DR-BM-1003-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | PEN | PEN
10343 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1004 | A | 131242-WST02-DR-BM-1004-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | PEN | PEN
10344 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1005 | A | 131242-WST02-DR-BM-1005-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | PEN | PEN
10345 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1006 | A | 131242-WST02-DR-BM-1006-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | PEN | PEN
10346 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1007 | A | 131242-WST02-DR-BM-1007-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1007 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN_CAT Ladder " | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000418&&000831&&001144&&001402&&001528&&001793 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-04, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 13 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10347 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1008 | A | 131242-WST02-DR-BM-1008-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1008 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN_CAT Ladder " | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000163&&000831&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-04, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10348 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1009 | A | 131242-WST02-DR-BM-1009-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | PEN | PEN
10349 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1010 | A | 131242-WST02-DR-BM-1010-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1010 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-09 | A.6 | 000163&&001144&&001402&&001528&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2026-01-28, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10350 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1011 | A | 131242-WST02-DR-BM-1011-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1011 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 2 SSN Electrical Building" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" && "SSN Water Tank Wier 1 and 2 TOC and Rebar Details" && "Shop Drawing for SWPR-03 Platform A&B Cat ladder" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000162&&000191&&000419&&001144&&001284&&001402&&001656&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-09, 2025-05-13, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-09-08, 2025-10-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03, 04 | 14 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10351 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1012 | A | 131242-WST02-DR-BM-1012-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1012 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000163&&000191&&000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10352 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1013 | A | 131242-WST02-DR-BM-1013-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1013 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Public Address System" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000419&&001144&&001402&&001793 | 2024-04-04, 2024-10-18, 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10353 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1014 | A | 131242-WST02-DR-BM-1014-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1014 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000164&&001144&&001402&&001793 | 2025-03-21, 2025-04-22, 2025-06-23, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10354 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1015 | A | 131242-WST02-DR-BM-1015-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1015 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10355 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1016 | A | 131242-WST02-DR-BM-1016-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1016 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Water Tank" && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000163&&001144&&001402&&001793 | 2025-03-21, 2025-04-28, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10356 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1017 | A | 131242-WST02-DR-BM-1017-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1017 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10357 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1018 | A | 131242-WST02-DR-BM-1018-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1018 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10358 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1019 | A | 131242-WST02-DR-BM-1019-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1019 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10359 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1020 | A | 131242-WST02-DR-BM-1020-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1020 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10360 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1021 | A | 131242-WST02-DR-BM-1021-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1021 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN ECCP-1000- GA & Wiring Diagram" | 2025-03-21 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001144&&001402&&001793 | 2025-03-21, 2025-06-23, 2025-08-19, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10361 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1022 | A | 131242-WST02-DR-BM-1022-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1022 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 Underground Services" && "Piping General Arrangement-UG & Plant Drain Manholes" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000161&&000429&&001402&&001793 | 2024-04-09, 2024-07-10, 2024-10-05, 2025-06-23, 2025-08-27, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10362 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1023 | A | 131242-WST02-DR-BM-1023-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | PEN | PEN
10363 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1024 | A | 131242-WST02-DR-BM-1024-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | PEN | PEN
10364 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1025 | A | 131242-WST02-DR-BM-1025-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | PEN | PEN
10365 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1026 | A | 131242-WST02-DR-BM-1026-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | PEN | PEN
10366 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1027 | A | 131242-WST02-DR-BM-1027-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1027 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10367 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1028 | A | 131242-WST02-DR-BM-1028-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1028 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10368 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1031 | A | 131242-WST02-DR-BM-1031-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1031 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10369 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1032 | A | 131242-WST02-DR-BM-1032-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1032 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10370 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1033 | A | 131242-WST02-DR-BM-1033-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1033 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10371 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1034 | A | 131242-WST02-DR-BM-1034-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1034 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-04 | 1 | 001176&&001402&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10372 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1035 | A | 131242-WST02-DR-BM-1035-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1035 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10373 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1036 | A | 131242-WST02-DR-BM-1036-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1036 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10374 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1037 | A | 131242-WST02-DR-BM-1037-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1037 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10375 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1038 | A | 131242-WST02-DR-BM-1038-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1038 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10376 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1039 | A | 131242-WST02-DR-BM-1039-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1039 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10377 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1040 | A | 131242-WST02-DR-BM-1040-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1040 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10378 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1041 | A | 131242-WST02-DR-BM-1041-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1041 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10379 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1042 | A | 131242-WST02-DR-BM-1042-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1042 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10380 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1043 | A | 131242-WST02-DR-BM-1043-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1043 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10381 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1044 | A | 131242-WST02-DR-BM-1044-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1044 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10382 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1045 | A | 131242-WST02-DR-BM-1045-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1045 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10383 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1046 | A | 131242-WST02-DR-BM-1046-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1046 | NA | "BMS Panel GA & Wiring Drawing " && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" | 2025-03-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001176&&001793 | 2025-03-28, 2025-07-11, 2025-11-17, 2026-01-28 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10384 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1047 | A | 131242-WST02-DR-BM-1047-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1047 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10385 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1048 | A | 131242-WST02-DR-BM-1048-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1048 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10386 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1049 | A | 131242-WST02-DR-BM-1049-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1049 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10387 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1050 | A | 131242-WST02-DR-BM-1050-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1050 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10388 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1051 | A | 131242-WST02-DR-BM-1051-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1051 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10389 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1052 | A | 131242-WST02-DR-BM-1052-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1052 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10390 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1053 | A | 131242-WST02-DR-BM-1053-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1053 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10391 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1054 | A | 131242-WST02-DR-BM-1054-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1054 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10392 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1055 | A | 131242-WST02-DR-BM-1055-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1055 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10393 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1056 | A | 131242-WST02-DR-BM-1056-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1056 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10394 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1057 | A | 131242-WST02-DR-BM-1057-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1057 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10395 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1058 | A | 131242-WST02-DR-BM-1058-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1058 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10396 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1059 | A | 131242-WST02-DR-BM-1059-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1059 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10397 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1060 | A | 131242-WST02-DR-BM-1060-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1060 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10398 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1061 | A | 131242-WST02-DR-BM-1061-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1061 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10399 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1062 | A | 131242-WST02-DR-BM-1062-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1062 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10400 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1063 | A | 131242-WST02-DR-BM-1063-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1063 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10401 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1064 | A | 131242-WST02-DR-BM-1064-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1064 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10402 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1065 | A | 131242-WST02-DR-BM-1065-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1065 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10403 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1066 | A | 131242-WST02-DR-BM-1066-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1066 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10404 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1067 | A | 131242-WST02-DR-BM-1067-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1067 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10405 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1068 | A | 131242-WST02-DR-BM-1068-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1068 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10406 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1071 | A | 131242-WST02-DR-BM-1071-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1071 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10407 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1072 | A | 131242-WST02-DR-BM-1072-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1072 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10408 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1073 | A | 131242-WST02-DR-BM-1073-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1073 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10409 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1074 | A | 131242-WST02-DR-BM-1074-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1074 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10410 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1075 | A | 131242-WST02-DR-BM-1075-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1075 | NA | "BMS Panel GA & Wiring Drawing " && "SSN RIO 0001A GA & Wiring Diagram" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | A | 001145&&001793 | 2025-03-21, 2025-08-19, 2026-01-28 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10411 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1076 | A | 131242-WST02-DR-BM-1076-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1076 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10412 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1077 | A | 131242-WST02-DR-BM-1077-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1077 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10413 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1078 | A | 131242-WST02-DR-BM-1078-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1078 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10414 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1079 | A | 131242-WST02-DR-BM-1079-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1079 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10415 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1080 | A | 131242-WST02-DR-BM-1080-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1080 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10416 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1081 | A | 131242-WST02-DR-BM-1081-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1081 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10417 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1082 | A | 131242-WST02-DR-BM-1082-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1082 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10418 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1083 | A | 131242-WST02-DR-BM-1083-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1083 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10419 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1084 | A | 131242-WST02-DR-BM-1084-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1084 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10420 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1085 | A | 131242-WST02-DR-BM-1085-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1085 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10421 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1086 | A | 131242-WST02-DR-BM-1086-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1086 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10422 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1087 | A | 131242-WST02-DR-BM-1087-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1087 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10423 | 001793 | 01 | M Balaji | EICA | NA | 131242 | WST02 | DR | BM | 1088 | A | 131242-WST02-DR-BM-1088-A | 2026-01-28 | BMS Panel GA & Wiring Drawing | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1088 | NA | "BMS Panel GA & Wiring Drawing " | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001793 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10424 | 001794 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0058 | 0 | 131242-WSW41-QA-E-0058-0 | 2025-10-27 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Distribution Board (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-24 | 2026-02-02 | Approved with Comments | 2026-02-20 | NO | Overdue |  | 131242-WSW41-QA-0058 | NA | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Distribution Board (GSM)" | 2025-10-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-16 | 98 | AWC | 2025-10-27 | 0 | 001794 | 2025-10-27 | 00 | 1 | Approved with Comments | AWC | 2026-02-20 | Overdue | 0 | AWC | AWC
10425 | 001795 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | I | 0003 | 0 | 131242-WST02-CD-I-0003-0 | 2025-10-28 | SSN Master Blower HMI Graphic List and Graphic Screen | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-11-25 | 2025-12-09 | Approved with Comments | 2025-12-29 | NO | Overdue |  | 131242-WST02-CD-0003 | NA | "SSN Master Blower HMI Graphic List and Graphic Screen" | 2025-10-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-17 | 42 | AWC | 2025-10-28 | 0 | 001795 | 2025-10-28 | 00 | 1 | Approved with Comments | AWC | 2025-12-29 | Overdue | 0 | AWC | AWC
10426 | 001796 | 00 | Bryan | Mech | NA | 131242 | WSW41 | MS | BH | 0001 | 0 | 131242-WSW41-MS-BH-0001-0 | 2025-10-28 | MSRA, SWP for ACMV System works | NA | 2025-11-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 160 | PEN | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | PEN | PEN
10427 | 001797 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | E | 0016 | 0 | 131242-WSW41-MS-E-0016-0 | 2025-10-28 | MSRA for MCCB Replacement Works | Rev 0: For Information | 2025-11-25 | 2026-02-02 | For Information |  | YES | NA |  | 131242-WSW41-MS-0016 | NA | "MSRA for MCCB Replacement Works" && "MSRA, SWP for Erection, Dismantling and Use of Scaffold " && "MSRA, SWP for FRP Tanks Defect Repair Lamination Works " | 2024-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-11 | 97 | INF | 2025-10-28 | 0 | 000632&&001797&&001798 | 2024-08-12, 2025-10-28 | 00 | 3 | For Information | INF | 2026-02-20 | Overdue | 0 | INF | INF
10428 | 001798 | 00 | Bryan | EICA | NA | 131242 | WSW41 | MS | M | 0016 | 0 | 131242-WSW41-MS-M-0016-0 | 2025-10-28 | MSRA, SWP for FRP Tanks Defect Repair Lamination Works | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-25 | 2025-12-29 | Approved with Comments | 2026-01-16 | NO | Overdue |  | 131242-WSW41-MS-0016 | NA | "MSRA for MCCB Replacement Works" && "MSRA, SWP for Erection, Dismantling and Use of Scaffold " && "MSRA, SWP for FRP Tanks Defect Repair Lamination Works " | 2024-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-11 | 62 | AWC | 2025-10-28 | 0 | 000632&&001797&&001798 | 2024-08-12, 2025-10-28 | 00 | 3 | For Information | INF | 2026-01-16 | Overdue | 0 | AWC | AWC
10429 | 001799 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | E | 0059 | 0 | 131242-WSW41-QA-E-0059-0 | 2025-10-29 | Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM) | Rev 0: Not approved - Revise and Resubmit. Refer to attached file for comments. | 2025-11-26 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WSW41-QA-0059 | NA | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" && "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | 2025-03-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-12 | 114 | NAP | 2025-12-18 | 1 | 001151&&001799&&001860 | 2025-03-24, 2025-10-29, 2025-11-24, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
10430 | 001800 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | M | 0026 | 0 | 131242-WSW41-PO-M-0026-0 | 2025-10-31 | Unpriced PO for Valve for Condensate System (Spirax Sarco) | Rev 0: For Information | 2025-11-28 | 2025-11-24 | For Information |  | YES | NA |  | 131242-WSW41-PO-0026 | NA | "Unpriced PO for Air Conditioning and Mechanical Ventilation System (Poh Meng)" && "Unpriced PO for Valve for Condensate System (Spirax Sarco)" | 2025-08-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-14 | 24 | INF | 2025-10-31 | 0 | 001615&&001800 | 2025-08-22, 2025-10-31 | 00 | 2 | For Information | INF | 2025-12-12 | Overdue | 0 | INF | INF
10431 | 001801 | 00 | Caedan | Contracts | NA | 131242 | WSW41 | PO | M | 0027 | 0 | 131242-WSW41-PO-M-0027-0 | 2025-10-31 | Unpriced PO for Manual Lifting Equipment (Growa) | Rev 0: For Information Only. | 2025-11-28 |  | For Information |  | YES | NA |  | 131242-WSW41-PO-0027 | NA | "Unpriced PO for Manual Lifting Equipment (Growa)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-11-20 | 157 | INF | 2025-10-31 | 0 | 001801 | 2025-10-31 | 00 | 1 | For Information | INF | 2025-12-18 |  | 0 | INF | INF
10432 | 001802 | 00 | Aaron | CSA | NA | 131242 | WSD11 | SD | S | THP-PF-01 & 02 Cat ladders | A | 131242-WSD11-SD-S-THP-PF-01 & 02 Cat ladders -A | 2025-10-31 | Shop Drawing for THP-PF-01 & 02 Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2026-01-12 | Not Approved | 2026-01-30 | NO | Overdue |  | 131242-WSD11-SD-THP-PF-01 & 02 Cat ladders | NA | "Shop Drawing for THP-PF-01 & 02 Cat ladders " | 2025-10-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 73 | NAP | 2025-10-31 | A | 001802 | 2025-10-31 | 00 | 1 | Not Approved | NAP | 2026-01-30 | Overdue | 0 | NAP | NAP
10433 | 001803 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | SSN Area and Electrical Building Cat ladders | A | 131242-WST02-SD-S-SSN Area and Electrical Building Cat ladders -A | 2025-10-31 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-SD-SSN Area and Electrical Building Cat ladders | NA | "Shop Drawing for SSN Area and Electrical Building Cat ladders " | 2025-10-31 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 73 | NAP | 2025-10-31 | A | 001803 | 2025-10-31 | 00 | 1 | Not Approved | NAP | 2026-01-30 | Overdue | 0 | NAP | NAP
10434 | 001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1007 | A.5 | 131242-WST02-SD-S-1007-A.5 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-SD-1007 | NA | "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " | 2025-08-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.5 | 001616&&001698&&001803 | 2025-08-22, 2025-09-26, 2026-02-09 | 00, 01 | 3 | Not Approved | NAP | 2026-03-27 |  | 0 | PEN | PEN
10435 | 001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5003 | A.5 | 131242-WST02-SD-S-5003-A.5 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-SD-5003 | NA | "ST617 THP-PF-02 Shop Drawing Submission" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " | 2025-07-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.5 | 001498&&001698&&001803 | 2025-07-22, 2025-09-26, 2026-02-09 | 00, 01 | 3 | Not Approved | NAP | 2026-03-27 |  | 0 | PEN | PEN
10436 | 001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5004 | A.5 | 131242-WST02-SD-S-5004-A.5 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-SD-5004 | NA | "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-09-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.5 | 001698&&001700&&001803 | 2025-09-26, 2025-09-29, 2026-02-09 | 00, 01 | 3 | Rejected | REJ | 2026-03-27 |  | 0 | PEN | PEN
10437 | 001803 | 01 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A.5 | 131242-WST02-SD-S-8600-A.5 | 2026-02-09 | Shop Drawing for SSN Area and Electrical Building Cat ladders | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-03-27 |  | 0 | PEN | PEN
10438 | 001804 | 00 | Joo Kwan | Process | NA | 131242 | WSD11 | PS | P | 0002 | 0 | 131242-WSD11-PS-P-0002-0 | 2025-10-31 | THP Functional Design Specification Workshop | The document is accepted for information only. | 2025-11-28 | 2026-02-09 | For Information |  | YES | NA |  | 131242-WSD11-PS-0002 | NA | "THP Functional Design Specification Workshop" | 2025-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-20 | 101 | INF | 2025-10-31 | 0 | 001804 | 2025-10-31 | 00 | 1 | For Information | INF | 2026-02-27 | Overdue | 0 | INF | INF
10439 | 001805 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0076 | 0 | 131242-WSW41-LT-PM-0076-0 | 2025-10-31 | CV of Team Member (ECO) | Approved | 2025-11-28 | 2025-12-10 | Approved |  | YES | NA |  | 131242-WSW41-LT-0076 | NA | "CV of Team Member (ECO)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-20 | 40 | APP | 2025-10-31 | 0 | 001805 | 2025-10-31 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10440 | 001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7300 | A | 131242-WST02-DR-EI-7300-A | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-7300 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 27 | AWC | 2026-02-03 | B | 001806&&001985 | 2025-10-31, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10441 | 001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3100 | A | 131242-WST02-DR-EP-3100-A | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-3100 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 27 | AWC | 2026-02-03 | B | 001806 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10442 | 001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3101 | A | 131242-WST02-DR-EP-3101-A | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-3101 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 27 | AWC | 2026-02-03 | B | 001806 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10443 | 001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7200 | A | 131242-WST02-DR-EP-7200-A | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-7200 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 27 | AWC | 2026-02-03 | B | 001157&&001806 | 2025-03-25, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10444 | 001806 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7201 | A | 131242-WST02-DR-EP-7201-A | 2025-10-31 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-11-27 | Approved with Comments | 2025-12-17 | YES | Resubmitted |  | 131242-WST02-DR-7201 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 27 | AWC | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10445 | 001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7300 | B | 131242-WST02-DR-EI-7300-B | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7300 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001806&&001985 | 2025-10-31, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10446 | 001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3100 | B | 131242-WST02-DR-EP-3100-B | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3100 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001806 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10447 | 001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3101 | B | 131242-WST02-DR-EP-3101-B | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3101 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001806 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10448 | 001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7200 | B | 131242-WST02-DR-EP-7200-B | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7200 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001806 | 2025-03-25, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10449 | 001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7201 | B | 131242-WST02-DR-EP-7201-B | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7201 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10450 | 001806 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7202 | B | 131242-WST02-DR-EP-7202-B | 2026-02-03 | SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7202 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001190&&001806 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10451 | 001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7302 | A | 131242-WST02-DR-EI-7302-A | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7302 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 39 | AWC | 2026-02-03 | B | 001807&&001985 | 2025-10-31, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10452 | 001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3102 | A | 131242-WST02-DR-EP-3102-A | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-3102 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 39 | AWC | 2026-02-03 | B | 001807 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10453 | 001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3103 | A | 131242-WST02-DR-EP-3103-A | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-3103 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 39 | AWC | 2026-02-03 | B | 001807 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10454 | 001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7205 | A | 131242-WST02-DR-EP-7205-A | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7205 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | AWC | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10455 | 001807 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7206 | A | 131242-WST02-DR-EP-7206-A | 2025-10-31 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7206 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | AWC | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10456 | 001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7302 | B | 131242-WST02-DR-EI-7302-B | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7302 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001807&&001985 | 2025-10-31, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10457 | 001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3102 | B | 131242-WST02-DR-EP-3102-B | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3102 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001807 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10458 | 001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3103 | B | 131242-WST02-DR-EP-3103-B | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3103 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001807 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10459 | 001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7205 | B | 131242-WST02-DR-EP-7205-B | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7205 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10460 | 001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7206 | B | 131242-WST02-DR-EP-7206-B | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7206 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2025-10-31, 2026-02-03 | 00, 01 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10461 | 001807 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7207 | B | 131242-WST02-DR-EP-7207-B | 2026-02-03 | SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7207 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-0001A & 0001B SLD, Schematic, GA Drawing" && "SSN UPSDB SLD " | 2025-03-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | B | 001157&&001190&&001807 | 2025-03-25, 2025-04-03, 2025-07-21, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
10462 | 001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3016 | A | 131242-WST02-DR-BE-3016-A | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | NAP | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10463 | 001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3020 | A | 131242-WST02-DR-BE-3020-A | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | NAP | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10464 | 001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7025 | A | 131242-WST02-DR-BE-7025-A | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10465 | 001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7026 | A | 131242-WST02-DR-BE-7026-A | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7026 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10466 | 001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7027 | A | 131242-WST02-DR-BE-7027-A | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7027 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10467 | 001808 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7028 | A | 131242-WST02-DR-BE-7028-A | 2025-10-31 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Not Approved | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7028 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | NAP | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10468 | 001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3016 | B | 131242-WST02-DR-BE-3016-B | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3016 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SDB-0003 SLD, Schematic and GA Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001165&&001559&&001808 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-07-01, 2025-08-05, 2025-08-22, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10469 | 001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3020 | B | 131242-WST02-DR-BE-3020-B | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10470 | 001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7025 | B | 131242-WST02-DR-BE-7025-B | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7025 | NA | "LVSG Schematic Diagram" && "SSN Control Network Connection Drawing" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000604&&000605&&000660&&001808 | 2024-08-01, 2024-08-19, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10471 | 001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7026 | B | 131242-WST02-DR-BE-7026-B | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7026 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10472 | 001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7027 | B | 131242-WST02-DR-BE-7027-B | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7027 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10473 | 001808 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7028 | B | 131242-WST02-DR-BE-7028-B | 2026-02-03 | SSN LDB-0004 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7028 | NA | "LVSG Schematic Diagram" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000604&&000605&&001808 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-05-04, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10474 | 001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3020 | A | 131242-WST02-DR-BE-3020-A | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10475 | 001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3021 | A | 131242-WST02-DR-BE-3021-A | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10476 | 001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7030 | A | 131242-WST02-DR-BE-7030-A | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7030 | NA | "LVSG Schematic Diagram" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 39 | AWC | 2026-02-03 | B | 000604&&000605&&001809 | 2024-08-01, 2024-11-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10477 | 001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7031 | A | 131242-WST02-DR-BE-7031-A | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7031 | NA | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 39 | AWC | 2026-02-03 | B | 001809 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10478 | 001809 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7032 | A | 131242-WST02-DR-BE-7032-A | 2025-10-31 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2025-11-28 | 2025-12-09 | Approved with Comments | 2025-12-29 | YES | Resubmitted |  | 131242-WST02-DR-7032 | NA | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 39 | AWC | 2026-02-03 | B | 001809 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10479 | 001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3021 | B | 131242-WST02-DR-BE-3021-B | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10480 | 001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3025 | B | 131242-WST02-DR-BE-3025-B | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3025 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000870&&001809&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10481 | 001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7030 | B | 131242-WST02-DR-BE-7030-B | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7030 | NA | "LVSG Schematic Diagram" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LVSG 0101AB Single Line Diagram" | 2024-08-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000604&&000605&&001809 | 2024-08-01, 2024-11-21, 2025-10-31, 2026-02-03 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10482 | 001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7031 | B | 131242-WST02-DR-BE-7031-B | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7031 | NA | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 001809 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10483 | 001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7032 | B | 131242-WST02-DR-BE-7032-B | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7032 | NA | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 001809 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10484 | 001809 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7033 | B | 131242-WST02-DR-BE-7033-B | 2026-02-03 | SSN LDB-0005 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7033 | NA | "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 23 | AWC | 2026-02-03 | B | 001809 | 2026-02-03 | 01 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10485 | 001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3025 | A | 131242-WST02-DR-BE-3025-A | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3025 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000870&&001809&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10486 | 001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3026 | A | 131242-WST02-DR-BE-3026-A | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10487 | 001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7035 | A | 131242-WST02-DR-BE-7035-A | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7035 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-02-03 | B | 001810 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10488 | 001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7036 | A | 131242-WST02-DR-BE-7036-A | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7036 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-02-03 | B | 001810 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10489 | 001810 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7037 | A | 131242-WST02-DR-BE-7037-A | 2025-10-31 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7037 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-02-03 | B | 001810 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10490 | 001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3025 | B | 131242-WST02-DR-BE-3025-B | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3025 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000870&&001809&&001810 | 2024-12-03, 2025-04-08, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10491 | 001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3026 | B | 131242-WST02-DR-BE-3026-B | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3026 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000164&&000870&&001810 | 2024-12-03, 2025-04-08, 2025-04-22, 2025-07-24, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 7 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10492 | 001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7035 | B | 131242-WST02-DR-BE-7035-B | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7035 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 001810 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10493 | 001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7036 | B | 131242-WST02-DR-BE-7036-B | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7036 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 001810 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10494 | 001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7037 | B | 131242-WST02-DR-BE-7037-B | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7037 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 001810 | 2025-10-31, 2026-02-03 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10495 | 001810 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7038 | B | 131242-WST02-DR-BE-7038-B | 2026-02-03 | SSN LDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7038 | NA | "SSN LDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-02-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 23 | AWC | 2026-02-03 | B | 001810 | 2026-02-03 | 01 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10496 | 001811 | 00 | Bryan | Mech | NA | 131242 | WSW41 | MS | M | 0017 | 0 | 131242-WSW41-MS-M-0017-0 | 2025-10-31 | MSRA & Safe Work Procedure For NDT Activities | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-11-28 | 2025-12-29 | Approved with Comments |  | YES | NA |  | 131242-WSW41-MS-0017 | NA | "MSRA & Safe Work Procedure For NDT Activities" && "MSRA, SWP for Jet Grouting" | 2024-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-14 | 59 | AWC | 2025-10-31 | 0 | 000633&&001811 | 2024-08-12, 2025-10-31 | 00 | 2 | Approved with Comments | AWC | 2026-01-16 | Overdue | 0 | AWC | AWC
10497 | 001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3030 | A | 131242-WST02-DR-BE-3030-A | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10498 | 001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3031 | A | 131242-WST02-DR-BE-3031-A | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10499 | 001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7040 | A | 131242-WST02-DR-BE-7040-A | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7040 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10500 | 001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7041 | A | 131242-WST02-DR-BE-7041-A | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7041 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10501 | 001812 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7042 | A | 131242-WST02-DR-BE-7042-A | 2025-10-31 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7042 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10502 | 001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3030 | B | 131242-WST02-DR-BE-3030-B | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3030 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10503 | 001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3031 | B | 131242-WST02-DR-BE-3031-B | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3031 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 SSN Water Tank" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" && "SSN PMS Panel GA and Wiring Diagram" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000163&&000870&&001702&&001812 | 2024-12-03, 2025-04-08, 2025-04-28, 2025-07-24, 2025-09-29, 2025-10-31, 2026-02-03 | 00, 01, 02 | 7 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10504 | 001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7040 | B | 131242-WST02-DR-BE-7040-B | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7040 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10505 | 001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7041 | B | 131242-WST02-DR-BE-7041-B | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7041 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10506 | 001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7042 | B | 131242-WST02-DR-BE-7042-B | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7042 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10507 | 001812 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7043 | B | 131242-WST02-DR-BE-7043-B | 2026-02-03 | SSN LDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7043 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001812 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10508 | 001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3035 | A | 131242-WST02-DR-BE-3035-A | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3035 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-0102A/B" && "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2025-10-31 | A | 000162&&000870&&001813 | 2024-12-03, 2025-04-08, 2025-04-09, 2025-07-24, 2025-10-27, 2025-10-31 | 00, 01, 02, 03, 04 | 6 | Approved with Comments | AWC | 2025-12-31 | Overdue | 0 | AWC | AWC
10509 | 001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3036 | A | 131242-WST02-DR-BE-3036-A | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3036 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000162&&001813 | 2025-04-09, 2025-10-27, 2025-10-31, 2026-02-03 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10510 | 001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7045 | A | 131242-WST02-DR-BE-7045-A | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7045 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10511 | 001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7046 | A | 131242-WST02-DR-BE-7046-A | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7046 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10512 | 001813 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7047 | A | 131242-WST02-DR-BE-7047-A | 2025-10-31 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7047 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-14 | 41 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10513 | 001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3036 | B | 131242-WST02-DR-BE-3036-B | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3036 | NA | "Milestone 2 - SSN Pump Station and Blower Area" && "Milestone 3 - SSN Pump Station and Blower Area" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2025-04-09 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000162&&001813 | 2025-04-09, 2025-10-27, 2025-10-31, 2026-02-03 | 00, 01, 03, 04 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10514 | 001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 3040 | B | 131242-WST02-DR-BE-3040-B | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3040 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000867&&001813 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10515 | 001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7045 | B | 131242-WST02-DR-BE-7045-B | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7045 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10516 | 001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7046 | B | 131242-WST02-DR-BE-7046-B | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7046 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10517 | 001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7047 | B | 131242-WST02-DR-BE-7047-B | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7047 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2025-10-31, 2026-02-03 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10518 | 001813 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | BE | 7048 | B | 131242-WST02-DR-BE-7048-B | 2026-02-03 | SSN LDB-0008 SLD, Schematic and GA Drawing (GSM) | Rev 1: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7048 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0008 SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | B | 000866&&001813 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
10519 | 001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7320 | A | 131242-WST02-DR-EI-7320-A | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7320 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10520 | 001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3120 | A | 131242-WST02-DR-EP-3120-A | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3120 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10521 | 001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3121 | A | 131242-WST02-DR-EP-3121-A | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3121 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10522 | 001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7255 | A | 131242-WST02-DR-EP-7255-A | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7255 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10523 | 001814 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7256 | A | 131242-WST02-DR-EP-7256-A | 2025-10-31 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-11 | Approved with Comments | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7256 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | AWC | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10524 | 001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7320 | B | 131242-WST02-DR-EI-7320-B | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7320 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10525 | 001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3120 | B | 131242-WST02-DR-EP-3120-B | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3120 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10526 | 001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3121 | B | 131242-WST02-DR-EP-3121-B | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3121 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10527 | 001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7255 | B | 131242-WST02-DR-EP-7255-B | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7255 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10528 | 001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7256 | B | 131242-WST02-DR-EP-7256-B | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7256 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001814 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-16 |  | 0 | PEN | PEN
10529 | 001814 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7257 | B | 131242-WST02-DR-EP-7257-B | 2026-01-27 | SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7257 | NA | "SSN UPSDB-0002 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | B | 001814 | 2026-01-27 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10530 | 001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7322 | A | 131242-WST02-DR-EI-7322-A | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7322 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10531 | 001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3122 | A | 131242-WST02-DR-EP-3122-A | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3122 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10532 | 001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3123 | A | 131242-WST02-DR-EP-3123-A | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-3123 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10533 | 001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7260 | A | 131242-WST02-DR-EP-7260-A | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7260 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10534 | 001815 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7261 | A | 131242-WST02-DR-EP-7261-A | 2025-10-31 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | YES | Resubmitted |  | 131242-WST02-DR-7261 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10535 | 001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7322 | B | 131242-WST02-DR-EI-7322-B | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7322 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10536 | 001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3122 | B | 131242-WST02-DR-EP-3122-B | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3122 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10537 | 001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3123 | B | 131242-WST02-DR-EP-3123-B | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3123 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10538 | 001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7260 | B | 131242-WST02-DR-EP-7260-B | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7260 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10539 | 001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7261 | B | 131242-WST02-DR-EP-7261-B | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7261 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-01-27 | B | 001815 | 2025-10-31, 2026-01-27 | 00, 01 | 2 | Not Approved | NAP | 2026-03-16 |  | 0 | PEN | PEN
10540 | 001815 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7262 | B | 131242-WST02-DR-EP-7262-B | 2026-01-27 | SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7262 | NA | "SSN UPSDB-0003 SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | B | 001815 | 2026-01-27 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10541 | 001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7328 | A | 131242-WST02-DR-EI-7328-A | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-7328 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10542 | 001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3128 | A | 131242-WST02-DR-EP-3128-A | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-3128 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10543 | 001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3129 | A | 131242-WST02-DR-EP-3129-A | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-3129 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10544 | 001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7275 | A | 131242-WST02-DR-EP-7275-A | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-7275 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10545 | 001816 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7276 | A | 131242-WST02-DR-EP-7276-A | 2025-10-31 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-7276 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10546 | 001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7328 | B | 131242-WST02-DR-EI-7328-B | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7328 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10547 | 001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3128 | B | 131242-WST02-DR-EP-3128-B | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3128 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10548 | 001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3129 | B | 131242-WST02-DR-EP-3129-B | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3129 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10549 | 001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7275 | B | 131242-WST02-DR-EP-7275-B | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7275 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10550 | 001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7276 | B | 131242-WST02-DR-EP-7276-B | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7276 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001816 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10551 | 001816 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7277 | B | 131242-WST02-DR-EP-7277-B | 2026-01-28 | SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7277 | NA | "SSN UPSDB-0006 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | B | 001816 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10552 | 001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7330 | A | 131242-WST02-DR-EI-7330-A | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | Approved with Comments | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-7330 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 47 | AWC | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10553 | 001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3130 | A | 131242-WST02-DR-EP-3130-A | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | Approved with Comments | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-3130 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 47 | AWC | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10554 | 001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3131 | A | 131242-WST02-DR-EP-3131-A | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | Approved with Comments | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-3131 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 47 | AWC | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10555 | 001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7280 | A | 131242-WST02-DR-EP-7280-A | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | Approved with Comments | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-7280 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 47 | AWC | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10556 | 001817 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7281 | A | 131242-WST02-DR-EP-7281-A | 2025-10-31 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-11-28 | 2025-12-17 | Approved with Comments | 2026-01-06 | YES | Resubmitted |  | 131242-WST02-DR-7281 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 47 | AWC | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10557 | 001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7330 | B | 131242-WST02-DR-EI-7330-B | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7330 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10558 | 001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3130 | B | 131242-WST02-DR-EP-3130-B | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3130 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10559 | 001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3131 | B | 131242-WST02-DR-EP-3131-B | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3131 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10560 | 001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7280 | B | 131242-WST02-DR-EP-7280-B | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7280 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10561 | 001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7281 | B | 131242-WST02-DR-EP-7281-B | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7281 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001817 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-17 |  | 0 | PEN | PEN
10562 | 001817 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7282 | B | 131242-WST02-DR-EP-7282-B | 2026-01-28 | SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7282 | NA | "SSN UPSDB-0007 SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | B | 001817 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10563 | 001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7318 | A | 131242-WST02-DR-EI-7318-A | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-7318 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10564 | 001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3118 | A | 131242-WST02-DR-EP-3118-A | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-3118 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10565 | 001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3119 | A | 131242-WST02-DR-EP-3119-A | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-3119 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10566 | 001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7250 | A | 131242-WST02-DR-EP-7250-A | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-7250 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10567 | 001818 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7251 | A | 131242-WST02-DR-EP-7251-A | 2025-10-31 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2025-11-28 | 2025-12-11 | Not Approved | 2025-12-31 | NO | Overdue |  | 131242-WST02-DR-7251 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-20 | 41 | NAP | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10568 | 001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7318 | B | 131242-WST02-DR-EI-7318-B | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7318 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10569 | 001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3118 | B | 131242-WST02-DR-EP-3118-B | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3118 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10570 | 001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3119 | B | 131242-WST02-DR-EP-3119-B | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3119 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10571 | 001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7250 | B | 131242-WST02-DR-EP-7250-B | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7250 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10572 | 001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7251 | B | 131242-WST02-DR-EP-7251-B | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7251 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | B | 001818 | 2025-10-31, 2026-01-28 | 00, 01 | 2 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10573 | 001818 | 01 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7252 | B | 131242-WST02-DR-EP-7252-B | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM) | Rev 0: Not approved - Revise and Resubmit | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7252 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | B | 001818 | 2026-01-28 | 01 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
10574 | 001819 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0134 | 0 | 131242-WST02-QA-M-0134-0 | 2025-11-04 | FAT Report for Lamella Clarifier Biomass Separator (ARS-5) | NA | 2025-12-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0134 | NA | "FAT Report for Lamella Clarifier Biomass Separator (ARS-5)" | 2025-11-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-24 | 153 | PEN | 2025-11-04 | 0 | 001819 | 2025-11-04 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-22 |  | 0 | PEN | PEN
10575 | 001820 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | DS | M | 5752 | 0 | 131242-WST02-DS-M-5752-0 | 2025-11-05 | Data Sheet for SSN IA Pressure Reducing Valve | NA | 2025-12-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5752 | NA | "Data Sheet for SSN IA Pressure Reducing Valve " | 2025-11-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-25 | 152 | PEN | 2025-11-05 | 0 | 001820 | 2025-11-05 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-23 |  | 0 | PEN | PEN
10576 | 001821 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0135 | 0 | 131242-WSW41-QA-M-0135-0 | 2025-11-05 | FAT Report for SS 316L Pipes - 32 Nos | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-03 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-QA-0135 | NA | "FAT Report for SS 316L Pipes - 32 Nos" | 2025-11-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 86 | AWC | 2025-11-05 | 0 | 001821 | 2025-11-05 | 00 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
10577 | 001822 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5381 | 0 | 131242-WST02-DR-I-5381-0 | 2025-11-05 | Hookup Drawing - Autosampler | NA | 2025-12-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5381 | NA | "Hookup Drawing - Autosampler" && "PC Pump GA Drawing " | 2024-12-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-19 | 152 | PEN | 2025-11-05 | 0 | 000925&&001822 | 2024-12-23, 2025-11-05 | 00 | 2 | Awaiting S.O.'s response | PEN | 2025-12-23 |  | 0 | PEN | PEN
10578 | 001823 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | E | 0060 | 0 | 131242-WSW41-QA-E-0060-0 | 2025-11-05 | FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-03 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSW41-QA-0060 | NA | " FAT Report for Compressor Pipe support in Bio solid building" && "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" && "Factory Acceptance Test Report for Pressure Switch" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-19 | 96 | AWC | 2026-01-13 | 1 | 001175&&001823&&001861 | 2025-03-27, 2025-11-05, 2025-11-24, 2026-01-13 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | AWC | AWC
10579 | 001824 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0137 | 0 | 131242-WSD11-QA-M-0137-0 | 2025-11-05 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2025-12-03 | 2026-01-30 | Not Approved | 2026-02-19 | YES | Resubmitted |  | 131242-WSD11-QA-0137 | NA | "FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite)" | 2025-11-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-25 | 86 | NAP | 2026-02-03 | 1 | 001824 | 2025-11-05, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10580 | 001824 | 01 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0137 | 1 | 131242-WSD11-QA-M-0137-1 | 2026-02-03 | FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite) | Rev 0: Not approved. To revise and resubmit. Refer to attached file for comments. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0137 | NA | "FAT report for Direct Activated Pressure Reducing Valve -Size 1"- PN16 (Pipeline-Elite)" | 2025-11-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | 1 | 001824 | 2025-11-05, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10581 | 001825 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0138 | 0 | 131242-WSW41-QA-M-0138-0 | 2025-11-06 | FAT Report for SS 316L Pipes - 21 Nos | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-04 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-QA-0138 | NA | "FAT Report for SS 316L Pipes - 21 Nos" | 2025-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 85 | AWC | 2025-11-06 | 0 | 001825 | 2025-11-06 | 00 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
10582 | 001826 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0139 | 0 | 131242-WSW41-QA-M-0139-0 | 2025-11-06 | FAT Report for SS 316L Pipes - 40 Nos | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-04 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-QA-0139 | NA | "FAT Report for SS 316L Pipes - 40 Nos" | 2025-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 85 | AWC | 2025-11-06 | 0 | 001826 | 2025-11-06 | 00 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
10583 | 001827 | 00 | Aaron | CSA | NA | 131242 | WSW41 | SD | S | FABRICATION DRAWIG | A | 131242-WSW41-SD-S-FABRICATION DRAWIG-A | 2025-11-06 | Shop Drawing for SWPR-Platform A & B_Railing (PE Endorsed) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-04 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WSW41-SD-FABRICATION DRAWIG | NA | "Shop Drawing for SWPR-Platform A & B_Railing (PE Endorsed)" | 2025-11-06 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 57 | NAP | 2025-11-06 | A | 001827 | 2025-11-06 | 00 | 1 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10584 | 001828 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0140 | 0 | 131242-WST02-QA-M-0140-0 | 2025-11-06 | Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+) | NA | 2025-12-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0140 | NA | "Test Report for ChlorFit Schedule 80 PVC-C Valves, Pipes & Fittings (+GF+)" | 2025-11-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-11-26 | 151 | PEN | 2025-11-06 | 0 | 001828 | 2025-11-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-24 |  | 0 | PEN | PEN
10585 | 001829 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0133 | 0 | 131242-WSW41-QA-M-0133-0 | 2025-11-06 | FAT Report for (CWP 204 ) SS 316L Pipes - 88 Pcs | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-04 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WSW41-QA-0133 | NA | "FAT Report for (CWP 204 ) SS 316L Pipes - 88 Pcs" | 2025-11-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-26 | 85 | AWC | 2025-11-06 | 0 | 001829 | 2025-11-06 | 00 | 1 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
10586 | 001830 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | C | 0045 | 0 | 131242-WSW41-QA-C-0045-0 | 2025-11-07 | Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025 | For information | 2025-12-05 | 2025-12-24 | For Information |  | YES | NA |  | 131242-WSW41-QA-0045 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Sep 2025" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FFOTP Panel (Fox) THP, SSN" && "WPS, PQR Document for Pipe & Pipe Support (Stainless Steel & Carbon Steel) Welding and Welder List- Cyclect Engineering Pte Ltd" | 2025-02-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-11-21 | 47 | INF | 2026-01-15 | 1 | 001019&&001545&&001830 | 2025-02-03, 2025-07-31, 2025-11-07, 2026-01-15 | 00, 01 | 4 | For Information | INF |  |  | 0 | INF | INF
10587 | 001831 | 00 | Hang Peng | QAQC | NA | 131242 | WSW41 | CD | IM | 0064 | 0 | 131242-WSW41-CD-IM-0064-0 | 2025-11-10 | VCM Submission for 2025-10 | For Information | 2025-12-08 | 2025-12-02 | For Information |  | YES | NA |  | 131242-WSW41-CD-0064 | NA | "VCM Submission for 2025-10" | 2025-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-11-30 | 22 | INF | 2025-11-10 | 0 | 001831 | 2025-11-10 | 00 | 1 | For Information | INF | 2025-12-22 | Overdue | 0 | INF | INF
10588 | 001832 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0141 | 0 | 131242-WST02-QA-M-0141-0 | 2025-11-10 | FAT Report & Mill Test Certificates for Hyperbolic Mixer | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-08 | 2026-01-30 | Approved with Comments | 2026-02-19 | NO | Overdue |  | 131242-WST02-QA-0141 | NA | "FAT Report & Mill Test Certificates for Hyperbolic Mixer" && "Material & Test Certificates for Blower's Encapsulation " | 2025-11-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-11-30 | 81 | AWC | 2025-11-10 | 0 | 001832&&001833 | 2025-11-10 | 00 | 2 | Approved with Comments | AWC | 2026-02-19 | Overdue | 0 | AWC | AWC
10589 | 001833 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0141 | 0 | 131242-WST02-QA-M-0141-0 | 2025-11-10 | Material & Test Certificates for Blower's Encapsulation | NA | 2025-12-08 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0141 | NA | "FAT Report & Mill Test Certificates for Hyperbolic Mixer" && "Material & Test Certificates for Blower's Encapsulation " | 2025-11-10 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-11-30 | 147 | PEN | 2025-11-10 | 0 | 001832&&001833 | 2025-11-10 | 00 | 2 | Approved with Comments | AWC | 2025-12-26 |  | 0 | PEN | PEN
10590 | 001834 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0144 | 0 | 131242-WSW41-QA-M-0144-0 | 2025-11-11 | FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets | NA | 2025-12-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0144 | NA | "FAT Report for Pipe Clamp shoe support, Stopper support- 60 sets" | 2025-11-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-01 | 146 | PEN | 2025-11-11 | 0 | 001834 | 2025-11-11 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-29 |  | 0 | PEN | PEN
10591 | 001835 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0028 | 0 | 131242-WSW41-PC-W-0028-0 | 2025-11-11 | Payment Claim No.28 | Rev (0): Approved. Please refer to S.O. correspondence no. 417 dated 12 November 2025. | 2025-12-09 | 2025-12-10 | Approved |  | YES | NA |  | 131242-WSW41-PC-0028 | NA | "Payment Claim No.28" | 2025-11-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-01 | 29 | APP | 2025-11-11 | 0 | 001835 | 2025-11-11 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10592 | 001836 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0145 | 0 | 131242-WSD11-QA-M-0145-0 | 2025-11-11 | FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area | NA | 2025-12-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0145 | NA | "FAT Report for Strainers - (Spirax Sarco) - THP & SSN Area" | 2025-11-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-01 | 146 | PEN | 2025-11-11 | 0 | 001836 | 2025-11-11 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-29 |  | 0 | PEN | PEN
10593 | 001837 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0146 | 0 | 131242-WSD11-QA-M-0146-0 | 2025-11-11 | FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area | NA | 2025-12-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0146 | NA | "FAT Report for Safety Valve, Strainer, Steam Trap, Air Trap - (Spirax Sarco) - THP & SSN Area" | 2025-11-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-01 | 146 | PEN | 2025-11-11 | 0 | 001837 | 2025-11-11 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-29 |  | 0 | PEN | PEN
10594 | 001838 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0147 | 0 | 131242-WSW41-QA-M-0147-0 | 2025-11-12 | FAT Report for SS 316L Pipes for streamline-55 pcs | NA | 2025-12-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0147 | NA | "FAT Report for SS 316L Pipes for streamline-55 pcs" | 2025-11-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-02 | 145 | PEN | 2025-11-12 | 0 | 001838 | 2025-11-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-30 |  | 0 | PEN | PEN
10595 | 001839 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0148 | 0 | 131242-WST02-QA-M-0148-0 | 2025-11-12 | FAT Report for ARI-Armaturen Safety Valve - (OVS) | NA | 2025-12-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0148 | NA | "FAT Report for ARI-Armaturen Safety Valve - (OVS) " | 2025-11-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-02 | 145 | PEN | 2025-11-12 | 0 | 001839 | 2025-11-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-30 |  | 0 | PEN | PEN
10596 | 001840 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | CD | I | 0016 | 0 | 131242-WST02-CD-I-0016-0 | 2025-11-12 | FAT document for SSN Blower PLC/RIO Panels | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-10 | 2025-12-11 | Approved with Comments | 2025-12-31 | NO | Overdue |  | 131242-WST02-CD-0016 | NA | "FAT document for SSN Blower PLC/RIO Panels" | 2025-11-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 29 | AWC | 2025-11-12 | 0 | 001840 | 2025-11-12 | 00 | 1 | Approved with Comments | AWC | 2025-12-31 | Overdue | 0 | AWC | AWC
10597 | 001841 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0149 | 0 | 131242-WSD11-QA-M-0149-0 | 2025-11-13 | FAT Report for Carbon Steel Pipe Support | NA | 2025-12-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0149 | NA | "FAT Report for Carbon Steel Pipe Support" | 2025-11-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-03 | 144 | PEN | 2025-11-13 | 0 | 001841 | 2025-11-13 | 00 | 1 | Awaiting S.O.'s response | PEN | 2025-12-31 |  | 0 | PEN | PEN
10598 | 001842 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0143 | 0 | 131242-WSW41-QA-M-0143-0 | 2025-11-14 | FAT Report for Motorized Steam Ball Valves (OVS/Rotork) | NA | 2025-12-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0143 | NA | "FAT Report for Motorized Steam Ball Valves (OVS/Rotork)" | 2025-11-14 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-04 | 143 | PEN | 2025-11-14 | 0 | 001842 | 2025-11-14 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-01 |  | 0 | PEN | PEN
10599 | 001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5650 | A | 131242-WST02-DR-M-5650-A | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | Approved with Comments | 2026-03-19 | NO | NA |  | 131242-WST02-DR-5650 | NA | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-07 | 102 | AWC | 2025-11-17 | A | 001843 | 2025-11-17 | 00 | 1 | Approved with Comments | AWC | 2026-03-19 | Overdue | 0 | AWC | AWC
10600 | 001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5651 | A | 131242-WST02-DR-M-5651-A | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | Approved with Comments | 2026-03-19 | NO | NA |  | 131242-WST02-DR-5651 | NA | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-07 | 102 | AWC | 2025-11-17 | A | 001843 | 2025-11-17 | 00 | 1 | Approved with Comments | AWC | 2026-03-19 | Overdue | 0 | AWC | AWC
10601 | 001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5652 | A | 131242-WST02-DR-M-5652-A | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | Approved with Comments | 2026-03-19 | NO | NA |  | 131242-WST02-DR-5652 | NA | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-07 | 102 | AWC | 2025-11-17 | A | 001843 | 2025-11-17 | 00 | 1 | Approved with Comments | AWC | 2026-03-19 | Overdue | 0 | AWC | AWC
10602 | 001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5655 | A | 131242-WST02-DR-M-5655-A | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | Approved with Comments | 2026-03-19 | NO | NA |  | 131242-WST02-DR-5655 | NA | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-07 | 102 | AWC | 2025-11-17 | A | 001843 | 2025-11-17 | 00 | 1 | Approved with Comments | AWC | 2026-03-19 | Overdue | 0 | AWC | AWC
10603 | 001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5656 | A | 131242-WST02-DR-M-5656-A | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | Approved with Comments | 2026-03-19 | NO | NA |  | 131242-WST02-DR-5656 | NA | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-07 | 102 | AWC | 2025-11-17 | A | 001843 | 2025-11-17 | 00 | 1 | Approved with Comments | AWC | 2026-03-19 | Overdue | 0 | AWC | AWC
10604 | 001843 | 00 | Yi Bo | Mech | NA | 131242 | WST02 | DR | M | 5657 | A | 131242-WST02-DR-M-5657-A | 2025-11-17 | Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2025-12-15 | 2026-02-27 | Approved with Comments | 2026-03-19 | NO | NA |  | 131242-WST02-DR-5657 | NA | "Data sheet and Drawing for Lifting Equipment - Portable A-Frame & T-Davit" | 2025-11-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-07 | 102 | AWC | 2025-11-17 | A | 001843 | 2025-11-17 | 00 | 1 | Approved with Comments | AWC | 2026-03-19 | Overdue | 0 | AWC | AWC
10605 | 001844 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5360 | A | 131242-WST02-DR-I-5360-A | 2025-11-18 | Hookup Drawing -Thermal Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-16 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5360 | NA | "Hookup Drawing -Thermal Mass Flowmeter" | 2025-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-08 | 27 | AWC | 2025-11-18 | A | 001844 | 2025-11-18 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10606 | 001844 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5631 | A | 131242-WST02-DR-I-5631-A | 2025-11-18 | Hookup Drawing -Thermal Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-16 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5631 | NA | "Hookup Drawing -Thermal Mass Flowmeter" | 2025-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-08 | 27 | AWC | 2025-11-18 | A | 001844 | 2025-11-18 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10607 | 001844 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5362 | A | 131242-WST02-DR-I-5362-A | 2025-11-18 | Hookup Drawing -Thermal Mass Flowmeter | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2025-12-16 | 2025-12-15 | Approved with Comments | 2026-01-02 | NO | Overdue |  | 131242-WST02-DR-5362 | NA | "Hookup Drawing -Thermal Mass Flowmeter" | 2025-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-08 | 27 | AWC | 2025-11-18 | A | 001844 | 2025-11-18 | 00 | 1 | Approved with Comments | AWC | 2026-01-02 | Overdue | 0 | AWC | AWC
10608 | 001845 | 00 | Kumar | CSA | NA | 131242 | WSW41 | MS | S | 0001 | 0 | 131242-WSW41-MS-S-0001-0 | 2025-11-18 | Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-16 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WSW41-MS-0001 | NA | "Laser Scanning Method of Statement " && "MSRA & SWP for Mobilization and Demobilization of Machinery" && "MSRA & SWP for Sheet Piling Work" && "MSRA SWP for Operating Forklift" && "MSRA and SWP for MEICA OPENING on Block-wall " && "MSRA, SWP for ACMV System works" && "MSRA, SWP for Installation of Precast Manhole and HDPE Underground Piping Work " && "MSRA, SWP for Soil Resistivity Test" && "MSRA, SWP for fire protection services " && "Proposed method of Statement for Post-Drill Anchor Bolt pipe supports Installation on Internal linabond coated surfaces of SSN Tanks" | 2023-10-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-02 | 45 | NAP | 2026-02-13 | 2 | 000113&&000487&&000488&&000565&&000722&&001161&&001392&&001398&&001796&&001845 | 2023-10-04, 2024-05-27, 2024-07-13, 2024-09-05, 2024-09-11, 2025-03-25, 2025-06-19, 2025-06-23, 2025-10-28, 2025-11-18, 2025-12-04, 2026-02-13 | 00, 01, 02 | 13 | Approved | APP |  |  | 0 | NAP | NAP
10609 | 001846 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0150 | 0 | 131242-WST02-QA-M-0150-0 | 2025-11-18 | FAT Procedure for Portable A Frame & T-Davit (Growa) | NA | 2025-12-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0150 | NA | "FAT Procedure for Portable A Frame & T-Davit (Growa)" | 2025-11-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-08 | 139 | PEN | 2025-11-18 | 0 | 001846 | 2025-11-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-05 |  | 0 | PEN | PEN
10610 | 001847 | 00 | K Balaji | Mech | NA | 131242 | WST02 | MS | M | 0004 | 0 | 131242-WST02-MS-M-0004-0 | 2025-11-18 | Method Statement for the Installation of Fine Bubble Diffuser | Rev 0: Approved with Comments. No re-submission required. Refer to attached file for comments. | 2025-12-16 | 2025-12-23 | Approved with Comments |  | YES | NA |  | 131242-WST02-MS-0004 | NA | "Method Statement for the Installation of Fine Bubble Diffuser" | 2025-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-08 | 35 | AWC | 2025-11-18 | 0 | 001847 | 2025-11-18 | 00 | 1 | Approved with Comments | AWC | 2026-01-12 | Overdue | 0 | AWC | AWC
10611 | 001848 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0077 | 0 | 131242-WSW41-LT-PM-0077-0 | 2025-11-19 | Notice For Extension Of Time And Cost For Delays For Power Turn On | NA | 2025-12-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0077 | NA | "Notice For Extension Of Time And Cost For Delays For Power Turn On" | 2025-11-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-09 | 138 | PEN | 2025-11-19 | 0 | 001848 | 2025-11-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-06 |  | 0 | PEN | PEN
10612 | 001849 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0030 | 0 | 131242-WSW41-RT-PM-0030-0 | 2025-11-19 | C4B Monthly Progress Report Number No. 30 (10 25) | Approved with comments which will be addressed in the next MPR. | 2025-12-17 | 2026-02-23 | Approved with Comments |  | YES | NA |  | 131242-WSW41-RT-0030 | NA | "C4B Monthly Progress Report Number No. 30 (10 25)" | 2025-11-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-09 | 96 | AWC | 2025-11-19 | 0 | 001849 | 2025-11-19 | 00 | 1 | Approved with Comments | AWC | 2026-03-13 | Overdue | 0 | AWC | AWC
10613 | 001850 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DS | M | 5345 | 0 | 131242-WSW41-DS-M-5345-0 | 2025-11-19 | Detailed Design PVC Strainer Data Sheet | NA | 2025-12-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DS-5345 | NA | "Detailed Design PVC Strainer Data Sheet" | 2025-11-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-09 | 138 | PEN | 2025-11-19 | 0 | 001850 | 2025-11-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-06 |  | 0 | PEN | PEN
10614 | 001851 | 00 | Joo Kwan | Process | NA | 131242 | WSW41 | DS | M | 5346 | 0 | 131242-WSW41-DS-M-5346-0 | 2025-11-19 | Detailed Design SS316 Strainer Data Sheet | NA | 2025-12-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DS-5346 | NA | "Detailed Design SS316 Strainer Data Sheet" | 2025-11-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-09 | 138 | PEN | 2025-11-19 | 0 | 001851 | 2025-11-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-06 |  | 0 | PEN | PEN
10615 | 001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DS | M | 5640 | 0 | 131242-WST02-DS-M-5640-0 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5640 | NA | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001852 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10616 | 001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5640 | 0 | 131242-WST02-DR-M-5640-0 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5640 | NA | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001852 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10617 | 001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5641 | 0 | 131242-WST02-DR-M-5641-0 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5641 | NA | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001852 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10618 | 001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5642 | 0 | 131242-WST02-DR-M-5642-0 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5642 | NA | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001852 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10619 | 001852 | 00 | Yibo | Mech | NA | 131242 | WST02 | DR | M | 5643 | 0 | 131242-WST02-DR-M-5643-0 | 2025-11-20 | Datat Sheet & Drawing for Portable A-Frame | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5643 | NA | "Datat Sheet & Drawing for Portable A-Frame" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001852 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10620 | 001853 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0151 | 0 | 131242-WSW41-QA-M-0151-0 | 2025-11-20 | Material & Test Certificates for Flange Adaptors (Synchong Hoe) | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0151 | NA | "Material & Test Certificates for Flange Adaptors (Synchong Hoe)" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001853 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10621 | 001854 | 00 | Balaji | QAQC | NA | 131242 | WST02 | QA | BS | 0018 | 0 | 131242-WST02-QA-BS-0018-0 | 2025-11-20 | Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng) | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0018 | NA | "Inspection and Test Plan and Factory Acceptance Test for Local Control Panels (Pho Meng)" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001854 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10622 | 001855 | 00 | Max | HSE | NA | 131242 | WSW41 | PS | HS | 0028 | 0 | 131242-WSW41-PS-HS-0028-0 | 2025-11-20 | Quarterly Risk Management Workshop 9th Quarterly RM Workshop – 31 Oct 2025 | For Information | 2025-12-18 | 2025-12-23 | For Information |  | YES | NA |  | 131242-WSW41-PS-0028 | NA | "Quarterly Risk Management Workshop 9th Quarterly RM Workshop – 31 Oct 2025" | 2025-11-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-10 | 33 | INF | 2025-11-20 | 0 | 001855 | 2025-11-20 | 00 | 1 | For Information | INF | 2026-01-12 | Overdue | 0 | INF | INF
10623 | 001856 | 00 | Max | HSE | NA | 131242 | WST02 | RT | S | 0006 | 0 | 131242-WST02-RT-S-0006-0 | 2025-11-20 | Safety Review Report for SSN Steel Structures and MEICA Equipment Installation | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-RT-0006 | NA | "SSN Hazardous Area Assessment Report" && "Safety Review Report for SSN Steel Structures and MEICA Equipment Installation" && "Test Report for PDA Test 600mm Dia Bored Pile P118,P135 & P156 (ST 615)" | 2024-07-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-04 | 137 | PEN | 2025-11-20 | 0 | 000545&&000772&&001856 | 2024-07-04, 2024-10-23, 2025-11-20 | 00 | 3 | Approved with Comments | AWC | 2026-01-07 |  | 0 | PEN | PEN
10624 | 001857 | 00 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0152 | 0 | 131242-WSD11-QA-M-0152-0 | 2025-11-20 | FAT Report for NON Return Check Valve (Breen) | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0152 | NA | "FAT Report for NON Return Check Valve (Breen)" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001857 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10625 | 001858 | 00 | Soe Myat | QAQC | NA | 131242 | WSD11 | QA | M | 0153 | 0 | 131242-WSD11-QA-M-0153-0 | 2025-11-20 | FAT Report for Sampling Sinks (4 units) | NA | 2025-12-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0153 | NA | "FAT Report for Sampling Sinks (4 units)" | 2025-11-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-10 | 137 | PEN | 2025-11-20 | 0 | 001858 | 2025-11-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-07 |  | 0 | PEN | PEN
10626 | 001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0001 | 0 | 131242-WSD11-MM-M-0001-0 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | For Information | 2026-02-09 | NO | Overdue |  | 131242-WSD11-MM-0001 | NA | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" && "THP Courtyard SCDF Consultation Letter" | 2024-12-03 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-04 | 61 | INF | 2025-11-20 | 0 | 000871&&001859 | 2024-12-03, 2025-11-20 | 00 | 2 | For Information | INF | 2026-02-09 | Overdue | 0 | INF | INF
10627 | 001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0002 | 0 | 131242-WSD11-MM-M-0002-0 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | For Information | 2026-02-09 | NO | Overdue |  | 131242-WSD11-MM-0002 | NA | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-10 | 61 | INF | 2025-11-20 | 0 | 001859 | 2025-11-20 | 00 | 1 | For Information | INF | 2026-02-09 | Overdue | 0 | INF | INF
10628 | 001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0003 | 0 | 131242-WSD11-MM-M-0003-0 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | For Information | 2026-02-09 | NO | Overdue |  | 131242-WSD11-MM-0003 | NA | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-10 | 61 | INF | 2025-11-20 | 0 | 001859 | 2025-11-20 | 00 | 1 | For Information | INF | 2026-02-09 | Overdue | 0 | INF | INF
10629 | 001859 | 00 | Htet Nu | PMT | NA | 131242 | WSD11 | MM | M | 0004 | 0 | 131242-WSD11-MM-M-0004-0 | 2025-11-20 | Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B) | Rev 0: For Information Only. To be updated as necessary | 2025-12-18 | 2026-01-20 | For Information | 2026-02-09 | NO | Overdue |  | 131242-WSD11-MM-0004 | NA | "Memo - MoM certificates for the Compressed Air System (Air Receivers 1 & 2, Air Dryer 1 A/B, Air Dryer 2 A/B)" | 2025-11-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-10 | 61 | INF | 2025-11-20 | 0 | 001859 | 2025-11-20 | 00 | 1 | For Information | INF | 2026-02-09 | Overdue | 0 | INF | INF
10630 | 001860 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0059 | 0 | 131242-WSW41-QA-I-0059-0 | 2025-11-24 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2025-12-22 | 2025-12-16 | Not Approved | 2026-01-05 | YES | Resubmitted |  | 131242-WSW41-QA-0059 | NA | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" && "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | 2025-03-24 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-08 | 22 | NAP | 2025-12-18 | 1 | 001151&&001799&&001860 | 2025-03-24, 2025-10-29, 2025-11-24, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
10631 | 001860 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0059 | 1 | 131242-WSW41-QA-I-0059-1 | 2025-12-18 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments | 2026-01-07 |  | Awaiting S.O.'s response |  | NO | NA |  | 131242-WSW41-QA-0059 | NA | "FAT Report for SS Pipes for site wide pipe rack (Cyclect -1 st batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for PMS Panel (Vector Infotech)THP, SSN" && "Vendor Manufacturing Inspection and test plan and FAT Procedure for Local Control Panels (GSM)" | 2025-03-24 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-01 | 109 | PEN | 2025-12-18 | 1 | 001151&&001799&&001860 | 2025-03-24, 2025-10-29, 2025-11-24, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP | 2026-02-04 |  | 0 | PEN | PEN
10632 | 001861 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0060 | 0 | 131242-WSW41-QA-I-0060-0 | 2025-11-24 | Factory Acceptance Test Report for Pressure Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2025-12-22 | 2025-12-16 | Not Approved | 2026-01-05 | YES | Resubmitted |  | 131242-WSW41-QA-0060 | NA | " FAT Report for Compressor Pipe support in Bio solid building" && "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" && "Factory Acceptance Test Report for Pressure Switch" | 2025-03-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-08 | 22 | NAP | 2026-01-13 | 1 | 001175&&001823&&001861 | 2025-03-27, 2025-11-05, 2025-11-24, 2026-01-13 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
10633 | 001861 | 01 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0060 | 1 | 131242-WSW41-QA-I-0060-1 | 2026-01-13 | Factory Acceptance Test Report for Pressure Switch | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0060 | NA | " FAT Report for Compressor Pipe support in Bio solid building" && "FAT Report for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss)" && "Factory Acceptance Test Report for Pressure Switch" | 2025-03-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-27 | 83 | PEN | 2026-01-13 | 1 | 001175&&001823&&001861 | 2025-03-27, 2025-11-05, 2025-11-24, 2026-01-13 | 00, 01 | 4 | Not Approved | NAP | 2026-03-02 |  | 0 | PEN | PEN
10634 | 001862 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0155 | 0 | 131242-WSD11-QA-M-0155-0 | 2025-11-24 | FAT Report for THP Courtyard Area Pipe Supports (Less than 2m) | NA | 2025-12-22 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0155 | NA | "FAT Report for THP Courtyard Area Pipe Supports (Less than 2m)" | 2025-11-24 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-14 | 133 | PEN | 2025-11-24 | 0 | 001862 | 2025-11-24 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-09 |  | 0 | PEN | PEN
10635 | 001863 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0156 | 0 | 131242-WST02-QA-M-0156-0 | 2025-11-25 | FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units | NA | 2025-12-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0156 | NA | "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant) - 4 units" | 2025-11-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-15 | 132 | PEN | 2025-11-25 | 0 | 001863 | 2025-11-25 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-12 |  | 0 | PEN | PEN
10636 | 001864 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0052 | 0 | 131242-WSW41-MI-C-0052-0 | 2025-11-26 | CSA Meeting Minutes 0052, 0053_07082025 & 21082025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0052 | NA | "CSA Meeting Minutes 0052, 0053_07082025 & 21082025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001864 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10637 | 001864 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0053 | 0 | 131242-WSW41-MI-C-0053-0 | 2025-11-26 | CSA Meeting Minutes 0052, 0053_07082025 & 21082025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0053 | NA | "CSA Meeting Minutes 0052, 0053_07082025 & 21082025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001864 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10638 | 001865 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0054 | 0 | 131242-WSW41-MI-C-0054-0 | 2025-11-26 | CSA Meeting Minutes 0054, 0055_04092025 & 18092025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0054 | NA | "CSA Meeting Minutes 0054, 0055_04092025 & 18092025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001865 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10639 | 001865 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0055 | 0 | 131242-WSW41-MI-C-0055-0 | 2025-11-26 | CSA Meeting Minutes 0054, 0055_04092025 & 18092025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0055 | NA | "CSA Meeting Minutes 0054, 0055_04092025 & 18092025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001865 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10640 | 001866 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0056 | 0 | 131242-WSW41-MI-C-0056-0 | 2025-11-26 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0056 | NA | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001866 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10641 | 001866 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0057 | 0 | 131242-WSW41-MI-C-0057-0 | 2025-11-26 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0057 | NA | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001866 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10642 | 001866 | 00 | Htet Nu | CSA | NA | 131242 | WSW41 | MI | C | 0058 | 0 | 131242-WSW41-MI-C-0058-0 | 2025-11-26 | CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025 | For information | 2025-12-24 | 2025-12-04 | For Information |  | YES | NA |  | 131242-WSW41-MI-0058 | NA | "CSA Meeting Minutes 0056, 0057,0058_02102025, 16102025 & 30102025" | 2025-11-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 8 | INF | 2025-11-26 | 0 | 001866 | 2025-11-26 | 00 | 1 | For Information | INF | 2025-12-24 | Overdue | 0 | INF | INF
10643 | 001867 | 00 | Balaji | EICA | NA | 131242 | WST00 | DR | BM | 1091 | A | 131242-WST00-DR-BM-1091-A | 2025-11-26 | SSN BMS Network Architecture Drawing | NA | 2025-12-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST00-DR-1091 | NA | "SSN BMS Network Architecture Drawing" | 2025-11-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-16 | 131 | PEN | 2025-11-26 | A | 001867 | 2025-11-26 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-13 |  | 0 | PEN | PEN
10644 | 001868 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0154 | 0 | 131242-WSD11-QA-M-0154-0 | 2025-11-27 | FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15) | NA | 2025-12-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0154 | NA | "FAT report for Pressure Regulating Valve - MV Resources (Size : DN 15)" | 2025-11-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-17 | 130 | PEN | 2025-11-27 | 0 | 001868 | 2025-11-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-14 |  | 0 | PEN | PEN
10645 | 001869 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0030 | 0 | 131242-WST02-QA-A-0030-0 | 2025-11-27 | Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2025-12-24 | Not Approved | 2026-01-13 | NO | Overdue |  | 131242-WST02-QA-0030 | NA | "Material Submission for SSN Watertank & Electrical building staircase steps non-slip nosing tiles (Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan for Outdoor (Thermoplastic Cable Ladder) " && "Vendor Manufacturing Inspection Test Plan for TSS Analyser - Optical" | 2025-05-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-11 | 27 | NAP | 2025-11-27 | 0 | 001300&&001469&&001869 | 2025-05-15, 2025-07-11, 2025-11-27 | 00 | 3 | Not Approved | NAP | 2026-01-13 | Overdue | 0 | NAP | NAP
10646 | 001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1011 | A | 131242-WST02-SD-S-1011-A | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WST02-SD-1011 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-11 | 77 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10647 | 001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1012 | A | 131242-WST02-SD-S-1012-A | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WST02-SD-1012 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-11 | 77 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10648 | 001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1013 | A | 131242-WST02-SD-S-1013-A | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WST02-SD-1013 | NA | "Lintel and Stiffener Shop Drawings" && "Shop Drawing for SSN Biomass GI Railing - Rev A" && "Shop Drawings for Block Wall" && "Shop Drawings for Lintel and Stiffener " | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-11 | 77 | NAP | 2025-11-27 | A | 001008&&001042&&001870 | 2025-01-26, 2025-02-14, 2025-03-21, 2025-08-13, 2025-11-27 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10649 | 001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 3005 | A | 131242-WST02-SD-S-3005-A | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WST02-SD-3005 | NA | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 77 | NAP | 2025-11-27 | A | 001870 | 2025-11-27 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10650 | 001870 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8602 | A | 131242-WST02-SD-S-8602-A | 2025-11-27 | Shop Drawing for SSN Biomass GI Railing - Rev A | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WST02-SD-8602 | NA | "Shop Drawing for SSN Biomass GI Railing - Rev A" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 77 | NAP | 2025-11-27 | A | 001870 | 2025-11-27 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10651 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1602 | A | 131242-WST02-SD-S-1602-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-1602 | NA | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 46 | AWC | 2025-11-27 | A | 001871 | 2025-11-27 | 00 | 1 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10652 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1603 | A | 131242-WST02-SD-S-1603-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-1603 | NA | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 46 | AWC | 2025-11-27 | A | 001871 | 2025-11-27 | 00 | 1 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10653 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1604 | A | 131242-WST02-SD-S-1604-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-1604 | NA | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 46 | AWC | 2025-11-27 | A | 001871 | 2025-11-27 | 00 | 1 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10654 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 1606 | A | 131242-WST02-SD-S-1606-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-1606 | NA | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 46 | AWC | 2025-11-27 | A | 001871 | 2025-11-27 | 00 | 1 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10655 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5403 | A | 131242-WST02-SD-S-5403-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-5403 | NA | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 46 | AWC | 2025-11-27 | A | 001871 | 2025-11-27 | 00 | 1 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10656 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 5604 | A | 131242-WST02-SD-S-5604-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-5604 | NA | "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" | 2025-11-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 46 | AWC | 2025-11-27 | A | 001871 | 2025-11-27 | 00 | 1 | Approved with Comments | AWC | 2026-01-30 | Overdue | 0 | AWC | AWC
10657 | 001871 | 00 | Aaron | CSA | NA | 131242 | WST02 | SD | S | 8600 | A | 131242-WST02-SD-S-8600-A | 2025-11-27 | Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports | R0: Approved with comments. PLease refer to comment sheet for resubmission. | 2025-12-25 | 2026-01-12 | Approved with Comments | 2026-01-30 | NO | Overdue |  | 131242-WST02-SD-8600 | NA | " Railing Shop Drawing For Electrical Building" && "Shop Drawing for Chemical Dosing Platform & Cabinets Steel Supports" && "Shop Drawing for SSN Area and Electrical Building Cat ladders " && "Shop drawing for Cat ladders at SSN Area and Electrical Building " && "Shop drawing for Retractable Cat Ladders for JMH 001 & 002 " | 2025-07-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-11 | 46 | AWC | 2026-02-09 | A.5 | 001458&&001698&&001700&&001803&&001871 | 2025-07-11, 2025-08-13, 2025-08-22, 2025-09-26, 2025-09-29, 2025-11-27, 2026-02-09 | 00, 01, 02 | 7 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10658 | 001872 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0001 | 0 | 131242-WST02-CD-B-0001-0 | 2025-11-27 | SSN- I/O List-BIO-0001 | Rev0: Not Approved | 2025-12-25 | 2025-12-29 | Not Approved | 2026-01-16 | YES | Resubmitted |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-11 | 32 | NAP | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
10659 | 001872 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0001 | 0 | 131242-WST02-CD-B-0001-0 | 2026-01-28 | SSN- I/O List-BIO-0001 | Rev0: Not Approved | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CD-0001 | NA | "SSN PLC I/O List" && "SSN RIO 0201 I/O List " && "SSN- I/O List-BIO-0001 " | 2024-07-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 000579&&001872 | 2024-07-22, 2024-11-06, 2025-03-06, 2025-06-16, 2025-08-19, 2025-11-27, 2026-01-28 | 00, 01, 02, 03, 04 | 7 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10660 | 001873 | 00 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0002 | 0 | 131242-WST02-CD-B-0002-0 | 2025-11-27 | SSN- I/O List-BIO-0002 | Rev0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-25 | 2025-12-29 | Not Approved | 2026-01-16 | YES | Resubmitted |  | 131242-WST02-CD-0002 | NA | "SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000" && "SSN- I/O List-BIO-0002 " | 2025-11-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-17 | 32 | NAP | 2026-01-28 | 0 | 001873&&001882 | 2025-11-27, 2025-12-08, 2026-01-28 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | NAP | NAP
10661 | 001873 | 01 | Balaji | EICA | NA | 131242 | WST02 | CD | B | 0002 | 0 | 131242-WST02-CD-B-0002-0 | 2026-01-28 | SSN- I/O List-BIO-0002 | Rev0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CD-0002 | NA | "SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000" && "SSN- I/O List-BIO-0002 " | 2025-11-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-01-28 | 0 | 001873&&001882 | 2025-11-27, 2025-12-08, 2026-01-28 | 00, 01 | 3 | Not Approved | NAP | 2026-03-17 |  | 0 | PEN | PEN
10662 | 001874 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0029 | 0 | 131242-WSW41-PS-HS-0029-0 | 2025-11-28 | Incentive/ Disincentive Audit Scheme for Jul 2025 | Rev 0: Scoring confirmed to be at 95/100 | 2025-12-26 | 2025-12-23 | For Information |  | YES | NA |  | 131242-WSW41-PS-0029 | NA | "Incentive/ Disincentive Audit Scheme for Jul 2025" | 2025-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-18 | 25 | INF | 2025-11-28 | 0 | 001874 | 2025-11-28 | 00 | 1 | For Information | INF | 2026-01-12 | Overdue | 0 | INF | INF
10663 | 001875 | 00 | Malon | HSE | NA | 131242 | WSW41 | PS | HS | 0030 | 0 | 131242-WSW41-PS-HS-0030-0 | 2025-11-28 | Incentive/ Disincentive Audit Scheme for Sept 2025 | Rev 0: Scoring confirmed to be at 95/100 | 2025-12-26 | 2025-12-23 | For Information |  | YES | NA |  | 131242-WSW41-PS-0030 | NA | "Incentive/ Disincentive Audit Scheme for Sept 2025" | 2025-11-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-18 | 25 | INF | 2025-11-28 | 0 | 001875 | 2025-11-28 | 00 | 1 | For Information | INF | 2026-01-12 | Overdue | 0 | INF | INF
10664 | 001876 | 00 | Joo Kwan | Process | NA | 131242 | WST02 | QA | N | 0200 | 0 | 131242-WST02-QA-N-0200-0 | 2025-11-28 | Commissioning Plan for Reactor and Blowers | R0: Not Approved. Please refer to comment sheet for resubmission. | 2025-12-26 | 2026-01-02 | Not Approved | 2026-01-22 | NO | Overdue |  | 131242-WST02-QA-0200 | NA | " Commissioning Plan for Reactor and Blowers" | 2025-11-28 | NO | YES | Project_Code not in project_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-18 | 35 | NAP | 2025-11-28 | 0 | 001876 | 2025-11-28 | 00 | 1 | Not Approved | NAP | 2026-01-22 | Overdue | 0 | NAP | NAP
10665 | 001877 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0061 | 0 | 131242-WSW41-QA-I-0061-0 | 2025-12-02 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN | NA | 2025-12-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0061 | NA | "FAT Report for SS Pipes in Sitewide Pipe Rack (Cyclect - 2nd batch)" && "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for FOIP Panel (FOX)THP,SSN" | 2025-04-02 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-16 | 125 | PEN | 2025-12-02 | 0 | 001184&&001877 | 2025-04-02, 2025-12-02 | 00 | 2 | Approved | APP |  |  | 0 | PEN | PEN
10666 | 001878 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0157 | 0 | 131242-WSD11-QA-M-0157-0 | 2025-12-03 | FAT Report for SS316L Pipes - G2D Line | NA | 2025-12-31 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0157 | NA | " FAT Report for SS316L Pipes - G2D Line" | 2025-12-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-23 | 124 | PEN | 2025-12-03 | 0 | 001878 | 2025-12-03 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-20 |  | 0 | PEN | PEN
10667 | 001879 | 00 | Franklin | Mech | NA | 131242 | WSD11 | CL | M | 1088 | 0 | 131242-WSD11-CL-M-1088-0 | 2025-12-04 | Steam Piping Stress Calculation Report | NA | 2026-01-01 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-CL-1088 | NA | "Steam Piping Stress Calculation Report" | 2025-12-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-24 | 123 | PEN | 2025-12-04 | 0 | 001879 | 2025-12-04 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-21 |  | 0 | PEN | PEN
10668 | 001880 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0029 | 0 | 131242-WSW41-PC-W-0029-0 | 2025-12-04 | Payment Claim No.29 | NA | 2026-01-01 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-PC-0029 | NA | "Payment Claim No.29" | 2025-12-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2025-12-24 | 123 | PEN | 2025-12-04 | 0 | 001880 | 2025-12-04 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-21 |  | 0 | PEN | PEN
10669 | 001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1604 | A | 131242-WST02-DR-S-1604-A | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | Approved with Comments | 2026-02-03 | NO | Overdue |  | 131242-WST02-DR-1604 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 40 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC | 2026-02-03 | Overdue | 0 | AWC | AWC
10670 | 001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1605 | A | 131242-WST02-DR-S-1605-A | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | Approved with Comments | 2026-02-03 | NO | Overdue |  | 131242-WST02-DR-1605 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 40 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC | 2026-02-03 | Overdue | 0 | AWC | AWC
10671 | 001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1610 | A | 131242-WST02-DR-S-1610-A | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | Approved with Comments | 2026-02-03 | NO | Overdue |  | 131242-WST02-DR-1610 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 40 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC | 2026-02-03 | Overdue | 0 | AWC | AWC
10672 | 001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1611 | A | 131242-WST02-DR-S-1611-A | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | Approved with Comments | 2026-02-03 | NO | Overdue |  | 131242-WST02-DR-1611 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 40 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC | 2026-02-03 | Overdue | 0 | AWC | AWC
10673 | 001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 1612 | A | 131242-WST02-DR-S-1612-A | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | Approved with Comments | 2026-02-03 | NO | Overdue |  | 131242-WST02-DR-1612 | NA | "SSN RIO - 203 GA & Wiring Diagram" && "Standardize Support Design for Shelter 1" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 40 | AWC | 2025-12-05 | A | 001453&&001881 | 2025-07-08, 2025-12-05 | 00 | 2 | Approved with Comments | AWC | 2026-02-03 | Overdue | 0 | AWC | AWC
10674 | 001881 | 00 | Aaron | CSA | NA | 131242 | WST02 | DR | S | 5402 | A | 131242-WST02-DR-S-5402-A | 2025-12-05 | Standardize Support Design for Shelter 1 | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-02 | 2026-01-14 | Approved with Comments | 2026-02-03 | NO | Overdue |  | 131242-WST02-DR-5402 | NA | "GA Drawing for FRP Tank" && "Standardize Support Design for Shelter 1" | 2024-12-17 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-19 | 40 | AWC | 2025-12-05 | A | 000911&&001881 | 2024-12-17, 2025-04-01, 2025-12-05 | 00, 01 | 3 | Approved with Comments | AWC | 2026-02-03 | Overdue | 0 | AWC | AWC
10675 | 001882 | 00 | Balaji | QAQC | NA | 131242 | WST02 | CD | I | 0002 | 0 | 131242-WST02-CD-I-0002-0 | 2025-12-08 | SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000 | NA | 2026-01-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CD-0002 | NA | "SSN HMI Graphic List and Graphic Screen and FAT Test procedure-WST02-ECCP-1000" && "SSN- I/O List-BIO-0002 " | 2025-11-27 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-22 | 119 | PEN | 2026-01-28 | 0 | 001873&&001882 | 2025-11-27, 2025-12-08, 2026-01-28 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | PEN | PEN
10676 | 001883 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0016 | 0 | 131242-WST02-DS-I-0016-0 | 2025-12-08 | Datasheet for NO2 & NO3 (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-05 | 2026-02-12 | Approved with Comments | 2026-03-04 | NO | Overdue |  | 131242-WST02-DS-0016 | NA | "Datasheet for NO2 & NO3 (SSN)" && "SSN Datasheet & Drawing of Biomass Separator " | 2024-03-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-22 | 66 | AWC | 2025-12-08 | 0 | 000409&&001883 | 2024-03-28, 2024-07-05, 2025-03-14, 2025-12-08 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-04 | Overdue | 0 | AWC | AWC
10677 | 001884 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0017 | 0 | 131242-WST02-DS-I-0017-0 | 2025-12-08 | Datasheet for Ammonia Analyser (SSN) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-05 | 2026-02-12 | Approved with Comments | 2026-03-04 | NO | Overdue |  | 131242-WST02-DS-0017 | NA | "Datasheet for Ammonia Analyser (SSN)" && "SSN Blower GA drawings and Data Sheets" | 2024-06-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-22 | 66 | AWC | 2025-12-08 | 0 | 000511&&001884 | 2024-06-05, 2025-12-08 | 00 | 2 | Approved with Comments | AWC | 2026-03-04 | Overdue | 0 | AWC | AWC
10678 | 001885 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0061 | 0 | 131242-WST02-QA-E-0061-0 | 2025-12-08 | SAT Report for MDB Panels WST02-MDB-0001A & WST02-MDB-0001B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-QA-0061 | NA | " SAT Report for MDB Panels WST02-MDB-0001A & WST02-MDB-0001B" | 2025-12-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 78 | AWC | 2025-12-08 | 0 | 001885 | 2025-12-08 | 00 | 1 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10679 | 001886 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0062 | 0 | 131242-WST02-QA-E-0062-0 | 2025-12-08 | SAT Report for MCC Panels WST02-MCC-0101A & WST02-MCC-0101B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-QA-0062 | NA | "SAT Report for MCC Panels WST02-MCC-0101A & WST02-MCC-0101B" | 2025-12-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 78 | AWC | 2025-12-08 | 0 | 001886 | 2025-12-08 | 00 | 1 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10680 | 001887 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | E | 0063 | 0 | 131242-WST02-QA-E-0063-0 | 2025-12-08 | SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-05 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-QA-0063 | NA | " SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B" && "FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX)" | 2025-12-08 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 78 | AWC | 2025-12-09 | 0 | 001887&&001889 | 2025-12-08, 2025-12-09 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10681 | 001888 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 9999 | 0 | 131242-WSW41-CD-IM--0 | 2025-12-08 | VCM Submission for 2025-11 | For information | 2026-01-05 | 2025-12-31 | For Information |  | YES | NA |  | 131242-WSW41-CD-9999 | NA | " VCM Submission for 2025-11" && "VCM Model Submission" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2024-12-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-22 | 23 | INF | 2026-02-09 | A | 000879&&001888&&001941&&002009 | 2024-12-09, 2025-12-08, 2026-01-08, 2026-02-09 | 00 | 4 | For Information | INF |  |  | 0 | INF | INF
10682 | 001889 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0063 | 0 | 131242-WST02-QA-I-0063-0 | 2025-12-09 | FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX) | R0: Approved with comments. Please find attached comment sheet for resubmission. | 2026-01-06 | 2025-12-19 | Approved with Comments | 2026-01-08 | NO | Overdue |  | 131242-WST02-QA-0063 | NA | " SAT Report for MCC Panels WST02-MCC-0102A & WST02-MCC-0102B" && "FAT Report for PLC Panel SSN-WST02-ECCP-1001(FOX)" | 2025-12-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-23 | 10 | AWC | 2025-12-09 | 0 | 001887&&001889 | 2025-12-08, 2025-12-09 | 00 | 2 | Approved with Comments | AWC | 2026-01-08 | Overdue | 0 | AWC | AWC
10683 | 001890 | 00 | NA | QAQC | NA | 131242 | NA | NA | NA | 9999 | 0 | 131242----- | 2025-12-09 | FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-06 | 2025-12-19 | Approved with Comments | 2026-01-08 | NO | Overdue |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-23 | 10 | AWC | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | AWC | AWC
10684 | 001891 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | I | 0023 | 0 | 131242-WST02-QA-I-0023-0 | 2025-12-09 | Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector | NA | 2026-01-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0023 | NA | "Samples Submission for Mini Metal Louvers Door set c/w ironmongery (Hang Hong Contractor Pte Ltd)" && "Vendor Manufacturing Inspection test plan for Capacitive Level Switch/Leak Detector" | 2025-06-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-23 | 118 | PEN | 2025-12-09 | 0 | 001396&&001415&&001891 | 2025-06-23, 2025-06-27, 2025-12-09 | 00 | 3 | Approved with Comments | AWC | 2026-01-26 |  | 0 | PEN | PEN
10685 | 001892 | 00 | NA | PMT | NA | 131242 | NA | NA | NA | 9999 | 0 | 131242----- | 2025-12-12 | Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A” | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema | 2025-12-26 | 115 | PEN | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | PEN | PEN
10686 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0001 | A.1 | 131242-WSD11-DR-A-0001-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0001 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | For Information | INF |  |  | 0 | PEN | PEN
10687 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0002 | A.1 | 131242-WSD11-DR-A-0002-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0002 | NA | "THP BCA BP Submission" && "THP Drawing Index" && "THP URA Amendment submissions" | 2024-10-28 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-05 | A | 000783&&001893&&001931 | 2024-10-28, 2025-12-14, 2026-01-05 | 00 | 3 | For Information | INF |  |  | 0 | PEN | PEN
10688 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0003 | A.1 | 131242-WSD11-DR-A-0003-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0003 | NA | "THP BCA BP Submission" && "THP URA Amendment submissions" | 2025-12-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-03 | 113 | PEN | 2026-01-05 | A | 001893&&001931 | 2025-12-14, 2026-01-05 | 00 | 2 | Awaiting S.O.'s response | PEN |  |  | 0 | PEN | PEN
10689 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A.1 | 131242-WSD11-DR-A-1002-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP |  |  | 0 | PEN | PEN
10690 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A.1 | 131242-WSD11-DR-A-1003-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | PEN | PEN
10691 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1004 | A.1 | 131242-WSD11-DR-A-1004-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP |  |  | 0 | PEN | PEN
10692 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A.1 | 131242-WSD11-DR-A-2000-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-2000 | NA | "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" | 2024-11-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-05 | A | 000819&&001893&&001931 | 2024-11-18, 2025-12-14, 2026-01-05 | 00 | 3 | For Information | INF |  |  | 0 | PEN | PEN
10693 | 001893 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A.1 | 131242-WSD11-DR-A-3000-A.1 | 2025-12-14 | THP URA Amendment submissions | NA | 2026-01-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-28 | 113 | PEN | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | PEN | PEN
10694 | 001894 | 00 | Kumar | CSA | NA | 131242 | WSW41 | QA | C | 0046 | 0 | 131242-WSW41-QA-C-0046-0 | 2025-12-15 | Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025 | For information | 2026-01-12 | 2025-12-29 | For Information |  | YES | NA |  | 131242-WSW41-QA-0046 | NA | "Issue for Information-Monthly Concrete Cube Records for Structural works for Oct 2025" && "Vendor Manufacturing Inspection Test Plan and FAT Procedure for LCS Panel" && "Vendor Manufacturing Inspection Test Plan for Top Manway (Aluminium Hatch)" | 2025-02-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2025-12-29 | 14 | INF | 2025-12-15 | 0 | 001030&&001635&&001894 | 2025-02-07, 2025-06-18, 2025-08-28, 2025-10-02, 2025-12-15 | 00, 01 | 5 | For Information | INF | 2026-01-16 | Overdue | 0 | INF | INF
10695 | 001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3145 | A | 131242-WSD11-DR-EP-3145-A | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3145 | NA | "G1 Booster Pump LCP Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-04 | 71 | NAP | 2025-12-15 | A | 001895 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10696 | 001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3146 | A | 131242-WSD11-DR-EP-3146-A | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-3146 | NA | "G1 Booster Pump LCP Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-04 | 71 | NAP | 2025-12-15 | A | 001895 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10697 | 001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7245 | A | 131242-WSD11-DR-EP-7245-A | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7245 | NA | "G1 Booster Pump LCP Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-04 | 71 | NAP | 2025-12-15 | A | 001895 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10698 | 001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7246 | A | 131242-WSD11-DR-EP-7246-A | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7246 | NA | "G1 Booster Pump LCP Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-04 | 71 | NAP | 2025-12-15 | A | 001895 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10699 | 001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7345 | A | 131242-WSD11-DR-EP-7345-A | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7345 | NA | "G1 Booster Pump LCP Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-04 | 71 | NAP | 2025-12-15 | A | 001895 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10700 | 001895 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7346 | A | 131242-WSD11-DR-EP-7346-A | 2025-12-15 | G1 Booster Pump LCP Drawings | Rev 0: Not approved - Revise and Resubmit | 2026-01-12 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSD11-DR-7346 | NA | "G1 Booster Pump LCP Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-04 | 71 | NAP | 2025-12-15 | A | 001895 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10701 | 001896 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | M | 0158 | 0 | 131242-WST02-QA-M-0158-0 | 2025-12-15 | ITP for Portable A Frame & T-Davit (Growa) | NA | 2026-01-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0158 | NA | "ITP for Portable A Frame & T-Davit (Growa)" | 2025-12-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-04 | 112 | PEN | 2025-12-15 | 0 | 001896 | 2025-12-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-01-30 |  | 0 | PEN | PEN
10702 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1541 | A | 131242-WSD11-DR-IP-1541-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1541 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10703 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1542 | A | 131242-WSD11-DR-IP-1542-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1542 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10704 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1543 | A | 131242-WSD11-DR-IP-1543-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1543 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10705 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1544 | A | 131242-WSD11-DR-IP-1544-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1544 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10706 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1545 | A | 131242-WSD11-DR-IP-1545-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1545 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10707 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1546 | A | 131242-WSD11-DR-IP-1546-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1546 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10708 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1547 | A | 131242-WSD11-DR-IP-1547-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1547 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10709 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1548 | A | 131242-WSD11-DR-IP-1548-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1548 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10710 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1549 | A | 131242-WSD11-DR-IP-1549-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1549 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10711 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1550 | A | 131242-WSD11-DR-IP-1550-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1550 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10712 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1551 | A | 131242-WSD11-DR-IP-1551-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1551 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10713 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1552 | A | 131242-WSD11-DR-IP-1552-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1552 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10714 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1553 | A | 131242-WSD11-DR-IP-1553-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1553 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10715 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1554 | A | 131242-WSD11-DR-IP-1554-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1554 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10716 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1555 | A | 131242-WSD11-DR-IP-1555-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1555 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10717 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1556 | A | 131242-WSD11-DR-IP-1556-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1556 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10718 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1557 | A | 131242-WSD11-DR-IP-1557-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1557 | NA | "THP FOIP-0001 GA & Wiring Drawings" && "THP ICA GA & Wiring drawings" | 2025-05-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-29 | 56 | AWC | 2025-12-15 | A | 001328&&001897 | 2025-05-28, 2025-12-15 | 00 | 2 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10719 | 001897 | 00 | Balaji | EICA | NA | 131242 | WSD11 | DR | IP | 1558 | A | 131242-WSD11-DR-IP-1558-A | 2025-12-15 | THP FOIP-0001 GA & Wiring Drawings | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WSD11-DR-1558 | NA | "THP FOIP-0001 GA & Wiring Drawings" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-04 | 56 | AWC | 2025-12-15 | A | 001897 | 2025-12-15 | 00 | 1 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10720 | 001898 | 00 | Joo Kwan | EICA | NA | 131242 | WST02 | SP | I | 0003 | 0 | 131242-WST02-SP-I-0003-0 | 2025-12-15 | SSNR Master Control | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-01-12 | 2026-02-16 | Not Approved | 2026-03-06 | NO | Overdue |  | 131242-WST02-SP-0003 | NA | "SSNR Master Control" | 2025-12-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-04 | 63 | NAP | 2025-12-15 | 0 | 001898 | 2025-12-15 | 00 | 1 | Not Approved | NAP | 2026-03-06 | Overdue | 0 | NAP | NAP
10721 | 001899 | 00 | NA | PMT | NA | 131242 | WSW41 | RT | PM | 0031 | 0 | 131242-WSW41-RT-PM-0031-0 | 2025-12-16 | C4B Monthly Progress Report Number No.31 (11 25) | NA | 2026-01-13 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-RT-0031 | NA | "C4B Monthly Progress Report Number No.31 (11 25)" | 2025-12-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-05 | 111 | PEN | 2025-12-16 | 0 | 001899 | 2025-12-16 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-02 |  | 0 | PEN | PEN
10722 | 001900 | 00 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | 0012 | 0 | 131242-WST02-VI-A-0012-0 | 2025-12-16 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-13 | 2026-01-07 | Not Approved | 2026-01-27 | YES | Resubmitted |  | 131242-WST02-VI-0012 | NA | "Vendor Approval - Passive Harmonic Filter" && "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." && "Vendor Approval of SSN Package (Capacitive Level Switches)" | 2024-05-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-30 | 22 | NAP | 2025-12-16 | 0 | 000464&&000926&&001900 | 2024-05-07, 2024-08-01, 2024-11-08, 2024-12-23, 2025-12-16 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-01-27 | Overdue | 0 | NAP | NAP
10723 | 001900 | 01 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | CRS | 1 | 131242-WST02-VI-A-CRS-1 | 2026-01-27 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | R1: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-09 | Approved with Comments | 2026-02-27 | YES | Resubmitted |  | 131242-WST02-VI-CRS | NA | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | 2026-01-27 | YES | NO | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-16 | 13 | AWC | 2026-02-11 | 2 | 001900 | 2026-01-27, 2026-02-11 | 01, 02 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10724 | 001900 | 02 | Yuen Fatt | Project | NA | 131242 | WST02 | VI | A | CRS | 2 | 131242-WST02-VI-A-CRS-2 | 2026-02-11 | Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd. | R2: Approved with comments. Please refer to comment sheet for resubmission. | 2026-03-03 | 2026-02-25 | Approved with Comments | 2026-03-17 |  | NA |  | 131242-WST02-VI-CRS | NA | "Vendor Approval of Metal Roofing and Cladding – SC Solutions Pte. Ltd." | 2026-01-27 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Department not in department_schema | 2026-02-25 | 14 | AWC | 2026-02-11 | 2 | 001900 | 2026-01-27, 2026-02-11 | 01, 02 | 2 | Approved with Comments | AWC | 2026-03-17 | Overdue | 0 | AWC | AWC
10725 | 001901 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 5001 | A | 131242-WSD11-DR-BF-5001-A | 2025-12-16 | Typical Fire Alarm Installation Detail (THP) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-13 | 2026-01-07 | Not Approved | 2026-01-27 | NO | Overdue |  | 131242-WSD11-DR-5001 | NA | "THP Handrail Layout and Cad Ladder Details" && "Typical Fire Alarm Installation Detail (THP)" | 2024-11-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-30 | 22 | NAP | 2025-12-16 | A | 000822&&001901 | 2024-11-18, 2025-12-16 | 00 | 2 | Not Approved | NAP | 2026-01-27 | Overdue | 0 | NAP | NAP
10726 | 001902 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 3000 | A1 | 131242-WSD11-DR-BF-3000-A1 | 2025-12-16 | Dry Riser Installation Details | NA | 2026-01-13 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-30 | 111 | PEN | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | PEN | PEN
10727 | 001902 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 5000 | A | 131242-WSD11-DR-BF-5000-A | 2025-12-16 | Dry Riser Installation Details | NA | 2026-01-13 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-5000 | NA | "Dry Riser Installation Details" && "THP Door and Finishes Schedules" | 2024-11-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-30 | 111 | PEN | 2025-12-16 | A | 000820&&001902 | 2024-11-18, 2025-12-16 | 00 | 2 | Not Approved | NAP | 2026-02-02 |  | 0 | PEN | PEN
10728 | 001902 | 00 | NA | BS | NA | 131242 | WSD11 | DR | BF | 7000 | A1 | 131242-WSD11-DR-BF-7000-A1 | 2025-12-16 | Dry Riser Installation Details | NA | 2026-01-13 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7000 | NA | "Dry Riser Installation Details" && "THP 1&2 Building Services DB SLD" && "THP Control System Architecture Drawing" && "THP MCC Schematic Diagram" && "THP Overall Single Line Diagram" && "THP Protected Corridor Fan Control Circuit Diagram" && "THP SLD" && "THP-Dry Riser System" | 2023-11-06 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2025-12-30 | 111 | PEN | 2025-12-16 | A1 | 000171&&000197&&000570&&000571&&001017&&001073&&001526&&001902 | 2023-11-06, 2023-11-21, 2024-03-13, 2024-07-16, 2024-07-29, 2024-10-01, 2024-10-03, 2024-11-21, 2025-01-21, 2025-02-03, 2025-02-25, 2025-03-07, 2025-07-24, 2025-10-23, 2025-12-16 | 00, 01, 02, 03, 04, 05 | 15 | Approved | APP |  |  | 0 | PEN | PEN
10729 | 001903 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DS | I | 0023 | 0 | 131242-WST02-DS-I-0023-0 | 2025-12-16 | Datasheet for Magnetic Level Gauge (SSN) | Rev 0: Not Approved. To revise and resubmit. Refer attached file for comments. | 2026-01-13 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WST02-DS-0023 | NA | "Datasheet for Magnetic Level Gauge (SSN)" | 2025-12-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 58 | NAP | 2025-12-16 | 0 | 001903 | 2025-12-16 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10730 | 001904 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DR | I | 5102 | B | 131242-WSD11-DR-I-5102-B | 2025-12-16 | Hook-up drawing for PDSH for CAS (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-13 | 2026-02-12 | Approved with Comments | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-5102 | NA | "Hook up Drawing for PDSH - CAS" && "Hook-up drawing for PDSH for CAS (THP)" | 2025-06-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2025-12-30 | 58 | AWC | 2025-12-16 | B | 001352&&001904 | 2025-06-10, 2025-12-16 | 00 | 2 | Approved with Comments | AWC | 2026-03-04 | Overdue | 0 | AWC | AWC
10731 | 001905 | 00 | NA | NA | NA | 131242 | NA | NA | NA | 9999 | B | 131242----- | 2025-12-17 | As Built Drawing for ST619 (THP Cooler Platform) | VOID, NOT IN USE | 2026-01-14 |  | Rejected |  |  | NA | To withdraw since duplicate submission with 1906. | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema | 2025-12-31 | 110 | REJ | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | REJ | REJ
10732 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 0306 | X | 131242-WSW41-SD-S-0306-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-0306 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001906 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10733 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1101 | X | 131242-WSW41-SD-S-1101-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1101 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10734 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1102 | X | 131242-WSW41-SD-S-1102-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1102 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10735 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1103 | X | 131242-WSW41-SD-S-1103-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1103 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10736 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 2100 | X | 131242-WSW41-SD-S-2100-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-2100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10737 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 3100 | X | 131242-WSW41-SD-S-3100-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-3100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" && "Sitewide Pipe Rack RC stumps at GL A-B/1-11 Settingout plan and Details" | 2024-07-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 000581&&001085&&001906 | 2024-07-23, 2025-03-04, 2025-12-17 | 00 | 3 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10738 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5100 | X | 131242-WSW41-SD-S-5100-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5100 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10739 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5101 | X | 131242-WSW41-SD-S-5101-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5101 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10740 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5102 | X | 131242-WSW41-SD-S-5102-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5102 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10741 | 001906 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 8002 | X | 131242-WSW41-SD-S-8002-X | 2025-12-17 | As Built Drawing for ST619 (THP Pipe Rack PR-01) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-8002 | NA | "As Built Drawing for ST619 (THP Pipe Rack PR-01)" && "Shop Drawing of ST614_Side Wide Pipe Rack 03" | 2025-03-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2025-12-31 | 110 | PEN | 2025-12-17 | X | 001085&&001906 | 2025-03-04, 2025-12-17 | 00 | 2 | Not Approved | NAP | 2026-02-03 |  | 0 | PEN | PEN
10742 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 0300 | X | 131242-WSW41-SD-S-0300-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-0300 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10743 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1000 | X | 131242-WSW41-SD-S-1000-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1000 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10744 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1001 | X | 131242-WSW41-SD-S-1001-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1001 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10745 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1002 | X | 131242-WSW41-SD-S-1002-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1002 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10746 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1003 | X | 131242-WSW41-SD-S-1003-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1003 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10747 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1004 | X | 131242-WSW41-SD-S-1004-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1004 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10748 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1005 | X | 131242-WSW41-SD-S-1005-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1005 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10749 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1006 | X | 131242-WSW41-SD-S-1006-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1006 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10750 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1007 | X | 131242-WSW41-SD-S-1007-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1007 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10751 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 1008 | X | 131242-WSW41-SD-S-1008-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-1008 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10752 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 2000 | X | 131242-WSW41-SD-S-2000-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-2000 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10753 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 2001 | X | 131242-WSW41-SD-S-2001-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-2001 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10754 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 3000 | X | 131242-WSW41-SD-S-3000-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-3000 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10755 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5000 | X | 131242-WSW41-SD-S-5000-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5000 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10756 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5001 | X | 131242-WSW41-SD-S-5001-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5001 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10757 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5002 | X | 131242-WSW41-SD-S-5002-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5002 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10758 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5003 | X | 131242-WSW41-SD-S-5003-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5003 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10759 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 5004 | X | 131242-WSW41-SD-S-5004-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-5004 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10760 | 001907 | 00 | NA | CSA | NA | 131242 | WSW41 | SD | S | 8001 | X | 131242-WSW41-SD-S-8001-X | 2025-12-17 | As built drawing for ST621 (SWPR PR 01 & 02) | NA | 2026-01-14 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-SD-8001 | NA | "As built drawing for ST621 (SWPR PR 01 & 02)" | 2025-12-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-06 | 110 | PEN | 2025-12-17 | X | 001907 | 2025-12-17 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-03 |  | 0 | PEN | PEN
10761 | 001908 | 00 | Jun | EICA | NA | 131242 | WST02 | RT | E | 0012 | 0 | 131242-WST02-RT-E-0012-0 | 2025-12-18 | SSN-Transformer Bay Gravel Sieve Analysis Report | Rev 0: Approved | 2026-01-15 | 2026-02-24 | Approved |  | YES | NA |  | 131242-WST02-RT-0012 | NA | "SSN-Transformer Bay Gravel Sieve Analysis Report" | 2025-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-07 | 68 | APP | 2025-12-18 | 0 | 001908 | 2025-12-18 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
10762 | 001909 | 00 | NA | BS | NA | 131242 | WST02 | QA | BS | 0020 | 0 | 131242-WST02-QA-BS-0020-0 | 2025-12-18 | SAT Procedure for Public Address System | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-01-07 | Not Approved | 2026-01-27 | NO | Overdue |  | 131242-WST02-QA-0020 | NA | "SAT Procedure for Public Address System" && "Samples Submission for Mini Metal Doorset c/w ironmongery (Hang Hong Contractor Pte Ltd)" | 2025-02-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 20 | NAP | 2025-12-18 | 0 | 001075&&001909 | 2025-02-27, 2025-12-18 | 00 | 2 | Not Approved | NAP | 2026-01-27 | Overdue | 0 | NAP | NAP
10763 | 001910 | 00 | NA | CSA | NA | 131242 | WSD11 | SD | S | Fab Drawing | 0 | 131242-WSD11-SD-S-Fab Drawing-NA | 2025-12-18 | THP PF02 Grating Support Beam Fab Drawing_TOS 15.785m SHD (PE Endorsed) | For Information | 2026-01-15 | 2026-01-12 | For Information |  | YES | NA |  | 131242-WSD11-SD-Fab Drawing | NA | "THP PF02 Grating Support Beam Fab Drawing_TOS 15.785m SHD (PE Endorsed)" | 2025-12-18 | NO | YES | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema | 2026-01-07 | 25 | INF | 2025-12-18 | 0 | 001910 | 2025-12-18 | 00 | 1 | For Information | INF | 2026-01-30 | Overdue | 0 | INF | INF
10764 | 001911 | 00 | NA | BS | NA | 131242 | WST02 | QA | BS | 0019 | 0 | 131242-WST02-QA-BS-0019-0 | 2025-12-18 | Site Acceptance Test Procedure for Clean Gas System Panel | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-01-07 | Not Approved | 2026-01-27 | NO | Overdue |  | 131242-WST02-QA-0019 | NA | "FAT report for SS Cable Ladder, Cable Tray, Accessories 3rd batch (United ULI) " && "Material Submission - 2HR Fire rated Galvanized steel doors & Ironmongery. (Hang Hong Contractor Pte Ltd)" && "Site Acceptance Test Procedure for Clean Gas System Panel" | 2025-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 20 | NAP | 2025-12-18 | 0 | 001013&&001078&&001911 | 2025-01-26, 2025-02-28, 2025-04-09, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP | 2026-01-27 | Overdue | 0 | NAP | NAP
10765 | 001912 | 00 | NA | CSA | NA | 131242 | WST02 | DR | S | 3002 | E | 131242-WST02-DR-S-3002-E | 2025-12-18 | ST Updates for SSN Staircase (ST607) | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-04 | Approved with Comments | 2026-02-24 | NO | Overdue |  | 131242-WST02-DR-3002 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "ST Updates for SSN Staircase (ST607)" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 48 | AWC | 2026-02-09 | A.6 | 000163&&000605&&000607&&001165&&001528&&001557&&001912 | 2024-08-01, 2024-11-21, 2025-01-21, 2025-03-25, 2025-04-28, 2025-05-04, 2025-07-24, 2025-08-05, 2025-08-22, 2025-11-07, 2025-12-18, 2026-02-09 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10766 | 001913 | 00 | Balaji | EICA | NA | 131242 | WSD11 | CD | I | 0010 | 0 | 131242-WSD11-CD-I-0010-0 | 2025-12-18 | THP RIO 0201 I/O List | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-01-15 | 2026-02-04 | Approved with Comments | 2026-02-24 | NO | Overdue |  | 131242-WSD11-CD-0010 | NA | "THP RIO 0201 I/O List" | 2025-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-07 | 48 | AWC | 2025-12-18 | 0 | 001913 | 2025-12-18 | 00 | 1 | Approved with Comments | AWC | 2026-02-24 | Overdue | 0 | AWC | AWC
10767 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1023 | C | 131242-WST02-DR-S-1023-C | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1023 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2026-02-04 | 1 | 000429&&001402&&001793&&001914 | 2024-04-09, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 7 | Not Approved | NAP |  |  | 0 | NAP | NAP
10768 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1024 | C | 131242-WST02-DR-S-1024-C | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1024 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2026-02-04 | 1 | 000429&&000778&&001402&&001793&&001914 | 2024-04-09, 2024-10-26, 2025-06-23, 2025-08-27, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 8 | Not Approved | NAP |  |  | 0 | NAP | NAP
10769 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1025 | B.1 | 131242-WST02-DR-S-1025-B.1 | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP |  |  | 0 | NAP | NAP
10770 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1026 | A | 131242-WST02-DR-S-1026-A | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1026 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN-Rain Water Drainage Layout and Detail Design" | 2024-04-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2026-02-04 | 1 | 000429&&000860&&001176&&001402&&001793&&001914 | 2024-04-09, 2024-11-30, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | NAP | NAP
10771 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1400 | H | 131242-WST02-DR-S-1400-H | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1400 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | H | 000753&&000836&&001148&&001730&&001914 | 2024-10-10, 2024-11-22, 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 6 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10772 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1401 | H | 131242-WST02-DR-S-1401-H | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1401 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | H | 001148&&001730&&001914 | 2025-03-21, 2025-07-29, 2025-10-08, 2025-12-18 | 00, 01 | 4 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10773 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1402 | C | 131242-WST02-DR-S-1402-C | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1402 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | C | 001148&&001914 | 2025-03-21, 2025-07-29, 2025-12-18 | 00, 01 | 3 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10774 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1403 | C | 131242-WST02-DR-S-1403-C | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1403 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO 0202 GA & Wiring Diagram" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | C | 001148&&001914 | 2025-03-21, 2025-07-29, 2025-12-18 | 00, 01 | 3 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10775 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 1607 | F | 131242-WST02-DR-S-1607-F | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-1607 | NA | "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN RIO - 203 GA & Wiring Diagram" | 2025-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | F | 001453&&001914 | 2025-07-08, 2025-12-18 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10776 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 5400 | F | 131242-WST02-DR-S-5400-F | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-5400 | NA | "Hookup Drawing -TSS Analyser" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Area Wall Mounted Pipe Support (PE Endorsed Drawing)" && "SSN Wall Mounted Pipe Support Design" && "SSN- Biomass separator footing detail" | 2024-10-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | F | 000753&&000836&&001730&&001788&&001914 | 2024-10-10, 2024-11-22, 2025-10-08, 2025-10-23, 2025-12-18 | 00 | 5 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10777 | 001914 | 00 | Charles | Const; | NA | 131242 | WST02 | DR | S | 5406 | E | 131242-WST02-DR-S-5406-E | 2025-12-18 | SSN - Tank pipe support Anchor bolts embedment design drill depths | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-15 | 2026-02-20 | Not Approved | 2026-03-12 | NO | Overdue |  | 131242-WST02-DR-5406 | NA | "GA Drawing for FRP Tank" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" | 2025-04-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-01 | 64 | NAP | 2025-12-18 | E | 000911&&001914 | 2025-04-01, 2025-12-18 | 00, 01 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10778 | 001915 | 00 | Franklin | Mech | NA | 131242 | WST02 | DS | M | 5650 | 0 | 131242-WST02-DS-M-5650-0 | 2025-12-18 | Data Sheet for Davit Arm and Mount Socket | NA | 2026-01-15 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5650 | NA | "Data Sheet for Davit Arm and Mount Socket" | 2025-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-07 | 109 | PEN | 2025-12-18 | 0 | 001915 | 2025-12-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-04 |  | 0 | PEN | PEN
10779 | 001915 | 00 | Franklin | Mech | NA | 131242 | WST02 | DS | M | 5655 | 0 | 131242-WST02-DS-M-5655-0 | 2025-12-18 | Data Sheet for Davit Arm and Mount Socket | NA | 2026-01-15 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DS-5655 | NA | "Data Sheet for Davit Arm and Mount Socket" | 2025-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-07 | 109 | PEN | 2025-12-18 | 0 | 001915 | 2025-12-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-04 |  | 0 | PEN | PEN
10780 | 001916 | 00 | NA | Mech | NA | 131242 | WST02 | OM | M | 0017 | 0 | 131242-WST02-OM-M-0017-0 | 2025-12-18 | O&M Manual for A-Frame and T-Davit | NA | 2026-01-15 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0017 | NA | "O&M Manual for A-Frame and T-Davit" | 2025-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-07 | 109 | PEN | 2025-12-18 | 0 | 001916 | 2025-12-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-04 |  | 0 | PEN | PEN
10781 | 001917 | 00 | NA | Mech | NA | 131242 | WST02 | OM | M | 0019 | 0 | 131242-WST02-OM-M-0019-0 | 2025-12-18 | Long term storage & Preservation procedure for A-Frame and T-Davit | NA | 2026-01-15 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-OM-0019 | NA | "Long term storage & Preservation procedure for A-Frame and T-Davit" | 2025-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-07 | 109 | PEN | 2025-12-18 | 0 | 001917 | 2025-12-18 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-04 |  | 0 | PEN | PEN
10782 | 001918 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | E | 0064 | 0 | 131242-WST02-QA-E-0064-0 | 2025-12-18 | SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-15 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WST02-QA-0064 | NA | "SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B)" && "Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN" | 2025-12-18 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-07 | 68 | AWC | 2025-12-19 | 0 | 001918&&001923 | 2025-12-18, 2025-12-19 | 00 | 2 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10783 | 001919 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | E | 0006 | 0 | 131242-WSD11-QA-E-0006-0 | 2025-12-18 | SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-15 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-QA-0006 | NA | "Instruments Factory Calibration Certificate and Quality inspection certificate for THP Train 1 & Train 2 ( Part-1)" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" && "T&C Documents for THP Air Compressor SAT, Air Dryer, Switches, Pressure Transmitter SAT, Penumatic On Off Valve SAT, Transmitter Hot Loop, Hot Loop Check " | 2025-01-20 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-01 | 68 | AWC | 2026-01-28 | 1 | 000993&&001011&&001919 | 2025-01-20, 2025-01-26, 2025-03-06, 2025-04-08, 2025-12-18, 2026-01-28 | 00, 01, 02, 03 | 6 | Approved with Comments | AWC |  |  | 0 | AWC | AWC
10784 | 001920 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | E | 0066 | 0 | 131242-WSD11-QA-E-0066-0 | 2025-12-18 | SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B | Rev 0: Rejected | 2026-01-15 | 2026-02-23 | Rejected |  | YES | NA |  | 131242-WSD11-QA-0066 | NA | "FAT report for THP Sludge cooler B Stage 1" && "SAT Report for MCC Panels WSD11-MCC-0001A & WSD11-MCC-0001B" | 2025-04-24 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-01 | 67 | REJ | 2025-12-18 | 0 | 001250&&001920 | 2025-04-24, 2025-12-02, 2025-12-18 | 00, 01 | 3 | Rejected | REJ | 2026-03-13 | Overdue | 0 | REJ | REJ
10785 | 001921 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | E | 0065 | 0 | 131242-WSD11-QA-E-0065-0 | 2025-12-18 | SAT Report for MDB Panels WST02-MDB-1001A & WST02-MDB-1001B | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-01-15 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-QA-0065 | NA | "SAT Report for MDB Panels WST02-MDB-1001A & WST02-MDB-1001B" | 2025-12-18 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-07 | 68 | AWC | 2025-12-18 | 0 | 001921 | 2025-12-18 | 00 | 1 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10786 | 001922 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | M | 0159 | 0 | 131242-WSD11-QA-M-0159-0 | 2025-12-19 | FAT Report for SS 316L (CWP 205) Pipes -149 Nos | NA | 2026-01-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0159 | NA | "FAT Report for SS 316L (CWP 205) Pipes -149 Nos" | 2025-12-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-08 | 108 | PEN | 2025-12-19 | 0 | 001922 | 2025-12-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-05 |  | 0 | PEN | PEN
10787 | 001923 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | I | 0064 | 0 | 131242-WST02-QA-I-0064-0 | 2025-12-19 | Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN | NA | 2026-01-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0064 | NA | "SAT Report for 22kV Power Cable Hipot Test (WST02-TRF-0101 A & WST02-TRF-0101 B)" && "Vendor Manufacturing Inspection Test Plan for Magnetic Level Gauge-SSN" | 2025-12-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-02 | 108 | PEN | 2025-12-19 | 0 | 001918&&001923 | 2025-12-18, 2025-12-19 | 00 | 2 | Approved with Comments | AWC | 2026-02-05 |  | 0 | PEN | PEN
10788 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1000 | A.2 | 131242-WST02-DR-A-1000-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP |  |  | 0 | NAP | NAP
10789 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1001 | A.2 | 131242-WST02-DR-A-1001-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
10790 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1002 | A.2 | 131242-WST02-DR-A-1002-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | NAP | NAP
10791 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1003 | A.2 | 131242-WST02-DR-A-1003-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | NAP | NAP
10792 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1004 | A.2 | 131242-WST02-DR-A-1004-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | NAP | NAP
10793 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1005 | A | 131242-WST02-DR-A-1005-A | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | NAP | NAP
10794 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1006 | A.2 | 131242-WST02-DR-A-1006-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | NAP | NAP
10795 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 1009 | A.2 | 131242-WST02-DR-A-1009-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | NAP | NAP
10796 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2000 | A.2 | 131242-WST02-DR-A-2000-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP |  |  | 0 | NAP | NAP
10797 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2001 | A.2 | 131242-WST02-DR-A-2001-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
10798 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2002 | A.2 | 131242-WST02-DR-A-2002-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
10799 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2003 | A.2 | 131242-WST02-DR-A-2003-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP |  |  | 0 | NAP | NAP
10800 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 2007 | A.2 | 131242-WST02-DR-A-2007-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-2007 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000812&&001194&&001924 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02 | 6 | Not Approved | NAP |  |  | 0 | NAP | NAP
10801 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 3000 | A.2 | 131242-WST02-DR-A-3000-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-05 | 21 | NAP | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP |  |  | 0 | NAP | NAP
10802 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 9000 | A.2 | 131242-WST02-DR-A-9000-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-9000 | NA | "SSN URA Submission" | 2025-12-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-11 | 21 | NAP | 2026-02-03 | A.2 | 001924 | 2025-12-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10803 | 001924 | 00 | NA | CSA | NA | 131242 | WST02 | DR | A | 9001 | A.2 | 131242-WST02-DR-A-9001-A.2 | 2025-12-22 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-01-19 | 2026-01-12 | Not Approved | 2026-01-30 | YES | Resubmitted |  | 131242-WST02-DR-9001 | NA | "SSN URA Submission" | 2025-12-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-11 | 21 | NAP | 2026-02-03 | A.2 | 001924 | 2025-12-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10804 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1000 | A.2 | 131242-WST02-DR-A-1000-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1000 | NA | "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "NEA Waiver Submission of SSN Plant" && "Plumbing and Sanitary (SSN Area)" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Overall GA & Equipment Layout Drawings" && "SSN Plumbing and Sanitary " && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000160&&000161&&000188&&000189&&000191&&000205&&000219&&000225&&000227&&000461&&000471&&000809&&001604&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-05-06, 2024-05-13, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-24, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-09-11, 2025-10-29, 2025-11-12, 2025-12-15, 2025-12-22, 2026-01-19, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 32 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10805 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1001 | A.2 | 131242-WST02-DR-A-1001-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1001 | NA | "BMS Panel GA & Wiring Drawing " && "Building Services ACMV" && "Fire Alarm-Gas Suppression" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building ACMV layout & Schedule" && "SSN Lighting Layout Plan" && "SSN Overall Area Layout And Sections" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN Railing Layout" && "SSN Rain Water Drainage Layout and Detail Design" && "SSN URA Submission" | 2023-11-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000160&&000161&&000188&&000191&&000205&&000219&&000225&&000227&&000809&&000834&&001144&&001625&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-11-30, 2023-12-04, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-13, 2024-11-22, 2025-02-18, 2025-02-20, 2025-03-21, 2025-04-10, 2025-05-15, 2025-07-15, 2025-08-04, 2025-08-19, 2025-08-26, 2025-09-11, 2025-10-29, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 33 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10806 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1002 | A.2 | 131242-WST02-DR-A-1002-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1002 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Electrical Building Archi Drawing" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-04 | 1 | 000160&&000161&&000190&&000191&&000192&&000205&&000227&&000832&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-07-06, 2024-08-13, 2024-10-05, 2024-11-22, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 28 | Not Approved | NAP |  |  | 0 | PEN | PEN
10807 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1003 | A.2 | 131242-WST02-DR-A-1003-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1003 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-04 | 1 | 000160&&000161&&000163&&000190&&000191&&000205&&000227&&000418&&000810&&001144&&001402&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 29 | Not Approved | NAP |  |  | 0 | PEN | PEN
10808 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1004 | A.2 | 131242-WST02-DR-A-1004-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1004 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Hose Reel (SSN Area)" && "Lightning Protection System" && "Milestone 2 SSN Chemical Dosing Area" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Lighting Layout Plan" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-09 | A.6 | 000160&&000161&&000163&&000190&&000191&&000192&&000205&&000227&&000418&&000811&&001144&&001402&&001528&&001793&&001924 | 2023-11-03, 2023-11-15, 2023-11-22, 2023-12-05, 2024-04-04, 2024-07-06, 2024-08-13, 2024-10-05, 2024-10-22, 2024-11-13, 2025-02-18, 2025-02-20, 2025-02-21, 2025-03-21, 2025-04-10, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-04, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-15, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 33 | Not Approved | NAP |  |  | 0 | PEN | PEN
10809 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1005 | A | 131242-WST02-DR-A-1005-A | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1005 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Lightning Protection System" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Milestone 2 Underground Services" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN External Fire Hydrant Layout & Details " && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN Power Layout Plan" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-09 | A.6 | 000161&&000163&&000191&&000205&&000227&&000418&&000661&&001144&&001402&&001528&&001793&&001924 | 2023-11-22, 2024-04-04, 2024-07-06, 2024-08-20, 2024-10-05, 2024-10-22, 2025-02-20, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-19, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-19, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 23 | Not Approved | NAP |  |  | 0 | PEN | PEN
10810 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1006 | A.2 | 131242-WST02-DR-A-1006-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1006 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Fire Alarm-Gas Suppression" && "Milestone 2 SSN Electrical Building" && "Milestone 2 SSN Water Tank" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN Integrated Security management system and Plant CCTV" && "SSN Integrated Security management system and plant CCTV" && "SSN URA Submission" | 2024-04-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-09 | A.6 | 000163&&000188&&000191&&000418&&001144&&001402&&001528&&001793&&001924 | 2024-04-04, 2024-10-22, 2025-03-21, 2025-04-28, 2025-05-15, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-09-11, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 17 | Not Approved | NAP |  |  | 0 | PEN | PEN
10811 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 1009 | A.2 | 131242-WST02-DR-A-1009-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1009 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "Railing Shop Drawing- SSN Tanks and Chemical Dosing area " && "Retractable Cat ladder JMH 01 & 02 (PE endorsed Drawing)" && "SSN ECCP-1000- GA & Wiring Diagram" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-09 | A.6 | 000164&&000812&&001144&&001402&&001528&&001733&&001793&&001924 | 2024-11-13, 2025-03-21, 2025-04-22, 2025-06-23, 2025-07-24, 2025-08-19, 2025-08-27, 2025-10-31, 2025-11-06, 2025-11-07, 2025-11-21, 2025-12-22, 2026-01-28, 2026-02-03, 2026-02-04, 2026-02-09 | 00, 01, 02, 03 | 16 | Not Approved | NAP |  |  | 0 | PEN | PEN
10812 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2000 | A.2 | 131242-WST02-DR-A-2000-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2000 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Overall Area Layout And Sections" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Piping Support Plan Layout (Cast-In Supports)" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "Shop Drawing for Louvre Door and Window" | 2023-11-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000161&&000205&&000778&&000809&&001194&&001604&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-10-26, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-12, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 12 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10813 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2001 | A.2 | 131242-WST02-DR-A-2001-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2001 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Electrical Building Archi Drawing" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" | 2023-11-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000161&&000205&&000832&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-22, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10814 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2002 | A.2 | 131242-WST02-DR-A-2002-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2002 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 001 Layout and Elevation" | 2023-11-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000161&&000205&&000810&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10815 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2003 | A.2 | 131242-WST02-DR-A-2003-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2003 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "Lightning Protection System" && "Milestone 2 Underground Services" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN Preliminary Lightning Protection System" && "SSN URA Submission" && "SSN_Shelter 002 Layout and Elevation" | 2023-11-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000161&&000205&&000811&&001194&&001924 | 2023-11-22, 2024-07-06, 2024-10-05, 2024-11-13, 2025-02-20, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 10 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10816 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 2007 | A.2 | 131242-WST02-DR-A-2007-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-2007 | NA | " SSN Panel RIO-208 - GA & Schematic Drawings" && "SSN Panel (FBTB-0501) - GA & Schematic Drawings" && "SSN URA Submission" && "SSN_Shelter 003 Layout and Elevation" | 2024-11-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000812&&001194&&001924 | 2024-11-13, 2025-04-03, 2025-07-11, 2025-11-17, 2025-12-22, 2026-02-03 | 00, 01, 02 | 6 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10817 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 3000 | A.2 | 131242-WST02-DR-A-3000-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3000 | NA | "LDB-0001 SLD, Schematic and GA Drawing" && "Milestone 2 SSN Electrical Building" && "SSN LVSG 0101AB Outline GA Drawing" && "SSN LVSG 0101AB Single Line Diagram" && "SSN Overall Area Layout And Sections" && "SSN URA Submission" | 2024-08-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 000191&&000605&&000607&&000809&&001557&&001924 | 2024-08-01, 2024-11-13, 2024-11-21, 2025-01-21, 2025-05-04, 2025-05-15, 2025-08-05, 2025-12-22, 2026-02-03 | 00, 01, 02, 03 | 9 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10818 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 9000 | A.2 | 131242-WST02-DR-A-9000-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-9000 | NA | "SSN URA Submission" | 2025-12-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 001924 | 2025-12-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10819 | 001924 | 01 | NA | CSA | NA | 131242 | WST02 | DR | A | 9001 | A.2 | 131242-WST02-DR-A-9001-A.2 | 2026-02-03 | SSN URA Submission | Rev 0: To update the drawings based on latest comments for FSSD plan Rev 7 submission. | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-9001 | NA | "SSN URA Submission" | 2025-12-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A.2 | 001924 | 2025-12-22, 2026-02-03 | 00, 01 | 2 | Not Approved | NAP | 2026-03-23 |  | 0 | PEN | PEN
10820 | 001925 | 00 | NA | Process | NA | 131242 | WST02 | SP | P | 0004 | 0 | 131242-WST02-SP-P-0004-0 | 2025-12-22 | SSN Blower Plant Control Narrative | Rev0: Approved with comments. Please revise as per the comments and resubmit. | 2026-01-19 | 2026-02-09 | Approved with Comments | 2026-02-27 | NO | Overdue |  | 131242-WST02-SP-0004 | NA | "SSN Blower Plant Control Narrative" | 2025-12-22 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-11 | 49 | AWC | 2025-12-22 | 0 | 001925 | 2025-12-22 | 00 | 1 | Approved with Comments | AWC | 2026-02-27 | Overdue | 0 | AWC | AWC
10821 | 001926 | 00 | NA | QAQC | NA | 131242 | WST02 | QA | M | 0160 | 0 | 131242-WST02-QA-M-0160-0 | 2025-12-23 | FAT Report for Solenoid Valves (Norgren) | NA | 2026-01-20 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0160 | NA | "FAT Report for Solenoid Valves (Norgren)" | 2025-12-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-12 | 104 | PEN | 2025-12-23 | 0 | 001926 | 2025-12-23 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-09 |  | 0 | PEN | PEN
10822 | 001927 | 00 | NA | QAQC | NA | 131242 | WSD11 | QA | M | 0161 | 0 | 131242-WSD11-QA-M-0161-0 | 2025-12-23 | FAT Report for SS 316L Pipes - 77 Nos | NA | 2026-01-20 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0161 | NA | "FAT Report for SS 316L Pipes - 77 Nos" | 2025-12-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-12 | 104 | PEN | 2025-12-23 | 0 | 001927 | 2025-12-23 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-09 |  | 0 | PEN | PEN
10823 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1101 | X | 131242-WSW41-DR-S-1101-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10824 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1102 | X | 131242-WSW41-DR-S-1102-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1102 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10825 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1103 | X | 131242-WSW41-DR-S-1103-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1103 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10826 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1104 | X | 131242-WSW41-DR-S-1104-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1104 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10827 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1105 | X | 131242-WSW41-DR-S-1105-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1105 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10828 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1106 | X | 131242-WSW41-DR-S-1106-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1106 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10829 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1107 | X | 131242-WSW41-DR-S-1107-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1107 | NA | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2025-12-29 | X | 001928 | 2025-12-29 | 00 | 1 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10830 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1108 | X | 131242-WSW41-DR-S-1108-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-1108 | NA | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2025-12-29 | X | 001928 | 2025-12-29 | 00 | 1 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10831 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2100 | X | 131242-WSW41-DR-S-2100-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-2100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10832 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2101 | X | 131242-WSW41-DR-S-2101-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-2101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10833 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2102 | X | 131242-WSW41-DR-S-2102-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-2102 | NA | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2025-12-29 | X | 001928 | 2025-12-29 | 00 | 1 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10834 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3100 | X | 131242-WSW41-DR-S-3100-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-3100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10835 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3101 | X | 131242-WSW41-DR-S-3101-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-3101 | NA | "As built drawing for ST614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2025-12-29 | X | 001928 | 2025-12-29 | 00 | 1 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10836 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5100 | X | 131242-WSW41-DR-S-5100-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - General Notes" && "Pipe Support Standard- SWPR" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2026-01-19 | E | 000297&&000909&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
10837 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5101 | X | 131242-WSW41-DR-S-5101-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S01 U-Bolt" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 01, 02 | 5 | Not Approved | NAP |  |  | 0 | NAP | NAP
10838 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5102 | X | 131242-WSW41-DR-S-5102-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5102 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
10839 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5103 | X | 131242-WSW41-DR-S-5103-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5103 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S03 PAD" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP |  |  | 0 | NAP | NAP
10840 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5104 | X | 131242-WSW41-DR-S-5104-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5104 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S04 GUIDE FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29 | 00, 01, 02 | 4 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10841 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5105 | X | 131242-WSW41-DR-S-5105-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5105 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S05 STOPPER FOR HORIZONTAL BARE PIPE" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-03-13, 2025-12-29 | 00, 01 | 3 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10842 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5106 | X | 131242-WSW41-DR-S-5106-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-5106 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S06 DUMMY PIPE SHEET 1" | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-12 | 56 | NAP | 2025-12-29 | X | 000297&&001928 | 2024-02-01, 2025-12-29 | 00 | 2 | Not Approved | NAP | 2026-03-13 | Overdue | 0 | NAP | NAP
10843 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8002 | X | 131242-WSW41-DR-S-8002-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-8002 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10844 | 001928 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0310 | X | 131242-WSW41-DR-S-0310-X | 2025-12-29 | As built drawing for ST614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-01-26 | 2026-02-23 | Not Approved | 2026-03-13 | NO | NA |  | 131242-WSW41-DR-0310 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-18 | 56 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP |  |  | 0 | NAP | NAP
10845 | 001929 | 00 | NA | QAQC | NA | 131242 | WSW41 | QA | E | 0067 | 0 | 131242-WSW41-QA-E-0067-0 | 2025-12-30 | Earthing System Test Report (SSN Electrical Building) | Rev 0: Not approved - Revise and Resubmit | 2026-01-27 | 2026-02-24 | Not Approved | 2026-03-16 | NO | NA |  | 131242-WSW41-QA-0067 | NA | "Earthing System Test Report (SSN Electrical Building)" | 2025-12-30 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 56 | NAP | 2025-12-30 | 0 | 001929 | 2025-12-30 | 00 | 1 | Not Approved | NAP | 2026-03-16 | Overdue | 0 | NAP | NAP
10846 | 001930 | 00 | NA | PMT | NA | 131242 | WSW41 | LT | PM | 0079 | 0 | 131242-WSW41-LT-PM-0079-0 | 2025-12-31 | Notice For Extension Of Time and Cost For Delays For Change In Country Regulations, Laws, Requirements By Authorities | Rev (0): Received for information. Please refer to S.O. correspondence no. 436 dated 13 Feb 2026. | 2026-01-28 | 2026-02-24 | For Information |  | YES | NA |  | 131242-WSW41-LT-0079 | NA | "Notice For Extension Of Time and Cost For Delays For Change In Country Regulations, Laws, Requirements By Authorities" | 2025-12-31 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-20 | 55 | INF | 2025-12-31 | 0 | 001930 | 2025-12-31 | 00 | 1 | For Information | INF | 2026-03-16 | Overdue | 0 | INF | INF
10847 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0001 | A | 131242-WSD11-DR-A-0001-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0001 | NA | "Compressed Air System - Anchor Bolts Details & Plinth Details" && "Drawing Index (Building and Services Mech.)" && "THP BCA BP Submission" && "THP Drawing Index" && "THP Drawing Index for Cable Raceway and Room Layout" && "THP URA Amendment submissions" | 2024-04-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000423&&000783&&000996&&001002&&001893&&001931 | 2024-04-06, 2024-10-28, 2025-01-21, 2025-01-26, 2025-12-14, 2026-01-05 | 00 | 6 | For Information | INF | 2026-02-20 |  | 0 | PEN | PEN
10848 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0002 | A | 131242-WSD11-DR-A-0002-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0002 | NA | "THP BCA BP Submission" && "THP Drawing Index" && "THP URA Amendment submissions" | 2024-10-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000783&&001893&&001931 | 2024-10-28, 2025-12-14, 2026-01-05 | 00 | 3 | For Information | INF | 2026-02-20 |  | 0 | PEN | PEN
10849 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 0003 | A | 131242-WSD11-DR-A-0003-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0003 | NA | "THP BCA BP Submission" && "THP URA Amendment submissions" | 2025-12-14 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 001893&&001931 | 2025-12-14, 2026-01-05 | 00 | 2 | Awaiting S.O.'s response | PEN | 2026-02-20 |  | 0 | PEN | PEN
10850 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1000 | A | 131242-WSD11-DR-A-1000-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP Lighting Layout Plan" && "THP Lightning Protection System" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000311&&000390&&000414&&000446&&001039&&001073&&001931 | 2023-11-30, 2023-12-05, 2024-02-13, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-06-04, 2025-08-21, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP | 2026-02-20 |  | 0 | PEN | PEN
10851 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1001 | A | 131242-WSD11-DR-A-1001-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1001 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Biosolid Building Fire Escape RC Corridor and C4A Staircase Compartment Design " && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP-Dry Riser System" | 2023-11-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000446&&000819&&001039&&001073&&001328&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-04-19, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-02-25, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 26 | Not Approved | NAP | 2026-02-20 |  | 0 | PEN | PEN
10852 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1002 | A | 131242-WSD11-DR-A-1002-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1002 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 25 | Not Approved | NAP | 2026-02-20 |  | 0 | PEN | PEN
10853 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1003 | A | 131242-WSD11-DR-A-1003-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP |  |  | 0 | PEN | PEN
10854 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 1004 | A | 131242-WSD11-DR-A-1004-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1004 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP URA Amendment submissions" | 2023-11-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000217&&000218&&000292&&000414&&001328&&001893&&001931 | 2023-11-30, 2023-12-05, 2024-04-02, 2024-08-13, 2024-09-03, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05 | 00, 01, 02, 03, 04 | 18 | Not Approved | NAP | 2026-02-20 |  | 0 | PEN | PEN
10855 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 2000 | A | 131242-WSD11-DR-A-2000-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-2000 | NA | "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP URA Amendment submissions" | 2024-11-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000819&&001893&&001931 | 2024-11-18, 2025-12-14, 2026-01-05 | 00 | 3 | For Information | INF | 2026-02-20 |  | 0 | PEN | PEN
10856 | 001931 | 00 | NA | CSA | NA | 131242 | WSD11 | DR | A | 3000 | A | 131242-WSD11-DR-A-3000-A | 2026-01-05 | THP BCA BP Submission | NA | 2026-02-02 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3000 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Dry Riser Installation Details" && "Milestone 2 THP Compressed Air System" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Layout, Elevations and Section Details" && "THP Lightning Protection System" && "THP MCC Outline Drawing" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP SLD" && "THP URA Amendment submissions" && "THP-Dry Riser System" | 2024-02-13 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-19 | 91 | PEN | 2026-01-05 | A | 000292&&000302&&000311&&000390&&000570&&000575&&000819&&001039&&001073&&001893&&001902&&001931 | 2024-02-13, 2024-03-23, 2024-07-17, 2024-08-27, 2024-10-01, 2024-10-03, 2024-10-18, 2024-11-18, 2024-11-21, 2025-02-12, 2025-02-25, 2025-03-07, 2025-05-09, 2025-06-04, 2025-10-23, 2025-11-28, 2025-12-14, 2025-12-16, 2026-01-05 | 00, 01, 02, 03, 04, 05 | 22 | Approved | APP |  |  | 0 | PEN | PEN
10857 | 001932 | 00 | Bryan | Mech | NA | 131242 | WSW41 | MS | BH | 0002 | 0 | 131242-WSW41-MS-BH-0002-0 | 2026-01-05 | MSRA, SWP for Testing and Commissioning for ACMV System works | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-02 | 2026-01-07 | Not Approved | 2026-01-27 | NO | Overdue |  | 131242-WSW41-MS-0002 | NA | "Delivery and Storage of Compressor Package at Biosolids Building " && "MSRA & SWP for Pre-Augering Work" && "MSRA, SWP for Electrical Work" && "MSRA, SWP for Erection, Modification and Dismantling of Scaffold Works" && "MSRA, SWP for Testing and Commissioning for ACMV System works" | 2024-07-08 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-19 | 2 | NAP | 2026-01-05 | 0 | 000551&&000564&&000759&&001532&&001932 | 2024-07-08, 2024-07-12, 2024-10-14, 2024-10-15, 2024-10-30, 2025-07-28, 2026-01-05 | 00, 01, 02 | 7 | Not Approved | NAP | 2026-01-27 | Overdue | 0 | NAP | NAP
10858 | 001933 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0065 | 0 | 131242-WSW41-QA-I-0065-0 | 2026-01-05 | Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP) | Rev 0. Approved with comments. Revise and resubmit required. Refer to the attached SRC response. | 2026-02-02 | 2026-01-22 | Approved with Comments | 2026-02-11 | NO | Overdue |  | 131242-WSW41-QA-0065 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for G2D Pressure Regulating Valve" && "Vendor Manufacturing Inspection Test Plan for Thermal Flow Switch (THP)" | 2025-04-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-19 | 17 | AWC | 2026-01-05 | 0 | 001220&&001933 | 2025-04-10, 2026-01-05 | 00 | 2 | Approved with Comments | AWC | 2026-02-11 | Overdue | 0 | AWC | AWC
10859 | 001934 | 00 | Freedomer | EICA | NA | 131242 | WSW41 | MM | PM | 0002 | 0 | 131242-WSW41-MM-PM-0002-0 | 2026-01-05 | Memo-Appointment of LEW Representatives_01 Nov 2025 | Rev 0: For Information | 2026-02-02 | 2026-02-09 | For Information |  | YES | NA |  | 131242-WSW41-MM-0002 | NA | "Memo-Appointment of LEW Representatives_01 Nov 2025" | 2026-01-05 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-25 | 35 | INF | 2026-01-05 | 0 | 001934 | 2026-01-05 | 00 | 1 | For Information | INF | 2026-02-27 | Overdue | 0 | INF | INF
10860 | 001935 | 00 | Dhanapal | QAQC | NA | 131242 | WSW41 | QA | I | 0066 | 0 | 131242-WSW41-QA-I-0066-0 | 2026-01-07 | Factory Acceptance Test Report for Thermal Flow Switch (THP) | Rev 0. Approved with comments. Revise and resubmit. Refer to attached SRC response | 2026-02-04 | 2026-01-22 | Approved with Comments | 2026-02-11 | NO | Overdue |  | 131242-WSW41-QA-0066 | NA | "Factory Acceptance Test Report for Thermal Flow Switch (THP)" | 2026-01-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-27 | 15 | AWC | 2026-01-07 | 0 | 001935 | 2026-01-07 | 00 | 1 | Approved with Comments | AWC | 2026-02-11 | Overdue | 0 | AWC | AWC
10861 | 001936 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DS | E | 0001 | 0 | 131242-WSD11-DS-E-0001-0 | 2026-01-07 | THP and SSN Cable Ladder/ Tray Data Sheet and Specifications | NA | 2026-02-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0001 | NA | " Data Sheet and Drawing of Air Compressor System " && "Data Sheet of Air Compressor" && "Data Sheet of Air Compressor System" && "THP and SSN Cable Ladder/ Tray Data Sheet and Specifications" | 2023-11-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-21 | 89 | PEN | 2026-01-07 | 0 | 000177&&001936 | 2023-11-09, 2024-04-04, 2024-08-12, 2024-11-06, 2026-01-07 | 00, 01, 02, 03 | 5 | Approved | APP |  |  | 0 | PEN | PEN
10862 | 001937 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DS | E | 0026 | 0 | 131242-WST02-DS-E-0026-0 | 2026-01-07 | SSN ACB Lifting Truck Data Sheet | Rev 0: Not approved - Revise and Resubmit | 2026-02-04 | 2026-02-09 | Not Approved | 2026-02-27 | NO | Overdue |  | 131242-WST02-DS-0026 | NA | "SSN ACB Lifting Truck Data Sheet" | 2026-01-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-27 | 33 | NAP | 2026-01-07 | 0 | 001937 | 2026-01-07 | 00 | 1 | Not Approved | NAP | 2026-02-27 | Overdue | 0 | NAP | NAP
10863 | 001938 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0163 | 0 | 131242-WST02-QA-M-0163-0 | 2026-01-07 | Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen) | NA | 2026-02-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0163 | NA | "Vendor Manufacturing ITP and Test Procedure for Safety Relief Valve (ARI Arimaturen)" | 2026-01-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-27 | 89 | PEN | 2026-01-07 | 0 | 001938 | 2026-01-07 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-24 |  | 0 | PEN | PEN
10864 | 001939 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0162 | 0 | 131242-WSD11-QA-M-0162-0 | 2026-01-07 | FAT Report for SS 316L (CWP 205) Pipes - 201 Nos | NA | 2026-02-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0162 | NA | "FAT Report for SS 316L (CWP 205) Pipes - 201 Nos" | 2026-01-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-01-27 | 89 | PEN | 2026-01-07 | 0 | 001939 | 2026-01-07 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-24 |  | 0 | PEN | PEN
10865 | 001940 | 00 | Kumar | QAQC | NA | 131242 | WSW41 | QA | A | 0031 | 0 | 131242-WSW41-QA-A-0031-0 | 2026-01-08 | SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team) | R0: Approved | 2026-02-05 | 2026-02-12 | Approved |  | YES | NA |  | 131242-WSW41-QA-0031 | NA | "FAT report for LVSG Panels (Sunlight)" && "FAT report for SS Cable Ladder, Cable Tray, Accessories 5th batch (HDMANN)" && "Issue for Information-Monthly Concrete Cube Records for Structural works for Jan & Feb 2025 " && "SSN Electrical Building & SSN Watertank metal door painting system material submission (ISO-Team)" | 2025-05-04 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-22 | 35 | APP | 2026-01-08 | 0 | 001267&&001303&&001439&&001940 | 2025-05-04, 2025-05-18, 2025-07-07, 2026-01-08 | 00 | 4 | Approved | APP |  |  | 0 | APP | APP
10866 | 001941 | 00 | Heng Peng | BIM | NA | 131242 | WSW41 | CD | IM | 9999 | 0 | 131242-WSW41-CD-IM-- | 2026-01-08 | VCM Submission for 2025-12 | NA | 2026-02-05 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-CD-9999 | NA | " VCM Submission for 2025-11" && "VCM Model Submission" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2024-12-09 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-22 | 88 | PEN | 2026-02-09 | A | 000879&&001888&&001941&&002009 | 2024-12-09, 2025-12-08, 2026-01-08, 2026-02-09 | 00 | 4 | For Information | INF |  |  | 0 | PEN | PEN
10867 | 001942 | 00 | Vincent | Contracts | NA | 131242 | WSW41 | LT | PM | 0080 | 0 | 131242-WSW41-LT-PM-0080-0 | 2026-01-12 | Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation | NA | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0080 | NA | "Notice For Extension Of Time And Cost For Delays For BMS SCADA Graphics Design Specification Standardisation" | 2026-01-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-01 | 84 | PEN | 2026-01-12 | 0 | 001942 | 2026-01-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-27 |  | 0 | PEN | PEN
10868 | 001943 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0164 | 0 | 131242-WSW41-QA-M-0164-0 | 2026-01-12 | Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax) | NA | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0164 | NA | "Vendor Manufacturing Inspection Test Plan and FAT procedure for Safety Relief Valve (Spirax)" | 2026-01-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-01 | 84 | PEN | 2026-01-12 | 0 | 001943 | 2026-01-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-27 |  | 0 | PEN | PEN
10869 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 8002 | C | 131242-WSD11-DR-S-8002-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-8002 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | NAP | 2026-01-12 | C | 001944 | 2026-01-12 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10870 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1100 | C | 131242-WSD11-DR-S-1100-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-1100 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" | 2023-12-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 31 | NAP | 2026-01-12 | C | 000236&&000292&&001328&&001944 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12 | 00, 01, 02, 03 | 7 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10871 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0306 | C | 131242-WSD11-DR-S-0306-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-0306 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | NAP | 2026-01-12 | C | 001944 | 2026-01-12 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10872 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0307 | C | 131242-WSD11-DR-S-0307-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-0307 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | NAP | 2026-01-12 | C | 001944 | 2026-01-12 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10873 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 0308 | C | 131242-WSD11-DR-S-0308-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-0308 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | NAP | 2026-01-12 | C | 001944 | 2026-01-12 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10874 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1101 | C | 131242-WSD11-DR-S-1101-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 31 | NAP | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF |  |  | 0 | NAP | NAP
10875 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 2100 | C | 131242-WSD11-DR-S-2100-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-2100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | NAP | 2026-01-12 | C | 001944 | 2026-01-12 | 00 | 1 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10876 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 3100 | C | 131242-WSD11-DR-S-3100-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-3100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP UPSDB-0001 SLD, Schematic and GA Drawing" && "THP UPSDB-0001A SLD, Schematic and GA Drawing" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 31 | NAP | 2026-01-27 | B | 001758&&001944 | 2025-10-22, 2026-01-12, 2026-01-27 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | NAP | NAP
10877 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5100 | C | 131242-WSD11-DR-S-5100-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-5100 | NA | "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP PC Pump GA Drawings" | 2024-08-15 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 31 | NAP | 2026-01-12 | C | 000651&&001944 | 2024-08-15, 2025-06-12, 2026-01-12 | 00, 01 | 3 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10878 | 001944 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5101 | C | 131242-WSD11-DR-S-5101-C | 2026-01-12 | ST622_QPD Amendment As built Drawing (Amendment of ST619) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Not Approved | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-5101 | NA | "Hookup Drawing for PIT at Air Receiver " && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" | 2025-06-10 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 31 | NAP | 2026-01-12 | C | 001351&&001944 | 2025-06-10, 2026-01-12 | 00 | 2 | Not Approved | NAP | 2026-03-04 | Overdue | 0 | NAP | NAP
10879 | 001945 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 5407 | B | 131242-WSD11-DR-S-5407-B | 2026-01-12 | G2D Pipe Support_Report from QPD | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Approved with Comments | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-5407 | NA | "G2D Pipe Support_Report from QPD" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | AWC | 2026-01-12 | B | 001945 | 2026-01-12 | 00 | 1 | Approved with Comments | AWC | 2026-03-04 | Overdue | 0 | AWC | AWC
10880 | 001945 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | S | 1613 | B | 131242-WSD11-DR-S-1613-B | 2026-01-12 | G2D Pipe Support_Report from QPD | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Approved with Comments | 2026-03-04 | NO | Overdue |  | 131242-WSD11-DR-1613 | NA | "G2D Pipe Support_Report from QPD" | 2026-01-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-02-01 | 31 | AWC | 2026-01-12 | B | 001945 | 2026-01-12 | 00 | 1 | Approved with Comments | AWC | 2026-03-04 | Overdue | 0 | AWC | AWC
10881 | 001945 | 00 | Aaron | CSA | NA | 131242 | WSD11 | CL | S | 0007 | 1 | 131242-WSD11-CL-S-0007-1 | 2026-01-12 | G2D Pipe Support_Report from QPD | R0: Approved with comments. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-12 | Approved with Comments | 2026-03-04 | NO | Overdue |  | 131242-WSD11-CL-0007 | NA | "G2D Pipe Support_Report from QPD" && "Steam Sparger Calculation" && "Support design for compressed Air system >2m" | 2024-08-20 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 31 | AWC | 2026-01-12 | 1 | 000664&&000960&&001945 | 2024-08-20, 2025-01-10, 2025-04-10, 2026-01-12 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-04 | Overdue | 0 | AWC | AWC
10882 | 001946 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0166 | 0 | 131242-WSW41-QA-M-0166-0 | 2026-01-12 | FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) | NA | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0166 | NA | "FAT Report for Manual Knife Gate Valves- Batch 5 (JASH) " | 2026-01-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-01 | 84 | PEN | 2026-01-12 | 0 | 001946 | 2026-01-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-27 |  | 0 | PEN | PEN
10883 | 001947 | 00 | Dhanapal | QAQC | NA | 131242 | WST02 | QA | I | 0067 | 0 | 131242-WST02-QA-I-0067-0 | 2026-01-12 | Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN | NA | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0067 | NA | "Vendor Manufacturing Inspection and Test Plan and FAT Procedure for Building Management System (BMS) (Willowglen) SSN" | 2026-01-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-01 | 84 | PEN | 2026-01-12 | 0 | 001947 | 2026-01-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-27 |  | 0 | PEN | PEN
10884 | 001948 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DS | E | 0003 | 0 | 131242-WSD11-DS-E-0003-0 | 2026-01-12 | THP and SSN Earthing Material Specifications | NA | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0003 | NA | "THP PLC RIO Component Datasheet" && "THP and SSN Earthing Material Specifications" | 2023-12-14 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-01-26 | 84 | PEN | 2026-01-12 | 0 | 000242&&001948 | 2023-12-14, 2024-03-11, 2026-01-12 | 00, 01 | 3 | Not Approved | NAP | 2026-02-27 |  | 0 | PEN | PEN
10885 | 001949 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0032 | 0 | 131242-WST02-QA-A-0032-0 | 2026-01-12 | Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-09 | 2026-02-02 | Not Approved | 2026-02-20 | NO | Overdue |  | 131242-WST02-QA-0032 | NA | "SAT Procedure for LVSG Panels (Sunlight)" && "Samples Submission for Staircase steps non-slip nosing tiles Huayu Construction Pte Ltd)" && "Vendor Manufacturing Inspection Test Plan for Tuning Fork Level Switches (SSN)" | 2025-07-16 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-26 | 21 | NAP | 2026-01-12 | 0 | 001481&&001554&&001949 | 2025-07-16, 2025-08-04, 2026-01-12 | 00 | 3 | Not Approved | NAP | 2026-02-20 | Overdue | 0 | NAP | NAP
10886 | 001950 | 00 | Kumar | QAQC | NA | 131242 | WST02 | QA | A | 0033 | 0 | 131242-WST02-QA-A-0033-0 | 2026-01-12 | Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal) | For Information | 2026-02-09 | 2026-02-20 | For Information |  | YES | NA |  | 131242-WST02-QA-0033 | NA | " Vendor Manufacturing Inspection Test Plan for Thermal Flow / Mass Flowmeter" && "Samples Submission for Aluminium double bank louvers with netting (Wan Sern Metal)" | 2025-07-14 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-01-26 | 39 | INF | 2026-01-12 | 0 | 001474&&001950 | 2025-07-14, 2026-01-12 | 00 | 2 | For Information | INF | 2026-03-12 | Overdue | 0 | INF | INF
10887 | 001951 | 00 | Mohan | QAQC | NA | 131242 | WSD11 | QA | M | 0167 | 0 | 131242-WSD11-QA-M-0167-0 | 2026-01-12 | FAT Report for Non Return Check Valve - Batch 2 (Breen) | NA | 2026-02-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0167 | NA | "FAT Report for Non Return Check Valve - Batch 2 (Breen)" | 2026-01-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-01 | 84 | PEN | 2026-01-12 | 0 | 001951 | 2026-01-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-02-27 |  | 0 | PEN | PEN
10888 | 001952 | 00 | Mohan | QAQC | NA | 131242 | WSW41 | QA | M | 0168 | 0 | 131242-WSW41-QA-M-0168-0 | 2026-01-13 | Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax) | NA | 2026-02-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0168 | NA | "Vendor Manufacturing Inspection and Test Plan & Test Procedure for Y Strainer (Spirax)" | 2026-01-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-02 | 83 | PEN | 2026-01-13 | 0 | 001952 | 2026-01-13 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-02 |  | 0 | PEN | PEN
10889 | 001953 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | LT | PM | 0081 | 0 | 131242-WSW41-LT-PM-0081-0 | 2026-01-14 | CV of Team Member (MEM) | NA | 2026-02-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0081 | NA | "CV of Team Member (MEM)" && "Purchase Of Spare Parts Under SOP 10" | 2026-01-14 | YES | NO | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-03 | 82 | PEN | 2026-02-11 | 0 | 001953&&002012 | 2026-01-14, 2026-02-11 | 00 | 2 | Awaiting S.O.'s response | PEN |  |  | 0 | PEN | PEN
10890 | 001954 | 00 | Yi Hao | Contracts | NA | 131242 | WSW41 | PC | W | 0030 | 0 | 131242-WSW41-PC-W-0030-0 | 2026-01-14 | Payment Claim No.30 | NA | 2026-02-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-PC-0030 | NA | "Payment Claim No.30" | 2026-01-14 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-03 | 82 | PEN | 2026-01-14 | 0 | 001954 | 2026-01-14 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-03 |  | 0 | PEN | PEN
10891 | 001955 | 00 | Htet Nu | PMT | NA | 131242 | WSW41 | RT | PM | 0032 | 0 | 131242-WSW41-RT-PM-0032-0 | 2026-01-15 | C4B Monthly Progress Report Number No.32 (12 25) | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-RT-0032 | NA | "C4B Monthly Progress Report Number No.32 (12 25)" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | 0 | 001955 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10892 | 001956 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0012 | 0 | 131242-WSD11-DS-I-0012-0 | 2026-01-15 | Datasheet for Thermal Flow Switch (THP-BOP) | Rev 0. Approved with comments. Revise and resubmit required. Refer to the attached SRC response. | 2026-02-12 | 2026-01-20 | Approved with Comments | 2026-02-09 | NO | Overdue |  | 131242-WSD11-DS-0012 | NA | "Data Sheet of Desuperheater " && "Datasheet for Thermal Flow Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema; Resubmission_Forecast_Date invalid date format (expected YYYY-MM-DD) | 2026-01-29 | 5 | AWC | 2026-01-15 | 0 | 000634&&000648&&001956 | 2024-08-12, 2026-01-15 | 00 | 3 | Approved with Comments | AWC | 2026-02-09 | Overdue | 0 | AWC | AWC
10893 | 001957 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5430 | A | 131242-WST02-DR-I-5430-A | 2026-01-15 | Hookup Drawing for NO2 / NO3 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5430 | NA | "Hookup Drawing for NO2 / NO3 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001957 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10894 | 001957 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5431 | A | 131242-WST02-DR-I-5431-A | 2026-01-15 | Hookup Drawing for NO2 / NO3 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5431 | NA | "Hookup Drawing for NO2 / NO3 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001957 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10895 | 001957 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5432 | A | 131242-WST02-DR-I-5432-A | 2026-01-15 | Hookup Drawing for NO2 / NO3 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5432 | NA | "Hookup Drawing for NO2 / NO3 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001957 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10896 | 001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5440 | A | 131242-WST02-DR-I-5440-A | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5440 | NA | "Hookup Drawing for NH4 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001958 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10897 | 001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5441 | A | 131242-WST02-DR-I-5441-A | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5441 | NA | "Hookup Drawing for NH4 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001958 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10898 | 001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5442 | A | 131242-WST02-DR-I-5442-A | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5442 | NA | "Hookup Drawing for NH4 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001958 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10899 | 001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5443 | A | 131242-WST02-DR-I-5443-A | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5443 | NA | "Hookup Drawing for NH4 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001958 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10900 | 001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5444 | A | 131242-WST02-DR-I-5444-A | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5444 | NA | "Hookup Drawing for NH4 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001958 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10901 | 001958 | 00 | Yean Yee | EICA | NA | 131242 | WST02 | DR | I | 5445 | A | 131242-WST02-DR-I-5445-A | 2026-01-15 | Hookup Drawing for NH4 Analyser | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5445 | NA | "Hookup Drawing for NH4 Analyser" | 2026-01-15 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-04 | 81 | PEN | 2026-01-15 | A | 001958 | 2026-01-15 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-04 |  | 0 | PEN | PEN
10902 | 001959 | 00 | Yean Yee | EICA | NA | 131242 | WSD11 | DS | I | 0013 | A | 131242-WSD11-DS-I-0013-A | 2026-01-15 | Datasheet for Electromagnetic Flow Meter (THP-BOP) | NA | 2026-02-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0013 | NA | "Data Sheet and Drawing of THP Feed Pump" && "Data Sheet of THP Feed Pump" && "Datasheet for Electromagnetic Flow Meter (THP-BOP) " && "THP Pump Motor Data Sheet" | 2024-04-05 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-01-29 | 81 | PEN | 2026-01-15 | A | 000421&&000634&&001959 | 2024-04-05, 2024-08-12, 2025-01-26, 2026-01-15 | 00, 01, 02 | 5 | Approved | APP |  |  | 0 | PEN | PEN
10903 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0001_FSSD BP | A | 131242-WSD11-DR-A-0001_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0001_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10904 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0002_FSSD BP | A | 131242-WSD11-DR-A-0002_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0002_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10905 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 0003_FSSD BP | A | 131242-WSD11-DR-A-0003_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-0003_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10906 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1000_FSSD BP | A | 131242-WSD11-DR-A-1000_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1000_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10907 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1001_FSSD BP | A | 131242-WSD11-DR-A-1001_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1001_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10908 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1002_FSSD BP | A | 131242-WSD11-DR-A-1002_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1002_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10909 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1003_FSSD BP | A | 131242-WSD11-DR-A-1003_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1003_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10910 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 1004_FSSD BP | A | 131242-WSD11-DR-A-1004_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1004_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10911 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 2000_FSSD BP | A | 131242-WSD11-DR-A-2000_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-2000_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10912 | 001960 | 00 | Aaron | CSA | NA | 131242 | WSD11 | DR | A | 3000_FSSD BP | A | 131242-WSD11-DR-A-3000_FSSD BP-A | 2026-01-19 | THP_FSSD (BP) Submission | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3000_FSSD BP | NA | "THP_FSSD (BP) Submission" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Document_Sequence_Number pattern mismatch (^[0-9]{4}$); Document_ID pattern mismatch (^[A-Z0-9-]+$); Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | A | 001960 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10913 | 001961 | 00 | Yuen Fatt | BS | NA | 131242 | WST02 | VI | B | 0007 | 0 | 131242-WST02-VI-B-0007-0 | 2026-01-19 | Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-VI-0007 | NA | "VENDOR APPROVAL OF LOUVRE DOOR AND WINDOW - WAN SERN METAL INDUSTRIES PTE. LTD." && "Vendor Approval of Earthing System & LPS Material" && "Vendor Approval of Earthing System & LPS Material (Heng)" && "Vendor Approval of Hydrogen Detection System – Pacific Reliance Pte. Ltd. (Gastron)" && "Vendor Approval of SSN Package (Ammonia Analyser - GSE & ISE)" | 2024-04-16 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | 0 | 000438&&000589&&001434&&001961 | 2024-04-16, 2024-07-26, 2024-07-28, 2024-09-02, 2024-10-18, 2025-02-27, 2025-07-04, 2026-01-19 | 00, 01, 02, 03 | 8 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10914 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0310 | E | 131242-WSW41-DR-S-0310-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-0310 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10915 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0311 | E | 131242-WSW41-DR-S-0311-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-0311 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-08 | 32 | NAP | 2026-01-19 | E | 001962 | 2026-01-19 | 00 | 1 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10916 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0312 | D | 131242-WSW41-DR-S-0312-D | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-0312 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-08 | 32 | NAP | 2026-01-19 | D | 001962 | 2026-01-19 | 00 | 1 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10917 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0313 | D | 131242-WSW41-DR-S-0313-D | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-0313 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-08 | 32 | NAP | 2026-01-19 | D | 001962 | 2026-01-19 | 00 | 1 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10918 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0314 | D | 131242-WSW41-DR-S-0314-D | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-0314 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-08 | 32 | NAP | 2026-01-19 | D | 001962 | 2026-01-19 | 00 | 1 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10919 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0315 | D | 131242-WSW41-DR-S-0315-D | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-0315 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2026-01-19 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-08 | 32 | NAP | 2026-01-19 | D | 001962 | 2026-01-19 | 00 | 1 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10920 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1100 | E | 131242-WSW41-DR-S-1100-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1100 | NA | "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Sitewide Piperack Earthing System" | 2024-01-23 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 000281&&001962 | 2024-01-23, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10921 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1101 | E | 131242-WSW41-DR-S-1101-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10922 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1102 | E | 131242-WSW41-DR-S-1102-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1102 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10923 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1103 | E | 131242-WSW41-DR-S-1103-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1103 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10924 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1104 | E | 131242-WSW41-DR-S-1104-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1104 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10925 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1105 | E | 131242-WSW41-DR-S-1105-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1105 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10926 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1106 | E | 131242-WSW41-DR-S-1106-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-1106 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10927 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2100 | E | 131242-WSW41-DR-S-2100-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-2100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10928 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2101 | E | 131242-WSW41-DR-S-2101-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-2101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10929 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3100 | E | 131242-WSW41-DR-S-3100-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-3100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10930 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5100 | E | 131242-WSW41-DR-S-5100-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-5100 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - General Notes" && "Pipe Support Standard- SWPR" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 000297&&000909&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 5 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10931 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5101 | E | 131242-WSW41-DR-S-5101-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-5101 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S01 U-Bolt" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-06-25, 2025-12-29, 2026-01-19 | 00, 01, 02 | 5 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10932 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5102 | E | 131242-WSW41-DR-S-5102-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-5102 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S02 SHOE (DN15 ~ DN450)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10933 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5103 | E | 131242-WSW41-DR-S-5103-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-5103 | NA | "As built drawing for ST614 (SWPR PR 03)" && "Pipe Support Standard - S03 PAD" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" && "Standard Pipe Support - For All Area " | 2024-02-01 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 000297&&001928&&001962 | 2024-02-01, 2025-03-13, 2025-12-29, 2026-01-19 | 00, 01 | 4 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10934 | 001962 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8002 | E | 131242-WSW41-DR-S-8002-E | 2026-01-19 | QPD As Built Drawing for ST 614 (SWPR PR 03) | R0: Not Approved. Please refer to comment sheet for resubmission. | 2026-02-16 | 2026-02-20 | Not Approved | 2026-03-12 | NO | NA |  | 131242-WSW41-DR-8002 | NA | "As built drawing for ST614 (SWPR PR 03)" && "QPD As Built Drawing for ST 614 (SWPR PR 03)" | 2025-12-29 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 32 | NAP | 2026-01-19 | E | 001928&&001962 | 2025-12-29, 2026-01-19 | 00 | 2 | Not Approved | NAP | 2026-03-12 | Overdue | 0 | NAP | NAP
10935 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0300 | F | 131242-WSW41-DR-S-0300-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0300 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10936 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0301 | F | 131242-WSW41-DR-S-0301-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0301 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10937 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0302 | F | 131242-WSW41-DR-S-0302-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0302 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10938 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0303 | F | 131242-WSW41-DR-S-0303-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0303 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10939 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0304 | F | 131242-WSW41-DR-S-0304-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0304 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10940 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0305 | F | 131242-WSW41-DR-S-0305-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0305 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10941 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0306 | F | 131242-WSW41-DR-S-0306-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0306 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10942 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0307 | F | 131242-WSW41-DR-S-0307-F | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0307 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10943 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0308 | F | 131242-WSW41-DR-S-0308- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0308 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10944 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 0309 | F | 131242-WSW41-DR-S-0309- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-0309 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10945 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1000 | F | 131242-WSW41-DR-S-1000- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-1000 | NA | "Drawing of Pre-Con Topographical Survey" && "Milestone 2 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-07-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | F | 000051&&000120&&000252&&001963 | 2023-07-18, 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2026-01-19 | 00, 01, 02, 04, 05 | 9 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10946 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1001 | F | 131242-WSW41-DR-S-1001- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-1001 | NA | "Panel Base Frame Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2025-04-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | F | 001235&&001963 | 2025-04-18, 2026-01-19 | 00 | 2 | For Information | INF | 2026-03-06 |  | 0 | PEN | PEN
10947 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1002 | F | 131242-WSW41-DR-S-1002- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-1002 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10948 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1003 | F | 131242-WSW41-DR-S-1003- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-1003 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10949 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 1004 | F | 131242-WSW41-DR-S-1004- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-1004 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10950 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2000 | F | 131242-WSW41-DR-S-2000- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-2000 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Earthing System" | 2024-01-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | F | 000281&&001963 | 2024-01-23, 2026-01-19 | 00 | 2 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10951 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 2001 | F | 131242-WSW41-DR-S-2001- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-2001 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | F | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10952 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 3000 | F | 131242-WSW41-DR-S-3000- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-3000 | NA | "LCS GA and Schematic Drawing" && "Milestone 2 Sitewide Pipe Rack" && "Milestone 3 Sitewide Pipe Rack" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Lightning Protection System" | 2023-12-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | F | 000120&&000252&&001206&&001963 | 2023-12-27, 2024-07-06, 2024-10-05, 2025-02-25, 2025-02-26, 2025-04-07, 2025-10-08, 2026-01-19 | 00, 01, 02, 04, 05, 06 | 10 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10953 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5000 | F | 131242-WSW41-DR-S-5000- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-5000 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" && "Sitewide Piperack Earthing System" && "Sitewide Piperack Handrail and Cad Ladder Layout and Details " | 2024-01-23 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | F | 000281&&001136&&001963 | 2024-01-23, 2025-03-20, 2026-01-19 | 00 | 3 | Not Approved | NAP | 2026-03-06 |  | 0 | PEN | PEN
10954 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5001 | E | 131242-WSW41-DR-S-5001-E | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-5001 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2024-03-11 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | E | 000099&&001963 | 2024-03-11, 2026-01-19 | 00, 01 | 2 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10955 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5002 | E | 131242-WSW41-DR-S-5002-E | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-5002 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2023-09-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | E | 000099&&001963 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10956 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 5003 | E | 131242-WSW41-DR-S-5003- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-5003 | NA | "C4B Sitewide Piping GA Drawing" && "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2023-09-13 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-01-19 | E | 000099&&001963 | 2023-09-13, 2024-03-11, 2026-01-19 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-06 |  | 0 | PEN | PEN
10957 | 001963 | 00 | Aaron | CSA | NA | 131242 | WSW41 | DR | S | 8001 | E | 131242-WSW41-DR-S-8001- | 2026-01-19 | QPD As Built Drawing for ST 621 (SWPR PR 01 & 02) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-DR-8001 | NA | "QPD As Built Drawing for ST 621 (SWPR PR 01 & 02)" | 2026-01-19 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-08 | 77 | PEN | 2026-01-19 | E | 001963 | 2026-01-19 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-06 |  | 0 | PEN | PEN
10958 | 001964 | 00 | Aaron | CSA | NA | 131242 | NA | NA | NA | 9999 | E | 131242----- | 2026-01-19 | Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | PEN | PEN
10959 | 001965 | 00 | Aaron | CSA | NA | 131242 | NA | NA | NA | 9999 | E | 131242----- | 2026-01-19 | Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed) | NA | 2026-02-16 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | YES | NO | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-02 | 77 | PEN | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ |  |  | 0 | PEN | PEN
10960 | 001966 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BF | 1003 | E | 131242-WSD11-DR-BF-1003- | 2026-01-20 | THP Fire Alarm System Layout Plan | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-1003 | NA | "Biosolid Building Cable Tray Wall Opening Layout & Section Drawings" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP BCA BP Submission" && "THP Fire Alarm System Layout Plan" && "THP GA Drawings" && "THP ICA GA & Wiring drawings" && "THP Layout, Elevations and Section Details" && "THP Lighting Layout Plan" && "THP Power Layout Plan" && "THP Protected Corridor Area-Building Service (Mechanical)" && "THP URA Amendment submissions" | 2023-11-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | E | 000217&&000218&&000292&&000390&&000414&&000819&&001039&&001328&&001893&&001931&&001966 | 2023-11-30, 2023-12-05, 2024-03-23, 2024-04-02, 2024-08-13, 2024-08-27, 2024-09-03, 2024-11-18, 2025-02-12, 2025-04-16, 2025-04-17, 2025-05-09, 2025-05-28, 2025-06-04, 2025-08-21, 2025-10-28, 2025-11-28, 2025-12-14, 2026-01-05, 2026-01-20 | 00, 01, 02, 03, 04 | 24 | Not Approved | NAP | 2026-03-09 |  | 0 | PEN | PEN
10961 | 001967 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0014 | 0 | 131242-WSD11-DS-I-0014-0 | 2026-01-20 | Datasheet for Pressure Gauge (THP-BOP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-17 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-DS-0014 | NA | "Data Sheet and Drawing of Reactor Feed Pump" && "Datasheet for Pressure Gauge (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-04-06 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-03 | 35 | AWC | 2026-01-20 | 0 | 000422&&000634&&001967 | 2024-04-06, 2024-08-12, 2025-04-10, 2026-01-20 | 00, 01, 02 | 5 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10962 | 001968 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5330 | 0 | 131242-WST02-DR-I-5330- | 2026-01-20 | Hookup Drawing -Tuning Fork Level Switch | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5330 | NA | "Hookup Drawing -Tuning Fork Level Switch" | 2026-01-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-09 | 76 | PEN | 2026-01-20 | 0 | 001968 | 2026-01-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-09 |  | 0 | PEN | PEN
10963 | 001968 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5331 | 0 | 131242-WST02-DR-I-5331- | 2026-01-20 | Hookup Drawing -Tuning Fork Level Switch | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5331 | NA | "Hookup Drawing -Tuning Fork Level Switch" | 2026-01-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-09 | 76 | PEN | 2026-01-20 | 0 | 001968 | 2026-01-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-09 |  | 0 | PEN | PEN
10964 | 001969 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5500 | 0 | 131242-WST02-DR-I-5500- | 2026-01-20 | Hookup Drawing for Magnetic Level Gauge | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5500 | NA | "Hookup Drawing for Magnetic Level Gauge" | 2026-01-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-09 | 76 | PEN | 2026-01-20 | 0 | 001969 | 2026-01-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-09 |  | 0 | PEN | PEN
10965 | 001969 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5501 | 0 | 131242-WST02-DR-I-5501- | 2026-01-20 | Hookup Drawing for Magnetic Level Gauge | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5501 | NA | "GA Drawing for Dosing Pump" && "Hookup Drawing for Magnetic Level Gauge" && "IFC of SSN Electrical Building Transformer Plinth Details " | 2024-07-17 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | 0 | 000573&&000917&&001969 | 2024-07-17, 2024-12-18, 2025-06-15, 2026-01-20 | 00, 01 | 4 | Approved with Comments | AWC | 2026-03-09 |  | 0 | PEN | PEN
10966 | 001970 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5470 | 0 | 131242-WST02-DR-I-5470- | 2026-01-20 | Hookup Drawing for Conductive Probe Level Switch | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5470 | NA | "Hookup Drawing for Conductive Probe Level Switch" | 2026-01-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-09 | 76 | PEN | 2026-01-20 | 0 | 001970 | 2026-01-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-09 |  | 0 | PEN | PEN
10967 | 001970 | 00 | NA | NA | NA | 131242 | WST02 | DR | I | 5471 | 0 | 131242-WST02-DR-I-5471- | 2026-01-20 | Hookup Drawing for Conductive Probe Level Switch | NA | 2026-02-17 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5471 | NA | "GA drawing for Sampling Sink" && "Hookup Drawing for Conductive Probe Level Switch" | 2025-09-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-03 | 76 | PEN | 2026-01-20 | 0 | 001642&&001970 | 2025-09-01, 2026-01-20 | 00 | 2 | Awaiting S.O.'s response | PEN | 2026-03-09 |  | 0 | PEN | PEN
10968 | 001971 | 00 | Kyi Kyi | EICA | NA | 131242 | WST02 | DS | E | 0027 | 0 | 131242-WST02-DS-E-0027-0 | 2026-01-21 | Data Sheet for Lamp Pole | Rev 0: Not approved - Revise and Resubmit. | 2026-02-18 | 2026-02-09 | Not Approved | 2026-02-27 | NO | NA |  | 131242-WST02-DS-0027 | NA | "Data Sheet for Lamp Pole" | 2026-01-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 19 | NAP | 2026-01-21 | 0 | 001971 | 2026-01-21 | 00 | 1 | Not Approved | NAP | 2026-02-27 | Overdue | 0 | NAP | NAP
10969 | 001972 | 00 | NA | NA | NA | 131242 | WSD11 | QA | M | 0171 | 0 | 131242-WSD11-QA-M-0171-0 | 2026-01-21 | FAT Report for G2D Booster Pumps (KSB) | NA | 2026-02-18 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0171 | NA | "FAT Report for G2D Booster Pumps (KSB)" | 2026-01-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-10 | 75 | PEN | 2026-01-21 | 0 | 001972 | 2026-01-21 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-10 |  | 0 | PEN | PEN
10970 | 001973 | 00 | NA | NA | NA | 131242 | WSW41 | QA | M | 0170 | 0 | 131242-WSW41-QA-M-0170-0 | 2026-01-22 | FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch | NA | 2026-02-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0170 | NA | "FAT Report for Stainless Steel Pipes, Fittings, Flanges (Froch Enterprise Co. Ltd & Zhejiang Jndia Pipeline Industry Co., Ltd) 4th Batch" | 2026-01-22 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-11 | 74 | PEN | 2026-01-22 | 0 | 001973 | 2026-01-22 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-11 |  | 0 | PEN | PEN
10971 | 001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5465 | C | 131242-WST02-DR-M-5465-C | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5465 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-05 | 74 | PEN | 2026-01-22 | C | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-11 |  | 0 | PEN | PEN
10972 | 001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5466 | C | 131242-WST02-DR-M-5466-C | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5466 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-05 | 74 | PEN | 2026-01-22 | C | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-11 |  | 0 | PEN | PEN
10973 | 001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5467 | D | 131242-WST02-DR-M-5467-D | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5467 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-08-25 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-05 | 74 | PEN | 2026-01-22 | D | 001619&&001974 | 2025-08-25, 2025-10-18, 2026-01-22 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-11 |  | 0 | PEN | PEN
10974 | 001974 | 00 | Salahudin | Mech | NA | 131242 | WST02 | DR | M | 5468 | D | 131242-WST02-DR-M-5468-D | 2026-01-22 | Splitter Box Structural Supports | NA | 2026-02-19 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-5468 | NA | "GA drawing for Splitter Box" && "Splitter Box Structural Supports" | 2025-10-18 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-05 | 74 | PEN | 2026-01-22 | D | 001619&&001974 | 2025-10-18, 2026-01-22 | 00, 01 | 2 | Awaiting S.O.'s response | PEN | 2026-03-11 |  | 0 | PEN | PEN
10975 | 001975 | 00 | NA | NA | NA | 131242 | WSD11 | DR | S | 1101 | D | 131242-WSD11-DR-S-1101- | 2026-01-26 | WD for ST622 | For Information. Please provide reaction loadings onto existing structures for review. | 2026-02-23 | 2026-02-12 | For Information | 2026-03-04 |  | NA |  | 131242-WSD11-DR-1101 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "ST622_QPD Amendment As built Drawing (Amendment of ST619)" && "THP Earthing Layout Plan" && "THP ICA GA & Wiring drawings" && "WD for ST622 " | 2023-12-12 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-09 | 17 | INF | 2026-01-26 | D | 000236&&000292&&001328&&001944&&001975 | 2023-12-12, 2024-08-13, 2025-03-28, 2025-05-09, 2025-05-28, 2025-11-28, 2026-01-12, 2026-01-26 | 00, 01, 02, 03 | 8 | For Information | INF | 2026-03-04 | Overdue | 0 | INF | INF
10976 | 001976 | 00 | NA | NA | NA | 131242 | WSD11 | QA | I | 0068 | 0 | 131242-WSD11-QA-I-0068-0 | 2026-01-26 | Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-23 | 2026-02-16 | Approved with Comments | 2026-03-06 | NO | NA |  | 131242-WSD11-QA-0068 | NA | "Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP)" | 2026-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-15 | 21 | AWC | 2026-01-26 | 0 | 001976&&001980 | 2026-01-26 | 00 | 2 | Approved with Comments | AWC | 2026-03-06 | Overdue | 0 | AWC | AWC
10977 | 001977 | 00 | NA | NA | NA | 131242 | WSD11 | QA | I | 0069 | 0 | 131242-WSD11-QA-I-0069-0 | 2026-01-26 | Factory Acceptance Test Report for Pressure Gauges (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-23 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-QA-0069 | NA | "FAT report for THP Train 1 (Pulper module, Pulper pump skid & Flash tank pump skid frame, Reactor 1 to 4 module, Upper platform module) Part-2" && "Factory Acceptance Test Report for Pressure Gauges (THP)" | 2025-04-28 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-09 | 29 | AWC | 2026-01-26 | 0 | 001256&&001977 | 2025-04-28, 2025-12-04, 2026-01-26 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10978 | 001978 | 00 | NA | NA | NA | 131242 | WST02 | QA | I | 0070 | 0 | 131242-WST02-QA-I-0070-0 | 2026-01-26 | Factory Acceptance Test Report for Magnetic Level Gauge | NA | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0070 | NA | "Factory Acceptance Test Report for Magnetic Level Gauge" | 2026-01-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-15 | 70 | PEN | 2026-01-26 | 0 | 001978&&001979 | 2026-01-26 | 00 | 2 | Awaiting S.O.'s response | PEN | 2026-03-13 |  | 0 | PEN | PEN
10979 | 001979 | 00 | NA | NA | NA | 131242 | WST02 | QA | I | 0070 | 0 | 131242-WST02-QA-I-0070-0 | 2026-01-26 | Factory Acceptance Test Report for Magnetic Level Gauge | NA | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0070 | NA | "Factory Acceptance Test Report for Magnetic Level Gauge" | 2026-01-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-15 | 70 | PEN | 2026-01-26 | 0 | 001978&&001979 | 2026-01-26 | 00 | 2 | Awaiting S.O.'s response | PEN | 2026-03-13 |  | 0 | PEN | PEN
10980 | 001980 | 00 | NA | NA | NA | 131242 | WSD11 | QA | I | 0068 | 0 | 131242-WSD11-QA-I-0068-0 | 2026-01-26 | Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP) | Rev 0: Approved with comments. To revise and resubmit. Refer attached file for comments. | 2026-02-23 | 2026-02-24 | Approved with Comments | 2026-03-16 | NO | NA |  | 131242-WSD11-QA-0068 | NA | "Vendor Manufacturing Inspection Test Plan for Pressure Gauges (THP)" | 2026-01-26 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-15 | 29 | AWC | 2026-01-26 | 0 | 001976&&001980 | 2026-01-26 | 00 | 2 | Approved with Comments | AWC | 2026-03-16 | Overdue | 0 | AWC | AWC
10981 | 001981 | 00 | NA | NA | NA | 131242 | WST02 | QA | M | 0173 | 0 | 131242-WST02-QA-M-0173-0 | 2026-01-26 | FAT Report for Splitter Box | NA | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0173 | NA | "FAT Report for Splitter Box" | 2026-01-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-15 | 70 | PEN | 2026-01-26 | 0 | 001981 | 2026-01-26 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-13 |  | 0 | PEN | PEN
10982 | 001982 | 00 | NA | NA | NA | 131242 | WSD11 | QA | M | 0172 | 0 | 131242-WSD11-QA-M-0172-0 | 2026-01-26 | FAT Report for G1 Booster Pumps (KSB) | NA | 2026-02-23 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-QA-0172 | NA | "FAT Report for G1 Booster Pumps (KSB)" | 2026-01-26 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-15 | 70 | PEN | 2026-01-26 | 0 | 001982 | 2026-01-26 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-13 |  | 0 | PEN | PEN
10983 | 001983 | 00 | NA | NA | NA | 131242 | WST02 | DS | E | 0028 | 0 | 131242-WST02-DS-E-0028-0 | 2026-01-27 | Data Sheet of Isolator for Motorized Valves | Rev 0: Not approved - Revise and Resubmit | 2026-02-24 | 2026-02-13 | Not Approved | 2026-03-05 | NO | NA |  | 131242-WST02-DS-0028 | NA | "Data Sheet of Isolator for Motorized Valves" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 17 | NAP | 2026-01-27 | 0 | 001983 | 2026-01-27 | 00 | 1 | Not Approved | NAP | 2026-03-05 | Overdue | 0 | NAP | NAP
10984 | 001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3144 | A | 131242-WST02-DR-EP-3144-A | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3144 | NA | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001984 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10985 | 001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3145 | A | 131242-WST02-DR-EP-3145-A | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3145 | NA | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001984 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10986 | 001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7305 | A | 131242-WST02-DR-EP-7305-A | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7305 | NA | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001984 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10987 | 001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7306 | A | 131242-WST02-DR-EP-7306-A | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7306 | NA | "SSN 203-VDB-0002 SLD, Schematic and GA Drawing" && "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2025-10-23 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-02-03 | B | 001772&&001984 | 2025-10-23, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10988 | 001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7307 | A | 131242-WST02-DR-EP-7307-A | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7307 | NA | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001984 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10989 | 001984 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7344 | A | 131242-WST02-DR-EI-7344-A | 2026-01-27 | SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7344 | NA | "SSN UPSDB-0005A SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001984 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10990 | 001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3138 | A | 131242-WST02-DR-EP-3138-A | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3138 | NA | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001985 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10991 | 001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3139 | A | 131242-WST02-DR-EP-3139-A | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3139 | NA | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001985 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10992 | 001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7300 | A | 131242-WST02-DR-EP-7300-A | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7300 | NA | "SSN 400-VDB-0001 SLD, Schematic and GA Drawing (GSM)" && "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-02-03 | B | 001806&&001985 | 2025-10-31, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10993 | 001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7301 | A | 131242-WST02-DR-EP-7301-A | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7301 | NA | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001985 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10994 | 001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7302 | A | 131242-WST02-DR-EP-7302-A | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7302 | NA | "SSN 400-VDB-0002 SLD, Schematic and GA Drawing (GSM)" && "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2025-10-31 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 69 | PEN | 2026-02-03 | B | 001807&&001985 | 2025-10-31, 2026-01-27, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
10995 | 001985 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7338 | A | 131242-WST02-DR-EI-7338-A | 2026-01-27 | SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7338 | NA | "SSN UPSDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001985 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10996 | 001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3136 | A | 131242-WST02-DR-EP-3136-A | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3136 | NA | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001986 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10997 | 001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 3137 | A | 131242-WST02-DR-EP-3137-A | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3137 | NA | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001986 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10998 | 001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7295 | A | 131242-WST02-DR-EP-7295-A | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7295 | NA | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001986 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
10999 | 001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7296 | A | 131242-WST02-DR-EP-7296-A | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7296 | NA | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001986 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
11000 | 001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EP | 7297 | A | 131242-WST02-DR-EP-7297-A | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7297 | NA | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001986 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
11001 | 001986 | 00 | Freedomer | EICA | NA | 131242 | WST02 | DR | EI | 7336 | A | 131242-WST02-DR-EI-7336-A | 2026-01-27 | SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7336 | NA | "SSN UPSDB-0003B SLD, Schematic and GA Drawing (GSM)" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | A | 001986 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
11002 | 001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3111 | A | 131242-WSD11-DR-EP-3111-A | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3111 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001987 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11003 | 001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3310 | A | 131242-WSD11-DR-EP-3310-A | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3310 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001987 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11004 | 001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7225 | A | 131242-WSD11-DR-EP-7225-A | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7225 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001987 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11005 | 001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7226 | A | 131242-WSD11-DR-EP-7226-A | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7226 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001987 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11006 | 001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7227 | A | 131242-WSD11-DR-EP-7227-A | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7227 | NA | "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001987 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11007 | 001987 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7310 | A | 131242-WSD11-DR-EI-7310-A | 2026-01-27 | THP UPSDB-0105B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7310 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0105B SLD, Schematic and GA Drawing" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | A | 000392&&001987 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11008 | 001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3113 | A | 131242-WSD11-DR-EP-3113-A | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3113 | NA | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001988 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11009 | 001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 3312 | A | 131242-WSD11-DR-EP-3312-A | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-3312 | NA | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001988 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11010 | 001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7230 | A | 131242-WSD11-DR-EP-7230-A | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7230 | NA | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001988 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11011 | 001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7231 | A | 131242-WSD11-DR-EP-7231-A | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7231 | NA | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001988 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11012 | 001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EP | 7232 | A | 131242-WSD11-DR-EP-7232-A | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7232 | NA | "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2026-01-27 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-16 | 30 | AWC | 2026-01-27 | A | 001988 | 2026-01-27 | 00 | 1 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11013 | 001988 | 00 | Freedomer | EICA | NA | 131242 | WSD11 | DR | EI | 7312 | A | 131242-WSD11-DR-EI-7312-A | 2026-01-27 | THP UPSDB-0106B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-02-24 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WSD11-DR-7312 | NA | "Compressor Sequencer Panel" && "THP UPSDB-0106B SLD, Schematic and GA Drawing" | 2024-03-25 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-10 | 30 | AWC | 2026-01-27 | A | 000392&&001988 | 2024-03-25, 2024-06-26, 2025-01-15, 2025-06-16, 2026-01-27 | 00, 01, 03, 04 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11014 | 001989 | 00 | Soe Myat | QAQC | NA | 131242 | WST02 | QA | M | 0174 | 0 | 131242-WST02-QA-M-0174-0 | 2026-01-27 | Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0174 | NA | "Splitter Box manufacturer’s WPS/PQR/WQT, Test procedures" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | 0 | 001989 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
11015 | 001990 | 00 | Mohan | QAQC | NA | 131242 | WST02 | QA | M | 0169 | 0 | 131242-WST02-QA-M-0169-0 | 2026-01-27 | Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box | NA | 2026-02-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0169 | NA | "Vendor Manufacturing Inspection Test Plan and Test Procedure for Splitter Box" | 2026-01-27 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-16 | 69 | PEN | 2026-01-27 | 0 | 001990 | 2026-01-27 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-16 |  | 0 | PEN | PEN
11016 | 001991 | 00 | NA | NA | NA | 131242 | WSD11 | DS | M | 0048 | 0 | 131242-WSD11-DS-M-0048-0 | 2026-01-28 | Steam Trap Data Sheet | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0048 | NA | "Steam Trap Data Sheet" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | 0 | 001991 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11017 | 001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3146 | A | 131242-WST02-DR-EP-3146-A | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3146 | NA | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001992 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11018 | 001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3147 | A | 131242-WST02-DR-EP-3147-A | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3147 | NA | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001992 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11019 | 001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7310 | A | 131242-WST02-DR-EP-7310-A | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7310 | NA | "SSN 201-VDB-0002 SLD, Schematic and GA Drawing" && "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-03 | B | 001769&&001992 | 2025-10-22, 2026-01-28, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC |  |  | 0 | PEN | PEN
11020 | 001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7311 | A | 131242-WST02-DR-EP-7311-A | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7311 | NA | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001992 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11021 | 001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7312 | A | 131242-WST02-DR-EP-7312-A | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7312 | NA | "SSN 201-VDB-0001A SLD, Schematic and GA Drawing" && "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2025-10-22 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-11 | 68 | PEN | 2026-02-03 | B | 001762&&001992 | 2025-10-22, 2026-01-28, 2026-02-03 | 00, 01 | 3 | Not Approved | NAP |  |  | 0 | PEN | PEN
11022 | 001992 | 00 | NA | NA | NA | 131242 | WST02 | DR | EI | 7346 | A | 131242-WST02-DR-EI-7346-A | 2026-01-28 | SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7346 | NA | "SSN UPSDB-0006B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001992 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11023 | 001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3132 | A | 131242-WST02-DR-EP-3132-A | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3132 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001993 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11024 | 001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3133 | A | 131242-WST02-DR-EP-3133-A | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3133 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001993 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11025 | 001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7285 | A | 131242-WST02-DR-EP-7285-A | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7285 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001993 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11026 | 001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7286 | A | 131242-WST02-DR-EP-7286-A | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7286 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001993 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11027 | 001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7287 | A | 131242-WST02-DR-EP-7287-A | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7287 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001993 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11028 | 001993 | 00 | NA | NA | NA | 131242 | WST02 | DR | EI | 7332 | A | 131242-WST02-DR-EI-7332-A | 2026-01-28 | SSN UPSDB-0101B SLD, Schematic and GA Drawing | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7332 | NA | "SSN UPSDB-0101B SLD, Schematic and GA Drawing" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001993 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11029 | 001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3134 | A | 131242-WST02-DR-EP-3134-A | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3134 | NA | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001994 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11030 | 001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 3135 | A | 131242-WST02-DR-EP-3135-A | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3135 | NA | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001994 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11031 | 001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7290 | A | 131242-WST02-DR-EP-7290-A | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7290 | NA | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001994 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11032 | 001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7291 | A | 131242-WST02-DR-EP-7291-A | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7291 | NA | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001994 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11033 | 001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EP | 7292 | A | 131242-WST02-DR-EP-7292-A | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7292 | NA | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001994 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11034 | 001994 | 00 | NA | NA | NA | 131242 | WST02 | DR | EI | 7334 | A | 131242-WST02-DR-EI-7334-A | 2026-01-28 | SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM) | NA | 2026-02-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7334 | NA | "SSN UPSDB-0102B SLD, Schematic and GA Drawing (GSM)" | 2026-01-28 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-17 | 68 | PEN | 2026-01-28 | A | 001994 | 2026-01-28 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-17 |  | 0 | PEN | PEN
11035 | 001995 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0015 | 0 | 131242-WSD11-DS-I-0015-0 | 2026-01-29 | Datasheet for Pressure Switch (THP-BOP) | NA | 2026-02-26 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0015 | NA | "Data Sheet of Flash Tank Discharge Pump " && "Datasheet for Pressure Switch (THP-BOP)" && "THP Pump Motor Data Sheet" | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-12 | 67 | PEN | 2026-01-29 | 0 | 000634&&000635&&001995 | 2024-08-12, 2024-11-13, 2026-01-29 | 00, 01 | 4 | Approved | APP |  |  | 0 | PEN | PEN
11036 | 001996 | 00 | NA | NA | NA | 131242 | WSW41 | QA | I | 0071 | 0 | 131242-WSW41-QA-I-0071-0 | 2026-01-30 | FAT Report for FFOTP Panel SSN & THP (FOX) | NA | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0071 | NA | "FAT Report for FFOTP Panel SSN & THP (FOX)" | 2026-01-30 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-19 | 66 | PEN | 2026-01-30 | 0 | 001996 | 2026-01-30 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-19 |  | 0 | PEN | PEN
11037 | 001997 | 00 | NA | NA | NA | 131242 | WSW41 | QA | I | 0072 | 0 | 131242-WSW41-QA-I-0072-0 | 2026-01-30 | FAT Report for FOIP Panel SSN & THP (FOX) | NA | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0072 | NA | "FAT Report for FOIP Panel SSN & THP (FOX)" && "Vendor Manufacturing Inspection Test Plan for Parabolic Screen" | 2025-06-04 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-13 | 66 | PEN | 2026-01-30 | 0 | 001344&&001997 | 2025-06-04, 2026-01-30 | 00 | 2 | Approved with Comments | AWC | 2026-03-19 |  | 0 | PEN | PEN
11038 | 001998 | 00 | NA | NA | NA | 131242 | WST02 | QA | I | 0073 | 0 | 131242-WST02-QA-I-0073-0 | 2026-01-30 | FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN | NA | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0073 | NA | "FAT Procedure for PLC & RIO Panels (MATTENPLANT) SSN" && "FAT report for SSN Anammox Reactor/Biomass Separator (Matten Plant)" | 2025-04-29 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-13 | 66 | PEN | 2026-01-30 | 0 | 001258&&001998 | 2025-04-29, 2026-01-30 | 00 | 2 | Approved with Comments | AWC | 2026-03-19 |  | 0 | PEN | PEN
11039 | 001999 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0016 | 0 | 131242-WSD11-DS-I-0016-0 | 2026-01-30 | Datasheet for Pressure Transmitter (THP-BOP) | NA | 2026-02-27 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0016 | NA | "Data Sheet of Precooler S2 CIRC Pump" && "Datasheet for Pressure Transmitter (THP-BOP) " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-13 | 66 | PEN | 2026-01-30 | 0 | 000636&&001999 | 2024-08-12, 2024-11-13, 2026-01-30 | 00, 01 | 3 | Approved | APP |  |  | 0 | PEN | PEN
11040 | 002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3011 | A | 131242-WSD11-DR-BE-3011-A | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3011 | NA | "Milestone 2 THP EICA Silo Area inside Biosolid Building" && "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP EICA Silo Area inside Biosolid Building" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP SLD" && "THP WAP FFOTP_GA & Wiring Diagram" | 2024-10-01 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000291&&000292&&000570&&001230&&001328&&002000 | 2024-10-01, 2024-10-03, 2024-11-21, 2024-12-10, 2025-01-22, 2025-03-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-08-22, 2025-10-23, 2025-10-28, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 15 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11041 | 002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3015 | A | 131242-WSD11-DR-BE-3015-A | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3015 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 001027&&001230&&001328&&002000 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11042 | 002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7020 | A | 131242-WSD11-DR-BE-7020-A | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7020 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11043 | 002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7021 | A | 131242-WSD11-DR-BE-7021-A | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7021 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11044 | 002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7022 | A | 131242-WSD11-DR-BE-7022-A | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7022 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11045 | 002000 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7023 | A | 131242-WSD11-DR-BE-7023-A | 2026-02-03 | THP LDB-0001B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7023 | NA | "THP LDB-0001B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002000 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11046 | 002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3016 | A | 131242-WSD11-DR-BE-3016-A | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3016 | NA | "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2026-02-03 | 00, 01, 02 | 8 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11047 | 002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 3020 | A | 131242-WSD11-DR-BE-3020-A | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-3020 | NA | "Milestone 2 THP Overall & Equipment Layout" && "Milestone 3 THP Overall & Equipment Layout" && "THP ICA GA & Wiring drawings" && "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP WAP FFOTP_GA & Wiring Diagram" && "THP-MCC-0001AB MCC Drawings" | 2025-02-07 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000292&&001027&&001230&&001328&&002001 | 2025-02-07, 2025-04-16, 2025-05-09, 2025-05-28, 2025-05-30, 2025-08-05, 2025-08-22, 2025-11-11, 2025-11-28, 2026-02-03 | 00, 01, 02, 03 | 10 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11048 | 002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7025 | A | 131242-WSD11-DR-BE-7025-A | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7025 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11049 | 002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7026 | A | 131242-WSD11-DR-BE-7026-A | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7026 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11050 | 002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7027 | A | 131242-WSD11-DR-BE-7027-A | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7027 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP MCC Schematic Diagram" && "THP SLD" | 2024-07-16 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&000571&&002001 | 2024-07-16, 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 7 | Approved | APP |  |  | 0 | PEN | PEN
11051 | 002001 | 00 | NA | NA | NA | 131242 | WSD11 | DR | BE | 7028 | A | 131242-WSD11-DR-BE-7028-A | 2026-02-03 | THP LDB-0002B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DR-7028 | NA | "THP LDB-0002B SLD, Schematic and GA Drawing" && "THP SLD" | 2024-10-01 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000570&&002001 | 2024-10-01, 2024-10-03, 2024-11-21, 2025-03-07, 2025-10-23, 2026-02-03 | 00, 01, 02, 03, 04, 05 | 6 | Approved | APP |  |  | 0 | PEN | PEN
11052 | 002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3041 | A | 131242-WST02-DR-BE-3041-A | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3041 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11053 | 002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3045 | A | 131242-WST02-DR-BE-3045-A | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3045 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000867&&002002 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11054 | 002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7050 | A | 131242-WST02-DR-BE-7050-A | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7050 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11055 | 002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7051 | A | 131242-WST02-DR-BE-7051-A | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7051 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11056 | 002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7052 | A | 131242-WST02-DR-BE-7052-A | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7052 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11057 | 002002 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7053 | A | 131242-WST02-DR-BE-7053-A | 2026-02-03 | SSN LDB-0001B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7053 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0001B SLD, Schematic and GA Drawing " | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002002 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11058 | 002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3046 | A | 131242-WST02-DR-BE-3046-A | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3046 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11059 | 002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3050 | A | 131242-WST02-DR-BE-3050-A | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3050 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000867&&002003 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11060 | 002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7055 | A | 131242-WST02-DR-BE-7055-A | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7055 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002003 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11061 | 002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7056 | A | 131242-WST02-DR-BE-7056-A | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7056 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11062 | 002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7057 | A | 131242-WST02-DR-BE-7057-A | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7057 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11063 | 002003 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7058 | A | 131242-WST02-DR-BE-7058-A | 2026-02-03 | SSN LDB-0002B SLD, Schematic and GA Drawing | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7058 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0002B SLD, Schematic and GA Drawing" | 2025-03-07 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002003 | 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 4 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11064 | 002004 | 00 | NA | NA | NA | 131242 | NA | NA | NA | 9999 | A | 131242----- | 2026-02-03 | Unpriced PO for Magnetic Level Gauge (Pipeline Process) | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-NA-NA-9999 | NA | "As Built Drawing for ST619 (THP Cooler Platform)" && "Commissioning Plan for EQ Tank and Lamella Clarifier" && "FAT Report for RIO Panels SSN-WST02-RIO-0204, SSN-WST02-RIO-0205, SSN-WST02-RIO-0206, SSN-WST02-RIO-0207, SSN-WST02-RIO-0208 (FOX)" && "Notice and Request for Certificate of Substantial Completion for Phase “Compressed Air System, To Provide Air Supply To C4A”" && "Shop As Built Drawing for ST 614 (SWPR PR 03) (PE Endorsed)" && "Shop As Built Drawing for ST 621 (SWPR PR 01 & 02) (PE Endorsed)" && "THP ICA GA & Wiring Drawings" && "Testing Check List (Process)" && "Unpriced PO for Magnetic Level Gauge (Pipeline Process)" | 2025-05-30 | NO | PEN | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 001330&&001636&&001637&&001890&&001892&&001905&&001964&&001965&&002004 | 2025-05-30, 2025-08-29, 2025-12-09, 2025-12-12, 2025-12-17, 2026-01-19, 2026-02-03 | 00 | 9 | Rejected | REJ | 2026-03-23 |  | 0 | PEN | PEN
11065 | 002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3051 | A | 131242-WST02-DR-BE-3051-A | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3051 | NA | "GA, Schematic Diagram and SLD for WST02-MCC-1001 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000867&&002005 | 2024-12-02, 2025-03-28, 2026-02-03 | 00, 01, 02 | 4 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11066 | 002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3055 | A | 131242-WST02-DR-BE-3055-A | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3055 | NA | "SSN MDB-1001A.B SLD, Schem and GA Drawings" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2025-03-21 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 001140&&002005 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11067 | 002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7060 | A | 131242-WST02-DR-BE-7060-A | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7060 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11068 | 002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7061 | A | 131242-WST02-DR-BE-7061-A | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7061 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11069 | 002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7062 | A | 131242-WST02-DR-BE-7062-A | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7062 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11070 | 002005 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7063 | A | 131242-WST02-DR-BE-7063-A | 2026-02-03 | SSN SDB-0003B SLD, Schematic and GA Drawing | NA | 2026-03-03 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-7063 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN SDB-0003B SLD, Schematic and GA Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 62 | PEN | 2026-02-03 | A | 000866&&002005 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-23 |  | 0 | PEN | PEN
11071 | 002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3056 | A | 131242-WST02-DR-BE-3056-A | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3056 | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 001140&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11072 | 002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 3060 | A | 131242-WST02-DR-BE-3060-A | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-3060 | NA | "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" && "SSN MDB-1001A.B SLD, Schem and GA Drawings" | 2025-03-21 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 001140&&002006 | 2025-03-21, 2025-07-21, 2026-02-03 | 00, 01 | 3 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11073 | 002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7065 | A | 131242-WST02-DR-BE-7065-A | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7065 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11074 | 002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7066 | A | 131242-WST02-DR-BE-7066-A | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7066 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11075 | 002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7067 | A | 131242-WST02-DR-BE-7067-A | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7067 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11076 | 002006 | 00 | NA | NA | NA | 131242 | WST02 | DR | BE | 7068 | A | 131242-WST02-DR-BE-7068-A | 2026-02-03 | SSN LDB-0004B SLD, Schematic and GA Drawing (GSM) | Rev 0: Approved with Comments. To revise and resubmit. Refer to attached file for comments. | 2026-03-03 | 2026-02-26 | Approved with Comments | 2026-03-18 | NO | NA |  | 131242-WST02-DR-7068 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "SSN LDB-0004B SLD, Schematic and GA Drawing (GSM)" | 2024-12-02 | NO | YES | Project_Code not in project_schema; Department not in department_schema | 2026-02-17 | 23 | AWC | 2026-02-03 | A | 000866&&002006 | 2024-12-02, 2025-03-07, 2025-03-28, 2025-07-01, 2026-02-03 | 00, 01, 02, 03 | 5 | Approved with Comments | AWC | 2026-03-18 | Overdue | 0 | AWC | AWC
11077 | 002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3020 | A | 131242-WST02-DR-A-3020-A | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3020 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0004 SLD, Schematic and GA Drawing (GSM)" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | A | 000164&&000866&&001165&&001808&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 12 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
11078 | 002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3021 | A | 131242-WST02-DR-A-3021-A | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3021 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN LDB-0005 SLD, Schematic and GA Drawing (GSM)" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | A | 000164&&000866&&001165&&001809&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-03, 2026-02-04 | 00, 01, 02, 03 | 11 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
11079 | 002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3022 | A | 131242-WST02-DR-A-3022-A | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3022 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
11080 | 002007 | 00 | NA | NA | NA | 131242 | WST02 | DR | A | 3023 | A | 131242-WST02-DR-A-3023-A | 2026-02-04 | Staircase 1 Block Wall Shop Drawing | NA | 2026-03-04 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-3023 | NA | "GA, Schematic Diagrame and SLD for WST02-MCC-0101 A/B" && "Milestone 2 SSN Pump Station and Lamella Clarifier" && "Milestone 3 SSN Pump Station and Lamella Clarifier" && "SSN Panel(FIOP,FFOTP)- GA &Wiring drawings" && "Staircase 1 Block Wall Shop Drawing" | 2024-12-02 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-18 | 61 | PEN | 2026-02-04 | A | 000164&&000866&&001165&&002007 | 2024-12-02, 2025-03-07, 2025-03-25, 2025-03-28, 2025-04-22, 2025-07-01, 2025-08-22, 2025-10-31, 2026-02-04 | 00, 01, 02, 03 | 9 | Approved with Comments | AWC | 2026-03-24 |  | 0 | PEN | PEN
11081 | 002008 | 00 | NA | NA | NA | 131242 | WSW41 | QA | M | 9999 | A | 131242-WSW41-QA-M-- | 2026-02-06 | Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve | NA | 2026-03-06 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-9999 | NA | "Vendor Manufacturing Inspection Test Plan and Hydro Test Procedure for Gestra Disco check valve and Resilient seat swing valve " | 2026-02-06 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-26 | 59 | PEN | 2026-02-06 | A | 002008 | 2026-02-06 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-26 |  | 0 | PEN | PEN
11082 | 002009 | 00 | NA | NA | NA | 131242 | WSW41 | CD | IM | 9999 | A | 131242-WSW41-CD-IM-- | 2026-02-09 | VCM Submission for 2026-01 | NA | 2026-03-09 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-CD-9999 | NA | " VCM Submission for 2025-11" && "VCM Model Submission" && "VCM Submission for 2025-12" && "VCM Submission for 2026-01" | 2024-12-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-02-23 | 56 | PEN | 2026-02-09 | A | 000879&&001888&&001941&&002009 | 2024-12-09, 2025-12-08, 2026-01-08, 2026-02-09 | 00 | 4 | For Information | INF | 2026-03-27 |  | 0 | PEN | PEN
11083 | 002010 | 00 | NA | NA | NA | 131242 | WSW41 | QA | M | 0176 | 0 | 131242-WSW41-QA-M-0176-0 | 2026-02-10 | FAT Report for SS316L Pipe (CWP 323) 117 Nos | NA | 2026-03-10 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-QA-0176 | NA | "FAT Report for SS316L Pipe (CWP 323) 117 Nos" | 2026-02-10 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-02 | 55 | PEN | 2026-02-10 | 0 | 002010 | 2026-02-10 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-03-30 |  | 0 | PEN | PEN
11084 | 002011 | 00 | Yihao | Contracts | NA | 131242 | WSW41 | PC | W | 0031 | 0 | 131242-WSW41-PC-W-0031-0 | 2026-02-11 | Payment Claim No.31 | Rev (0): Approved. Please refer to S.O. correspondence no. 433 dated 10 Feb 2026. | 2026-03-11 | 2026-02-24 | Approved |  | YES | NA |  | 131242-WSW41-PC-0031 | NA | "Payment Claim No.31" | 2026-02-11 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-03-03 | 13 | APP | 2026-02-11 | 0 | 002011 | 2026-02-11 | 00 | 1 | Approved | APP |  |  | 0 | APP | APP
11085 | 002012 | 00 | NA | NA | NA | 131242 | WSW41 | LT | PM | 0081 | 0 | 131242-WSW41-LT-PM-0081-0 | 2026-02-11 | Purchase Of Spare Parts Under SOP 10 | NA | 2026-03-11 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0081 | NA | "CV of Team Member (MEM)" && "Purchase Of Spare Parts Under SOP 10" | 2026-01-14 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-02-25 | 54 | PEN | 2026-02-11 | 0 | 001953&&002012 | 2026-01-14, 2026-02-11 | 00 | 2 | Awaiting S.O.'s response | PEN | 2026-03-31 |  | 0 | PEN | PEN
11086 | 002013 | 00 | NA | NA | NA | 131242 | WSW41 | LT | PM | 0082 | 0 | 131242-WSW41-LT-PM-0082-0 | 2026-02-12 | Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards | NA | 2026-03-12 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0082 | NA | "Notice for Extension of Time and Cost for Shipment Delay of Power Distribution Boards " | 2026-02-12 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-04 | 53 | PEN | 2026-02-12 | 0 | 002013 | 2026-02-12 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-04-01 |  | 0 | PEN | PEN
11087 | 002014 | 00 | NA | NA | NA | 131242 | WSW41 | RT | PM | 0033 | 0 | 131242-WSW41-RT-PM-0033-0 | 2026-02-20 | C4B Monthly Progress Report Number No.33 (01 26) | NA | 2026-03-20 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-RT-0033 | NA | "C4B Monthly Progress Report Number No.33 (01 26)" | 2026-02-20 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-12 | 45 | PEN | 2026-02-20 | 0 | 002014 | 2026-02-20 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-04-09 |  | 0 | PEN | PEN
11088 | 002015 | 00 | NA | NA | NA | 131242 | WST02 | QA | M | 0177 | 0 | 131242-WST02-QA-M-0177-0 | 2026-02-24 | ITP and Test Procedure for Chemical Dosing Cabinets | NA | 2026-03-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0177 | NA | "ITP and Test Procedure for Chemical Dosing Cabinets" | 2026-02-24 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-16 | 41 | PEN | 2026-02-24 | 0 | 002015 | 2026-02-24 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-04-13 |  | 0 | PEN | PEN
11089 | 002016 | 00 | NA | NA | NA | 131242 | WSW41 | CN | S | 0003 | 0 | 131242-WSW41-CN-S-0003-0 | 2026-02-24 | RFC for Electrical Building Chequer Plate | NA | 2026-03-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-CN-0003 | NA | "RFC for Electrical Building Chequer Plate" | 2026-02-24 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-16 | 41 | PEN | 2026-02-24 | 0 | 002016 | 2026-02-24 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-04-13 |  | 0 | PEN | PEN
11090 | 002017 | 00 | NA | NA | NA | 131242 | WST02 | QA | M | 0178 | 0 | 131242-WST02-QA-M-0178-0 | 2026-02-24 | FAT Report for Chemical Dosing Cabinets | NA | 2026-03-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0178 | NA | "FAT Report for Chemical Dosing Cabinets " | 2026-02-24 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-16 | 41 | PEN | 2026-02-24 | 0 | 002017 | 2026-02-24 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-04-13 |  | 0 | PEN | PEN
11091 | 002018 | 00 | NA | NA | NA | 131242 | WST02 | DR | C | 1025 | A | 131242-WST02-DR-C-1025-A | 2026-02-24 | C4B SSN Drain Hydraulic Calculation | NA | 2026-03-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-DR-1025 | NA | "ACMV LCP GA & Wiring Drawing" && "BMS Panel GA & Wiring Drawing " && "C4B SSN Drain Hydraulic Calculation" && "Piping General Arrangement-UG & Plant Drain Manholes" && "SSN - Tank pipe support Anchor bolts embedment design drill depths" && "SSN Panel (ECCP-1001)- GA & Wiring Drawings" && "SSN Pavement Plan" && "SSN Piping Support Plan Layout (Cast-In Supports)" | 2024-04-09 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | A | 000429&&000778&&000835&&001176&&001402&&001793&&001914&&002018 | 2024-04-09, 2024-10-26, 2024-11-22, 2025-03-28, 2025-07-11, 2025-11-17, 2025-11-21, 2025-12-18, 2026-01-28, 2026-02-04, 2026-02-24 | 00, 01, 02, 03 | 11 | Not Approved | NAP | 2026-04-13 |  | 0 | PEN | PEN
11092 | 002018 | 00 | NA | NA | NA | 131242 | WST02 | CL | C | 1000 | 0 | 131242-WST02-CL-C-1000-0 | 2026-02-24 | C4B SSN Drain Hydraulic Calculation | NA | 2026-03-24 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-CL-1000 | NA | "C4B SSN Drain Hydraulic Calculation" && "SSN Underground Piping Stress Calculation Report" | 2024-07-31 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-10 | 41 | PEN | 2026-02-24 | 0 | 000603&&002018 | 2024-07-31, 2026-02-24 | 00 | 2 | Approved with Comments | AWC | 2026-04-13 |  | 0 | PEN | PEN
11093 | 002019 | 00 | NA | NA | NA | 131242 | WST02 | QA | E | 0068 | 0 | 131242-WST02-QA-E-0068-0 | 2026-02-25 | SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) | NA | 2026-03-25 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WST02-QA-0068 | NA | "FAT Report for SSN Tanks SS Cast in Pipes (Cyclect-5th Batch) " && "SAT Procedure for Aeration Blower ABCDE Harmonic Filter Panel (Danfoss) " | 2025-04-03 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-03-11 | 40 | PEN | 2026-02-25 | 0 | 001199&&002019 | 2025-04-03, 2026-02-25 | 00 | 2 | Approved | APP |  |  | 0 | PEN | PEN
11094 | 002020 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0017 | 0 | 131242-WSD11-DS-I-0017-0 | 2026-03-02 | Datasheet for Temperature Sensor (THP-BOP) | NA | 2026-03-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0017 | NA | "Data Sheet of Digester Feed Pump" && "Datasheet for Temperature Sensor (THP-BOP) " | 2024-08-12 | YES | NO | Project_Code not in project_schema; Department not in department_schema | 2026-03-16 | 35 | PEN | 2026-03-02 | 0 | 000637&&002020 | 2024-08-12, 2025-03-04, 2026-03-02 | 00, 01 | 3 | Approved | APP |  |  | 0 | PEN | PEN
11095 | 002021 | 00 | NA | NA | NA | 131242 | WSD11 | DS | I | 0018 | 0 | 131242-WSD11-DS-I-0018-0 | 2026-03-02 | Datasheet for Differential Pressure Flowmeter (THP-BOP) | NA | 2026-03-30 |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSD11-DS-0018 | NA | "Data Sheet for Pre Cooler Cooling Water Control Valve" && "Datasheet for Differential Pressure Flowmeter (THP-BOP) " | 2024-09-03 | NO | PEN | Project_Code not in project_schema; Department not in department_schema | 2026-03-16 | 35 | PEN | 2026-03-02 | 0 | 000697&&002021 | 2024-09-03, 2025-05-05, 2026-03-02 | 00, 01 | 3 | Approved with Comments | AWC | 2026-04-17 |  | 0 | PEN | PEN
11096 | 002022 | 00 | NA | NA | NA | NA | NA | NA | NA | 9999 | 0 |  |  | NA | NA |  |  | Awaiting S.O.'s response |  |  | NA |  | NA-NA-NA-9999 | NA | "NA" && "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | 2025-07-01 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Submission_Date cannot be null |  |  | PEN | 2025-07-01 | 1 | 001418&&002022&&002023&&002024 | 2025-07-01 | 00 | 4 | Not Approved | NAP |  |  | 0 | PEN | PEN
11097 | 002023 | 00 | NA | NA | NA | NA | NA | NA | NA | 9999 | 0 |  |  | NA | NA |  |  | Awaiting S.O.'s response |  |  | NA |  | NA-NA-NA-9999 | NA | "NA" && "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | 2025-07-01 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Submission_Date cannot be null |  |  | PEN | 2025-07-01 | 1 | 001418&&002022&&002023&&002024 | 2025-07-01 | 00 | 4 | Not Approved | NAP |  |  | 0 | PEN | PEN
11098 | 002024 | 00 | NA | NA | NA | NA | NA | NA | NA | 9999 | 0 |  |  | NA | NA |  |  | Awaiting S.O.'s response |  |  | NA |  | NA-NA-NA-9999 | NA | "NA" && "Reinstatement of SSN Water Tank Opening Reinstatement for PE endorsement" | 2025-07-01 | NO | YES | Project_Code not in project_schema; Facility_Code not in facility_schema; Document_Type not in document_type_schema; Discipline not in discipline_schema; Document_ID does not start with valid code from project_schema; Department not in department_schema; Submission_Date cannot be null |  |  | PEN | 2025-07-01 | 1 | 001418&&002022&&002023&&002024 | 2025-07-01 | 00 | 4 | Not Approved | NAP |  |  | 0 | PEN | PEN
11099 | 002025 | 00 | Mabele | Contracts | NA | 131242 | WSW41 | LT | PM | 0083 | 0 | 131242-WSW41-LT-PM-0083-0 | 2026-03-05 | Notice For Extension Of Time And Cost For Delays For Power Turn On | NA |  |  | Awaiting S.O.'s response |  |  | NA |  | 131242-WSW41-LT-0083 | NA | "Notice For Extension Of Time And Cost For Delays For Power Turn On " | 2026-03-05 | NO | PEN | Project_Code not in project_schema; Department not in department_schema; Latest_Approval_Status not in approval_code_schema | 2026-03-25 | 32 | PEN | 2026-03-05 | 0 | 002025 | 2026-03-05 | 00 | 1 | Awaiting S.O.'s response | PEN | 2026-04-22 |  | 0 | PEN | PEN